## Slide 1: DHET Certification Backlog Reduction Status
23 March 2022

## Slide 2: Content
Objectives
SITA’s Role in the Certification Value Chain
Resulting and Certification Process
Backlog Day Zero target timeline (previous commitment)
Progress and status of the certification backlog statistics
Key interventions planned to be undertaken over next report period
Key application changes & interventions undertaken
Conclusion

## Slide 3: Objectives
Overview
Provide an overview of SITA’s role in the resulting and certification value chain
Feedback
Provide feedback on previous commitments made by SITA
Progress Update
Provide a progress update on the certification backlog against the baseline agreed upon

## Slide 4: Stakeholder Roles and Responsibilities
DHET | SITA | Umalusi
Provide business rules Make business decisions Capture outstanding marks (raw marks) Provide Portfolio of Evidence for raw mark changes Address outstanding Irregularities Execute system functionality for resulting and certification Submit datasets to Umalusi for all qualifications Analyse and resolve candidate records not approved by Umalusi Quality assure candidate records: NATED Resulting N1, N4 to N6 NATED Certification N1, N2, N4 to N6 Develop and execute communication strategy | Provide system functionality to meet business requirements Align data (excluding raw marks) Support DHET to execute system functionality for resulting and certification Submit datasets to Umalusi Analyse and resolve candidate records not approved by Umalusi Develop / update and execute programs for reporting and resolution purposes | Quality assure candidate records: GETC Resulting and Certification NC (V) Resulting and Certification L2 to L4 NATED Resulting N2&N3 and Certification N3 Approve / not approve and provide return datasets - including reasons for non-approval where required (5 day turnaround time)

## Slide 5: Resulting and Certification Process
Exam Cycle & Course/ Subject Structures
Candidate Registration
Historical Norms
Standardi-sation
Statistical Moderation & Resulting
Main Exam
Supplementary Exam (NCV)
Resulting
Mop-up (201711 onwards) (Repeat)
Mop-up (201711 onwards (Repeat)
Re-Mark/Re-Check
Re-Mark/Re-Check
Certification
First Issue
Consolidation/ Combination (Repeat)
Full/ Combined Certification
Main & Suppl Consolidation
Certification
First Issue
Consolidation (Repeat)
Full/
Combined Certification
Centre Registration/ Maintenance
Exam Material/ Packing
SBA Assessments/ Written Exams
Re-Issues/ Replacements
Written Exam
Data Quality Assurance
Business & System Processes
Notes: Historical Norms: Average for the written component based on the previous 5/6 examinations depending on the qualification used to compare the current examinations performance against the norm during the standardisation process
Standardisation: Done on a national level per subject. 95% of the written marks must be captured to continue with standardization. A computer adjustment is calculated and the Standardisation Committee will determine the external adjustment that must be applied
Statistical Moderation & Resulting: Done on a centre, subject and attendance type level where the SBA/practical component is compared. 80% of the combination of the written and SBA marks must be captured (subjects with <=14 candidates have sliding scale). SBA and/or Final adjustment is determined and the final subject result as well as candidate overall result is determined
Re-Mark/Re-Check: Candidates can apply for their scripts to be re-marked/re-checked if they suspect that their result are not correct. Re-mark/re-check must be completed prior to certification
Mop-up: Process that was introduced from 201711 where candidates who had outstanding marks which were since captured, or where marks were incorrectly captured could be submitted to Umalusi for quality assurance to be approved before certification can be done.
First Issue Certificate: Certificate (full or subject certificate) that is issued for subjects offer in one exam sitting
Full/Combined Certificate: Certificate that is issued where the qualification was achieved over multiple exam sittings and previous subject certificates were issued

## Slide 6: Backlog Day Zero target timeline (Previously presented)
Long Term
Medium Term
Short Term
Feb
2020
Mar
2020
Apr
2020
May
2020
Jun
2020
Jul
2020
Aug
2020
Sep
2020
Oct
2020
Nov
2020
Dec
2020
Jan
2021
Feb
2021
Mar
2021
Apr
2021
NATED
Engineering Studies
NATED
Business Studies
NCV Full
GETC
NATED
Engineering Studies
NATED
Business Studies
GETC
80% Reduction of Backlog as Communicated on 18 February 2020
95% Reduction of Backlog as Communicated on 18 February 2020
Principles / Critical Success Factors to Backlog Day Zero
Not everything will be resolved by the system
Records that cannot be resolved by the system must be resolved through business decisions
Dedicated DHET and SITA officials to be allocated to the Backlog Day Zero Programme
Swift dataset turnaround times by all stakeholders and communication / resolving candidate records that have not been approved by Umalusi
Timely business decisions and business rules
Qualification | October 2020 | November 2020 |  | December 2020
GETC-ABET | Secondary focus |  |  | 
NATED Business Studies | Primary Focus |  | Secondary | 
NATED Engineering Studies | Secondary |  | Primary Focus | 
NC(V) First Issues | Secondary Focus |  |  | 
NC (V) Full Certificates | Primary Focus |  | Secondary Focus | 
GETC

## Slide 7: Progress and status of the certification backlog statistics
The initially planned 95% reduction by end March 2021 was met, and currently the overall performance against the baseline is at 99.85%
With the bulk of the candidate records already addressed those remaining are the more complex cases, where manual and business interventions are most often required to correct/align data, once all the analysis has been completed.
Engineering Studies outstanding records main categories include:
Candidate records where the previous exams are not located on the system and were transferred from previous Examination Bodies
Evaluation Errors
Records that have been analysed and creation of certificates to continue
The NC(V) Full certificate outstanding records are mainly related to cases where business rules changed, however the software programs did not take into consideration that this should only have been applied from the date when the changes became effective. Records prior to the effective date for the business rule change were thus updated incorrectly and require a very thorough analysis and manual correction of the data on a record per record basis.

## Slide 8: Key interventions undertaken
The validations for outstanding candidate records were refined. This will ensure that non-qualifying candidates are not included in the outstanding statistics for CET & NATED
Key adjustments on the functionality of the systems
Enhanced functionality to process (resulting and extracting) candidates for multiple examination cycles as opposed to one exam cycle at a time (CET)
Updated moderation records where candidates were fully absent or irregular
Enhanced current extracting and analysis programs to list the outstanding candidates and include indicators for certificates not yet printed, candidates with dyscalculia and mathematics offered, mop-up processes not completed (NATED)
Enhanced functionality to view candidates on the Frequency, Moderation Log and Candidate Mop-up Files
DHET, Umalusi & SITA agreed to process candidates where multiple mark changes were applied after the initial resulting. Initially only a single mop-up was catered for and resulted in QAA rejections (NCV)

## Slide 9: Conclusion
As per the commitments the target to achieve a 95% reduction by the end of March 2021 was met. As part of the operational work, there will always be fluctuations in the candidates to be certified for previous years and this is dealt with on an ongoing basis as these become certifiable
SITA remains committed to resolving any system or data matters preventing candidates from receiving their certificates to limit the adverse impact on Citizens
The mop-up process are still not running smoothly and despite many interventions there are still process, software program and data deficiencies that are being addressed and the process needs optimisation
The post backlog examination cycles are continuously monitored to ensure that a new backlog is not created

## Slide 10: Thank You Questions