## Slide 1
KZN INFORMAL SETTLEMENTS PRESENTATION
MAY 2022
GROWING KWAZULU-NATAL TOGETHER

## Slide 2: PRESENTATION OUTLINE
GROWING KWAZULU-NATAL TOGETHER
Overview of informal settlements in the province
KZN Allocation summary and targets
2022.23 ISUPG Business plan targets and Approved projects
Upgrading plans status and implementation plan conducted in KZN (2019 to date)
Challenges
Way forward

## Slide 3: KZN Allocation Summary
GROWING KWAZULU-NATAL TOGETHER
R756 868 000
  Programme 2 Planning R197,481,288.04
    Land Acquisition R28,414,207.69
    Bulk Infrastructure R48 394 478
    35 Projects in Planning
  Programme 3 Permanent Services R559 386 711,96
    10142 sites to be achieved
    20 Projects at servicing
    NB: R166 000 000 has been highlighted for Disaster assistance which will results in the review of the 2022/23 targets

## Slide 4: SUMMARY of informal settlements in KZN province
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements
EThekwini Metro | 730
Amajuba | 7
Harry Gwala | 9
Ilembe | 22
King Cetshwayo | 8
Ugu | 10
Umgungundlovu | 115
Umkhanyakude | 5
Umzinyathi | 8
uThukela | 8
Zululand | 15
Total | 937
The identification and verification exercise commissioned by the National Department of Human settlements through The National Upgrading Support Programme (NUSP) in collaboration with the Province and municipalities culminated in approximately 937 informal settlements being identified
Source: Identification of informal settlements in KZN report;2018

## Slide 5
2022.23 ISUPG BUSINESS PLAN AND NON-FINANCIAL TARGETS
GROWING KWAZULU-NATAL TOGETHER

## Slide 6
ISUPG- PROJECTS IN PLANNING |  |  | 
DISTRICT | MUNICIPALITY | PROJECT NAME | BUDGET
AMAJUBA | Newcastle Municipality | Drycut Farm Housing Project | R461 580,00
 | Newcastle Municipality | Vezokuhle | R1 713 810,00
 | Newcastle Municipality | Johnstown, Blaauuboschslaagte and Cavan Phase 2&3 Catalytic Housing Project (bulks ) | R33 394 478,95
 | eMadlangeni Municipality | Balgray Housing Project | R175 323,00
 | Newcastle Municipality | Soulcity/ Stamfordhill | R1 119 139,25
UMGUNGUNDLOVU | Msunduzi Municipality | Kwa 30 Informal Settlement Upgrade | R455 291,00
 | Msunduzi Municipality | Khalanyoni Informal Settlement Upgrade | R1 138 230,00
 | Msunduzi Municipality | Edendale J2 and Quarry | R949 000,00
 | Msunduzi Municipality | Edendale Bulwer Informal Settlement | R786 000,00
 | Msunduzi Municipality | Bhobhonono Masomini | R3 688 266,00
 | Mngeni Municipality | Hillside | R426 542,00
 | Msunduzi Municipality | Sobantu | R256 000,00
 | Msunduzi Municipality | Snathing Phase 1 Informal Settlement Upgrade | R3 384 000,00
 | Msunduzi Municipality | Smero Caluza | R3 688 266,00
 | Msunduzi Municipality | Glenwood 2 South East Sector | R10 560 870,00
 | Msunduzi Municipality | Mkhondeni SACCA | R198 998,00
 | Msunduzi Municipality | Peace Valley 2 Informal Settlement Upgrade | R845 000,00
 | Mkhambathini Municipality | Stockdale Informal Settlement Upgrade | R317 000,00
 | Msunduzi Municipality | Harewood | R1 084 000,00
 | Mpofana Municipality | Rosetta Housing | R376 808,00
GROWING KWAZULU-NATAL TOGETHER
6

## Slide 7
ISUPG- PROJECTS IN PLANNING |  |  | 
DISTRICT | MUNICIPALITY | PROJECT NAME | BUDGET
HARRY GWALA | Ubuhlebezwe Municipality | Ixopo Slums | R3 499 958,00
UTHUKELA | Alfred Duma Municipality | Ntokozweni(Gumtree) | R800 000,00
 | Alfred Duma Municipality | Ezakheni C | R60 000,00
ZULULAND | Abaqulusi Municipality | Bhekumthetho Housing Project | R5 684 614,00
 | Ulundi Municipality | Babanango Phase 3 | R546 409,00
 | eDumbe Municipality | Mangosuthu Village | R2 412 026,00
 | eDumbe Municipality | eDumbe Phase 3 | R730 000,00
ILEMBE | Kwadukuza Municipality | Mgigimbe | R250 832,94
 | Kwadukuza Municipality | Nyathikazi Housing Development - Phase 1 | R4 969 440,32
 | Kwadukuza Municipality | Driefontein | R305 505,00
 | Kwadukuza Municipality | Charlottedale | R5 911 589,40
 | Kwadukuza Municipality | Madundube | R14 297 940,95
 | Kwadukuza Municipality | Shakasprings | R937 488,54
KING CETSHWAYO | Umhlathuze Municipality | Mzingazi | R1 000 000,00
 | Umhlathuze Municipality | Mandlazini | R680 000,00
 | Umhlathuze Municipality | Mandlazini Airport Buffer | R490 000,00
 | Umhlathuze Municipality | Mzingwenya | R1 000 000,00
 | Umhlathuze Municipality | Nseleni | R1 000 000,00
 | Umhlathuze Municipality | Vulindlela | R1 000 000,00
GROWING KWAZULU-NATAL TOGETHER
7

## Slide 8
ISUPG- PROJECTS IN PLANNING |  |  | 
DISTRICT | MUNICIPALITY | PROJECT NAME | BUDGET
KING CETSHWAYO | uMfolozi Municipality | Nzalabantu | R1 800 000,00
 | uMfolozi Municipality | Mzingazi uMfolozi | R1 800 000,00
 | Umhlathuze Municipality | Empangeni IRDP | R15 000 000,00
 | Mthonjaneni Municipality | Thubalethu | R5 146 674,00
UMKHANYAKUDE | Big 5 False Bay Municipality | Phumlani Slums Clearance Project | R526 000,00
ETHEKWINI | EThekwini Metro | Greater Amaoti | R20 000 000,00
 | EThekwini Metro | Ntuzuma C Phase 2 | R1 000 000,00
 | EThekwini Metro | Ntuzuma D Phase 2&3 Extension | R1 500 000,00
 | EThekwini Metro | Redcliffe Valley View Informal Settlement Upgrade | R1 000 000,00
 | EThekwini Metro | Kennedy Road Informal Settlement Upgrade | R500 000,00
 | EThekwini Metro | Namibia Stop 8 | R2 500 000,00
 | EThekwini Metro | Umlazi S1, S2, S3 | R3 500 000,00
 | EThekwini Metro | Ntuzuma G Extension | R800 000,00
 | EThekwini Metro | Bhambayi Phase 1 Ext(Pat Marshall) | R1 000 000,00
 | EThekwini Metro | Amahlongwa | R500 000,00
 | EThekwini Metro | Umkhomazi | R1 000 000,00
 | EThekwini Metro | Pilgrim X | R400 000,00
 | EThekwini Metro | Craigieburn | R500 000,00
PLANNING |  |  | R169,067,080.35
LAND ACQUISITION |  |  | R28,414,207.69
TOTAL |  |  | R197,481,288.04
GROWING KWAZULU-NATAL TOGETHER
8

## Slide 9
ISUPG- PROJECTS IN SERVICES |  |  |  | 
DISTRICT | MUNICIPALITY | PROJECT NAME | BUDGET | SITES TO BE SERVICED
AMAJUBA | Newcastle Municipality | Johnstown, Blaauuboschslaagte and Cavan Phase 1 Catalytic Housing Project | R8 340 450,00 | 150
 | Dannhauser Municipality | Dannhauser Housing Project | R11 120 600,00 | 200
 | Newcastle Municipality | Johnstown, Blaauuboschslaagte and Cavan Phase 2&3 Catalytic Housing Project | R433 703 400,00 | 7800
UMGUNGUNDLOVU | Msunduzi Municipality | North East Sector 2 Glenwood Housing Project | R15 624 724,00 | 281
 | Mpofana Municipality | Rosetta Housing | R 5 124 216,00 | 92
 | Mngeni Municipality | St Joseph | R4 288 746,00 | 77
UTHUKELA | Inkosi Langalibalele Municipality | Ephangeni | R13 357 120,08 | 228
KING CETSHWAYO | Umlalazi Municipality | Sunnydale Phase 2 | R1 904 754,93 | 21
 | Umhlathuze Municipality | Dumisane Makhaye Village | R1 121 627,95 | 133
ETHEKWINI | EThekwini Metro | Lamontville Slums Clearance | R4 050 000,00 | 72
 | EThekwini Metro | Ntuzuma G Infill | R7 715 473,00 | 138
 | EThekwini Metro | Ntuzuma C Ph 2 | R2 350 000,00 | 42
 | EThekwini Metro | Etafuleni | R2 350 000,00 | 42
 | EThekwini Metro | Ntuzuma D Ph 2 & 3 | R2 350 000,00 | 42
 | EThekwini Metro | Umlazi Infill Part 4 and Part3 , extension of Part 4 | R2 350 000,00 | 42
ILEMBE | Kwadukuza Municipality | Nyathikazi Housing Development - Phase 1 | R8 332 800,00 | 149
 | Kwadukuza Municipality | Etete Phase 4 | R17 446 800,00 | 313
 | Kwadukuza Municipality | Mgigimbe | R8 332 800,00 | 149
 | Kwadukuza Municipality | Madundube Housing Project Phase 1 | R9 523 200,00 | 171
TOTALS |  |  | R559 386 711,96 | 10142
GROWING KWAZULU-NATAL TOGETHER
9

## Slide 10: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
Harry Gwala | 9 | 9 | Upgrading plans completed in Umzimkhulu (3), UBuhlebezwe (3) and Greater Kokstad (3) municipalities. Greater Kokstad informal settlements. Marikana -B2 Moyeni -B1 Horseshoe -C UBuhlebezwe informal Settlements. High flats -B1& C Ixopo slums -B1&C Morning view/Fairview -B1&C Umzimkhulu informal Settlements. Cala street -B1 Clydesdale border -B1 KwaMankofu -B1 | Upgrading plans for all 9 projects in Harry Gwala completed. Close out reports still pending. Once close out report is received. Province will utilize recommendations from upgrading plans to compile installations of interim services submissions to TEC in next financial year 2022/23 business plan.

## Slide 11: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
iLembe | 22 | 16 | Upgrading plans completed in KwaDukuza (16) municipalities. Service provider has been appointed by province to do upgrading plan for Charlottedale. Completed upgrading plans in KwaDukuza: San Souci – A/B1 Ohlange – A/B1. Ntwashini – B1. Lindelani Extension – B1. Dump site – B1. Hillview – B1. Nyoni yaManzi – B1. Murugans Area – B1 Mpongompongwen – B1. Shayamoya – B1. Mawowane – B1. Emadanishini – B1 Hangoes – B1 Umgababa – B1. Sheffield – B1 Shakasprings – C | Submission to be prepared for all B1 category settlements for designs and installation of interim services. Submission for the remainder of informal settlements in Ndwedwe and Mandeni will be presented to TEC 1 at the beginning of the 2022/23 financial year.

## Slide 12: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uGu | 9 | 9 | Upgrading plans completed in Ray Nkonyeni (4) and UMdoni (5) local municipalities. NUSP Project has completed all 6 phases and has been closed out. Submissions prepared for all B1 category settlements to be prepared. Ray Nkonyeni informal settlements; Louisiana-B2&C Masinenge-B1&C Mkholombe-B1&C Paddock-B2 UMdoni Settlements; KaMbetheni-B2& C NPA-B1&C Roseville-B1&C Sanathan-B1 Temporal Houses-B1 | Submissions prepared for detailed planning and interim engineering services designs prepared for All B1 settlements. Submission to be presented at Tec 1 (8 March 2022). Ray Nkonyeni and UMdoni Local Municipalities to endorse completed upgrading plans for implementation. Submissions to be undertaken for all B1 category settlements by Province subject to consultation and endorsement of upgrading plans by Municipality.

## Slide 13: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uMgungundlovu | 115 | 39 | Upgrading plans in UMshwathi (9), UMsunduzi (11), Richmond (2), Umngeni (6) Mpofana (3), Mkhambathini (7) are completed. Remainder of informal settlements located within UMsunduzi were assessed previously in 2016 and are completed (25). Mpofana: Brickyard – B2 NCD Milk Factory – B2 Town Hall – B2 uMngeni: Cedara – B2 Lidgetton / Ezitolo – B1 Mandela Capture Site – B2 Railway – C Sphumelele – C Thokoza - C uMshwathi: Esidakeni – B1 Fair View Farm / Emagrapsini – B1 Gonowakhe – B1 Loliwe – C Loliwe 2 – C Maistry 1 – B2 Maistry 2– B2 Mkhushwa – B1 New Hanover Railway – C Mpolweni – B1 | UMshwathi (9), Mpofana (3) Umngeni (6) Mpofana, uMngeni, uMshwathi – plans finalized, are yet to be adopted by Council UMsunduzi (12), Richmond (2), Mkhambathini (7): A submission for emergency interim services is being drafted. Initially, submission had been drafted, due to special financial implications, TEC1 advised on input from SCM and then re-tabling. After approval of interim services submission a SP will be appointed – first to draft the services designs, and obtain approvals. Once designs are completed they will act as project manager for the implementation. This also applies for the 2016 Msunduzi UP’s (the 25).

## Slide 14: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uMgungundlovu (cont.) | 115 | 39 | Mkhambathini Emabhodini, B1 Farm Mist (KwaMadolo) Informal Settlement, B2 KwaMavalindlela Informal Settlement, B2 Mandalyn Informal Settlement, B1 Sotobe Informal Settlement, C Umlaas Road Informal Settlement, C Umlaas Road Informal Settlement, C Richmond: Bhongoza, C Mkhuzane, C Msunduzi: Ashdown Ext 4, B1 Emadakeni, B1 Entabeni, B1 Mbali Small 18, B1 Marikana, B1 Pavallion, B2 Shawela, B1 Shayamoya, B1 Zoonule, B1 Thembelihle Extension, B2 Woodstock, B1 | UMsunduzi (12), Richmond (2), Mkhambathini (7): A submission for emergency interim services is being drafted. Initially, submission had been drafted, due to special financial implications, TEC1 advised on input from SCM and then re-tabling. After approval of interim services submission a SP will be appointed – first to draft the services designs, and obtain approvals. Once designs are completed they will act as project manager for the implementation. This also applies for the 2016 Msunduzi UP’s (the 25).

## Slide 15: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uMgungundlovu (cont.) | 115 | 25 | Msunduzi (2016): Buntine Place, A Imbali Crossing, C Tehuis – Edendale, B1 Shamrock, C Wayside Place, C Mattison Drive, C Crest Place, C Mayfair Road, C Comet Place, C Nhlalakahle, C Springvale, C Maryvale, C Gomorra, C Old Greytown Road, C Privet Road, C Jesmondene, A, C Ortmann Road, C Skomplaas, B1 Shottie, B2, C Namibia, B2, C Coal Yard, B2, C Imbali Unit 4, B1 Willowfontein- Terminus, B1 Phupha, B1 Edendale BB, C Panekeni, B1 | UMsunduzi (12), Richmond (2), Mkhambathini (7): A submission for emergency interim services is being drafted. Initially, submission had been drafted, due to special financial implications, TEC1 advised on input from SCM and then re-tabling. After approval of interim services submission a SP will be appointed – first to draft the services designs, and obtain approvals. Once designs are completed they will act as project manager for the implementation. This also applies for the 2016 Msunduzi UP’s (the 25).

## Slide 16: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uMzinyathi | 8 | 7 | Upgrading plans completed in Endumeni (7).1 informal settlement removed by municipality from list. Endumeni Settlements Mzomusha - A KwaKunene Farm – B1 Craigside – B1 Private Land – B1 Dlamini Cwebezela – B1 Dlamini Village – B1 Transit Camp - C | To date all deliverables have been concluded and signed off and presented to the Project Steering Committee. The process of adoption by the Endumeni Municipal Council is anticipated in the next Council sitting as scheduled for March 2022. Application of the study’s recommendation will be implemented in the short, medium and long term under the UISP Grant/Subsidy. Submissions are in preparation for reservation of subsidies for detailed planning and interim engineering services designs for all category B1 and A settlements

## Slide 17: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
uThukela | 10 | 10 | Upgrading plans completed in Okhahlamba (2). Alfred Duma (6) informal settlements upgrading plans done in 2016 have been revised by HDA Okhahlamba informal settlements: Eskom - C Central (Public works) - C Alfred Duma informal settlements: Mthandi - B1 Thembalihle - B1 Intokozweni (Gumtree) - B1 Area K - B1 Qwaqwa - B2 Umbulwane (Steadville Strip) - B1 Indomba - B1 St Chads- B1 | Okhahlamba upgrading plans are complete and have been endorsed by the municipality, both settlements will be relocated to an active project that is currently in the detailed planning stage. Alfred Duma upgrading plans are near completion and require a bulk confirmation from the district, Intokozweni (Gumtree) is in the process of appointing a service provider for detailed planning and engineering services designs. Submissions prepared for detailed planning and engineering services designs prepared for Mthandi and St Chads. Anticipate receipt of the bulk confirmation from the district and endorsement by the Municipality by the end of March 2022 for upgrading plans.

## Slide 18: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
GROWING KWAZULU-NATAL TOGETHER
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
Zululand | 15 | 15 | Upgrading plans in uPhongolo (1), Abaqulusi (6), Ulundi (3), eDumbe completed Abaqulusi Local Municipality; Ma300 Informal Settlement B2 KwaGxoba Informal Settlement B1 Dumping Site Informal Settlemen-B2 New Worker Informal Settlemen-B1 Boyana Informal Settlement-B2 "Mkhukhu Yase Lakeside Informal Settlement“-B2 uPhongolo Local Municipality; Candover-A Ulundi Local Municipality THOKOZA-B2 B-South Emkhukwini-B2 Nyathini/Industrial-B2/C | Upgrading plans have been complete. Region to commence with drafting of TEC submissions and anticipate presentation in May 2022.

## Slide 19: UPGRADING PLANS CONDUCTED IN KZN (2019 TO DATE)
District Municipality | No. of Informal Settlements | Number of upgrading plans | Upgrading plan Status as at 28 February 2022 | Comments/Process plan on implementation
Zululand (cont.) | 15 | 15 | eDumbe Local Municipality Khambule Informal Settlement B1 Eskhaleni Informal Settlement B1 Moscow Informal Settlement B1 Madelakufa Informal Settlement B1 Phoqukhalo Informal Settlement B1 | Upgrading plans have been complete. Region to commence with drafting of TEC submissions and anticipate presentation in May 2022.
GROWING KWAZULU-NATAL TOGETHER

## Slide 20: challenges
GROWING KWAZULU-NATAL TOGETHER
Acquisition of suitable alternative land for relocation is scarce and expensive
Lengthy processes for land acquisition
Lack of adequate bulk infrastructure
Land invasions and continuous urbanisation
Exponential growth and proliferation of informal settlements
Conventional housing service delivery is slow
Township establishment processes is slow
poor health quality
lack of secure land tenure
squatter settlements located on private land

## Slide 21: WAY FORWARD
GROWING KWAZULU-NATAL TOGETHER
2022.23 UISP allocation is R756,868,000.
Completed Upgrading plans will create a roadmap to informal settlements upgrading to ensure technical assessments, socio-economic, environmental, geotechnical factors and the availability of bulk infrastructure services are provided to those living under precarious conditions
The Department through its Integrated Planning directorate will be appointing service providers to undertake detailed planning and detailed designs to install interim/basic as well as permanent services in various informal settlements within the Province.
The KZN UISP forum, provides vehicle for reporting and monitoring of the UISP and grant utilisation and a platform for knowledge sharing, robust stakeholder participation and engagement thereby ensuring stratified and collaborative participation.
Department continues to offer technical assistance to municipalities and informal settlement practitioners within the Province for optimum incremental upgrading interventions

## Slide 22
THANK YOU
(031) 336 5300 (dbn)
Kwazulu-Natal Department of Human Settlements
www.kzndhs.gov.za
@kzndohs
0800 701 701
ANTI-FRAUD E-MAIL:
fraudhotline@kzndhs.gov.za
(033) 392 6400 (pmb)