## Slide 1: Department of Military Veterans
STATUS OF THE RECORD REVIEW REPORT
08 MAY 2022

## Slide 2: Table of contents
  1. Status of key focus areas
  2. Financial management key matters for attention
  3. Performance management key matters for attention
  4. Procurement and contract management key matters for attention
  5. Compliance management key matters for attention
  6. Human resources management key matters for attention
  7. IT management key matters for attention
  8. Oversight and monitoring key matters for attention
  9. Financial Health key matters for attention
  10. Key Service Delivery Matters
  11. Fraud Risk Indicators
  12. Key emerging risks/developments/Modified cash standard 13. Progress on the overall commitments made
  14. Audit-related matters
The Process of Internal Control
Control Environment
Control Activities
Information and Communication
Monitoring
Risk Assessment

## Slide 3: Status of key focus areas
The status as presented below is based on the review performed and reflects the involvements from the previous assessment
Status of key focus areas
Oversight and monitoring
HR management
IT management
Financial health
Financial management
Performance management
Compliance management
Procurement and contract management
Good | The basics are in place as no concerns were identified.
Concerning | Concerns identified.
Intervention required | Level of concerns identified is an indicator that the AO needs to urgently intervene to prevent audit failure.
 | Improved
 | Unchanged
 | Regressed
The legend applied is as follows:

## Slide 4: Financial management key matters for attention
In assessing the implemented preventative controls around asset management, the following was identified as weaknesses:
The asset verification per the policy is scheduled to only take place annually, with the asset reconciliation to the general ledger done on a monthly basis. Missing assets may therefore not be identified in a timely manner, but only during the annual asset count.
No evidence was provided by the department that the asset register reconciliation has been conducted on a monthly basis. In the prior year, the department engaged the services of a consultant to assist with the asset register and that process was not concluded in a timely manner resulting in management not utilising the consultant’s assets register when preparing the annual financial statements in the prior year.
The contract with the service provider appointed to to assist with the asset register expired as at 31 October 2021 and the process was not fruitful as there were disagreements on the number of assets between the department and the consultant. There is a risk of inadequate contract management and possible fruitless and wasteful expenditure on the amounts paid to the consultant.
The asset register does not describe the condition of each asset in detail. Including this information would help the department to identify which assets are in a useable condition, which assets are obsolete and/or damaged in order to dispose of them in a timely manner and to ensure maintenance of the assets. Keeping assets that are not in a working condition in the assets register would also result in overstatement of assets disclosed in the department’s annual financial statements.

## Slide 5: Financial management key matters for attention(cont…)
The Modified Cash Standard (MCS) requires that assets not found during a verification process be documented in a loss control register pending the outcome of an investigation. A follow up was performed on the investigation of the major assets to the value of R 6 172 000 (513 individual assets) and minor assets to the value of R1 013 000 (384 individual assets) that were disclosed as under investigation in the 2020-21 financial statements and it was noted that the investigation to determine whether assets were lost, stolen or disposed of has not yet been concluded. This deficiency has been reported over a number of years and is still not addressed.
According to the latest action plan, progress made to date to address the asset register verification is only at approximately 60%.
The LOGIS system is not yet fully functional due to human capital related challenges and the required training for the LOGIS Syscon has not been attended by the LOGIS Syscon as a result the department is still making use of manual registers( excel) which further increases the risk of errors .
The above matters were raised during the previous audit and as per the action plan finance is to conduct verifications at the regions in February 2022. This might result in the department not having sufficient time to address discrepancies identified during the asset verification.
The department has numerous suspense accounts, with amounts that have been in the accounts for more than one year. This indicates that management does not investigate and clear amounts timeously on the suspense accounts. Unclearing of the suspense account may result in inaccurate financial statements as there are figures that will not be accounted for which may be important to the users of the financial statements as well as non-compliance with the requirements of para 4, 5 of the PMB/Bank reconciliation procedure manual which requires that all control/suspense accounts be cleared via online exception functionality or general journal before system closure.

## Slide 6: Performance management key matters for attention
The department has under achieved in its performance for the period 01 April 2021 – 31 December 2021. The overall achievement by the department on its performance objectives was recorded at 42%. On review of the governance structure meetings it was also noted that the portfolio committee is also concerned about the continuous non-achievement of performance.
For the scoped in programme, Socio-economic Support (SES), we noted that for the third quarter the department had planned for five targets and only one was achieved. The following are the targets that have not been achieved:
For PPI 201, Number of approved Non-Statutory Forces received from the verification panel for inclusion in the database.The target for the three quarters ended 31 December 2021 was 2250 and as at the end of quarter three only 789 has been reported as achieved.
PPI 202, Number of of Military Veterans provided with newly built houses per year, the annual target is 355 and only 28 military veterans were provided with newly built houses.
PPI 204, Number of Military Veterans participating in the pension benefit pilot project, the annual target is 200, with the cumulative target for quarter three being 150 and no achievement has been reported as at the end of the quarter.

## Slide 7: Performance management key matters for attention(cont…)
PPI 205, Number of Military Veterans participating in the subsidized public transport benefit pilot project, the annual target for the indicator is 200, the target was planned to be achieved in full in quarter two, and no achievement has been reported.
The department is currently in the process of determining the implications on the budget for the full implementation of the policy for the pension and subsidised public transport as these two indicators were not budgeted for in the 2021/22 financial year, the targets for these indicators have not been achieved and there is a possibility that they will not be achieved by year, this will have a negative impact on the delivery of services to military veterans.
During the review of the reported performance information for quarter one by internal audit, there were differences noted between the reported achievement and the supporting documentation. This is an indicator that the department has not fully implemented adequate preventative controls to ensure that performance reporting is reliable. Inaccurate reporting will also result in adverse audit outcomes for the department.

## Slide 8: Performance management key matters for attention(cont…)
The department did not submit the second quarter performance report to the executive authority and National Treasury within 30 days of the end of the quarter. The report was submitted on 08 December 2021. Non-submission of the quarterly reports in a timely manner will result in non- compliance with the Revised Framework for Strategic Plans and Annual Performance Plans. This will also have an impact on the relevant authorities in exercising their responsibilities on oversight timeously.

## Slide 9: Procurement and contract management key matters for attention
On review of the department’s quarter two progress report on the procurement plan it was noted that the department is behind on its procurement plan. As at the end of the quarter, no progress was reported on the procurement plan. As these planned contracts could relate to essential procurement for the department to effectively function, there is a risk that the department may continue to extend existing contracts and exceed the threshold for variation and extensions or procurement could continue on expired contracts resulting in irregular expenditure.
There are contracts that have expired that the department has a continued need for the services e.g. telecommunications services, the new service providers were only appointed in the third quarter. There is a risk that the department may have continued using the services of the service providers without a valid contract being in place resulting in non-compliance and possible increase in irregular expenditure.

## Slide 10: Compliance management key matters for attention
The progress made by management to investigate irregular expenditure that was reported in the previous year was assessed and the following was noted.
  In the 2020-21 financial year, the department disclosed irregular, fruitless and wasteful expenditure under assessment/determination. Follow ups were made on the progress made with this process as well as any additional actions taken in relation to these matters were requested in request for information (RFI) 07 of 2021/22, however it was noted that the department has not performed the determination test within 30 days in line with the requirements of the irregular and fruitless and wasteful expenditure frameworks, resulting in non-compliance with the requirements of the frameworks.
  On engagement with management, it was indicated that all the cases have been provided to the external investigator for investigation.
  During the performance of this review, follow-ups were also made on the progress of implementation of the recommendations by the Department of Planning, Monitoring and Evaluation (DPME) as part of initial investigation into prior years’ irregular expenditure, it was noted that of the 64 cases, 4 written warnings were issued to the affected officials and the rest of the cases have been provided to the external investigator.

## Slide 11: Compliance management key matters for attention (cont…)
The delays in concluding investigations may lead to non-compliance with the requirements of section 38(1) (h) (iii) of the Public Finance Management Act 1 of 1999 (PFMA) and treasury regulation 4.1.2 and negative audit outcomes.
Our review also revealed that the department has not complied with National Treasury Instruction note 34 and Treasury Regulation 8.2.3 on paying service providers within 30 days for the period 01 April 2021 to 30 November 2021. The main causes listed are the challenges with LOGIS and the department not having an effective invoice tracking system. This will result in the department incurring fruitless and wasteful expenditure for interest paid on late payments to service providers.
The department should expedite the process of ensuring that LOGIS is fully functional to improve its operating effectiveness in expenditure management.

## Slide 12: Human Resource management key matters for attention
The overall vacancy rate is currently at 10%. The key vacant positions are:
Deputy Director-General: Corporate Services (vacant since 1 September 2019).
Other key long-outstanding vacant posts include:
Chief Director: Beneficiary Support (more than 12 months)
Director Financial Accounting ( more than 12 months)
The department is also experiencing a number of vacancies in divisions linked to performance management as follows :
Deputy Director General – Socio Economic support
Assistant director – Monitoring and evaluation
Chief Director Beneficiary support
The department should expedite the process of filling vacant posts as some of these affect service delivery to military veterans and may result in misstatements in performance reporting.
The department’s organisational structure was approved on 30 June 2010 and has not been regularly reviewed. Leadership should expedite the process of review and approval of the organisational structure as it may result in an outdated organisational structure, which does not address the current needs of the department.

## Slide 13: Human Resource management key matters for attention(cont..)
The internal audit unit is still not adequately capacitated. This has had a negative impact on the internal audit unit’s ability to adequately complete their annual plan and fully perform the critical duties and roles to add value to the department. The Director Internal Audit is currently acting as the Chief Financial Officer (CFO), and there is a vacancy in that position, there is currently no official acting in that capacity, which puts further strain on the internal audit unit’s capacity challenges.
The department has embarked on a process to appoint an external service provider to support the internal audit function, but the process has not yet been finalised. With year-end approaching, this may result in non-compliance with Treasury Regulations relating to activities that the internal audit function is required to perform. Furthermore, there might be insufficient time for management to address any control deficiencies identified by the service provider prior to submission of the final financial statements for external audit. This was also reported in the previous review period.

## Slide 14: IT management key matters for attention
Based on the action plan to address the 2020/21 IT audit findings it was noted that the management was in the process of addressing weaknesses noted on IT governance, security management, IT service continuity and user access management.
The design of the Disaster Recovery Plan (DRP) in alignment to the Business Continuity Plan (BCP) was still not completed. A Tasking Letter incorporating a comprehensive Business Impact Analysis, BCP and DRP implementation plan has been submitted to SITA for implementation.
The department was still utilising Military Veterans Beneficiaries Database (MVBD) based on the Microsoft Access tool to manage military veterans’ beneficiaries. The MVBD does not have functionality to log and retain activities performed by users as well as changes made on MVBD. As a result, the auditors will not be able to provide assurance on implemented user access and change management controls around the MVBD. The DMV and SITA has entered into agreement for the development and implementation of the Integrated Database Management System (IDBMS). The agreement clearly outline the cost implications and highlighting the rollout approach of the system.

## Slide 15: Oversight & monitoring key matters for attention
During the review of internal audit, we have noted that the internal audit unit has still not had a five-year external quality assessment review done as per the previous action plan. A request by the department was sent to National Treasury to assist with the external review. The department should expedite the process of the external review to ensure that the internal audit division is compliant with the requirements of IIA standard 1312.
Treasury Regulation 3.2.9 provides that internal audit must perform their functions independently from management; however, the director internal audit is acting as the CFO of the department (while the appointed CFO is on suspension). Should the director return to her position as head of internal audit she will review activities for which she was a preparer or reviewer, posing a self-review threat to independence. The department should put measures in place in order to reduce the self-review threat.
The audit committee comprises of three members, however the third members’ membership has been suspended resulting in the department not meeting the requirements of section 77(a) of the PFMA, which requires that the audit committee consist of at least three persons.

## Slide 16: Oversight & monitoring key matters for attention(cont..)
The audit committee charter para 7.2 states that a quorum shall be attained in a meeting when there are 3 members present. On review of the audit committee meeting minutes for 10 August 2021 and the meeting held on 29 November 2021 it was noted that only two members attended. This results in delays in oversight decisions as no decisions were made in these meetings. The department should ensure that the members on the committee are sufficient to account for events where one or two members are not present at the meeting to form a quorum. This would ensure compliance with the audit committee charter and be in line with good governance practice.
The department has some policies that have not been reviewed over a period of five years, other policies are in draft and not yet signed for final approval but are said to be in effect, for example the Human Resource Administration (Talent attraction, selection, Appointment, Probation, induction, Remuneration, Exit/termination, Transfer/Secondment, resettlement), Probation policy etc. The lengthy delays in approving policies, as well as the implementation of policies not yet fully approved, may result in inconsistencies and weaknesses in the control environment.
There was no meeting scheduled for the audit committee to review the quarterly report for quarter one, the first quarter report was presented at the audit committee meeting held on 29 November 2021 as a result the report was sent to National Treasury and the Executive Authority without being reviewed by the audit committee, TR3.1.10(d) requires the audit committee to review the adequacy, reliability and accuracy of the financial information provided to management and other users of such information. It was further noted that the audit committee has not yet reviewed the quarter two report and it has also been submitted to National Treasury and the Executive Authority without being reviewed by the audit committee.

## Slide 17: Oversight & monitoring key matters for attention(cont..)
The previous slides results in the audit committee not providing timely oversight on the department’s performance and non-compliance with TR3.1.10(d).
The department did not take appropriate actions to ensure that all action plans developed to address internal control deficiencies identified in the prior year are implemented on time. During the review of the audit action plan it was noted that as at 29 November 2021 the following progress had been made :
  For programme two (SES) - two items were listed on the action plan and of the two one had been implemented at a 40% and 1 is due on 31 March 2022.
  For compliance - 11 actions were planned and six of the tasks were in progress and five are complete.
  Finance had 19 tasks on their action plan with four of the tasks being in progress and the other 15 are complete.
  The above may result in recurring audit findings as the internal control deficiencies identified in the prior year are not addressed timeously.

## Slide 18: Financial Health key matters for attention
As at the end of quarter three, the department has accruals and payables not recognised to the value of R86 179 000. There has also been an increase in the creditor payment period from the last assessment of 142 days to 162 days with the accruals and payables not recognised that are exceeding 30 days at 97, 4% which could result in the department being liable for possible interest on late payments

## Slide 19: Key service delivery matters
Based on the third quarter financial statements, the spending patterns of the department indicate that the service delivery programmes are behind with their spending. As of quarter three (31 December 2021), the department has only spent 43,9% of the socio-economic support budget and 43,4% of the empowerment and stakeholder management with an overall 47,6% of the department’s budget spent, which could have a negative impact on key service delivery.
The underspending of the department may also impact the department negatively in terms of budget cuts by the National Treasury.
The issue of a credible military database is critical and should be addressed urgently to assist the department in achieving its mandate of delivering benefits to deserving military veterans. Based on the quarter three report, the department is still behind in achieving this target to validate the number of military veterans on its database. As at the end of quarter three 789 military veterans were verified over the planned cumulative target of 2 250.
The department has had numerous complaints relating to service delivery to military veterans, the above issues may worsen the unrest of the military veterans.

## Slide 20: Fraud risk indicators
The department has a number of investigations that are ongoing from the Hawks , SIU and other external investigators into fraud and corruption and other non-compliances within the department

## Slide 21: Key emerging risks/developments/Modified cash standard
The following emerging risks are relevant for the 2021-22 audit cycle.
Componentisation of assets
  Departments are encouraged to componentise assets in their asset registers, as it will become a requirement in future. The effective date to componentise assets has not been determined yet.
Classification of housing-related expenditure
  Departments of Human Settlements should implement the transitional provisions in the Human Settlements Departments: Transition Guide on Classification of Expenditure issued by the OAG to classify housing related-expenditure. The effective date to classify housing related-expenditure in accordance with the ERF without any deviation is 1 April 2022.
Inventory
  Departments are encouraged to develop their inventory management systems, as the inventory disclosure note will become a requirement in future. The effective date to disclose inventory is still to be determined by the accountant-general.

## Slide 22: Progress on the overall commitments made
Commitments | Date of commitment | Status
Enforcement of consequence management on all identified cases of irregular, fruitless and wasteful expenditure incurred as well as cases of fraud identified. | 30 June 2021 | A change of strategy made a determination to outsource the services using another State Department I.e. Department of Planning, Monitoring and Evaluation. The determination process resulted in a report being issued for DMV Accounting Officer’s consideration and consequence management. The Accounting Officer is applying his mind on the content of the report and appropriate steps will be followed. Priority is being given to cases related to irregular expenditure at this stage
Keep reliable and accurate assets register | 30 June 2021 | Linked to the project team formed between DMV and DPME, the DMV asset register reliability and accuracy will also be addressed where all matters including assets under investigation will be addressed with corrective action and consequence management effected. Security of the asset register will be done through implementation of LOGIS where another project team is also working on LOGIS reimplementation. The reimplementation will be concluded within the current financial year.
Ensure a reliable and secure IT System will provide confidence on the military veteran’s database and business continuity. | 30 June 2021 | The Department has prioritised the establishment of a credible and reliable military veterans’ database. The Plan developed covers the elements of verification, data cleansing and technological enhancement. The plan has been presented to DOD and various stakeholders. The implementation of the plan is in progress and is at 45%. A presentation was also made to parliament, which raised the requirement to publish the information. In the past year, the target accelerated beyond the pace at which it was targeted. The target was 300 and currently 356 has been achieved. A further improvement is envisaged.
Formalization of key policies mainly in the service delivery environment with more priority to Education Support, Housing Assistance, Business Support and Skills Development and Burial Support | 30 June 2021 | The approved policies on Education support, Business and Skills Development and Burial support together with the standard operational procedures and policy guidelines were submitted to AG. The existing burial policy was approved in April 2013, the business support and skills development approved in December 2013, Housing support policy is also approved and the education support policy approved in April 2018. Two of the policies, namely Education support and Skills development, have approved Standard Operating Procedures, whilst the burial policy has a draft standard operating procedures. The housing benefit is being implemented in conjunction with the Military Veterans Regulations of 2014. The department has begun a process of reviewing all the service delivery policies, including the four policies referred to, based on the challenges identified and consultations with departmental stakeholders. The updated four policies (Healthcare, Compensation, Housing and Counselling) are in a final draft were consulted with DMV stakeholders on 27-28 November 2019. Final inputs on the policies are expected to be incorporated before the end of the financial year. The Education Support, Business Support and Skills Development and Burial Support will be consulted with DMV stakeholders in March 2020. Unlike other departments, polices have to be consulted with the DMV statutory bodies as prescribed in the Military Veterans Act, 2011. It is the consultation with stakeholders that often delays the finalisation of the policies. The policy unit is now capacitated to assist the department to finalise all outstanding policies. Progress is now being monitored in management forums.
Encourage a DMV compliance system, which will proactively assist the Department in ensuring continuous adherence with legislation. | 30 June 2021 | The department does have a compliance management unit whose role is to, among others; develop a compliance universe for the department. Compliance Policy Register was developed and presented at MANCO. It is constantly circulated on monthly basis to the branches for them to confirm the status of the existing policies. Compliance with legislation is monitored on a monthly basis through checklists. Invoice Process Flow developed to monitor 30-day payment period. The department does not have a Compliance Management System but depends on manual documentation. A letter requesting assistance on the Compliance system was sent SITA in 2016. SITA said they are currently working the request and present the findings to all the interested parties in due course
Provide reliable and validated reports including Portfolio of Evidence. | 30 June 2021 | The department will ensure that, Portfolio of Evidence is validated prior to submission to Internal audit and the Auditor General. Alignment of submitted POE with evidence required per TID will be monitored.
Commitments | Date of commitment | Status
Enforcement of consequence management on all identified cases of irregular, fruitless and wasteful expenditure incurred as well as cases of fraud identified. | 30 June 2021 | A change of strategy made a determination to outsource the services using another State Department I.e. Department of Planning, Monitoring and Evaluation. The determination process resulted in a report being issued for DMV Accounting Officer’s consideration and consequence management. The Accounting Officer is applying his mind on the content of the report and appropriate steps will be followed. Priority is being given to cases related to irregular expenditure at this stage

## Slide 23: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Keep reliable and accurate assets register | 30 June 2021 | Linked to the project team formed between DMV and DPME, the DMV asset register reliability and accuracy will also be addressed where all matters including assets under investigation will be addressed with corrective action and consequence management effected. Security of the asset register will be done through implementation of LOGIS where another project team is also working on LOGIS reimplementation. The reimplementation will be concluded within the current financial year.

## Slide 24: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Ensure a reliable and secure IT System will provide confidence on the military veteran’s database and business continuity. | 30 June 2021 | The Department has prioritised the establishment of a credible and reliable military veterans’ database. The Plan developed covers the elements of verification, data cleansing and technological enhancement. The plan has been presented to DOD and various stakeholders. The implementation of the plan is in progress and is at 45%. A presentation was also made to parliament, which raised the requirement to publish the information. In the past year, the target accelerated beyond the pace at which it was targeted. The target was 300 and currently 356 has been achieved. A further improvement is envisaged.

## Slide 25: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Formalization of key policies mainly in the service delivery environment with more priority to Education Support, Housing Assistance, Business Support and Skills Development and Burial Support | 30 June 2021 | The approved policies on Education support, Business and Skills Development and Burial support together with the standard operational procedures and policy guidelines were submitted to AG. The existing burial policy was approved in April 2013, the business support and skills development approved in December 2013, Housing support policy is also approved and the education support policy approved in April 2018. Two of the policies, namely Education support and Skills development, have approved Standard Operating Procedures, whilst the burial policy has a draft standard operating procedures. The housing benefit is being implemented in conjunction with the Military Veterans Regulations of 2014.

## Slide 26: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Formalization of key policies mainly in the service delivery environment with more priority to Education Support, Housing Assistance, Business Support and Skills Development and Burial Support | 30 June 2021 | The department has begun a process of reviewing all the service delivery policies, including the four policies referred to, based on the challenges identified and consultations with departmental stakeholders. The updated four policies (Healthcare, Compensation, Housing and Counselling) are in a final draft were consulted with DMV stakeholders on 27-28 November 2019. Final inputs on the policies are expected to be incorporated before the end of the financial year.

## Slide 27: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Formalization of key policies mainly in the service delivery environment with more priority to Education Support, Housing Assistance, Business Support and Skills Development and Burial Support | 30 June 2021 | The Education Support, Business Support and Skills Development and Burial Support will be consulted with DMV stakeholders in March 2020. Unlike other departments, polices have to be consulted with the DMV statutory bodies as prescribed in the Military Veterans Act, 2011. It is the consultation with stakeholders that often delays the finalisation of the policies. The policy unit is now capacitated to assist the department to finalise all outstanding policies. Progress is now being monitored in management forums

## Slide 28: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Encourage a DMV compliance system, which will proactively assist the Department in ensuring continuous adherence with legislation | 30 June 2021 | The department does have a compliance management unit whose role is to, among others; develop a compliance universe for the department. Compliance Policy Register was developed and presented at MANCO. It is constantly circulated on monthly basis to the branches for them to confirm the status of the existing policies. Compliance with legislation is monitored on a monthly basis through checklists. Invoice Process Flow developed to monitor 30-day payment period.

## Slide 29: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Encourage a DMV compliance system, which will proactively assist the Department in ensuring continuous adherence with legislation. | 30 June 2021 | The department does not have a Compliance Management System but depends on manual documentation. A letter requesting assistance on the Compliance system was sent SITA in 2016. SITA said they are currently working the request and present the findings to all the interested parties in due course

## Slide 30: Progress on the overall commitments made(cont..)
Commitments | Date of commitment | Status
Provide reliable and validated reports including Portfolio of Evidence. | 30 June 2021 | The department will ensure that, Portfolio of Evidence is validated prior to submission to Internal audit and the Auditor General. Alignment of submitted POE with evidence required per TID will be monitored.

## Slide 31: Audit-related matters
There is a delay in the submission of information by the department which had an impact on finalisation of the engagement letter, audit strategy and status of records review by the audit team. Delays on the audit will affect the audit team’s ability to meet the legislated time-lines, audit outcomes and the audit budget. Management is requested to cooperate with the audit team and provide information timely in line with the agreed communication protocol.

## Slide 32
Target Date for MONITORING of risk register 26th MAY 2022
Action plan
Update of narratives
submission 20 MAY 2022