## Slide 1
DSBD 2021/22 QUARTER FOUR PERFORMANCE REPORT
PORTFOLIO COMMITTEE ON SMALL BUSINESS DEVELOPMENT
Date: 11 MAY 2022
PRESENTER: DIRECTOR-GENERAL

## Slide 2
PRESENTATION OUTLINE
1 | BACKGROUND AND PURPOSE
2 | GOVERNANCE AND COMPLIANCE
3 | OVERALL PERFORMANCE SUMMARY
4 | PERFORMANCE HIGHLIGHTS
5 | UNDER-ACHIEVEMENTS
6 | FINANCIAL REPORT
7 | HUMAN RESOURCE REPORT
8 | OVERALL PERFORMANCE BY PROGRAMME
9 | RECOMMENDATION

## Slide 3
1. BACKGROUND AND PURPOSE

## Slide 4
BACKGROUND AND PURPOSE
1.1. The report presents an overview of the activities of the Department of Small Business Development (DSBD) in line with the Public Finance Management Act 1 of 1999, Treasury Regulations 5.3 and 30.3, the 2021/22 Guidelines for National Quarterly Performance Reports, and the revised Framework for Strategic Plans and Annual Performance Plans.
1.2. The 2021/22 Q4 Performance Report reflects:
  1.2.1 Progress made on the implementation of Output Indicators and Annual
  Targets set in 2021/22 Annual Performance Plan in respect of Quarter Four;
  1.2.2 Actual output, and reasons for deviations;
  1.2.3 Corrective measures for 2021/22 Quarter Four;
  1.2.4 Financial Report; and
  1.2.5 Human Resource Report.

## Slide 5
2. GOVERNANCE AND COMPLIANCE

## Slide 6
GOVERNANCE AND COMPLIANCE
Committee | No. of Scheduled Meetings | Actual No. of Meetings | Dates
Executive Committee | 3 | 3 | 31 JANUARY 2022 3 MARCH 2022 28 MARCH 2022
Management Committee | 3 | 3 | 17 JANUARY 2022 14 FEBRUARY 2022 14 MARCH 2022
Risk and Ethics Management Committee | 1 | 1 | 7 MARCH 2022 & 14 MARCH 2022 (continuation of the meeting of 7 March to conclude to agenda items)
Audit and Risk Committee | 1 | 1 | 25 MARCH 2022
ICT Steering Committee | 1 | 1 | 15 MARCH 2022
TOTAL | 9 | 9 | 

## Slide 7
GOVERNANCE AND COMPLIANCE (cont)
2.1. The Department complied with all the relevant provisions and rules of:
      The National Assembly;
  The National Council of Provinces;
  The Public Finance Management Act (PFMA), 1999 (No.1 of 1999);
  Treasury Regulations; and
  The National Treasury Framework for Annual Performance Reporting.
2.2. The Department submitted the 2021/22 Q3 Performance Report to the Minister on 30 January 2022.
2.3. The Department submitted the 2021/22 Q3 Performance Report to the Department of Planning, Monitoring and Evaluation (DPME) on 30 January 2022.
2.4. The Department presented the response to the State of the Nation Address 2022 to the
Portfolio Committee on Small Business Development on 2 March 2022.
2.5. The Department presented the 2021/22 Quarter Three Performance Report to the
Portfolio Committee on 23 March 2022.

## Slide 8
3. OVERALL PERFORMANCE SUMMARY

## Slide 9
PERFORMANCE SUMMARY – 2021/22 QUARTER FOUR
Performance Statement:
The Department has 25 output indicators, 25 Annual Targets in the tabled 2021/22 APP and is reporting against 23 Quarterly targets.
Branch | No. of Output Indicators | Quarterly Targets | Achieved | Not Achieved
1. Administration | 9 | 7 | 4 (43%) | 3 (57%)
2. Sector and Market Development | 6 | 6 | 4 (66.7%) | 2 (33.3%)
3. Development Finance | 6 | 6 | 4 (66.7%) | 2 (33.3%)
4. Enterprise Development | 4 | 4 | 2 (50%) | 2 (50%)
Total | 25 | 23 | 14 (60.9%) | 9 (39.1%)

## Slide 10
PERFORMANCE SUMMARY – 2021/22 QUARTER FOUR
Chart: Performance Report – Q4 2021/22
| Q1 2019/20 | Q2 2019/20 | Q3 2019/20 | Q4 2019/20 | Q1 2020/21 | Q2 2020/21 | Q3 2020/21 | Q4 2020/21 | Q1 2021/22 | Q2 2021/22 | Q3 2021/22 | Q4 2021/22
Achieved | 0.757 | 0.81 | 0.7 | 0.85 | 0.35 | 0.89 | 0.95 | 0.8 | 0.429 | 0.545 | 0.625 | 0.609
Partially Achieved
Not achieved | 0.243 | 0.19 | 0.3 | 0.15 | 0.65 | 0.11 | 0.05 | 0.2 | 0.571 | 0.455 | 0.375 | 0.391

## Slide 11
4. PERFORMANCE HIGHLIGHTS

## Slide 12
PERFORMANCE HIGHLIGHTS
The Department paid 100% of valid creditors within 25 days.
A 3.8 % representation of PWDs was achieved (vs Q4 target of 3.2%).
The Department in partnership with its agencies implemented 33 public engagements in District Municipalities (vs Q4 target of 6).
Phase 3: SMME Database – Key Trade Exchange Platform integrated and enhanced reporting implemented.
A total of 52 products (vs Q4 target of 50) produced and services rendered by SMMEs and Co-operatives were linked to market.
55 (vs Q4 target of 50) SMMEs and Co-operatives exposed to international market opportunities.
The SMMEs Development Index survey report was approved by EXCO.
Annual Report on the contribution to jobs by SMMEs and Co-operatives in economic sectors was approved by EXCO.
384 Crafters supported (vs Q4 target of 300) through the Craft Customised Sector Programme.
Township and Rural Enterprises supported to the value of R177.7 million (vs Q4 target of R69.4 million).
6 315 start-up youth businesses supported financially and non-financially.
A report on 13 800 competitive SMMEs and Co-operatives supported (vs Q4 target of 8 000) was approved by EXCO.
Consolidated report on 70 063 competitive SMMEs and Co-operatives supported (vs annual target of 25 000) was approved by EXCO.
The Department submitted the National Integrated Small Enterprise Development (NISED) Masterplan to Minister for consideration and approval to present to Cabinet.
Report on the implementation and monitoring of the performance outcomes of the proposed red-tape reduction interventions in Harry Gwala (Ubuhlebezwe local municipality), King Cetshwayo (uMhlathuze local municipality) and Ugu (Ray Nkonyeni local municipality) was completed.

## Slide 13
5. UNDER-ACHIEVEMENTS

## Slide 14
Under-achievements for 2021/22 Q4
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
1. | Expenditure Report. | % variance on annual budget. | <5% variance on annual budget. | <5% variance on annual budget. | Target not achieved: 15.2% above Q4 projections. | Cashflow projection was R367.5 million, expenditure was R423.4 million resulting in overspending of R55.89 million. | Proper planning of projects by Project Managers and alignment of projections to expenditure.
2. | <10% vacancy rate. | Percentage vacancy rate in funded permanent posts. | <10% vacancy rate in funded permanent posts. | <10% vacancy rate in funded permanent posts. | Target not achieved: 16.2% vacancy rate in funded permanent posts. | 1. Moratorium implemented in August 2021. Although the moratorium was lifted for 17 posts, 17 posts are still under moratorium. 2. Two (2) permanent posts filled, however, termination of 2 permanent staff during the quarter prevented a decrease of the vacancy rate. 3. Under capacity in the Human Resource Unit leading to delays in filling of posts, increase workload within HR Administration (x2 officials). | Full lifting of the moratorium on posts, prioritise the finalization of the organizational structure, implementation of a recruitment plan and employment of additional resources in the Human Resources Unit of the Department.
3. | ≥50% women in SMS employed. | Percentage of female SMS representation. | ≥ 50% of female SMS representation. | ≥ 50% of female SMS representation. | Target not achieved: 47.1% of female SMS representation. | Early retirement of one (1) woman employee in SMS and appointment of one (1) male employee in SMS during the quarter. | Filling of SMS posts in line with Employment Equity priorities.

## Slide 15
Under-achievements for 2021/22 Q4
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
4 | Women-owned enterprises monitored to participate on SheTradesZA platform. | Number of women-owned enterprises monitored to participate on SheTradesZA platform. | 2 000 women-owned Enterprises monitored to participate on SheTradesZA platform. | 500 women-owned enterprises monitored to participate on SheTradesZA platform. | Target not achieved: 268 women-owned enterprises monitored to participate on SheTradesZA platform. | Low registration of women-owned enterprise in the SheTradesZA Hub. | The Department will prioritise implementing a media and marketing plan and budget aimed at popularizing the programme during the 2022/23 financial year.
5 | Incubation Support Programme evaluation conducted. | Incubation Support Programme evaluation approved by EXCO. | Incubation Support Programme (ISP) evaluation conducted and approved by EXCO. | Incubation Support Programme (ISP) evaluation conducted and approved by EXCO. | Target not achieved: Incubation Support Programme (ISP) evaluation not conducted and approved by EXCO. | Request for single source Government Technical Advisory Centre (GTAC) declined by Treasury and therefore the evaluation did not proceed. | The process to be initiated again in the new financial year.
6 | SMMEs and Co-operatives Funding Policy approved. | Cabinet memo on the SMMEs and Co-operatives Funding Policy submitted to Minister for Cabinet approval. | SMMEs and Co-operatives Funding Policy approved, implemented and reported on. | SMMEs and Co-operatives Funding Policy implemented and reported on. | Target not achieved: SMMEs and Co-operatives Funding Policy not implemented and reported on. | The Department was requested to undertake further consultations. Through Ecosystem Development for Small Enterprises (EDSE), the Department secured the experts to assist the Department to undertake extensive consultations with the private sector. | The Department, together with the policy expert, will conduct extensive stakeholders consultation sessions in Quarter One (1) 2022/23. Once all the relevant stakeholders have been consulted, the Policy will be refined and finalised.

## Slide 16
Under-achievements for 2021/22 Q4
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
7 | Co-operatives supported financially. | Co-operatives supported to the value of the R’ million. | Co-operatives supported to the value of R88.6 million. | Co-operatives supported to the value of R25 million. | Target not achieved: No Co-operatives supported during the quarter. | Poor quality of applications received for Co-operatives Development Support Programme. | Redirect all non-compliant applications to Seda for business development support or non-financial support to make them funding-ready.
8 | National Small Enterprise Amendment Bill submitted to Parliament. | Approved submission to Minister on the National Small Enterprise Amendment Bill. | National Small Enterprise Amendment Bill taken through Parliamentary process. | National Small Enterprise Amendment Bill taken through Parliamentary process. | Target not achieved: National Small Enterprise Amendment Bill not taken through Parliamentary process. | The Department is still ensuring compliance to legislative processes – The Office of the Chief State Law Advisor (OCSLA) has informed the Department that Section 20(2) of the National Small Enterprise Act is unconstitutional and needs to be amended. | The Department will require guidance from the Office of State Attorneys to amend Section 20(2) of the Action – the Bill. The Department will obtain endorsement from the OCSLA on the Bill.
9 | Schedule to the National Small Enterprise Act (NSEA) amended. | Approved submission to Minister on the Schedule to the National Small Enterprise Act amended. | Revised Schedule to the National Small Enterprise Act amended and submitted to Minister for approval to gazette. | Revised Schedule to the National Small Enterprise Act amended and submitted to Minister for approval to gazette. | Target not achieved: Revised Schedule to the National Small Enterprise Act not amended and submitted to Minister for approval to gazette. | The OCSLA informed the Department that the 2019 update of the Schedule was unconstitutional and ultra-Vires, and that the Department must first have the 2019 Schedule set a side through an appropriate court before the Schedule can be updated. | The Department will initiate a process to have the 2019 update of the Schedule set aside through an appropriate court pending advise from the State Attorney.

## Slide 17
6. FINANCIAL REPORT

## Slide 18
2021/22 Q4 PROJECTION VS ACTUAL EXPENDITURE
Chart: R'000
| Q4 Actual Expenditure | Q4 Variance | Percentage variance
 | 423428 | -55893 | -0.15208
18
Notes: Cash flow projected R367.5 million

## Slide 19
2021/22 Q4 PERFOMANCE PER PROGRAMME
Chart: 
| Administration | Sector and Market Development | Development Finance | Enterprise Development






 | 16457 | 23691 | 253987 | 73400
 | 30919 | 52053 | 275438 | 65107
 | -14462 | -28362 | -21451 | 8293
Projections
Expenditure
Variance
19
Notes: % Spent
Prog 1: 187.9%
Prog 2: 219.7%
Prog 3: 108.4%
Prog 4: 88.7%
Total: 115.2%

## Slide 20
2021/22 PER PROGRAMME
Programme One- Administration
Expenditure for Quarter Four is R31.4 million against projection of R16.5 million resulting in an over expenditure of R14.5 million(87.9%) mainly due payment of outstanding invoices for operating leases (R7.8 million),Travel (R2 million), Legal costs(R209 thousand), Vodacom device payments(R768 thousand), these payments were Projected in previous quarters but only paid in Q4. Compensation of employees(R4 million) as a result of funds declared as savings not being drawn in the last month.
Programme Two – Sector Market and Development
Expenditure for Quarter Four is R51.9 million against projection of R23.7 million(219.7%) resulting in an over expenditure of R28.4 million(119.7%) mainly due to payments of the Product Markets claims (R23 million) projected in previous quarters, goods and services payments R4.6 million (payments of 2019/20 claims from seda for the China expo(R3 million) and Ethiopia expo(R1.6 million).
Programme Three – Development Finance
Expenditure for Quarter Four was R275.1 million against projection of R254 million resulting in an over expenditure of R21.5 million(8.5%) mainly due to payments for BBSDP(R7.3 million), Craft CSP (R7.5 million) due to projections in Q3 but payments in Q4. sefa youth challenge fund(R5.2 million) due to Budget reprioritisation in Q4, and CDSP realignment R1.6 million.
Programme Four – Enterprise Development
Expenditure for Quarter Four was R65.1 million against projection of R73.4 million resulting in an under expenditure of R8.3 million(8.4%) mainly due the Compensation of employees (R6.2 million) due to Vacancies and lower travel than projected(R2 million).
20

## Slide 21
2021/22 Q4 PERFOMANCE PER ECONOMIC CLASSIFICATION
Chart: R’000
| Compensation of employees | Goods and services | Interest | Financial Assets | Transfers and subsidies | Capital assets
Projections | 45035 | 24804 | 4 | 6 | 296197 | 1489
Expenditure | 35858 | 28511 | 357775 | 1279
Variance | 9177 | -3707 | 4 | 6 | -61578 | 210
21
Notes: % Spent
COE: 79.6%
G&S: 114.9%
Interest: 0.0%
Financial Assets: 0.0%
Transfers: 120.8%
Capital: 85.9%
Total: 115.2%

## Slide 22
2021/22 Q4 PER ECONOMIC CLASSIFICATION
Compensation of Employees – Expenditure for quarter four is R35.9 million (79.6%) against projection of R45 million resulting a variance of R9.2 million (20.4%) due to a vacancy rate of 16.2% (34 posts)
Goods and services – Expenditure for quarter four is R28.5 million (115%) against projection of R24.8 million resulting in an over expenditure of R3.7 million (-15%) largely due to payments for office accommodation for Ministerial offices, payments for Seda from the 201920 financial year for China expo and Ethiopia.
Transfers and subsidies - Expenditure for quarter four amounted to R358 million (126.5%) against projection of R296.2 million resulting in an overspending of R61.6 million (-26.5%) due to:
  processing of transfer payments in Q4 which were initially projected in Q2 and Q3 amounting to R61.9 million. Craft CSP (R7.5 million), BBSDP (R7.3 million), Product Markets (R23 million), Blended Finance (R5.2 million), IMEDP realignment (R17 million) and CDSP realignment (R1.6 million).
Machinery and Equipment – Expenditure for quarter four was R1.3 million (86%) against projection of R1.5 million resulting in an under expenditure of R210 thousand (14%) due to non delivery of computer equipment.
22

## Slide 23
AUDIT FINDINGS PROGRESS AS AT 31 March 2022
23
Area | Number of findings | Internal Control Deficiency | Progress
Incentives | 4 | BBSDP and CIS post investment site inspection not undertaken (2). IMEDP: No evidence of delivery of equipment. IMEDP: Applicants not meeting qualifying criteria. | BBSDP post investment site inspection not finalised – Seda assisting with the process IMEDP – evidence of delivery collected on 202122 deliveries AND all applicants met requirements
Provisions | 1 | Provision balances are accurately disclosed. | The provision note for Q1 and Q2 IFS were thoroughly reviewed and only the provision items were disclosed. BBSDP. Partial achievement
Internal Audit | 3 | No audit committee in place for 11 months of the financial year. Information system environment of the department not evaluated. External quality assurance review not performed. | Achieved. The Audit Committee is in place Note Achieved: The POPIA Assessment was completed in Q2. The ICT General controls review was conducted, and draft report issued. The closing meeting could not take place due to unavailability of the auditee representative. Not achieved. The appointment of service provider was not finalized following the Treasury advise to suspend procurement of services above R30000. A request for exemption was submitted to NT and the service provider will be appointed once approval is received.
Total | 8 |  | 

## Slide 24
7. HUMAN RESOURCE REPORT

## Slide 25
VACANCY RATE
KEY INDICATOR | TARGET | STATUS
Vacancy rate | 10% | Not Achieved - 16.2% (34/210)
Chart: VACANCY RATE
| APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR
 | 0.10577 | 0.12981 | 0.12019 | 0.125 | 0.12981 | 0.19231 | 0.13876 | 0.15789 | 0.15789 | 0.1619 | 0.1619 | 0.1619
Note: Termination (resignation and retirement) of 2 permanent staff during the quarter prevented a decrease of the vacancy rate.
Q4 and Annual Target < 10%

## Slide 26
WOMEN IN SENIOR POSITIONS
KEY INDICATOR | TARGET | STATUS
Women in SMS | 50% | Not Achieved – 47.1% (16/34)
Chart: WOMEN IN SMS
| APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR
 | 0.57143 | 0.57143 | 0.57143 | 0.57143 | 0.57143 | 0.5625 | 0.52778 | 0.5 | 0.5 | 0.5 | 0.47059 | 0.47059
Q4 and Annual Target at ≥50%
Note: Termination of 1 females in SMS and appointment of 1 male in SMS impacted representation.

## Slide 27
PERSONS WITH DISABILITIES
KEY INDICATOR | TARGET | STATUS
People with a disability | 3.2% | Target Exceeded 3.8% (7/182)
Chart: PERSONS WITH DISABILITIES
| APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR
 | 0.032558 | 0.033654 | 0.033333 | 0.034483 | 0.036458 | 0.034286 | 0.037234 | 0.038251 | 0.038674 | 0.038674 | 0.038889 | 0.038462
Q4 and Annual Target – 3.2%
Note: A slight increase in headcount (appointment of 1 permanent employee and 3 contract employees) impacted representation.

## Slide 28
8. OVERALL PERFORMANCE BY PROGRAMME

## Slide 29
PROGRAMME 1

## Slide 30
Overall Performance by Programme 1 – Administration
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
1. | Payment register. | % of valid creditors paid within 25 days. | 100% of valid creditors paid within 25 days. | 100% of valid creditors paid within 25 days | Target achieved: 100% of valid creditors paid within 25 days. | N/A | N/A
2. | Expenditure Report. | % variance on annual budget. | <5% variance on annual budget. | <5% variance on annual budget. | Target not achieved: 15.2% above Q4 projections. | Cashflow projection was R367.5 million, expenditure was R423.4 million resulting in overspending of R55.89 million. | Proper planning of projects by Project Managers and alignment of projections to expenditure.
3. | <10% vacancy rate. | Percentage vacancy rate in funded permanent posts. | <10% vacancy rate in funded permanent posts. | <10% vacancy rate in funded permanent posts. | Target not achieved: 16.2% vacancy rate in funded permanent posts. | 1. Moratorium implemented in August 2021. Although the moratorium was lifted for 17 posts, 17 posts are still under moratorium. 2. Two (2) permanent posts filled, however, termination of 2 permanent staff during the quarter prevented a decrease of the vacancy rate. 3. Under capacity in the Human Resource Unit leading to delays in filling of posts, increase workload within HR Administration (x2 officials). | Full lifting of the moratorium on posts, prioritise the finalization of the organizational structure, implementation of a recruitment plan and employment of additional resources in the Human Resources Unit of the Department.

## Slide 31
Overall Performance by Programme 1 – Administration
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
4. | ≥50% women in SMS employed. | Percentage of female SMS representation. | ≥ 50% of female SMS representation. | ≥ 50% of female SMS representation. | Target not achieved: 47.1% of female SMS representation. | Early retirement of one (1) woman employee in SMS and appointment of one (1) male employee in SMS during the quarter. | Filling of SMS posts in line with Employment Equity priorities.
5. | ≥3.2% representation of PWDs. | Percentage representation of PWDs. | ≥3.2% representation of PWDs. | ≥3.2% representation of PWDs. | Target achieved: 3.8% representation of PWDs. | N/A | N/A
6. | DSBD and its Agencies’ public engagement programmes implemented in District Municipalities. | Number of DSBD and its Agencies’ public engagement programmes implemented in District Municipalities. | 24 DSBD and its Agencies’ public engagement programmes implemented in District Municipalities. | 6 DSBD and its Agencies’ public engagement programmes implemented in District Municipalities. | Target achieved: 33 DSBD and its Agencies’ public engagement Programmes implemented in District Municipalities. | The Department in partnership with its agencies and District Municipalities distributed working materials / equipment to various informal traders through the Informal and Micro-Enterprise Development Programme (IMEDP). The Department and its agencies also embarked on a country wide product and programmes awareness campaign (Roadshows and Partnership Dialogues) for SMMEs and Co-operatives in District Municipalities. | N/A

## Slide 32
Overall Performance by Programme 1 – Administration
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
7. | Phase 3: SMME Database implemented. | SMME Database – Key Trade Exchange Platform integrated and enhanced reporting implemented. | Phase 3: SMME Database – Key Trade Exchange Platform integrated and enhanced reporting implemented. | Phase 3: SMME Database – Key Trade Exchange Platform integrated and enhanced reporting implemented. | Target achieved: Phase 3: SMME Database – Key Trade Exchange Platform integrated and enhanced reporting implemented. | N/A | N/A

## Slide 33
PROGRAMME 2

## Slide 34
Overall Performance by Programme 2 –
Sector and Market Development
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
1. | Products Produced and services rendered by SMMEs and Co-operatives linked to market. | Number of products produced and services rendered by SMMEs and Co-operatives linked to market. | 250 products produced and services rendered by SMMEs and Co-operatives linked to market. | 50 products produced and services rendered by SMMEs and Co-operatives linked to market. | Target exceeded: 52 products produced and services rendered by SMMEs and Co-operatives linked to market. | DSBD introduced more products and services to retailers in order to give retailers a larger variety and increase opportunities to list SMMEs and Co-operatives. | N/A
2. | Women-owned enterprises monitored to participate on SheTradesZA platform. | Number of women-owned enterprises monitored to participate on SheTradesZA platform. | 2 000 women-owned Enterprises monitored to participate on SheTradesZA platform. | 500 women-owned enterprises monitored to participate on SheTradesZA platform. | Target not achieved: 268 women-owned Enterprises monitored to participate on SheTradesZA platform. | Low registration of women-owned enterprise in the SheTradesZA Hub. | The Department will prioritise implementing a media and marketing plan and budget aimed at popularizing the programme during the 2022/23 financial year.
3. | SMMEs and Co-operatives exposed to international market opportunities. | Number of SMMEs and Co-operatives exposed to international market opportunities. | 200 SMMEs and Co-operatives exposed to international market opportunities. | 50 SMMEs and Co-operatives exposed to international market opportunities. | Target achieved: 55 SMMEs and Co-operatives exposed to international market opportunities. | The SBD Portfolio participated in more events to catch-up with the previous quarters’ achievement. | N/A

## Slide 35
Overall Performance by Programme 2 –
Sector and Market Development
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
4. | Approved SMMEs Development Index Survey report. | Annual Report on the participation of SMMEs and Co-operatives in economic sectors approved by EXCO. | Annual Report on the contribution to jobs by SMMEs and Co-operatives in economic sectors approved by EXCO. | Annual Report on the contribution to jobs by SMMEs and Co-operatives in economic sectors approved by EXCO. | Target achieved: Annual Report on the contribution to jobs by SMMEs and Co-operatives in economic sectors approved by EXCO. | N/A | N/A
5. | Approved SMMEs Development Index Survey report. | SMMEs Development Index Survey report produced. | SMMEs Development Index Survey report approved by EXCO. | SMMEs Development Index Survey report approved by EXCO. | Target achieved: SMMEs Development Index Survey report approved by EXCO. | N/A | N/A
6. | Incubation Support Programme evaluation conducted. | Incubation Support Programme evaluation approved by EXCO. | Incubation Support Programme (ISP) evaluation conducted and approved by EXCO. | Incubation Support Programme (ISP) evaluation conducted and approved by EXCO. | Target not achieved: Incubation Support Programme (ISP) evaluation not conducted and approved by EXCO. | Request for single source Government Technical Advisory Centre (GTAC) declined by Treasury and therefore the evaluation did not proceed. | The process to be initiated again in the new financial year.

## Slide 36
PROGRAMME 3

## Slide 37
Overall Performance by Programme 3 –
Development Finance
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
1. | SMMEs and Co-operatives Funding Policy approved. | Cabinet memo on the SMMEs and Co-operatives Funding Policy submitted to Minister for Cabinet approval. | SMMEs and Co-operatives Funding Policy approved, implemented and reported on. | SMMEs and Co-operatives Funding Policy implemented and reported on. | Target not achieved: SMMEs and Co-operatives Funding Policy not implemented and reported on. | The Department was requested to undertake further consultations. Through Ecosystem Development for Small Enterprises (EDSE), the Department secured the experts to assist the Department to undertake extensive consultations with the private sector. | The Department, together with the policy expert, will conduct extensive stakeholders consultation sessions in Quarter One (1) 2022/23. Once all the relevant stakeholders have been consulted, the Policy will be refined and finalised.
2. | Co-operatives supported financially. | Co-operatives supported to the value of the R’ million. | Co-operatives supported to the value of R88.6 million. | Co-operatives supported to the value of R25 million. | Target not achieved: No Co-operatives supported during the quarter. | Poor quality of applications received for Co-operatives Development Support Programme. | Re-direct all non-compliant applications to Seda for business development support or non-financial support to make them funding-ready.
3. | Township and Rural Enterprises supported financially. | Township and Rural Enterprises supported to the value of the R’ million. | Township and Rural Enterprises supported to the value of R694 million. | Township and Rural Enterprises supported to the value of R69.4 million. | Township and Rural Enterprises supported to the value of R177.7 million. | Due to the fast-tracking of online processing that resulted in an increase in the number of approvals and disbursements. | N/A

## Slide 38
Overall Performance by Programme 3 –
Development Finance
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
4. | SMMEs and Co-operatives in the Craft Sector supported through Craft Customised Sector Programme. | Number of Crafters supported through the Craft Customised Sector Programme. | 800 Crafters supported through the Craft Customised Sector Programme. | 300 Crafters supported through the Craft Customised Sector Programme. | 384 Crafters supported through the Craft Customised Sector Programme | To catch-up with the previous quarters’ achievement. | N/A
5. | Start-up youth businesses supported financially and non-financially. | Number of start-up youth businesses supported financially and non-financially. | 5 000 start-up youth businesses supported financially and non-financially. | 1 500 start-up youth businesses supported financially and non-financially. | 6 315 start-up youth businesses supported financially and non-financially. | The SBD Portfolio supported more youth start-ups as part of mainstreaming youth support across all Portfolio interventions. | N/A
6. | Consolidated report on supported Competitive SMMEs and Co-operatives produced. | Consolidated report on the number of competitive SMMEs and Co-operatives supported approved by EXCO. | Consolidated report on the 25 000 competitive SMMEs and Co-operatives supported approved by EXCO. | Report on the 8 000 competitive SMMEs and Co-operatives supported. Consolidated report on the 25 000 competitive SMMEs and Co-operatives supported approved by EXCO. | Report on the 13 800 competitive SMMEs and Co-operatives supported. Consolidated report on the 70 063 competitive SMMEs and Co-operatives supported approved by EXCO. | The quarterly target was exceeded by 5 800, and the annual target was exceeded by 45 063. The major contributor to the variance is the number of clients that were assisted through sefa and Seda support programmes due to increased demand to support SMMEs and Co-operatives that were adversely impacted by the July 2021 unrest in KwaZulu-Natal and Gauteng provinces. | N/A

## Slide 39
PROGRAMME 4

## Slide 40
Overall Performance by Programme 4 –
Enterprise Development
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
1. | National Integrated Small Enterprise Development Masterplan submitted to Cabinet. | Cabinet memo on the National Integrated Small Enterprise Development Masterplan submitted to Minister for Cabinet approval. | National Integrated Small Enterprise Development Masterplan submitted to Minister for Cabinet approval. | National Integrated Small Enterprise Development Masterplan submitted to Minister for Cabinet approval. | Target achieved: National Integrated Small Enterprise Development Masterplan submitted to Minister for Cabinet approval. | N/A | N/A
2. | National Small Enterprise Amendment Bill submitted to Parliament. | Approved submission to Minister on the National Small Enterprise Amendment Bill. | National Small Enterprise Amendment Bill taken through Parliamentary process. | National Small Enterprise Amendment Bill taken through Parliamentary process. | Target not achieved: National Small Enterprise Amendment Bill not taken through Parliamentary process. | The Department is still ensuring compliance to legislative processes – The Office of the Chief State Law Advisor (OCSLA) has informed the Department that Section 20(2) of the National Small Enterprise Act is unconstitutional and needs to be amended. | The Department will require guidance from the Office of State Attorneys to amend Section 20(2) of the Action – the Bill. The Department will obtain endorsement from the OCSLA on the Bill.
3. | Schedule to the National Small Enterprise Act (NSEA) amended. | Approved submission to Minister on the Schedule to the National Small Enterprise Act amended. | Revised Schedule to the National Small Enterprise Act amended and submitted to Minister for approval to gazette. | Revised Schedule to the National Small Enterprise Act amended and submitted to Minister for approval to gazette. | Target not achieved: Revised Schedule to the National Small Enterprise Act not amended and submitted to Minister for approval to gazette. | The OCSLA informed the Department that the 2019 update of the Schedule was unconstitutional and ultra-Vires, and that the Department must first have the 2019 Schedule set a side through an appropriate court before the Schedule can be updated. | The Department will initiate a process to have the 2019 update of the Schedule set aside through an appropriate court pending advise from the State Attorney.

## Slide 41
Overall Performance by Programme 4 –
Enterprise Development
No. | Output | Output Indicator | Annual target | Q4 milestone | actual output | Reason For Deviation | Corrective Measures
4. | Red-Tape Reduction Action Plan developed and Implemented. | Number of districts assisted through the Red-Tape Reduction Action Plan. | Three (3) districts assisted through the Red-Tape Reduction Action Plan. | Implementation and Monitoring of the performance outcomes of the interventions. | Target achieved: Implementation and Monitoring of the performance outcomes of the interventions was done. | N/A | N/A

## Slide 42
9. RECOMMENDATION

## Slide 43
RECOMMENDATION
It is recommended that the Portfolio Committee on Small Business Development adopts the 2021/22 Quarter Four Performance Report of the Department of Small Business Development.

## Slide 44
Thank You!
Thank You!