## Slide 1: PROGRESS REPORT TO THE PRESIDENTIAL TASK TEAM ON MILITARY VETERANS REGARDING THE ADVANCEMENT OF MILITARY VETERANS’ AFFAIRS AS AT 30 APRIL 2022

## Slide 2: DMV’S CAPACITY TO DISBURSE BENEFITS AS CONTEMPLATED IN SEC 11 OF THE MILITARY VETERANS ACT
The DMV faces capacity challenges in terms of disbursing Sec 11 benefits.
There DMV appears to have deviated in its legislative mandate which requires the organization to coordinate and set policy standards regarding the advancement of military veterans’ affairs. The DMV has positioned itself as an implementing agency. However, this problem is being addressed through the Organisational Re-design work-stream.

## Slide 3: THE IMPACT OF WORK-STREAMS ON THE DMV
The work-streams are an invaluable source of capacity and innovation to the DMV – given their respective purposes, objectives and planned milestones.
A disciplinary process will soon be embarked upon to address non-delivery by the identified DMV officials who were instructed to coordinate the activities of the Socio-Economic Support work-stream.

## Slide 4: ON WHAT LEVELS ARE THEY AND FROM WHERE IN THE ORGANISATIONAL STRUCTURE ARE THEY DEPLOYED?
EMPLOYEE | RACE | GENDER | SALARY LEVEL | RANK | BRANCH / OFFICE | DATE OF SUSPENSION
1 | B | F | 15 | DDG: ESM | Empowerment and Stakeholder Management | 2021/08/04
2 | B | M | 14 | Chief Director: MV Skills and Empowerment | Skills Empowerment | 2021/08/04
3 | B | M | 14 | Chief Financial Officer | Financial Management | 2021/08/19
4 | B | M | 14 | Chief Director: Provincial Office Management | Provincial Office and Stakeholder Management | 2021/08/05

## Slide 5: TYPE OF TRANSGRESSIONS
EMPLOYEE | CURRENT STATUS
1 | Allegations relating to: Gross dereliction of duties, Gross insubordination, Gross negligence, Absenteeism, Disregard for policies and processes, Fruitless and wasteful expenditure, Contravention with the PFMA
2 | Allegations relating to: Contravention with ESM Policy, Dereliction of duty, Fraudulent misrepresentation, Contravention with PFMA Failure to carry out lawful instruction Insubordination Gross dishonesty Contravention with PSA

## Slide 6: TYPE OF TRANSGRESSIONS (continues)
EMPLOYEE | CURRENT STATUS
3 | Allegations relating to: Disregard for policies and processes, Fruitless and wasteful expenditure, Contravention with the PFMA Insubordination, Mismanagement, Failure to perform in a level of CFO
4 | Allegations relating to: Gross insubordination, Poor performance, Disregard for policies and processes Failure to comply with PMDS Policy

## Slide 7: PROGRESS REGARADING THE DISCIPLINARY PROCESS
EMPLOYEE | CURRENT STATUS
1 | Investigation completed and the employee was formally charged by the department. The matter sat on 18 February 2022. The chairperson instructed that the matter should be finalised by the 30th and 31st of March 2022
2 | Investigation completed and the employee was formally charged. The matter set on 22 November 2021 however it was postponed to 12-13 April 2022 because the employee was requesting information including laptop from the depart to use it for his defence.
3 | Investigation completed and the employee was formally charged by the department. The matter scheduled to sit on 25 February 2022 however postponed to 6-8 April 2022 due to non-avaliability of the employee and the initiator.
4 | Investigation completed and the employee was formally charged by the department. The matter sat on 31 January 2022 however it was postponed to 10 March 2022. The matter was postponed because the Initiator has withdrawn, new date has been was set for 28 March 2022.

## Slide 8: IMPROVING SERVICE DELIVERY
INTEGRATED BENEFITS MANAGEMENT SYSTEM | PROGRESS AS AT MARCH 2022 | TIMEFRAME
In the 2020/21 FY the DMV had planned to create an automated database of military veterans and implement a benefit management system to streamline its delivery of benefits, and improve credibility, integrity and security of the register of military veterans. | The DMV entered into agreement with SITA for development and Implementation of the Integrated Database Management System (IDMS) through a signed proposal. Business requirements specifications were defined for the Registration, Basic and Tertiary Education, Healthcare, Counselling & Treatment, Burial Support & Honouring, Housing, Compensation and Payment modules. Roll-out of automated benefits Implementation of Education module Healthcare, Counselling & Treatment, Burial Support & Honouring and Compensation Transport and Pension, Facilitation of business opportunities Facilitation of employment and Training and Skills development and final Go-live of the IDMS During the roll-out process, only DMV support staff will access the system. The Military Veterans will be able to access the automated benefits as from 01/10/2022 | 23/09/2021 01/04/2022 01/06/2022 01/07/2022 01/10/2022 01/10/2022

## Slide 9: Who, in terms of the Military Veterans Act, is designated to establish SANMVA?
Sec 7(1)(a) of the Military Veterans Act, 18 of 2011, prescribes that:
“The Director-General must as soon as possible after commencement of this Act establish a body which is to be an association representing military veterans’ organisations nationally.”
Sec 7(1)(b) of the Military Veterans Act, 18 of 2011, prescribes that:
“The Minister must publish the date of establishment by notice of Gazette.”
Sec 7(2) of the Military Veterans Act, 18 of 2011, prescribes that:
“The Director-General must in conjunction with military veterans’ organisations create mechanisms to ensure that the association serves as an umbrella structure representing military veterans’ organisations.”
Sec 7(3) of the Military Veterans Act, 18 of 2011, prescribes that:
“The mechanisms contemplated in subsection (2) must at least result in the association-
Representing military veterans’ organisations in a fair manner;
Conducting its business in a fair manner;
Holding free, fair and regular elections;
At least once a year reporting to the Minister on its activities.”

## Slide 10: In law, who must perform the duties of SANMVA when SANMVA is not operational?
Sec 7(4)(a) of the Military Veterans Act, 18 of 2011 prescribes that:
“A military veterans’ organisation is not obliged to join SANMVA.”
Sec 7(4)(b) of the Military Veterans Act, 18 of 2011 prescribes that:
“A military veterans’ organisation contemplated in paragraph (a) may engage the Minister or other persons or structures established or referred to in this Act, provided such organization is recognised by the Minister as a non-governmental organization or association established in respect of military veterans that lawfully represents the interests of military veterans.”
Sec 8(1) of the Military Veterans Act, 18 of 2011 prescribes that “the association must-
perform the functions provided for in this Act;
Advise the Minister on such matters relating to legislation and policy affecting military veterans as the Minister may require; and
Advise the Minister or the Director-General on any other matter relating to the affairs of military veterans that the Minister or the Director-General may require”

## Slide 11: What plans have been put in place to install SANMVA?
A funding model has been finalised to support SANMVA when it goes to its elective conference.
There is dedicated personnel in the DMV tasked with assisting SANMVA to go to its elective conference, planned for April 2022.
Note: The MK unity conference is planned for April 2022, and there is dedicated personnel in the DMV to assist this process.

## Slide 12
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | DMV PROGRESS AS AT 24 FEBRUARY 2022 | TIMEFRAME
EDUCATION SUPPORT (SOCIO-ECONOMIC SUPPORT) | Education Support | The Department has received feedback from National Treasury on the review of the education support threshold for the academic year 2022. The revised threshold is as follows: Grade R – 7 is R30 000 per annum Grade 8- 12 is R35 000 National Treasury advised aligning of tertiary tuition fees to the current NSFAS/ DHET approved amounts. Approved beneficiaries in 2021 Basic education: 2 650 Tertiary: 552 Decline 214 Reasons: reached their years of support post graduate studies 2022 academic year intake: Basic education: Total applied2 272 Approved 1862 Decline 43 Military veterans not registered on the DMV Database - Post graduate studies: 15 Pending 367( Unabridged birth certificate and latest results) Tertiary: Total applied 514 Approved: 500 | 31 March 2022

## Slide 13
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | DMV PROGRESS AS AT 24 FEBRUARY 2022 | TIMEFRAME
EDUCATION SUPPORT (SOCIO-ECONOMIC SUPPORT) | Education Support | The team has not concluded the adjudication process required for awarding support. This is due to The Department has started paying of tuition fees for 2022 for both continuing and new approved beneficiaries. 5 beneficiaries have been placed within DMV namely: 1 X KZN office 1 X WC office 1 X GP office 2 X HQ at database and Education support A plan is underway to place 18 previously supported students as interns in all 9 provincial offices to support the provincial offices to deal with education support. GRADUATES There will be some beneficiaries supported by the DMV who will be graduating during the upcoming season in April 2022. Amongst them are: medical doctors; engineers and lawyers. | 31 March 2022

## Slide 14
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | STUDY FIELDS: PROGRESS AS AT 24 FEBRUARY 2022 | TIMEFRAME
EDUCATION SUPPORT (SOCIO-ECONOMIC SUPPORT) | Education Support | Disciplines of studies: Science –Molecular and Life Sciences, Human physiology; Agricultural Science; Environmental science, plant and animal reproduction Health Sciences – MBCHB, MEDICAL LABORATORY SCIENCES, Physiotherapy, Nursing, forensic science and technology, Pharmacy, emergency medical care Commerce – Accounting, Financial and Business Management, chemical Engineering – Mechanical, Mining, civil, electrical, electrical infrastructure construction Humanities – Social Science, Marketing Management, Arts, Education; Psychology, Dramatic, Industrial and Organisational psychology, political science, child development, local government law and administration, Public Relations, Human Resources, public administration IT – Computer science, Business informatics Law - LLB Fashion Tourism Food Technology Security – Safety and security management, police Property and real estate Banking – Investment and Corporate finance Music Film - VIDEO TECHNOLOGY Pilot Mathematics | On-going

## Slide 15: SKILLS DEVELOPMENT: ICT TRAINING
ICT Skills Training to Military Veterans and their dependents | PROGRESS AS AT MARCH 2022 | TIMEFRAME
In 2022/23 the DMV planned to train 10 000 Military Veterans and their dependents in ICT Skills from February 2022 to 31 March 2024. | The DMV entered into agreement with SITA for the development of MVs and depetheir dependents ICT skills for ability to interact with the Integrated Database Management System (IDMS), to be capable ICT users and access the benefits with ease, for employability and entrepreneurship through a signed proposal. To date SITA through its partner the National Electronic Media Institute of South Africa (NEMISA) has provided digital literacy training to the following MVs and dependents: | February 2022 to March 2024

## Slide 16
Weeks |  | Colab | Province | Venue |  |  | Beneficiaries attended training
21-25 Feb 2022 |  | Vaal University of Technology | Gauteng | VUT Main Campus, Vanderbijlpark |  |  | 77
28 Feb-4 March 2022 |  | Vaal University of Technology | Gauteng | VUT Main Campus, Vanderbijlpark |  |  | 80
 |  | Northwest west University | Northwest | Mafikeng Campus |  |  | 47
7 Mar – 12 Mar 2022 |  | Vaal University of Technology | Gauteng | VUT Main Campus Vanderbijlpark |  |  | 120
 |  | University of Mpumalanga | Mpumalanga | Mbombela Campus Building 5 |  |  | 43
 |  | University of Limpopo | Limpopo | UL Main Campus Turfloop |  |  | 60
 |  | University of Western Cape | Western Cape | Community women Action Van Riebeek road, Eerte Rivier |  |  | 18
 |  |  |  | Manenberg People’s Centre Thames Avenue |  |  | 20
 |  |  |  | Bosasa Community Hall |  |  | 17
 |  | University of Northwest | Northwest | Kismet Community Hall |  |  | 50
 |  |  |  |  | 532 |  | 

## Slide 17
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | PROGRESS AS AT 24 FEBRUARY 2022 | TIMEFRAME
SKILLS & EMPOWERMENT | Socio-Economic Integration. Military veterans must participate in socio economic activities | The Department of Military Veterans (DMV) has partnered with the State Information Technology Agency (SITA) for the development and implementation of the Integrated Database Management System (IDMS) and the provision of ICT Training programmes to the Military Veterans and their dependents. Partnership with SITA and the National Electronic Media Institute of South Africa (NEMISA) to provide Digital Literacy to the 5000 military veterans and their dependents. A total of 10 000 is the target for this project. This also involves partnership with Microsoft for provision the computer literacy skills to the MVs and dependents, as per the Act. The programme focuses on digital literacy and technical ICT skills. TVET colleges and universities Partnership with MTN for provision of Tools of Trade. Military veterans will receive certificates upon completion of their training. Digital literacy training for 10 000 military veterans will assist them in the successful navigation of the IT space and enable them to be proficient in MS Office. Digital Literacy Training - Focusing on the applications received from the Military Veterans (21 February 2022 to 31 March 2022). Includes profiling of MVs for skills development. On 21 March 2022, 80 military veterans started the IT training course and they have graduated at the Vaal University of Technology. | Feb 2022

## Slide 18
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | PROGRESS AS AT 24 FEBRUARY 2022 | TIMEFRAME
SKILLS & EMPOWERMENT | Socio-Economic Integration. Military veterans must participate in socio economic activities | The model of empowerment includes skills development that is linked to the Government Programme of Action to advance Infrastructure, Agriculture, Safety and Security, Poverty Alleviation, Business Entrepreneurship and Cooperatives. This will be carried out in accordance with the DMV’s strategic objective of creating strategic partnerships with inter alia, Sector Training Authorities (SETAs), Technical and Vocational Education and Training (TVET) colleges, Small Enterprise Development Agency (SEDA), the Small Enterprise Finance Agency (SEFA) Agri-SETA and SITA (in terms of ICT training). Government department and provinces are beginning to report on interventions done for Military Veterans. Our provincial offices continuously advise Military Veterans on programmes that have an exit strategy. The DMV has engaged various organisations seeking partnerships (MICT SETA; LGSETA; SASSETA; SERVICES SETA; CONSTRUCTION SETA; AGRI-SETA AND SITA) Budget has been set aside to support training of military veterans through SETAs. Upon completion of their training they will be provided with tools-of-trade. On the job training (i.e., regarding infrastructure) will be in collaboration with the DOD (i.e., Engineering Corps). | Jan 2022

## Slide 19
# | ISSUES RAISED BY MILITARY VETERANS AND THE CONSENSUS DOCUMENT | DMV PROGRESS TO DATE AS AT 15 FEBRUARY 2022
HOUSING (CONTINUED) | Decent Houses | 2 131 Military Veterans have been provided with houses during the period 2015/16 – 2021/22. Gauteng province accounts for most houses delivered and. KZN is the worst performing province of total housing provision. Houses provided to Military Veterans from 2015/16 – 2020/21 per province as follows:-

## Slide 20: Thank You