## Slide 1: A REPORT ON THE PERFORMANCE OF THE Informal settlements upgrading PARTNERSHIP GRANT (ISUPG)
Select Committee on Appropriation
10 August 2022

## Slide 2: PRESENTATION OUTLINE
Purpose of the presentation
Background and context
Implementation of informal settlements upgrading programme
Informal Settlements Upgrading Partnership Grant (ISUPG) performance
Recommendations

## Slide 3: PURPOSE
To present the implementation of the Upgrading of Informal Settlements Programme (UISP)
To present the performance of the Informal Settlements Upgrading Partnership Grant (ISUPG)

## Slide 4: Background & Context
The framework for the upgrading of informal settlements is defined in the following…
  Upgrading of Informal Settlements Programme (UISP) that outlines the upgrading processes, outputs, as well as roles and responsibilities of the three spheres of government
  The ISUPG Framework describes the grant parameters and conditions for accessing the grant
  Informal Settlements Partnership Grant (ISUPG) that is used to buy the outputs outlined in the approved annual business plan
ISUPG started in July 2021 for both provinces and metropolitan municipalities. Therefore, the 2021/22 financial year was the first year of implementation
In the informal settlements upgrading an incremental approach has been adopted

## Slide 5: Background & Context
WHERE DO WE COME FROM
Focus on housing instead of implementing UISP
Moving from upgrading plans to implementation
More funds spent on rudimentary services without any plans for permanent solution
Lack of understanding of UISP & ISUPG
Lack of pipeline planning
Lack of understanding of infrastructure planning
MTSF 2019 – 2024 TARGETS
1500 informal settlements upgraded to phase 3 of UISP by 2024

## Slide 6: Background & Context: Informal Settlements
PROVINCE | NUMBER OF INFORMAL SETTLEMENTS
Eastern Cape | 481
Free State | 161
Gauteng | 731
KwaZulu-Natal | 740
Limpopo | 74
Mpumalanga | 368
Northern Cape | 151
North West | 136
Western Cape | 763
TOTAL | 3605
METROPOLITAN MUNICIPALITY | NUMBER OF INFORMAL SETTLEMENTS
Buffalo City | 154
City of Cape Town | 464
City of Ekurhuleni | 119
City of Johannesburg | 210
City of Tshwane | 186
EThekwini | 530
Mangaung | 47
Nelson Mandela Bay | 94
Total | 1804
About 50% of these informal settlements are in metropolitan municipalities

## Slide 7: Overall Achievements
Established a baseline for informal settlements upgrading
Established a dashboard on informal settlements
Establishment of a framework for monitoring and reporting performance
  Project based reporting
  Direct relationship between business plans and reporting
Three levels of monitoring
  Programme performance (are we achieving the envisages objectives and outcomes of UISP)
  Grant nonfinancial performance (what has been bought)
  Grant expenditure (how much has been spent)
Provincial & municipal engagements and support on upgrading of informal settlements institutionalised
Systematising informal settlements upgrading in line with UISP
Redefining the upgrading outputs
Establishment of a dashboard for Informal settlements in partnership with the Housing Development Agency
Moving towards digitalisation of planning and reporting
By the end of 2021/22 financial 1284 informal settlements were in various stages of upgrading

## Slide 8: UISP Phase 1: Prefeasibility
KPA | Outputs/ Activities
Number of prefeasibility studies | Social Facilitation
 | Prefeasibility studies. These include… Determine land ownership Initial scoping & geotechnical suitability Desktop environment scoping Geographic location Availability of amenities and transport routes Estimation of number of households
The main output of this phase is a draft or indicative upgrading plan and an estimated cost of upgrading the settlement. It is expected that the community is part of this process

## Slide 9: UISP Phase 2: Preplanning Studies, Detailed Planning Design, Land, Bulk and Interim Services
KPA | Outputs /Activities
Pre-Planning / Feasibility Studies | EIA Application
 | Traffic Impact Study
 | Geotechnical investigation
 | Surveying and registration of households in the settlement
 | Township Layout Plan
 | Pegging and approval of General Plan
 | Township Register Opened
 | Infrastructure (Engineering) Services Report
Land | Land Assembly (excluding Acquisition)
 | Land Acquisition
Bulk Infrastructure | Bulk Infrastructure
Detailed Planning Design | Water
 | Sewer
 | Roads and Storm water
 | Electricity
Interim Services | Water
 | Sanitation
 | Roads and Storm Water
 | Electricity
While realising all the requirements for township proclamation as well as ensuring the construction of required bulk infrastructure, interim services must also be provided
At this stage informal settlements are provided with a human rights package

## Slide 10: UISP Phase 3 - Permanent Municipal Engineering Services
KPA | Outputs /Activities
Permanent Municipal Engineering Services | Water services
 | Sanitation solutions
 | Roads and storm water
 | Electricity
Social and Economic Amenities | Social and Economic Amenities
Conveyancing | Conveyancing (Issuing of Title Deeds)
Expected changes in each informal settlement after completion of Phase 3 | Expected changes in the informal settlements
Site level (Household) | Serviced sites: (reticulation) Water Sanitation Solution Electricity/Energy Source Title deeds registered
Settlement level (Community) | Storm Water Drainage; Roads; Public Lighting; Public Spaces; Essential amenities Proclamation of the township
However, the challenges of providing a title deed at this stage might limit access to housing subsidy

## Slide 11: OUTPUTS DEFINED IN THE ISUPG GRANT FRAMEWORK INLINE WITH UISP
Phase 1: | Phase 2 | Phase 3
Number of prefeasibility studies | Preplanning/ Feasibility Studies Number of environmental studies undertaken Number of geotechnical studies conducted Number of any relevant studies other relevant studies conducted Land Acquisition Hectares of land acquired for in-situ upgrading Hectares of land acquired for relocation Hectares of land transferred and registered Hectares of land availed in terms of land availability development agreement Bulk Infrastructure Number of settlements supplied / to be supplied with bulk infrastructure Interim Services Number of settlements benefitting from interim municipal engineering services and/or any alternative technology Rudimentary services Number of settlements provided with rudimentary services | Number of settlements provided with municipal engineering services and/or any alternative technology Number of serviced sites developed Number of social and / economic amenities. The specific types of amenities must only be provided in collaboration municipality and the community Number of sites transferred to end uses Number of households provided with secure tenure Number of engineering designs, water sewer, roads, and storm water drainage concluded Number of layout plans approved

## Slide 12: INFORMAL SETTLEMENTS UPGRADING nonfinancial PERFORMANCE: provinces & METROPOLITAN MUNICIPALITIES

## Slide 13: 2021/22 UISP Annual Provincial Performance
Province | Phase 1 | Phase 2 | Phase 3 | Completed Phase 3
Eastern Cape | 19 | 89 | 11 | 0
Free State | 3 | 15 | 19 | 2
Gauteng | 37 | 36 | 0 | 0
KwaZulu-Natal | 64 | 50 | 23 | 0
Limpopo | 5 | 5 | 17 | 4
Mpumalanga | 1 | 24 | 10 | 0
Northern Cape | 1 | 14 | 19 | 4
North West | 11 | 49 | 22 | 0
Western Cape | 24 | 27 | 15 | 10
 | 165 | 309 | 136 | 20
Reported performance is for 01 April 2021 – 31 March 2022
Performance in informal settlements is reported using various milestones defined in each Phase of UISP
In the 2021/22 financial year 610 informal settlements were upgraded using Phases 1 – 3 of UISP as an indicator of performance and a manual for the required outputs/activities

## Slide 14: Serviced Sites Delivered by Provinces in 2021/22 FY
Province | Serviced Sites | Informal Settlements with Layout plans
Eastern Cape | 0 | 5
Free State | 2282 | 0
Gauteng | 0 | 0
KwaZulu-Natal | 5198 | 0
Limpopo | 2184 | 4
Mpumalanga | 1485 | 8
Northern Cape | 1083 | 14
North West | 6723 | 22
Western Cape | 2120 | 10
TOTAL | 21 075 | 63
When serviced sites are completed it mean electricity, water and sanitation solutions are all provided per household or at site level. These services are often provided incrementally

## Slide 15: 2021/22 UISP NATIONAL PERFORMANCE
Metropolitan Municipality | Phase 1 | Phase 2 | Phase 3 | Completed Phase 3
Buffalo City | 0 | 13 | 37 | 0
City of Cape Town | 18 | 12 | 18 | 0
City of Ekurhuleni | 40 | 15 | 27 | 0
City of Johannesburg | 45 | 16 | 0 | 0
City of Tshwane | 25 | 13 | 37 | 2
Ethekwini | 0 | 217 | 21 | 0
Mangaung Metro | 0 | 0 | 19 | 0
Nelson Mandela Bay | 9 | 80 | 12 | 0
TOTAL | 137 | 366 | 171 | 2
In the 2021 financial year, 674 informal settlements were upgraded by Metropolitan Municipalities

## Slide 16: SERVICED SITES DELIVERED IN 2021/22 FY
Metropolitan Municipality | Serviced Sites Completed | Informal Settlements with Approved Layout Plans
Buffalo City | 255 | 0
City of Cape Town | 945 | 0
City of Johannesburg | 0 | 0
City of Tshwane | 1584 | 0
Ekurhuleni | 0 | 0
Ethekwini | 662 | 0
Mangaung | 0 | 0
Nelson Mandela Bay | 150 | 0
TOTAL | 3596 | 0

## Slide 17: Informal Settlements Upgrading
Relocation site for several informal Settlements in Ekurhuleni
Ruby Club at CoJ. General Plan has been approved. Households provided with electricity

## Slide 18: Informal Settlements Upgrading
Layout Plan
Site within a residential area

## Slide 19: Eastern Cape 2022/23 Q1 Performance: Phase 1
Key Performance Area | Planned Outputs /activities | Number of informal settlements | Number of Outputs | Progress/ Achievement | Challenges | Remedial Work
Number of prefeasibility studies | Social facilitation | 112 | 112 | The work is only starting in quarter 2 | None | None

## Slide 20: Eastern Cape 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Progress / Achievement | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 30 | 30 | All projects are at procurement stage | SCM challenges | Appointment of contractors will be concluded through the appointment of Project resource Teams
 | Sanitation solution | 30 | 30 |  |  | 
 | Roads and storm water | 30 | 30 |  |  | 

## Slide 21: Free State 2022/23 Q1 Performance: Phase 1
Key Performance Area | Planned Outputs /activities | Number of informal settlements | Number of Outputs | Achievements / Progress | Challenges | Remedial Action
Number of prefeasibility studies | Social facilitation | 12 | 12 | 9 = 0% completed still at procurement phase No community meeting has taken place to date. 1 = 50% completed through HDA The compact was done internally by officials from HDA with no expenses incurred on the exercise. 1 = 70% completed through HDA The compact was done internally by officials from HDA with no expenses incurred on the exercise | 4 projects has Procurement committees disbanded The municipality only agreed on proceeding with the projects in May 2022 | Urgent appointment of procurement committees' members Funds will be redirected to other performing projects during the review process.

## Slide 22: Free State 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Achievements / Progress | Challenges | Remedial Action
Pre-Planning Studies | EIA Application | 14 | 14 | 95 % no progress 2 settlements received environmental authorisation 3 sites awaiting DESTEA 2 awaiting approval of SG diagramme 1 has first draft township layout circulated for comments | Long time that is taken to get final land development planning approvals There are disputes with community regarding the size of erven versus the approved layout plan | Constant interaction with DESTEA Matter of erven size has been taken to court has bigger sites were allocated fraudulently
 | Traffic Impact Study | 10 | 10 |  |  | 
 | Geotechnical investigation | 12 | 12 |  |  | 
 | Land Scoping/ Surveying | 8 | 8 |  |  | 
 | Township Layout Plan | 16 | 16 |  |  | 
 | Surveying and registration of households in the settlement | 0 | 0 |  |  | 
 | Pegging and approval of General Plan | 17 | 17 |  |  | 
 | Township Register Opened | 20 | 20 |  |  | 
Bulk Infrastructure | Bulk Infrastructure | 1 | 1 | 0% completed |  | 
Detailed Planning Design | Water | 14 | 14 | 0% completed |  | 
 | Sewer | 15 | 15 | 0% completed |  | 
Interim Services | Water | 38 | 38 | 0% completed |  | 
 | Sanitation | 38 | 38 | 0% completed |  | 

## Slide 23: Free State 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Achievements / Progress | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 12 | 12 | The contractors are on site in 5 projects 1 project completed 3 projects still require procurement Slow progress has been reported in 1 project | High water table Hard rock Legal dispute between contractor and department Delays in procurement Unavailability of bulk The start of Procurement was delayed by National Treasury moratorium on Preferential Procurement Regulations | The Dept. has resumed the process. The TOR and Bid committees have been approved. The procurement process is underway. Fast tract the dispute between the engineer and the department. Contractor used other method to deal with hard rock Fasttrack procurement Request HDA to assist with bulk infrastructure
 | Sanitation solution | 12 | 12 |  |  | 

## Slide 24: Gauteng 2022/23 Q1 Performance: Phase 1 Pre-feasibility
KPA | Outputs | Name Of Informal Settlements | Planned | Achievement / Progress | Challenges | Remedial Action
Prefeasibility studies | Number of Social Facilitation | 10 | 12 | 10 draft social compact have been achieved pending signatures from community and municipalities before Department’s signatures. | Difficulty in assessing some settlement by the social facilitator and enumerators. The difficulty relates to Pikoko where the community refused the social facilitator access into the community requesting that the land ownership issue between City of Joburg and Mogale City be resolved. | Continued joint community engagements by municipality, department as well as other stakeholders involved

## Slide 25: Gauteng 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Progress / Achievement | Challenges | Remedial Actions
Pre-Planning Studies | EIA Application | 71 | 71 | 9 | None | None
 | Traffic Impact Study | 71 | 71 | 0% completed | None provided | None provided
 | Geotechnical investigation | 71 | 71 | 0% completed | None provided | None provided
 | Land Scoping/ Surveying | 71 | 71 | 0% completed | None provided | None provided
 | Township Layout Plan | 0 | 0 | 9 – 60% completed | None | None
 | Surveying and registration of households in the settlement | 0 | 0 | 12 = 30% completed | Number of households increased | Serviced provider contract to be amended to resolver the difference
 | Pegging and approval of General Plan | 34 | 34 | 0% completed | None provided | None provided
 | Township Register Opened | 0 | 0 | 0% completed | None provided | None provided
 | Infrastructure (Engineering) Services Report | 71 | 71 | 0% completed | None provided | None provided
Land | Land Assembly (excluding Acquisition) | 37 | 37 | 0% completed | None provided | None provided
 | Land acquisition | 0 | 0 |  |  | 
Bulk Infrastructure | Bulk Infrastructure | 16 | 16 | 0% completed | None provided | None provided
Detailed Planning Design | Water | 30 | 30 | 0% completed | None provided | None provided
 | Sewer | 30 | 30 | 0% completed | None provided | None provided
Interim Services | Water | 71 | 71 |  | The Dept. entered into a tripartite agreement at the beginning of this programme between the GDHS, GPF and HDA. All necessary administrative processes have been completed to facilitate the transfer for continuation of the provision of the services | The R224 526 291 budgeted for this purpose is to be transferred to the HDA Fast track the process of transferring of the funds to the HDA
 | Sanitation | 72 | 72 |  |  | 
 | Roads and Storm Water | 0 | 0 |  |  | 
 | Sewer | 0 | 0 |  |  | 
 | Access Roads | 0 | 0 |  |  | 
 | Electricity | 0 | 0 |  |  | 

## Slide 26: Gauteng 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Achievements / Progress | Challenges | Remedial action
Permanent Individual Municipal Engineering Services | Water services | 30 | 30 | 0% completed Projects are at procurement stage | The funding is for alternative sanitation and water provision. The start of Procurement was delayed by National Treasury moratorium on Preferential Procurement Regulations. | The Dept. has resumed the process. The TOR and Bid committees have been approved. The procurement process is underway.
 | Sanitation solution | 30 | 30 |  |  | 

## Slide 27: KZN 2022/23 Q1 Performance: Phase 1 Prefeasibility
Planned Outputs /activities | Number of informal settlements | Planned | Achievements / Progress | Challenges | Remedial action
Social facilitation | 35 | 13 | 6 are 20% completed 9 are 30% completed 6 are at 80 – 90 % 1 awaiting appointment of service providers | To introduce the service provider to the new municipal council. | A meeting has been set for August 2022 to introduce the service provider to the new council.
Prefeasibility studies | 0 | 18 | 3 = 50% completed 2 = 55%completed 1 = 65% completed 3 = 20% completed 1 = completed by the HDA 2 = 90% completed 4 = 30% completed 2 = 40% completed | Delays in getting WULA | Engagements with the concerned Department are ongoing

## Slide 28: KZN 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Progress / Achievement | Challenges | Remedial Actions
Pre-Planning Studies | EIA Application | 20 | 21 | 7 = 30% completed. 2 = 40% completed. 1 = 90% completed. | Introduction of the service provider to the new municipali council. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council. For 90% completed projects top funding is required.
 | Traffic Impact Study | 7 | 7 |  |  | 
 | Geotechnical investigation | 29 | 30 | 7 = 30% completed. 1 = 90% completed. 1 = 20 completed. | Introduction of the service provider to the new municipali council. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council.
 | Land Scoping/ Surveying | 13 | 13 | 1 = 30% completed. 1 = 90 completed. | Introduction of the service provider to the new municipali council. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council.
 | Township Layout Plan | 35 | 36 | 7 = 30% completed. 2 = 40% completed. 3 = 90% completed. 1 = 20% completed. 1 = 55% completed. | Service provider currently undertaking detailed planning studies. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council.
 | Surveying and registration of households in the settlement | 0 | 0 | 0 | Not reported. | Not indicated.
 | Pegging and approval of General Plan | 25 | 25 | 1 = 30% completed. 3 = 90% completed. 1 = 55% completed. | Introduction of the service provider to the new municipali council. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council.
 | Township Register Opened | 7 | 7 | 1 = 50% completed. 1 = 80% completed. | Awaiting SPLUMA and WULA approvals | Ethekwini Municipality currently resolving issue
 | Surveying and registration of households in the settlement | 9 | 5 | 1 = 80% completed. | None | None
 | Infrastructure (Engineering) Services Report | 32 | 32 | 1 = 30% completed. 3 = 90% completed. 1 = 20% completed. 1 = 55% completed. 1 = 60% completed. 1 = 65% completed. 1 = 95% completed. 2 = 70% completed. | Introduction of the service provider to the new municipal council The 70% completed awaiting SPLUMA final submission. | Meeting has been scheduled for August 2022 to introduce the service provider to the new council.

## Slide 29: KZN 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Progress / Achievement | Challenges | Remedial Actions
Land | Land Assembly (excluding Acquisition) | 10 | 10 | 1 = 55% completed. | For 55% complete project, Pre-Planning studies, detailed geotechnical report, Contour Survey/Floodline Determination, SPLUMA submission, Civil Engineer Services report. | Msunduzi Planning has finally supplied comments, to try and resolve the matter of the cemeteries in household properties - June 2022. Once amended accordingly, SPLUMA .
 | Land acquisition | 1 | 1 | 1 = 55% completed. | For 55% complete project, Pre-Planning studies, detailed geotechnical report, Contour Survey/Floodline Determination, SPLUMA submission, Civil Engineer Services report. | Msunduzi Planning has finally supplied comments, to try and resolve the matter of the cemeteries in household properties - June 2022. Once amended accordingly, SPLUMA .
Bulk Infrastructure | Bulk Infrastructure | 32 | 5 | 1= 5%bulk completed. 1 = 78% completed. 1 = 90% completed. | No challenges | No challenges

## Slide 30: KZN 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Progress/ achievement | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 19 | 19 | 6 projects are delayed but a recovery programme is in place Construction underway Finalising planning as EIA needed to be redone in 1 project 100% complete = 1 project 30% serviced sites completed 1 project still to appoint a civil contractor | The project is delayed by people that settled in the way of services; some are not beneficiaries of the project. Sanitation solution not supported by district municipality Lengthy SCM processes | Recovery programme is being implemented and plans for specific projects completed Community engagement
 | Sanitation solution | 14 | 14 |  |  | 
 | Roads and storm water | 18 | 18 |  |  | 
 | Electricity | 1 | 1 |  |  | 

## Slide 31: Limpopo 2022/23 Q1 Performance: Phase 1
Planned Outputs /activities | Number of informal settlements | Planned | Achievements / Progress | Challenges | Remedial action
Social facilitation | 13 | 18 | 0% achievement | The Province did not report any progress made to date with regards to the total number of Social Facilitation achieved to date or in Quarter 1 | The provincial visits

## Slide 32: Limpopo 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Achievement/ Progress | Challenges | Remedial Action
Pre-planning | Land Scoping/ Surveying | 0 | 0 | 4 Projects 40% of work completed 6 projects 10% of work completed 6 Projects 0% of work completed 1 Project 90% of work completed 1 Project 60% of work completed 1 Project 6% of work completed | None provided | None provided
 | Township Layout Plan | 0 | 0 |  |  | 
 | Pegging and approval of General Plan | 14 | 18 |  |  | 
While there is good progress regarding the upgrading of informal settlements, the Province deviated from the approved plan by delivering on Land Scoping/ Surveying and Township Layout Plan

## Slide 33: Limpopo 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Planned | Achievement/ Progress | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 11 | 11 | 4236 | 5 Projects planned to deliver 2 680 Sites 0% achieved to date | Awaiting confirmation of the availability of water, design approval pending Delays in approval of Engineering services Design excessive hard rock ,and spillage of rain water. | Monitoring of progress The service provider has increased the working teams for blasting the rocks on site
 | Sanitation solution | 11 | 11 | 4236 | 6 Projects planned to deliver 1 556 are in various stages of implementation (4%, 6%, 19%, 25%, 33%, 51%) |  | None provided
 | Roads and storm water | 11 | 11 |  | 0% progress |  | None provided

## Slide 34: Mpumalanga 2022/23 Q1 Performance: Phase 2
Province | KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Progress / Achievement | Challenges | Remedial action
Mpumalanga Province | Pre-Planning Studies | EIA Application | 25 | 32 | 0% progress has been reported | None provided | None provided
 |  | Traffic Impact Study | 23 | 23 |  |  | 
 |  | Geotechnical investigation | 22 | 22 |  |  | 
 |  | Land Scoping/ Surveying | 33 | 33 |  |  | 
 |  | Township Layout Plan | 31 | 31 |  |  | 
 |  | Pegging and approval of General Plan | 33 | 33 |  |  | 
 |  | Township Register Opened | 34 | 34 |  |  | 
 |  | Land acquisition | 0 | 0 |  |  | 
 | Bulk Infrastructure | Bulk Infrastructure | 2 |  | 0% progress | None | None
Quarter 1 Performance
The report submitted did not indicate any progress regarding the budgeted milestones on preplanning and construction of bulk infrastructure
Undertaken Remedial: Province to provide substantive information

## Slide 35: Mpumalanga 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Progress / Achievement | Challenges | Remedial action
Permanent Individual Municipal Engineering Services | Water services | 6 | 6 | About 1652 serviced sites were delivered | There are 7 projects that incurred payment but are not in the business plan | Revision of the business plan
 | Sanitation solution | 6 | 6 |  |  | 
 | Roads and storm water | 6 | 6 |  |  | 

## Slide 36: Northern Cape Q1 2022/23 Plans: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Progress/Achievement | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 8 | 8 | 5 = 100% completed 1 = 84% completed 1 = 54% completed 1 = 60% completed | High water table Hardrock Community unrests Hardrock Electrical contractor working, excavating and damaging completed roads | Blasting and pecking the rock On going talks with municipality to reinstate the Damaged Roads Pumping ground water
 | Sanitation solution | 8 | 8 |  |  | 
 | Roads and storm water | 8 | 8 |  |  | 

## Slide 37: Northern West 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Progress/Achievement | Challenges | Remedial Action
Pre-Planning Studies | EIA Application | 12 | 15 | 0% progress | None reported | None provided
 | Traffic Impact Study | 18 | 21 |  |  | 
 | Geotechnical investigation | 13 | 16 |  |  | 
 | Land Scoping/ Surveying | 29 | 32 |  |  | 
 | Township Layout Plan | 33 | 36 |  |  | 
 | Surveying and registration of households in the settlement | 0 | 0 |  |  | 
 | Pegging and approval of General Plan | 35 | 38 |  |  | 
 | Township Register Opened | 48 | 51 |  |  | 
 | Infrastructure (Engineering) Services Report | 22 | 25 |  |  | 
Land | Land Assembly (excluding Acquisition) | 30 | 30 | Land parcels to be procured by the HDA | Due diligence | None provided
 | Land acquisition | 11 | 11 |  |  | 

## Slide 38: Northern West 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Progress/Achievement | Challenges | Remedial Action
Permanent Individual Municipal Engineering Services | Water services | 18 | 19 | 10 projects are at procurement stage 2 projects have a developer appointed and are at design stage 2 projects are at 15% completed 2 projects at 100% completion Project manager appointed | None | None
 | Sanitation solution | 18 | 19 |  |  | 
 | Roads and storm water | 18 | 19 |  |  | 

## Slide 39: Western Cape 2022/23 Q1 Performance: Phase 1
Planned Outputs /activities | Number of informal settlements | Planned | Achievements / Progress | Challenges | Remedial action
Social facilitation | 13 | 17 | 1 project has Social Compacts concluded for the upgrading of 5 5 informal settlement Social Facilitation work concluded through SAWIC in Thembalethu informal Settlements | Stakeholder corporation in securing sustainable livelihood plans Delay in project packaging | Deploy security to protect decanting sites Ongoing negotiation with Professional Service Providers

## Slide 40: Western Cape 2022/23 Q1 Performance: Phase 2
KPA | Planned Outputs /Activities | Number of informal settlements | Number of outputs and informal settlement projects | Achievements / Progress | Challenges | Remedial action
Pre-Planning Studies | EIA Application | 7 | 7 | No performance has been reported | None | None
 | Traffic Impact Study | 7 | 7 |  |  | 
 | Geotechnical investigation | 7 | 7 |  |  | 
 | Land Scoping/ Surveying | 7 | 7 |  |  | 
 | Township Layout Plan | 1 | 1 |  |  | 
 | Infrastructure (Engineering) Services Report | 19 | 19 |  |  | 
Bulk Infrastructure | Bulk Infrastructure | 1 | 1 | No performance reported in others | None | None
Interim Services | Water | 5 | 6 | Expenditure reported in 1 project | None | none
 | Sanitation | 5 | 6 |  |  | 
 | Roads and Storm Water | 7 | 7 |  |  | 

## Slide 41: Western Cape 2022/23 Q1 Performance: Phase 3
KPA | Planned Outputs /Activities | Number of informal settlements | Number of informal settlement projects | Achievements / Progress | Challenges | Remedial action
Permanent Individual Municipal Engineering Services | Water services | 8 | 8 | 1 project still undergoing planning and packaging 3 Projects are under construction 1 Project not yet started 7 projects not reported on | Community unwilling to move to TRA sites | Appointment of a facilitator to support the contractor
 | Sanitation solution | 12 | 12 |  |  | 
 | Roads and storm water | 11 | 11 |  |  | 

## Slide 42: FINANCIAL PERFROMANCE
UISP 2022/23

## Slide 43: Informal Settlements Upgrading Partnership Grant (ISUPG) Provinces Expenditure Performance as at 31 March 2022
As of 31 March 2022:
Four Provinces (EC, FS, KZN and NC) reported 100% spending of their respective budgets;
NC reported 100% expenditure after receiving an additional funding amounting to R60 million
MP, NW and WC spent above 90% of their total allocations.
Despite the R20m stopped, LP still only managed to spent 58% of its reduced budget.
NW Province has commitment of R65m which is more that the R22m available therefore they requested PT to repurpose R43m from HSDG to ISUPG. Rollover application has been submitted to NT
Provinces | Voted Funds |  |  | Year to date (1 April 2021 - 31 March 2022) |  |  | 
 |  | Funds Stopped and Reallocated | Total Available Funds | Spent by Provinces | Unspent Against Voted Funds | Rollover applied | Amount to be surrendered
 | R'000 |  |  | R'000 | R'000 |  | 
Eastern Cape | 432 428 | - | 432 428 | 432 428 | - | - | -
Free State | 228 001 | - 20 000 | 208 001 | 207 695 | 306 | - | 306
Gauteng | 1 109 179 | - 20 000 | 1 089 179 | 852 223 | 236 956 | 236 956 | -
KwaZulu-Natal | 714 375 | - | 714 375 | 714 375 | - | - | -
Limpopo | 254 336 | - 20 000 | 234 336 | 136 537 | 97 799 | 97 799 | -
Mpumalanga | 259 233 | - | 259 233 | 239 456 | 19 777 | - | 19 777
Northern Cape | 76 709 | 60 000 | 136 709 | 136 709 | - | - | -
North West | 358 028 | - | 358 028 | 335 567 | 22 461 | 22 461 | -
Western Cape | 457 429 | - | 457 429 | 452 233 | 5 179 | 5 179 | 
Total | 3 889 718 | - | 3 889 718 | 3 507 223 | 382 495 | 357 216 | 20 083

## Slide 44: Informal Settlements Upgrading Partnership Grant (ISUPG) Provinces Expenditure Performance as of 30 June 2022
Voted funds for the 2022/23 financial year amount to R4,1 billion, with a total expenditure of R408 million at the end of June 2022.
This is a low performance from Provinces with only 38% of funds being spend from the transferred funds .
The Eastern Cape Province is the only Province that has reported zero expenditure at the end of the first quarter.
EC,FS,GP,KZN,LP have all performed under 30% of their transferred funds, MP 98% whilst there was overspending by NC and NW.
Provinces | Voted Funds | Year to date (1 April 2022 - 30 June 2022) |  |  |  |  |  |  | 
 |  | Transferred Funds | Spent by Provinces | Unspent against Transferred Funds | Unspent Against Voted Funds | % Spent against Transferred Funds | % Spent against Voted Funds | Unspent as % of Transferred Funds | Unspent as % of Voted Funds
 | R'000 | R'000 | R'000 | R'000 | R'000 |  |  |  | 
Eastern Cape | 458 151 | 137 445 | - | 137 445 | 458 151 | 0 | 0 | 100 | 100
Free State | 241 563 | 62 983 | 14 147 | 48 836 | 227 416 | 22 | 6 | 78 | 94
Gauteng | 1 175 155 | 235 031 | 27 670 | 207 361 | 1 147 485 | 12 | 2 | 88 | 98
KwaZulu-Natal | 756 868 | 310 267 | 35 942 | 274 325 | 720 926 | 12 | 5 | 88 | 95
Limpopo | 269 465 | 98 650 | 26 529 | 72 121 | 242 936 | 27 | 10 | 73 | 90
Mpumalanga | 274 653 | 68 226 | 66 557 | 1 669 | 208 096 | 98 | 24 | 2 | 76
Northern Cape | 81 272 | 16 491 | 26 876 | - 10 385 | 54 396 | 163 | 33 | -63 | 67
North West | 379 324 | 58 060 | 109 850 | - 51 790 | 269 474 | 189 | 29 | -89 | 71
Western Cape | 484 638 | 102 000 | 101 240 | 760 | 383 398 | 99 | 21 | 1 | 79
Total | 4 121 089 | 1 089 153 | 408 811 | 680 342 | 3 712 278 | 38 | 10 | 62 | 90

## Slide 45: Informal Settlement Upgrading Partnership Grant (ISUPG) Metros as at 30 June 2022
As at 30 of basic services. June 2022:
The overall expenditure stands at 76% of the total available as at 30 June 2022.
All Metros spent more than 50% of total available funds, except for NMB and Mangaung which are at 36% and 34% respectively.
National Treasury stopped portions of ISUPG funds from 5 Metros in terms of DORA Section 18 amounting to R143 million: BCM (R28 Mil), NMB (R33 Mil), MNG (R50 Mil), COE (R15 Mil) and COJ (R17 Mil). These funds were reallocated to eThekwini in line with gazette number 46095.
Metros are spending their funds under planning and provision
METROS | Voted Funds | Stopped/Reallocation | Total available funds | ISUPG EXPENDITURE (01 JULY 2021 - 30 JUNE 2022) |  |  | 
 |  |  |  | Spent by Municipality | Unspent against total available funds | % Spent against total available Funds | % Unspent against total available funds
 | R'000 | R'000 | R'000 | R'000 | R'000 |  | 
Buffalo City | 266 258 | (28,000) | 238 258 | 206 348 | 31 910 | 86.6 | 13.4
Nelson Mandela Bay | 316 045 | (33,000) | 283 045 | 101 949 | 181 096 | 36.0 | 64.0
Mangaung | 263 893 | (50,000) | 213 893 | 73 130 | 140 763 | 34.2 | 65.8
City of Ekurhuleni | 688 066 | (15,167) | 672 899 | 584 375 | 88 524 | 86.8 | 13.2
City of Johannesburg | 646 375 | (17,000) | 629 375 | 563 965 | 65 410 | 89.6 | 10.4
City of Tshwane | 560 301 |  | 560 301 | 448 198 | 112 103 | 80.0 | 20.0
eThekwini | 686 369 | 143,167 | 829 536 | 564 590 | 264 946 | 68.1 | 31.9
City of Cape Town | 518 140 |  | 518 140 | 464 085 | 54 055 | 89.6 | 10.4
Total | 3 945 447 |  | 3 945 447 | 3 006 640 | 938 807 | 76.2 | 23.8
1

## Slide 46: RECOMMENDATIONS
The Committee is requested to …
  Note the report
  Provide comments on the report

## Slide 47: Thank you
www.dhs.gov.za
UISP@dhs.gov.za