## Slide 1: 2021/22 Q3 & Q4 Performance Report
August 2022

## Slide 2
Strategic Focus
Impact statement:
Accelerated use of digital technologies to improve quality of life
Vision:
A digitally transformed society

## Slide 3
Highlights
NEMISA had its LMS zero-rated
NEMISA expanded the Ya Rona digital literacy project to 5 local municipalities in the Lejweleputswa District Municipality in the Free State Province
In Q3, a 3-Day NEMISA Innovation Datathon was hosted across all nine (9) provinces of South Africa as part of the NEMISA’s Annual Performance Plan.
Other events held in Q4 include Colloquium and Digital Skills Summit, Ya Rona programme and “Future Proofing Community Radio” series of workshops

## Slide 4
Overall performance summary
NEMISA achieved 16 of the 19 planned targets set for quarter 3. All targets set for quarter 4 were achieved.
Chart: Q3 : Overall Performance
| Achieved | Not Achieved
Overall Performance | 16 | 3
Chart: 
| Achieved | Not Achieved
Q4 : Overall Performance | 19 | 0

## Slide 5
Programme 1:Administration
Programme 1: Administration |  |  |  |  |  | 
No | Annual Target | Q3 Target | Achievement | Q4 Target | Q4 Achievement | Year to date achievement
1.1.1 | Transformation and Change Strategy implemented | Progress Report on the Transformation and Change Strategy implementation plan | A progress report on the Transformation and Change Strategy implementation plan has been completed | Progress report on Transformation and Change Strategy implementation plan | Progress report on the Transformation and Change Strategy implementation plan has been completed | Progress report on the Transformation and Change Strategy implementation plan has been completed
1.1.2 | Upskilling staff with digital skills | Progress report on the digital skills training | Quarterly progress report on digital skills training initiatives completed | Report on digital skills training for the year | Report on digital skills training initiatives completed | Report on digital skills training initiatives completed
1.1.3 | Organisation structure and culture change report | Progress report on the organisational structure and cultural change | Quarterly progress report on the organisational structure and cultural change completed | Progress report on the organisational structure and cultural change | Report on the organisational structure and cultural change completed | Report on the organisational structure and cultural change completed
1.1.4 | Reviewed curriculum of training programmes to align with the National Digital and Future Skills Strategy | Progress report on the reviewed training programmes to align with the National Digital and Future Skills Strategy on the future of work | Quarterly progress report on the reviewed training programmes to align with the National Digital and Future Skills Strategy on the future of work completed | Report on the reviewed training programmes align ed with the National Digital and Future Skills Strategy on the future of work | Report on the review of two (2) training programmes completed | Report on the review of two (2) training programmes completed
1.1.5 | The research report on the future of work | Progress report on research completed thus far | Developed Progress report on research completed | Submit the research reports to Board | Research on the future of work has been completed and is submitted to the Board | Research on the future of work has been completed and is submitted to the Board.

## Slide 6
Programme 1:Administration
Programme 1: Administration |  |  |  |  |  | 
No | Annual Target | Q3 Target | Achievement | Q4 Target | Achievements | Year to date achievement
1.2.1 | Content development increased to complement the LMS | Progress report developed: Produce two productions for LMS content development | Quarterly progress report developed: Produced three productions for LMS content development | Progress report developed: Produce two productions for LMS content development. | Progress report developed: Two productions delivered | 8 productions were completed for the year.
1.2.2 | Create work experience for interns | 90% of interns are retained in the internship | 18 (84%) interns in operation | 90% of interns are retained in the internship. | 90% retention achieved in Q4 | 90% retention of interns is achieved in Q4
1.2.3 | Getting the OTT to run and improve | Increase in the number of users in the OTT | There has been an increase in the number of users from 150 to 420 users | Increase in the number of users in the OTT. | There’s been an average growth rate of 500 users in the OTT. | There’s been an average growth rate of 500 users in the OTT.
1.2.4 | To expand the platform through partnerships | No planned target | - | One new partnership submitted for approval by the Board. | One new partnership submitted for approval by the Board. A partnership with SAPO has been concluded. | One new partnership submitted for approval by the Board. A partnership with SAPO has been concluded.
1.2.5 | New controls are implemented and monitored to prevent recurrence of audit findings | 30% of the Audit findings are addressed and controls implemented. Preventative measures are implemented to manage the risk of new findings | 60% of the Audit findings are addressed and controls implemented. Preventative measures are implemented to manage the risk of new findings | 10% of the Audit findings are addressed and controls implemented. Preventative measures are implemented to manage risk of new findings | 69% of the Audit mitigation controls are addressed and implemented. Preventative measures are implemented to manage risk of new findings. Outstanding audit actions relate to the preparation of Annual Financial Statements | 69% of the Audit mitigation controls are addressed and implemented. Preventative measures are implemented to manage risk of new findings. Outstanding audit actions relate to the preparation of Annual Financial Statements

## Slide 7
Programme 2:Multi Stakeholder Collaboration
Programme 2: Multi-stakeholder Collaboration |  |  |  |  |  | 
No | Annual Target | Q3 Target | Achievements | Q4 Target | Achievements | Year to date Achievement
2.1 | 2 MoUs | 1 MoU signed with a private organisation | 1 MoU signed with a private organisation (Google) | 1 MoU signed with Government institution | 1 MoU signed with Government institution An agreement with SITA has been concluded. | 1 MoU signed with Government institution An agreement with SITA has been concluded.
2.2 | Partnership performance reports of 2020/21 signed agreements | - | - | Partnership Performance Report for 2021/22 is submitted to the Board. | Partnership Performance Report for 2021/22 is completed | Partnership Performance Report for 2021/22 is completed

## Slide 8
Programme 3: e-Astuteness Development
Programme 3: e-Astuteness development |  |  |  |  |  | 
No | Annual Targets | Q3 Targets | Actual Achievement | Q4 Target | Actual Achievement | Year to date achievement
3.1 | 60 000 citizens trained in basic digital literacy | 15 000 | 12 670 | 10 000 | 49 565 | 73 952
3.2.1 | 120 learners trained in creative media courses | No planned target | - | 120 | 190 | 190
3.2.2 | 1 creative media course developed | 1 Creative media course drafted and submitted to board for approval. | Creative media course content drafted and submitted to board for approval. | No planned target | - | Creative media course content drafted and submitted to board for approval at the end Q3.
3.3 | 2 750 citizens trained on specialist technology courses | 1000 citizens trained in specialist technology courses | 1 029 | 250 | 2808 | 5094
3.4 | 800 employees within government departments and institutions participating in digital transformation advocacy and awareness campaigns | 300 Government employees participating in digital transformation | 112 | No planned target | 46 | 896
3.5 | LMS implemented to support online digital skills roll out | Quarterly report on the content development process and the functioning of the LMS to show progress in implementation. | Quarterly report on the content development process and the functioning of the LMS to show progress in implementation completed | Quarterly report on the content development process and the functioning of the LMS to show progress in implementation. | Quarterly report on the content development process and the functioning of the LMS to show progress in implementation completed | Quarterly report on the content development process and the functioning of the LMS to show progress in implementation completed

## Slide 9
Programme 3: e-Astuteness Development
 | Outcomes | Challenges at the end of quarter 3 | Corrective actions
3.1 | Number of Citizens trained in basic digital literacy | The reason for the lower performance is as a result of lower than expected performance by the CoLabs, not having a full complement of the independent facilitators as well as that of the Ya Rona Ambassadors in the areas where training was earmarked to take place. There has as well been a low completion rate in the online learning platforms which indicates that improved controls are required to ensure learners complete their online courses. | NEMISA will implement a recovery plan for the unachieved targets with the aim on APP targets through the partnerships that are in place. NEMISA will in Q4 train Teacher assistants in digital literacy in partnership with the Department of Basic Education. Through a partnership with the Department of Home Affairs there are plans to train unemployed youth in digital literacy and other courses on digital technologies. One to one meetings with underperforming CoLabs are underway and monthly reporting is required from them instead of quarterly reports. A zero rated LMS is also expected to assist online learning while NEMISA is working improving online learning support.

## Slide 10
Programme 4:Knowledge for innovation
Programme 4: Knowledge for Innovation |  |  |  |  |  | 
No | Annual Target | Q3 Target | Achievement | Q4 Target | Q4 Actual Achievement | Year-to-date achievement
4.1 | 1 Hackathon hosted | Hackathon Hosted and outcomes report developed | A dackathon was hosted and outcomes report developed | No planned target | - | The hackathon was hosted, and an outcomes report developed
4.2 | 1 Digital skills Summit hosted | Preparation report for hosting of digital skills Summit is submitted to the Board for noting | A preparation report for hosting of digital skills Summit is submitted to the Board for noting | Digital skills Summit hosted, and an outcomes report developed | The Digital skills summit | The Summit was hosted, and an outcomes report developed
4.3 | 1 Colloquiums hosted | Preparation report for hosting of the Colloquium is submitted to the Board for noting | A preparation report for hosting of the Colloquium is submitted to the Board for noting | Colloquium hosted and outcomes report developed. | The Colloquium hosted and an outcomes report developed. | The Colloquium hosted and an outcomes report developed.

## Slide 11
Programme 5: Aggregation Framework
Programme 5: Aggregation Framework |  |  |  |  |  | 
No | Annual Target | Q3 Target | Actual Achievement | Q4 Target | Q4 Actual Achievement | Year – to date achievement
5.1 | Evaluation and impact report developed | Quarterly Monitoring and evaluation report developed | Quarterly Monitoring and evaluation report developed | Quarterly Monitoring and evaluation report developed | Quarterly Monitoring and evaluation report developed Impact Assessment Report was completed | 4 Quarterly Monitoring and evaluation report developed. Evaluation and impact report completed. Impact Assessment Report was completed

## Slide 12
Institutional development
Appointments made in Q4
Project Manager: Creative Media (Fixed-term)
Finance Officer (Permanent)
HR Officer (Fixed-term)
Group | Quarter 3 | Quarter 4
Permanent staff | 33 | 31
Fixed-term staff | 12 | 13
Temporary staff | 2 | 2
Total | 47 | 46

## Slide 13
Q3 Smart Oversight Overview
Name | Position | Q3 Ordinary Board | Q3 Special Board | Q4 Ordinary Board | Q4 Special Board
Ms Molebogeng Leshabane | Chairperson | 1 | 2 | 2 | 2
Ms Tobeka Buswana | Member | 1 | 2 | 2 | 2
Ms Nomonde Hlatshaneni | Member | 1 | 2 | 2 | 2
Mr Melvyn Lubega | Member | 1 | 1 | 2 | 2
Prof Christian Michael Adendorff | Member | 1 | 2 | 2 | 2
Mr Lionel Ricardo Adendorf | Member | 1 | 2 | 2 | 2
Mr William Trevor Rammitlwa | CEO | 1 | 2 | 2 | 2
Mr Jaruzelski Leonid Le Guma | ARC Chairperson | 1 | 2 | 2 | 1

## Slide 14
Financial Information
Quarter 3
NEMISA posted a surplus of R487,128.57 for the quarter ending 31 December 2021
NEMISA is in a good financial health situation, the entity has a strong cashflow flow balance and remains liquid and solvent.
Current ratio: 1:1, this is the same as the industry norm of 1:1.
Total debt to ratio: 0.9:1
Quarter 4
NEMISA made a surplus of R3 521,376.88 for the quarter.
The Entity has a strong cash flow balance and remains liquid and solvent.
The current ratio is 1:1; this is the same as the industry norm of 1:1.
The debt ratio is 0.9:1, which indicates that cash flow is sufficient to fund long and short-term liabilities.
There was no fruitless and wasteful, irregular expenditure for the quarter

## Slide 17
Financial Information
Q4 Direct Expenditure:
Direct expenditure relates to the training expenses in media courses, basic digital literacy training, 4IR related courses. Employee salaries (Project managers, Lectures, Project support staff) 15% CoLab 46% and Online learning 22%, is the majority of actual Direct expenditure
Chart: Direct expenditure Breakdown
| CoLab | Online learning | Yarona | IHT | Employee salaries
 | 9729040 | 4710473.6 | 1595986.36 | 1783881.69 | 3213081

## Slide 18
Implementation of the Audit Action Plan
AGSA Audit Action Plan | Total no. of Audit action Plans | Number of Audit Actions completed | Number of Audit action Plans in progress
Total audit action plans | 24 | 22 | 2
Audit action Plans Implementation % | 100% | 92% | 8%

## Slide 19
Thank you
Kea Leboga