## Slide 1: National Progress On Programme On Blocked And Incomplete Projects
Portfolio Committee
31 August 2022

## Slide 2: Purpose
To provide the members of the Portfolio Committee on Human Settlements with a progress report on the National Blocked Projects Programme Process Plan For Blocked and Incomplete Projects

## Slide 3: Contents
Purpose
National Unblocking Programme Process Plan
Definition of Blocked Projects
Overall List of Blocked and Incomplete Projects
Blocked Projects in the 2022/2023 Business Plan
Reasons Projects Blocked/Incomplete
Provincial Plans On The Programme
Recommendations

## Slide 4: National Unblocking Process Plan
2.Confirmation
PDs to respond:
3. Provincial Action Plan - Response from Province
Analysis of a Provincial Response
With Reasons and Action Plan
Define the support required from National
Classification of support Required
4. Support Intervention
War Room
Deploy Technical Capacity
Deploy Admin Capacity
Policy Interpretation Services
5. Final Evaluation & Exit Strategy
0- 6 months – Prepare National Implementation Plan
6 – 24 months – Assist and Monitor Implementation of Plan
Communication& Social Facilitation
1. Analysis on HSS - Systems Analysis
Check list
Inclusion in the Business Plans
NDHS is developing a National Unblocking Programme Plan (NUPP).
The business planning process comprises of a series of steps that have been developed.
Where relevant, the NUPP will have a communication plan that advised beneficiaries of the next step e.g. potential areas where opportunities will be available.

## Slide 5: Definition of Blocked and Incomplete Projects
1. The original definition covered projects that:
  Have not incurred any expenditure after more than 12 months and more.
  Experience challenges in the middle of a project and cannot continue,
  Projects that are less than or equal to 89% of physical completion in terms of units and sites
  Projects that are not moving but still has beneficiaries attached to the project
  Projects at 90% and above are considered incomplete projects
2. The definition of a blocked project has been revised to cover projects that are deemed by the Province that may need a special intervention that is beyond the administrative capability of a Province or a Municipality – There are various

## Slide 6: Overall List of Blocked and Incomplete Projects
Province | Number of Districts | Overall Number of Blocked Projects for 2022 / 2023 | Projects in the Business Plan of 2022 / 2023
EC | 8 | 79 | 25
Free State | 5 | 226 | 14
Gauteng | 5 | 80 | 21
KZN | 11 | 350 | 14
Limpopo | 5 | 21 | 6
Mpumalanga | 2 | 4 | 3
Northern Cape | 0 | 0 | 0
North West | 4 | 37 | 42
Western Cape | 4 | 7 | 7
Total | 44 | 804 | 149

## Slide 7: Main Reasons for the Blocked Projects
Province | No. of Districts | No of Projects | Poor Performing Contractors | Bulk Infrastructure | Land Issues | Title Deeds | Internal Serviced | Socio-political Issues | Subsidy quantum issues | Geo Tech/ or Close down | Other (Tranche to Mun
Eastern Cape | 8 | 79 | 56 | 8 | 9 |  | 6 |  |  |  | 
Free State | 5 | 226 | 169 | 5 | 1 |  | 5 |  |  | 36 | 
Gauteng | 5 | 80 | 14 | 12 |  | 54 |  |  |  |  | 
KZN | 11 | 350 | 10 | 26 | 9 | 271 | 1 | 8 | 6 |  | 19
Limpopo | 5 | 21 | 21 |  |  |  |  |  |  |  | 
Mpumalanga | 2 | 4 | 1 | 2 | 1 |  |  |  |  |  | 
North West | 4 | 37 | 9 | 1 | 27 |  |  |  |  |  | 
Northern Cape | 0 | 0 |  |  |  |  |  |  |  |  | 
Western Cape | 4 | 7 |  |  |  |  |  |  |  |  | 7
Total | 44 | 804 | 286 | 54 | 47 | 325 | 12 | 8 | 6 | 36 | 26

## Slide 8: Blocked Projects Included in the 2022/2023 Business Plans
Province | No. of Districts | No. of Projects | Total Annual No of Sites | Total Annual Site Budget | Total Annual No of Units | Total Annual Unit Budget
Eastern Cape | 6 | 41 | 395 | R 3 348 500,00 | 257 | R 42 557 511,40
Free State | 3 | 14 | 0 | 0 | 447 | R 48 108 684,00
Gauteng | 4 | 21 | 1052 | R 64 363 953,50 | 76 | R 5 182 782,95
KZN | 5 | 14 | 0 | R20 990 162,30 | 143 | 0
Limpopo | 3 | 6 | 47 | R 2 612 918,00 | 174 | R 23 909 448,00
Mpumalanga | 2 | 4 | 0 | 0 | 132 | R 31 664 320,00
Northern Cape | 0 | 0 | 0 | 0 | 0 | 0
North West | 3 | 42 | 0 | 0 | 247 | R 34 374 410,20
Western Cape | 4 | 7 | 0 | 0 | 759 | R 138 975 000,00
Total | 25 | 149 | 1494 | R 91 315 538,80 | 2235 | R 324 772 156,55

## Slide 9: Why Is Work Incomplete
Province | Common Reasons | Response
Eastern Cape | Poor Performance of contractors Bulk Infrastructure, connector and link Illegal land occupations | OpsCap Provision For Project and Contract Management Increased HSDG and USDG Funding For Bulk and Link Upscale Serviced Sites Provision
Free State | Tranche payments to Free State Development Corporation | Enforcement of DoRA Provisions - Non-Approval of Roll-Overs
Gauteng | Projects needed to be closed and lack of bulk | Increased HSDG and USDG Funding For Bulk and Link
Kwa Zulu Natal | Beneficiary unrest during elections One house per uMuzi Construction Mafia Geotechnical and Subsidy Quantum Variances | Implementation Of Programme Recovery Plans Review Of Minimum Norms and Standards Enlisting SAPS Support Code Provides For Approval Variances
Limpopo | Mostly poor performance of contractors (Abandonment Of The Project) | Directive On Establishment Of Restrictive Authority Committees By Provinces
Mpumalanga | Bulk infrastructure and Illegal land Occupation | Increased HSDG and USDG Funding For Bulk and Link Upscale Serviced Sites Provision
North West | The main reason was the tranche payments made to the Municipalities | Enforcement of DoRA Provisions - Non-Approval of Roll-Overs
Northern Cape | Projects needed to be closed | Provincial Analysis Of HSS And Mitigation Measures
Western Cape |  | 

## Slide 10: Progress to Date
149 Blocked projects included in the 2022/2023 Business Plan
Appointment of additional capacity:
  War Room Specialist appointed
  Professional Resource Teams Panels to be appointed to assist with scoping and implementation plans,
Establishment of the National Steering Committee
Approval by Acting Director General on the establishment of “Restrictive Authority Committees” in all Provinces
Notes: The Terms of Reference for appointment of the PRTs submitted to the SCM

## Slide 11: Progress To Date On One On One Engagements With Provinces
One on one meetings held with Gauteng, Eastern Cape and Limpopo
Issues raised include the following:
  Clean up and updating of the HSS as well request for training in the use of the HSS for both Provincial and Regional Managers.
  Submission of joint application to the SIPS programme for Bulk Infrastructure through the assistance of PRT’s.
  Approval of Professional Resource Team for scoping and development of implementation plans
  Report on quarterly reports for projects in the Business Plans

## Slide 12: Short, Medium and Long Term Targets
Monitoring of projects in the business plans - Digitised monitoring and tracking dashboard being developed with HDA/On-site visits/Quarterly reports - Immediate
Follow-up in-person oversight held with Gauteng, Eastern Cape and Limpopo and balance of Provinces from September 2022 – November 2022 – Focus on planning and funding – Immediate and continuing
Supplementation of capacity to prepare National Implementation Plan – short to medium term.
Directive to Provinces to analyse HSS to remove duplicated project and beneficiaries – short to medium
The training of provincial and municipal - November 2022 – March 2023 – short to medium.
Specific programme interventions – supplementing bulk and link funding/upscale the provision of serviced site – medium to long term

## Slide 13: Recommendations
It is recommended that progress report as of July 2022 on the National Blocked Projects Programme Process Plan, be noted

## Slide 14: Thank You