## Slide 1: 22 AUGUST 2022
PRESENTATION TO THE MINISTRY OF DEFENCE AND MILITARY VETERANS
UPDATE/PROGRESS REPORT WRT THE DEPARTMENT OF MILITARY VETERANS FACILITIES

## Slide 2: PRESENTATION OUTLINE
Purpose.
DMV Headquarters.
Provincial Offices.
Recommendation.

## Slide 3: PURPOSE
The purpose of this presentation is to provide progress report to the Ministry of Defence and Military Veterans regarding the Department of Military Veterans facilities.

## Slide 4
The Department of Military Veterans HQ (DMV HQ) lease expired at the end of November 2018.
Prior the expiry of the lease a request was submitted to Department of Public Works and Infrastructure (DPWI) to acquire new DMV HQ and subsequently correspondences, departmental bilateral meetings and DG to DG meeting were held to enforce DPWI to speedily finalise on the acquisition of the DMV HQ, and these efforts bearded unfruitful results to date.
On the 10 June 2021, DPWI wrote a deviation letter to National Treasury (NT) for the acquisition of Passenger Rail of South Africa (PRASA) building. A response was received from NT requesting more clarity on the request from DPWI.
DMV HQ

## Slide 5
Subsequently, on the 22 September 2021 the DMV Accounting Officer wrote a letter to the DPWI Accounting Officer informing him to finalise on the acquisition of the DMV HQ.
On 14 October 2021, DPWI responded that they are commencing engagements with NT for the acquisition of PRASA.
DMV made follow-ups weekly and during monthly Bilateral meetings with both National and Regional DPWI.
A DG to DG meeting was held on 25 January 2022 to solicit intervention from DG DWPI on the acquisition of DMV outstanding facilities.
In the Bilateral meeting that was held on the month of July 2022, DPWI stated they will prepare a deviation letter for the DG to approve and provide the DMV with the Project Execution Plan.
Project Execution Plan submitted by DPWI shows that the preferred PRASA building will be secured by November 2022
DMV HQ

## Slide 6: PROVINCIAL OFFICES
PROVINCE | STATUS
North West | The lease agreement expired on 31 May 2021. The lease was renewed from 01 June 2021 and will expire on 31 June 2026.
Eastern Cape | The lease agreement expired on 31 August 2021. Initially the DMV requested that the lease be renewed for a period of three years whilst waiting to be included on the precinct plan. However, DPWI Eastern Cape Regional Office advised that the lease be renewed for a period of five years, since the precinct plan is not on their plans as yet. DMV submitted a letter on 29 September 2021 to that effect. The interim extension will end on 31 August 2022 whilst the process of to sign the lease is being finalised.
Mpumalanga | The lease agreement expired on 28 February 2021. The lease has been renewed starting from 01 March 2022 and will be running for two years. DMV will be included in the precincts plan.

## Slide 7: PROVINCIAL OFFICES
PROVINCE | STATUS
Free State | The lease agreement commenced on 01 March 2020 and will expire on 28 March 2025.
Western Cape | The lease agreement commenced on 01 July 2020 and will expire on 31 July 2025.
NC | The lease agreement commenced on 01 September 2020 and will expire on 31 September 2025.

## Slide 8: PROVINCIAL OFFICES
PROVINCE | STATUS
KZN | DPWI KZN Regional Office acquired a shared building (Aquasky Building) at 275 Anton Lembede Street in Durban CBD. DPWI will submit the cost analyses to the DMV to approve and confirm the availability of funds.
Limpopo | A tender for Polokwane DMV Regional Office was advertised and closed, five bidders responded to the advert. On 14 October 2021 the DMV was invited for site inspection. During final SCM evaluation, it was found that all the bidders do not meet the required specifications. The tender will readvertised.
Johannesburg | DPWI JHB Region indicated that they received an approval for the DMV request to be included on the procurement plan. A Bid Specification Committee was held on the 27 July 2022.

## Slide 9: RECOMMENDATION
The DMV will continue to engage DPWI weekly and on monthly bilateral meetings to finalise on the acquisition of the outstanding DMV required facilities.

## Slide 10
THANK YOU