## Slide 1: MEETING FOR PORTFOLIO COMMITTEE MEETING ON HUMAN SETTLEMENTS REPORT: BLOCKED PROJECTS, ERADICATION OF MUD HOUSES, REMOVAL OF ASBESTOS ROOF, UPGRADING OF INFORMAL SETTLEMENTS AND TITTLE DEEDS 31st AUGUST 2022

## Slide 2: TABLE OF CONTENT
Purpose of presentation
Unblocking of Blocked projects
Eradication of Mud houses
Plans to remove Asbestos Roofing
Title Deeds
Upgrading of Informal Settlements Programme
Conditional Grants Performance
Funds shifted to another Province
2

## Slide 3: PURPOSE OF THE PRESENTAION
The purpose of the presentation is to brief the Portfolio Committee on various priority intervention housing programmes;
The presentation will further provide an overview of the two Conditional Grants (HSDG & ISUPG) performance for the current financial year, 2022/23;
3

## Slide 4: BLOCKED PROJECTS
4

## Slide 5: Current Status on Blocked Project
5
Initial HSS Numbers | No. of Projects by Provinces | Active / Running | Closed off | Not started and closed off
465 | 232 | 17 | 36 | 179
Province | No. of Districts | No of Projects | No. of Units/ Approved Beneficiaries | Total Estimate Required | Budget 2022/2023 | Projected Budget 2023/2024 | Projected Budget 2024/2025
Free State | 5 | 232 | 9 077 | R953 085 000 | R30 551 648 | R168 000 000 | R182 000 000

## Slide 6: BLOCKED PROJECTS UNDER IMPLEMENTATION 2022-23
District - Region | Municipality | HSS Project Number | HSS Project Desc | Total Annual No of Units | Total Annual Title Deed Restoration | Total Annual Title Deed New | Total Annual Budget
FEZILE DABI | MOQHAKA LOCAL MUNICIPALITY | F08010002/1 | Viljoenskroon 200 Mohlahleli (Snowball Constr (2008/2009) - Phase 1 | 96 | 101 | 0 | R 12 751 924,00
 |  | F08010002/2 | Viljoenskroon 200 Mohlahleli (Snowball Constr (2008/2009) - Phase 1 | 36 | 99 | 0 | R 5 401 128,00
 |  | F10090021/1 | Kroonstad 170 (Distinctive Choice Land Rest (Moleboheng Developers (Tuthela B Enter 2010/2011) - Phase 1 | 15 | 0 | 0 | R 2 872 972,00
 | NGWATHE LOCAL MUNICIPALITY | F06080010/1 | Parys 300 Project Superb Homes 2006/2007 - Phase 1 | 4 | 150 | 0 | R 863 794,00
 |  | F08010003/1 | Vredefort 400 Superb Homes (2008/2009) - Phase 1 | 14 | 0 | 0 | R 2 119 410,00
 |  | F97080007/1 | Parys 200 Maono Incompl. 2013/15 (Terisano Housing Support Centre - Phase 1 | 8 | 0 | 0 | R 1 271 646,00

## Slide 7: BLOCKED PROJECTS UNDER IMPLEMENTATION 2022-23
7
District - Region | Municipality | HSS Project Number | HSS Project Desc | Total Annual No of Units | Total Annual Title Deed Restoration | Total Annual Title Deed New | Total Annual Budget
MANGAUNG | MANGAUNG METRO MUNICIPALITY | F04070004/1 | Botshabelo 500 Subs. - Quantum Leap Inv. Sections D L M N - Phase 1 | 10 | 19 | 0 | R 174 554,00
 |  | F07120005/1 | Thaba Nchu 100 Jungle Arrow (2006/07) - Phase 1 | 3 | 97 | 0 | R 776 146,00
 |  | F14080008/1 | Botshabelo 35 Incomplete Iceburg 2017/18 Furnserve 2014/15 - Phase 1 | 30 | 0 | 30 | R 723 921,00
XHARIEP | KOPANONG LOCAL MUNICIPALITY | F10100006/1 | Edenburg 69 Mampotla Trading (2010/2011) - Phase 1 | 1 | 0 | 0 | R 159 505,00
TOTAL |  |  |  | 217 | 466 | 30 | R27 115 00

## Slide 8: Reasons for Blocked Projects
8
A result of units left over from past interventions, Mostly Massification programmes (a provincial specific programme);
Most of the companies/support organizations paid are no longer in existence;
Land: No adequate serviced sites available;
Contractors: Lack of capacity, cash flow problems, poor performance and quality of workmanship;
Beneficiary: identification and qualification problems, missing beneficiaries, illegal occupation, etc.

## Slide 9: IMPLEMENTATION PLAN FOR BLOCKED PROJECTS
9
Scale down projects with beneficiary challenges
Clean HSS information
Terminate contracts of poor performing contractors
Prioritise implementation of blocked projects

## Slide 10: MUD HOUSING PROJECTS
10

## Slide 11: SUMMARY OF MUD HOUSES
Approximately 978 mud houses across the province 68 units completed in the previous years R 42,892,850.00 budget for 2022/23 financial year to deliver 300 units 0 units delivered in 2022/23 financial year Mud houses to be eradicated in 3 financial years:
11
11

## Slide 12: MUD HOUSES – MTEF TARGETS
12
12
 | 2022/23 MTEF |  | 2023/24 MTEF |  | 2024/25 MTEF | 
GRANT FRAMEWORK | BUDGET R’000 | UNITS | BUDGET R’000 | UNITS | BUDGET R’000 | UNITS
HSDG | R 42,892,850 | 300 | R34,862,700 | 300 | R34,862,700 | 378

## Slide 13: MUD HOUSES – CHALLENGES AND MITIGATION
13
13
CHALLENGES | MITIGATION
Its taking long to verify mud houses due to limited capacity | Involvement of Municipalities through ward councillors and ward committees for identification and verification process
Applications declined due to various reasons – i.e. some beneficiaries already benefited elsewhere | Deal with each case on its merit and request ministerial override where necessary
Accessibility of areas where these mud houses are located – difficult terrain | Involvement of Municipalities through ward councillors and ward committee for identification and verification process
Mud houses located in communal land where there are currently no municipal engineering services; | Provide for rudimentary services

## Slide 14: ASBESTOS PROJECTS
14

## Slide 15: SUMMARY OF FREE STATE ASBESTOS ROOF ASSESSMENT
15
District | Target - units with Asbestos roofs | Total Budget (estimated budget) | Was an assessment done
MANGAUNG DISTRICT | 11 129 | R590 593 772.00 | YES
XHARIEP DISTRICT | 2 934 | R156 285 260.00 | YES
THABO MOFUTSANYANA DISTRICT | 12 058 | R639 893 944.00 | YES
FEZILE DABI DISTRICT | 3 718 | R197 306 824.00 | YES
LEJWELEPUTSWA DISTRICT | 6 451 | R342 341 668.00 | YES
Total: | 36 301 | R1 926 421 468.00 | 
15

## Slide 16: REMOVAL OF ASBESTOS ROOFS – 2022/23 FINANCIAL YEAR
16
16
Planned 22/23 Annual target | Planned budget
70 | R9 884 910

## Slide 17: ASBESTOS HOUSES – CHALLENGES AND SOLUTIONS
17
17
CHALLENGES | REMEDIAL ACTION
Some house are dilapidated | Structural integrity assessment to be condcted
Provincial earmark funding to demolish structurally unsound houses not sufficient | Shifting funds from non-performing projects within the HSDG

## Slide 18: TITLE DEEDS
18

## Slide 19: TITLE DEEDS – MTEF TARGETS
OUTPUT INDICATOR | 2022/23 | 2023/24 | 2024/25
PRE 1994 TITLE DEEDS REGISTERED | 800 | 800 | 800
POST 1994 | 2775 | 1453 | 1453
POST 2014 | 1618 | 1453 | 1453
NEW TITLE DEEDS | 250 | 568 | 624
19

## Slide 20: TITLE DEEDS – BACKLOGS
CATEGORIES | BACKLOG
PRE- 1994 | 10 298
POST - 1994 | 14 768
POST 2014 | 3 627
20

## Slide 21: TITLE DEEDS – CHALLENGES AND WAYFORWARD
CHALLENGES | WAY-FORWARD
Disputes amongst family members; Disputes caused by different people sharing same site; Unreported estates; Township registers not opened/ opened but not proclaimed; Floating township title deed amongst conveyancers; Delay in signing of deeds documents submitted by conveyancers by Municipal Managers. | Expansion of the conveyancers database; Consumer education to be intensified. To improve on monitoring of conveyancers and working relationship with municipalities. Initate the nullification of title deeds that were erroneously transferred through a class action Prioritize the opening of township register and proclamation; The Department to assess the magnitude of the impact caused by non reported estates on the performance of the title deed programme and propose definitive programme to mitigate such challenges.
21

## Slide 22: UPGRADING OF INFORMAL SETTLEMENTS PROGRAMME
22

## Slide 23: PROGRAMME OVERVIEW
 | Number | Comments | 
Total No of IS in FS | 161 (inc 47 in Mangaung Metro) | Category A | 63
 |  | Category B1 | 19
 |  | Category B2 | 5
 |  | Category C | 62
 |  | Category A & C | 11
 |  | Category B1 & C | 1
Estimated number of HH in the FS (IS) | 77 683 |  | 
Total number of IS Categorized | 161 |  | 
Total number of Upgrading Plans Dev (as per NUSP) | 161 |  | 
The proposed ISUPG allocation for 2022/23 | R241 563 000 |  | 
The number of settlements identified to receive funding in terms of ISUPG | 55 |  | 
Upgraded settlements to date | 2 |  | 
23

## Slide 24: Informal Settlements Audit
 | FEZILE DABI | LEJWELEPUTSWA | THABO MOFUTSANYANA | XHARIEP | MANGAUNG METRO | TOTAL FS
TOTAL NU. OF SETTLEMENTS | 20 | 47 | 32 | 15 | 47 | 161
NO. ON 2022/23 ISUPG BP | 12 | 25 | 11 | 6 | 0 | 55
NO. FULLY UPGRADED TO DATE | 1 | 1 | 0 | 0 | 0 | 2
24

## Slide 25: Informal Settlements Status
NO of settlements where Town Planning is completed | NO of Settlements where Reticulation is completed | NO of settlements where services are planned for installation |  |  |  |  | 
 |  | 2022/3 | Budget | 2023/4 | Budget | 2024/25 | Budget
58 | 2 | 17 | R92 500 000 | 30 | R161 600 000 | 35 | R231 700 000
25

## Slide 26: Upgrading of Settlements
Development Phase | Number of Settlements | Progress to Date
1 | 2 | Social compacts completed and HDA is proceeding with phase 2 activities. The following studies are completed: Land surveying Geotechnical report Wetland Baseline assessment Palaeontological Impact assessment Heritage Impact Assessment Hydrological assessment
2 | 36 | 3 EIA Submission and 8 EIA Authorization 2 SG submissions (approval pending) 2 SG approvals MPT approval
3 | 17 | Connections to the sites (water and sewer)
26

## Slide 27: Challenges Faced
Little or no forward planning in Municipalities leading to mushrooming of informal settlements; Burden of land development and upgrading of informal settlements placed on the province due to financial status of municipalities, thus resulting in slow progress Delays in acquiring approvals from third parties; Delays in procurement of services geared towards upgrading – Procurement moratorium
27

## Slide 28: CONDITIONAL GRANTS PERFORMANCE
28

## Slide 29: CONDITIONAL GRANTS PERFORMANCE MEETING 1st QUARTER OF 2022/23
29
CONDITIONAL GRANTS | MAIN APPROPRIATION 2022/23 | EXPENDITURE 30 JUNE 2022 | UNSPENT BALANCE 30 JUNE 2022 | SPENT
 | R'000 | R'000 | R'000 | %
Informal Settlements Upgrading Programme | 241 563 | 14 147 | 227 416 | 5.86%
Human Settlements Development Grant | 813 041 | 45 067 | 767 974 | 5.54%
TOTAL | 1 054 604 | 59 214 | 995 390 | 5.60%

## Slide 30: CHALLENGES AND REMEDIAL ACTION
HDA prior year’s performance for MTOP reflected a significant amount of funds unspent as at March 2022. The Department therefore resolved not to transfer the planned allocation of R 23 750 million subject to funds currently with the HDA being fully expended. Regular financial monitoring will be performed to ensure that funds transferred for MTOP are spent as planned. It is anticipated that the planned allocation of R 23 750 million will be transferred during the second quarter. Of the 17 Housing projects which were projected with allocation of R 57 378 million to deliver towards the targeted 194 units for the 1st quarter. Nine(9) projects have not yet been procured for this year. There were also construction delays which were caused by adverse weather conditions on certain infrastructure projects
30
30

## Slide 31: CHALLENGES AND REMEDIAL ACTION
In addition, housing projects that are performing slow due to unintended stoppages on site by local forums .
31

## Slide 32: CATCH UP PLAN PER CONDITIONAL GRANT
Focus and prioritize housing projects to ensure procurement is speedily completed; There will be close monitoring on the Contractor Development Programme; The Department will also ensure that there is close monitoring and quality control on all projects; During the revision of the business plan, budgets will be reprioritized to performing projects.
32

## Slide 33: FUNDS WITH-HELD – 2021/22 FINANCIAL YEAR
R20 000 000 was withheld from the Informal Settlements Upgrading Partnership Grant (ISUPG); There was no impact on this as the targets were 99% achieved; Projects that were mainly affected where those still under procurement process.
33

## Slide 34
THANK YOU