## Slide 1: PRESENTATION BY THE DEPARTMENT OF PUBLIC WORKS AND INFRASTRUCTURE ON PROGRESS REGARDING THE DEVOLUTION OF THE INFRASTRUCTURE MAINTENANCE FUNCTION FROM DPWI TO THE DOD
STANDING COMMITTEE ON APPROPRIATIONS
02 SEPTEMBER 2022

## Slide 2: STANDING COMMITTEE REQUIREMENTS
DPWI was requested to report to the Standing Committee on Appropriations on the following key areas:
Progress report on all projects that were transferred from DPWI to the DOD after the Committee’s oversight visit to Free State and Gauteng Provinces, to date.
Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
Any legal or administrative challenges faced by the DPWI in transferring the infrastructure maintenance function to the DOD; (REIS INPUTS)
Any other matter related to this subject that may be useful to the Committee in exercising its oversight mandated functions;

## Slide 3: DEVOLUTION OF MAINTENANCE FUNCTION FROM DPWI TO DOD
Total devolution of maintenance function from DPWI to the DOD has not taken place yet, owing to:
The concurrence of the Ministers of Public Works & Infrastructure, Defence, Public Service and Administration and National Treasury is required prior to devolution as per Section 19 (1)(a) of GIAMA
The Minister of Defence has requested more time for her to consider the request made by her predecessor for devolution.
As an interim measure, the Executive Authority of DPWI is amenable to consider assignment of work on a project-by-project basis.
DPWI will assist DoD with technical support, where necessary.

## Slide 4: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
SUMMARY OF REPAIRS AND REFURBISHMENT (PLANNED MAINTENANCE) for 2022/23 Financial Year (FY)
There is total of 114 project requests by Client Departments across the value chain. (With and Without allocation by Client Departments)
Once we receive the budget allocation, DPWI can start planning but it will not be finalised in the current financial year.
Only 29 projects have allocation for 2022/23 FY
10 projects with allocation are on planning (Design Development Stage) (4) with allocation of
7 projects with allocation are in construction stage (5B).
3 projects with allocation are in Practical Completion Stage (6A)
6 projects with allocation are on Final Delivery Stage (7-7A)
3 Projects with allocation are on Final Account Stage (8)

## Slide 5: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS ON PLANNING PHASE OF IMPLEMENTAION (1 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | 
Lenasia | Military base | Repair and renovations to military base | 046949 | 4 | 2022/09/01 | 36 | 41 877 766 | 1 261 473 | 40 616 293 | Designs Development were almost completed. DOD requested project to place project on status 4C (Design Stop) Project on hold awaiting further instruction regarding implementation.
Zeerust | Military base | Repair and renovation to kitchen, officers' mess, and repair s to sinking single quarters | 049519 | 4 | 2022/07/29 | 36 | 11 000 000 | 4 856 072 | 6 143 928 | Design Development complete Project is scheduled to be completed in 2023
NABOOMSPRUIT | AMMUNITION DEPOT | REPAIR AND MAINTENACE OF C OMPRESSOR SYSTEMS AND ISSUE COMPLIANCE CERTIFICATE | 049894 | 4 | 2022/09/30 | 3 | 629 503 | - | 629 503 | Design development was completed Project Manager is in the requesting approval of funding prior to advertised Project is scheduled to be advertised in October 2022

## Slide 6: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS ON PLANNING PHASE OF IMPLEMENTAION (2 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | 
POLOKWANE |  | POLOKWANE: LIMPOPO ASB:REPAIRS AND MAINTENANCE OF COMPRESSOR SYSTEM AND ISSUE COMPLIANCE CERTIFICATE | 049896 | 4 | 2022/09/01 | 6 | 3 182 792 | - | 3 182 792 | Design development is complete Bid Specification Committee meeting scheduled for 26th of August 2022 Project is scheduled to be advertised beginning of October 2022
MBOMBELA(NELSPRUIT) | MILITARY AREA | REPAIR AND RENOVATION OF SUBSTATIONS 1-9 MOZAMBIQUE BORDER L INE | 050603 | 4 | 2023/06/30 | 24 | 2 696 612 | - | 2 696 612 | Designs are 100% completed, All disciplines were granted approval by the departmental professionals. Sketch plans are at 100 % Project sketch plans were approved on the 29 August 2021 The instruction was issued on the 13/10/2021 from KAM head office not to proceed with the project to the next stage since all DOD projects that on status 4 (Design Development ) will not be funded

## Slide 7: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS ON PLANNING PHASE OF IMPLEMENTAION (3 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | 
LOUIS TRICHARDT | AIR FORCE BASE | MAKHADO: FOLLOW ON RAMP FOR REFUELLING SYSTEM | 051081 | 4 | 2024/06/30 | 36 | 200 000 | 578 072 | - 378 072 | Status core report was submitted in October 2019 Project is on hold pending completion of site clearance process Design development stopped due to lack of funding
LOUIS TRICHARDT | AIR FORCE BASE | MAKHADO: SERVICE AND REPAIR OF FIRE PROTECTION AND MONI TORING SYSTEM | 051918 | 4 | 2022/09/27 | 24 | 708 434 | - | 708 434 | design development was completed Project Manager is in the requesting approval of funding prior to advertised Project is scheduled to be advertised in October 2022
LOUIS TRICHARDT | AIR FORCE BASE | MAKHADO: REPLACEMENT AND REPAIR OF ROOF AND SERVICING OF KIT CHEN EQUIPMENT | 051919 | 4 | 2023/03/31 | 24 | 1 017 500 | - | 1 017 500 | Project is on design development phase Sketch plans approval scheduled for end of March 2022 Project is scheduled to be advertised beginning of May 2023

## Slide 8: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS ON PLANNING PHASE OF IMPLEMENTAION (4 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | 
PHALABORWA | MILITARY BASE | 5 SPECIAL FORCES: HEBRON RESIDENTIAL AREA: REHABILITATION OF STATE HOUSES | 051927 | 4 | 2022/08/27 | 24 | 2 500 000 | - | 2 500 000 | Project is on design development phase First proposed civil engineering designs were rejected on the basis credentials of the engineer who proposed and approved the designs Revised designs are expected by the end of September 2022
CAPE TOWN | 2 MILITARY HOSPITAL | TOTAL FACILITIES MANAGEMENT CONTRACT | 056348 | 4 | 2022/07/29 | 48 | 37 469 379 | - | 37 469 379 | The project has been registered onto the 2022/2023 Departmental Procurement Plan. BSC has finalised and submitted for NBAC approval both the Procurement Strategy and Terms of Reference on the 14/07/2022. FM Branch awaits the outcome from NBAC to go out on tender. Taking into consideration the delays experienced from the above, the envisaged date for the appointment of TFM SP for 2 Mil Hosp is mid October 2022
 |  |  |  |  |  |  | 101 281 986 | 6 695 617 | 94 586 369 | 

## Slide 9: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS IN CONSTRUCTION PHASE WITH ALLOCATION (1 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | PROGRESS
Kimberley | 3 S A I battalion | Repairs and renovations to the mess complex | 046877 | 5B | 2020/11/26 | 6 | 1 330 911 | - | 1 330 911 | Project Manager discovered that DoD is utilising kitchen and reconnected all the equipment’s before practical completion is taken DoD is utilising the facility to prepare meals for SAPS recruits SAPS training scheduled to be completed in December 2022. Project is suspended indefinitely
Johannesburg |  | SA Irish military base: repairs and renovations to entire military bases | 046956 | 5B | 2016/05/06 | 18 | 12 000 000 | 202 453 | 11 797 547 | First contractor was terminated due to under performance and cash-flow problem Regional Office is in the process of sourcing replacement contractor Project is scheduled to be advertised by end of August 2022

## Slide 10: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS IN CONSTRUCTION PHASE WITH ALLOCATION (2 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | PROGRESS
Mthatha | Military base | 14 SAI: refurbishment of internal roads | 049607 | 5B | 2021/02/09 | 24 | 21 090 000 | 3 736 289 | 17 353 711 | The contract was signed in February 2021 Site hand over was delayed by approval of OHS file and the approval of file which was delayed by the work permit from the Department of Labour. The site hand over meeting was held on the 23 June 2021. The overall progress is 40% which is behind the schedule as it was supposed to be at 63%. The expenditure is 32% and the timed lapsed is 70%. The project is behind the schedule due to rainy weather and issues of site management by the contractor which have since been was resolved. Project is anticipated to be completed on the 23rd of January 2023.

## Slide 11: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS IN CONSTRUCTION PHASE WITH ALLOCATION (3 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | PROGRESS
CAPE TOWN | YSTERPLAAT AIR FORCE BASE | INSTALLATION OF FIRE DETECTION SYSTEM | 050719 | 5B | 2019/11/06 | 12 | 2 000 862 | 326 783 | 1 674 079 | Progress claimed by contractor at 67%. Value of work certified 72.6%. EOT 8 claim was rejected - needs to be revised. VO's outstanding, waiting on information from consultant. Outstanding VO's needs to be approved because it has a bit impact on the progress of work outstanding. Project is scheduled to be completed in November 2022
MTHATHA | MILITARY BASE | 14 SAI: CONDITION BASED MAINTENANCE FOR THE ENTIRE BASE INLCULDING BUILDING, ELECTRICAL, MECHANICAL AND CIVIL WORKS | 051728 | 5B | 2017/08/17 | 36 | 59 584 480 | 32 557 242 | 27 027 238 | Project is construction stage Progress to date is 73% expenditure 64% against 47% Project is scheduled to be completed in March 2023

## Slide 12: Progress report on the maintenance and refurbishment of all DOD facilities currently under the maintenance of the DPWI;
STATUS OF PROJECTS IN CONSTRUCTION PHASE WITH ALLOCATION (4 OF 4)
TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | CONTRACT PERIOD | TOTAL ALLOCATION | TOTAL EXP | BALANCE | PROGRESS
RANDFONTEIN | MILITARY BASE | PRESIDENT KRUGER: BUILDING: COMPLETE REPAIR AND RENOVATION I NCLUDING FENCING | 051822 | 5B | 2020/02/11 | 18 | 19 923 399 | 12 482 751 | 7 440 648 | Project is in construction phase Progress to date is 90% Project anticipated to be completed on the 30th Aug 2022
CAPE TOWN |  | SA NAVY SILVERMINE: REPAIR TO THE SECURITY FENCE AT THE RADI O COMMUNICATIONS HUB | 053071 | 5B | 2017/12/13 | 10 | 1 225 000 | - | 1 225 000 | Progress on site is at 91% and expenditure stands at 85%. Currently the time lapsed on the project stands at 557% Project expected to be completed in September 2022
 |  |  |  |  |  |  | 117 154 652 | 49 305 518 | 67 849 134 | 

## Slide 13: END OF PRESENTATION
THANK YOU!