## Slide 1
PRESENTATION TO THE PORTFOLIO COMMITTEE
ON ARTS AND CULTURE
02 September 2022
PESP 3 STATUS UPDATE

## Slide 2
ART IS POWER! WA TWA!

## Slide 3
The PESP Call was released on 20 June 2022 and closed on 29 July 2022.
The closing time was initially set for 17h00. However, the traffic on the GMS around the closing time slowed down the system, which led to numerous requests from the sector to extend the closing time.
The closing time was extended to 12h00 midnight.
1. BACKGROUND

## Slide 4
The NAC received a total 4810 applications for the PESP.
Applications were submitted through the Grant Management System and as well as manual submissions.
9 455 were registered on the Grant Management System, however, 4 465 submitted were submitted online.
345 manual applications were received.
2. UPDATE ON APPLICATION SUBMISSIONS

## Slide 5
3. UPDATE ON APPLICATION SUBMISSIONS APPLICATIONS RECEIVED PER DISCIPLINE
CRAFT | DANCE | MUSIC | THEATRE | VISUAL ARTS | MULTI-DISCIPLINE | LITERATURE | NO FORMS | TOTAL
402 | 327 | 1108 | 510 | 381 | 1766 | 274 | 42 | 4810
GMS + MANUAL SUBMISSIONS

## Slide 6
4. UPDATE ON SUBMISSIONS APPLICATIONS RECEIVED PER DISCIPLINE

## Slide 7
5. UPDATE ON SUBMISSIONS: PROVINCIAL REPRESENTATION OF APPLICATIONS RECEIVED
EC | NC | LIM | KZN | NW | MP
477 | 175 | 476 | 739 | 399 | 349
Overall stats (Manual + GMS)
WC | FS | GP | Not Stated | Total
270 | 407 | 1458 | 60 | 4810

## Slide 8
5. PROVINCIAL REPRESENTATION OF APPLICATIONS RECEIVED
Overall stats (Manual + GMS)
Chart: Provincial statistics
| EC | NC | LIM | KZN | NW | MP | WC | FS | GP
 | 477 | 175 | 476 | 739 | 399 | 349 | 270 | 407 | 1458

## Slide 9
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
1. MOA signed between DSAC and NAC to roll out the plan | Signed MOA setting out deliverables and timelines | DSAC Project Leadership, Interim CEO, Director General | 20-04-2022 | 10-05-2022 | MOU signed and sent to DSAC.
2. Finalise guidelines and criteria for funding allocation to beneficiaries supported by a NAC governance policy on grant allocation. Funding guidelines in place detailing eligibility of applicants, excluded persons from applications, compliance requirements, etc. | Signed off funding criteria by POCC Chair and grant governance policy by Council Guidelines developed and approved by Council | Project Leader Interim CEO POCC | 25 -04-2022 | 03-05-2022 | Complete, approved by Council.

## Slide 10
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
3. Identify resource needs for the Funding Call and allocate responsibilities to project team. Confirmation of available financial resources for recruitment. | HR Plan approved | Project Leader supported by HR Manager and Interim CFO. | 05-04-2022 | 30-04-2022 | Complete. HR plan approved
4. Set up a call Centre with the required equipment, telephone and internet lines. | Operational Call Centre | Project Leader/IT Manager | 04 -04-2022 | 15-05-2022 | Complete. Call Centre operational.

## Slide 11
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/ MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
5. Engage key stakeholders (local authorities, industry partners on helpdesks). | Stakeholder engagement plan and communications plan presented and approved by Council | Marketing and Communications Manager | 25-04-2022 | 31- 05- 2022 | Stakeholder Engagement Plan and Communication plan currently being implemented.
6. Undertake virtual roadshows throughout the nine provinces to engage prospective applicants. | Workshops undertaken | Project Leader ADOs Programme Manager | 01-07-2022 | 22-07-2022 | Complete. Virtual road shows undertaken in all the nine provinces. Physical roadshows took place in the North-West and KZN province organized by the respective provinces.

## Slide 12
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
7. Vetting system led by a compliance officer | Detailed vetting process approved for admin compliance Detailed vetting process for all applications eligible for Panel adjudication (including checking against the CIPC and NPO register) | Compliance Officers | 01-07-2022 | 26-08-2022 | Not started. Applications still in progress of administration review.
8. Reviewing and verification process | Verified list of applications Verified list of Declined Verified list of shortlisted applications for panel review | Arts Development Team Programme Manage | 01-07-2022 | 26-08-2022 | Reviews have started. Applications still in progress of administration review. Verification not started yet.

## Slide 13
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
9. Adjudication process | Index of Panel reviews for recommended applications Index of Panel reviews for declined applications Accurate budget allocation Panel reports/Minutes | Advisory Panels/ Arts Development Team/Finance Team/Project Leader | 15-08-2022 | 16-09-2022 | Budget allocation per panel approved by Council. Not started with funding indexes. Applications are still at the administration and panel review stage.
10. Panel of Chairpersons Committee (POCC) – endorsement and recommendations | Recommended applications for approval Approved Panel reports | POCC Project Leader | 19-09-2022 | 22-09-2022 | Not started. Advisory Panels have not made recommendations yet.

## Slide 14
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
11. Council Approvals and Announcement | Approved and signed funding indexes/ schedules Funding announcements published on NAC website | Council Project Leader Programme Manager Communications and Marketing Manager | 23-09-2022 | 30-09-2022 | Not started. Applications still in progress of administration review.
12. Contracting with successful applicants | Grant notification letters issued Contracting | Interim CEO Finance team Arts Development Team Project Leader Programme Manager | 07-10-2022 | 28-10-2022 | Not started. Applications still in progress of administration review.

## Slide 15
6. PROGRESS ON TIMELINES
KEY MILESTONES | KEY PERFORMANCE INDICATOR/MEASURE | RESPONSIBILITY | TIME FRAME |  | 
 |  |  | START DATE | END DATE | STATUS
13. Reporting, Monitoring and Evaluation | Funding disbursements Monitoring of project implementation Assessments of project reports and financial reports | Arts Development Team, Monitoring and Evaluation Finance and Compliance Officers | 01-11-2022 | 30-04-2023 | Not started.
14. PESP close out report | Approved and signed close out report | Project Leader Interim CEO Council | 31-03-2023 | 31-05-2023 | Not started.

## Slide 16
Post the closing date, the NAC Website and social media infographics informs and guides applicants in respect of the contracting process and the requirement for compliant tax status.
Further information guidelines will be run throughout the review process and during post funding phase.
7. COMMUNICATION AND FUNDING POST FUNDING

## Slide 17
Review of applications in progress. Panel members have begun with their reviews
It is envisaged that Advisory Panel meetings will commence from 02 September to finalise recommendations.
Outcomes will be released on 30 September 2022.
Release of Grant Notification Letters and contracting phase will be in October.
8. PROGRESS TO DATE

## Slide 18
COMMENTS/QUESTIONS/NOTES
THANK YOU