## Slide 1: DEPARTMENT OF EDUCATION COVID -19 PPE REPORT PERTAINING TO AG’S SPECIAL REPORT

## Slide 2: Table of contents
COVID -19 EXPENDITURE REPORT
STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG
IRREGULAR EXPENDITURE INCURRED
CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION

## Slide 3
COVID -19 EXPENDITURE REPORT

## Slide 4: COVID 19 EXPENDITURE
Expenditure per economic classification | 2020/21 | 
 | Budget | Expenditure
 | R'000 | R'000
Compensation of employees |  | 
Screeners and Cleaners | 197 384 | 193 148
Goods services | 160 884 | 94 563
Transfers and subsidies: Section 21 schools | 9 000 | 8 615
 | 367 268 | 296 326

## Slide 5: COVID 19 EXPENDITURE…CONT
The COVID -19 expenditure was incurred on procurement of the following:
Cloth Masks
Gloves
Face Shields
Sanitisers
Aprons
Thermometers
Disinfectants and other measures

## Slide 6
STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG

## Slide 7: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG
DEFICIENCIES IDENTIFIED ON PPE NEEDS ASSESSMENT | 
Finding | Different processes were implemented to determine the PPE needs at schools. Some of Provincial departments of education did not take advantage of (SA-SAMS) to determine the PPE demand and need assessment for schools in terms of the number of employees and learners
AG Recommendation(s) | The management should ensure that SA-SAMS and other systems such as EMIS are regularly updated so that they can be used as a source of needs assessment
Why the finding(s) couldn’t be avoided | The Department used SA-SAMS data which was not updated in Term 2 to determine the PPE demand and needs assessment.
Investigation(s) & outcomes | Schools monitoring was performed by Management during the first week of the first cohort and deficiencies on needs assessment identified were reported and addressed by top up of PPEs needed.

## Slide 8: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Measures implemented to strengthen Internal Control Weakness | SA-SAMS is updated regularly to produce reliable data to be used for establishing COVID-19 Essential needs analysis for schools. PPEs were classified by grades, teachers and non- teaching staff and principals signed off reports on the PPEs received. Shortages were reported timeously and top ups made. Roles have been clarified for each section in the whole process from needs assessment , requisitions , procurement and delivery to districts and subsequently to schools.

## Slide 9: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
DEFICIENCIES IDENTIFIED ON PPE SUPPLIED TO SCHOOLS | 
Finding | There was no consistency in terms of how PPE were distributed to schools in the province, districts and schools. This resulted in insufficient PPE supplied to schools.
Recommendation(s) | The provincial department of education management should follow-up with schools to identify schools that are financially struggling to assist in procuring PPEs for additional school officials and volunteers and also close a gap of PPE shortages such as face shields for educators.
Why the finding(s) couldn’t be avoided | The usage of SA-SAMS data that was not updated in Term 2. The bulk order that was placed with Imperial Health Sciences (Transversal Contract) on 21/04/2020 got cancelled in order to prioritise Health Department. This led to new orders being placed on 14/05/2020 using request for quotations which was limited to R 500 000. Due to limited stock availability in the market and urgent delivery timelines, some order dates became very close to the delivery dates and some deliveries could not arrive on time at schools.

## Slide 10: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Investigation(s) & outcomes | Monitoring of Schools was performed during the first week of the first cohort and deficiencies identified were reported and addressed by topping up the supply. The department bought PPEs for additional school officials and volunteers. All public schools were catered for in the procurement of COVID 19 Essentials.

## Slide 11: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Measures implemented to strengthen Internal Control Weakness | Management has ensured that SA-SAMS is updated regularly whereby all levels are now required to submit signed off quality validation certificates. Orders were placed according to the requests made by districts informed by the number of learners, educators, and non-teaching staff at schools. Learners signed registers as proof that they had received the masks. A template was developed and used by districts and schools to record what was requested against what had been received and what was still outstanding. Over or under supply of PPEs detected were corrected.

## Slide 12: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
DEFICIENCIES IDENTIFIED ON QUALITY OF PPE SUPPLIED TO SCHOOLS | 
Finding | Substandard quality of PPE were delivered to schools by suppliers. The following are examples of schools supplied with such PPEs: Leolane and Ramoshie schools.
AG Recommendation(s) | The provincial department should follow-up on the suppliers that delivered PPE that are defective and implement corrective measures. The provincial department of education management should develop and provide guidelines for districts and schools to ensure that they verify quality of products received within the turn-around time so that the department can implement corrective measures to address quality defects timely.

## Slide 13: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Why the finding(s) couldn’t be avoided | There were no guidelines on how to verify quality of products immediately when received, and also how to handle deficiencies in COVID-19 Essentials when identified (Masks). There were tight timeframes, limited stock availability in the market, as a result some deliveries arrived at night and during weekends when officials did not have ample time to check quality per specifications immediately more especially masks. More than one service provider delivered to one district in big quantities which made it difficult to check the quality of each mask.

## Slide 14: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Investigation(s) & outcomes | Deliveries happened at the Districts and Head Office acted as soon as quality concerns were raised. The investigations at the two schools were made although it was after the Auditor General finalised their audit. The department performed further investigations at other schools and products with deficiencies on quality were returned to district offices to identify service providers who delivered them.
Action(s) against officials & service providers( blacklisting & recovering money) | 10 000 defective face shields, amounting to R400 000, were identified by head office and were returned to the service provider immediately for replacement with correct quality. The replacement was done within 4 days as per the agreement. No investigations were initiated after the service providers replaced the defective products.

## Slide 15: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Measures implemented to strengthen Internal Control Weakness | Guidelines in line with the specifications for masks to identify deficiencies on quality were developed and communicated by EAP to schools. Penalty clause was also included in the request for quotation as well as in the purchase order.

## Slide 16: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
PROCUREMENT AND CONTRACT MANAGEMENT - NON-COMPLIANCE WITH NATIONAL TREASURY DISASTER MANAGEMENT INSTRUCTION NOTE | 
Finding | The North West department did not include the minimum threshold for local content as evaluation criteria. This constituted non-compliance with National Treasury instruction note 5 par. 4.6(d) (amended on 21 May 2020), 2011 Preferential Procurement Regulations (PPR) 9(1) and 2017 PPR 8(2), which aim to benefit local communities. These state that, for designated sectors, the invitation to tender issued by organs of state must include a specific condition that only locally produced or manufactured goods that meet the minimum threshold for local production and content will be considered. The department did not comply with these requirements. The North West department did not ensure that all suppliers were registered on the DSBD database as per National Treasury instruction note 5 of 2020-21. This constituted non-compliance with supply chain laws and regulations.

## Slide 17: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
AG Recommendation(s) | The department should strengthen payment processing controls and daily review controls, and should match and reconcile delivery notes with invoices before making payment. All payment documentation should be stamped “paid” as soon as the payment has been made to avoid invoices being presented for payment more than once. The department should reconcile PPE items ordered, delivered and distributed to detect and correct discrepancies. People who sign supporting documents for transactions should always print their names next to their signatures and attach these documents to the relevant payment vouchers. The department should keep a specimen list of signatures.

## Slide 18: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
AG Recommendation(s) | The department should strengthen daily controls and monitoring controls to ensure that the regulations in the National Treasury instruction notes for emergency procurement in response to the national state of disaster are adhered to when procuring PPEs. The department must stay up to date with legislation amendments from the National Treasury to ensure compliance. They should also implement dedicated preventative and detective controls to ensure compliance with SCM regulations, particularly local content requirements and any new developments. The education department should ensure that all goods purchased are within scope for the contract concluded by the department of health. The department must start identifying suppliers that can supply goods falling outside the scope of the contract to avoid future irregular.

## Slide 19: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Why the finding(s) couldn’t be avoided | The limited suppliers that were registered on the DSBD database in North West did not have enough capacity to cater for the number of masks that were required at that particular time. SCM operated with skeleton staff during that time as a result effective quality assurance could not be performed at Request For Quotation stage, hence the local content was not applied consistently. The Department used declaration of interest forms to determine whether employees were involved in other businesses. If not declared, the department was unable to detect employees who are doing business with other organs of state, (Municipalities), however none of the employees have done business with the department.
Investigation(s) & outcomes | AG has provided the department with a list of 34 employees who did business with organs of state, mainly with municipalities, these employees are being subjected to disciplinary action. SIU investigated procurement of the PPEs, and recommendations to discipline affected employees has been made to the department.

## Slide 20: STATUS OF IMPLEMENTATION OF THE RECOMMENDATIONS BY AG…cont
Measures implemented to strengthen Internal Control Weakness | A checklist was developed that incorporated all the National Treasury Instruction Notes, Preferential Procurement Regulations and SCM regulations. This checklist was also aligned to the reviewed Standard Operating Procedures (SOPs) and it was used from Request for Quotation, evaluation, ordering, delivery, invoicing and payment processes. This strengthened daily controls and monitoring tools. Amendments on legislation are communicated immediately to ensure officials stay up to date with legislation. Preventative and detective controls are implemented. All documents are sent to Internal Control for pre-auditing to conduct compliance checks in order to pick up and prevent irregularities proactively. The identification of bid rigging indicators are also detected at this stage. Non compliance is recorded in the non compliance/irregular expenditure register, investigations in that regard will follow and the outcome thereof will determine the necessary actions to be taken.

## Slide 21
IRREGULAR EXPENDITURE INCURRED IN RELATION TO COVID -19

## Slide 22: IRREGULAR EXPENDITURE INCURRED IN RELATION TO COVID -19
No. | Supplier Name | Description of incident | Amount
1. | Oletile Holdings | One quotation attached | R1 035 000
2. | Mainstreet 699mpty ltd | Highest scoring supplier not appointed | R989 000
3. | NA Tsunke | Highest scoring supplier not appointed | R1 225 000
4. | Kamogelo Investment | Requisition not approved by Accounting officer | R 1 221 875,00
5. | Taddi Ya Musa Enterprises | Not registerred on SBD | R 975 000,00
TOTAL |  |  | R5 445 875

## Slide 23
CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION

## Slide 24: CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION
Thirty four (34) officials who conducted business with organs of state as detected by AG were investigated and the progress registered is as follows:
Of the 34 cases 25 have been finalised, final written warnings were issued, suspension without pay for three months was also part of the sanctions, some of the officials had resigned;
The remaining 9 cases are pending due to non-responsive municipalities;

## Slide 25: CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION…CONT
Special Investigation Unit (SIU) cases:
  Five (5) cases received
  Three (3) finalised -02 dismissed (Former CFO and SCM Assistant Director) [Of the two dismissed one is on arbitration (Former CFO - scheduled for 12-13 September 2022), 01 not guilty (SCM Office Manager)
  Two (2) cases are still ongoing (Chief Director FMS – to be scheduled and Deputy Director SCM - scheduled for 29-31 August 2022)

## Slide 26: CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION…CONT
Former CFO is linked to the irregular appointment of Red Eyes Trading Enterprise (Pty) Ltd and Kamogelo Investments
Former SCM Assistant Director is linked to Red Eyes Trading
SCM Office Manager is linked to the following companies:
Mainstreet 699 (PTY) LTD
Tadi ya Musa Enterprise
Tadi ya musa Enterprise
NA Tsunke (PTY) LTD
Health Zone Pharmacy and Clinic

## Slide 27: CONSEQUENCE MANAGEMENT PROGRESS REGISTERED PERTAINING TO NON COMPLIANCE WITH SCM LEGISLATION…CONT
Chief Director FMS is linked to the following companies:
Mainstreet 699 (PTY) (LTD)
Tadi Ya Musa Enterprise
CTU Manufcturers
Health Zone Pharmacy
NA Tsunke
Deputy Director SCM is linked to the following companies:
Red Eyes Trading
D Xtra Trading
Kamogelo Investments

## Slide 28: Thank You