## Slide 1: PRESENTATION ON THE ECD CONDITIONAL GRANT TO THE SELECT COMMITTEE
07 September 2022

## Slide 2: PURPOSE
Brief the Select Committee members on the implementation of ECD Conditional Grant with specific focus on
  Performance during 2021/22 financial year;
  Status of the migration of ECD from DSD to DBE

## Slide 3: BACKGROUND
In order to enhance the implementation of the ECD policy, National Treasury allocated an amount of R1,057 billion as a conditional grant in the 2021/22 financial year to enable National DSD to better control and ring-fence expansion of ECD in the country in line with the approved national Integrated ECD Policy.
During the 2021/22 financial year, an additional amount of R178 million was allocated to the Department to extend the ECD Employment Stimulus Relief Fund until 31 March 2022
The total ECD conditional grant allocation of R1,235 billion was aimed at:
  Increasing the coverage of children accessing ECD services through the ECD subsidy to poor children;
  Assist to improve the conditionally registered ECD centres to meet basic requirements in order to be fully registered; and
  To contribute to the Department of Social Development’s efforts to re-invigorate the ECD sector from the hardships emanating from the impacts of COVID-19.
The grant is divided into three components:
  Subsidy component (including the ECD Stimulus Relief Fund);
  ECD maintenance component; and
  Administration component.

## Slide 4: KEY CONDITIONS OF THE ECD CONDITIONAL GRANT
Subsidy Grant
The grant will assist registered ECD centres that are not fully funded from the equitable share, fully and conditionally registered centres that are not funded and registered non-centre based ECD programmes not funded. The subsidy is targeted at qualifying children from birth to 5 years or until they enter Grade R.
The value of the subsidy paid is at a rate of R17 per child for a maximum period of 264 days.
The value of the subsidy for non-centres based programmes is R6 per child for the number of sessions conducted.

## Slide 5: KEY CONDITIONS OF THE ECD CONDITIONAL GRANT
  INFRASTRUCTURE GRANT
Partial care facilities offering ECD programmes that are registered conditionally or unregistered will be eligible for the maintenance grant.
Minor building and maintenance improvements is aimed at ensuring ECD centres comply with the health and safety norms and standards, as identified by the National Department of Social Development, will be funded from the grant.
Provinces must conduct assessments of conditionally registered centres and cost them in order to qualify for maintenance grant funding in 2022/23.
All maintenance projects must be recorded on the National Treasury Infrastructure Reporting Model (IRM).

## Slide 6: ECD STIMULUS
CONDITIONS FOR ELIGIBILITY
ECD services that are fully or conditionally registered to provide ECD services with their Provincial Department of Social Development
Unregistered ECD services that provide early learning are eligible to benefit from the ECD-ESRF.
THE TYPES OF ECD SERVICES THAT ARE ELIGIBLE INCLUDE:
ECD centres; and
The following non- centre-based services which are:
o Play groups
o Toy Library
o Child Minder
o Mobile ECD
An ECD service does not need to be a registered as an NPO to receive this benefit.
Organisations that run, manage or oversee multiple centre and or non-centre based ECD services, may apply for more than one ECD programme and more than one type of ECD programme.
If the organisation does not directly employ the staff in the centre and non-centre based ECD service and provides an oversight and support role, then a written and signed agreement must have been in place prior to the 01 March 2020 with each programme applied for, which governs the relationship with that programme and sets out respective roles and responsibilities

## Slide 7
ECD CONDITIONAL GRANT 2021 MTEF ALLOCATIONS
Province | 2021/22 | 2022/23 | 2023/24
 | R'000 | R'000 | R'000
Eastern Cape | 157 970 | 172 974 | 180 313
Free State | 63 533 | 57 703 | 60 151
Gauteng | 152 107 | 166 961 | 174 044
KwaZulu-Natal | 227 031 | 246 758 | 257 227
Limpopo | 143 443 | 146 231 | 152 435
Mpumalanga | 96 251 | 95 254 | 99 295
Northern Cape | 25 302 | 24 196 | 25 223
North West | 88 751 | 101 924 | 106 249
Western Cape | 102 273 | 101 631 | 105 943
Unallocated | - | 78 286 | 81 607
Total | 1 056 661 | 1 191 918 | 1 242 487

## Slide 8: COMPLIANCE TO THE GRANT FRAMEWORK 2021/22 AND PERFORMANCE

## Slide 9: RESPONSIBILITIES OF NATIONAL DEPARTMENT
 | National Responsibility | Compliance
1 | Appointment and management of service providers; | Completed
2 | Develop Business Plans and submit after they get signed off by Heads of Department to national DSD; | Completed
3 | Provinces to implement the Business Plans as approved by national department (national should be notified in writing about deviations before implementation can take place); | Completed
4 | Comply with terms and conditions of the receiving officer outlined in the Division of Revenue Act (DoRA); | Completed
5 | Submit monthly financial reports to National Treasury 15 days after the end of the month; | Completed
6 | Submit quarterly performance reports to national department within 30 days after the end of each quarter; | Completed

## Slide 10: RESPONSIBILITIES OF PROVINCIAL DEPARTMENT
 | National Responsibility | Compliance
1 | Appointment and management of service providers; | Completed
2 | Develop Business Plans and submit after they get signed off by Heads of Department to national DSD; | Completed
3 | Provinces to implement the Business Plans as approved by national department (national should be notified in writing about deviations before implementation can take place); | Completed
4 | Comply with terms and conditions of the receiving officer outlined in the Division of Revenue Act (DoRA); | Completed
5 | Submit monthly financial reports to National Treasury 15 days after the end of the month; | Completed
6 | Submit quarterly performance reports to national department within 30 days after the end of each quarter; | Completed

## Slide 11: Financial allocations, payments and expenditure 2021/22

## Slide 12
ECD CONDITIONAL GRANT ALLOCATIONS VS EXPENDITURE FOR THE 2021/22 FINANCIAL YEAR
The Department also monitored funds that were approved for rolled over from the 2020/21 financial year.
A total amount of R385,658 million was approved for roll-over to the 2021/22 financial year in the PDSD allocation as part of Provincial Treasury.
Grant Component | Original Allocation | Additional | Final | Provincial Roll Overs | Total Available Budget for 2021/22 | Expenditure | Over/Underspending
 | 2021/22 | Allocation | Voted | from 2020/21 | R'000 | 2021/22 | 
 | R'000 | R'000 |  | R'000 |  | R'000 | 
Subsidy | 939 081 | - | 939 081 | 13 606 | 952 687 | 892 034 | 60 653
ECD Employment Stimulus Funds | - | 178 000 | 178 000 | 351 853 | 529 853 | 245 259 | 284 594
Total Subsidy Component | 939 081 | 178 000 | 1 117 081 | 365 459 | 1 482 540 | 1 137 293 | 345 247
Maintenance Component | 86 741 | - | 86 741 | 20 199 | 106 940 | 73 416 | 33 524
Administration Component | 30 839 | - | 30 839 | - | 30 839 | 24 166 | 6 673
Totals | 1 056 661 | 178 000 | 1 234 661 | 385 658 | 1 620 319 | 1 234 875 | 385 444

## Slide 13: TOTAL ALLOCATION TO PROVINCES FOR THE 2021/22 FINANCIAL YEAR
 | 2021/22 |  | 
Provinces | Voted | ECD | Final
 |  | Stimulus | Approp
 | R'000 | R'000 | R'001
Eastern Cape | 157 970 | 26 611 | 184 581
Free State | 63 533 | 10 702 | 74 235
Gauteng | 152 107 | 25 623 | 177 730
KwaZulu-Natal | 227 031 | 38 245 | 265 276
Limpopo | 143 443 | 24 164 | 167 607
Mpumalanga | 96 251 | 16 214 | 112 465
Northern Cape | 25 302 | 4 262 | 29 564
North West | 88 751 | 14 951 | 103 702
Western Cape | 102 273 | 17 228 | 119 501
Total | 1 056 661 | 178 000 | 1 234 661

## Slide 14: SUMMARY 2021/22 BUDGET VS EXPENDITURE AS AT 31 MARCH 2022
The National Department of DSD transferred 100% of the allocated budget of R 1,235 billion in line with the approved payment schedules.
Included in the total expenditure of R1,235 billion is funds rolled over from the 2020/21 financial year.
Province | Budget | Provincial Roll overs | Total available | Spent at | Percentage Spent by Provincial DSD
 | Allocation |  |  | 31-Mar-22 | 
 | R'000 | R'000 | R'000 | R'000 | %
Eastern Cape | 184 581 | 60 270 | 244 851 | 183 870 | 75%
Free State | 74 235 | 37 336 | 111 571 | 93 854 | 84%
Gauteng | 177 730 | 77 763 | 255 493 | 195 164 | 76%
KwaZulu-Natal | 265 276 | 85 185 | 350 461 | 276 884 | 79%
Limpopo | 167 607 | 46 589 | 214 196 | 178 247 | 83%
Mpumalanga | 112 465 | 38 196 | 150 661 | 105 415 | 70%
Northern Cape | 29 564 | 9 519 | 39 083 | 34 214 | 88%
North West | 103 702 | 28 795 | 132 497 | 48 140 | 36%
Western Cape | 119 501 | 2 005 | 121 506 | 119 086 | 98%
Totals | 1 234 661 | 385 658 | 1 620 319 | 1 234 874 | 76%

## Slide 15: PERFORMANCE ON INFRASTRUCTURE COMPONENT

## Slide 16: PROVINCIAL PERFORMANCE ON THE INFRASTRUCTURE GRANT PER QUARTER
Province | Annual Target | Q1 | Q2 | Q3 | Q4 | Total ECD’s benefiting from the grant (Q1-4)
Eastern Cape | 9 | 0 | 0 | 6 | 2 | 8
Free State | 41 | 0 | 0 | 11 | 16 | 27
Gauteng | 17 | 0 | 0 | 0 | 12 | 12
KwaZulu Natal | 45 | 0 | 0 | 0 | 14 | 14 (0)
Limpopo | 52 | 0 | 40 | 6 | 5 | 51
Mpumalanga | 38 | 0 | 0 | 2 | 23 | 25
Northern Cape | 9 | 0 | 0 | 0 | 4 | 4 (9)
North West | 12 | 0 | 0 | 0 | 4 | 4
Western Cape | 50 | 19 | 11 | 9 | 11 | 50
Total | 273 | 19 | 51 | 34 | 91 | 195

## Slide 17
Province | Reasons for non- expenditure
Eastern Cape | The low cost ECD was not constructed as there were issues with land. It took longer to resolve the issue of land as the one that was earmarked was owned by the tribal authority. This issue was resolved late in the financial year because the land had to be transferred to the NPO. DBE is taking over the responsibility proceed with constructing with the low cost ECD that was planned to be constructed in 2021/22 financial year in 2022/23 financial year..
Free State | There was a delay in the appointment of an implementing agent. Then there were challenges between the department and DPW&I. As a result the province did not acquire the PTO from the Municipality for the identified site. DBE is continuing and will be implementing the project in-house. They are busy with the BOQ and outstanding engineering drawings together with other projects that were not done in 2021/22.
Gauteng | Some of the ECD centres that were targeted closed down and it was to late to replace them. Infrastructure have not yet received the replacement list from programme. To date there is no work done as there is no replacement.
KwaZulu Natal | There were challenges with the implementing agent relating to delays in procurement of service providers. The project manager left and a new project manager had to be appointed which resulted in further delays. The expenditure is 100% because funds were transferred to the implementing agent. During the 1st quarter there was an agreement between DSD province and Lima to transfer everything in order to enable the implementing agent to procure material and pay contractors. The department opted for the transfer option instead of paying invoices themselves. All backlog projects will be implemented by DBE.

## Slide 18
Province | Reasons for non- expenditure
Limpopo | Construction of the low cost ECD was still underway and contractor not paid. The implementing agent (DPW) only appointed the service provider in February 2022. The project is at 60% completion.
Mpumalanga | The low cost ECD and other centres were not completed and the province made sectional payments to contractors. The implementing agent (DPW) appointed contractors in February 2022. Projects that were not completed are 99%-100% complete but contractors are not paid because of the funds were transferred to DBE.
Northern Cape | The procurement process took long to complete because the province could not find suitable contractors to do the work. The quotation process was done 3 times and only at third attempt the province got suitable contractors but it was already too late since SCM issued an instruction that projects should be stopped by the first week of February 2022 due to the fact that the function was moving to DBE. The projects are still on hold including the current financial year projects.
North West | The procurement process took longer since the quotations that were received from service providers were over the available budget and threshold. The province received quotations for the second time after the second briefing however it was already too late to appoint service providers/contractors. The backlog will be dealt with during 2022/23 financial year by DBE.
Western Cape | The province was not able to make the full payment before the end of the financial year but have since processed all payments.

## Slide 19: Initiatives that NDSD put in place to assist provinces:
Capacity Building
  Made available funding through the conditional grant for the employment of technical staff qualified in the built environment to implement the programme. All provinces appointed staff except Gauteng.
  Developed guidelines to guide provinces on how to implement the infrastructure component of the grant.
  Capacity building was done with provinces on the 22- 23 January 2020, 14-15 October 2020 and 28 September 2021 and 5 October 2021.
  Supported provinces on an advisory capacity as and when they required it.
  Worked with ECD partners e.g. Ilifa Labantwana and PPT to also provide advisory services to provinces.
Procurement processes
  Developed a procurement strategy to address procurement challenges and improve the way provinces appointed contractors to manage the projects but only the Limpopo Province implemented it which is evident in their progress.
Low cost ECD centre designs
  Developed low cost designs for uniformity in the construction of the ECD and to reduce the time taken by provinces to develop their own designs.
Monitoring
  Monitoring visits were undertaken quarterly to check progress on site.
  Quarterly meetings were held with provinces to track progress and provide advice on corrective actions.

## Slide 20: PERFORMANCE ON SUBSIDY COMPONENT

## Slide 21: Summary of performance on Subsidy Grant 2021/22
Province | Target | Number of Children Benefiting | Number of days
Eastern Cape | 14 035 | 8 420 | 264
Free State | 2 085 | 2 084 | 264
Gauteng | 8 135 | 9 079 | 264
KwaZulu-Natal | 14 615 | 14 615 | 264
Limpopo | 12 785 | 9 414 | 264
Mpumalanga | 4 625 | 4 625 | 264
Northern Cape | 1 221 | 1 221 | 264
North West | 6 592 | 9 124 | 264
Western Cape | 8 295 | 4 265 | 264
TOTALS | 72 388 | 62 907 | 

## Slide 22: REASONS FOR UNDER-PERFORMANCE ON SUBSIDY
Late signing of SLAs which affect quarterly payments especially in the NW province.
NPOs non-compliance on submission of reports and compliance documents.

## Slide 23: SUPPORT PROVIDED TO PROVINCES
National supported provinces through the different structures that have been developed which included the Conditional Grant and Coordinators meetings that were held quarterly
The Project Manager also engaged with individual provinces that were struggling to ensure better understanding of the frame working and reporting.
Senior Management structures were used as consultation platforms and for elevation of challenges and decision making.

## Slide 24: PERFORMANCE ON STIMULUS PACKAGE

## Slide 25: BACKGROUD
The Presidential Employment Stimulus fund of R474.3 million was made available to the employees of ECD services in the 2020/21 financial year;
This project was administered by the National Department of Social Development (DSD) until 31 March 2022
  More than 27 000 applications from the ECD sector were received.
  After verifications done, 109 801 ECD practitioners were still to be verified for eligibility for payment.
Province | Number of staff applied | Number of staff eligible
Eastern Cape | 11 392 | 11 329
Free State | 8 235 | 8 034
Gauteng | 25 507 | 25 092
KwaZulu Natal | 20 171 | 18 520
Limpopo | 17 807 | 16 651
Mpumalanga | 8 824 | 8 707
Northern Cape | 6 284 | 6 213
North West | 2 764 | 2 707
Western Cape | 12 636 | 12 548
Total | 113 620 | 109 801

## Slide 26: Presidential Stimulus Package – status as at 31 march 2022
SUMMARY 2021/22 FINANCIAL YEAR |  |  |  |  | 
Province | Roll over approved | Total nr of Staff |  | Staff paid 31 March 2022 | Actual Expenditure at 31 March 2022
Eastern Cape | R 54 370 000.00 | 10 650 |  | 5 739 | R 24 023 454.00
Free State | R 24 915 000.00 | 6 138 |  | 5 932 | R 24 831 382.00
Gauteng | R 77 763 000.00 | 25 092 |  | 10 314 | R 43 174 499.00
KwaZulu Natal | R 79 979 048.00 | 16 150 |  | 11 534 | R 48 281 000.00
Limpopo | R 46 017 000.00 | 13 594 |  | 9 741 | R 40 776 872.00
Mpumalanga | R 30 495 000.00 | 7 226 |  | 5 150 | R 21 557 900.00
Northern Cape | R 9 519 000.00 | 2 041 |  | 2 594 | R 10 859 410.00
North West | R 28 795 000.00 | 6 140 |  | 1 590 | R 6 655 740.00
Western Cape | R - | 12 427 |  | 5 996 | R 25 099 256.00
TOTAL | R 351 853 048.00 | 99 458 |  | 58 590 | R 245 259 513.00

## Slide 27: Presidential Stimulus Package – roll overs requested
The Western Cape provincial Department of Social Development has contracted a “Third party” in the payment and management on the ECD Stimulus Package since the inception of this project. WC is still continuing to proceed with the payments.
SUMMARY 2022/23 ROLL OVER REQUEST |  | 
Province | Roll over REQUESTED | Total No of Staff remaining
Eastern Cape | R 23 664 000 | 5 653
Free State | R 9 640 000 | 2 303
Gauteng | R 23 366 000 | 5 582
KwaZulu Natal | R 38 804 000 | 9 270
Limpopo | R 54 370 000 | 12 989
Mpumalanga | R 30 694 000 | 7 333
Northern Cape | R 5 879 000 | 1 404
North West | R 14 951 000 | 3 572
Western Cape | R - | -
TOTAL | R 201 368 000 | 48 105

## Slide 28: SUPPORT PROVIDED TO PROVINCES
    NPO’s were contracted through our partnership with DGMT to assist ECD organisations to complete the applications.
    Capacity building and information sessions were held with provinces on the implementation and processes for stimulus package by DSD and partners e.g. Nelson Mandela Foundation.
    Different structures were established with all provinces as a platform to support provinces and meetings were held weekly.
    Provinces were assisted and supported during the establishment of help desks at provincial and district levels to enable ECD’s to obtain assistance.
    SMS’s were sent to advise ECD’s on their applications and information that was outstanding
    Reporting and monitoring tools were developed to promote standardisation across the provinces.

## Slide 29: NEXT STEPS ON THE STIMULUS
National Treasury has already made “Roll over funds” recommendations to the Provincial Treasuries;
Once allocation letters has been issued, DSD will assist DBE in the processing of the payment to eligible ECD practitioners:
  Application / payment verification
  ECD Site verification
  ECD guidelines set by Social Development Sector
Payments to all eligible ECD practitioners to be finalised by 31 March 2023 by Department of Basic Education.

## Slide 30: MIGRATON OF ECD FROM DSD TO DBE

## Slide 31: BACKGROUND ON THE ECD FUNCTION
A Cabinet memorandum on the function shift served in Cabinet in March 2022.
On 1 April 2022, the Minister of Social Development, Hon. Ms Lindiwe Zulu, MP, officially handed over the ECD function to the Minister of Basic Education, Hon. Mrs Angie Motshekga, MP.
The launch marked a partnership between the DBE and other State departments, NGOs, civil society, partners and other entities to ensure that all children, including those with disabilities are provided with access to quality ECD.
The handover marked achievement of the commitments of the NDP, ANC’s 54th National Conference and the National Integrated ECD Policy in terms of policy and programme shift.
This also means that the management and implementation of the conditional grant is now being managed by the Department of Basic Education.

## Slide 32: RECOMMENDATIONS
It is recommended that the committee:
Note the presentation in respect of the performance of the ECD conditional grant in 2022/23;
Note that projects that were not completed in 2021/22 will be completed in 2022/23; and
Note that the ECD function has moved from DSD to DBE with effect from the 01 April 2022.

## Slide 33
#ECD IS EVERYBODY ‘S BUSINESS
THANK YOU