## Slide 1: PROGRESS ON IMPLEMENTATION OF A RING-FENCED MIG PROGRAMME BY DSAC
BRIEFING TO THE SPORT, ARTS AND CULTURE
PORTFOLIO COMMITTEE: Date: 20 SEPTEMBER 2022

## Slide 2
PROGRESS ACHIEVED SINCE 2016/17
Since inception of the ring-fencing intervention, DSAC has so far made the following allocations:
ALLOCATION OF THE RINGFENCED SPORT INFRASTRUCTURE GRANT
2016/17 – 30 municipalities = R 300 000 000
2017/18 – 34 municipalities = R300 000 000
2018/19 – 30 municipalities (2 repeats: Gamagara and Lekwa) = R 273 000 000
2019/20 – 22 municipalities (1 repeat: Kamiesberg returned) = R266 000 000
2020/21 – 23 municipalities (3 repeats: Masilonyana, Polokwane & Mahikeng)= R 255 000 000
2021/22 – 29 municipalities (2 repeats: Polokwane and Mahikeng) = R255 000 000
2022/23 – 27 municipalities (9 repeats: Emthanjeni, Mahikeng, Magareng, Umsobomvu, Tokologo, Masilonyane, Mantsopa and Emalahleni) = R252 858 000
NUMBER OF ALLOCATIONS SO FAR = 193
TOTAL AMOUNT ALLOCATED = R 1 901 858 000 (ALMOST R2 BILLION ALLOCATED IN THE PAST 7 YEARS)
NUMBER OF BENEFICIARY MUNICIPALITIES = 178
OUTSTANDING MUNICIPALITIES = 27

## Slide 3: SUMMARY OF OVERALL PERFORMANCE
YEAR | NO. OF PROJECTS ALLOCATED | COMPLETED PROJECTS | INCOMPLETE BUT ON PROGRESS | INCOMPLETE AND STOPPED/ CANCELLED | % OF COMPLETIONS
2016/17 | 30 | 26 | 1 (Kokstad) | 3 (Engcobo & Khai-Ma – Stopped) (Kamiesberg – Cancelled) | 86
2017/18 | 34 | 27 | 2 (Mbizana and Walter Sisulu) | 5 (Raymond Mhlaba Kopanog, Emfuleni – Stopped) (Siyancuma & Langeberg – Cancelled) | 80
2018/19 | 30 | 7 |  |  | 90
2019/20 | 22 | 15 |  |  | 68
2020/21 | 23 (subtract mutl-year projects: Polokwne and Mahikeng) | 15 |  |  | 71 (Mahikeng and Polokwne not factored)
2021/22 | 29 | 1 | 25 | 3 (Matjhabeng/ Siyancuma and Richtersvekd) | 
2022/23 | 27 | na | na | na | na

## Slide 4: SUMMARY OF 2016/17 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 4 | 46 661 | 3 | 1 (Engcobo) | Error in grandstand and change room designs- under investigation COGTA EC
FS | 2 | 20 000 | 2 | 0 | NB: Tokologo Facility: is completed but not functional because municipality lacked funds install engineering services that connect to the main line of sewerage network. The works require additional R3.5 million but DSAC reallocated in 2022/23 to resolve the matter
GP | 1 | 10 000 | 1 | 0 | NA
KZN | 3 | 45 000 | 1 | 1 (Kokstad) | Project commenced without EIA and was stopped due to non-compliance. The project is at 90% completion, the remaining item is tiling of the swimming pool and cleaning.

## Slide 5: SUMMARY OF 2016/17 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
LP | 4 | 38 000 | 4 | 0 | NA
MP | 5 | 36 860 | 4 | 0 | NA
NC | 4 | 27 700 | 2 | 2 (Kamiesberg & Khai-Ma) | Kamiesberg: Project was not registered because site was owned by school and not approved by COGTA. Funds were returned. Municipality was reallocated 2 years later and completed. Khai-Ma: divided the allocation meant for 1 into 3 projects resulting in significant shortfalls in all 3 and were left incomplete, in fact is a worst and unusable state.
NW | 4 | 43 500 | 4 | 0 | NA
WC | 3 | 27 | 3 | 0 | NA

## Slide 6: 2016/2017 FINANCIAL YEAR
4
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT MUNICIPALITY | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC104 | Makana Local Municipality | Sarah Baartman | Upgrading of Joza indoor facility | R13 000 000,00 | Complete
EC137 | Engcobo Local Municipality | Chris Hani | Upgrading of Ngcobo sport field | R13 661 000,00 | Stopped at 60%
EC157 | King Sabata Dalindyebo Local Municipality | O.R Tambo | Upgrading of Ngangelizwe sportfield | R10 000 000,00 | Complete
EC444 | Ntabankulu Local Municipality | Alfred Nzo | Construction of Ntabankulu Sport ground | R10 000 000,00 | Complete
FS163 | Mohokare Local Municipality | Xhariep | Zastron/Itumeleng: Upgrading of Sports facility Zastron/Itumeleng | R10 000 000,00 | Complete
FS182 | Tokologo Local Municipality | Lejweleputswa | Upgrading of Tshwaraganang community stadium | R10 000 000,00 | Complete
GT485 | Randfontein Municipality | West Rand | Construction of Badirile Sport ground within Rand Local Municipality | R10 000 000,00 | Complete
KZN227 | Richmond Local Municipality | uMgungundlovu | Construction of Richmond indoor sport ground | R15 000 000,00 | Complete
KZN262 | Phongola Local Municipality | Zululand | Construction of Phongola Sport Field | R15 000 000,00 | Complete
KZN433 | Greater Kokstad Local Municipality | Sisonke | Construction of Kokstad Sports Field | R15 000 000,00 | 95% completion
LIM331 | Greater Giyani Local Municipality | Mopani | Construction of 3 sites within Greater Giyani Local Municipality | R15 000 000,00 | Complete
LIM335 | Maruleng Local Municipality | Mopani | Construction of a multi purpose facility in Finale Balloon Village | R4 000 000,00 | Complete
LIM353 | Molemole Local Municipality | Sekhukhune | Construction of a multi purpose sport facility in Ramokgopa | R9 000 000,00 | Complete
LIM472 | Elias Motsoaledi Local Municipality | Sekhukhune | Elias Motsoaledi Local Municipality - Upgrading of Hlogotlou Stadium | R10 000 000,00 | Complete

## Slide 7: 2016/2017 FINANCIAL YEAR …
5
MP302 | Chief Albert Luthuli Local Municipality | Gert Sibande | Construction of the Silobela multi purpose facility | R7 232 000,00 | Complete
MP305 | Lekwa Local Municipality | Gert Sibande | Refurbishment of Sakhile ground | R11 500 000,00 | Complete
MP302 | Msukaligwa Local Municipality | Gert Sibande | Refurbishment ofMpumalanga sport ground | R10 128 000,00 | Complete
MP311 | Victor Khanye Local Municipality | Nkangala | Construction of Sport field within Dipaleseng Municipality | R6 600 000,00 | complete
MP312 | Emalahleni Local Municipality | Nkangala | Construction of multi-purpose sports field | R8 000 000,00 | Complete
NC064 | Kamiesberg Local Municipality | Namakwa | Construction of Sports field | R1 200 000,00 | Cancelled- Registration declined
NC067 | Khai Ma Local Municipality | Namakwa | Construction of Poffadder multi-purpose sport field | R8 000 000,00 | stopped
NC072 | Umsobomvu Local Municipality | Pixley ka Seme | construction of Noupoort Community Indoor Gym | R6 500 000,00 | Complete
NC453 | Gamagara Local Municipality | Taolo Gatsewe | Contruction of Kathu multi-purpose sport facility | R10 000 000,00 | Complete
WC012 | Cederberg Local Municipality | West Coast | Upgrading of Clanwilliam sport fields | R7 679 000,00 | Complete
WC034 | Swellendam Local Municipality | Eden Municipalities | Upgrading of Railton sport facility | R7 000 000,00 | Complete
WC053 | Beaufort West Local Munipacility | Central Karoo Municipalities | Upgrading of Merweville Sport Grounds | R12 500 000,00 | Complete
NW381 | Ratlou Local Municipality | Ngaka Modiri Molema | Upgrading of the Setlagole multi purpose sport facility | R15 000 000,00 | Complete
NW383 | Mafikeng Local Municipility | Ngaka Modiri Moleme | Construction of Lotlhakane multi purpose sport field and construction of a multi purpose sport field in Montshiwa | R12 000 000,00 | Complete
NW293 | Mamusa Local Municipality | Dr Ruth Segomotsi Mompati | Upgrading of Itelegeng sport facility | R5 000 000,00 | Complete
NW396 | Lekwa Teamane Municipality | Dr Ruth Segomotsi Mompati | Upgrade of Cristiana multi purpose facility | R11 500 000,00 | Complete

## Slide 8: SUMMARY OF 2017/18 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 4 | 20 321 | 1 | 3 (Raymond Mhlaba, Walter Sisulu and Mbizana) | Raymond Mhlaba: Disputes between main and sub-contractors. Lack of co-operation from municipality compromising DSAC ability to monitor the project. Walter Sisulu: Disputes between Municipality, Contractor & Consultant. Mbizana: – project was co-funded and structured as a multi-year. Progress 95% with final track final layer. Project required R47 million and DSAC allocated R12 million, and municipality co-funded.
FS | 5 |  | 4 | 1 (Kopanong) | Contractor appointed had financial challenges and repudiated from the contract. Project reported to still have R1, 4 million available but outstanding work far exceeds this amount. Only evidence of the works done from R7,8 million is incomplete ablution, courts and few uninstalled pipes. DSAC visited municipality in July to establish plans to complete the facility. No report and plans for completion have been submitted as per resolution so far.
GP | 3 |  | 2 | 1(Emfuleni) | Lack of cooperation with monitoring and support efforts of DSAC. Positions of relevant officials were vacant and there were periodic changes of people acting. Last progress reported was only appointment of Consultants for designs
KZN | 4 | 32 873 | 4 | 0 | NA
LP | 5 | 33 381 | 5 | 0 | NA

## Slide 9: SUMMARY OF 2017/18 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘0000 | COMPLETED PROJECTS | INCOMLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
MP | 5 | 28 654 | 5 | 0 | Thembiisle Hani facility was completed in 2019 but did not comply with norms and standards. Municipality investigated that and still to submit a report.
NC | 3 | 20 867 | 2 | 1 (Siyancuma) | Project never registered with COGTA due to a delay by municipality to acquire approval from SANRAL as the site identified was adjacent to the National road
NW | 3 | 37 274 | 3 | 0 | NA
WC | 2 | 28 000 | 1 | 1 (Langeberg) | COGTA declined to register a project because site identified was positioned for facility to benefit the poor and non-poor households, and therefore required municipality to counter-fund with 50% counter-funding which municipality could not afford

## Slide 10: 2017/2018 FINANCIAL YEAR
6
 | MUNICIPALITY | DISTRICT MUNICIPALITY | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC129 | Raymond Mhlaba Local Municipality | Amathole | Upgrading of Sportfield within Raymond Mhlaba Local Municipality | R5 000 000,00 | Project stopped at , 25%
EC138 | Sakhisizwe Local Municipality | Chris Hani | Upgrading of sports field within Sakhisizwe Local Municipality | R12 500 000,00 | Complete
EC145 | Walter Sisulu Local Municipality | Joe Gqabi | Upgrading of sports field within Walter Sisulu Local Municipality | R10 821 000,00 | Construction, 80%
EC443 | Mbizana Local Municipality | Alfred Nzo | Construction of Sport facility within Mbizana Local Municipality | R12 000 000,00 | 90% complete
FS162 | Kopanong Municipality | Xhariep | Construction of Spoprts field within Kopanong Local Municipality | R9 200 000,00 | Project stopped at 50%
FS185 | Nala Local Municipality | Lejweleputswa | Upgrading of sports facility within Nala Local Municipality | R4 373 000,00 | Complete
FS195 | Phumelela Local Municipality | Thabo Mofutsanyana | Upgrading of Sport field withim Phumelela Local Municipality | R9 604 000,00 | Complete
FS203 | Ngwathe Local Municipality | Fezile Dabi | Construction of a sport field within Ngwathe Local Municipality | R7 412 000,00 | Complete
FS205 | Mafube Local Municipality | Fezile Dabi | Upgrading of a sport field within Mafube Local Municipality | R4 308 000,00 | Complete
GT421 | Emfuleni Local Municipality | Sedibeng | Upgrading of Swimming pool within Emfuleni Local Municipality | R9 593 000,00 | Stopped
GT423 | Lesedi Local Municipality | Sedibeng | Construction of Sport Field within Lesedi Local Municipality | R15 108 000,00 | Complete
GT485 | Westonaria Local Municipality/Rand West City | West Rand | Construction of Multi-purpose centre within Westonaria Local Municipality | R8 172 000,00 | Complete
KZN221 | Umshwati Local Municipality | uMgungundlovu | Construction of Umshwati Local Municipality | R11 000 000,00 | Complete
KZN242 | Nquthu Local Municipality | uMzinyathi | Construction of Sports Field within Nquthu Local Municipality | R11 000 000,00 | Complete
KZN265 | Nongoma Local Municipality | Zululand | Construction of Sports Fields within Nongoma Local Municipality | R11 000 000,00 | Complete
KZN293 | Ndwedwe Local Municipality | iLembe | Construction of Sports Field within Ndwedwe Local Municipality | R11 000 000,00 | complete

## Slide 11: 2017/2018 FINANCIAL YEAR…
7
LIM32 | Greater Letaba Local Municipality | Mopani | Construction of stadium within Greater Letaba Local Municipality | R2 564 000,00 | Complete
LIM334 | Ba-phalabrowa Local Municiapality | Mopani | Construction of stadium within Ba-phalaborwa Local Municipality | R7 084 000,00 | Complete
LIM354 | Polokwane Local Municipality | Capricon | Construction of Sports Complex within Polokwane Local Municipality | R7 764 000,00 | Completed
LIM355 | Lepelle-Nkumpi Local Municipality | Capricon | Construction of stadium within Lepelle-Nkumpi Local Municipality | R5 137 000,00 | completed
LIM471 | Ephraim Mogale Local Municipality | Sekhukhuni | Construction of stadium within Ephraim Mogale Local Municipality | R10 832 000,00 | Complete
MP303 | Mkhondo Local Municipality | Gert Sibande | Refurbishment of Sports Complex within Mkondo Local Municipality | R2 500 000,00 | Complete
MP304 | Dr Pixley Ka Seme Local Municipality | Gert Sibande | Construction of combi courts | R2 500 000,00 | Complete
MP315 | Thembisile Hani Local Municipality | Nkangala | Construction of multi-purpose centre | R5 904 000,00 | Complete
MP324 | Nkomazi Local | Ehlanzeni | Construction of Sport field | R4 654 000,00 | Complete
MP325 | Bushbuckridge Local Municipality | Ehlanzeni | Sonstruction of sports field | R13 096 000,00 | Complete
NC065 | Hantam Local Municipality | Namakwa | Construction of Sports field, Calviania, Neuwoudvlle, Loeriesfontein and Brandvlei | R6 866 588,00 | Complete
NC078 | Siyancuma Local Municipality | Dr. Pixley Ka Seme | Construction of Kemble Sport field | R6 866 588,00 | Cancelled = Funds taken back
NC091 | Sol Plaaitjie Local Municipality | Francis Baard | Construction of Sport field Florinaville swimming pool, Galeshewe stadium and De Beers stadum | R6 866 588,00 | Complete
NW | Taung Local Municipality | Dr. Ruth Segomotsi Mompati | Construction of a sport facility | R15 000 000,00 | Complete
NW371 | Moretele Local | Bojanala Platinum | Construction of sport facility | R15 000 000,00 | Complete
NW385 | Ramotshere Molloa Local Municipality | Ngaka Modiri Moleme | Upgrading of multi-purpose stadium | R7 274 000,00 | Complete
WC047 | Bitou Local Municipality | Garden Route | Construction of a sports ground | R13 000 000,00 | Complete
 | Langeberg Local Municipality |  | Upgrading of sport facilities and multi-purpose courts | R15 000 000 | Cancelled - Registration Declined

## Slide 12: SUMMARY OF 2018/19 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS
EC | 4 | 42 350 | 2 | 2 (Emalahleni and Inquza Hill) | Emalahleni: Contractual disputes with the contractor and contract terminated. Municipality pursuing the legal route. The municipality availed R4 million in 2022/23 to augment additional allocation made by DSAC Ingquza Hill: Municipality could not afford cost escalations arsing from delays caused by COVID.
FS | 4 | 40 280 | 4 | 0 | NA
GP | 1 | 3 659 | 1 | 0 | NA
KZN | 4 | 38 000 | 4 | 0 | NA
LP | 4 | 34 200 | 4 | 0 | NA

## Slide 13: SUMMARY OF 2018/19 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
MP | 4 | 34 974 | 2 | 2 (Dipaleseng and Mbombela) | Dipaleseng: interference by business forum which led to disputes between contractor and municipality- Mbombela: Municipality 85% contractor on site, Municipality counter funded with 13 Million
NC | 4 |  | 2 | 2 (Phokwane & Gasegonyana) | Phokwane - Claims and payment disagreements, repudiation by municipality. Project collapsed and works that were completed are vandalised Gasegonyane – Cashflow challenges by the Contractor and contract terminated.
NW | 3 | 27 550 | 3 | 0 | NA
WC | 2 | 13 965 | 1 | 1 (George) | The municipality had challenges with identified site, letter of concern was sent by DSAC, and closely monitoring, site issue being finalised

## Slide 14: 2018/2019 FINANCIAL YEAR
8
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT MUNICIPALITY | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC121 | Mbashe Local Municipality | Amathole | Upgrading of Ngumbela Sports Facility | R11 400 000,00 | Practical completion
EC136 | Emalahleni Local Municipality | Chris Hani | Construction of Indwe Sport Ground | R11 000 000,00 | Procument of contractor
EC153 | Ingquza Hill Local Municipality | OR Tambo | Construction of ward 3 Multi purpose Sport Field | R8 550 000,00 | Construction,85%
EC441 | Matatiele Local Municipality | Alfred Nzo | Construction of Cedarville Sport Center | R11 400 000,00 | Complete
FS161 | Letsemeng Local Municipality | Xhariep | Upgrading of stadium in Sonwabile | R12 065 000,00 | Complete
FS183 | Tswelopele Local Municipality | Lejweleputswa | Construction of a cricket pitch and a clubhouse | R7 600 000,00 | Complete
FS191 | Setsoto Local Municipality | Thabo Mofutsanyana | Upgrading of Moemang Sport and Recreation Facility | R9 500 000,00 | Complete
FS196 | Mantsopa Local Municipality | Thabo Mofutsanyana | Construction of Hobhouse Sport facillities | R11 115 000,00 | Complete
GT481 | Mogale City | West Rand | Upgrading of Rietvallei 2 & 3 Sport Complex | R3 659 000,00 | Complete
KZN238 | Alfred Duma Local Municipality | uThukela | Construction of Accacciaville Sportfield | R9 500 000,00 | Complete
KZN241 | eDumbe Local Municipality | Zululand | Construction o Bilanyoni Sportfield | R9 500 000,00 | Complete
KZN284 | Umlalazi Local Municipality | King Cetshwayo | Construction of Basamlilo Sportfield | R9 500 000,00 | Complete
KZN286 | Nkandla Local Municipality | King Cetshwayo | Construction of Nkungumathe Sportfield | R9 500 000,00 | Complete
LIM | Collins Chabane Local Municipality | Vhembe | Construction of a combi-court in Mulamula | R1 500 000,00 | Complete
LIM343 | Thulamela Local Municipality | Vhembe | Upgrading of Makwarela Stadium | R15 500 000,00 | Complete
LIM366 | Bela-Bela Local Municipality | Waterberg | Construction of Moloto Street Stadium | R12 075 000,00 | completed
LIM473 | Makhuduthamaga Local Municipality | Sekhukhuni | Construction of Moroangoato Sport Ground | R5 125 000,00 | Complete

## Slide 15: 2018/2019 FINANCIAL YEAR…
9
MP305 | Lekwa Local Municipality | Gert Sibande | Upgrading of courts at Sakhile stadium | R1 710 000,00 | Complete
MP306 | Dipaleseng Local Municipality | Gert Sibande | Upgrading of Siyathemba Stadium | R13 864 904,00 | Stopped
MP321 | Thaba Chweu Local Municipality | Ehlanzeni | Upgrading of Mashakeng stadium | R9 000 000,00 | Complete
MP326 | Mbombela Municipality | Ehlanzeni | Construction of Masoyi Stadium | R10 400 000,00 | Construction, 60%
NC064 | Kamiesberg Local Municipality | Namakwa | Upgrading of Kharkama Sport Facility | R4 370 000,00 | Complete
NC094 | Phokwane Local Municipality | Francis Baard | Upgrading of Ganspan Sports Complex | R11 290 750,00 | Stopped
NC452 | Gasegonyane Local Municipality | John Taole-Gaetsewe | Upgrading of Mothibastad Sports Complex | R10 545 000,00 | IStopped
NC453 | Gamagara Local Municipality | John Taole-Gaetsewe | Construction of Kathu Sport Complex | R2 009 250,00 | Complete
NW372 | Madibeng Local Municipality | Bojanala Platinum | Construction of Maboloka Sports Facility | R9 500 000,00 | Complete
NW382 | Tswaing Local Municipality | Ngaka Modiri Moleme | Refurbishment of Agisanang Sport Facility | R8 550 000,00 | Complete
NW392 | Naledi Local Municipality | Dr. Ruth Mompati Segomotsi | Construction of Huhudi Sports Facility | R9 500 000,00 | Complete
WC013 | Bergrivier Local Municipality | West Coast | Upgrading of existing Eric Goldschmidt Sports Ground, Velddrift, Eendkuil, Pelia Park Sports Grounds in Porterville | R5 415 000,00 | Complete
WC044 | George Local Municipality | Garden Route | Upgrading of Sport facilities in Rosemore with a Tartan track | R8 550 000,00 | Cancelled

## Slide 16: SUMMARY OF 2019/20 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 3 | 29 225 | 1 | 2 | Amahlathi: municipality lost allocated funds due to non performance. Municipality in subsequent year allocated from its baseline MIG. First contractor appointed was terminated and new one appointed. Current progress 60% Mhlontlo: Site identified required EIA which was completed and progress is at 85%.
FS | 3 | 29 000 | 2 | 1 (Metsimaholo) | Municipality phased the project and co-funded. Allocation made by DSAC is spent in full but facility is not complete because it is planned to be completed in phase 2.
GP | 1 | 10 000 | 1 | 0 | NA
KZN | 3 | 35 000 | 2 | 1 (uMzimkhulu) | NB: Umzimkhulu LM project is a multi-year project and Phase 1 is completed
LP | 2 | 42 000 | 1 | 1 (Polokwane) | Polokwane Soft ball stadium is a multi year project and still on design stage

## Slide 17: SUMMARY OF 2019/20 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
MP | 2 | 22 000 | 2 | 0 | NA
NC | 3 | 28 941 | 3 | 0 | NA
NW | 3 | 41 500 | 1 | 2 (Kagisanong-Molopo and Mahikeng) | Kagisano Molopo – Contractor had cash flow issues, contract was terminated – concern letter sent and progress meetings are conducted- Municipality in a process of resolving it Mahikeng – Multi-year project phase 1 and 2 completed
WC | 2 | 21 000 | 2 | 0 | NA

## Slide 18: 2019/2020 FINANCIAL YEAR
10
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC108 | Kouga Local Municipality | Sarah Baartman | Upgrading of Sportfield in KwaNomzamo | R6 225 000,00 | Complete
EC124 | Amahlathi Local Municipality | Amathole | Construction of the Multi-Purpose Sport Facility in Mlungisi (phase2) | R12 000 000,00 | Construction, 60%
EC156 | Mhlontlo Local Municipality | OR Tambo | Upgrading of Mvumelwano Sportfield (phase2) | R11 000 000,00 | Construction, 85%
FS181 | Masilonyana Local Municipality | Lejweleputswa | Construction of Sport Center at Tshepong /Verkeerdevlei | R9 000 000,00 | Complete
FS193 | Nketoane Local Municipality | Thabo Mofutsanyana | Construction of the Lindley/Ntha sport facility stadium | R13 000 000,00 | Complete
FS204 | Metsimaholo Local Municipality | Fezile Dabi | Construction of Refengkgotso sports complex | R7 000 000,00 | Phase 1 completed and phase to commence in 2022/23
GT422 | Midvaal Local Municipality | Sidebeng | Upgrading of Lakeside Sport Complex | R10 000 000,00 | P1-Complete
KZN222 | uMngeni Local Municipality | uMgungundlovu | Upgrading of Mpophomeni stadium | R11 000 000,00 | Complete
KZN244 | Msinga Local Municipality | uMzinyathi | Construction of Gxushaneni Sport Facility | R12 000 000,00 | Complete
KZN435 | Umzimkhulu Local Municipality | Harry Gwala | Construction of Umzimkhulu Centre | R12 000 000,00 | Pase 1 complete- multi year
LIM345 | Colins Chabane Local Municipality | Vhembe | Construction of Davhana Stadium phase1 | R12 000 000,00 | Complete

## Slide 19: 2019/2020 FINANCIAL YEAR…
11
LIM354 | Polokwane Local municipality | Capricon | Construction National Softball Stadium and Moletjie Soccer Pitch (3 Year Project) | R30 000 000,00 | multi year
MP307 | Govan Mbeki Local Municipality | Gert Sibande | Upgrading of Lebohang stadium in Leandra | R11 000 000,00 | Complete
MP314 | Emakhazeni Local Municipality | Nkangala | Upgrading of Siyathuthuka Stadium | R11 000 000,00 | Complete
NC073 | Emthanjeni Local Municipality | Pixley Ka Seme | Upgrading of Khwezi Sport Grounds | R11 941 000,00 | Complete
NC087 | Dawid Kruiper Local Municipality | ZF Mgcawu | The development of sports ground in Rosedale | R9 000 000,00 | Complete
NC093 | Magareng Local Municipality | Francis Baard | Upgrading of Ikhutseng stadium | R8 000 000,00 | Complete
NW383 | Mafikeng Local Municipality | Ngaka Modiri Molema | Upgrading of Mahikeng Tennis Precinct into National Tennis Precinct (3 Year Project) | R20 000 000,00 | Phase 1 and 2 complete
NW397 | Kagisano Molopo Local Municipality | Dr. Ruth Segomotsi Mompati | Construction of Peterplessis sports facilities | R9 500 000,00 | 50% complete
NW405 | JB Marks Local Municipality | Dr. Kenneth Kaunda | Upgrading of Ikageng sports facility | R12 000 000,00 | Complete
WC032 | Overstrand Local Municipality | Overberg | Upgrading of the Hawston Sport Ground in Overstrand | R10 000 000,00 | Complete
WC052 | Prince Albert Local Municipality | Central Karoo | Construction of sport fields and sport facilities for town of Prince Albert (phase 1) | R11 000 000,00 | Funds were returned

## Slide 20: SUMMARY OF 2020/21 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 3 | 29 400 | 3 |  | NA
FS | 3 | 25 728 | 2 | 1 (Moqhaka) | Moqhaka: slow implementation of the works but the contractor is still on site and waiting delivery artificial turf. Current progress as of date of this document is 80%
GP | 0 | 0 | NA | 0 | NA
KZN | 4 | 42 600 | 3 | 1 (Jozini) | Jozini: Project delayed by community unrests, disturbances by Local Business Forum and lack of machinery and plant. Outstanding work on the date of this report: Awaiting delivery of artificial turf for installation
LP | 3 | 46 000 | 1 | 2 (Polokwane (multi-year), Musina and Thabazimbi) | Polokwane: project is a multi-year and contractor was appointed but not scheduled to complete in this year. There were however still delays due to COVID Lockdown Regulations, community protest demanding subcontracting. Thabazimbi – delays in project registration, finalisation of designs as DSAC needed to ensure they are compliant with N&S. Current progress (on the date of this document is 85%)

## Slide 21: SUMMARY OF 2020/21 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS
MP | 1 | 10 000 | 1 | 0 | NA
NC | 4 | 39 830 | 3 | 1 | NamaKhoi: Allocation returned to NT. Municipality was approved for a project in Bergsig as per their Business Plan but upon receipt of allocation they wanted to implement in Buffelsrevier. They were advised to write a letter and submit a new plan for the latter site, but delayed until funds were taken due to non-expenditure
NW | 3 | 40 300 | 1 | 1 (Mahikeng and Ditsobotla) | Mahikeng: Project is a allocated over 3 years and was on-going in this year Ditsobotla: Project completed. Only water and electricity connection
WC | 2 | 19 000 | 1 | 1 ( Matsikama) | Matzikama is at 95%

## Slide 22: 2020/2021 FINANCIAL YEAR
12
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC442 | Umzimvubu Local Municipality | Alfred Ndzo | Construction of Phepheni sport ground | R 10 000 000,00 | Complete
EC135 | Intsika Yethu Local Municipality | Chris Hani | Upgrading of Magwala Sport Ground | R 10 000 000,00 | Complete
EC105 | Ndlambe Local Municipality | Sarah Baartman | Upgrading of Marselle Sports field Kenton on Sea Phase 2 | R 9 400 000,00 | Complete
MP | Steve Tshwete Local Municipality | Nkangala | Construction of Kwazamokuhle Stadium | R 10 000 000.00 | Complete
FS181 | Masilonyana Local Municipality | Lejweleputswa | Construction of Winnie Mandela Sport Facility | R 6 728 000,00 | Complete
FS201 | Moqhaka Local Municipality | Fezile Dabi | Construction of Refengkgotso sports complex | R 10 000 000,00 | Construction,80%
FS192 | Dihlabeng Local Municipality | Thabo Mofutsanyana | Construction of Fateng Tse Ntso Sport facility | R 9 000 000,00 | Complete
NC062 | Nama Khoi LM | Namakwa | Bergsig Sport Facility | R 7 500 000,00 | Allocation returned to NT

## Slide 23: 2020/2021 FINANCIAL YEAR…
13
NC075 | Renosterberg LM | Pixley Ka Seme | Upgrading of Vanderkloof Sport Facility. | R 11 500 000,00 | Complete
NC076 | Thembelihle LM | Pixley Ka Seme | Development of Steynville Sport Facility | R 11 500 000,00 | Complete
NC084 | Khei LM | ZF Mgcawu | Development of Grootdrink Sport Facility. | R 9 330 000,00 | Complete
KZN281 | Umfolozi | King Cetshwayo | Construction of the Dondotha Sports field | R 13 000 000,00 | Complete
KZN272 | Jozini | uMkhanyakudi | Construction of Ndumo Sport Complex phase 4 | R 9 600 000,00 | Construction, 76%
KZN235 | Okhahlamba | uThukela | Construction of Khethani Sports Field - Ward 01 | R 10 000 000,00 | Complete
KZN237 | Inkosi iLanga libalele | uThukela | Upgrade of Wembezi Sports Field Ward 9 | R 10 000 000,00 | Complete
NW384 | Ditsobotla | Ngaka Modiri Molema | Refurbishment of Itekeng Sports Facility | R 10 300 000,00 | Construction, 95%

## Slide 24: 2020/2021 FINANCIAL YEAR…
14
NW374 | Kgetleng Revier | Bojanala | Refurbishment of Reagile Sports Facility | R 10 000 000,00 | Complete
NW383 | Mahikeng | Ngaka Modiri | Construction of Tennis Courts at Mmabatho Stadium | R 20 000 000,00 | Multi-year and ongoing
LIP361 | Thabazimbi | Waterberg | Upgrading of sports and recreation facilities in Raphuti (ward 4) | R 11 000 000,00 | 85% Completion
LIP341 | Musina | Vhembe | Completion of Harper Sport Facility | R 5 000 000,00 | Complete
LIP354 | Polokwane LM | Capricorn | Construction of Moletjie field and Softball field | R 30 000 000,00 | Multi year project at 65% completion
WC043 | Mosselbay LM | Garden Route | New soccer facility for Wolwadans | R 9 000 000,00 | Complete
WC011 | Matzikama LM | West coast | Upgrading of existing and construction of new sport facilities in Klawer (Ward 6) | R 10 000 000,00 | 95% completion

## Slide 25: SUMMARY OF 2021/22 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 5 |  | 1 | 4 | Summarise reasons
FS | 2 |  | 0 | 2 | M-A-P: Matjhabeng: Delayed procurement of citing uncertainty of the existence of the allocation as. Following clarity PSP and Contractor were appointed but works did not commence stopped due to lack of funds. DSAC is following the matter up because R7 million was allocated. Project Inactive
GP | 0 |  | 0 | 0 | 
KZN | 7 |  | 0 | 7 | Summarise the reasons
LP | 5 |  | 0 | 5 | Summarise reasons

## Slide 26: SUMMARY OF 2021/22 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
MP | 0 | 0 | NA | NA | NA
NC | 5 |  | 0 | 5 | Siyancuma: Second allocation returned and municipality cited lack of capacity and SANRAL matter as the reason. Richtersveld: Wanted to split the funds across 4 towns and built non-core facilities when a plan was approved for actual core facilities in Port Nolloth. Funds were taken through Stopping and Reallocation process of COGTA Dikgatlong, Tsantsabane and Kgatelopele: Projects at construction stage but were delayed by registration process and procurement proceses
NW | 3 |  | 0 | 3 | Summarise the reasons
WC | 2 |  | 0 | 2 | Summarise the reasons

## Slide 27: 2021/2022 FINANCIAL YEAR
15
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC121 | Mbashe | Amathole | Upgrading of Ngumbela sports facility ward 2 | R4 000 000,00 | Complete
EC142 | Senqu | Joe Gqabi | Construction of sport facility in Bluegums village Ward 11 | R8 000 000,00 | Aappointment of contractor
EC155 | Nyandeni Local Municipality | OR Tambo | Construction of sport facility in Nyandeni local Municipality | R9 000 000,00 | Construction, 20%
EC101 | Dr. Bayer Naude Local Municupality | Sarah Baartman | Upgrading of the collie koeberg sport complex | R7 000 000,00 | Phase 1- complete. Phase 2-Construction 45%
EC106 | Sunday River Valley | Sarah Baartman | Construction of Sport facility in Sunday’s River Valley Local Municipality | R8 000 000,00 | Construction, 20%
FS | Matjhabeng | Lejweleputswa | Construction of a sportfield in Matjhabeng | R7 000 000,00 | Construction, 5%
FS | Maluti-a- Phofung | Thabo Mofutsanyana | Construction of a sport field in Maluti-a-Phofung | R10 000 000,00 | Construction, 90%
KZN254 | Dannhauser | Amajuba | Construction of Danncol sport centre | R8 000 000,00 | Construction, 55%
KZN436 | Dr. Nkosazana Dlamini Zuma | Harry Gwala | Construction of Creighton sport field | R8 000 000,00 | 90% completion
KZN294 | Maphumolo | Ilembe | Construction of Sakuyaze sport field | R8 000 000,00 | Procurement
KZN214 | Umuziwabantu | Ugu | Construction of a sport field | R8 000 000,00 | 80% , Complete
KZN224 | Impendle | Umgungundlovu | Construction of sport field in Impendle | R8 000 000,00 | 85% Construction
KZN226 | Mkhambathini | Umgungundlovu | Upgarding of Banqobile sport field | R8 000 000,00 | 55% Completion
KZN245 | Umvoti | uMzinyathi | Construction of Khandabathule sport field | R10 000 000,00 | 45% construction

## Slide 28: 2021/2022 FINANCIAL YEAR…
16
LIM351 | Blouberg | Capricorn | Construction of indigenous games platforms and outdoor gyms | R10 000 000,00 | 85%, Construction
LIP354 | Polokwane | Capricorn | Construction of Polokwane Soft ball stadium | R15 000 000,00 | Multi year and at 73%
LIM476 | Fetakgomo Tubatse | Waterberg | Construction of sport facility in Fetakgomo Tubatse | R10 000 000,00 | 90% construction
LIM | Musina | Vhembhe | Upgrading of Lesley Manyathela stadium | R6 500 000,00 | 53% completion
LIM | Thulamela | Vhembhe | Construction of indigenous games platforms and outdoor gyms | R6 000 000,00 | Procurement
NC | Dikgatlong | Francis Baard | Construction of sport facility in Dikgatlong | R8 000 000,00 | Construction 20%
NC | Richtersveld | Namakwa | Construction of sport facility in Richtersveld | R7 000 000,00 | Allocation returned to NT
NC | Siyancuma | Pixley Ka Seme | Construction of sport facility in Siyancuma | R7 000 000,00 | Allocation returned to NT
NC | Kgatelopele | ZF Mgcawu | Construction of sport facility in Kgatelopele | R12 000 000,00 | Construction,68%
NC | Tsantsabane | ZF Mgcawu | Construction of sport facility in Tsantsabane | R12 000 000,00 | Construction,66%
NW375 | Moses Kotane | Bojanala Platinum | Upgrading of Madikwe sport facility | R9 000 000,00 | 73% Construction
NW404 | Maquassi Hills | Dr Kenneth Kaunda | Construction of Wolmaranstad ext 13 sports ground | R10 000 000,00 | 45% construction
NW383 | Mahikeng | Ngaka Modiri | Construcrion of Mmabatho tennis stadium phase 3 | R20 000 000,00 | completed phase 1 and 2
WC022 | Witzenberg | Cape Winelands | Construction of a sport field in Witzenberg | R1 500 000,00 | Construction 50%
WC031 | Theewaterskloof | Overberg | Upgrading of pineview sport facility Grabouw | R7 858 000,00 | Procurement

## Slide 29: SUMMARY OF 2021/22 ALLOCATIONS
PROVINCE | NO OF PROJECTS | TOTAL BUDGET (R‘000) | COMPLETED PROJECTS | INCOMPLETE PROJECTS | REASONS FOR INCOMPLETIONS/ COMMENTS
EC | 4 | 38 000 | NA | NA | Projects scheduled for completion end June 2023
FS | 3 | 22 000 | NA | NA | Projects scheduled for completion end June 2023
GP | 1 | 10 000 | NA | NA | Projects scheduled for completion end June 2023
KZN | 4 | 40 000 | NA | NA | Projects scheduled for completion end June 2023
LP | 3 | 31 000 | NA | NA | Projects scheduled for completion end June 2023
MP | 1 | 10 058 | NA | NA | Projects scheduled for completion end June 2023
NC | 5 | 27 500 | NA | NA | Projects scheduled for completion end June 2023
NW | 1 | 10 300 | NA | NA | Projects scheduled for completion end June 2023
WC | 5 | 46 000 | NA | NA | Projects scheduled for completion end June 2023 (except Swartland scheduled for implementation in 2023)

## Slide 30: 2022/2023 FINANCIAL YEAR
16
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT | PROJECT NAME | BUDGET ALLOCATED | STATUS
EC109 | Kou-kama LM | Sarah Baartman District | Upgrading of Krakeel sportfield (ward 2) | R 8 000 000,00 | Procurement of contractor
EC126 | Ngqushwa LM | Amathole District | Rehabilitation of new creation sportfield | R 10 000 000,00 | Procurement of contractor
EC123 | Great Kei LM | Amathole District | Construction of a sportfield in Komga - Ward 7 | R 10 000 000,00 | Procurement and Design
EC136 | Emalahleni LM | Chris Hani District | upgrading of Indwe Sport Field | R 10 000 000,00 | Procurement of contractor
FS181 | Masilonyana LM | Lejweleputswa District | Construction of Netball courts at Winnie Mandela Museum | R 2 000 000,00 | Procurement and Design
FS182 | Tokologo LM | Lejweleputswa District | construction of Malebogo community stadium | R 10 000 000,00 | Procurement and Design
FS196 | Mantsopa LM | Thabo Mofutsanyana District | construction of multi- sport facility in Mahlatswetsa | R 10 000 000,00 | Procurement and Design
GT484 | Merafong LM | West Rand District | Construction of sport field within Merafong Local Municipality | R 10 000 000,00 | Procurement and Design
KZN212 | Umdoni LM | Ugu District | Upgrading of uMzinto sportfield (Phase 3) | R 10 000 000,00 | Procurement and Design
KZN292 | Kwadukuza LM | iLembe District | Construction of Groutville Market Sportfield - Ward 10 | R 10 000 000,00 | Procurement of contractor
KZN266 | Ulundi LM | Zululand District | Construction of Ezihlabeni sport field | R 10 000 000,00 | Procurement and Design
KZN285 | Mthonjaneni LM | King Cetshwayo District | Construction of Kwesezulu Sportfield Ward 7 | R 10 000 000,00 | Procurement and Design

## Slide 31: 2022/2023 FINANCIAL YEAR …
16
MUNICIPALITY CODE | MUNICIPALITY | DISTRICT | PROJECT NAME | BUDGET ALLOCATED | STATUS
LIM333 | Greater Tzaneen LM | Mopani District | Construction of Leretjeng Sport Ground (Ward11) | R11 000 000.00 | Procurement and Design
LIM354 | Polokwane LM | Capricorn District | Construction of a Softball Stadium in Polokwane | R10 000 000.00 | Construction- multi year project
LIM362 | Lephalale LM | Waterberg District | Construction of Marapong Sport Centre(Phase 2) | R10 000 000.00 | Procurement and Design
MP316 | Dr JS Moroka LM | Nkangala District | Construction of a sport field within Dr JS Moroka Local Municipality | R10 058 000.00 | Procurement and Design
NC066 | Karoo Hoogland LM | Namakwa District | Upgrading of Willistone Sport Facility | R9 000 000.00 | Procurement and Design
NC072 | Umsobomvu LM | Pixley Ka Seme District | Upgrading of Kuyasa Sport Ground in Colesberg | R9 500 000.00 | Procurement and Design
NC073 | Emthanjeni LM | Pixley Ka Seme District | Upgrading of Nonzwakazi Stadium | R9 500 000.00 | Procurement and Design
NC074 | Kareeberg LM | Pixley Ka Seme District | Upgrading of Sport Facility in Carnarvon | R11 000 000.00 | Procurement and Design
NC093 | Magareng LM | Francis Baard District | Upgrading of Ikhutseng Sport Facilty (Phase 2) | R 6 500 000.00 | Procurement and Design
NW383 | Mafikeng LM | Ngaka Modiri Molema District | Upgrading Mmabatho Tennis stadium | R 10 300 000.00 | Procurement of contractor
WC045 | Oudtshoorn LM | Garden route District | Upgrading of Bongolethu sport ground | R 10 000 000.00 | Procurement and Design
WC025 | Breede Valley LM | Cape winelands District | Upgrading of Dewel and Rawsonville sport grounds | R 6 000 000.00 | Procurement and Design
WC015 | Swartland LM | West Coast District | upgrading of Sarling and Chartsworth sport fields | R 10 000 000.00 | Project to be implement 23/24
WC042 | Hessequa LM | Garden route District | Construction of new cricket and soccer facility in Heidelberg | R 9 000 000.00 | Procurement and Design
WC048 | Knysna LM | Garden route District | Construction of sport field and sport facilities in Bongani (Phase 2) | R 11 000 000.00 | Procurement and Design

## Slide 32: CHALLENGES
Using ring-fenced MIG funds for other priorities impacts of the timeous delivery of the sport infrastructure projects
Poor construction contract management in municipality, compromising effective monitoring and management, resolution of contractual disputes and timeous completions
DSAC is disempowered to impose any penalties (e.g. withholding of tranches in instances of non-compliance by municipalities) because of the nature, conditions and governance of the Grant.
Loss of significant funds allocated during stopping and reallocation process by COGTA. The sport infrastructure funds lost during this process are not reallocated to other performing sport infrastructure projects, instead funds are reallocated to other uses elsewhere.
Decline of registration of some projects on the basis that MIG cant be used to built sport facilities on sites owned by public school - even where there is general consensus among affected community, municipality and school through MoA to ensure such facility will be accessible to all. [EPG report recommends focus on delivering sport facilities in school as well as the bedrock of the sport and recreation system)

## Slide 33: CHALLENGES
Decline of registration of some projects (e.g. Langeberg) on the basis that site identified is accessible to both non-poor and poor households, and MIG, even for sport facilities, is restricted to only poor households, otherwise municipalities must counter-fund if non-poor households were to benefit. DSAC holds a different view on this matter but also this reasoning defeats mandate of DSAC of promoting Social Cohesion through creating such spaces that facilitate interaction and integration among different races, gender and class
Decrease of ring-fenced budget from R300 million compromises adequate supply of sport facilities to meet facility demand to support transformation targets in various sporting codes (e.g. swimming )
Inadequate technical capacity in provincial departments of sport to ensure adequate support and monitoring of the sport infrastructure projects
Poor alignment of supply of facilities to sport development programmes/ plans in provinces, leading to non-use/ opening of completed facilities
Lack of enforcement of 5% earmarked for sport infrastructure to ensure adequate supply and maintenance of sport infrastructure

## Slide 34: RECOMMENDATIONS
Finalisation of the draft MoA between COGTA and DSAC to, inter alia, (i) facilitate mechanisms of recourse where municipalities when municipalities do not comply and (ii) ensure DSAC plays a role in reallocation of funds stopped from sport infrastructure projects
Amendment of such provisions in the MIG Conditional Framework that prevents delivery of sport facilities in school sites and “social cohesion sites” where such sites makes spatial, developmental, social transformation and financial sense
Increase the ring-fence MIG sport infrastructure budget to minimum of R400 million from the earmarked 5% as much of the latter is any case not used for the intended purpose of sport facilities by municipalities
Enforcement of use of 5% for intended sport facilities purpose by COGTA through decline of any municipalities’ Project Implementation Plan (PIP) that do not allocate such 5% to sport infrastructure projects
Enforcement of use of 5% by SALGA by making delivery of sport facilities by local government, in line with Schedule 5B of the Constitution of RSA, a standing items of sone of its oversight meetings
Building of built environment capacity by provincial departments responsible for sport in line with their responsibilities imposed by MIG Conditional Framework