## Slide 1: 2022/23 quarter 1 analysis report of the Department of Water & Sanitation
PRESENTATION TITLE
Presented by:
Name Surname
Directorate
Date
Presented by:
Dr Sean Phillips
Director-General
20 September 2022
For the period 01 April to 30 June 2022

## Slide 2: Contents
Purpose……………………………………………………………………………………….3
Part A: Executive summary………………………………………………………………..4-6
Part B: Overview of non-financial performance ….………………………...…..…..…8-28
Part C: Overview of financial performance............................................................29-44
Part D: Overview of financial recovery plan..........................................................46-61
Part E: Appendix with additional slides on details of water services infrastructure development grants per project/ water services authority/ benefitting municipalities........................................................................................................65-88

## Slide 3: Purpose
To brief the Portfolio Committee on the Department of Water and Sanitation’s first quarter performance for the 2022/23 financial year

## Slide 4: Overview (1)
The first quarter highlight achievement and various challenges facing the Department on a number of areas including the following:
  Financial performance and position
  Service delivery
  Clearing of legacy cases of improper expenditure (i.e., unauthorised, irregular, fruitless and wasteful);
  The existence of fraud and corruption; and
  Institutional performance challenges with the water sector value chain.
The Department has developed and is currently implementing Turnaround and Financial Recovery Plan addressing inter alia:
  Strategic context
  Performance and consequence management systems
  Strategic leadership
  Institutional stabilization
  Capacity and transformation
  Sustainable service delivery
  Infrastructure maintenance and development
  Financial Management.
There are ongoing interventions to correct systematic challenges within the water sector, this is done in collaboration with National Treasury, COGTA, Municipalities and Water Boards.

## Slide 5: Overview (2)
A total of 23 Senior Management posts have been filled since the start of the 2021/2022 financial year which includes the post of Director-General that was filled with effect from 1 January 2022.
The CFO and all other DDG posts have also been filled.
All Chief Director posts have been filled (with the exception of the post that was vacated by the current CFO) – the new incumbent will assume duty on the 1st of October 2022.
One vacant Director post (Forensic Investigation and Quality Assurance) is in process of being filled. The Forensic Investigation Unit had 8 investigators, 3 of whom have since vacated the positions. This creates a capacity constraint.
The Department is now following a pro-active approach is preparing recruitment and selection processes in instances where it becomes aware of any future vacancies.
The Department is also currently reprioritising other critical vacancies in line with the Compensation of Employees budget allocation for the 2022 MTEF and also in line with the approved organizational structure. Specific emphasis is being placed on professional and critical positions.

## Slide 6: Quarter 1 comparison of non-financial and financial performance
Programme | Programme | % actual achievement | % budget spent | Areas of under performance
1 | Administration | 81% | 19% | Implementation of the risk management plan Expenditure on annual budget Reduction of debtor days
2 | Water Resources Management | 77% | 39% | Cabinet approval of the National Water Amendment Bill National Water Resources Strategy -3 gazette National Water Resources Infrastructure Agency Cabinet approval Conveyance systems rehabilitation Creation of job opportunities through implementing O & M projects Raw water charges consultations Draft regulation for water allocation reform Stakeholder consultation on the water economic regulator Water users monitored for compliance
3 | Water Services Management | 80% | 4% | Updating the 9 provincial sanitation situational analysis Regional bulk infrastructure project phases under construction (mega and large) Cabinet approval of the Water Services Amendment Bill Evaluation of water boards performance against performance plans
Total |  | 78% | 13% | 

## Slide 7: Part B: overview of non financial performance
Overview of the cumulative fourth quarter performance
progress in implementing the 2017 preferential procurement regulations
cumulative fourth quarter performance per budget programme

## Slide 8: Overview of the overall first quarter performance of the Department
Chart: Consolidated performance
| Achieved | Partially achieved | Not achieved
Column1 | 62 | 7 | 10
Chart: Consolidated performance per programme
| Programme 1: Administration | Programme 2: Water Resources Management | Programme 3: Water Services Management
Achieved | 0.81 | 0.77 | 0.8
Partially achieved | -0.13 | -0.05 | -0.12
Not achieved | -0.06 | -0.18 | -0.08
Achieved
(from 100%)
Partially achieved
(from 50 to 99%)
Not achieved
(less than 50%)
Notes: Analysis notes:
Overall performance reflects 3% reduction compared to the same period during the previous financial year.
Administration performance reflects a 21% improvement compared to the same period during the previous financial year.
Water Resource Management reflects a 13% reduction compared to the same period during the previous financial year.
Water and Sanitation Services Management reflects the same performance when compared to the same period during the previous financial year.

## Slide 9: Consolidated progress in implementing the 2017 preferential procurement regulations
Consolidated first quarter procurement
Chart: 
| SMMEs | Non-SMMEs
Column1 | 149685869.71 | 94861687.22
Consolidated first quarter procurement per B-BBEE status level
Chart: 
| EME | QSE | Generic
Series 1 | 92343241.31 | 57342628.4 | 94966466.58
Legend:
Exempted Micro Enterprise (EME): annual turnover of R10 million and below;
Qualifying Small Enterprise (QSE): annual turnover between R 10 million and R50 million;
Generic enterprise: annual turnover above R50 million
61% was achieved from a target of 30%
38% was achieved from a target of 15%
23% was achieved from a target of 15%
Notes: The SMME procurement reflects a 10% improvement compared to the same period during the previous financial year.
The QSE procurement reflects a 11% reduction compared to the same period during the previous financial year.
The EME procurement reflects a 21% improvement compared to the same period during the previous financial year.

## Slide 10: Consolidated progress for designated groups
Chart: 
| Women | Youth | PWD
Sales | 0.39 | 0.22 | 0.02
39% was achieved from a target of 40%
22% was achieved from a target of 30%
2% was achieved from a target of 7%
Notes: The procurement for designated group compared to the previous financial year is as follows:
Women reflects a 28% reduction
Youth reflects a 16% reduction
PWD reflects a 2% improvement

## Slide 11: Analysis of performance: administration (programme 1)
Overview sub-programme performance
Summary of sub-programme achievements for the quarter
Details on areas of partial and non-achievement for the quarter

## Slide 12: Overview sub-programme performance
Chart: % performance against Q1 milestones
| Departmental Management | Corporate Services | Financial Management | Provincial & International Coordination
Achieved | 0.5 | 1 | 0.71 | 1
Partially achieved | -0.5 | 0 | -0.15 | 0
Not achieved | 0 | 0 | -0.14 | 0
Achieved
(from 100%)
Partially achieved
(from 50 to 99%)
Not achieved
(less than 50%)

## Slide 13: Summary of sub-programme achievements for the quarter
Departmental Management | Corporate Services
20% compliance with the approved audit action plan | 839 engineers and scientist posts filled 15% training interventions implemented 25 safety and security assessments conducted Maintained 100% availability of information technology systems Implementation of 418 communication and public participation programmes
Financial Management | Provincial and International Coordination
SMME procurement at 61% of which: 38% targeted procurement spent on exempted micro enterprises 23% targeted procurement spent on qualifying small enterprises Implementation of financial recovery plan at 100% | Implementation of 2022/23 annual international relations programme as follows: 2 initiatives 10 agreements 8 obligatory Implementation of 45 activities for stakeholder management and partnership programme

## Slide 14: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Departmental Management |  |  |  |  | 
1.1.2 | Percentage compliance with the implementation of risk management plan | 100% | 89% (8 of 9 activities) | Under by 11% | Target partially met The declaration for interest for MMS was postponed from 1 June 2022 to 31 July 2023. Mitigation: This has been deferred to the next financial year.
Financial Management (Main Account) |  |  |  |  | 
1.4.2 | Percentage expenditure on annual budget | 25 | 13% | Under by 12% | Target partially met Goods & services, Capital, Transfers and subsidies. Mitigation: Implementation of Infrastructure procurement strategy and timely budget reprioritisations.
Financial Management (Water Trading) |  |  |  |  | 
1.1.5 | Number of debtor days | 150 days | 360 days | Increased by 210 days | Target not met The debtors book increased as a result of non-payment by customers. Mitigation: The department has appointed a panel of debt collectors and continues to engage through IGR processes.

## Slide 15: Analysis of performance: WATER RESOURCE MANAGEMENT (programme 2)
Overview sub-programme performance
Summary of sub-programme achievements for the quarter
Details on areas of partial and non-achievement for the quarter

## Slide 16: Performance overview per sub-programme
Chart: % performance against Q1 milestones
| Integrated Water Resources Planning | Water Ecosystems Management | Water Resources Information & Management | Water Resources Policy & Strategy | Water Resources Institutional Oversight | Water Resources Infrastructure Management | Water Resources Regulation
Achieved | 1 | 1 | 1 | 0 | 0.75 | 0.78 | 0.67
Partially achieved | 0 | 0 | 0 | 0 | -0.25 | 0 | -0.08
Not achieved | 0 | 0 | 0 | -1 | 0 | -0.22 | -0.25
Achieved
(from 100%)
Partially achieved
(from 50 to 99%)
Not achieved
(less than 50%)

## Slide 17: Summary of sub-programme achievements for the quarter
Integrated Water Resource Planning | Water Ecosystems Management
Status report on the implementation of the National Water & Sanitation Master Plan Status report on the monitoring of reconciliation strategies for Mngeni, Amathole, Orange and Crocodile West Inception report on climate change risk and vulnerability assessments & adaptation options Status reports on environmental impact study for Clanwilliam Bulk Conveyance Infrastructure and Lower Coerney Balancing Dam | Legal notice for the Thukela river system being vetted
Water Resources & Information Management | Water Resources Institutional Oversight
Implemented river eco-status monitoring in 70 rivers 5 water resource monitoring programmes reviewed and maintained 6 water and sanitation information systems maintained Status report on the development of the National Digitised Integrated Water and Sanitation Monitoring System design Bavaria gauging station at 80% completion | Assessed annual performance plans and quarterly reports for 2 CMAs, TCTA and WRC Stakeholder consultation Mzimvubu-Tsitsikamma CMA Stakeholder consultation for the transformation of Tierport irrigation boards

## Slide 18: Summary of sub-programme achievements for the quarter
Water Resources Infrastructure Management | Water Resources Regulation
2 bulk raw water projects under construction (Hazelmere and Mzimvubu advance works) 81 maintenance projects completed as planned 96 unscheduled maintenance projects completed Bloemhof Dam and Stompdrift Dam safety evaluation completed Nkadimeng Dam and Marico Bosveld Dam rehabilitation projects under construction Adherence to water supply agreements / authorisations and operating rules at 213% 27 job opportunities created through implementing operations of water resources infrastructure projects | Resource directed measures monitoring framework An assessment report for Upper Olifant catchment drafted for Mine Water. Catchment vision report for Mzimvubu-Tsitsikama developed Updated the existing waste discharge charge strategy 2022/23 Water Research Levy approved 133% applications for water use authorisation finalised within applicable period 75 of reported non-compliant cases investigated 150 wastewater systems monitored against the regulatory requirements

## Slide 19: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Water Resources Policy & Strategy |  |  |  |  | 
5.1.1 | National Water Act Amendment Bill developed | Submit the Water Services Amendment Bill to clusters for approval to publish for public comments | SEIAS report submitted to Presidency and preliminary certification is issued. | NWA amendment Bill not submitted to Clusters | Target not met OCSLA feedback required a revision of certain issues in the Bill
5.1.2 | National Water Resources Strategy Edition 3 (NWRS-3) developed | Conduct 60 days public consultations on the NWRS3 version 1 | A gazette notice prepared and approved | Gazette not published | Target not met Finalisation of the procurement processes
Water Resources Institutional Oversight |  |  |  |  | 
6.2.3 | National Water Resources Infrastructure Agency gazetted for establishment | Cabinet memo prepared for Cabinet | Draft Cabinet memo prepared | Cabinet memo not approved | Target not met Cabinet memo not approved

## Slide 20: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Water Resources Infrastructure Management |  |  |  |  | 
3.5.5 | Number of kilometres of conveyance systems rehabilitated per annum | 1km | 0.354km | Under by 0.646km | Target not met The termination of the diesel transversal contract created a diesel shortage in the construction site which equates to 13 weeks.
3.6.1.1 | Number of job opportunities created through implementing operations of water resources infrastructure projects | 25 | 0 | Under by 25 | Target not met Delay in starting of some projects affected the creation of job opportunities.

## Slide 21: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Water Resources Regulation |  |  |  |  | 
5.1.3 | Raw water charges developed | Consultation on 2023/24 raw water charges | Consultation meeting for BGCMA and Southern Cluster on the 2023/24 Raw Water charges. | Consultations with other users unable to commence | Target not met All other regional consultations will continue in July 2022. Schedule attached.
6.1.1 | Regulation for advancement of water allocation reform finalised | Version 1 of Draft 2 Regulation consolidated for comments | Version 1 of Draft 2 regulations | Version 1 of Draft 2 regulations not circulated for comments | Target not met The National Water Act does not have enabling provisions for the promulgation of these Regulations in terms of Section 26
6.2.5 | Water economic regulator gazetted for establishment | Approval for stakeholder consultation on second draft business case | Appointed PSP to finalise the business case for the establishment of a Regulator Commission. | Approval for stakeholder consultation on second draft business case | Target not met Change in Strategic direction:- Pronunciation of the Regulator Commission as opposed Independent Economic Regulator
5.1.5 | Number of water users monitored for compliance | 102 | 81 | Under by 21 | Target partially met Some inspections were deferred for finalization at a later period

## Slide 22: Analysis of performance: WATER services MANAGEMENT (programme 3)
Overview sub-programme performance
Summary of sub-programme achievements for the quarter
Details on areas of partial and non-achievement for the quarter

## Slide 23: Performance overview per sub-programme
Chart: % performance against Q1 milestones
| Water Services & Local Management | Regional Bulk Infrastructure Grant | Water Services Infrastructure Grant | Water Services Policy & Strategy | Water Services Institutional Oversight | Water Services Regulation
Achieved | 0.9 | 0.71 | 1 | 0 | 0.5 | 1
Partially achieved | 0 | -0.29 | 0 | 0 | -0.5 | 0
Not achieved | -0.1 | 0 | 0 | -1 | 0 | 0
Achieved
(from 100%)
Partially achieved
(from 50 to 99%)
Not achieved
(less than 50%)

## Slide 24: Summary of achievements for the quarter
Water Services & Local Management | Regional Bulk Infrastructure Grant
Inception report for water conservation and water demand management strategies Training on IWA reporting requirements within the 8 large water supply system Final No-Drop requirements: 4 consultation/ Communication on the No Drop Requirements for the 2022/23 Audit year Feasibility studies: 4 draft assessment reports for water and wastewater services projects (RBIG) Implementation readiness studies: 2 draft assessment reports for water and wastewater services projects (RBIG) The implementation programme finalised for district municipalities (DMs) 5-year water and sanitation reliability plans All 144 WSAs registered online Municipal priority action plan: Status report developed reflecting total numbers and vulnerabilities per province Draft National Faecal Sludge Management Strategy updated | A total of 82 regional bulk project phases under construction of which 7 are mega project phases 55 are large project phases 20 are small project phases A total of 5 project phases completed of which 1 is a mega project phase 1 is a large project phase 3 are small project phases Implementation of the Vaal and Giyani intervention projects 286 job opportunities created through implementing RBIG infrastructure projects
Water Services Infrastructure Grant | Water Services Regulation
A total of 270 projects under construction A total of 42 projects completed | Blue Drop : Assessment criteria developed Sector consultation (Symposiums) for upcoming Blue Drop Audits WC, LP, KZN, EC, NC, FS and NW Symposium held.

## Slide 25: Provincial water services infrastructure grants numbers
Province | Regional bulk project phases |  | Water services infrastructure grant projects |  | Intervention project(s)
 | Under construction | Completed | Under construction | Completed | 
Eastern Cape | 14 | - | 44 | 18 | -
Free State | 17 | 2 | 29 | 2 | -
Gauteng | 1 | - | 8 | 3 | 1
KwaZulu-Natal | 4 | 1 | 43 | - | -
Limpopo | 11 | - | 57 | 1 | 1
Mpumalanga | 20 | 1 | 28 | 14 | -
Northern Cape | 3 | 1 | 29 | - | -
North West | 8 | - | 23 | 1 | -
Western Cape | 4 | - | 9 | 3 | -
Total | 82 | 5 | 270 | 42 | 2
Achieved
(from 100%)
Partially achieved
(from 50 to 99%)
Not achieved
(less than 50%)
Recovery from previous quarter
Notes: Overall target for RBIG projects:
Under construction is 93
Completed is 7
WSIG projects completed target is 55

## Slide 26: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Water Services and Local Management |  |  |  |  | 
5.2.2 | National Sanitation Integrated Plan | Updated 9 provincial situational analysis reports | 0 (From the total of 144 WSAs, only 111 WSAs submitted the responses on the scoping questionnaire tool for data collection and 47 WSAs still outstanding) | Updated 9 provincial situational analysis reports not finalised | Target not met Response from WSAs on the scoping questionnaire for data collection were minimal resulting in analysis of available data for updating provincial situational reports not achievable
Regional Bulk Infrastructure Grant |  |  |  |  | 
3.9. 3.1 | Number of mega regional bulk infrastructure project phases under construction | 7 | 6 | Under by 1 | Target partially met Polokwane WWTW phase 1 of 2: Contractor for Phase 1A abandoned site due to cashflow challenges.
3.9.3.2 | Number of large regional bulk infrastructure project phases under construction | 61 | 55 | Under by 6 | Target partially met KZN: financial commitments for 3 projects has been reached and 1 projects awaiting the appointment of an APP FS: legal proceeding underway for 1 project arising from contractor termination and 1 project is on hold due to contractor cash flow challenges.

## Slide 27: Details on areas of partial and non-achievement for the quarter
Performance indicator |  | 2022/23 Q1 target | 2021/22 Q1 achievement | Deviation from Q1 target | Comments
Water Services Policy & Strategy |  |  |  |  | 
5.2.1 | Water Services Amendment Bill developed | Submit the Water Services Amendment Bill to clusters for approval to publish for public comments | The preliminary certificate that enables the Department to table the WSA Bill to Clusters and Cabinet has not been received and this is delaying the achievement of the following milestones. | Water Services Amendment Bill was not submitted to clusters | Target not met The preliminary certificate that enables the Department to table the WSA Bill to Clusters has not been received.
Water Services Institutional Oversight |  |  |  |  | 
6.3.1 | Performance of water boards evaluated against their performance plans | Assessment of shareholder compacts and quarterly reports for 9 water boards | Assessment of shareholder compacts for 8 water boards and quarterly reports for 9 water boards | Under by 1 | Target partially met Due to the disestablishment of Sedibeng Water by 31 July 2022, only 8 Water Boards SHCs and BPs were assessed.

## Slide 28: Part B: overview of financial performance

## Slide 29: Main Account 2022/23 Financial Performance
Programmes | Annual appropriation | Year to date cumulative approved drawings | Year to date cumulative actual expenditure | Available budget/ Variance | Variance - Accumulated drawings and actual expenditure | Projected spending | Expenditure as % of annual appropriation | Variance - Accumulated drawings and actual expenditure
 | R'000 | R'000 | R'000 | R'000 | R'000 | % | % | %
Administration | 2 012 509 | 514 525 | 391 420 | 1 621 089 | 123 105 | 25,57% | 19,45% | 6,12%
Water Resources Management | 3 782 924 | 1 501 148 | 1 476 163 | 2 306 761 | 24 985 | 39,68% | 39,02% | 0,66%
Water Services Management | 12 744 236 | 2 134 247 | 555 020 | 12 189 216 | 1 579 227 | 16,75% | 4,36% | 12,39%
Total Programmes | 18 539 669 | 4 149 920 | 2 422 603 | 16 117 066 | 1 727 317 | 22,38% | 13,07% | 9,32%
Economic classification |  |  |  |  |  |  |  | 
Current payments | 3 672 301 | 900 814 | 643 251 | 3 029 050 | 257 563 | 24,53% | 17,52% | 7,01%
Compesation of employees | 1 836 433 | 462 174 | 442 217 | 1 394 216 | 19 957 | 25,17% | 24,08% | 1,09%
Goods and services | 1 835 868 | 438 640 | 201 034 | 1 634 834 | 237 606 | 23,89% | 10,95% | 12,94%
Interest and rent on land | - | - | - | - | - | 0,00% | 0,00% | 0,00%
Transfers and subsidies | 10 528 115 | 2 112 727 | 1 439 574 | 9 088 541 | 673 153 | 20,07% | 13,67% | 6,39%
Province and municipalities | 6 223 394 | - | 164 | 6 223 230 | (164) | 0,00% | 0,00% | 0,00%
Departmental agencies and accounts | 2 612 130 | 1 141 661 | 1 145 013 | 1 467 117 | (3 352) | 43,71% | 43,83% | -0,13%
Foreign governments and international organisations | 250 978 | 146 851 | 146 851 | 104 127 | - | 58,51% | 58,51% | 0,00%
Public corporations and private enterprises | 1 413 686 | 811 973 | 143 729 | 1 269 957 | 668 244 | 57,44% | 10,17% | 47,27%
Non-profit institutions | 1 142 | 557 | 500 | 642 | 57 | 48,77% | 43,78% | 4,99%
Households | 26 785 | 11 685 | 3 317 | 23 468 | 8 368 | 43,63% | 12,38% | 31,24%
Payments for capital assets | 4 339 253 | 1 136 379 | 339 778 | 3 999 475 | 796 601 | 26,19% | 7,83% | 18,36%
Buildings and other fixed structures | 4 193 668 | 1 113 079 | 291 940 | 3 901 728 | 821 139 | 26,54% | 6,96% | 19,58%
Machinery and equipment | 99 202 | 23 300 | 5 872 | 93 330 | 17 428 | 23,49% | 5,92% | 17,57%
Software and other intangible assets | 46 383 | - | 41 966 | 4 417 | (41 966) | 0,00% | 90,48% | -90,48%
Payments for financial assets | - | - | - | - | - | 0,00% | 0,00% | 0,00%
Total economic classification | 18 539 669 | 4 149 920 | 2 422 603 | 16 117 066 | 1 727 317 | 22,38% | 13,07% | 9,32%

## Slide 30
Programme | Annual Budget | % spent against Annual budget | YTD Budget | YTD Actual Expenditure | Available Budget | % spent on YTD budget | % Variance
 | R’000 | % | R’000 | R’000 | R’000 | % | %
1. Administration | 1 293 018 | 12% | 306 105 | 159 970 | 1 133 049 | 52% | 48%
2. Implementation of water resources management activities | 738 874 | 29% | 295 816 | 216 009 | 522 865 | 73% | 27%
3. Operations, maintenance and refurbishment of national water resources schemes | 2 329 928 | 9% | 752 987 | 198 814 | 2 131 113 | 26% | 74%
4. Financing and investment in raw water infrastructure | 9 560 135 | 7% | 695 256 | 695 256 | 8 864 879 | 100% | 0%
5. Bulk water supply to strategic users | 2 328 334 | 7% | 755 170 | 173 616 | 2 154 718 | 23% | 77%
6. Implementation of dam safety | 184 471 | 13% | 40 100 | 24 150 | 160 321 | 60% | 40%
Total | 16 434 760 | 9% | 2 845 434 | 1 467 815 | 14 966 944 | 52% | 48%
Economic Classification | R’000 | % | R’000 | R’000 | R’000 | % | %
Compensation of Employees | 1 480 709 | 20% | 391 983 | 289 051 | 1 191 657 | 74% | 26%
Goods and Services | 2 625 232 | 14% | 790 720 | 357 429 | 2 267 804 | 45% | 55%
Trans Caledon Tunnel Authority (TCTA) | 9 560 135 | 7% | 695 256 | 695 256 | 8 864 879 | 100% | 0%
Payments for Capital Assets | 2 768 684 | 5% | 967 476 | 126 079 | 2 642 605 | 13% | 87%
Total | 16 434 760 | 9% | 2 845 434 | 1 467 815 | 14 966 944 | 52% | 48%
WTE 2022/23 Financial Performance

## Slide 31: Financial overview
The expenditure for the period ended 30 June 2022 amounted to R2.422 billion, representing thirteen per cent (13%) of the total adjusted budget of R18.539 billion, leaving total unspent funds of R2.532 billion.
The department reported an under expenditure of R1.727 billion.
Significant under expenditure per economic classification is as follows:
  Compensation of employees: R19.957 million
  Under spending mainly due to mandatory outer year budget reduction of R94,732 million, these funds may not be committed to prevent unauthorised expenditure in the year of budget reduction.
  b) Goods and services: R237.606 million
  The variance is due to impact of moratorium on procurement resultant from the constitutional court judgement, and other operational budget.
  c) Payments for capital assets: R796.601 million
  This is due to slow moving projects, procurement processes by Implementing Agents under water services and regional bulk infrastructure grants explained per province in the subsequent slides.
  d) Transfers and subsidies: R673.153 million
  Water Boards scheduled to second quarter pending finalisation of compliance documents.
  The 2022/23 local government payment schedule has been approved with transfer dates starting 28 July 2022 for WSIG and 4 August 2022 for RBIG.

## Slide 32: Earmarked, specifically and exclusively appropriated infrastructure items
Summary of Infrastructure Programmes | Original appropriation | Shifting of funds/ budget reallocation | Revised Allocation | Year to date cumulative approved drawings | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of Revised Allocation | Variance - Drawings and actual expenditure
 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | % | % | %
Regional Bulk Infrastructure Grant (RBIG): Conditional allocations to local government | 2 521 420 | - | 2 521 420 | - | - | 2 521 420 | - | 0,00% | 0,00% | 0,00%
Regional Bulk Infrastructure Grant (RBIG): Allocations-in-kind to municipalities for designated special programmes | 3 455 050 | - | 3 455 050 | 569 559 | 233 841 | 3 221 209 | 335 718 | 16,48% | 6,77% | 9,72%
Total RBIG | 5 976 470 | - | 5 976 470 | 569 559 | 233 841 | 5 742 629 | 335 718 | 9,53% | 3,91% | 5,62%
Water Services Infrastructure Grant (WSIG): Conditional allocations to local government | 3 701 019 | - | 3 701 019 | - | - | 3 701 019 | - | 0,00% | 0,00% | 0,00%
Bucket Eradication Programme (BEP): Allocations-in-kind to municipalities for designated special programmes | 110 174 | (22 987) | 87 187 | 8 232 | - | 87 187 | 8 232 | 9,44% | 0,00% | 9,44%
Water Services Infrastructure Grant (WSIG): Allocations-in-kind to municipalities for designated special programmes | 661 162 | (42 013) | 619 149 | 158 992 | 56 920 | 562 229 | 102 072 | 25,68% | 9,19% | 16,49%
Water Services Infrastructure Grant (WSIG): Disaster response allocation to provide water tankering services in KwaZulu-Natal | - | 65 000 | 65 000 | - | 315 | 64 685 | (315) | 0,00% | 0,48% | -0,48%
Total WSIG Total | 4 472 355 | - | 4 472 355 | 167 224 | 57 235 | 4 415 120 | 109 989 | 3,74% | 1,28% | 2,46%
Lepelle water board: Regional Bulk Infrastructure Grant | 422 000 | - | 422 000 | 422 000 | - | 422 000 | 422 000 | 100,00% | 0,00% | 100,00%
Magalies water board: Regional Bulk Infrastructure Grant | 109 284 | - | 109 284 | - | - | 109 284 | - | 0,00% | 0,00% | 0,00%
Sedibeng water board: Regional Bulk Infrastructure Grant | 143 729 | - | 143 729 | 143 729 | 143 729 | - | - | 100,00% | 100,00% | 0,00%
Umgeni water board: Regional Bulk Infrastructure Grant | 738 673 | - | 738 673 | 246 244 | - | 738 673 | 246 244 | 33,34% | 0,00% | 
Total Water Boards | 1 413 686 |  | 1 413 686 | 811 973 | 143 729 | 1 269 957 | 668 244 | 57,44% | 10,17% | 47,27%
Water Trading Entity - Acid mine drainage and other capital projects | 2 122 638 | - | 2 122 638 | 655 520 | 655 520 | 1 467 118 | - | 30,88% | 30,88% | 0,00%
Water Trading Entity - Contribution to operations and maintenance | 221 141 | - | 221 141 | 221 141 | 221 141 | - | - | 100,00% | 100,00% | 0,00%
Water Trading Entity - Establishment of Catchment Management Agencies | 70 000 | - | 70 000 | 70 000 | 70 000 | - | - | 100,00% | 100,00% | 0,00%
Water Trading Entity - Raising of clanwilliam dam olifants doorn river water resource project | 195 000 | - | 195 000 | 195 000 | 195 000 | - | - | 100,00% | 100,00% | 0,00%
Komati Basin Water Authority (KOBWA) | 248 278 | - | 248 278 | 146 851 | 146 851 | 101 427 | - | 59,15% | 59,15% | 0,00%
Total - Water Trading Entity and KOBWA | 2 857 057 | - | 2 857 057 | 1 288 512 | 1 288 512 | 1 568 545 | - | 45,10% | 45,10% | 0,00%
Total | 14 719 568 | - | 14 719 568 | 2 837 268 | 1 723 318 | 12 996 250 | 1 113 950 | 19,28% | 11,71% | 7,57%

## Slide 33: RBIG & WSIG 5B Financial Performance Per Province
Provinces | Original appropriation | Year to date cumulative actual spending | Available Budget/ Variance | Expenditure as % of original appropriation
 | R’000 | R’000 | R’000 | %
Eastern Cape | 431,907 | - | 431,907 | 0.00%
Free State | 204,407 | - | 204,407 | 0.00%
Gauteng | - | - | - | 0.00%
KwaZulu-Natal | 228,810 | - | 228,810 | 0.00%
Limpopo | 154,584 | - | 154,584 | 0.00%
Mpumalanga | 697,142 | - | 697,142 | 0.00%
Northern Cape | 135,102 | - | 135,102 | 0.00%
North West | 399,581 | - | 399,581 | 0.00%
Western Cape | 269,887 | - | 269,887 | 0.00%
Total RBIG | 2,521,420 | - | 2,521,420 | 0.00%
Narrative: Transfers to municipalities will take place on the 28 July 2022 and 4 August 2022 during the first quarter of their financial year. This is in accordance to the approved drawings.
Provinces | Original appropriation | Year to date cumulative actual spending | Available Budget/ Variance | Expenditure as % of original appropriation
 | R’000 | R’000 | R’000 | %
Eastern Cape | 498,051 | - | 498,051 | 0.00%
Free State | 332,599 | - | 332,599 | 0.00%
Gauteng | 196,678 | - | 196,678 | 0.00%
KwaZulu-Natal | 939,400 | - | 939,400 | 0.00%
Limpopo | 463,462 | - | 463,462 | 0.00%
Mpumalanga | 487,745 | - | 487,745 | 0.00%
Northern Cape | 266,948 | - | 266,948 | 0.00%
North West | 370,676 | - | 370,676 | 0.00%
Western Cape | 145,460 | - | 145,460 | 0.00%
Total WSIG | 3,701,019 | - | 3,701,019 | 0.00%

## Slide 34: WSIG 6B Financial Performance Per Province
Budget reprioritisation amounts includes R65 million for the KZN disaster, R32 million section 63 Umkhanyakude and R67.400 million for Eastern Cape NMB and Kouga water crisis intervention.
Shifting of funds was effected on slow moving projects, the shifting applied will not affect the current projects negatively as they are behind schedule and funding is being redirected to these projects during AENE and MTEF to prevent negative impact on affected communities.
Provinces | Year to date DoRA cumulative payment schedule | Shifting of funds/ budget reallocation |  | Revised Allocation | Year to date cumulative approved drawings | Year to date cumulative actual spending | Variance - Drawings and actual expenditure | Expenditure as % of Revised Allocation
 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | %
Eastern Cape | 30 000 | (2 662) | 57 400 | 84 738 | 14 650 | 3 193 | 11 457 | 3,77%
Free State (BEP) | 60 638 | (20 502) | - | 40 136 | 3 732 | - | 3 732 | 0,00%
Free State (WSIG) | - | 15 120 | - | 15 120 | - | 5 123 | (5 123) | 33,88%
Gauteng | 45 414 | (4 030) | (10 000) | 31 384 | - | 2 041 | (2 041) | 6,50%
KwaZulu-Natal | - |  | 32 600 | 32 600 | - | - | - | 0,00%
Limpopo | 271 814 | (24 123) | (60 000) | 187 691 | 50 892 | 6 012 | 44 880 | 3,20%
Mpumalanga | 140 000 | (12 425) | - | 127 575 | 27 782 | 18 796 | 8 986 | 14,73%
Northern Cape (WSIG) | 40 000 | (2 006) | - | 37 994 | - | 16 254 | (16 254) | 42,78%
Northern Cape (BEP) | 49 536 | (2 485) | - | 47 051 | 4 500 | - | 4 500 | 0,00%
North West | 133 934 | (11 887) | (30 000) | 92 047 | 65 668 | 5 501 | 60 167 | 5,98%
Western Cape | - | - | - | - | - | - | - | 0,00%
Total | 771 336 | (65 000) | (10 000) | 696 336 | 167 224 | 56 920 | 110 304 | 8,17%
Provinces | Original appropriation | Shifting of funds/ budget reallocation |  | Revised Allocation | Year to date DoRA cumulative payment schedule | Year to date cumulative actual spending | Variance - Drawings and actual expenditure | Expenditure as % of Revised Allocation
 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000 | %
KwaZulu-Natal | - | 65 000 |  | 65 000 | - | 315 | (315) | 0,48%
Eastern Cape | - |  | 10 000 | 10 000 | - | - | - | 0,00%
Total | - | 65 000 | 10 000 | 75 000 | - | 315 | (315) | 0,42%
Grand Total | 771 336 | - | - | 771 336 | 167 224 | 57 235 | 109 989 | 7,42%

## Slide 35: RBIG 6B Financial Performance Per Province
Some of the provinces recorded expenditure in line with the projections, however others recorded low expenditure due to the following reasons:
  Implementing Agents capacity constraints
  Work stoppages and Contractual disputes
  Community protests
  Disruptions by some business demanding allocation of tenders.
As part of recovery plans the Department has developed Infrastructure Procurement Strategy including implementation of project management systems, and support to the Implementing Agents.
Acceleration Plans are being implemented for projects including Bucket Eradication Programme, Vaal River Intervention Project and Madibeng Bulk Water Supply.
Provinces | Revised Allocation | Year to date DoRA Cumulative payment schedule | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Expenditure as % of Revised Allocation
 | R’000 | R’000 | R’000 | R’000 | R’000 | %
Eastern Cape | 355 681 | 64 913 | 41 523 | 314 158 | 23 390 | 11,67%
Free State (RBIG) | 691 129 | 27 700 | 44 045 | 647 084 | (16 345) | 6,37%
Free State (BEP) | 254 688 | 21 635 | 11 712 | 242 976 | 9 923 | 4,60%
Gauteng | 669 410 | 167 352 | 5 914 | 663 496 | 161 438 | 0,88%
Limpopo | 807 856 | 174 014 | 63 226 | 744 630 | 110 788 | 7,83%
Mpumalanga | 364 696 | 44 076 | 46 313 | 318 383 | (2 237) | 12,70%
Northern Cape (RBIG) | 54 643 | 19 726 | 3 862 | 50 781 | 15 864 | 7,07%
Northern Cape (BEP) | 1 814 | - | - | 1 814 | - | 0,00%
North West | 239 936 | 45 143 | 17 246 | 222 690 | 27 897 | 7,19%
Western Cape | 15 197 | 5 000 | - | 15 197 | 5 000 | 0,00%
Total | 3 455 050 | 569 559 | 233 841 | 3 221 209 | 335 718 | 6,77%

## Slide 36: Commitments Balances 2022/23
Province | June 2022 | March 2022 | Movement | % Movement to date
 | R’000 | R’000 | R’000 | %
Eastern Cape | 1 175 287 | 1 144 292 | 30 995 | 3%
Free State | 518 830 | 504 068 | 14 762 | 3%
Gauteng | 183 535 | 164 191 | 19 344 | 12%
KwaZulu-Natal | - | - | - | 0%
Limpopo | 1 716 164 | 1 696 107 | 20 057 | 1%
Mpumalanga | 513 798 | 586 786 | (72 988) | (12%)
Northern Cape | 113 772 | 117 635 | (3 863) | (3%)
North West | 1 354 382 | 1 149 013 | 205 369 | 18%
Western Cape | 4 427 | 4 427 | 0 | 0%
Head Office: Sanitation | 639 202 | 650 915 | 11 713 | (2%)
Total | 6 219 397 | 6 017 433 | 201 964 | 3%
Cumulative infrastructure projects commitments balances for Head Office and Regions as at 30 June 2022 amounts to R6.235 billion.
Some of the commitments are stagnant, and/or involves contractual disputes.
Nonperforming contractors included in the commitments are being engaged and where there is breach of contract, penalties and termination clauses will be invoked.

## Slide 37: Commitments Balances 2022/23 Continued…
Province | June 2022 | March 2022 | Movement
 | R’000 | R’000 | 
Senekal- Bulk Services | 67 551 | 67 551 | -
Fickburg- Bulk Services | 56 051 | 56 051 | -
Clocolan- Bulk Services | 59 598 | 59 598 | -
Postdene Maranteng | 7 689 | 7 689 | -
Griekwastad Campbel | 41 773 | 41 773 | -
Reitz and Petrus Steyn | 101 609 | 106 581 | (4 973)
Arlington and Dealeasville | 140 442 | 140 442 | -
Motswedimosa / Fraser Moleketi | - | - | -
Nketoana and Tokologo Bulk -Dealesville | 8 473 | 8 473 | -
Setsoto Mun - Clocolan / Ficksburg/ Senekal | 152 137 | 158 877 | (6 740)
Siyancuma | 3 879 | 3 879 | -
Total Bucket Eradication Programme | 639 202 | 650 915 | (11 713)
Cumulative Sanitation infrastructure projects commitments balances as at 30 June 2022 amounts to R639.202 million.
Contractors' performance assessments are being reviewed to resolve factors contributing to lack of performance, where there is breach of contract, penalties and termination clauses will be invoked.
Lack of performance is affecting spending of the programme and service delivery.

## Slide 38: Measures to prevent underspending
As part of the measures to prevent underspending the Department has reprioritised budgets between projects with supporting acceleration plans, including effective contract management, penalties and termination of non-performing Contractors. Some of the key prioritised projects includes the following:
Vaal River System Intervention – Rand Water
  The Emfuleni Section 63 Directive is being implemented by Rand Water with an estimated refurbishment cost of R655.960 million in the 2022/23 financial year.
  The Department has appointed seven Contractors (Replacement of collapsed pipelines and Electromechanical) and issued work packages with a combined value of R223.712 million during the month of August 2022 and construction has already commenced.
  Project performance has been affected by community protests and interruptions by business interest groups.
  More work packages are being processed and construction is being accelerated. Upon work certification significant expenditure will be realised thus mitigating underspending.
  The current budget allocation of R400 million will be increased with unspent funds from identified non-performing projects.
2. Madibeng Bulk Water Supply – Magalies Water
  The project had many challenges which resulted in work stoppages, community protests, liquidation of one of the service providers, poor project execution etc.
  Efforts have been made to resolve these challenges and six Contractors including Civil, Mechanical and Electrical Contractors have been appointed with expenditure projections estimated at R488 million in the 2022/23 financial year.
  The project is accelerating, and it is anticipated that additional funding will be required.
  The current budget allocation of R105 million will be increased with unspent funds from identified non-performing projects.

## Slide 39: Measures to prevent underspending
Loskop Regional Bulk Water Supply Scheme
  Three Contractors with a combined value of R1.5 billion have been appointed on 5 September 2022 and construction is expected to commence at the end of September 2022 as contractors are currently busy with contractual obligations such as Surety and Insurances.
  The current budget allocation of R140 million is projected to be spent in the 2022/23 financial year.
  Construction will be accelerated, and upon work certification significant expenditure will be realised.
4. Upgrade of the Olifantspoort and Ebenezer Water Supply Scheme – Lepelle Northern Water
  An amount of R422 million has been allocated through Budget Facility for Infrastructure Fund.
  Memorandum of Agreement has been concluded with transfer scheduled for the second quarter to enable Lepelle Northern Water to finalise the Implementation Readiness Study and the start of the refurbishment works.
  5. Budget reallocations between projects within the same province
  Reallocations between projects are also being processed, subsequent slide provides example of these budget adjustments within a province. These are also aimed at preventing underspending.

## Slide 40: Eastern Cape Province RBIG Schedule 6B Budget Reprioritisation
Project Name | Allocated Budget R'000 | Actual Exp. R'000 | Proposed Adjustment R'000 | Proposed Reallocation R'000 | Reason for adjustment
Ndlambe Bulk Water Supply | 26 246 | 1 226 | (21 246) | 5 000 | Ndlambe Local Municipality to be appointed as Implementing Agent, taking over from Amatola Water Board.
Xhora East Water Supply | 15 000 | 4 361 | 15 000 | 30 000 | Contractor is fast-tracking the works on site.
Graaf-Reinet Emergency Water Supply Scheme (WSS) | 7 000 | - | (6 285) | 715 | Project completed remaining budget allocation is for retention monies.
Sundays River - Paterson Bulk Water Supply | 4 500 | - | - | 4 500 | Implementing Agent submitted acceleration plan, and Contractor is back on site.
Ikwezi Bulk Water Supply | 25 000 | 11 515 | 5 000 | 30 000 | Contractor is fast-tracking the works on site.
Kirkwood Water Treatment Works | 15 000 | 66 | (10 000) | 5 000 | Implementing Agent delay in appointing Contractor, acceleration plan has been prepared.
Misgund Bulk Water Supply | 10 000 | 400 | (5 000) | 5 000 | Implementing Agent delay in appointing Contractor, acceleration plan has been prepared.
James Kleynhans Bulk Water Supply (BWS) | 30 000 | 2 797 | - | 30 000 | Contractor has been terminated due to poor performance. Acceleration and Procurement Plan has been finalised.
Mount Ayliff Bulk Peri Urban Water Supply | 15 000 | 20 186 | 35 000 | 50 000 | Contractor is fast-tracking the works on site. Progressing well.
Ngqamakhwe Bulk Water Supply (Butterworth Water Transfer Scheme) | 207 935 | 31 090 | (72 782) | 135 153 | Contractor has been terminated due to poor performance. Acceleration and Procurement Plan has been finalised.
Nooitgedagt Coega | - | 39 609 | 60 313 | 60 313 | Project progressing well.
Sub Total | 355 681 | 111 290 | - | 355 681 | 

## Slide 41: Gauteng Province RBIG Schedule 6B Budget Reprioritisation
Project Name | Allocated Budget R'000 | Actual Exp. R'000 | Proposed Adjustment R'000 | Proposed Reallocation R'000 | Reason for adjustment
Meyerton Waste Water Treatment Works | 50 000 | 812 | (20 000) | 30 000 | The project was put on hold at 96% due to contractor liquidation. Procurement of Civil contractors underway for the remaining works and complete the project.
Vaal River System Intervention | 400 000 | 78 973 | 120 000 | 520 000 | The Emfuleni Section 63 Directive is being implemented by Rand Water with an estimated refurbishment cost of R655.960 million in the 2022/23 financial year. Work packages totaling R223.712 million issued.
Sedibeng Regional Waste Water Treatment Works | 69 410 | 10 422 | (30 000) | 39 410 | The designs for the project Leeukuil and Rietspruit waste water treatment plants have been concluded. Module 7 designs concluded. Implementation readiness processes underway.
Sebokeng Wastewater Treatment Works | 50 000 | 29 789 | (5 000) | 45 000 | Budget provision for the project implementation readiness and settlement of outstanding Rand Water invoices.
Westonaria Regional Bulk Sanitation (Zuurbekom) | 60 000 | - | (60 000) | - | Process of updating Implementation Readiness Studies has begun and Municipality has been engaged to ensure that the project is still feasible for implementation.
Rothdene pump station and rising main | 10 000 | 13 122 | 25 000 | 35 000 | The project is at 96% complete and expected to be completed in the current financial year. Funding allocated for the completion of the remaining works.
Mohlakeng pump station and sewer outfall | 30 000 | - | (30 000) | - | Process of updating Implementation Readiness Studies has begun and Municipality has been engaged to ensure that the project is still feasible for implementation.
Sub Total | 669 410 | 133 118 | - | 669 410 | 

## Slide 42: Limpopo Province RBIG Schedule 6B Budget Reprioritisation
Project Name | Allocated Budget R'000 | Actual Exp. R'000 | Proposed Adjustment R'000 | Proposed Reallocation R'000 | Reason for adjustment
Giyani BWS Drought Relief (Nandoni to Ntsami) | 65 000 | 41 437 | 75 000 | 140 000 | Acceleration to complete the project by the end of financial year or first quarter of 2023/24. There are invoices at hand to the value of R25 million.
Giyani Water Services RM08 | 313 960 | 60 193 | (100 960) | 213 000 | Project on hold and likely to underspend the local business forum closed the site due to dispute over new security contract. This matter is receiving attention to ensure speedy resolution.
Mametja Sekororo Bulk Water Supply | 38 896 | 5 892 | (9 903) | 28 993 | First phase of the project is expected to be completed by end of third quarter. Second phase is expected to start in fourth quarter upon approval of IRS and the budget will be adjusted then in line with the implementation plan.
Sinthumule Kutama Bulk Water Augmentation (including Luvuvhu) | 50 000 | 13 757 | 20 000 | 70 000 | Acceleration to complete the project by March 2023
Mogalakwena Bulk Water Scheme | 40 000 | 28 287 | 40 000 | 80 000 | New contracts expected to commission the completed phase 1 of the project. Acceleration plan developed to expedite progress on the existing contracts.
Moutse Bulk Water Scheme | 30 000 | - | 70 799 | 100 799 | Variation order approved and SLA signed between Sekhukhune DM and DWS construction to complete and commission project 1. There are outstanding claims for P&Gs of DWS construction by the time project was on hold.
Nebo Bulk Water Scheme | 40 000 | - | - | 40 000 | Project on hold due to outstanding variation order approval that is beyond 20%. Sekhukhune DM engaged National Treasury and was processing the variation order for approval. This variation order is being finalised.
Mooihoek/Tubatse Bulk Water Scheme | 60 000 | 3 889 | (15 885) | 44 115 | Under performing contractor for Phase 4G1.1 terminated. Sekhukhune DM in the process of appointing new contractor to complete the scope. The contractor for phase 4G1.2 appointed subcontractor to assist in expediting progress on site.
Babanana pipeline | 170 000 | 3 455 | (79 051) | 90 949 | 2 subcontractors appointed to assist DWS construction and expedite the project progress. The new contractors are expected to resume site by October 2022.
Sub Total | 807 856 | 156 910 | 0 | 807 856 | 

## Slide 43: Mpumalanga Province RBIG Schedule 6B Budget Reprioritisation
Project Name | Allocated Budget R'000 | Actual Exp. R'000 | Proposed Adjustment R'000 | Proposed Reallocation R'000 | Reason for adjustment
Thembisile Water Scheme (Loskop) | 140 000 | 5 276 | - | 140 000 | Three Contractors with a combined value of R1.5 billion have been appointed on 5 September 2022 and construction is expected to commence at the end of September 2022 as contractors are currently busy with contractual obligations such as Surety and Insurances.
Western Highveld (Rust de Winter) Bulk Water Scheme | 5 000 | 688 | - | 5 000 | Feasibility studies in progress.
Balf/Siyat/Greyl/Willem/Nthor Bulk Water Supply | 50 000 | 71 107 | 60 000 | 110 000 | Phase 2 3 and 4 are already under construction.
Lekwa Waster Services | 40 000 | - | (20 000) | 20 000 | There are delays in the finalisation of the feasibility studies.
Amsterdam and Sheepmore Bulk Water Scheme | 40 000 | 1 129 | (20 000) | 20 000 | In the process of finalising WULA and concurrence from Eswatini.
Embalenhle Bulk Sewer and WWTW's refurbishment & upgrading | 10 000 | - | - | 10 000 | Finalising appointment of Gert Sibande District Municipality as and Implementing Agent.
Sibange Bulk Water Supply | 30 000 | 14 503 | - | 40 000 | Project phases are progressing as scheduled.
Driekoppies Upgrading | 49 696 | 2 833 | (20 000) | 29 696 | Poor performance by Contractor. Engagements are underway with the Implementing Agent to resolve the matter.
Sub Total | 364 696 | 98 892 | 0 | 807 856 | 

## Slide 44: North West Province RBIG Schedule 6B Budget Reprioritisation
Project Name | Allocated Budget R'000 | Actual Exp. R'000 | Proposed Adjustment R'000 | Proposed Reallocation R'000 | Reason for adjustment
Madibeng Bulk Water Supply (Brits) | 105 608 | 24 421 | 30 000 | 135 608 | Six Contractors including Civil, Mechanical and Electrical Contractors have been appointed with expenditure projections estimated at R488 million in the 2022/23 financial year. As project expenditure is being certified, budget under spending and declared savings from other provinces will be redirected to projects requiring additional funding.
Moretele South Bulk Water Supply (Klipdrift) | 30 000 | 29 101 | - | 30 000 | N/A
Mafikeng South Bulk Water Supply | 30 000 | 2 511 | (10 000) | 20 000 | Implementing Agent terminated Contractor due to non-performance. The termination of the Mechanical and electrical contractor delayed the project completion. The Company has been liquidated.
Ratlou Bulk Water Supply | 34 328 | 1 337 | (10 000) | 24 328 | The remaining portion of the civil work at 97%, and remaining balance is to complete Setlagole project. Commencement of Madibogo Phase 2 will be delayed, until Setlagole is complete. Madibogo will start with planning of detail design by January 2023.
Potchefstroom Wastewater Treatment Works upgrade (Tlokwe) Phase 1 to 5 | 40 000 | 2 573 | (10 000) | 30 000 | Implementing Agent terminated Contractor due to poor performance. Termination of the Contractor contributes to the delays of the project. Appointment of the contractor planned for October / November 2022.
Sub Total | 239 936 | 59 943 | - | 239 936 | 

## Slide 45: PART D: overview of the financial recovery plan

## Slide 46: Summary of status report
Broad strategies | Key outputs | Status
Funding and budget management | Implementation of audit action plans | Internal and External Audit Action Plans were developed and are being implemented.
 | Zero balance on overdraft | Positive bank balance achieved.
 | Implementation of debt collection and revenue enhancement strategy | Implementation of Revenue enhancement strategy, credit control and intergovernmental relations.
Expenditure control, financial governance and accountability | Implementation of the accruals and payables management plan | Prior years accruals and payables have been reduced through payments made from reprioritised budgets.
 | Fruitless and wasteful expenditure condonations and remedial measures. | Preventative measures have been implemented to ensure that no further incidents are reported.
 | Irregular expenditure condonations and remedial measures report | Condonation requests have been submitted to National Treasury. Irregular expenditure was incurred on running contracts which were declared as irregular in the previous financial years.
 | Report on implementation of exit strategies on irregular contracts | Legal review of irregular contracts is in progress. This includes work by the SIU and Legal Services.
Alignment of strategic intent | Align strategy, annual performance plans (APP) and budgets | Strategy and APP have been aligned to Estimates of National Expenditure and Procurement Plans.
Capital budget and asset management | Comprehensive reconciliations of assets and liabilities to enable maintenance of proper accounting records for management and reporting purposes. | Status reports have been compiled for infrastructure assets with remedial actions. Annual engineer’s reviews have been compiled with remedial actions

## Slide 47: Financial highlights
MAIN ACCOUNT | June | March | Movement
Details | 2022 | 2022 | Movement
 | R'000 | R'000 | R'000
Bank balance Favourable (Unfavourable balance) | 3 499 019 | 1 756 287 | 1 742 732
Prepayments and advances | 123 409 | 156 965 | (33 556)
Contingent Assets | 3 714 892 | 3 622 404 | 92 488
Accruals and payables | 335 855 | 405 823 | (69 968)
Commitments | 6 255 779 | 6 116 970 | 138 809
Contingent liabilities | 11 033 259 | 11 197 640 | (164 381)
Unauthorised expenditure | 641 109 | 641 109 | -
Fruitless and wasteful expenditure | 16 813 | 16 813 | -
Irregular expenditure | 9 459 330 | 9 459 106 | 224
Advances includes amounts paid as per the Implementation Agreements with Water Boards and HDA for Regional Bulk and Water Services Infrastructure projects, including Bucket Eradication Programme.
Contingent assets includes mainly legal claims by the Department (Joint with Special Investigating Unit) for the Giyani Water Project & Fumile Advisory Services. The matters are before the Polokwane & Gauteng High Courts).
Contingent Liabilities, Accruals and payables reductions are due to settlements processed in the current period.
Unauthorised expenditure relates to prior year’s overspending of the main division of the vote due to the War-on-Leaks Project and Bucket Eradication Programme. National Treasury has submitted consolidated recommendations to SCOPA and amounts will be cleared once approval is granted.
No Irregular expenditure were reported for the period under review.
No fruitless and wasteful expenditure were reported for the period under review.

## Slide 48: Financial highlights
By end of June 2022, an amount of R25.4867 billion was owed by trade customers. In addition to enforcement of credit control measures, the Department is part of the Multidisciplinary Revenue Committee (MdRC) which comprises of National Treasury, South African Local Government Association and Department of Cooperative Government and Traditional Affairs which focusses on providing solutions to water debt challenges across the value chain.
Long-term Financial liabilities represents the amounts owed to Trans-Caledon Tunnel Authority (TCTA) in accordance with various construction contracts for the development and maintenance of infrastructure assets. Compared to prior year these the Long-term Financial Liabilities have decreased by R1.946 billion.
Contingent liabilities mainly consist of legal claims against the Department by several service providers in respect of contractual disputes which are on litigation process.
Fruitless and Wasteful Expenditure has been incurred as a result of irrecoverable construction costs incurred in the internal projects and external projects.
WATER TRADING ENTITY | June | March | Movement | 
Details | 2022 | 2022 | Movement | 
 | R'000 | R'000 | R'000 | 
Bank balance Favourable | 4 125 228 | 2 141 999 | 1 983 229 | 
Trade receivables (Gross) | 25 486 008 | 24 613 875 | 872 133 | 
Contingent Assets | 2 925 | 2 925 | - | 
Long- term Financial liabilities | 13 060 459 | 11 114 432 | 1 946 027 | 
Payables from exchange transactions | 2 159 567 | 2 281 500 | (121 933) | 
Commitments | 1 171 979 | 1 848 706 | (676 727) | 
Contingent liabilities | 323 279 | 323 279 | - | 
Fruitless and wasteful expenditure | 206 808 | 206 808 | - | 
Irregular expenditure | 7 102 949 | 7 082 046 | 20 903 | 

## Slide 49: Audit outcomes
The 2020/21 audit outcomes:
  The main vote received qualified audit opinion with findings.
  The WTE received unqualified audit opinion with findings
The audit qualification was resolved in the 2021/22 financial year.
Detailed audit action plans have been put in place with specific corrective actions and milestones, with progressive implementation towards achieving a clean audit (see Annexure A)
Preventative measures being implemented incorporate the following:
  Awareness, staff training and development
  Strengthening internal controls
  Compliance and governance structures
  Consequence management
The Department is proactively engaging with the Office of the Accountant-General on matters related to accounting treatment of some of the transactions.
The following slides discuss some of the key irregularities raised by the AG

## Slide 50: Progress on Unauthorised, Irregular, Fruitless and Wasteful Expenditure
Details | Main Account |  | Water Trading Entity | 
 | 2022/23 (Q1) R'000 | 2021/22 R'000 | 2022/23 (Q1) R'000 | 2021/22 R'000
Unauthorised expenditure | 641 109 | 641 109 | - | -
Fruitless and wasteful expenditure | 16 813 | 16 813 | 206 808 | 206 808
Irregular expenditure | 9 459 330 | 9 459 106 | 7 102 949 | 7 082 046
No unauthorised expenditure was incurred since the prior period incidents.
The Unauthorized Expenditure relates to overspending on Bucket eradication and War on Leaks programmes in prior years and was reported to National Treasury for processing to Parliament.
Fruitless and wasteful expenditure relates mainly to costs that could not be recovered from projects, these were incurred on internal and external construction projects. Further incidents were noted on the WTE and are currently at an assessment stage.
Included in the Irregular Expenditure is an amount of R8.800 billion submitted for condonation.
The reported incidents of unauthorized, irregular, fruitless and wasteful expenditure are at various processing stages, including investigations (by the department, Special Investigating Unit and South African Police Service), disciplinary proceedings and court proceedings.
The Department appointed a panel of Professional Service Providers (PSPs) to augment the current investigation capacity of the Internal Audit Unit.

## Slide 51: Summary of Unauthorised Expenditure
Details | 2022/23 (Q1) R’000 | 2021/22 R’000
Bucket eradication programme | 292 269 | 292 269
War on Leaks programme | 348 840 | 348 840
Closing balance | 641 109 | 641 109
No unauthorised expenditure incurred in 2021/22 and 2022/23 financial years.
Reported to National Treasury for processing to Parliament, awaiting outcome.
The amount of R292.269 million relates to over-spending of the vote in the 2016/17 financial year, mainly as a result of the payment of expenditure on the Bucket Eradication Programme (BEP)
The amount of R348.840 million relates to over-spending of the main division within the vote and is attributable to the expenditure incurred on War on Leaks (WoL) Programme without a budget in 2017/18 financial year.

## Slide 52: Summary of Fruitless and Wasteful Expenditure
Fruitless and wasteful expenditure relates mainly to costs that could not be recovered and capitalised to projects, these were incurred on internal and external construction projects.
Investigations are being accelerated to enable finalisation before the end of 2022/23 financial year.
Further incidents were noted on the WTE and are currently at an assessment stage.
Details | Main Acc | WTE | Total
 | 2022/23 (Q1) | 2022/23 (Q1) | R’000
 | R’000 | R’000 | 
Opening balance | 16 813 | 206 808 | 223 621
Additions (New cases) | - | - | -
Deductions (Amounts recoverable) | - | - | -
Deductions (Amounts written-off) | - | - | -
Closing balance | 16 813 | 206 808 | 223 621

## Slide 53: Summary of Irregular Expenditure
Details | Main Acc | WTE | Total
 | 2022/23 (Q1) | 2022/23 (Q1) | R’000
 | R’000 | R’000 | 
Opening balance | 9 459 106 | 7 082 046 | 16 541 152
Additions | 224 | 20 903 | 21 127
Condonations | - | - | -
Closing balance | 9 459 330 | 7 102 949 | 16 562 279
Of which: |  |  | 
Condonations in progress | 6 176 170 | 2 641 307 | 8 817 477
Submitted for investigation | 265 405 | 1 770 315 | 2 035 720
Assessment | 3 017 755 | 2 691 327 | 5 709 082
Total | 9 459 330 | 7 102 949 | 16 562 279
Percentage breakdown |  |  | 
Condonations in progress | 65% | 37% | 53%
Submitted for investigation | 3% | 25% | 12%
Assessment | 32% | 38% | 35%
Total | 100% | 100% | 100%
Of the irregular expenditure R16.562 billion, total amount of R8.817 billion is in the process of condonation with R2.035 billion submitted for investigation and R5.709 billion under assessment.
A panel of Professional Service Providers (PSPs) Forensic Audit and Investigators, are assisting to accelerate the investigations in progress.
Current cases include:
- Main Account: Proper process not followed when appointing the official to the post of the Deputy Director.
- WTE: Emergency procurement not supported by National Treasury in the previous financial year.

## Slide 54: Irregular expenditure in process of condonation
Description | Main Account | WTE | Total | Status/ Comments
 | R'000 | R'000 | R'000 | 
Giyani Water Services Project | 3 381 034 | - | 3 381 034 | The disciplinary hearing was concluded. The employee was found not guilty. Department has taken the matter on review. The matter is currently in the labour court. The department is reviewing the Presiding Office’s report verdict in the labour court. Awaiting the outcome of the review application.
Upgrading of the Thukela Goedertrouw Scheme | - | 477 310 | 477 310 | Two employees implicated. Department has taken the matter on review. The matter is currently in the labour court. The department is reviewing the Presiding Officer’s verdict at the Labour Court The other employee has been served with a charge sheet. Labour Court review will determine the way forward on this matter.
Desalination Plant Richards Bay | 301 168 | 9 684 | 310 852 | Two employees implicated. Both employees implicated have been served with charge sheets. Hearing in respect of one employee is nearing conclusion (leading of evidence has been concluded and the employee was found guilty on 9 of the 10 charges). Pronouncement of sanction is awaited. Hearing resumed on 10 August 2022. Final outcome is expected in October 2022.
Support and maintenance of SAP ECC6 | - | 285 951 | 285 951 | Disciplinary file currently being processed by Labour Relations.

## Slide 55: Irregular expenditure in process of condonation
Description | Main Account | WTE | Total | Status/ Comments
 | R'000 | R'000 | R'000 | 
Unlimited SAP licences | - | 285 000 | 285 000 | Hearing is nearing conclusion (leading of evidence has been concluded and the employee was found guilty on 9 of the 10 charges). Pronouncement of sanction is awaited. Hearing resumed on 10 August 2022. Outcome is expected in October 2022. Combined Civil litigation is underway (DWS and SIU).
War on Leaks Project | 823 130 | 1 499 330 | 2 322 460 | Disciplinary file currently being processed by Labour Relations.
Bucket Eradication Project | 1 503 707 | - | 1 503 707 | Disciplinary file currently being processed by Labour Relations.
Financial advisory services | 17 901 | - | 17 901 | Disciplinary hearing started in October 2021. The hearing proceeded on 19-21 July 2022. The hearing will continue on 3-5 October 2022. (Managed by Gauteng Finance Department). Furthermore Civil Litigation is underway for recovery of costs incurred.
Isiphethu | - | 17 188 | 17 188 | Representation has been made by the employee. Decision has to be made whether disciplinary action will proceed.
Payments made without a Purchase Order | - | 66 844 | 66 844 | Condonation application under consideration by National Treasury.
Transfer payments | 114 879 |  | 114 879 | Condonation application under consideration by National Treasury.
Gift of the Givers | 20 376 |  | 20 376 | Condonation application under consideration by National Treasury.
Dube ZT of CTSAP Investigators | 3 477 |  | 3 477 | Condonation application under consideration by National Treasury.
Total | 6 165 672 | 2 641 307 | 8 806 979 | 

## Slide 56: Irregular expenditure condoned by National Treasury
In total the amount of irregular expenditure condoned by National Treasury is R1.488 billion.
The department ensures that remedial actions are taken, to ensure that a similar irregular expenditure is not incurred in future.
The Department strengthened and enhanced internal controls for procurement processes, procedures and contract management so as to address root causes of irregular expenditure.
Details | R’000 | Description
Caps M – Cleaning services | 53 587 | This incident has been condoned by the National Treasury on 05 May 2022, and it applies to both Main Account and WTE.
Alteram Solutions – Call Centre (CRM) | 230 545 | This incident has been condoned by the National Treasury on 07 June 2022, and it applies to WTE.
Private Security Services | 967 491 | This incident has been condoned by the National Treasury on 07 June 2022, and it applies to both Main Account and WTE.
EOH Mthombo – Information Technology Services | 236 349 | This incident has been condoned by the National Treasury on 07 June 2022, and it applies to Main Account.
Total | 1 487 972 | 

## Slide 57
Irregular expenditure trend analysis
Chart: Trend Analysis of IE Per Financial Year
| 2022/23 (Q1) R'000 | 2021/22 R'000 | 2020/21 R'000 | 2019/20 R'000 | 2018/19 R'000 | 2017/18 R'000 | 2016/17 R'000 | 2015/16 R'000 | 2014/15 R'000
WTE | 20903 | 239869 | 179995 | 142146 | 2460392 | 1631993 | 4346 | 54566 | 4151
Main Account | 224 | 220864 | 270697 | 694624 | 3129522 | 1977841 | 1685990 | 1711346 | 87936

## Slide 58
Total Irregular expenditure trend analysis
Chart: Trend Analysis of Total IE Per Financial Year
| 2022/23 (Q1) R'000 | 2021/22 R'000 | 2020/21 R'000 | 2019/20 R'000 | 2018/19 R'000 | 2017/18 R'000 | 2016/17 R'000 | 2015/16 R'000 | 2014/15 R'000
WTE | 7102949 | 7082046 | 7909028 | 7729033 | 7357423 | 4897031 | 330221 | 325875 | 655324
Main Account | 9459330 | 9459106 | 9903612 | 9632942 | 9285547 | 6156025 | 4179070 | 2493172 | 330162

## Slide 59: Narrative of the total Irregular Expenditure balance as incurred per financial year
To date, the total/accumulative irregular expenditure per financial year amounts to R16.562 billion, this figure has been adjusted from 17.812 billion due to the condonation approved by National Treasury.
 | 2022/23 (Q1) R'000 | 2021/22 R'000 | 2020/21 R'000 | 2019/20 R'000 | 2018/19 R'000 | 2017/18 R'000 | 2016/17 R'000 | 2015/16 R'000 | 2014/15 R'000
WTE | 7 102 949 | 7 082 046 | 7 909 028 | 7 729 033 | 7 357 423 | 4 897 031 | 330 221 | 325 875 | 655 324
Main Account | 9 459 330 | 9 459 106 | 9 903 612 | 9 632 942 | 9 285 547 | 6 156 025 | 4 179 070 | 2 493 172 | 330 162
Total | 16 562 279 | 16 541 152 | 17 812 640 | 17 361 975 | 16 642 970 | 11 053 056 | 4 509 291 | 2 819 047 | 985 486

## Slide 60
Preventative measures against fraud and corruption
The Department is implementing a turnaround and financial recovery plan which incorporates stabilisation of the Department (Leadership, ethics and organisational culture, staff training and development), improvement of systems of internal controls, preventative measures against fraud and corruption
Trend analysis of improper expenditure is reflecting a decline in incidents of irregular, fruitless and wasteful expenditure
There are no new incidents of unauthorised expenditure
There are also measures taken to eliminate irregular, fruitless and wasteful expenditure. Supported by preventative controls measures
An exit strategy on irregular contracts is also being implemented to ensure that the current incidents of irregular expenditure resulting from prior periods contract are terminated
Progress has been made on disciplinary and investigation matters including continued engagement with various law enforcement agencies
The streamlined and integrated water sector value chain support and interventions measures by the Department are also part of service delivery improvement plans

## Slide 61: Progress on forensic Investigation cases 2019/2020 to 2022/23
A total of 228 total cases were reported to Internal Audit Unit
135 Forensic Investigation cases were investigated by the Department’s Internal Audit Unit during the period 2019/20 to 2022/23.
98 of the allegations were confirmed to be true while 37 were unfounded.
20 cases are currently under investigation.
73 cases have not been investigated yet.
Other cases will be investigated by External Services Providers in order to expedite them.
A panel of investigators has been appointed to expedite these cases
The finalised cases (98) referred to:
  Employee Relations to take disciplinary action against the officials who committed financial and other acts of misconduct;
  SAPS and the Hawks for criminal investigation; and
  Legal Services for Civil Recovery in instances where the Department has suffered financial loss.
These cases resulted in sanctions against the transgressors. These sanctions included: Dismissal, Demotion, Suspension without pay, Written Warning letters.
These cases resulted in an amount of R996 883.24 being recovered through Civil Recovery processes and a judgement of R27 510 067.17 in favour of the Department.
74 awareness sessions during the period 2019/20 to 2022/23 wherein 1 781 officials were trained about anti-fraud and corruption measures.
Notes: Engage DG on the Capacity Challenges and how DWS has mitigated?
[Indicate that Panel has been appointed , add a point in the slide on progress.]

## Slide 62: Thank you

## Slide 63: PART e: APPENDIX WITH additional slides
DETAILS OF WATER SERVICES INFRASTRUCTURE DEVELOPMENT GRANTS PER PROJECT/ WATER SERVICES AUTHORITY/ BENEFITTING MUNICIPALITIES
RBIG 5B financial performance per province and benefiting municipalities
RBIG 6B financial performance per province, benefiting municipalities and projects
RBIG 6B Water Board financial performance per province and projects
WSIG 5B financial performance per province and benefiting municipalities
WSIG 6B financial performance per province

## Slide 64: 5. AN OVERVIEW OF GRANTS PERFORMANCE
Regional Bulk Infrastructure Grant: Water Boards Per Project and Province

## Slide 65: Water Boards Financial Performance
Transfer Payments for the Budget Facility for Infrastructure and Regional Bulk Infrastructure Grant |  |  |  |  |  |  | 
Project Name | Original appropriation | Shifting of funds / budget reallocation | Total revised allocation | Year to date cumulative approved drawings | Year to date cumulative actual spending | Available Budget/ Variance | Expenditure as % of Revised Allocation
Project Name | R'000 | R'000 | R'000 | R'000 | R'000 | R'000 | %
Upgrade of Olifants and Ebenezer water supply schemes (Budget Facility for Infrastructure) | 422 000 | - | - | 422 000 | - | 422 000 | 0,00%
Total | 422 000 | - | - | 422 000 | - | 422 000 | 0,00%
North West Regional Bulk Infrastructure Grant (RBIG): Magalies Water Board |  |  |  |  |  |  | 
Pilanesberg Bulk Water Supply Scheme phase 3 | 109 284 | - | - | - | - | 109 284 | 0,00%
Total | 109 284 |  |  | - | - | 109 284 | 0,00%
KwaZulu-Natal Regional Bulk Infrastructure Grant (RBIG): Umgeni Water Board |  |  |  |  |  |  | 
Umshwathi Regional Bulk Water Supply Scheme | 445 673 | (420 948) | 24 725 | 246 244 | - | 445 673 | 0,00%
Lower uMkhomazi Bulk Water Supply Scheme (Budget Facility for Infrastructure) | 193 000 | 459 448 | 652 448 | - | - | 193 000 | 0,00%
Greater Mpofana Regional Bulk Water Supply Phase 1-3 | 50 000 | - | 50 000 | - | - | 50 000 | 0,00%
Maphumulo Bulk Water Supply | 50 000 | (38 500) | 11 500 |  |  | 50 000 | 0,00%
Total | 738 673 | - | 11 500 | 246 244 | - | 738 673 | 0,00%
Northern Cape Regional Bulk Infrastructure Grant (RBIG): Sedibeng Water Board |  |  |  |  |  |  | 
Replacement of Namakwa Bulk Water Supply | 143 729 | - | - | 143 729 | 143 729 | - | 100,00%
Total Allocations for Water Boards | 1 413 686 | - | - | 811 973 | 143 729 | 1 269 957 | 10,17%

## Slide 66: Water Boards Financial Performance
Narrative
Lepelle Northern Water: R422 million has been rescheduled for transfer in the second quarter upon finalisation of the Implementation agreement for the Olifantspoort and Ebenezer Project by DDG: W&S SM.
Magalies Water: R109 million - will be transferred in January 2023 as per the approved drawings.
Umgeni Water: R246.2 million - requested reprioritisation of funds from projects experiencing delays to projects that are advancing. The – Lower uMkhomazi Bulk Water Supply Scheme project is likely move faster than anticipated due to the budget reallocation proposed. Construction is currently underway. Submission for budget reprioritization has been forwarded to National Treasury for approval.
Sedibeng Water: R143.7 million - transferred during the first quarter as per the approved drawings, part of ring-fenced funds to Bloem Water upon disestablishment of Sedibeng Water.

## Slide 67: 5. AN OVERVIEW OF GRANTS PERFORMANCE
Regional Bulk Infrastructure Grant: 5B Per Province / Municipalities

## Slide 68: Regional Bulk Infrastructure Grant: 5B per province / municipality
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Eastern Cape Province | 431 907 | - | - | 0%
DC13 Chris Hani District Municipality | 216 907 |  |  | 0,00%
DC14 Joe Gqabi District Municipality | 15 000 |  |  | 0,00%
DC15 O.R. Tambo District Municipality | 200 000 |  |  | 0,00%
Free State Province | 204 407 | - | - | 0,00%
FS163 Mohokare Local Municipality | 4 407 |  |  | 0,00%
FS191 Setsoto Local Municipality | 150 000 |  |  | 0,00%
FS203 Ngwathe Local Municipality | 50 000 |  |  | 0,00%
Kwa-Zulu Natal Province | 228 810 | - | - | 0,00%
DC26 Zululand District Municipality | 15 247 |  |  | 0,00%
DC28 Uthungulu District Municipality | 213 563 |  |  | 0,00%
Limpopo Province | 154 584 | - | - | 0,00%
LIM354 Polokwane Local Municipality | 154 584 |  |  | 0,00%
Mpumalanga Province | 697 142 | - | - | 0,00%
MP301 Chief Albert Luthuli Local Municipality | 165 142 |  |  | 0,00%
MP302 Msukaligwa Local Municipality | 175 000 |  |  | 0,00%
MP313 Steve Tshwete Local Municipality | 145 000 |  |  | 0,00%
MP324 Nkomazi Local Municipality | 200 000 |  |  | 0,00%
MP326 City of Mbombela | 10 000 |  |  | 0,00%
MP321 Thaba Chweu Local Municipality | 2 000 |  |  | 0,00%
Northern Cape Province | 135 102 | - | - | 0,00%
NC065 Hantam Local Municipality | 50 000 |  |  | 0,00%
NC085 Tsantsabane Local Municipality | 85 102 |  |  | 0,00%
North West Province | 399 581 | - | - | 0,00%
DC39 Dr Ruth Segomtsi Mompti District Municipality | 399 581 |  |  | 0,00%
Western Cape Province | 269 887 | - | - | 0,00%
WC011 Matzikama Local Municipality | 10 000 |  |  | 0,00%
WC022 Witzenberg Local Municipality | 19 239 |  |  | 0,00%
WC044 George Local Municipality | 240 648 |  |  | 0,00%
Total Regional Bulk Infrastructure Grant (RBIG) | 2 521 420 | - | - | 0,00%

## Slide 69: 5. AN OVERVIEW OF GRANTS PERFORMANCE
Water Services Infrastructure Grant: 5B Per Province / Municipality

## Slide 70: Water Services Infrastructure Grant: 5B per province and municipality (1)
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Eastern Cape Province | 498 051 | - | - | 0%
EC101 Dr Beyers Naude Local Municipality | 10 939 |  |  | 0,00%
EC102 Blue Crane Route Local Municipality | 10 000 |  |  | 0,00%
EC104 Makana Local Municipality | 16 112 |  |  | 0,00%
EC105 Ndlambe Local Municipality | 85 000 |  |  | 0,00%
EC106 Sundays River Valley Local Municipality | 20 000 |  |  | 0,00%
DC12 Amathole District Municipality | 86 000 |  |  | 0,00%
DC13 Chris Hani District Municipality | 60 000 |  |  | 0,00%
DC14 Joe Gqabi District Municipality | 60 000 |  |  | 0,00%
DC15 O.R. Tambo District Municipality | 50 000 |  |  | 0,00%
DC44 Alfred Nzo District Municipality | 100 000 |  |  | 0,00%
Free State Province | 332 599 | - | - | 0,00%
FS161 Letsemeng Local Municipality | 20 000 |  |  | 0,00%
FS162 Kopanong Local Municipality | 20 000 |  |  | 0,00%
FS163 Mohokare Local Municipality | 22 088 |  |  | 0,00%
FS181 Masilonyana Local Municipality | 23 334 |  |  | 0,00%
FS182 Tokologo Local Municipality | 15 720 |  |  | 0,00%
FS183 Tswelopele Local Municipality | 12 276 |  |  | 0,00%
FS184 Matjhabeng Local Municipality | 25 800 |  |  | 0,00%
FS185 Nala Local Municipality | 11 528 |  |  | 0,00%
FS191 Setsoto Local Municipality | 15 301 |  |  | 0,00%
FS192 Dihlabeng Local Municipality | 13 000 |  |  | 0,00%
FS193 Nketoana Local Municipality | 20 000 |  |  | 0,00%
FS194 Maluti- a-Phofung Local Municipality | 38 896 |  |  | 0,00%
FS195 Phumelela Local Municipality | 15 328 |  |  | 0,00%
FS196 Mantsopa Local Municipality | 11 720 |  |  | 0,00%
FS201 Moqhaka Local Municipality | 10 292 |  |  | 0,00%
FS203 Ngwathe Local Municipality | 15 000 |  |  | 0,00%
FS204 Metsimaholo Local Municipality | 22 316 |  |  | 0,00%
FS205 Mafube Local Municipality | 20 000 |  |  | 0,00%

## Slide 71: Water Services Infrastructure Grant: 5B per province and municipality (2)
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Gauteng Province | 196 678 | - | - | 0,00%
GT422 Midvaal Local Municipality | 18 864 |  |  | 0,00%
GT423 Lesedi Local Municipality | 18 874 |  |  | 0,00%
GT481 Mogale City Local Municipality | 45 160 |  |  | 0,00%
GT484 Merafong City Local Municipality | 40 420 |  |  | 0,00%
GT485 Rand West City Local Municipality | 73 360 |  |  | 0,00%
Kwa-Zulu Natal Province | 939 400 | - | - | 0,00%
DC21 Ugu District Municipality | 70 000 |  |  | 0,00%
KZN225 Msunduzi Local Municipality | 60 000 |  |  | 0,00%
DC22 uMgungundlovu District Municipality | 85 600 |  |  | 0,00%
DC23 uThukela District Municipality | 80 800 |  |  | 0,00%
DC24 uMzinyathi District Municipality | 80 000 |  |  | 0,00%
KZN252 Newcastle Local Municipality | 48 000 |  |  | 0,00%
DC25 Amajuba District Municipality | 70 000 |  |  | 0,00%
DC26 Zululand District Municipality | 95 000 |  |  | 0,00%
DC27 uMkhanyakude District Municipality | 60 000 |  |  | 0,00%
KZN282 Umhlathuze Local Municipality | 50 000 |  |  | 0,00%
DC28 King Cetshwayo District Municipality | 65 000 |  |  | 0,00%
DC29 ILembe District Municipality | 80 000 |  |  | 0,00%
DC43 Harry Gwala District Municipality | 95 000 |  |  | 0,00%
Limpopo Province | 463 462 | - | - | 0,00%
DC33 Mopani District Municipality | 50 000 |  |  | 0,00%
DC34 Vhembe District Municipality | 60 000 |  |  | 0,00%
LIM354 Polokwane Local Municipality | 77 160 |  |  | 0,00%
DC35 Capricorn District Municipality | 115 000 |  |  | 0,00%
LIM366 Bela Bela Local Municipality | 62 010 |  |  | 0,00%
LIM367 Mogalakwena Local Municipality | 47 640 |  |  | 0,00%
DC47 Greater Sekhukhune District Municipality | 51 652 |  |  | 0,00%

## Slide 72: Water Services Infrastructure Grant: 5B per province and municipality (3)
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Mpumalanga Province | 487 745 | - | - | 0,00%
MP301 Chief Albert Luthuli Local Municipality | 62 745 |  |  | 0,00%
MP302 Msukaligwa Local Municipality | 60 000 |  |  | 0,00%
MP303 Mkhondo Local Municipality | 55 000 |  |  | 0,00%
MP304 Pixley Ka Seme Local Municipality | 20 000 |  |  | 0,00%
MP311 Victor Khanye Local Municipality | 20 000 |  |  | 0,00%
MP312 Emalahleni Local Municipality | 15 000 |  |  | 0,00%
MP313 Steve Tshwete Local Municipality | 35 000 |  |  | 0,00%
MP314 Emakhazeni Local Municipality | 20 000 |  |  | 0,00%
MP315 Thembisile Local Municipality | 25 000 |  |  | 0,00%
MP321 Thaba Chweu Local Municipality | 40 000 |  |  | 0,00%
MP324 Nkomazi Local Municipality | 50 000 |  |  | 0,00%
MP325 Bushbuckridge Local Municipality | 55 000 |  |  | 0,00%
MP326 City of Mbombela | 30 000 |  |  | 0,00%

## Slide 73: Water Services Infrastructure Grant: 5B per province and municipality (4)
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Northern Cape Province | 266 948 | - | - | 0,00%
NC451 Joe Morolong Local Municipality | 40 000 |  |  | 0,00%
NC452 Gasegonyana Local Municipality | 30 000 |  |  | 0,00%
NC453 Gamagara Local Municipality | 5 000 |  |  | 0,00%
NC061 Richtersveld Local Municipality | 10 000 |  |  | 0,00%
NC062 Nama Khoi Local Municipality | 20 000 |  |  | 0,00%
NC064 Kamiesberg Local Municipality | 5 000 |  |  | 0,00%
NC065 Hantam Local Municipality | 11 000 |  |  | 0,00%
NC066 Karoo Hoogland Local Municipality | 13 000 |  |  | 0,00%
NC071 Ubuntu Local Municipality | 9 000 |  |  | 0,00%
NC072 Umsobomvu Local Municipality | 15 000 |  |  | 0,00%
NC073 Emthanjeni Local Municipality | 16 000 |  |  | 0,00%
NC075 Renosterberg Local Municipality | 5 000 |  |  | 0,00%
NC076 Thembelihle Local Municipality | 10 000 |  |  | 0,00%
NC078 Siyancuma Local Municipality | 6 000 |  |  | 0,00%
NC082 !Kai !Garib Local Municipality | 9 000 |  |  | 0,00%
NC084 Kheis Local Municipality | 5 000 |  |  | 0,00%
NC085 Tsantsabane Local Municipality | 6 000 |  |  | 0,00%
NC086 Kgatelopele Local Municipality | 12 000 |  |  | 0,00%
NC087 //Khara Hais/Mier Local Municipality | 5 000 |  |  | 0,00%
NC091 Sol Plaatjie Local Municipality | 19 948 |  |  | 0,00%
NC093 Magareng Local Municipality | 5 000 |  |  | 0,00%
NC094 Phokwane Local Municipality | 10 000 |  |  | 0,00%
North West Province | 370 676 | - | - | 0,00%
NW371 Moretele Local Municipality | 65 000 |  |  | 0,00%
NW373 Rustenburg Local Municipality | 70 000 |  |  | 0,00%
NW375 Moses Kotane Local Municipality | 65 000 |  |  | 0,00%
DC39 Dr Ruth Segomtsi Mompti District Municipality | 90 000 |  |  | 0,00%
NW403 City of Matlosana Local Municipality | 15 676 |  |  | 0,00%
NW404 Maquassi Hills Local Municipality | 30 000 |  |  | 0,00%
NW405 JB Marks Local Municipality / | 35 000 |  |  | 0,00%

## Slide 74: Water Services Infrastructure Grant: 5B per province and municipality (5)
Name of Region and Municipality | Grant Allocation | Transfer |  | Spent
 | 2022 Division of Revenue Bill (DoRB) allocation | Year to date actual transfers | Year to date DoRA cumulative payment schedule | Expenditure as % of main appropriation
 | R'000 | R'000 | R'000 | %
Western Cape Province | 145 460 | - | - | 0,00%
WC011 Matzikama Local Municipality | 9 196 |  |  | 0,00%
WC013 Bergrivier Local Municipality | 3 150 |  |  | 0,00%
WC022 Witzenberg Local Municipality | 15 701 |  |  | 0,00%
WC025 Breede Valley Local Municipality | 5 107 |  |  | 0,00%
WC032 Overstrand Local Municipality | 27 439 |  |  | 0,00%
WC033 Cape Agulhas Local Municipality | 17 000 |  |  | 0,00%
WC034 Swellendam Local Municipality | 6 437 |  |  | 0,00%
WC047 Bitou Local Municipality | 9 079 |  |  | 0,00%
WC051 Laingsburg Local Municipality | 17 360 |  |  | 0,00%
WC052 Prince Albert Local Municipality | 6 552 |  |  | 0,00%
WC053 Beaufort West Local Municipality | 28 439 |  |  | 0,00%
Total Water Services Infrastructure Grant (WSIG) | 3 701 019 | - | - | 0,00%

## Slide 75: 5. AN OVERVIEW OF GRANTS PERFORMANCE
Regional Bulk Infrastructure Grant: 6B Per Project / Water Services Authority/ Benefiting Municipality

## Slide 76: Eastern Cape Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Eastern Cape Province |  |  |  |  |  |  |  |  | 
RL01 | Ndlambe Bulk Water Supply | Ndlambe Local Municipality | 10 000 | 2 671 | 1 226 | 8 774 | 1 445 | 26,71% | 12,26%
RL16 | Xhora East Water Supply | Mbhashe Local Municipality | 15 000 | 2 246 |  | 15 000 | 2 246 | 14,97% | 0,00%
RS01 | Graaf-Reinet Emergency Water Supply Scheme (WSS) | Dr Beyers Naude Local Municipality | 7 000 | - |  | 7 000 | - | 0,00% | 0,00%
RS02 | Sundays River - Paterson Bulk Water Supply | Sundays River Valley Local Municipality | 4 500 | - |  | 4 500 | - | 0,00% | 0,00%
RS05 | Ikwezi Bulk Water Supply | Dr Beyers Naude Local Municipality | 25 000 | 5 693 | 3 395 | 21 605 | 2 298 | 22,77% | 13,58%
RS06 | Kirkwood Water Treatment Works | Dr Beyers Naude Local Municipality | 15 000 | 910 | 66 | 14 934 | 844 | 6,07% | 0,44%
RS07 | Misgund Bulk Water Supply | Koukamma Local Municipality | 5 000 | 1 000 | 260 | 4 740 | 740 | 20,00% | 5,20%
RS42 | James Kleynhans Bulk Water Supply (BWS) | Makana Local Municipality | 30 000 | 6 190 | 1 732 | 28 268 | 4 458 | 20,63% | 5,77%
RS49 | Mount Ayliff Bulk Peri Urban Water Supply | Umzimvubu Local Municipality | 15 000 | 9 788 | 13 145 | 1 855 | (3 357) | 65,25% | 87,63%
RS67 | Ngqamakhwe Bulk Water Supply (Butterworth Water Transfer Scheme) | Mnquma Local Municipality | 168 868 | 36 415 | 473 | 168 395 | 35 942 | 21,56% | 0,28%
RS117 | Nooitgedagt Coega |  | 60 313 |  | 21 226 | 39 087 | (21 226) | 0,00% | 35,19%
RS 157 | Ndlambe Bulk Water Supply | Ndlambe Local Municipality | - |  |  | - | - | 0,00% | 0,00%
Total Eastern Cape Province |  |  | 355 681 | 64 913 | 41 523 | 314 158 | 23 390 | 18,25% | 11,67%

## Slide 77: Free State Province Regional Bulk Infrastructure Grant: 6B per project (1)
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Free State Province |  |  |  |  |  |  |  |  | 
BEP | Arglington Bulk Sewer Services | Nketoana Local Municipality | 54 346 | - | 1 517 | 52 829 | (1 517) | 0,00% | 2,79%
BEP | Clocolan Bulk Sewer Services | Setsoto Local Municipality | 30 000 | 3 000 | 3 175 | 26 825 | (175) | 10,00% | 10,58%
BEP | Dealesville Bulk Sewer Services | Tokologo Local Municipality | 9 236 | 2 400 |  | 9 236 | 2 400 | 25,99% | 0,00%
BEP | Ficksburg Bulk Sewer Services | Setsoto Local Municipality | 60 009 | 1 100 | 3 430 | 56 579 | (2 330) | 1,83% | 5,72%
BEP | Petrus Sten Bulk Sewer Services | Nketoana Local Municipality | 29 766 | - | 1 787 | 27 979 | (1 787) | 0,00% | 6,00%
BEP | Reitz Bulk Sewer Services | Nketoana Local Municipality | 36 331 | 5 309 | 1 669 | 34 662 | 3 640 | 14,61% | 4,59%
BEP | Senekal Bulk Sewer Services | Setsoto Local Municipality | 35 000 | 9 826 | 134 | 34 866 | 9 692 | 28,07% | 0,38%
Sub Total (1) |  |  | 254 688 | 21 635 | 11 712 | 242 976 | 9 923 | 8,49% | 4,60%

## Slide 78: Free State Province Regional Bulk Infrastructure Grant: 6B per project (2)
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Free State Province |  |  |  |  |  |  |  |  | 
RL12 | Nketoana Regional Water Supply | Nketoana Local Municipality | 28 000 | - |  | 28 000 | - | 0,00% | 0,00%
RL24 | Tokologo Regional Water Supply 2 | Tokologo Local Municipality | 40 000 | 5 000 |  | 40 000 | 5 000 | 12,50% | 0,00%
RL25 | Dihlabeng Bulk Water Supply Phase 3 | Dihlabeng Local Municipality | 30 000 | 4 000 |  | 30 000 | 4 000 | 13,33% | 0,00%
RL34 | Mathjabeng Bulk Sewer (Welkom) | Matjhabeng Local Municipality | 150 000 | 1 000 |  | 150 000 | 1 000 | 0,67% | 0,00%
RS12 | Jagersfontein/Fauresmith Bulk Water Supply | Kopanong Local Municipality | 800 | 1 000 |  | 800 | 1 000 | 125,00% | 0,00%
RS148 | Brandford bulk sewer | Masilonyana Local Municipality | 9 000 | - | 2 131 | 6 869 | (2 131) | 0,00% | 23,68%
RS149 | Lindley Sewer | Nketoana Local Municipality | 9 000 | 4 600 |  | 9 000 | 4 600 | 51,11% | 0,00%
RS150 | Refurbishment of Fika-patso WTWs | Maluti-a-Phofung Local Municipality | 20 000 | - |  | 20 000 | - | 0,00% | 0,00%
RS151 | Mantsopa water and sanitation intervention | Mantsopa Local Municipality | 10 000 | - | 838 | 9 162 | (838) | 0,00% | 8,38%
RS152 | Mafube water and sanitation intervention | Mafube Local Municipality | 15 000 | 1 100 |  | 15 000 | 1 100 | 7,33% | 0,00%
RS18 | Tswelopele Bulk Water Supply | Tswelopele Local Municipality | 33 329 | 4 500 | 4 402 | 28 927 | 98 | 13,50% | 13,21%
RS19 | Maluti-a-Phofung BWS Phase 2 | Maluti-a-Phofung Local Municipality | 40 000 | - | 3 888 | 36 112 | (3 888) | 0,00% | 9,72%
 | Maluti-a-Phofung Intervention | Maluti-a-Phofung Local Municipality | 100 000 | - |  | 100 000 | - | 0,00% | 0,00%
RS26 | Frankfort Bulk Sewer (Mafube) | Mafube Local Municipality | 30 000 | 2 500 | 1 333 | 28 667 | 1 167 | 8,33% | 4,44%
RS51 | Upgrading of Deneysville WWTW | Metsimaholo Local Municipality | 50 000 | 4 000 |  | 50 000 | 4 000 | 8,00% | 0,00%
RL61 | Welbedacht Pipeline | Mangaung Metropolitan Municipality | 79 400 |  | 30 651 | 48 749 | (30 651) | 0,00% | 38,60%
RS52 | Masilonyana Bulk Water Supply | Masilonyana Local Municipality | 15 000 | - |  | 15 000 | - | 0,00% | 0,00%
 | Refurbishment of Kroonstad WWTW and Pumpstations | Moqhaka Local Municipality | 15 000 | - |  | 15 000 | - | 0,00% | 0,00%
 | Construction of Reversal Gravity Pipeline in Qwaqwa | Maluti-a-Phofung Local Municipality | 16 600 | - | 802 | 15 798 | (802) | 0,00% | 4,83%
Sub Total (2) |  |  | 691 129 | 27 700 | 44 045 | 647 084 | (16 345) | 4,01% | 6,37%
Total Free State Province |  |  | 945 817 | 49 335 | 55 757 | 890 060 | -6 422 | 5,22% | 5,90%

## Slide 79: Gauteng Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Gauteng Province |  |  |  |  |  |  |  |  | 
RL04 | Meyerton Waste Water Treatment Works | Midvaal Local Municipality | 50 000 | 12 501 |  | 50 000 | 12 501 | 25,00% | 0,00%
RL62 | Vaal River System Intervention | Emfuleni Local Municipality | 400 000 | 99 999 | 1 154 | 398 846 | 98 845 | 25,00% | 0,29%
RM02 | Sedibeng Regional Waste Water Treatment Works | Emfuleni, Midvaal and City of Johannesberg | 69 410 | 17 352 | 2 477 | 66 933 | 14 875 | 25,00% | 3,57%
RM05 | Sebokeng Waste Water Treatment Works | Emfuleni Local Municipality | 50 000 | 12 501 |  | 50 000 | 12 501 | 25,00% | 0,00%
RM06 | Westonaria Regional Bulk Sanitation (Zuurbekom) | Rand West City Local Municipality | 60 000 | 15 000 |  | 60 000 | 15 000 | 25,00% | 0,00%
RS55 | Rothdene pump station and rising main | Midvaal Local Municipality | 10 000 | 2 499 | 2 283 | 7 717 | 216 | 24,99% | 22,83%
RS56 | Mohlakeng pump station and sewer outfall | Rand West City Local Municipality | 30 000 | 7 500 |  | 30 000 | 7 500 | 25,00% | 0,00%
Total Gauteng Province |  |  | 669 410 | 167 352 | 5 914 | 663 496 | 161 438 | 25,00% | 0,88%

## Slide 80: Limpopo Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Limpopo Province |  |  |  |  |  |  |  |  | 
RM08 | Giyani Water Services | Greater Giyani Local Municipality | 313 960 | 57 006 | 19 598 | 294 362 | 37 408 | 18,16% | 6,24%
RL29 | Mametja Sekororo Bulk Water Supply | Maruleng Local Municipality | 38 896 | 19 092 | 2 788 | 36 108 | 16 304 | 49,08% | 7,17%
RL28 | Giyani Bulk Water Supply Drought Relief | Greater Giyani Local Municipality | 65 000 | 17 635 | 3 577 | 61 423 | 14 058 | 27,13% | 5,50%
RS135 | Bambanana Pipeline | Maruleng Local Municipality | 170 000 | 11 092 | 478 | 169 522 | 10 614 | 6,52% | 0,28%
RL13 | Sinthumule Kutama Bulk Water Supply | Makhado Local Municipality | 50 000 | 23 432 | 13 584 | 36 416 | 9 848 | 46,86% | 27,17%
RM04 | Mogalakwena Bulk Water Supply | Mogalakwena Local Municipality | 40 000 | 14 503 | 21 276 | 18 724 | (6 773) | 36,26% | 53,19%
RL14 | Moutse Bulk Water Supply | Ephraim Mogale/ Elias Motsoaledi local municipalities | 30 000 | 3 390 | - | 30 000 | 3 390 | 11,30% | 0,00%
RM12 | Nebo Bulk Water Supply | Tubatse Local Municipality/ Makhudumathaga LM | 40 000 | 16 003 |  | 40 000 | 16 003 | 40,01% | 0,00%
RM07 | Mooihoek/Tubatse Bulk Water Supply | Tubatse Local Municipality | 60 000 | 11 861 | 1 925 | 58 075 | 9 936 | 19,77% | 3,21%
Total Limpopo Province |  |  | 807 856 | 174 014 | 63 226 | 744 630 | 110 788 | 21,54% | 7,83%

## Slide 81: Mpumalanga Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Mpumalanga Province |  |  |  |  |  |  |  |  | 
RL35 | Thembisile Water Scheme (Loskop) | Thembisile Local Municipality | 140 000 | 3 500 | 219 | 139 781 | 3 281 | 2,50% | 0,16%
RL36 | Western Highveld (Rust de Winter) Bulk Water Scheme | Thembisile Hani and Dr JS Moroka Local Municipality | 5 000 | - |  | 5 000 | - | 0,00% | 0,00%
RL53 | Balf/Siyat/Greyl/Willem/Nthor Bulk Water Supply | Dipaleseng Local Municipality | 50 000 | 10 858 | 36 366 | 13 634 | (25 508) | 21,72% | 72,73%
RS153 | Lekwa Waster Services | Lekwa Local Municipality | 40 000 | 4 200 | - | 40 000 | 4 200 | 10,50% | 0,00%
RS159 | Amsterdam and Sheepmore Bulk Water Scheme | Mkhondo and Msukaligwa Local Municipality | 40 000 | 1 000 | 539 | 39 461 | 461 | 2,50% | 1,35%
RS160 | Embalenhle Bulk Sewer and WWTW's refurbishment & upgrading | Goven Mbeki Local Municipality | 10 000 | - |  | 10 000 | - | 0,00% | 0,00%
RS30 | Sibange Bulk Water Supply | Nkomazi Local Municipality | 30 000 | 14 718 | 6 994 | 23 006 | 7 724 | 49,06% | 23,31%
RS37 | Driekoppies Upgrading | Nkomazi Local Municipality | 49 696 | 9 800 | 2 195 | 47 501 | 7 605 | 19,72% | 4,42%
Total Mpumalanga Province |  |  | 364 696 | 44 076 | 46 313 | 318 383 | (2 237) | 12,09% | 12,70%

## Slide 82: Northern Cape Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Northern Cape Province |  |  |  |  |  |  |  |  | 
BEP | Griekwastad Campbell | Siyancuma Local Municipality | 1 814 | - |  | 1 814 | - | 0,00% | 0,00%
RS28 | Upington Wasterwater treatment works | Dawid Kruiper Local Municipallity | 36 367 | 19 726 | 3 072 | 33 295 | 16 654 | 54,24% | 8,45%
RS29 | Warrington Wasterwater treatment works |  | 18 276 |  | 790 | 17 486 | (790) | 0,00% | 4,32%
Total Northern Cape Province |  |  | 56 457 | 19 726 | 3 862 | 52 595 | 15 864 | 34,94% | 6,84%

## Slide 83: North West Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
North West Province |  |  |  |  |  |  |  |  | 
RL09 | Madibeng Bulk Water Supply (Brits) | Madibeng Local Municipality | 105 608 | 22 719 | 14 728 | 90 880 | 7 991 | 21,51% | 13,95%
RL15 | Moretele South Bulk Water Supply (Klipdrift) | Moretele Local Municipality | 30 000 | 5 948 |  | 30 000 | 5 948 | 19,83% | 0,00%
RL33 | Mafikeng South Bulk Water Supply | Mafikeng Local Municipality | 30 000 | 6 264 | 2 168 | 27 832 | 4 096 | 20,88% | 7,23%
RS32 | Ratlou Bulk Water Supply | Ratlou Local Municipality | 34 328 | 3 364 | 350 | 33 978 | 3 014 | 9,80% | 1,02%
RS35 | Potchefstroom Waste Water Treatment Works upgrade (Tlokwe) Phase 1 to 5 | JB Marks Local Municipality | 40 000 | 6 848 |  | 40 000 | 6 848 | 17,12% | 0,00%
Total North West Province |  |  | 239 936 | 45 143 | 17 246 | 222 690 | 27 897 | 18,81% | 7,19%

## Slide 84: Western Cape Province Regional Bulk Infrastructure Grant: 6B per project
Project Code | Project Name | Benefitting Municipality | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation
 |  |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | %
Western Cape Province |  |  |  |  |  |  |  |  | 
RS134 | Clanwilliam /Lambertsbaai Regional Water Supply and Desalination | Cederberg Local Municipality | 15 197 | 5 000 | - | 15 197 | 5 000 | 32,90% | 0,00%
Total Western Cape Province |  |  | 15 197 | 5 000 | - | 15 197 | 5 000 | 32,90% | 0,00%

## Slide 85: 5. AN OVERVIEW OF GRANTS PERFORMANCE
Water Services Infrastructure Grant: 6B Per Project / Water Services Authority/ Benefitting Municipality

## Slide 86: Eastern Cape and Free State provinces Water Services Infrastructure Grant: 6B per project and municipality
Project Name | Beneiftting Municipality/ Water Services Authority | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation | Variance - Drawings and actual expenditure
 |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | % | %
Eastern Cape Province |  | 27 338 | 14 650 | 3 193 | 24 145 | 11 457 | 53,59% | 78% | 0%
No Projects | Ndlambe Local Municipality | 19 525 | 14 650 | 3 193 | 16 332 | 11 457 | 75,03% | 16,35% | 58,68%
Covid-19 Projects | Covid-19 Projects | 7 813 | - | - | 7 813 | - | 0,00% | 0,00% | 0,00%
Free State Province |  | 55 256 | 3 732 | 5 123 | 50 084 | (1 391) | 6,75% | -37,28% | 0,00%
Water Services Infrastructure Grant (WSIG) |  | 15 120 | - | 5 123 | 9 948 | (5 123) | 0,00% | 0,00% | 0,00%
DR-Smithfield 2 Pump & Inst Sen | Mohokare Local Municipality | 730 | - | 722 | 8 | ( 722) | 0,00% | 98,90% | -98,90%
DR Cornelia boreholes | Mafube Local Municipality | 1 500 | - | 1 496 |  | (1 496) |  | 99,73% | 
DR Viljoenskroon boreholes | Moqhaka Local Municipality | 230 | - | 222 |  | ( 222) |  | 96,52% | 
DR-Ngwathe Refurb WTW | Ngwathe Local Municipality | 390 | - | 389 |  | ( 389) |  | 99,83% | 
DR-Qwaqwa Dev & Eqp Boreholes | Maluti-a-Phofung Local Municipality | 2 300 | - | 2 267 |  | (2 267) |  | 98,57% | 
DR-Qwaqwa Rep Valve, Pipeline & Leaks | Maluti-a-Phofung Local Municipality | 30 | - | 27 |  | ( 27) |  | 90,00% | 
DR-Qwaqwa : Comet to HaRankopane | Maluti-a-Phofung Local Municipality | 4 940 | - | - | 4 940 | - | 0,00% | 0,00% | 0,00%
DR-Windburg/ Brandford EQP Boreholes | Masilonyana Local Municipality | 5 000 | - | - | 5 000 | - | 0,00% | 0,00% | 0,00%
Bucket Eradication Programme (BEP) |  | 40 136 | 3 732 | - | 40 136 | 3 732 | 9,30% | 100,00% | 0,00%
Senekal WWTW | Setsoto Local Municipality | 40 136 | 3 732 | - | 40 136 | 3 732 | 9,30% | 0,00% | 9,30%

## Slide 87: Gauteng, Mpumalanga and Northern Cape provinces Water Services Infrastructure Grant: 6B per project and municipality
Project Name | Beneiftting Municipality/ Water Services Authority | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation | Variance - Drawings and actual expenditure
 |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | % | %
Gauteng Province |  | 41 384 | - | 2 041 | 39 343 | (2 041) | 0,00% | 0,00% | 0,00%
Covid-19 Projects | Emfuleni Local Municipallity | 41 384 | - | 2 041 | 39 343 | (2 041) | 0,00% | 4,93% | -4,93%
Limpopo Province |  | 247 691 | 50 892 | 6 012 | 241 679 | 44 880 | 20,55% | 2,43% | 0,00%
CVD-Mopani DM | Mopani District Municipality | 40 425 | 11 400 | 507 | 39 918 | 10 893 | 28,20% | 1,25% | 26,95%
Thabazimbi Development of BWSS | Thabazimbi Local Municipality | 49 499 | 7 000 | 1 322 | 48 177 | 5 678 | 14,14% | 2,67% | 11,47%
Lephalale dev of W&S Sup Serv | Lephalale Local Municipality | 61 200 | 17 000 | 3 904 | 57 296 | 13 096 | 27,78% | 6,38% | 21,40%
Modimolle WTWSS | Modimolle-Mookgopong Local Municipality | 49 499 | 2 500 | 279 | 49 220 | 2 221 | 5,05% | 0,56% | 4,49%
Sekhukhune WTSS | Sekhukhune District Municipality | 47 068 | 12 992 | - | 47 068 | 12 992 | 27,60% | 0,00% | 27,60%
Mpumalanga Province |  | 127 575 | 27 782 | 18 796 | 108 779 | 8 986 | 21,78% | 14,73% | 0,00%
Rooikoppen Sewer Upgrade | Lekwa Local Municipallity | 82 013 | 18 682 | 15 068 | 66 945 | 3 614 | 22,78% | 18,37% | 4,41%
Delmas WWTW Upgrade | Victor Khanye Local Municipality | 45 563 | 9 100 | 3 728 | 41 835 | 5 372 | 19,97% | 8,18% | 11,79%
Northern Cape Province |  | 85 045 | 4 500 | 16 254 | 47 959 | (11 754) | 5,29% | -261,20% | 0,00%
Water Services Infrastructure Grant (WSIG) |  | 37 994 | - | 16 254 | 908 | (16 254) | 0,00% | 42,78% | 0,00%
Covid- Sol Plaatje LM Sust Wat Supp | Sol Plaatjie Local Municipallity | 3 771 | - | - |  | - |  | 0,00% | 
Covid- Siyancuma LM Sust Wat Supp | Siyancuma Local Municipallity | 17 061 | - | - |  | - |  | 0,00% | 
No Projects | Dikgatlong Local Municipality | 17 162 | - | 16 254 | 908 | (16 254) | 0,00% | 94,71% | -94,71%
Bucket Eradication Programme (BEP) |  | 47 051 | 4 500 | - | 47 051 | 4 500 | 9,56% | 0,00% | 0,00%
Campbell | Siyancuma Local Municipallity | 35 464 | - | - | 35 464 | - | 0,00% | 0,00% | 0,00%
Motswedimosa | Sol Plaatjie Local Municipallity | 1 520 | 1 000 | - | 1 520 | 1 000 | 65,79% | 0,00% | 65,79%
Postdene/ Maranteng | Tsantsabane Local Municipality | 10 067 | 3 500 | - | 10 067 | 3 500 | 34,77% | 0,00% | 34,77%

## Slide 88: North West province Water Services Infrastructure Grant: 6B per project and municipality
Project Name | Beneiftting Municipality/ Water Services Authority | Total revised allocation | Year to date cumulative cashflow | Year to date cumulative actual spending | Available Budget/ Variance | Variance - Drawings and actual expenditure | Projected spending | Expenditure as % of revised allocation | Variance - Drawings and actual expenditure
 |  | R'000 | R’000 | R’000 | R’000 | R’000 | % | % | %
North West Province |  | 122 047 | 65 668 | 5 501 | 116 546 | 60 167 | 53,81% | 4,51% | 0,01%
Madibeng Refub & Augm of Wtr Inf | Madibeng Local Municipality | 43 194 | 30 129 | 5 501 | 37 693 | 24 628 | 69,75% | 12,74% | 57,02%
No Projects | Kgetlengrivier Local Municipality | 28 928 | 23 100 | - | 28 928 | 23 100 | 79,85% | 0,00% | 79,85%
Mafikeng & Ramtsh Mla RWS | Ngaka Modiri Molema District Municipality | 49 926 | 12 439 | - | 49 926 | 12 439 | 24,92% | 0,00% | 24,92%
Total Water Services Infrastucture Grant (WSIG): Indirect Grant |  | 706 336 | 167 224 | 56 920 | 628 535 | 110 304 | 23,67% | 8,06% | 0,00%

## Slide 89: END