## Slide 1: CRL Rights Commission
Presentation to the
Portfolio Committee on
Cooperative Governance and Traditional Affairs:
Annual Report 2021/2022
11 October 2022

## Slide 2: Presentation Outline
Part A: CRL Rights Commission 2021/2022 Performance on Predetermined Targets
  Audit Outcomes of the Previous Financial Years and the Year Under Review
  Strategy Plan 2020/2021: Impact Statement, Programmes and Outcomes
  Outcomes and Outcome Indicators
  Our Vision, Mission
  Our Values
  Progress towards the achievement of institutional Impacts and Outcomes
  Summary of Results on the 2021/22 Annual Targets per programme
  Summary of Overall Achievement: Graphical presentation
  Organisational Overall Achievement
  Performance on the 2021/22 Annual Targets per programme
    10.1. Programme 1: Administration
    10.2. Programme 2: Legal Services and Conflict Resolution (LSCR)
    10.3. Programme 3: Public Engagement and Education (PEE)
    10.4. Programme 4: Research and Policy Development (RPD)
    10.5. Programme 5: Communication and Marketing, IT and Linkages
  11. Summary of Targets not achieved and strategies to address the same
Part B
  12. Financial Performance

## Slide 3: 1. Audit Outcomes of the Previous Financial Years and the Year Under Review

## Slide 4: 2. Strategy Plan 2021/2022: Impact Statement, Programmes and Outcomes

## Slide 5: 3. Outcomes and Outcome Indicators

## Slide 6: 4. Our Vision and Mission

## Slide 7: 5. Our Values
Values | Definitions
Transparency | Requires being committed in being open, honest and straightforward in my conduct at all times when I embark on organisational operations.
Professionalism | Being committed to upholding a high standard of self-conduct, self-presentation and adherence to workplace policies and procedures.
Responsiveness | I must be committed to understanding the organisational, contextual and my job demands, so I can ensure the provision of appropriate service on time, to uphold our organisational mandate.
Accountability | Being committed to take full responsibility for my decisions, conduct and actions in the workplace and ensuring that I support and assist my colleagues to uphold the same commitments.
Integrity | Being committed to firm adherence to the code of conduct and ethics, as prescribed by the organisational policies and procedures.
Impartiality | Being committed to unbiased, fair play and conduct in all my dealings with colleagues, partners and other stakeholders in the workplace.
Respect | Being committed to actions whereby I treat colleagues, partners and other stakeholders with appreciation and dignity at all times.

## Slide 8: 6. Progress towards the achievement of institutional Impacts and Outcomes
Impact Statement | Enabled environment for cultural, religious and linguistic communities to co-exist and participate in the development, peace, friendship, humanity, tolerance, national unity on the basis of equality, non discrimination and free association |  |  | 
MTSF Priorities | Social cohesion and safe communities, Better Africa and the world and A capable, ethical and developmental state |  |  | 
Outcomes | Outcome Indicator | Baseline | Five Year Targets | Progress
1 | Maintenance of unqualified audit opinion and improved oversight | Clean audit | Unqualified audit opinion for each year until 2023/24 | Clean audit
 | Reduction of wasteful, fruitless and irregular expenditure to zero | No irregular expenditure | Zero fruitless, Irregular and wasteful expenditure | Zero fruitless, wasteful and irregular expenditure
2 | Percentage of complaints resolved within the approved turnaround timeframes | 33% of complaints handled annually | 80% of complaints handled annually | 59% handled annually
 | Percentage and number of legislative reviews conducted | 0% of reviewed bills before Parliament 15 municipal by-laws reviewed | 100% of reviewed Bills before Parliament Number of Municipal By-Laws reviewed | 67% of Bills before Parliament 30 Metropolitan By-Laws reviewed
3 | Number of engagements and educational programmes conducted and community councils structured and recognised on CRL rights for the promotion of objectives of the Commission | 44 engagement and educational programmes conducted with cultural, religious and linguistic communities | 250 engagements and educational programmes conducted with cultural religious and linguistic communities | 92 engagements and educational campaigns conducted with cultural, religious and linguistic communities
4 | Number of research reports with recommendations to organs of state that seeks to influence legislation and policy position | 5 research reports produced per annum | 20 research reports with recommendations produced. | 9 research reports with recommendations were produced
5 | Number of reports on Communications, Marketing and Knowledge Management systems produced and implementation of approved ICT Governance framework | 5 reports on communications, marketing and knowledge Management systems | 20 reports on communications, marketing and knowledge management systems | 9 reports on communication and marketing and knowledge Management systems

## Slide 9: 7. Summary of Results on the 2021/22 Annual Targets per programme
Programmes | Total No of targets | No. of targets fully achieved | No. of targets not met | Achievement in percentages
Programme 1: Administration | 8 | 6 | 2 | 75%
Programme 2: Legal Services and Conflict Resolution (LS&CR) | 5 | 3 | 2 | 60%
Programme 3: Public Engagement and Education (PEE) | 3 | 3 | 0 | 100%
Programme 4: Research and Policy Development (RPD) | 4 | 4 | 0 | 100%
Programme 5: Communication, Marketing and IT and Linkages (CMIL) | 3 | 3 | 0 | 100%
TOTALS | 23 | 19 | 4 | 82%

## Slide 10: 8. Summary of Overall Achievement: Graphical Presentation
Chart: Summary of overall achievement
| Programme 1: Administration | Programme 2: LSCR | Programme 3: PEE | Programme 4: RPD | Programme 5: CMIL
Total number of Targets | 8 | 5 | 3 | 4 | 3
No of targets fully achieved | 6 | 3 | 3 | 4 | 3
No targtes not met | 2 | 2 | 0 | 0 | 0
Achievement in Percentages | 75 | 60 | 100 | 100 | 100

## Slide 11: 9. Organisational Overall Achievement
Chart: Achievement in Percentage: 82%
| Administration | LSCR | PEE | RPD | CMIL
Achievement in Percentage: 82% | 0.75 | 0.6 | 1 | 1 | 1

## Slide 12
Performance on the 2021/22 Annual Targets per Programme

## Slide 13: 10.1. Programme 1: Administration
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/2020 | Audited Actual Performance 2020/2021 | Planned Annual Targets 2021/22 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Good corporate governance, sound financial management and administrative support in line with legislation | Reports and recommendations for increased oversight, reporting and evaluation and coordination | Number of recommendations from plenary and oversight committee meetings held per annum | 4 Plenary and 4 Oversight Committee meetings per annum | 4 Plenary and 4 Oversight Committee meetings per annum | 8 recommendations made from Plenary and oversight committee meetings held per annum | 8 recommendations made from Plenary and oversight committee meetings held per annum | Achieved | No deviation
 |  | Number of quarterly performance reports reviewed per annum | 4 quarterly reports were reviewed by the CEO within 30 days after the start of the new quarter | 4 quarterly reports were reviewed by the CEO within 30 days after the start of the new quarter | 4 reviewed quarterly performance reports per annum | 4 reviewed quarterly performance reports per annum | Achieved | No deviation
 |  | Number of quarterly financial statements reviewed per annum | Unqualified audit reports on Financial Statements. | Unqualified audit reports on Financial Statements. | 4 quarterly financial statement reviewed per annum | 4 quarterly financial statements reviewed per annum | Achieved | No deviation
 |  | Number of quarterly internal audit reports per annum | 4 quarterly internal audit reports reviewed by the Audit Committee per annum | 4 quarterly internal audit reports reviewed by the Audit Committee per annum | 4 quarterly internal audit reports per annum | 4 quarterly internal audit reports per annum | Achieved | No deviation

## Slide 14: Programme 1: Administration …continues
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/2020 | Audited Actual Performance 2020/2021 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Good corporate governance, sound financial management and administrative support in line with legislation | Reports and recommendations for increased oversight, reporting and evaluation and coordination | Percentage of approved performance agreements aligned to the strategy and the structure annually | 28 performance agreements submitted on time. | 28 performance agreements submitted on time. | 100% approved annual performance agreements aligned to the strategy and the structure annually | 100% approved annual performance agreements aligned to the strategy and the structure annually | Achieved | No deviation
 |  | Percentage of workplace skills development plan implemented per annum | 37.1% of workplace skills development plan has been implemented | 100% of Workplace skills development plan implemented per annum | 100% of Workplace skills development plan implemented per annum | 155% of Workplace skills development plan implemented per annum | Over-achieved | This is attributed to accelerated training drive due to the backlog from the previous years

## Slide 15: Programme 1: Administration …continues
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/2020 | Audited Actual Performance 2020/2021 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Good corporate governance, sound financial management and administrative support in line with legislation | Reports and recommendations for increased oversight, reporting and evaluation and coordination | Percentage of queries on internal and external audit findings resolved annually | External and Internal audit findings register have been updated and all audit findings resolved | 100% of all queries on internal and external audit findings resolved annually | 100% of all queries on internal and external audit findings resolved annually | 83.75 % Of all queries on internal and external audit findings resolved annually | Not achieved | Remaining queries are under investigation and report will be updated as soon as the matters are concluded
 |  | Number of reports on implemented risk management strategy per annum | Risk Management Workshop conducted, and risk register updated annually | 4 reports on implemented risk management strategies per annum | reports on implemented risk management strategies per annum | 1 report on implemented risk management strategies per annum | Not achieved | Service Provider was appointed in the 3rd quarter. Risk assessment was done in the 3rd quarter. Risk report compiled in the 4th quarter

## Slide 16: Programme 1: Overall Achievements
Chart: Overall achievement in Percentage: 75%
| Total No. of targets | No.of targets fully achieved | No. of targets not met
Administration overall achievement in Percentage | 8 | 6 | 2

## Slide 17: 10.2. Programme 2: Legal Services and Conflict Resolution (LSCR)
Outcomes | Outputs | Output Indicators | Audited Actual Performance2019/20 | Audited Actual Performance2020/21 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Strengthened conflict resolution and legislative reviews to promote and protect cultural, religious and linguistic rights of communities | Register of complaints/requests handled | Percentage of complaints/requests handled per annum | 32% of Cases were processed in line with Complaints Handling Manual | 33% of complaints (new and carried over) handled annually | 80% of new complaints handled annually | 85% of new complaints handled | Over-achieved | New management and strategy in dealing with complaints
 |  |  |  |  | 80% of carried over complaints from the previous year handled annually | 80% of carried over complaints from the previous year handled annually | Achieved | New management and strategy in dealing with complaints
 | Register of legal advice and opinions to the Commission; and to the public on cultural, religious and linguistic rights | Percentage of Legal opinions and/or drafts in responses to all requests per annum | 0% response to all requests: 36 Legal opinions and/or drafts have been produced. | 100% response to all legal advice and opinion requests annually | 100% response to all legal advice and opinion requests annually | 100% response to all legal advice and opinion requests annually | Achieved | No deviation

## Slide 18: Programme 2: Legal Services and Conflict Resolution (LSCR) …continues
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/20 | Audited Actual Performance 2020/21 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Strengthened conflict resolution and legislative reviews to promote and protect cultural, religious and linguistic rights of communities | Report on reviewed Bills before Parliament and report on reviewed legislation that impacts cultural, religious and linguistic rights of communities as guided by received complaints | Number and percentage of reviewed Bills before Parliament and on reviewed legislation that impacts cultural, religious and linguistic rights of communities, as guided by received complaints per annum | One report on Bills before Parliament Recognition of Customary marriages Comments on issue paper on single marriage Statute Hearings on use of languages | Reviewed 0% of Bills before Parliament that impacts on the mandate of the CRL Rights Commission annually | Review 100% of Bills before Parliament that impacts on the mandate of the CRL Rights Commission annually | 67% of reviewed Bills before Parliament and and/or legislations that impact on cultural, religious and linguistic rights of communities as guided by received complaints | Not achieved | Due to insufficient human capacity at the time, the unit missed the Basic Education Amendment Bill as it was focusing more on the legislative review of the Witchcraft Suppression Act in the last quarter of the financial year. The Bill will however still be reviewed in the next financial year 2022/2023, as it is still before parliament.

## Slide 19: Programme 2: Legal Services and Conflict Resolution (LSCR) …continues
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/20 | Audited Actual Performance 2020/21 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Strengthened conflict resolution and legislative reviews to promote and protect cultural, religious and linguistic rights of communities | Report on reviewed Bills before Parliament and report on reviewed legislation that impacts cultural, religious and linguistic rights of communities as guided by received complaints | Number and percentage of reviewed Bills before Parliament and on reviewed legislation that impacts cultural, religious and linguistic rights of communities, as guided by received complaints per annum | New target | 15 Reviewed municipal Metropolitan By- Laws:7 on fireworks and 8 on cemeteries that impact cultural, religious and linguistic rights of communities per annum | 16 Reviewed municipal metropolitan By-Laws that impact cultural, religious and linguistic rights of communities per annum: 8 on animal slaughtering for cultural/religious purposes and 8 on initiation schools | 15 Review reports on metropolitan municipalities’ by- Laws that impact on cultural, religious and linguistic rights of communities: 8 on slaughtering of animals for cultural and religious purpose and 7 on customary initiation school | Not achieved | There was no customary initiation By-law in Buffalo metropolitan municipality to review.

## Slide 20: Programme 2: Overall Achievements
Chart: Legal Services & Conflict Resolution overall achievement in percentages:60%
| Total No. of targets | Total targets achieved | Total targets not met
Legal Services & Conflict Resolution overall achievement in percentages | 5 | 3 | 2

## Slide 21: Brief Descriptive Highlights - Legal Services and Conflict Resolution Programme
1. Complaints Handling
1.1. 2021/2022 financial year
  68 complaints received.
  34 were on religion, 33 on culture and only 1 on language.
  58 cases were finalized i.e. for the year under review.
1.2. Carried Over Cases from 2020/2021 Financial year
  20 cases were carried over and 18 of these were finalized.
  2 are still in progress due to their complexities, and are carried over to 2022/23 financial year.
.2. Legislative Reviews
The Bills are Cannabis for Private Purpose Bill and The Witchcraft Suppression Act.

## Slide 22: Brief Descriptive Highlights - Legal Services and Conflict Resolution Programme
Review of By-laws
15 By-laws have been reviewed:
A. Slaughtering of animals for cultural and religious purposes
City of Joburg, Ekurhuleni, and City of Cape Town Metropolitan Municipalities – Time period for application for slaughtering of animals must be revised to accommodate slaughtering for funerals, which is a traditional or cultural or practice to cultural and religious communities.
Nelson Mandela Bay Metropolitan Municipality - by-law relating to slaughtering of animals should outline explicitly the procedures to be followed.
City of Tshwane and eThekwini Metropolitan Municipalities - should develop by-laws relating to cultural and religious slaughtering or revise their current by-laws relating to keeping of animals to include cultural and religious slaughtering.
B. Customary initiation schools by laws.
Buffalo city metropolitan municipality - no by-law relating to a customary initiation school.

## Slide 23: 10.3. Programme 3: Public Engagement and Education (PEE)
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/2020 | Audited Actual Performance 2020/2021 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/22 | Deviation from planned target to actual achievement | Reasons for deviations
Effective, structured and informed communities on cultural, religious and linguistic rights matters | Reports on engagements with communities on cultural, religious and linguistic rights of communities conducted | Number of engagements with communities on cultural, religious and linguistic communities conducted per annum | 4 engagements with PEE stakeholders on C-R-L matters have been conducted | 24 engagements with communities on cultural, religious and linguistic rights of communities per annum | 25 engagements with communities on cultural, religious and linguistics rights of communities per annum | 27 engagements with communities on cultural, religious and linguistics rights of communities were conducted per annum | Over-achieved | Increased human resources capacity and the reprioritisation of funds
 | Reports on public educational campaigns on cultural, religious and linguistic rights of communities conducted | Number of public educational campaigns on cultural, religious and linguistic rights of communities conducted per annum | 10 educational programmes have been conducted on CRL matters | 20 public educational campaigns on cultural, religious and linguistic rights of communities conducted per annum | 20 public educational awareness campaigns on cultural, religious and linguistic rights of communities conducted per annum | 21 public educational awareness campaigns on cultural, religious and linguistic rights of communities conducted per annum | Over-achieved | Increased human resources capacity and the reprioritisation of funds
 | Established and maintained database of cultural, religious and linguistic community organisations and institutions | Updated, established and maintained database of community organisations and institutions per annum | Community Council Policy has been reviewed by March 2020 | 1 updated maintained database of community organisations and institutions per annum | 1 Updated and maintained database of community organisation and institutions per annum | 1 Updated and maintained database of community organisation and institutions per annum | Achieved | No deviation

## Slide 24: Programme 3: Overall Achievements
Chart: Overall achievement in percentage: 100%
| Total No of targets | No of targets achieved | No of targets not met
Overall achievement in percentage | 3 | 3 | 0

## Slide 25: Brief Descriptive Highlights – Public Engagement and Education unit
25 engagements with Communities. Theme ‘helping communities develop their diminished heritage’
engaged with the Bakone Royal Council in Mpumalanga within the area of jurisdiction of Kgoshi Mashego in Bushbuckridge and in Limpopo (Senwabarwana and Makwarela i.e. (Vhembe District Municipality)
engaged with Khoisan Communities in Limpopo (Polokwane), Mpumalanga (Mbombela and eMalahleni), Free State (Mangaung), Western Cape (Elsiereviere, Lamberts Bay, Saldanha Bay and Drakenstein) and in several other areas in Gauteng.
The Unit also conducted engagements with the Muslim communities:
stakeholder engagement with the South African Hajj and Umrah Council (SAHUC) and the Muslim Religious leaders on the religious rights of Muslim communities.
20 awareness campaigns with communities. Theme ‘promoting cultural diversity in our local communities’ and ‘promotion of religious diversity.’ The campaigns were conducted in the following provinces:
Northwest (Haartebeesfontein, Jourbetina, Alabama, Khuma, Bloemhof) and in the Eastern Cape: Libode, Mamulweni, Nyandeni and Nqeleni.

## Slide 26: 10.4. Programme 4: Research and Policy Development (RPD) Unit
Outcomes | Outputs | Output Indicators | Audited Actual Performance2019/2020 | Audited Actual Performance 2020/2021 | Planned Annual Targets 2021/22 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Research recommendations to inform evidence-based policies and sustained resuscitation of diminishing and diminished community heritages | Research reports on cultural, religious and linguistic rights produced | Number of research reports on cultural, religious and linguistic rights produced per annum | 1 Research report on a topic approved by the research committee has been produced | 5 research reports on cultural, religious and linguistic rights produced per annum | 4 research reports on cultural, religious and linguistic rights produced per annum | 4 research reports on cultural, religious and linguistic rights produced per annum | Achieved | No deviation

## Slide 27: Programme 4: Overall Achievements
Chart: Overall achievement in percentage: 100%
| Total numbr of targets | No of targets achieved | No of targets not met
Overall achievement if percentage | 4 | 4 | 0

## Slide 28: Brief Descriptive Highlights - Research and Policy Development (RPD) Unit
4 research Reports:
1. Is African Traditional Religion equivalent to Traditional Healing?
Objectives:
To understand African Traditional Religion as a religion.
To explore how African Traditional Religion can be elevated to the same equal status as all other religions.
To understand why is African Traditional Religion always represented and talked about during debates and ceremonies by other people, like Traditional healers, and not by its own followers?
Recommendations
African Traditional Healing and African Traditional Religion are two separate institutions and should never be mixed up.
African Religion must be promoted and where possible be more documented.
The Department of Health should promote the profession of traditional healing to the same level as it does with western doctors.

## Slide 29: Brief Descriptive Highlights - Research and Policy Development (RPD) Unit …continues
2. Resuscitation of African Cultural Values
Objectives:
To explore how communities could resuscitate their cultural values?
To understand how African cultural values could complement and promote social cohesion, moral regeneration and nation building?
To come up with strategies of how communities could resuscitate the core value of Ubuntu?
Recommendations
Core values should be cultivated in the family unit and community targeting young people at early age.
The Department of Education and Higher Learning should promote African values and ensure that they form part of schools’ and universities’ curriculums.
Traditional Leadership should be given the space and be supported in a conscious effort to assert African historical traditions, values, and consciousness.
The competition that exists between the rights bestowed on us by the constitution and customary law on rights and values needs to be relooked at and a scientific study should be conducted to promote values from both these two systems of laws equally.

## Slide 30: Brief Descriptive Highlights - Research and Policy Development (RPD) Unit …continues
3. The Constitutional Rights of Unmarried Biological Fathers within the CRL Community Rights in a diverse country
Objectives:
To understand the cultural communities’ rights and traditions against the backdrop of the constitutional court ruling, awarding the biological unmarried fathers’ rights to register his child with his surname.
To hear from different cultural communities if according to their culture, biological unmarried fathers have rights?
To understand the cultural process practiced/followed in a case where a child is born from two unmarried people?
Recommendations
In matters that affect the constitution and cultures of people, the Constitutional Court should consult with cultural experts and traditional leaders to hear their counsel before pronouncing on matters that affect people’s cultures and way of life.
Efforts must be made by the Courts to align their judgements with the cultural, religious, and traditional beliefs of all South African citizens.

## Slide 31: Brief Descriptive Highlights - Research and Policy Development (RPD) Unit …continues
4. Use of Official Languages by Organs of State
Objectives:
To look at how far the organs of state have gone with the use of all official languages.
Positive measures, the organs of state are employing to elevate the status and advance the use of these languages.
What organs of state have put in place to regulate and monitor the use of the official languages in their respective units.
To what extent do the official languages enjoy parity of esteem and equitable freedom?
What efforts are organs of state making to elevate and promote official languages to become languages of record, teaching, research, science, technology, and commerce.

## Slide 32: Brief Descriptive Highlights - Research and Policy Development (RPD) Unit …continues
Recommendations
In order to enjoy parity of esteem, languages must be used as languages of record, teaching, research, science, technology and commerce.
That public service centres where the public can send their complaints about the unequal use of official languages by organs of state should be established soon.
Organs of state should share publications and communicate with the members of the public more effectively about their linguistic rights in their own languages and in languages spoken in the areas or regions where they live.
The spoken and used regional languages should be streamlined and should be granted official status in the regions where they are spoken.
NB. This report will be launched and full details will be on the independent report.

## Slide 33: 10.5. Programme 5: Communication, Marketing, IT and Linkages (CMIL) Unit
Outcomes | Outputs | Output Indicators | Audited Actual Performance 2019/20 | Audited Actual Performance 2020/21 | Planned Annual Targets 2021/2022 | Actual Achievement 2021/2022 | Deviation from planned target to actual achievement | Reasons for deviations
Intensified communication, marketing and knowledge management systems | Reports on the implemented internal and external communication and marketing strategy | Number of reports on Implemented internal and external communication strategy per annum | External and Internal Communication Strategy has been approved | 4 reports on Implemented internal and external communication strategy per annum | 4 reports on Implemented internal and external communication strategy per annum | 4 reports on Implemented internal and external communication strategy per annum | Achieved | No deviation
 | Stable and secure ICT environment that meets all functional needs of the Commission and its strategy | Number of reports on maintained and upgraded infrastructure And implemented ICT Governance Framework per annum | IT Governance Framework has been reviewed | 4 reports on maintained and upgraded infrastructure and implemented ICT Governance Framework per annum | 4 reports on maintained and upgraded infrastructure and implemented ICT Governance Framework per annum | 4 reports on maintained and upgraded infrastructure and implemented ICT Governance Framework per annum | Achieved | No deviation
 | Report on monitored activities on social media platforms | Number of reports of activities on social media platform per annum | Report on active social media platforms and posts produced per annum | 4 reports on activities on social media platforms per annum | 4 reports On activities on social media platform per annum | 4 reports On activities on social media platform per annum | Achieved | No deviation

## Slide 34: Programme 5: Overall Achievements
Chart: Overall achievement in Percentage: 100%
| Total No. of targets | No of targets achieved | No of targets not met
Overall achievement in Percentage: 100% | 3 | 3 | 0

## Slide 35: 11. Summary of Targets not achieved and strategies to address the same
PPI | Performance Indicator | Planned Annual Target | Annual Achievement | Reason for variance and corrective measure
7 | Percentage of queries on internal and external audit findings resolved annually | 100% of all queries on internal and external audit findings resolved annually | 83.75% of all queries on internal and external audit findings resolved annually | Remaining queries are under investigation and report will be updated as soon as the matters are cconcluded.
8 | Number of reports on implemented risk management strategy per annum | 4 reports on implemented risk management strategies per annum | 1 report on implemented risk management strategies per annum | Service Provider was appointed in the 3rd quarter. Risk assessment was done in the 3rd quarter. Risk report was compiled in the 4th quarter. The reports will be finalised in the current financial year
11 | Report on reviewed Bills before Parliament and report on reviewed legislation that impacts cultural, religious and linguistic rights of communities, as guided by received complaints | Review 100% of bills before Parliament that impact the mandate of the CRL Rights Commission annually | 67% of reviewed bills before Parliament and/ or legislations that impact on cultural, religious and linguistic rights of communities as guided by received complaints | Due to insufficient human capacity at the time, the unit missed the Basic Education Amendment Bill as it was focusing more on the legislative review of the Witchcraft Suppression Act in the last quarter of the financial year. The Bill will however still be reviewed in the new financial year.

## Slide 36: PART B
FINANCIAL PERFORMANCE

## Slide 37: Allocation and Economic Classification
Economic Classification | Final Allocation R’000 | Actual Expenditure R’000 | Variance R’000 | Expenditure % of Final Allocation
Current Payment Compensation of employees Goods and Services | 27 948 18 336 | 26 002 12 844 | 1 946 5 492 | 6.96 29.95
Payment of Capital assets | _ | _ | _ | _
Total | 46 284 | 38 846 | 7 438 | 16.07

## Slide 38: Reasons for Underspending
In respect of employee cost the underspending is a result of vacancies that were filled during the last quarter of the financial year.
In respect of goods and services the savings resulted from:
  The internal audit service that was appointed in the fourth quarter.
  A provision in respect of retained earnings that had to be reversed.
  A reduction in the scope of the external audit due to the Covid-19 Pandemic.

## Slide 39: Report on the 2021/22 Irregular Expenditure
No additional irregular expenditure was reported during the year under review.
The past irregular expenditure was investigated and a request for condonement was made to National Treasury. The outcome of the request is still awaited.

## Slide 40: Report on 2021/2022 Fruitless and Wasteful Expenditure
No new cases of fruitless and wasteful expenditure were reported during the year under review.
The disciplinary processes in respect of wasteful expenditure are underway.
The recoverability of the wasteful expenditure is currently being investigated.

## Slide 41: Conclusion

## Slide 42: Conclusion

## Slide 43: Thank you