## Slide 1: SOUTH AFRICAN HUMAN RIGHTS COMMISSION
Annual Report 2021-22
Portfolio Committee on Justice and Correctional Services
19 October 2022

## Slide 2: OVERVIEW OF PRESENTATION
Chairperson’s Introductory Remarks
An overview of Audit Outcomes and Corrective Action as at 31 March 2022
  Performance
  Finance
3. Annual Performance Report 2021 - 2022
  Programme 1: Administration
  Programme 2: Promotion of Human Rights
  Programme 3: Protection of Human Rights
  Programme 4: Monitoring of Human Rights

## Slide 3: Audit Outcomes Performance Information Key Findings of the AG Audit
Source information, evidence and method of calculation for measuring the planned indicator was not clearly defined.
Systems and processes were not adequate to enable consistent measurement and reliable reporting of performance against the predetermined indicator definitions.
Supporting evidence for reported events did not agree to the reported achievement.
The AGSA was unable to obtain sufficient appropriate audit evidence to support the reasons for some of the variances between the planned target and the achievement reported.

## Slide 4: Audit Corrective Action Performance information
Executive Authority engagement with the Auditor-General for strategic advice.
Digitisation and automation of systems: document management and promote efficiency and accessibility of information.
Revision of performance indicators to meet SMART criteria: adherence with DPME recommendations and subjected planning information to experts for review.
Procuring services of experts to enhance internal auditing of performance information.
Convening internal quarterly performance information workshops with all staff.
Establishment of cross function Task Team to assess, advise and act on the resolution of audit findings.

## Slide 5: Overview of 2021-22 Financial Statements Financial Performance Review
Annual Financial Statements
Per the Audited Annual Financial Statements: Statement of Financial Position: Total net assets to be R 61.8m for the year (2020/21 R 61.7m) Statement of Financial Performance: Surplus for the year to be R 0.1m ( 2020/21 R 16.7m).
The financial viability assessment by AGSA resulted in the overall assessment being ‘Good’ (2020/21 ‘Good’).
The main drivers being:
Employee related costs R 140.1m (2020.21 R 129m)
General Expenses R 44.1m (2020/21 R 31.0m)

## Slide 6: Overview of 2021-22 Financial Statements Financial Performance Review
Item |  | 2021-22 Actual | % of Total Expenditure | 
Personnel costs |  | R140.1m | 71% | 
Corporate support committed costs: |  | R36.2m | 19% | 
Office rentals and municipal charges (remaining budget covers motor vehicles, telephone, video-conferencing, inventories and other admin costs) Auditor-General Fees and other audit and finance fees Other costs included: ICT Infrastructure and contract related costs Human Resources: capacity development, employee wellness, recruitment, performance management |  | R11.6m R2.6m R5.6m R1.8m | - - - - | 
Core operational costs | R19.8m |  | 10% | 

## Slide 7: Audit Outcomes Financial Report Key Findings of the AG Audit
The Commission received an unqualified audit for the year, however; Material misstatements were identified on payables and commitments, Material findings on performance management, and Non-compliance with legislation particularly in supply chain management was identified.
Inadequate monitoring, review and consequence management resulted in the non-compliances.
Under capacity in Internal Audit resulted in delays of completion of internal audits.
Some prior year findings on IT governance were not addressed.

## Slide 8: Audit Corrective Action Financial information
The contract post of Head of Corporate Services was appointed and joined August 2022.
A new search has been initiated to replace the permanent position of the Chief Financial Officer.
A turnaround plan for SCM has been incorporated in the 2022/23 APP.
Plans are in place to procure an updated ERP system with more capabilities.
Monthly Tracker documents have been devised based on audit findings, are updated monthly with updates reported through to the ACEO monthly.

## Slide 9
An overview of performance
Annual Performance Report 2021 – 2022

## Slide 10: Overview of Performance 2020-21 Achievement of targets over the last 5 years
Chart: % achievement of targets
| 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22
 | 0.75 | 0.73 | 0.88 | 0.64 | 0.61

## Slide 11: Overview of Performance 2020-21 Achievement of targets by Programme
Programme | Total Targets | Annual Targets Fully Achieved
Programme 1: Administration | 13 | 5
Programme 2: Promotion of Human Rights | 15 | 10
Programme 3: Protection of Human Rights | 8 | 5
Programme 4: Monitoring of Human Rights | 8 | 7
Total | 44 | 27

## Slide 12
Programme 1 achievements: Administration
A stable institution with capacity to effectively deliver on planned priorities

## Slide 13: Programme 1 achievements: Administration
Administration programme key achievements
Human capital management: ongoing recruitment and capacity development
Governance, audit, risk and compliance: stable operations and oversight, unqualified audit
Compliance with key legislative requirements
Innovative use of ICT: ensured ongoing corporate communications and remote work

## Slide 14: Programme 1: Administration Areas of under - performance (1)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Percentage expenditure against total budget | 98% - 102% expenditure | 94% | Procurement delays. Projects with open purchase orders rolled over to the new financial year.
2 | Percentage implementation of Risk Treatment Plan | 80% - 100% Implementation | 67.5% | Delayed procurement on some of the risk treatment plan related activities.
3 | Percentage implementation of Recommendations of 2020-21 Remuneration Structures and Conditions of Service Report | Develop SAHRC Conditions of Service and Remuneration | 15% | Capacity constraints and consequent priority on other key processes.
4 | Percentage implementation of Organisational Culture Renewal Plan | 80% - 100% Implementation | 60% | Capacity constraints and delayed procurement processes
5 | Percentage implementation of Internal Audit Plan | 80% - 100% Implementation | 63% | Delays in the provision of information and processes at the various business unit levels.

## Slide 15: Programme 1: Administration Areas of under - performance (2)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
6 | Percentage resolution of audit findings | 80% - 100% resolution | 45% | Capacity constraints, resulting in focus biased towards what is considered core functions of business units than on the findings
7 | Completion of Impact Monitoring and Evaluation Report | Complete Report | Report not completed. | Capacity constraints and a focus on other key processes and special projects. Project plan developed for study toe e conducted in the new financial year.
 | Completion of Report on the sufficiency of the SAHRC Budget by Sept 2021 | Complete Report | Report not completed. | Non-responsiveness to calls for proposals

## Slide 16
Programme 2: Promotion of Human Rights
Influenced pro-human rights policies, legislation, service delivery and awareness

## Slide 17: Programme 2 Promotion of human rights (1)
Promotion of human rights
Hosted Imbizo to understand the impact of the unrest of the July 2021 civil unrest
3. Hosted National Schools Moot Court Competition – positive impact on learners through mooting techniques: promotes knowledge of Constitutional values, human rights and the rule of law; influences future career choices and create a cohort of young human rights ambassadors in schools, families and communities
Promoting functionality of equality courts through public awareness and strategic engagements

## Slide 18: Programme 2 Promotion of human rights (2)
Promotion of human rights
4. Collaborative anti-corruption efforts with the FISD and other stakeholders to engage and explore various intervention mechanisms, including a focus on strengthening the legal framework for the protection of whistle-blowers
Promoting non-discrimination and gender equality through implementation of the Amman Declaration in collaboration with the Commission on Gender Equality: dealing with all forms of discrimination against women and girls, gender-based violence, violations of economic, social and cultural rights, reproductive rights
Empowering human rights champions in communities

## Slide 19: Programme 2 Promotion of human rights (3)
Promotion of human rights
7. Facilitated a session to promote children’s rights and pro-human rights budgeting through reflection on the Medium Term Budget Policy Statement (MTBPS) - stakeholders including National Treasury, UNICEF, SPII and Budget Justice Coalition
8. The Commission has also contributed towards international discussions and efforts on the right to equality focusing on Sexual Orientation and Gender Identity Expression (SOGIE) along with institutions in the Network of African National Human Rights Institutions (NANHRI).
Commission selected to represent Africa at the Global Alliance of National Human Rights Institutions (GANHRI) Subcommittee on Accreditation (SCA) - a process where NHRIs are periodically evaluated with reference to the Paris Principles, which aim to ensure independence, pluralism, effectiveness, and accountability

## Slide 20: Programme 2 achievements: Promotion of human rights (4)
12302 Media Items
Reach of 17 118 842 188
AVE = R 423 000 235,80
Broadcast
3586 Articles
Reach of 2 666 385 840
AVE = R 154 790 555,40
Print
2114 Inserts
Reach of 674 127 215
AVE = R 65 528 113,85
Online
6602 Articles
Reach of 13 778 329 133
AVE = R 202 681 566,50

## Slide 21: Programme 2: Promotion of Human Rights Areas of under – performance (1)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Percentage implementation of Action Plan on 2020-21 Racial Polarisation Conference Resolutions | 80% - 100% implementation | Target not met as action plans were not implemented | Service provider delayed completion of the report that would inform the action plans for implementation
2 | Percentage implementation of Action Plan on Impact of Covid-19 on children and youth Conference Resolutions | Host Conference by June 2021 and implement 80% - 100% of Action Plan | Conference hosted but action plans not implemented | Capacity constraints as focus area Commissioner was on long sick leave.
3 | Percentage implementation of Action Plan on Provincial Human Rights Dialogue Resolutions | Host 9 Provincial Human Rights Dialogues by June 2021. Implement 80% - 100% of Action Plans | Provincial dialogues hosted but not all provinces implemented the action plans on resolutions. | Provincial focus biased towards the hosting of the dialogues, as opposed to the implementation of the resolutions.

## Slide 22: Programme 2: Promotion of Human Rights Areas of under – performance (2)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
4 | Convening of Annual Provincial Human Rights Stakeholder Engagements | Convene 9 Annual Provincial Human Rights Stakeholder Engagements by August 2021 | Convened 22 stakeholder engagements, but most of the reported activities did not meet indicator definition. | Misinterpretation of the performance indicator. Awareness workshops will be conducted.
5 | Hosting of Virtual National Schools Moot Court Competition | Host Virtual National Schools Moot Court Competition by September 2021 | Competition hosted by Oct 2021 | Target only met in Oct 2022 instead of Sep 2022. Dependency on external scheduling, which is often concluded after the approval of the institutional annual plan.

## Slide 23
Programme 3: Protection of Human Rights
Appropriate redress secured where human rights have been violated

## Slide 24: Programme 3 achievements: Protection of human rights (1)
Protecting human rights
Protection efforts directed primarily to early resolution, however from time to time the Commission did resort to litigation on behalf of complainants
Some of the initiatives undertaken to address systemic violations:
Protecting equality, socio-economic, and civil and political rights: Investigative hearings into the July 2021 civil unrest
Dysfunctionality of waste water treatment plants in the EC
Access to services, justice and call centres for persons with disability in FS and GP
Environmental disaster in KZN following July unrest and closure of beaches and recreational facilities
Completion of the Annual Trends Analysis Report

## Slide 25: Programme 3 achievements: Protection of human rights (2)
Protecting human rights
Inquiry and engagements into local government service delivery in MP and NW
Inquiry into racism in the advertising industry - contribute towards social cohesion and acknowledges the diverse make-up of the country, while allowing for freedom of speech and expression
Some of the strategic engagements conducted for the protection of human rights:
Rights of farm dwellers in the NC
Protecting the rights of homeless people in the WC

## Slide 26: Programme 3 achievements: Finalised cases by province
Prov | Received Enquiries | Finalised Enquiries | Complaints Received | Finalised complaints | % complaints finalised | Complaints and Enquiries Received | Complaints and Enquiries finalised | %
EC | 133 | 133 | 519 | 352 | 68% | 652 | 485 | 74%
FS | 333 | 333 | 392 | 171 | 44% | 725 | 504 | 70%
GP | 1254 | 1253 | 353 | 118 | 33% | 1606 | 1371 | 85%
KZN | 506 | 506 | 777 | 446 | 57% | 1283 | 952 | 74%
LP | 179 | 179 | 772 | 438 | 57% | 951 | 617 | 65%
MP | 418 | 400 | 164 | 105 | 64% | 564 | 505 | 90%
NC | 280 | 280 | 283 | 126 | 45% | 563 | 406 | 72%
NW | 331 | 331 | 320 | 136 | 43% | 651 | 467 | 72%
WC | 783 | 783 | 1499 | 533 | 36% | 2282 | 1316 | 58%
 | 4217 | 4198 | 5079 | 2425 | 48% | 9277 | 6623 | 71%

## Slide 27: Programme 3 achievements: Top 5 complaints lodged
No. | Nature of Rights Violated | 2017-18 No. of cases | 2018-19 No. of cases | 2019-20 No. of cases | 2020-21 No. of cases | 2021-22 No. of cases
1. | Equality | 747 | 783 | 827 | 771 | 660
2. | Health Care, Food, Water and Social Security | 492 | 595 | 702 | 704 | 608
3. | Just Administrative Action | 457 | 452 | 641 | 501 | 438
4. | Labour Relations | 397 | 386 | 457 | 435 | Not in Top 5
5. | Human Dignity | 389 | 411 | 446 | 425 | 348
- | Education | Not in Top 5 | Not in Top 5 | Not in Top 5 | Not in Top 5 | 337

## Slide 28: Programme 3: Protection of Human Rights Areas of under - performance
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Number of strategic impact litigation matters instituted | Institute 15 strategic impact litigation matters | 11 Instituted | Some identified matters were not approved.
2 | Percentage utilisation of the CRM System to promote efficient and effective complaints handling | Full (100%) utilisation of the CRM System | 98% utilisation | Delays in license renewal. Some users awaiting training.
3 | Review of the SAHRC Complaints Handling Procedures | Revised Complaints Handling Procedures | Revised CHP | Awaiting approval.

## Slide 29
Programme 4: Monitoring of Human Rights
Improved accountability for human rights in the country

## Slide 30: Programme 4 achievements: Monitoring of human rights (1)
Monitoring the observance of human rights
Monitoring implementation of the national vaccine roll out strategy and the right to health
Schools monitoring: opening of schools; Covid-19 compliance; water, sanitation and infrastructure – findings of non-compliance with the Minimum Uniform Norms and Standards for Public School Infrastructure
Children’s rights monitoring efforts undertaken in collaboration with the Center for Child Law – focus on secure care centres
Partnered with strategic stakeholders for the implementation of the Independent Monitoring Mechanism under the Convention on the Rights of Persons with Disabilities – focus on capacity to improve government’s response towards barriers faced by persons with disability
Monitoring places of detention or deprivation of liberty as per the Secretariat for the National Preventative Mechanism role of the Commission

## Slide 31: END THANK YOU
www.sahrc.org.za
@sahrcommission