## Slide 1
OVERVIEW REPORT OF THE SECTION 139 CONSTITUTIONAL INTERVENTION AT MSUNDUZI MUNICIPALITY
PC ON COGTA
2 NOVEMBER 2022

## Slide 2: TABLE OF CONTENTS
2
BACKGROUND
IMPLEMENTATION OF THE RECOVERY PLAN – SUMMARY PROGRESS
SUPPORT TO INTERVENTION MUNICIPALITIES INCLDUING MSUNDUZI
CONCLUSIONS

## Slide 3: BACKGROUND REASONS FOR THE INTERVENTION
3
The municipality was put under intervention in terms of section 139(1) of the Constitution in April 2019. The following were the main reasons for the intervention:
Failure by the municipality to hold councillors accountable for deliberately absenting themselves from critical meetings
Failure to institute consequence management measures
Failure by the Council to exercise oversight on management with particular reference to the management of conditional grants
Failure by the Council to exercise oversight over management resulting in the cash position of the municipality being overdrawn
Failure to take reasonable steps to prevent unauthorized and irregular expenditure
Failure by the Council to investigate the unauthorized and irregular expenditure
Failure to hold management or any person accountable for causing unauthorized and irregular expenditure
Failure by the Council to implement consequence management measures against persons responsible for incorrectly or failing to maintain proper records
Failure by the Council to resolve innumerable service delivery related challenges besetting the city, with particular reference to waste management, roads and street maintenance as well as electricity services.
Failure by the Council to investigate allegations of malfeasance and maladministration against senior managers and other leaders of the municipality.

## Slide 4: BACKGROUND … cont RESOLUTIONS OF THE PROVINCIAL EXECUTIVE COUNCIL
4
The Provincial Executive Council (Executive Council) assumed functions specified in terms of sections 51, 56and 57 of the Municipal Systems Act as well as those related to financial management and service delivery including project management.
The Executive Council also authorized the MEC for CoGTA to appoint a Representative or Representatives to be based at the municipality whose task would be to prepare and implement the Recovery Plan incorporating the following terms of reference on behalf of the Executive Council:
  ensuring the implementation of financial systems, policies and procedures including preparation and implementation of cost cutting measures
  to be a compulsory signatory on the municipality’s primary bank account and any other bank accounts that the municipality may operate;
  establishment and acting as chairperson of the Interim Finance Committee (IFC) to monitor and manage the cash flow of the municipality, approve or dis-approve purchase requisitions and to ensure that the municipality’s cash position is not overdrawn;
  ensure that the IFC meets regularly and reports fortnightly to the Executive Committee of Council on the cash flow position, payments approved and disapproved and commitments made (via approved purchase orders);

## Slide 5: BACKGROUND … cont RESOLUTIONS OF THE PROVINCIAL EXECUTIVE COUNCIL … cont
5
  implement governance systems and procedures including oversight over the administration including ratification of decisions taken by the Municipal Council, the Executive Committee, Committees, Municipal Manager and Section 56 Managers in terms of delegated or original authority;
  ensuring that the requirements of the LG Disciplinary Regulations for Senior Managers, 2010 are met timely by the municipality.
  ensuring the implementation of findings arising from any investigations into fraud or maladministration or corruption;
  ensuring implementation of remedial action plans dealing with negative findings from the Auditor General;
  ensuring the implementation of all projects undertaken by the municipality including unblocking projects that have stalled.
  ensuring that the municipality implements measures to urgently improve its operations and maintenance programme with particular reference to waste management, roads and electricity maintenance;

## Slide 6: IMPLEMENTATION OF THE INTERVENTION PLAN - SUMMARY PROGRESS
6
SUMMARY INDICATORS PER MUNICIPALITY
MUNICIPALITY AND INTERVENTION TYPE | KEY INDICATORS |  |  |  |  | 
 | Audit Outcome (2020/2021) | Budget (2022/23) | Senior Management Vacancies & Date of Vacancy | MIG Exp. (30 June 2022) | Sec 106 Investigation | Consequence Management
1. Msunduzi 139(1)(b) | Unqualified | Funded | GM: Technical (July 2022) GM: Electricity (July 2021) | 100% | 2 Section 106 reports – Have been implemented, 15 of the 17 recommendations in the first report implemented and only 4 of the 20 in the second report remains outstanding. | Consequence management was fully implemented against the Municipal employees.
Municipality | MM | CFO | Technical | Corporate | Community | Electricity
Msunduzi | Filled | Filled | Vacant (July 2022) | Filled | Filled | Vacant (July 2021)
STABILITY AT SENIOR MANAGEMENT LEVEL AS AN INDICATOR OF IMPROVEMENT

## Slide 7: GRANT PERFORMANCE AS AN INDICATOR OF IMPROVEMENT
Municipality | 2019/2020 | 2020/2021 | 2021/2022 (Prognosis/Projected)
Msunduzi | Qualified | Unqualified | Unqualified
AUDIT OUTCOMES AS AN INDICATOR OF IMPROVEMENT
Municipality | 2020/2021 Number of audit findings | 2020/2021 Number of audit findings resolved | 2020/2021 Number of audit findings in progress | Percentage of findings resolved
Msunduzi | 7 | 2 | 5 | 28%
AUDIT ACTION PLAN – AUDIT REPORT FINDINGS
Municipality | 2021/2022 |  |  |  | 
 | MIG | WSIG | RBIG | INEP | Notes
Msunduzi | 100% | 100% | - | 76% | 
Table of Contents
PART 1: CAUSE OF FIRE
7
IMPLEMENTATION OF THE INTERVENTION PLAN - SUMMARY PROGRESS … cont

## Slide 8: FINANCIAL VIABILITY RATIOS (JUNE 2022) AS AN INDICATOR OF IMPROVEMENT
8
Municipality | Annual budget funding status 2020/2021 | Annual budget funding status 2021/2022 | Draft Budget funding status 2022/2023
Msunduzi | Unfunded | Funded | Funded
FUNDED BUDGET AS AN INDICATOR OF IMPROVEMENT
UIFW REDUCTION (30 JUNE 2022 Unaudited AFS) AS AN INDICTOR OF IMPROVEMENT
Municipality | UIFW CLOSING BALANCE 2020/2021 AUDITED AFS (As Restated) | UIFW INCURRED FOR THE YEAR. (R) | TOTAL WRITTEN OFF/RECOVERED BY COUNCIL ® | TOTAL UIFW BALANCE FOR THE YEAR ® | PERCENTAGE OF UIFW WRITTEN OFF (%)
Msunduzi | R 2 795 187 700 | R 26 138 926 | (1 101 117 445) | R 1 720 209 181 | 39%
Municipality | Cash Coverage (Norm 1-3months) | Collection (Norm 95%) | Employee Costs (Norm 25%-40%) | Eskom Debt As at 30/08/22 | WB Debt As at 30/08/22
Msunduzi | 0,42 | 77% | 24% | R202 Million | R329 Million
IMPLEMENTATION OF THE INTERVENTION PLAN - SUMMARY PROGRESS … cont

## Slide 9: IMPLEMENTATION OF THE INTERVENTION PLAN - SUMMARY PROGRESS … cont
9
The Municipal Council and all committees have been stable since the 2021 Local Government Election.
The UIFW opening balances for 2021/2022 is R 1,881 billion, incurred to date is R 26,138 million, R1,101 Billion has been written off and total balance as at 30 June 2022 R 1,720 billion. All identified UIFWs are investigated by MPAC and consequence management is being applied.
The municipality have developed strategies to address electricity outages in the city and surrounding areas. Network Development Plan is in place to address the ageing and overloading infrastructure. The Municipality is working in collaboration with Eskom, MISA and businesses to address the electricity issues.
According to EDTEA audit, New England Landfill Site compliance improved substantially.
While the municipality has achieved progress which is indicated by the attainment of an unqualified audit opinion for the 2020/2021 financial year, the municipality identified as having a persistent precarious financial position.
Cogta deployed financial and engineering experts to assist the municipality with a range of matters. They are appointed on twelve (12) months contracts effective from January 2022.

## Slide 10
 | Umngeni Water | COGTA | MISA | DWS | Provincial Treasury
MAIN ROLE | Leads take over in terms of the Ministerial Directive as per Section 63 of the WSA | Section (139) (b) Monitoring & support | Strategic Support as national entity of COGTA | WSIG and RBIG monitoring and Water Services Regulations | Asset management, budget management as part of Section 139 (4) intervention
DEPLOYED FOCAL PERSON |  | MR (1) | Electrical Engineer (1) - | Assistant Project Manager (1) | 
SUPPORT STAFF | Provided hands on support for Darvil Sewer Project | Technical Experts (1) | Allocated R8m to support a clean up process in the municipality. |  | Treasury have deployed internal officials to assist the municipality in respect of financial support.
 |  | Financial Expert (1) |  |  | 
 |  | Governance Expert (1) |  |  | 
 |  | MR Support Staff (1) |  |  | 
 |  | COGTA - grant funding for repairs and maintenance of aged infrastructure through the Accelerated Infrastructure Renewal Programme - R15 million for electricity infrastructure upgrade |  |  | 
TOTAL TECHNICAL SUPPORT = 8 |  | 5 | 1 | 1 | 1
FUNDING |  | MIG 2022/23 – R222 7 152 000 2023/24 – R237 790 000 Accelerated Renewal Programme 2022/23 – R15 000 000 |  | WSIG 2021/22 – R40m 2022/23 – R60m 2023/24 – R65,890m 2024/25 – R70,405m | 
10
CURRENT SUPPORT DEPLOYED AT MSUNDUZI
There is a plethora of technical and financial support that has been deployed at Msunduzi from different sector departments and government entities.
The table below depicts the support framework currently in place to assist the Msunduzi Municipality.
MISA has deployed an Electrical Engineer to support the operations of the municipality. The engineer has been introduced to management and has commenced with duties. The municipality received financial support in terms of the internship implementation, capacity building and development opportunities of Recognition of Prior Learning (RPL) for employees with experience in the infrastructure related fields.
Cogta has deployed a Finance Expert to support with implementation of the Audit Action Plan; POE preparation; compilation of IFS and AFS; addressing UIFW and skilling SCM employees on prevention of UIFW expenditure; revenue enhancement strategies; Skills transfer to the BTOs.
Cogta has further deployed a Governance Expert to assist on all governance and compliance matters.
Moreover, a Water War Room is being revived to streamline all the support offered to the Municipality. The Water War Room will now be an integral part of the One on One engagements and for close monitoring.
SPECIALIST SUPPORT TO MSUNDUZI MUNICIPALITY

## Slide 11
OTHER SUPPORT
Support by Governance and Municipal Finance Units of KZN COGTA in training of newly established MPAC structures.
Support during senior manager recruitment processes.
Orientation Workshops for Councillors
Training of MPACs
Councillor Skills Audit conducted and targeted training identified.
Support during establishment of Ward Committees and revival of Municipal Rapid Response Teams (MRRTs), and all Ward Committees and MRRTs established.
SALGA – has allocated financial resource to support the municipality in terms of training officials and councillors
Revival of Back to Basics campaigns targeting weak functional areas identified during the assessment: revenue enhancement (Masakhane Campaigns); pothole repairs, street light repairs, clean-up campaigns, etc.).
Capacity building of Councillors and municipal officials
Skills transfer by deployed Finance Experts to BTO staff
SETA – The municipality received financial support from the following SETAs in terms of internship implementation: LGSETA Services, MIC SETA
To address fundamental negative impact that results from the lack of infrastructure maintenance, COGTA supports willing municipalities with preparation of Business Plans to access:
  5% of MIG for PMU;
  10% of MIG for O&M; and
  5% of MIG for Asset Management
SPECIALIST SUPPORT TO MSUNDUZI MUNICIPALITY … cont

## Slide 12
12
The MEC met with Msunduzi Municipality in September 2022 and outlined to them the requirements for taking the municipality out of the intervention.
While there is acknowledgement that the challenges facing the municipality are complex and could take long to turn around, the municipality was given three months to show tangible progress.
Another session will be held with the municipality in January 2023 at which time recommendations will be submitted to the Provincial Executive Council to consider terminating or extending the intervention further as the case may be.
CONCLUSIONS

## Slide 13: ANNEXURE A Detailed Progress Report

## Slide 14
GROWING KWAZULU-NATAL TOGETHER
STATE OF MSUNDUZI MUNICIPALITY
OCTOBER 2022

## Slide 15
15
CONTENTS
ITEMS | SLIDE NO.
BACKGROUND | 
FOCAL AREA 1: REPORT ON THE STATE OF GOVERNANCE, POLITICAL AND ADMINISTRATIVE STABILITY | 
FOCAL AREA 2: THE STATE OF FINANCIAL VIABILITY AND MANAGEMENT | 
FOCAL AREA 3: SERVICE DELIVERY AND SOCIO-ECONOMIC DEVELOPMENT | 
MUNICIPAL SUPPORT AND INTERVENTION PLANS (MSIPs) | 
RECOMMENDATIONS | 

## Slide 16
16
BACKGROUND
Msunduzi Municipality (KZN 225) is a local municipality in Umgungundlovu District Municipality, KwaZulu-Natal, South Africa. It encompasses the city of Pietermaritzburg, which is the capital of the KwaZulu-Natal province and the main economic hub of Umgungundlovu District Municipality. Msunduzi has an area of 634 km², consists of 37 wards and has a population of 618 536 majority of which speak IsiZulu.
Councillors are elected representatives serving a predetermined term of office on the local Council on behalf of their respective constituents. The Msunduzi Municipal Council has a total of 81 seats. Political appointments for the are as follows: -
Speaker: NE Majola
Mayor: M Thebolla
Deputy Mayor: M Mkhize
Chief Whip: SW Dlamini
The Executive Committee is made up of 6 members.
There are 5 Portfolio Committees that report to the Executive Committee: -
Finance Portfolio
Infrastructure Portfolio
Community Services Portfolio
Sustainable Developments and City Enterprises Portfolio
Corporate Services Portfolio

## Slide 17
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as of June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Political: | Council structures are stable. 21 Public protests recorded in one financial year – mainly relating to water and electricity | All Council structures were established post LGE and remain stable. Newly elected councillors attended SALGA ICIP training and KZN COGTA orientation workshop held on 12 – 14 April 2022 MPAC has undergone training by COGTA on 18 and 19 May 2022 and has adopted its Annual Work Plan. | Council structures are almost all operational except aids council and rules committee MPAC has developed Annual Work Plans which reflect the timeframes in the MFMA for planning and budgeting cycles and the Annual Work Plans have been approved by Municipal Councils. Municipal Rapid Response has been established. Participation in the DDM Hubs and Clusters is taking place The Mayors has approved and signed the Service Delivery and Budget Implementation Plan for the 2021/22 Financial Year, and were all submitted to COGTA. Public Protests July 2022- Ward 11 Water & Electricity, Imbali Unit 1, Water & Bad Infrastructure; August 2022 - Ward 15 the issues were electricity related September 2022 - Ward 33: Public protest on the Jika Joe Housing Project (23/09/2022). Ward Councillor and Human Settlement officials met with the community member and they provided progress on the housing project. The issues of water and electricity remains a challenge in the district, in particular in Msunduzi requiring intervention from the relevant stakeholders. COGTA Rapid Response facilitated the establishment of the uMgungundlovu / ESKOM War Room to address the challenges faced by ESKOM in finishing the electricity bulk line from ILM, Mpofana, Umgeni, Msunduzi and Richmond. This construction was facing a lot of disruptions that have since been addressed through the war room.

## Slide 18
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as of June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Governance: | The municipality is under 139(1b) 2 x Section 106 reports have been issued and slow implementation of recommendations Poor Performance Management Slow progress in the implementation of Consequence Management Measures. | Section 139 intervention has been extended to 31 October 2022. Ministerial Representative resigned effective from April 2022 and a new MR has been appointed and is continuing to implement the Recovery Plan As at 31 May 2022, there are 47 consequence management cases with 43 completed. There are currently no suspensions. All Ward Committees established. Municipal Rapid Response Team revived under leadership of Speaker. | Intervention Plan - Municipal debts still needs to be reduced at least to R3 billions in this financial year; IFC is still convened every Wednesdays to monitor the progress in this regard; Consequence management cases are being attended to and finalised; Resuscitation of war room is underway; Collection of waste has well improved. Participation in the DDM Hubs and Clusters is taking place Only 4 (10%) out of 41 Ward Committees were declared functional for the quarter ending June 2022. 37 Ward Committees not functional. This is a serious red flag – however the municipality has advised that the reasons for non-functionality are as a result of non-submission of evidence and that they are meeting. The audit on performance over a 3 year trend shows that Msunduzi has regressed which is regrettable as it is a huge drop from Clean to Qualified audit outcomes. This shows inconsistent organizational performance and a need to strengthen political oversight on the administration. Only 67% of performance targets were met as at 30 June 2022. Majority of unachieved targets have been incorporated into the SDBIP for the 2022/23 financial year with the associated corrective measures. However, some unachieved targets have been removed or reprioritized due to lack of budget / funding. Forensic Report tabled in September 2020 & January 2021 : Santosh Manilal Report - There are 19 recommendations of which 6 are implemented and 13 are still a work in progress. Morar Report - There are 17 recommendations of which 15 are implemented and 2 are still a work in progress

## Slide 19
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as of June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Administration: | All senior management posts are filled. Notwithstanding, the municipality still does not have adequate expertise in electricity, waste management, roads and communication (including customer care). The Municipal Manager resigned and exited the municipality on 31 March 2022. Additionally, the Electricity Supply Services Business Unit and Senior Management position was created in 2021. Current vacancy rate is fifty five percent (55%). Organogram was reviewed and adopted late 2021 with an implementation date of January 2022 - immediate reduction strategy is to fill prioritized revenue enhancing and support posts (272) Ongoing failure to complete disciplinary processes within the prescribed timeframe of 90 days from the date of commencement. Poorly functional Customer Care Unit and inadequate Communication with stakeholders and poor response time to address complaints Role and independence of Internal Audit needs to be strengthened (vacancy rate in IA dept = 46%) | MM post advertised and recruitment process ongoing. The post of GM: Electricity Supply Services has been re-advertised to increase the pool. 240 critical vacancies have been filled to date. The post of Senior Manager SAP ERP has been prioritised for filling as part of the capacitation of internal staff to run SAP ERP. it will be advertised before end of June 2022. This will address the billing system complaints and the other financial matters relating to the SAP system. Awareness campaigns and media statements are being issued to improve communication with the consumers. Social media campaigns are done on weekly basis to share messages and provide update on water and electricity faults and interventions to address those faults. Call Centre: The upgrade of the PABX System is currently underway to improve functionality of the call centre. Expiry of senior management employment contracts: CFO – Permanent Head of Corporate Services – Permanent Head of Technical – 30 September 2025 Head of Community – 30 September 2025 | MM post filled with effect from 01 October 2022 Technical Services - Interviews took place 05 October 2022. Two more candidates to be be interviewed on 12 October 2022. Electricity Supply Services - Council has appointed. The appointment is in the Departmental process. Consequence Management - As at 30 September 2022, Total cases = 102; 46 ongoing cases on the roll, 56 closed cases; Presiding Officers and Prosecutors were appointed on all matters Customer Care - The Municipality is in a process or procuring a software that will enable a feedback mechanism where a complaint had been lodged and to enable pro-active communication where a service delivery disruption/faults occurs. This process is at an advanced stage. The funding has been allocated for the project; however there are challenges with the service provider which the ICT Unit is working on addressing. The challenge is that the Service Provider has not been paid and have suspended their services. this will impact negatively on the roll-out and start date of the new system. The organisational service charter was approved by the Council at its meeting that took place on the 29th of June 2022. The action plan will be implemented by business units. The Customer Care Policy was also adopted by Council at its meeting held on the 29th of June 2022; the workshops are currently being undertaken per business unit. Daily service delivery campaigns are undertaken through the Municipality's social media platforms to profile the Municipality's programmes and projects. Public Notices are issued timeously for planned service delivery disruptions and progress updates are issued on hourly basis for unplanned service delivery disruptions. Media statement and public notices are issued weekly to communicate and update on the Municipality's progress in terms of service delivery. Where there are service delivery disruptions notices and update are issued through social media channels.

## Slide 20
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Perfor Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Financial Viability and Management: | The Budget is funded with high risk of sustainability. Negative Audit Outcomes: Qualified audit for 2018/19 and 2019/20; Unqualified with findings in 2020/21 One of highest contributor to UIFW in the province at R1,7 billion. Eskom owed R518.94m Water Board arrear debt is R202m Poor revenue collection and ineffective billing system Slow Infrastructure Grants Expenditure - MIG and WSIG Expenditure. ​ One of highest contributors to UIFW expenditure in the province – R2,7 billion by June 2021 High Debtors’ book – +R5 billion Collection rate – The collection rate was good in September at 133% but declined again in October to 92% and is unstable. Billing system management and control still remains a challenge Cash coverage ratio – This ratio is critical and is significantly below the norm at 0.16 months in October 2021. There is a risk of the municipality not being able to fund its fixed monthly operational expenditure. This is also evident in that payment arrangements are being entered into with Eskom and Umgeni water. Current Ratio – The current ratio has been maintained just above the norm of 1:63 : 1, however, it is of great concern that debtors makes up about 80% of current assets most of which has been long outstanding. | 2022/23 budget is funded and was passed by the Municipal Council on 30 May 2022 The municipality improved to an unqualified audit outcome in the 2020/21 audit. There is an audit plan that was developed in order to implement recommendations of the Audit Committee and there is a committee that seats daily in order to monitor the progress. A slow pace in clearing audit findings as only 9% of the audit findings have been cleared. There has been commitment from senior managers to fast track the implementation of actions. A Finance Expert is deployed by KZN COGTA to support the municipal financial turnaround. Eskom debt reduced to R198.297 million (31 May 2022) and Water Board debt reduced to R60 million (31 May 2022). Payment plans approved and current accounts being paid. Revenue collection at 83 % for May 2022 which is lower than the Treasury norm of 95% The Organisational structure was reviewed to beef up the Revenue Management Unit. A Service Provider appointed to deal with audit of bulk customers including government Activities to reduce the Debtors Book include consolidation of accounts, increased water restrictions and electricity disconnections, weekly monitoring of debt collectors progress (number of summons and executions issued), Weekly Revenue Collection Monitoring by the Acting City Manager, Council is finalising a planned audit of all meters (water & electricity), this planned audit also includes audit of non purchasing prepaid meters. The council has written off +R1,1 billion of unauthorized expenditure.. Remaining balance of UIFW expenditure for both prior years and incurred up to April 2022 is +R1,8 billion. Investigations are ongoing to deal with prior year UIFW expenditure and UIFW registers are updated. | The budget is funded and was adopted on 30 May 2022 Debtors Collection Rate – 110% Employee Related costs – 23% The Cash Coverage Ratio was 0.33 months in September 2022, which was less than then prescribed norm of 1-3 months. The Current Ratio was 1.10 in September 2022, which was less than then prescribed norm of 1.5 - 2 UIFW Total as at 30 June 2022: - Unauthorised: R1 156 418 234, Irregular : R517 944 608.96, Fruitless and Wasteful : R45 843 528 TOTAL R1 720 206 370.96, Total written off R1 101 117 445 Arrear Eskom Debt –R241 292 643.97 (Payment plan in place) Arrear Water Board Debt - R331 814 179.32 (Payment plan in place) The audit outcome for the past 3 years : - 2019/20 FY – Qualified, 2020/21 FY – Unqualified with matters, 2021/22 FY – In progress The 2020-21 Audit Action Plan has been implemented. There are 67 out of 109 audit findings that have been resolved being 61% and 39% in progress of being resolved. Management monitors implementation of audit action on daily basis and meetings are held from Monday to Wednesday at 17h30. Debt : Households R4 141 358 055, Business/Commercial R809 827 808, Government R218 944 044, Any other R221 236 957 The payment plan for Umgeni and Eskom has been finalized and the municipality is paying according to the payment plan as far as Eskom is concern and as for Umgeni the municipality is behind and a will enter into fresh negotiations. Eskom Opening Balance as at September 2022 = 201 860 135, 57 Current Invoice = 353 659 964,01 Payment made in September = (100 000 000,00) Payment made in October = (160 000 000,00 Closing Balance = 295 520 099, 58 Umgeni Opening Balance as at September 2022 = 326 496 659,38 Current Invoice = 89 656 110,10 Payment made in September = (55 000 000) Payment made in October = (00 000 000,00) Closing balance = 364 852 420 , 97

## Slide 21
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Financial Viability and Management: | ….CONT | ….CONT | The collection rate for the month of September was R579 795 277 (110%), August was (R479 006 085) 88%, July was 77% (R426 564 665), June was 91% (R415 187 841) and May was 97% (R445 209 242). However, the actual amount collected for June was lower than May mainly due to load shedding and the back-up that was not in place. The municipality should be collecting at more than 100% in order to ensure that the old debt is recovered. From the beginning of September, the municipality has embarked on Operation QoqamaMillion where the ACM, ACFO, revenue management, electricity and water section are visiting different properties to conduct disconnections and water restrictions for arrear accounts. These disconnections are conducted on a daily basis and the consolidation of accounts is also in progress. These daily disconnections have resulted in an increase of R100 million in terms of the actual debtors amount collected." The Debtors' Collection for the month of September 2022 was R579 795 277 and we are still waiting for the age analysis to determine the Gross Debtors Closing balance. The CoGTA action plan has been developed to address the gaps identified in billing, customer care and credit control. There are various strategies that have been implemented by the municipality to address the issue of debtor's collection, the strategies include the daily electricity disconnections, water restrictions, The action plan is regularly updated and monitored by the revenue enhancement committee. The customers are also being contacted to remind them of the overdue accounts.. Revenue Enhancement meetings are still being held every Wednesday morning and chaired by the City Manager and attended by all stakeholders. The revenue section continue to issue to issue the daily disconnections lists as well as the water restriction listing, however, there has been a decline in terms of the number of customers approach the municipality for reconnection and payment arrangements. The municipality will now focus on enhancing the monitoring of the disconnected properties.

## Slide 22
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Service Delivery: | Challenges include : - Waste management and the landfill site non-compliance issues, Refuse removal and dirty CBD, No grass cutting, Non- attendance to filling of potholes, storm water, and the Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Water And Sanitation Provision Inadequate Capacity of Bulk Infrastructure and Raw Water Resources – R200 mln needed for backlog Upgrade of system - 600 mln needed to serve all with water Physical losses 20/21 = 34%, NRW = 45% Aged Infrastructure, Water Losses Unauthorised Consumption (Illegal Connections) Inadequate Human Resources for Essential Staff 70% of OPEX is spent on Bulk Purchases uMngeni Water resources system is so constrained that uMngeni Water/DWS is considering limiting bulk annual supply to Msunduzi and all other WSA’s until the Mkhomazi Dam is built. Poor functionality of PMU | Water and Sanitation provision and support provided WSIG – Vulindlela Phase 2 Water Pipeline Extension – estimated project cost R108 489 million. 70% expenditure as at 31 May 2022. WSIG – Eradication of Sanitation Backlog in Wards 1-12 Phase 1 – estimated project costs R49 million. 70% as at 31 May 2022. MIG Expenditure – 79.87% of MIG as at 31 May 2022. MISA - Ward phase 1 – water project - replacement of existing pipeline - 6,792km of new water pipeline installed in Ward 3 & 6 accumulatively by the end of May 2022. PMU - Hands on support provided by KZN COGTA with monthly meetings.; Technical expert is assisting with identifying the challenges with performance of MIG. Water Meter Replacement Contract and leak detection programmes are currently underway. To replace approximately 4 000 water metres and identification and repair of all visible and non-visible leakages, which once detected and repaired will reduce real water losses. 4 Additional Plumbers have been employed including the shortlisting of Foreman/Charge hands/Supervisors which will assist in the operational responses to reduce water losses. The Darvill Sewer outfall pipeline that requires urgent major repairs has received attention through applying temporary measures preventing it to burst and the municipality has applied to utilize MIG to address the Darvill sewer challenges. DWS, KZN COGTA and EDTEA are supporting the refurbishment of the pipeline. Revised Non- Revenue Water Master Plan completed and going through approval processes.. | MIG Expenditure –100% as at 30 June 2022. Current Mig Allocation is R227,153 million of which R30 million = 46% of transfer has been spent as at 30 September 2022. Overall the municipality is sitting at 13% expenditure of total allocation. Small Town Rehabilitation: Mkhambathini, R14m, transferred by Cogta as at 28 Sept 2022 Nxamalala Tac Minor Rehab – Budget R144 000 which is 100% spent Mafunze Tac Minor Rehab – Budget of R72 000 which is 100% spent Msunduzi Heroes Acre Memorial Park – Budget of R5 million - As per the Business Plan, the project was meant to commence on 01/07/22 but no work has been undertaken thus far. Appointment of a Service Provider. - The City Manager needs to expedite the appointment process. There was a Service Provider appointed on the 13/09/22 but his contract was terminated on the 30/09/22 due to a contractual impasse. A new Service Provider to be appointed by 14/10/22 Corridor Development: Msunduzi, R6.6 m transferred by Cogta as at 28 Sept 2022 WSIG – R60 million of which R12 million has been transferred and as at 30 Sept 2022 only R1,5 million (2,6%) has been spent – the slow expenditure has resulted in a recommendations for the withholding of 2nd tranche of funding due to poor performance. The project is broken down as follows: - Vulindlela Phase 2 Water Pipeline Extension – estimated project cost R108 489 million – 2022/23 allocation =R5 000 000 however there is 0 expenditure Eradication of Sanitation Backlog in Wards 1-12 Phase 1 – estimated project costs R49 million – 2022/23 allocation = R30 000 – of the R12 000 000 transferred only RR1,5 has been spent = (2,6%) Vulindlela Phase 3 – Water Supply – Upgrades in Wards 1-9 and 39 – Project at planning stage – Project estimate is R25 million which exceeds approved budget . 70% as at 31 May 2022.

## Slide 23
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Service Delivery: | Challenges include : - Waste management and the landfill site non-compliance issues, Refuse removal and dirty CBD, No grass cutting, Non- attendance to filling of potholes, storm water, and the Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Poor functionality of PMU Disaster Management is not fully functional and funding is required (scored 72% on functionality), | Water Meter Replacement Contract and leak detection programmes are currently underway. To replace approximately 4 000 water metres and identification and repair of all visible and non-visible leakages, which once detected and repaired will reduce real water losses. 4 Additional Plumbers have been employed including the shortlisting of Foreman/Charge hands/Supervisors which will assist in the operational responses to reduce water losses. Revised Non- Revenue Water Master Plan completed and going through approval processes. | Water: The contractors have identified 302 leaks in 4 wards. Labour issues have been experienced but have been resolved. Material has been ordered. The CBD is being prioritised, following high water leakage areas as identified by flow logging. The nett effect will result results in identification and repair of all visible and non-visible leakage, which once detected and repaired will reduce real losses. High Water Loss areas have been identified to dispatch contractors. 3 contractors have commenced within Leak Detection. To date 80% of existing Pressure Management Zones have been reinstated to their optimal functionality. On-going monitoring and adjustments are undertaken within these systems, as to mitigate the burst frequency and prevent leakage within the defined pressure managed zones. An apparent loss policy is currently at draft stage which will assist with a standard Operation Procedure to deal with illegal connections. (This will deal with root cause as identified by AG). 4 Additional Plumbers have been employed including the shortlisting Foreman/Charge hands/Supervisors which will assist in the operational responses to reduce water losses. The 4 additional plumbers have commenced on the 1st August 2021. The Superintendent Water and Foremen : Metering both commenced on the 1st January 2022. The City Manager has approved the advertisement of the outstanding Water Foreman positions including foreman. An additional 10 vans has further been ordered which will assist plumbers with reducing losses. 10 additional plumbers are going to acting whilst these positions are advertised. The Operations and Maintenance draft budget submission for the 2022/2023 financial year has significantly increased which will be used to repair leaks and burst pipes. In relation to ageing infrastructure, only a limited budget in relation to Capex of R 1 000 000 has been made available in the 2021/2022 financial year. The Water Losses in relation to the 2020/2021 financial year closed at 29,5% which is below the 30% in line with MFMA Circular 2022. This is above the norm of 30% in terms of circular 72. The rand value will increase due to the increase in tariffs. Replacement of water pipes in the northern areas is currently ongoing (Contractor and consultant). A total of 1,4km of pipes have been replaced. The War of leaks programs will commence in October 2022 which will entail approximately 42 apprentice plumbers dedicated to wards and assisting with soft leaks both in low - cost housing developments.

## Slide 24
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Service Delivery: | Challenges include : - Waste management and the landfill site non-compliance issues, Refuse removal and dirty CBD, No grass cutting, Non- attendance to filling of potholes, storm water, and the Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Poor functionality of PMU Disaster Management is not fully functional and funding is required (scored 72% on functionality), | The Darvill Sewer outfall pipeline that requires urgent major repairs has received attention through applying temporary measures preventing it to burst and the municipality has applied to utilize MIG to address the Darvill sewer challenges. DWS, KZN COGTA and EDTEA are supporting the refurbishment of the pipeline. | Darville Sewer Crisis: - MIG: SAC approval attained from DWS on the 5 July 2022. Project presented and approved by KZN CoGTA on the 22 September 2022. Awaiting formal approval letter. Project presented and approved by Msunduzi BSC on the 27 September 2022. Awaiting SCM project number to advertise tender Tender will be for phase 1 of 2 phases for the material supply only. Detailed design and tender documents are complete.
 |  | Electricity Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. | Electricity Provision The Northdale outdoor project is scheduled to be completed in November 2022 by Eskom. The construction is at 45% at the end of September 2022. The meter audits are in progress and the 6000 meters will be audited in 2022/23 financial year. Approximately 397 meters have been audited as at 30 September 2022. Electricity Meter changes are in progress Roof Repairs are in progress at Electricity Buildings. The priority vacancy list for 2022/23 has been submitted for advertisement. The SVA forms have been completed and awaiting advertising. Report on the development in Mshwathi served at IS Portfolio on 28 July 2022. The meeting with Umshwathi scheduled for 14 September 2022 had taken place, with a further meeting taking place on 05 October 2022 Electricity Maintenance Plan served at Executive Committee on 08 September 2022, with the implementation being ongoing. Electrification of households is ongoing with approximately 190 connections having been achieved as at 30 September 2022."

## Slide 25
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Service Delivery: | Challenges include : - Waste management and the landfill site non-compliance issues, Refuse removal and dirty CBD, No grass cutting, Non- attendance to filling of potholes, storm water, and the Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Poor functionality of PMU Disaster Management is not fully functional and funding is required (scored 72% on functionality), | Challenges include: - Traffic Roads Landfill Site O&M Nonfunctioning of PMU Disaster Management Waste Management and the Landfill Site According to EDTEA audit, New England Landfill Site compliance improved from 31% to 60%. The decommissioning plan of the New England Landfill site has been developed (Lifespan expires in 2027) and is with Council structures. The process of identifying a new site has commenced. To augment the existing capacity, the municipality retained the services of a landfill/waste management expert. This is an external service provider whose primary focus is to assist the municipality to comply with the requirements of the Landfill Licence including the preparation of a decommissioning plan. MISA has allocated R8m to support a clean up process in the municipality. This programme resulted in employment opportunities to people within the municipality. The CBD is cleaned and the contract workers have also been assigned into wards. | Lack of traffic management operations in the CBD: Resultant to the decision by Council Committees in the realization of the single law enforcement, the management of the line function is currently busy with a process of integrating various existing pockets of law enforcement within the Msunduzi Municipality, with an intention through amongst others to strengthen and improve police visibility, traffic law enforcement and also to acquire much needed and critical policing and law enforcement powers which to this end the municipality has not been accorded by the National Police Commissioner. This process in conclusion will realize the final establishment of a municipal police division for Msunduzi Municipality. Roads and Maintenance 19 803 325 square meters of potholes have been repaired. 245 manhole covers have been replaced. 315 square meters of walkways and road surface have been repaired/reinstated. 370 km of stormwater pipes and channels and 142 catchpits have been maintained. Landfill Site The item has been presented before Council and was approved , the implementation of the approved compliance action plan is currently underway as per the internal Audit report dated April 2022. This report is also coupled with the latest monthly reports recording progress on the implementation of the approved compliance action plan. This covers all the line items as listed under section 4.1 and section 3.1 of the revised compliance notice issued in terms of section 31 (L) of the National Environmental Management Act 107 of 1998. The municipality has also obtained approval of BSc for advertising the emergency contract which is responding the approved compliance action plan. Access Control at the Landfill site has been addressed. There is no unlawful disposal of waste happening on site. There are no more waste pickers on site

## Slide 26
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Service Delivery: | Challenges include : - Waste management and the landfill site non-compliance issues, Refuse removal and dirty CBD, No grass cutting, Non- attendance to filling of potholes, storm water, and the Major electricity outages that occurred as a result of fire outbreaks at the Mason and Retief sub stations Non-revenue water by volume is 43.22% Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Electrical infrastructure is in bad state resulting infrequent & prolonged outages. Poor functionality of PMU Disaster Management is not fully functional and funding is required (scored 72% on functionality), | Challenges include: - O&M Nonfunctioning of PMU Disaster Management Disaster Management and Fire and Rescue services Post of Disaster Manager was advertised and 4 Contract workers were absorbed as permanent staff to address disaster management capacity challenges. Funds allocated for procuring Emergency Disaster Relief Disaster Management inundated with requests from Councillors from all wards for finalisation of assessments. Staff are all engaged in finalising these assessments PMU The municipality has prepared Business Plans to obtain funds to address PMU capacity. | Operations And Maintenance Operations and maintenance budget is R17 874 950.00 equivalent to 7.87% PMU Operating cost is R9 172 910.00 equivalent to 4.04% Appointment of Technical support is R1 800 000.00 equivalent to 0.79% Disaster Management A budget of R850k has been approved for the 2022/2023 financial year. Any shortfall will be raised during mid-term budget adjustments. The Post of Manager Disaster Manager was advertised and closed on 18 March 2022, shortlisting will be held on the 2022/09/29. ECC Controller posts shortlisting will be held on the 2022/09/27. 2x Disaster Officer posts have also been advertised awaiting HR to complete process. All 41 Wards have been completed and submitted to the UMDM Disaster Management. This includes Risk Mapping for all Wards. The status remains the same. Request for a four(4) ton vehicle has been moved over to the 2023/2024 budget year. Disaster Management Advisory Forum first quarter meeting was supposed to take place on the 29th September 2022. The meeting was postponed to October as there was no quorum. Non Functional PMU Technical expert is assisting with identifying the challenges with performance of MIG. PMU Business Plans for the 2022/23 FY was submitted to COGTA on 12th April 2022. The reprioritization of the MIG IP is schedule in August 2022. The PMU vacancy rate is sitting at 52% A total of Three posts have been advertised: Chief Project Manager, Project Manager and Finance Manager all awaiting for shortlisting of candidates

## Slide 27
Province: KwaZulu Natal |  |  | 
District: UMGUNGUNDLOVU |  |  | 
Municipality: MSUNDUZI |  |  | 
Key Performance Area | Status quo against SOLG as at June 2021 | Status Quo as at June 2022 | Status Quo as at Sept/Oct 2022
Local Economic Development | LED Strategy and Economic Recovery Plan adopted, requires review and alignment to National LED Strategy Have not adopted a single land use in terms of SPLUMA | The report to adopt the LED Strategy has been finalised and presented to SMC The SDF which is aligned to Section 21 of the SPLUMA was adopted as a part of the IDP | Reviewed LED Strategy was adopted by Council on 7 September 2022 The SDF which is aligned to Section 21 of the Spluma Act was adopted on 31 of March 2022 as a part of the IDP

## Slide 28
THANK YOU