## Slide 1: PRESENTATION TO THE PORTFOLIO COMMITTEE ON DEFENCE AND MILITARY VETERANS
Presentation by: Director-General
9 November 2022

## Slide 2: PURPOSE
To provide the Portfolio Committee with the status report of the work-streams

## Slide 3: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Legislative Review | To develop implementation plans aimed at addressing the policy and legislative issues raised by the Military Veterans. | The Ministerial inputs into the proposed amendments were sourced by the Department in November 2021. Technical advice sought from the Department of Justice and Constitutional Development and Government Technical Advisory Centre due to lack of legal personnel in the department since April 2022 to date was that the department must develop a policy consensus document on the issues raised and present to the Ministry for guidance and approval. The policy consensus document was submitted to the Ministry in October 2022 but yet to be presented to the Ministry for their guidance and concurrence. The policy consensus document was also presented to the Advisory Council in October 2022. The Ministry will set up a task team with relevant expertise to take this matter forward. The Bill will be submitted to the Cabinet as soon as the task team has advised to initiate the formal process of inviting public comment. From there, the process of forwarding the Bill to Parliament can begin in earnest.

## Slide 4: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Organization Redesign | To align the DMV structure to its legislative mandate, strategy and business processes. | The Department partnered with National Treasury’s Government Technical Advisory Centre to assist with development of the macro-organizational structure following advice from the DPSA and National Treasury that they will come into process when they need to asses and independently advise the department on the work done. GTAC submitted the final report on the updated service delivery model, macro-organizational structure and the costing model on the 31 August 2022 with the intention to develop the micro-organizational design after consulting the Ministry. The Department consulted the Ministry on the 1 November 2022 on guidance on the process before going ahead with the micro-organizational design. The Minister will set up a task team with the relevant skills and capabilities from within the Ministry to take process forward, together with the process of consulting DPSA and NT, until the process is complete within this financial year

## Slide 5: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Socio Economic Support | To facilitate meaningful interaction with the social cluster and facilitate the identification of short to medium and long term programmes of government to benefit MV’s. | This is biggest and the most important workstream and deals with the socio-economic issues of Military Veterans. It was acknowledged that there is a challenge in coordination the work of the workstream due to its complex nature and size. The PTT supported the recommendation that this workstream be broken down into various workstreams that are aligned to the benefits of the department such as education, health, empowerment and housing. Attempts are therefore underway to reconfigure the structure of the work-stream. Furthermore, the role of other spheres government must be clearly clarified and included within the framework of the Intergovernmental relations framework. The protocol agreement to be signed with the provinces will include the role of other spheres of government

## Slide 6: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Database Verification, cleansing and Enhancement | To develop a project plan for an accelerated completion of the verification process | The verification process was halted for some time after the Limpopo visits due to internal departmental challenges (Contractual matters and logistics). All these matters have since been resolved. Major General Mashoala has since accepted (signed) the contract as the Chairperson of the committee commencing from 1st November 2022. Other contracts have been issued to other members of the verification committee. DMV is awaiting for their acceptance of which they will commence with immediate effect upon acceptance of the contracts. The other members are re-installed as per the instruction by the Minister within the National Treasury regulations.

## Slide 7: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Heritage and memorialization | To facilitate collaborative research of best practices with relevant countries around matters of heritage and memorialization of liberation veterans | The National Policy on the Repatriation of Human Remains and Heritage Objects was adopted by Cabinet on the 16 March 2021. A Repatriation and Restitution Office (RRO) is being established at the South African Heritage Resources Agency to implement the policy. SAHRA has appointed a manager in the RRO to commence duties on 01 November 2022. A Repatriation and Restitution Advisory Committee has been appointed by the Minister of Sport, Arts and Culture to develop criteria, monitor its implementation and advise on ethical matters related to the restitution and repatriation of human remains. A second meeting of the Advisory Committee on the National Policy on the Repatriation of Human Remains and Heritage Objects was held on 10 May 2022, where the Committee resolved that: A workshop to determine the most impactful but less costly repatriation model and implementation plan be developed. The requested workshop to determine the most impactful but less costly repatriation model and implementation plan took place on 04 - 05 August 2022 at Freedom Park.

## Slide 8: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Heritage and memorialization | To facilitate collaborative research of best practices with relevant countries around matters of heritage and memorialization of liberation veterans | The Government of Botswana approved South Africa’s proposal to construct the two monuments in November 2019. However, the planned site clearance and initial joint planning activities between South Africa and Botswana were postponed due to Covid19. At the Bi-National Commission (BNC) between South Africa and Botswana hosted in Pretoria from 19-22 April 2022, South Africa (DSAC) reaffirmed its commitment to construct two monuments in Botswana. The Bi-National Commission made the following resolutions: South Africa to conduct a visit for site clearance processes of the two sites where the monuments will be constructed in Lobatse and Gaborone respectively. The two countries should finalise the MoU for the implementation of the construction of the monuments and provide an update by the Mid-Term Review in November 2022. Minister of Sport, Arts and Culture led a multi-stakeholder technical visit to Botswana on 06-10 June 2022 to meet with the Minister of Environment, Mineral Resources Conservation and Tourism and other relevant stakeholders. Subsequently, Minister of Sport, Arts and Culture led a multi-stakeholder technical visit to Botswana on 06-10 June 2022 to meet with the Minister of Environment, Mineral Resources Conservation and Tourism and other relevant stakeholders. Although one of the outcomes of the visit was the hosting of a Memorial Lecture to mark the 60th Anniversary of the Lobatse Conference scheduled for October 2022, the Memorial Lecture was postponed till further notice.

## Slide 9: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Heritage and memorialization | To facilitate collaborative research of best practices with relevant countries around matters of heritage and memorialization of liberation veterans | (SADC OUTREACH PROGRAMME FOR HUMAN REMAINS EXHUMATIONS & REPATRIATION) The planned Technical visit to Angola in Quarter 2 of the current financial year did not happen due to the national election and the passing of the former President of Angola. A virtual planning meeting was hosted between the two countries on 01 September 2022. The meeting resolved that Angola should communicate suitable dates for the technical visit. Handover of the bust of Dr Agostinho Neto to Freedom Park The year 2022 marks the Centenary of Dr Agostinho Neto, the first President of the Republic of Angola. As part of paying tribute to and honouring the father of the Nation, Angola will handover his bust to Freedom Park. The Handover Ceremony is scheduled to take place on 13 November 2022 at Freedom Park. The name of President Jose Eduardo Dos Santos has been approved to be inscribed on the wall of remembrance at Freedom Park .

## Slide 10: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Heritage and memorialization | To facilitate collaborative research of best practices with relevant countries around matters of heritage and memorialization of liberation veterans | (MEMORIALISATION OF FALLEN HEROES) Identified common areas for collaboration between South Africa and Tanzania including proposal for restoring and upgrading of Kongwa, and other graves in Tanzania. DSAC and Tanzania are planning to host Cultural Seasons in Tanzania in November 2022 and this visit will also entail a technical site visit. This engagement will further provide a platform for taking forward the planning for safe-guarding liberation heritage sites, graves and negotiations for possible repatriation of human remains in Tanzania DMV and DSAC must conduct a feasibility study on the development of norms and standards that will assist in commemorating and memorialising our fallen heroes and heroines to address inconsistencies and lack of uniformity in design, costs, family support, etc...

## Slide 11: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Pensions and Benefits | To review and update the pension actuarial enquiry undertaken by the DMV in 2014 in order to determine the appropriate Military Veterans quantum in line with inflation. | Military Veterans Pension Policy was approved by the Presidential Task Team on the 26 April 2022. The department is working on the regulations to operationalize the implementation of the benefit (Eligibility and qualifying criteria, application process, appeal process, etc) The next step is to table the regulations in Parliament as soon as possible GPAA already working on a payment system for the benefit The DMV and GPAA working on a profoma application form The Department has made the following budget provisions for the MTEF, including the current financial year
2022/23 | 2023/24 | 2024/25 | 2025/26
RM36.9 | RM102 | RM109 | RM115

## Slide 12: WORK-STREAMS: THEIR PURPOSE AND PROGRESS TO DATE
WORK | PURPOSE | PROGRESS TO DATE
Communications | To ensure that communication and engagement are harnessed effectively throughout the period of the Presidential Task Team. | The work of the communications work-stream is cross-cutting, on-going and continues to monitor and reports on the work of the PTT as it supports the PTT.

## Slide 13: Thank You

## Slide 14
End of Presentation