## Slide 1
National Solar Water Heating Programme (NSWHP) progress update to Portfolio Committee on Mineral Resources and Energy (PPCMRE) scheduled
November 2022
Jointly implemented by:

## Slide 2: PRESENTATION OUTLINE
Abbreviations
01
Background and Summary
Progress on storage of SWH
Installation Progress
Stolen and Damaged Systems
Conclusion
02
03
04
05
06

## Slide 3: ABBREVIATIONS
Central Energy Fund - CEF
Department of Mineral Resources - DMR
Department of Mineral Resources and Energy - DMRE
Department of Energy - DOE
NATIONAL SOLAR WATER HEATER – NSWH
Nuclear Energy Corporation South Africa -NECSA
Request For Bid - RFB
Solar Water Heaters – SWHs
Strategic Fuel Fund - SFF
ABBREVIATIONS
01

## Slide 4: Background
The Department procured 87 206 Baseline Systems from 12 local suppliers to be installed in 19 municipalities across South Africa as part of the National Solar Water Heater Programme (NSWHP).
The NSWHP experienced significant delays in the early stages of implementation owing to several challenges in key activities.
The Department has moved 72 857 SWHs to municipalities and SOE facilities to curb the high storage costs.
About 14 349 SWH are still withheld by suppliers demanding additional storage fees and DMRE is in a legal process to retrieve without paying additional storage costs.
Notwithstanding these challenges installation has commenced and to date 21 367 SWH systems installed out of over 38 921 that were earmarked for Phase 1.
BACKGROUND and SUMMARY
02

## Slide 5: Background
Project Procurement for Phase 2 was put on hold due to the provisions of the PPPFA, particularly the Preferential Procurement Regulation, 2017 (Procurement Regulations) being declared invalid by the Constitutional Court on 16 February 2022, and the subsequent moratorium placed on all procurement processes from the date the judgment was handed down as per the NT advisory of 25 February 2022.
The Department and CEF initiated the procurement process for the installation of about 42 083
remaining units in Phase 2.
Participating municipalities have been identified and framework agreements concluded.
Technical feasibility studies have been concluded in participating municipalities.
SWH baseline systems have been allocated and delivered to 15 out of the initial 19 Municipalities.
Four municipalities : Ekurhuleni, Cape Town, Swartland, and Ndlambe have exited the programme.
Training of installer assistants has commenced in various municipalities and a total of 846 have been trained out the planned 2 644. Training programme has been put on hold due to financial challenges
BACKGROUND and SUMMARY
03

## Slide 6
The Department has incurred fruitless and wasteful expenditure due to storage of SWH by the suppliers beyond the 120 days designated as free storage in the SWH Supply Agreement with the manufactures.
The Department took long to collect the manufactured SWH.
The Department has instituted an investigation through National Treasury. NT appointed KPMG to conduct forensic investigation related to the fruitless and wasteful expenditure incurred by the Department as a result of delayed collection of manufactured SWH.
KPMG has commenced the forensic investigation on SWH storage costs which is currently ongoing
The Department awaits the outcome and is committed to implement the forensic investigation recommendations.
The Portfolio Committee will be apprised of all relevant developments post the release of the KPMG report.
PROGRESS ON STORAGE
04

## Slide 7: PROGRESS ON STORAGE
The Department is addressing the storage challenges for the procured Solar Water Heaters which resulted in significant fruitless and wasteful expenditure. The following has been done:-
The Department procured 87 206 SWH and has removed 72 857 SWHs from the Suppliers.
A total of 14349 SWH are still held by suppliers for various reasons and arbitration is in progress.
Out of the 72 857 removed from Suppliers, 62 757 SWH were delivered directly to municipalities storage facilities and 10 100 SWH are stored at SFF and Necsa respectively.
Out of the units at SFF 5100 SWH base line systems are in the process of disposal to various institutions.
The Department is in consultation with City Power which has expressed an interest to off take 20 000 SWH to install on new RDP houses and as part of repair and replace of the SWH installed during the Eskom SWH project.
The units to be allocated to City Power will be from the units designated for Ndlambe, Ekurhuleni, City of Cape Town and Swartland (these municipalities have terminated the NSWH Framework Agreement) and other municipalities unable to take full complements allocated or have challenges.
PROGRESS ON STORAGE
05

## Slide 8
Description | Number
Units procured | 87206
Units collected from Suppliers | 72857
Units delivered to Municipalities | 62 757
Units at Necsa | 2000
Units at SSF | 8199
Units still held by suppliers | 14349
Units installed | 21367
RECONCILIATION AND LOCATION OF SWH PROCURED
06

## Slide 9
The Department has been involved in legal battles with 6 of the suppliers who have demanded different issues ranging from additional storage costs, demand to increase storage rates and differences in calculating storage fees.
The suppliers have with held 14 349 as a results
Solid State Power (SSP) case has been completed and the DMRE won the case where SSP was claiming in excess of R44 million for additional storage cost. SSP lost the case and was only awarded warranty money which we had withheld and DMRE had to pay the legal fees of both parties.
All other cases are pending and DMRE is confident that the result will be mainly positive.
LEGAL CHALLENGES
07

## Slide 10
A total of 87 206 Baseline Systems were procured through five bid categories.
About 206 SWHs were installed in a pilot project in Nelson Mandela Bay Metropolitan and 150 SWHs were installed in Sol Plaatje Municipality as part of the repair and replace component of the NSWHP by the IPP Office on behalf of the Central Energy Fund (CEF). Total available for installation is 86 856 SWH.
The installation of SWHs has been divided into two phases.
In Phase 1, of the project, a total of 38921 (about 33%) baseline systems were allocated to the appointed installation service providers, split between the DMRE and CEF.
The units were allocated in 18 Municipalities. At present 21 367 have been installed.
Phase 2 is planned for 42 083 installations.
INSTALLATION PROGRESS
08

## Slide 11
Province | Municipality | Phase 1 Contracted | Progress up to
Northern Cape | Sol Plaatje | 6000 | 841
 | Emthanjeni | 1759 | 1759
North-West | Mahikeng | 5000 | 4292
 | City of Matlosana | 3701 | 1924
 | JB Marks | 3500 | 2108
Western Cape | Matzikama | 0 | 0
 | Bitou | 3000 | 2225
 | Cape Agulhas | 2000 | 500
 | Mossel Bay | 2000 | 2893
Eastern Cape | Makana | 2276 | 12
 | Elundini | 2800 | 793
Kwa-Zulu Natal | eThekwini | 1320 | 9
 | Mpofana | 0 | 0
Gauteng | Tshwane | 377 | 377
Limpopo | Polokwane | 5146 | 3646
 | Total | 38879 | 21367
INSTALLATION PROGRESS FOR PHASE 1
09

## Slide 12: ACCELERATION PLAN AND CORRECTIVE MEASURES
A total of 21 367 out of 38 921 SWHs have been installed under Phase 1 and I (a) in nine (9) municipalities.
However the following challenges were experienced:
  Manufacturers refusing to conduct PST until payments are made
  Procurement of consumables for both PST and full installation.
  Manufacturers refusing to supply missing and faulty components
  Delays in the submission of beneficiary list by municipalities to address the outcome of TFA, e.g. asbestos houses.
  Municipalities' demands on only commencing installation when Learner training is completed.
  Demand for 30% of the project to be allocated to local business and community disruptions.
  Disputes with about 6 suppliers who became uncooperative and refused to supply components or provide training.
  Four municipalities withdrew from the programme.
PHASE 1 INSTALLATION CHALLENGES
10

## Slide 13: ION ACCELERATION PLAN AND CORRECTIVE MEASURES
A total of 42 083 systems are planned to be installed during phase 2:
  The plan is to conclude Phase2 installation by the end of September 2
  The Moratorium on Procurement resulting from a Constitutional Court declaration on PPPFA negatively affected our plans.
  The procurement of service providers is underway.
  The target is to appoint more service providers to improve throughput.
  Plans for the procurement of additional components is also underway.
  The beneficiary list is being finalised by the Municipalities and some have submitted.
PHASE 2 INSTALLATION PREPARATION
11

## Slide 14
Province | Municipality | Total Allocation | Possible Phase 2 Allocation
 | Emthanjeni | 4000 | 1709
North-West | Mahikeng | 10000 | 5000
 | City of Matlosana | 5000 | 1299
Western Cape | Matzikama | 2000 | 2000
Eastern Cape | Makana | 6000 | 5988
 | Elundini | 5000 | 2200
Kwa-Zulu Natal | eThekwini | 6000 | 4680
 | Mpofana | 5000 | 5000
Gauteng | Tshwane | 5000 | 4623
Limpopo | Polokwane | 16000 | 9584
 | Total | 82000 | 42083
PHASE 2 ALLOCATION
12

## Slide 15
Some of the SWH system stored in various facilities have been vandalised and components especially copper pipes stolen.
Most of the incidents have been reported to police and case number submitted to the Department.
Investigations are pending but no case has been finalised.
As installation progresses some of the systems have been damaged.
The affected municipalities are Polokwane, JB Marks, City of Matlosana, Matzikama, Sol Plaatjie, Bitou , Cape Agalhus and Makana municipality.
STOLEN AND DAMAGED SYSTEMS
13

## Slide 16: CCELERATION PLAN AND CORRECTIVE MEASURES
Notes progress in implementation of the NSWHP.
Notes that storage challenges have been significantly addressed
Training of installer assistants had gained momentum, but lack of funding has put programme on hold.
The Department is in arbitration process with five suppliers, four of which are withholding SWH baseline systems fully paid for by the Department.
Phase two implementation is under bid evaluation and the Department anticipates installation to be completed in 2023.
Assert disposal of 5 100 SWH baseline systems from Itakane/Isolar under consideration(under liquidation) .
Arbitration process to recover units with other suppliers is underway.
We have alerted police and municipalities to enhance security measures..
CONCLUSION
14

## Slide 17: Thank you