## Slide 1: PORTFOLIO COMMITTEE ON HUMAN SETTLEMENTS: STRATEGY ON ISSUANCE OF TITTLE DEEDS
8 February 2022

## Slide 2: Outline
Purpose
Background
Interventions to Date
Institutional Arrangements
Nature of the Backlogs
Capacity for Implementation
Targets and Delivery
Recommendations for IGR Collaborations – Operation Vulindlela

## Slide 3: 1. Purpose
1. To apprise the Portfolio Committee of the Strategy for the issuance of Tittle Deeds

## Slide 4: 2. Background
By July 2014, the Minister of Human Settlements raised the issue of title deeds as a national priority and charged the Estate Agency Affairs Board (EAAB) with the responsibility of framing a strategy.
The Title Restoration Project was established, based on initial title deed backlog of 818 371, which scope and nature could not be confirmed. To date, 39% of the original pre (45 992) and post 1994 (280,322) has been cleared.
Without making the key policy and implementation changes on the Human Settlement Development Grant – side of the Human Settlements Programme, insofar as it applied to new projects (1 April 2014 to date), the backlog recurred – 252 928 post 2014 and new.
The current 2020-2025 Medium Term Strategic Framework pegs the backlog on title deeds at 1 193 222.

## Slide 5: 3. Interventions to Date
1. Policy Interventions:
Revision of the Housing Code 2009
Updating of the 1997 Housing Process Guide in 2017
A Strategy for the Transfer of Properties (2016
Guidelines for Dispute Resolution
Ministerial Directives in 2017 to tighten certain policy and project management processes
2. Administrative Interventions
Ring-fencing funding for title restoration since 2016/17 in the Human Settlement Development Grant
The TRP Dashboard was introduced in 2016, that enabled the electronic submissions for documents for the registration of title deeds
The Title Restoration Grant was introduced in 2018/19 - 2020, as separate grant to eliminate the pre and post 1994 title deed backlog. Accompanying the Grant Framework was a Compliance and Reporting Framework, which purpose was to
operationalise compliance to the Conditions of the TRG
Notes: Since inception of the Title Restoration project the department has followed a two-pronged strategy:
1. Resolve backlog of properties not registered through:
      Facilitation Process: to determine rights of property;
      Technical Process: resolve issues of proclamation and issuing of deeds
      2. Improve registration process of current projects
      Tighten institutional relations with DRDLR, in particular, Deeds Registry, Surveyor-General bulk registrations, township establishment, etc.
      In long-term, interrogate less complex forms of survey & registration.
Both strategies have been underpinned by a range of interventions, administrative and financial, at policy level, institutionally, hands-on support and improved reporting processes.

## Slide 6
National Project Office
Provincial Implementation
9 Provincial Steering
Committees
National Steering Committee
MinMec
Technical MinMec
MinTop
EMT
Appropriate policy frameworks, operational support
Financial Arrangements & Grant Frameworks
Compliance
Credible implementation plans
Performance & expenditure monitoring
Assume overall responsibility for Project Dashboard
Provide specialist technical & advisory support to Provinces
Sector-related blockages resolved
Conveyancing
Planning & Surveying
Performance Reporting - Project Dashboard + HSS
Resolve sector-related blockages at provincial level
Inputs
Input
Outputs
Outputs
Decisions
(Input)
Appropriate & adequate full time staffing solutions (Data Man., Project Man.)
Data (Deeds Records, HSS)
Decisions and approvals
TRG
Reporting
Verifiable & confirmed deliverables
Funding flows iro direct grant
Reporting requirements
4. Institutional Arrangements
Notes: 5.2.1 The National Project Office has never functioned at full capacity, similarly, provincial capacity assembly for the project has been inadequate, insofar as appropriate skills and adequate manpower is concerned.
5.2.2 A Ministerial Conveyancing Task Team was appointed in 2017 to assist provinces in the implementation of the Project. The skill set was however, inappropriate, as conveyancing was not the problem, but rather township establishment, which was identified already in the 2014 Inception Report.
5.2.3 Through the National Project Steering Committee, the monitoring and reporting on the project had improved greatly. Successes have been recorded with the turnaround times for registration in the deeds offices, through the improved working relationship with the Deeds Registry. What remains unresolved at this level, is the transfer of state owned properties, held by the Departments of Public Works and Infrastructure and Agriculture, Land Reform and Rural Development.
5.2.4 Provincial Steering Committees, meant to improve working relations between provinces that are implementing the project and the municipalities in which projects are located, have collapsed. The main issue of contention is about service providers appointed by the province to perform work in municipalities. Where provinces transfer money to municipalities for the implementation of the project, provincial oversight is weak and municipal accountability poor.
5.2.5 To support provinces with implementation and reporting, the National Department in 2018, appointed Programme Delivery Facilitators (PDFs) in five provinces. The effectiveness of the PDFs are constrained by the internal provincial capacity. There are cases where PDFs are having to take over the full-time job of officials, with no authority whatsoever, as well as cases where PDFs are not performing at all.

## Slide 7: 5. Nature of the Backlogs

## Slide 8: Township Establishment affected by lack of Bulk
Province | No of Projects in Metros | No of potential title deeds | No of projects in Municipalities | No of potential title deeds | Financial Implications
Eastern Cape | 4 | 3 573 | 23 | 15 869 | 
Free State | - | - | 103 | 12 672* | 
Gauteng | - | - | 11 | 12 258* | 747 782 692
KwaZulu Natal | - | - | 10 | 5 637 | 
*Limpopo | - | - | 475 | 97 515 | 
Mpumalanga | No report |  |  |  | 
Northern Cape | 0 | 0 | 0 | 0 | 
North West | - | - | 12 | 52 470 | 389 618 423
Western Cape | No report |  |  |  | 
Total | 4 | 3 573 | 634 | 196 421 | 

## Slide 9: 5. Capacity for Implementation
National Project Office: Chief Town & Regional Planner
Eastern Cape: Assistant Director
Free State: Director and Deputy Director supported by external service provider
Gauteng: Chief Directorate supported by external service provider
Kwa Zulu Natal: Directorate
Limpopo: Directorate
Mpumalanga: Deputy Director & Planner
Northern Cape: None
North West: Deputy Director, Assistant Director, supported by Programme Delivery Facilitator
Western Cape: Chief Directorate – tranches money to municipalities for implementation, supported by Housing Development Agency.

## Slide 10
6. MTSF Targets & Delivery
Category of Title Deeds | 5-Year MTSF Targets | Annual MTSF Target | Annual Business Plan Target (2022/23) | Cumulative Audited Progress (2019/20 - 2021/22 | Annual Progress (Q1, 2 and 3 of 2022/23
Pre 94 | 45 535 | 15 000 | 5 798 | 10 603 | 1 3704
Post 94 | 500 845 | 166 948 | 35 180 | 56 192 | 8 550
Post 2014 | 346 842 | 115 614 | 19 624 | 10 391 | 5 036
New | 300 000 | 100 000 | 5 289 | 987 | 255
Total | 1 193 222 | 397 562 | 65 891 | 78 164 | 15 211

## Slide 11
2022/23 Planned Title Deed Output

## Slide 12: Sector-wide Risks
RISKS | Mitigation Measures
Growing recurring backlog | Implementing the MinMec Resolutions on Titling during the business planning process
Refinancing of old projects | Considering cost-cutting measures in respect of conveyancing contracts against the appointment of legal professionals in provinces
Declining financial priority | Determining minimum annual targets per province per output
Reduced institutional capabilities on the project | Prescribing capacity requirements at provincial level
Fiscal constraints at policy level | Resolution through grants revision process

## Slide 13: 6. Recommendations for intergovernmental working arrangements – Operation Vulindlela
Department: A,RD&LR | Areas of Cooperation
Surveyor-General’s Office | Verification of HSS information against SG records Record-sharing (General Plans, Site Numbers, etc.) Status reports at general plan / project level
Spatial Planning and Land Use Management | Agreed process for township establishment finalisation SPLUMA Exemptions
Deeds Registry | Double Registrations
In conjunction with DPWI | State Land Transfers
Department: Justice & Correctional Services | 
Master of the High Court | Deceased Estates Dispute resolution
National Treasury | 
Budget Office | Dedicated funding arrangements – emphasis on bulk services outside of metro’s
IGR | Resolution of NWHC residential property portfolio
Provinces and municipalities | Power of Attorney Issuing of Title Deeds

## Slide 14: MAWIGA Ministerial Project
Approved July 2022
4 886 title deeds in Garankuwa Unit 1, 2, 3, 4, 5, 6, 16; Kudube Unit 1 and 2 and Mabopane A, B, C and D
3 048 title deeds in Garankuwa Units 7 and 8, Mabopane M, S, U, X and Winterveld.
Appointed 2 Conveyancers: JTP Consortium and Pfukane Khusile – beneficiary verification is underway with the first title deeds expected to be delivered in April 2023.

## Slide 15
Thank You