## EXPANSIONS REPORT
5.5.2 GOVERNANCE MONITORING AND COMPLIANCE: 2021/2022 QUARTER 3 (16 SEPT - 15 DEC) REPORT EXPANSIONS | [23 empty] | EXPANSION SUBMISSIONS TRACKING TOOL | [8 empty] | ADDITIONAL INFORMATION
Number | Period / Quarter | Rollover / New (Use dropdown List) | Date Received By GMC (yyyy/mm/dd) | Date Cases Allocated To Team Member (yyyy/mm/dd) | Team Allocation (Use dropdown List) | Team Member | Entity/Department (Use dropdown List) | Project Description | Supplier / Service Provider | Reason for Expansion (Use dropdown List) | Root Causes (Use dropdown List) | Value of Contract Expansion [R] | Original Contract Value [R] | Value of Previous Expansion [R] | not supported/not supported/Conditional supported (Use dropdown List) | Award/recommended by AO/ AA date (yyyy/mm/dd) | Contract start date (yyyy/mm/dd) | Contract expiry (yyyy/mm/dd) | Status (Use dropdown List) | Application Signed Date (yyyy/mm/dd) | Comments | Not finalised cases by allocated individual | AGE ANALYSIS NUMBER OF DAYS EXPANSION NOT FINALISED BY ALLOCATED INDIVIDUAL | Date Expansion (yyyy/mm/dd): Submitted to CD: GMC | AGE ANALYSIS: NUMBER OF DAYS SINCE ALLOCATED EXPANSION SUBMITTED TO CD | Expansion Date (yyyy/mm/dd): Checked by Chief Director | AGE ANALYSIS: NUMBER OF DAYS TO FINALISE EXPANSIONS BY CHIEF DIRECTOR: GMC | Comments | Expansion Submission Date (yyyy/mm/dd): To Chief Procurement Officer (CPO) | AGE ANALYSIS NUMBER OF DAYS SINCE SIGNED EXPANSION SUBMITTED TO OCPO | Reviewed Expansion on Return Date (yyyy/mm/dd): From Chief Procurement Officer (CPO) | Comments | Date Signed (yyyy/mm/dd) | Not finalised cases by allocated individual | AGE ANALYSIS NUMBER OF DAYS DEVIATION REPORT RECEIVED | Actual Amount Not Supported | Actual Amount Conditional Supported | Total amount Pending, Noting, Closing & Other |  | DROPDOWN LISTS
1 | Q3 2020/21 | New | 2021-09-20 | 2021-09-20 | Team B | Manqoba | Petroleum, Oil and Gas Corporation of South Africa (PetroSA) | Extension of leas office space in Europe | Regus | Continuation of service | Contract Extension | 285770 | 1310107.52 | 0 | Supported | 2021-09-20 | 2021-10-01 | 2022-09-20 | Finalised | 2021-09-29 |  | 9 | Finalised |  |  |  | 0 |  |  | 0 | [8 empty] | Date Not Expired | New | Team B | Inadequate market research and analysis | Supported | Withdrawn | Closed bid process (Limited market) | Letter to GMC | AMBER - require response in 2-5 days | Q2 2020/21 | Returned with comments
2 | Q3 2020/21 | New | 2021-09-29 | 2021-10-01 | Team B | Manqoba | Petroleum, Oil and Gas Corporation of South Africa (PetroSA) | Extension of security guard service contract for head office. | Fidelity Security Service | Finalizing a tender process | Poor contract management | 350000 | 7379846 | 6686748 | Not Supported | 2021-09-29 | 2021-10-01 | 2021-10-31 | Finalised | 2021-10-13 |  | 12 | Finalised
3 | Q3 2020/21 | New | 2021-09-23 | 2021-09-23 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Rental od PABX | Plus1X Communication (Pty) Ltd | Continuation of service | Poor Planning | 23691.23 | 237 580.44 | 35 537.04 | Not Supported | 2021-09-22 | 2021-10-01 | 2021-11-30 | Finalised | 2021-10-13 |  | 20 | Finalised
4 | Q3 2020/21 | New | 2021-10-07 | 2021-10-07 | Team B | Sbusiso | Safety and Security Sector Education and Training Authority (SASSETA)SETA | Disciplinary hearing | Mabece Tilana Incorporated Attorneys | Continuation of service | Preferred Supplier / Single Source | 0 | 0 | 0 | Closed | 2021-10-04 | Not Stated | Not Stated | Finalised | 2021-12-15 |  | 69 | Finalised
5 | Q3 2020/21 | New | 2021-10-05 | 2021-10-05 | Team B | Hulisani | South African Health Products Regulatory Authority (SAPHRA) | Legal services | Maenetje Attorneys | Continuation of service | Preferred Supplier / Single Source | 500000 | 1500000 | 0 | Supported | 2021-10-05 | Not Stated | Not Stated | Finalised | 2021-10-13 |  | 8 | Finalised
6 | Q3 2020/21 | New | 2021-09-29 | 2021-09-29 | Team B | Khanya | Magalies Water | The Moretele South Pipeline Bulk Water Supply construction | Murray and Dickson Construction (Pty) | Significant cost overruns which were due to unexpected risks on the projec | Contract Extension | 57942347.5 | 294099607.09 | 25849608.44 | Conditional Support | 2021-09-29 | Not Stated | Not Stated | Finalised | 2021-10-18 |  | 19 | Finalised
7 | Q3 2020/21 | New | 2021-09-23 | 2021-09-23 | Team B | Khanya | Trans-Caledon Tunnel Authority (TCTA) | Provision of insurance brokering services and placement of corporate insurance | Sankofa Insurance Brokers | Continuation of service | Extensions on current contracts due to new tender processes not concluded in time | 55000 | 262000 | 22500 | Conditional Support | 2021-09-22 | 2021-10-01 | 2022-03-30 | Finalised | 2021-09-30 |  | 7 | Finalised
8 | Q3 2020/21 | New | 2021-09-27 | 2021-09-27 | Team B | Khanya | South African Maritime Safety Authority (SAMSA) | Provision of security service at SAMSA special projects (MSP) Port Quay 500 | Fidelity Security Service | Continuation of service | Extensions on current contracts due to new tender processes not concluded in time | 135413.08 | 947891.56 | 135413.08 | Conditional Support | 2021-09-09 | 2021-10-01 | 2021-11-30 | Finalised | 2021-09-30 |  | 3 | Finalised
9 | Q3 2020/21 | New | 2021-09-30 | 2021-09-30 | Team B | Khanya | Trans-Caledon Tunnel Authority (TCTA) | Provision of office accommodation | Inani Prop Holdings (Pty) Ltd | Continuation of service | Extensions on current contracts due to new tender processes not concluded in time | 11021600.6 | 15475893.63 | 0 | Conditional Support | 2021-09-30 | 2021-12-01 | 2022-11-30 | Finalised | 2021-10-22 |  | 22 | Finalised
10 | Q3 2020/21 | New | 2021-09-27 | 2021-09-27 | Team B | Khanya | Bloem Water | Construction of the new bypass 1000mm diameter Steel pipeline from Leeuwkop Chamber to Brandkop Reservoir | Udumo Trading 26 (Pty) Ltd T/A Ultimate Dynamic | Extension of Time and Change in design due to unforseen circumstances | Service Delivery Urgency | 38066450.37 | 359669847.95 | 49087444.14 | Conditional Support | 2021-09-08 | Not Stated | Not Stated | Finalised | 2021-11-04 |  | 38 | Finalised
11 | Q3 2020/21 | New | 2021-09-27 | 2021-09-27 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Design, Construction and Implementation of a New Railway Signaling System 74 stations and Design, Construction and Implement Civil, Overhead Traction Equipment (OHTE) and Track (COT) works - Gauteng Stage 2 | Siemens Limited | Increased scope of work and extension of time | Poor Planning | 241128853.35 | 2710 500 00,00 | R114 421 800,0 | Not Supported | 2021-10-07 | Not Stated | Not Stated | Finalised | 2021-11-04 |  | 38 | Finalised
12 | Q3 2020/21 | New | 2021-09-27 | 2021-09-27 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Design, Construction and Implementation of a New Railway Signaling System and Guateng Nerve Centre (GNC) Gauteng Stage 1 | Siemens Limited | Increased scope of work and extension of time | Poor Planning | 36712110 | R1 005 98 342.00 | R145 266 076.00 | Not Supported | 2021-10-07 | Not Stated | Not Stated | Finalised | 2021-11-04 |  | 38 | Finalised
13 | Q3 2020/21 | New | 2021-10-13 | 2021-10-13 | Team B | Manqoba | Driving License Card Account (DLCA) | Extension of lease agreement for office space for 5 years | State Information Technology Agency | There is a delay in the acquisition of a new building | Contract Extension | 10926321.43 | Not Stated | 1274737.5 | Conditional Support | 2021-10-13 | Not Stated | Not Stated | Finalised | 2021-11-16 |  | 34 | Finalised
14 | Q3 2020/21 | Appeal | 2021-10-15 | 2021-10-15 | Team B | Manqoba | Petroleum, Oil and Gas Corporation of South Africa (PetroSA) | Charter of the Greatship Manisha (PSV) | Marine Crew Services | PetroSA is unable to proceed with the long term contract due to financial challenges | Business Strategy/operations | 12405000 | 98604803 | 52125400 | Not Supported | 2021-10-15 | Not Stated | Not Stated | Finalised | 2021-12-20 |  | 66 | Finalised
15 | Q3 2020/21 | New | 2021-10-14 | 2021-10-14 | Team B | Hulisani | The South African National Roads Agency SOC Ltd (SANRAL) | Repair of various structures on national route N12 sections 19 & 20 between Gillooly’s interchange and Delmas interchange | INGEROP SA AND KNIGHT PIESOLD JV | project progress was delayed by National Treasury announcing new tender requirements and regulations | Contract Extension | 8853697.55 | 5282979 | 1252468.73 | Not Supported | 2021-10-14 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 35 | Finalised
16 | Q3 2020/21 | New | 2021-10-14 | 2021-10-14 | Team B | Khanya | Road Accident Fund (RAF) | Office lease accommodation at RAF East London | Drury Lane Properties | Continuation of service | Extensions on current contracts due to new tender processes not concluded in time | 2907161.1 | 34603216.04 | 22625437.27 | Conditional Support | 2021-10-04 | 2021-12-01 | 2022-02-28 | Finalised | 2021-10-22 |  | 8 | Finalised
17 | Q3 2020/21 | New | 2021-10-12 | 2021-10-12 | Team B | Hulisani | State Diamond Trader | ICT support services | Redwill ICT | To allow hand over | Extensions on current contracts due to new tender processes not concluded in time | 180000 | 2020718 | 859000 | Supported | 2021-10-12 | 2021-11-01 | 2021-01-31 | Finalised | 2021-10-22 |  | 10 | Finalised
18 | Q3 2020/21 | New | 2021-10-29 | 2021-10-29 | Team B | Sbusiso | South African Medical Research Council (SAMRC) | Open Label Clinical Trial | Marsh (Pty) Ltd | Continuation of service | Poor Planning | 2000000 | 7 000 000.00 | 3 700 000.00 | Supported | 2021-10-29 | Not Stated | Not Stated | Finalised | 2021-11-08 |  | 10 | Finalised
19 | Q3 2020/21 | New | 2021-11-03 | 2021-11-03 | Team B | Khanya | Road Accident Fund (RAF) | Office lease accommodation at RAF Polokwane | TVR Beleggings | Continuation of service | Contract Extension | 998757.7 | 3 201 680.21 | 1 852 749.66 | Conditional Support | 2021-10-26 | 2021-12-01 | 2022-10-01 | Finalised | 2021-11-25 |  | 22 | Finalised
20 | Q3 2020/21 | New | 2021-11-03 | 2021-11-03 | Team B | Sbusiso | Road Accident Fund (RAF) | Office lease accommodation at RAF Durban | Delta Fund (pty) Ltd | Continuation of service | Poor Planning | 21350019.74 | 13 329 465.24 | 0 | Supported | 2021-10-27 | 2021-11-10 | 2022-11-09 | Finalised | 2021-11-08 |  | 5 | Finalised
21 | Q3 2020/21 | New | 2021-11-03 | 2021-11-03 | Team B | Khanya | Road Accident Fund (RAF) | Office lease accommodation at RAF Mahikeng | Columbia Falls Properties (Pty) Ltd | Continuation of service | Poor Planning | 1141453.2 | 4044775.52 | 2799040 | Not Supported | 2021-10-26 | 2022-01-01 | 2022-12-31 | Finalised | 2021-11-18 |  | 15 | Finalised
22 | Q3 2020/21 | New | 2021-11-03 | 2021-11-03 | Team B | Hulisani | Lepelle Northern Water | Implementation of LNW 09/15/16 Mopani District Municipality emergency water and wastewater revitalisation intervention programme – Giyani BWS drought relief (Nandoni to Nsami) | Vharanani Properties (Pty) Ltd | Continuation of service | Contract Extension | 7762930.12 | 521035541.78 | 17425381.53 | Supported | 2021-11-03 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 15 | Finalised
23 | Q3 2020/21 | New | 2021-10-21 | 2021-10-21 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Design, Construction and Implementation of a New Railway Signaling System and Installation of the New Cape Town Centralised Traffic Control Building in Bellville | Thales Maziya Consortium (TMC) | Increased scope of work and extension of time | Poor Planning | 204483200.66 | 1864771512.08 | 603686821.22 | Not Supported | 2021-10-20 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 28 | Finalised
24 | Q3 2020/21 | Appeal | 2021-09-30 | 2021-09-30 | Team B | Khanya | Department of Water and Sanitation (DWS) | Independent environment control officer | Zitholele Consulting (Pty) Ltd | Continuation of work: Clan William Dam Project | Business continuity | 2149576.22 | 3 605 473,44 | 189 421,57 | Conditional Support | 2021-07-27 | 2021-09-01 | 2025-10-30 | Finalised | 2021-11-15 |  | 46 | Finalised
25 | Q3 2020/21 | New | 2021-11-08 | 2021-11-08 | Team B | Hulisani | The South African National Roads Agency SOC Ltd (SANRAL) | Legal services | DUBE N ATTORNEYS INC | Continuation of service | Contract Extension | 1470620 | 1562500 | 0 | Supported | 2021-11-05 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 10 | Finalised
26 | Q3 2020/21 | New | 2021-11-10 | 2021-11-10 | Team B | Hulisani | National Agricultural Marketing Council (NAMC) | Internal Audit Services | Nexia SAB & T | Continuation of service | Contract Extension | 303033.24 | 865809.27 | 0 | Supported | 2021-11-10 | Not Stated | Not Stated | Finalised | 2021-11-25 |  | 15 | Finalised
27 | Q3 2020/21 | New | 2021-11-03 | 2021-11-03 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Management Information System | Solugrowth | Continuation of Services | Poor Planning | 1222947.19 | 4 352 011.56 | 3 389 395.09 | Not Supported | 2021-11-03 | 2021-12-01 | 2022-05-31 | Finalised | 2021-11-23 |  | 20 | Finalised
28 | Q3 2020/21 | New | 2021-11-18 | 2021-11-18 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Lease accommodation | Integer | Continuation of services | Poor Planning | 2285146.2 | 12 151 907.29 | 30 542 453.91 | Not Supported | 2021-11-18 | 2021-12-01 | 2022-02-28 | Finalised | 2021-11-25 |  | 7 | Finalised
29 | Q3 2020/21 | New | 2021-11-08 | 2021-11-08 | Team B | Hulisani | The South African National Roads Agency SOC Ltd (SANRAL) | Legal services | Goitse Pilane Attorneys | Continuation of service | Contract Extension | 1530937.5 | 1684375 | 0 | Supported | 2021-11-05 | Not Stated | Not Stated | Finalised | 2021-11-23 |  | 15 | Finalised
30 | Q3 2020/21 | Appeal | 2021-11-08 | 2021-11-08 | Team B | Khanya | Magalies Water | The Moretele South Pipeline Bulk Water Supply construction | Murray and Dickson Construction (Pty) | Appeal: Significant cost overruns which were due to unexpected risks on the projec | Contract Extension | 57942347.5 | 294099607.09 | 25849608.44 | Conditional Support | 2021-09-29 | Not Stated | Not Stated | Finalised | 2021-12-14 |  | 36 | Finalised
31 | Q3 2020/21 | New | 2021-10-28 | 2021-10-28 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Gauteng North – Replace Foundations, Structure and Small Part Steelwork Project Number PR1705-2008 | Gibb (Pty) Ltd | Increase the amount of professional fees for continuation construction monitoring and project close-out services | Contract Extension | 3492076 | 3779316.6 | 1955707.48 | Conditional Support | 2021-09-29 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 56 | Finalised
32 | Q3 2020/21 | Appeal | 2021-11-26 | 2021-11-26 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Provision of Management Information System | Solugrowth | Continuation of services | Continue using existing software | 1012439.88 | 4352 011.56 | 3389395.09 | Supported | 2021-11-25 | 2021-12-01 | 2021-05-30 | Finalised | 2021-12-08 |  | 12 | Finalised
33 | Q3 2020/21 | New | 2021-11-25 | 2021-10-25 | Team B | Manqoba | Central Energy Fund SOC Ltd (CEF) | Provision of legal services | Mkhabela Huntley Attornerys | Continuation of services | Contract Extension | 2564500 | 1351480 | 0 | Supported | 2021-11-25 | Not Stated | Not Stated | Finalised | 2021-12-20 |  | 56 | Finalised
34 | Q3 2020/21 | New | 2021-11-16 | 2021-11-16 | Team B | Manqoba | National Nuclear Regulator (NNR) | Office accomodation lease | Agricultural Research Concil | Continuation of services | Contract Extension | 1466858.58 | 5011066.08 | 0 | Not Supported | 2021-11-16 | Not Stated | Not Stated | Finalised | 2021-12-06 |  | 20 | Finalised | 2021-11-29
35 | Q3 2020/21 | New | 2021-11-18 | 2021-11-18 | Team B | Hulisani | Council for Geoscience (CGS) | airworthiness services (maintenance services) | Fly High Aviation | Continuation of services | Contract Extension | 2649134.01 | 287416.97 | 0 | Not Supported | 2021-11-09 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 35 | Finalised | 2021-12-01
36 | Q3 2020/21 | New | 2021-11-24 | 2021-11-24 | Team B | Khanya | Road Accident Fund (RAF) | Office lease accommodation at RAF Nelspruit | FGK Capital (Pty) Ltd | Continuation of services | Contract Extension | 840544.2 | 2569779.12 | 657225 | Conditional Support | 2021-11-24 | 2022-02-01 | 2022-07-30 | Finalised | 2021-12-21 |  | 27 | Finalised
37 | Q3 2020/21 | Appeal | 2021-11-29 | 2021-11-29 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Office accomodation lease | Integer | Continuation of services | Poor Planning | 2285146.2 | 12 151 907.29 | 30 542 453.91 | Supported | 2021-11-29 | 2021-12-01 | 2022-02-28 | Finalised | 2021-12-01 |  | 2 | Finalised
38 | Q3 2020/21 | New | 2021-12-02 | 2021-12-02 | Team B | Sbusiso | Media, Information and Communication Technologies Sector Education and Training Authority (MICT SETA)SETA | Rental of 30 laptops | Tezolla Consulting | Continuation of services |  | 286729.2 | 286 729.20 | 0 | Supported | 2021-12-02 | 2021-12-16 | 2022-06-15 | Finalised | 2021-12-21 |  | 19 | Finalised
39 | Q3 2020/21 | New | 2021-12-06 | 2021-12-06 | Team B | Manqoba | Railway Safety Regulator (RSR) | Representation in a disciplinary hearing as initiators | Ka-Mbonane Cooper Law Attorneys (KC Law Attorneys) | Continuation of services | Preferred Supplier / Single Source | 300000 | 480000 | 0 | Supported | 2021-12-06 | Not Stated | Not Stated | Finalised | 2021-12-21 |  | 15
40 | Q3 2020/21 | New | 2021-12-07 | 2021-12-07 | Team B | Hulisani | Perishable Products Export Control Board (PPECB) | travel management services | FCM Travel Solution | Continuation of services | Preferred Supplier / Single Source | 4486909.28 | 4917757.7 | 1330984.99 | Not Supported | 2021-12-07 | 2022-03-01 | 2025-02-28 | Finalised | 2021-12-21 |  | 14 | Finalised
41 | Q3 2020/21 | New | 2021-12-09 | 2021-12-14 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Renovarions and Aircon/Fire Protection and ICT Infrastructure | Eris Properies (Trydium ) | Expansion of scope | Drafting of poor specifications (TORs) and evaluation criteria | 10565490.54 | 44 455 305.82 | 0 | Not Supported | 2021-12-09 | Not Stated | Not Stated | Finalised | 2021-12-21 |  | 7 | Finalised
42 | Q3 2020/21 | New | 2021-12-10 | 2021-12-10 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Design, Construction and Implementation of a New Railway Signaling System 74 stations and Design, Construction and Implement Civil, Overhead Traction Equipment (OHTE) and Track (COT) works - Gauteng Stage 2 | Siemens Limited | Increased scope of work and extension of time | Poor Planning | 202070111.09 | 2710500000 | 11442800 | Not Supported | 2021-10-07 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 13 | Finalised
43 | Q3 2020/21 | New | 2021-12-10 | 2021-12-10 | Team B | Khanya | Passenger Rail Agency of South Africa (PRASA) | Design, Construction and Implementation of a New Railway Signaling System and Guateng Nerve Centre (GNC) Gauteng Stage 1 | Siemens Limited | Increased scope of work and extension of time | Poor Planning | 36588318.38 | 100598342 | 145266076 | Not Supported | 2021-10-07 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 13 | Finalised
44 | Q3 2020/21 | Appeal | 2021-12-13 | 2021-12-13 | Team B | Khanya | Bloem Water | Construction of the new bypass 1000mm diameter Steel pipeline from Leeuwkop Chamber to Brandkop Reservoir | Udumo Trading 26 (Pty) Ltd T/A Ultimate Dynamic | Extension of Time and Change in design due to unforseen circumstances | Service Delivery Urgency | 38066450.37 | 359669847.95 | 49087444.14 | Not Supported | 2021-09-08 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 10 | Finalised
45 | Q3 2020/21 | New | 2021-12-13 | 2021-12-13 | Team B | Khanya | Airports Company South Africa (ACSA) | Additional Baggage Carousel at the ACSA O.R. Tambo International Airport | KVM Risk Solutions (Pty) Ltd | Business Continuity | Service Delivery Urgency | 958842.5 | 830398.8 | 377632.4 | Supported | 2021-12-10 | Not Stated | Not Stated | Finalised | 2021-12-23 |  | 10 | Finalised
46 | Q3 2020/21 | New | 2021-12-03 | 2021-12-03 | Team B | Knowledge | Road Traffic Infringement Agency (RTIA) | Legal Services | ENSafrica | Business Continuity | Emergency | 3102242.32 | 857472 | 0 | Conditional Support | 2021-12-13 | Not Stated | Not Stated | Not Finalised |  |  | -44533 | Finalised
47 | Q3 2021/22 | New | 2021-09-20 | 2021-09-20 | Team C | Lindani | South African Revenue Service (SARS) | Warehouse space lease extension | Tannek CC | Business continuity | Contract Extension | 807490.2 | 190 038,56 | 589 551,78 | Conditional Support | 2021-09-15 | 2021-11-01 | 2024-10-01 | Finalised | 2021-09-30 |  | 10 | Finalised
48 | Q3 2021/22 | New | 2021-09-20 | 2021-09-20 | Team C | Kea | South African Revenue Service (SARS) | Kempton Park Detector Dog Unit Ofice lease space | DENEL | Business continuity | Contract Extension | 14634478.93 | 7 527 305,97 | 11 624 647,04 | Supported | 2021-09-20 | 2021-11-01 | 2026-10-31 | Finalised | 2021-10-21 |  | 31 | Finalised
49 | Q3 2021/22 | New | 2021-09-27 | 2021-09-27 | Team C | Lindani | Department of Home Affairs (DHA) | Extension of physical guarding services contract for Western Cape | Bamogale Enterprise | Tender process underway | Business continuity | 8083698.48 | 35292052,48 | 5560975,17 | Not Supported | 2021-09-27 | 2021-10-01 | 2022-03-31 | Finalised | 2021-09-30 |  | 3 | Finalised
50 | Q3 2021/22 | New | 2021-09-30 | 2021-10-01 | Team C | Lindani | Industrial Development Corporation (IDC) | Extension of Regional Lease Agreement-Western Cape | Prime Zone Properties (Pty) Ltd | Cost efficient | Extension of Accommodation Leases | 5965383.84 | 3 949 919,64 | 0,00 | Conditional Support | 2021-09-30 | 2021-12-01 | 2026-11-30 | Finalised | 2021-10-18 |  | 17 | Finalised
51 | Q3 2021/22 | Rollover | 2021-09-30 | 2021-09-30 | Team C | Moses | South African Post Office (SAPO) | Full maintenance leased vehicles | Avis Car Rental | Bussiness Continuity | Contract Extension | 28000000 | 198,375,147,20 | 12000000 | Supported | 2021-09-13 | not indicated | not indicated | Finalised | 2021-11-04 |  | 35 | Finalised
52 | Q3 2021/22 | New | 2021-10-01 | 2021-10-04 | Team C | Petrus | Office of the Chief Justice (OCJ) | ICT Security enhancement features of the antivirus and malware protection solution | Pursuit Knowledge Consulting | Business continuity | Continue using existing software | 1000000 | Not Indicated | 0,00 | Supported | 2021-09-30 | not indicated | not indicated | Finalised | 2021-10-18 |  | 14 | Finalised
53 | Q3 2021/22 | New | 2021-09-23 | 2021-10-01 | Team C | Lindani | South African Revenue Service (SARS) | Decommissioning and reinstatement of the Riverwalk building | Mowana Properties | cost efficient | Business Strategy/operations | 1731175.79 | 3 405 661,46. | 0,00 | Conditional Support | 2021-09-23 | not indicated | not indicated | Finalised | 2021-10-18 |  | 17 | Finalised
54 | Q3 2021/22 | New | 2021-10-04 | 2021-10-04 | Team C | Petrus | South African Revenue Service (SARS) | Oracle Java SE contract | Oracle America Inc | Business continuity | Continue using existing software | 9354960 | $ 1 725 000.00. | 0,00 | Supported | 2021-09-27 | 2021-10-16 | 2022-10-15 | Finalised | 2021-10-18 |  | 14 | Finalised
55 | Q3 2021/22 | Appeal | 2021-10-06 | 2021-10-06 | Team C | Moses | Broadband Infraco | Extension of lease | CZ Karoo Eiendomme | Extension of lease | Extension of Accommodation Leases | 222772.2 | 153003,80 | 222772,20 | Not Supported | 2021-10-04 | 2019-05-15 | 2022-05-14 | Finalised | 2021-10-21 |  | 15 | Finalised
56 | Q3 2021/22 | New | 2021-10-08 | 2021-10-08 | Team C | Petrus | South African Post Office (SAPO) | Preparing the annual financial statements | Kreston Pretoria | Business continuity | Preferred Supplier / Single Source | 682000 | 1796413,04 | 259000,0 | Supported | 2021-10-08 | 2021-11-12 | 2022-03-31 | Finalised | 2021-11-16 |  | 39 | Finalised
57 | Q3 2021/22 | New | 2021-10-08 | 2021-10-08 | Team C | Lindani | South African Revenue Service (SARS) | 1000 Smart Virtual Workplace lines, Maintenance and Support | Internet Solutions | Business continuity | Continue using existing software | 17602000 | 483 423 022,00 | 0,00 | Not Supported | 2021-10-07 | 2021-11-01 | 2022-06-30 | Finalised | 2021-10-21 |  | 13 | Finalised
58 | Q3 2021/22 | New | 2021-10-08 | 2021-10-08 | Team C | Lindani | National Treasury | the hosting and maintenance of the Vulekamali data portal | OpenUp | Tender process underway | Business continuity | 46383.3 | 139150,00 | 0,00 | Supported | 2021-10-06 | 2021-10-13 | 2021-01-12 | Finalised | 2021-10-21 |  | 13 | Finalised
59 | Q3 2021/22 | New | 2021-10-11 | 2021-10-18 | Team C | Petrus | Interfront | Internet connectivity service | Liquid Telecommunications SA (Pty) Ltd | Business continuity | Business Strategy/operations | 51883.66 | 311 301,96 | 77 825,49 | Supported | 2021-10-08 | 2021-11-01 | 2021-12-31 | Finalised | 2021-10-21 |  | 3 | Finalised
60 | Q3 2021/22 | New | 2021-10-12 | 2021-10-18 | Team C | Lindani | South African Revenue Service (SARS) | Lease for Klerksdorp branch | Sodema CC | Business continuity | Extension of Accommodation Leases | 36336598 | 24 699 461,01 | 0,00 | Conditional Support | 2021-10-12 | 2022-01-01 | 2026-12-31 | Finalised | 2021-11-04 |  | 17 | Finalised
61 | Q3 2021/22 | New | 2021-09-23 | 2021-10-13 | Team C | Petrus | Independent Communications Authority of South Africa (ICASA) | office accommodation for the Mpumalanga Regional Office | Bousaam Trust | Failed bid process/Business continuity | Lack of understanding of procurement legislation | 2045604.2 | 2045 604,20 | 259918.19 | Supported | 2021-09-22 | 2021-10-01 | 2022-09-30 | Finalised | 2021-10-21 |  | 8 | Finalised
62 | Q3 2021/22 | New | 2021-10-13 | 2021-10-13 | Team C | Petrus | Development Bank of Southern Africa (DBSA) | Variation of contract Student Housing Infrastructure Programme (SHIP) | J Maynards (South Africa) (PTY) LTD | cost efficient | Poor contract management | 366677.5 | 9 974 017,85 | 1159898.05 | Supported | 2021-10-13 | Not indicated | Not indicated | Finalised | 2021-10-21 |  | 8 | Finalised
63 | Q3 2021/22 | New | 2021-10-15 | 2021-10-15 | Team C | Petrus | South African Revenue Service (SARS) | Lease extension Stellenbosch office | Valerida Beleggings Pty (Ltd) | Cost efficient | Extension of Accommodation Leases | 4453021.31 | 2 830 573,49 | 6 128 900,99 | Supported | 2021-10-15 | 2021-12-01 | 2026-11-30 | Finalised | 2021-10-21 |  | 6 | Finalised
64 | Q3 2021/22 | New | 2021-10-29 | 2021-10-29 | Team C | Petrus | National Treasury | Implementation of the Cities support programme Phase 2 | Various suppliers | Business continuity | Contract Extension | 21778337.52 | 42 000 000,00 | 47 300 000,00 | Supported | 2021-10-29 | Not indicated | Not indicated | Finalised | 2021-11-15 |  | 17 | Finalised
65 | Q3 2021/22 | New | 2021-10-22 | 2021-10-22 | Team C | Lindani | Government Pensions Administration Agency (GPAA) | Network Services | MTN | Business Continuity | Poor contract management | 35631337.06 | 32 380 923,34 | 23 658 198,08 | Supported | 2021-10-21 | 2021-11-01 | 2022-10-31 | Finalised | 2021-11-15 |  | 24 | Finalised
66 | Q3 2021/22 | New | 2021-10-22 | 2021-10-22 | Team C | Lindani | Government Pensions Administration Agency (GPAA) | Call Centre Services | MTN | Business Continuity | Poor contract management | 7129923.81 | 14 388 114,53 | 16 526 797,42 | Not Supported | 2021-10-26 | 2021-11-01 | 2022-10-31 | Finalised | 2021-11-16 |  | 25 | Finalised
67 | Q3 2021/22 | New | 2021-11-04 | 2021-11-08 | Team C | Rachel | South African Revenue Service (SARS) | Office Lease Vereeniging | Revenue House (Pty) Ltd | Business Continuity | Contract Extension | 14562512.83 | 6 894 680,43 | 46272232.45 | Supported | 2021-11-02 | 2021-12-01 | 2023-11-30 | Finalised | 2021-11-18 |  | 10 | Finalised
68 | Q3 2021/22 | Appeal | 2021-11-10 | 2021-11-11 | Team C | Moses | National Treasury | Capping Contract value | Data Dimension | Single Source | Preferred Supplier / Single Source | 52000000 | Not Indicated | Not Indicated | Within AA/AO mandate Noting | 2021-11-10 | Not indicated | Not indicated | Finalised | 2021-11-23 |  | 12 | Finalised
69 | Q3 2021/22 | New | 2021-11-12 | 2021-11-12 | Team C | Lindani | South African Revenue Service (SARS) | Lease Extension for Richards Bay Branch Office | Lockaway Investment Pty (Ltd) | Extension of lease | Extension of Accommodation Leases | 14962462.91 | 9 748 844,95 | 0,00 | Conditional Support | 2021-11-12 | 2022-03-01 | 2027-02-28 | Finalised | 2021-11-23 |  | 11 | Finalised
70 | Q3 2021/22 | Appeal | 2021-11-03 | 2021-11-12 | Team C | Lindani | South African Revenue Service (SARS) | 1000 Smart Virtual Workplace lines, Maintenance and Support | Internet Solutions | Business continuity | Continue using existing software | 17602000 | 483 423 022,00 | 0,00 | Conditional Support | 2021-11-02 | 2021-11-01 | 2022-06-30 | Finalised | 2021-11-23 |  | 11 | Finalised
71 | Q3 2021/22 | New | 2021-11-22 | 2021-11-22 | Team C | Lindani | South African Revenue Service (SARS) | BMC Remedy software licences | Gijima Holdings (Pty) Ltd | Business continuity | Contract Extension | 6604721 | 40 933 779.64 | 0,00 | Conditional Support | 2021-11-19 | Not indicated | 2025-12-08 | Finalised | 2021-12-06 |  | 14 | Finalised |  | -44522
72 | Q3 2021/22 | New | 2021-11-24 | 2021-11-24 | Team C | Petrus | Broadband Infraco | leasing of office space in Durban for a period of twelve | Keenland Investment 125 (Pty) Limited | Business continuity | Extension of Accommodation Leases | 371744.4 | 1 054 463,28 | 0,00 | Conditional Support | 2021-11-23 | 2021-12-01 | 2022-11-30 | Finalised | 2021-12-01 |  | 7 | Finalised |  | -44524
73 | Q3 2021/22 | New | 2021-11-24 | 2021-11-26 | Team C | Lindani | State Information Technology Agency (SITA) | cleaning and hygiene services to SITA Centurion, Erasmuskloof, Numerus, Blenny and Beta Buildings | Delta Facilities Management (Pty) Ltd | Transition period for new supplier | Business continuity | 2008207.5 | 22 830 295,91 | 3 347 012,52 | Conditional Support | 2021-11-23 | 2021-12-01 | 2022-02-28 | Finalised | 2021-12-01 |  | 7 | Finalised |  | -44526
74 | Q3 2021/22 | New | 2021-12-03 | 2021-12-03 | Team C | Lindani | South African Post Office (SAPO) | SAP ERP Software Suit | SAP | Business continuity | Contract Extension | 8980036.51 | 56 598 266,00 | 25 693 072,16 | Not Supported | 2021-12-03 | 2022-01-01 | 2022-12-31 | Finalised | 2021-12-21 |  | 18 | Finalised |  | -44533
75 | Q3 2021/22 | New | 2021-12-03 | 2021-12-03 | Team C | Lindani | Government Communication and Information System (GCIS) | Distribution of all GCIS produced products and AD Hoc Work focusing more towards the National, Fortnightly distribution of the Government Newspaper, Vuk'uzenzele | Not indicated | Tender process underway | Extensions on current contracts due to new tender processes not concluded in time | 1000000 | 34 066 353,46 | 8 980 748,80 | Supported | 2021-12-02 | 2022-02-01 | 2022-03-31 | Finalised | 2021-12-14 |  | 11 | Finalised |  | -44533
76 | Q3 2021/22 | New | 2021-12-07 | 2021-12-08 | Team C | Rachel | South African Revenue Service (SARS) | Provision of job evaluation services | Korn Ferry (Pty) Ltd | Single Source | Preferred Supplier / Single Source | 991760 | 1 500 000,00 | 0,00 | Conditional Support | 2021-12-07 | Not indicated | Not indicated | Finalised | 2021-12-21 |  | 14 | Finalised |  | -44538
77 | Q3 2021/22 | New | 2021-10-29 | 2021-12-08 | Team C | Petrus | Commission for Conciliation, Mediation and Arbitration (CCMA) | Provision of Disaster Recovery as a service (DRAAS) and Backuop as service (BAAS) for a period of 24 months | SGT Solutions (Pty) Ltd | Business continuity | Business continuity | 2511600 | 6 145 912,89 | 0,00 | Supported | 2021-10-26 | 2022-01-01 | 2023-12-31 | Finalised | 2021-12-21 |  | 53 | Finalised
78 | Q3 2021/22 | New | 2021-12-09 | 2021-12-10 | Team C | Rachel | South African Revenue Service (SARS) | Renewal of the existing ACL Software Maintenance and Support services and provision of seven additional ALC analytic licenses for a period of five (05) years | Surtech Solutions | Business continuity | Sole supplier | 1121190.2 | 5 214 386,19 | 0,00 | Not Supported | 2021-12-08 | Not indicated | Not indicated | Not Finalised |  |  | -44539 | -44539
79 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C | Lindani | Unemployment Insurance Fund (UIF) | Provisioning of deep cleaning and hygiene services | Delta Facilities Management (Pty) Ltd | Transition period for new supplier | Business continuity | 158777.94 | 317 555,88 | 0,00 | Not Supported | 2021-12-08 | 2022-01-01 | 2022-02-28 | Finalised | 2021-12-21 |  | 8 | Finalised
80 | Q3 2021/22 | New | 2021-12-07 | 2021-12-21 | Team C | Rachel | Statistics South Africa (Stats SA) | Google services | Google | Increased demand | Business Strategy/operations | 1687500 | 1 035 000 | 0,00 | Conditional Support | 2021-12-07 | Not indicated | Not indicated | Finalised | 2021-12-23 |  | 16 | Finalised
81 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease New Castle | Viking Pony Properties | Cost efficient | Extension of Accommodation Leases | 3700622.46 | 3 085 622,46 | 0,00 |  | 2021-12-13 | 2022-07-01 | 2023-10-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
82 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Johannesburg | City Property Representing Olitzki Properties (OPH) | Cost efficient | Extension of Accommodation Leases | 9564255.6 | 47 124 106,73 | 0,00 |  | 2021-12-13 | 2022-11-01 | 2023-12-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
83 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Cape Town | The 78 Partnership CC | Cost efficient | Extension of Accommodation Leases | 11457116 | 43 995 676,98 | 0,00 |  | 2021-12-13 | 2022-04-01 | 2023-07-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
84 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Mbombela | Vukile Property Fund Represented by Broll Property Group Ltd | Cost efficient | Extension of Accommodation Leases | 869612.32 | 2 133 440,50 | 2380935.84 |  | 2021-12-13 | 2022-05-01 | 2023-08-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
85 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Tzaneen | Realty 1 PG Rentals TZ | Cost efficient | Extension of Accommodation Leases | 226278.26 | 129 779.10 | 923 696,02 |  | 2021-12-13 | 2022-12-01 | 2023-11-30 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
86 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Bloemfontein | MFT Property Management Trust/ Micheal Family Trust | Cost efficient | Extension of Accommodation Leases | 4496387.52 | 23 086 465,31 |  |  | 2021-12-13 | 2022-06-01 | 2023-09-30 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
87 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Vryburg | Realnet | Cost efficient | Extension of Accommodation Leases | 180004.44 | 400 232,80 | 573 496,07 |  | 2021-12-13 | 2022-09-01 | 2023-08-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
88 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Kimberly | Hostprops 1111 CC | Cost efficient | Extension of Accommodation Leases | 1920000 | 4 377 307,62 | 1 608 408,36 |  | 2021-12-13 | 2022-04-01 | 2023-07-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
89 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office lease Polokwane | Dealta Property Fund | Cost efficient | Extension of Accommodation Leases | 2438905.42 | 15 059 11,81 | 6 819 761,76 |  | 2021-12-13 | 2022-11-01 | 2023-10-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
90 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Ekurhuleni | Heracle Share Block | Cost efficient | Extension of Accommodation Leases | 6250077.6 | 20 917 007,89 | 10 994 471,76 |  | 2021-12-13 | 2022-06-01 | 2023-09-30 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
91 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Emalahleni | Nganya | Cost efficient | Extension of Accommodation Leases | 4570836 | 26 418 772,20 | 0,00 |  | 2021-12-13 | 2022-07-01 | 2023-10-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
92 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Gqeberha | Sinmark Investments CC | Cost efficient | Extension of Accommodation Leases | 3719037.07 | 21 718 525,22 | 3 012 420,08 |  | 2021-12-13 | 2022-04-01 | 2023-07-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
93 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease East London | Border Remedies | Cost efficient | Extension of Accommodation Leases | 2347380 | 11 327 912,81 | 3 872 997,60 |  | 2021-12-13 | 2022-02-01 | 2021-05-31 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
94 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Head Office | Rebosis | Cost efficient | Extension of Accommodation Leases | 16624923.68 | 56 906 451,46 | 0,00 |  | 2021-12-13 | 2022-08-01 | 2021-11-30 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
95 | Q3 2021/22 | New | 2021-12-13 | 2021-12-13 | Team C |  | Commission for Conciliation, Mediation and Arbitration (CCMA) | Office Lease Rustenburg | Redefine Properties | Cost efficient | Extension of Accommodation Leases | 1670880 | 9 403 543,98 | 1 322 502,85 |  | 2021-12-13 | 2022-03-01 | 2021-11-30 | Not Finalised |  | Moved to Q4 2021/2022 | -44543 | -44543
96 | Q3 2020/21 | New | 2021-09-21 | 2021-09-21 | Team A | Bonolo | Transnet SOC Ltd | Provision of material handling equipment Port of Richards Bay | Leomat Plant Hire (Pty) Ltd & Bell Equipment co SA (Pty) Ltd | Business Continuation | Poor Planning | 41098125 | 82196250 | 0.00 | Conditional Support | 2021-09-20 | 2021-09-22 | 2021-12-22 | Finalised | 2021-12-23 |  | 93 | Finalised
97 | Q3 2020/21 | New | 2021-09-21 | 2021-09-21 | Team A | Bonolo | Eskom Holdings SOC Ltd | Procurement of the provision of Group B Hire Cars for (Outage 124, 224, 125 and 225) for Koeberg Operating Unit | Europcar | Additional cars required | Poor contract management | 10444180 | 25 704 133.31 | 0.00 | Not Supported | 2021-09-20 | 2022-03-31 | 2022-07-31 | Finalised | 2021-10-13 |  | 22 | Finalised
98 | Q3 2020/21 | New | 2021-09-28 | 2021-09-28 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply, transportation, erection and dismantling of scaffolding and insulation material | Southey Contracting (Pty) Ltd; Kaefer Thermal Contracting Services (Pty) Ltd; and TMS Group Industrial Services (Pty) Ltd | Finalise the tender process | Poor contract management | 229168461.06 | 378 499 500.00 | Not stated | Conditional Support | 2021-09-28 | 2021-11-01 | 2021-12-31 | Finalised | 2021-10-22 |  | 24 | Finalised
99 | Q3 2020/21 | New | 2021-09-30 | 2021-09-30 | Team A | Bonolo | Eskom Holdings SOC Ltd | Technical Support and Maintenance Services and the manufacture, supply and delivery of air heater and draught plant fans and spares for (FIFTEEN) Coal Fired Generation Power Stations | Howden Africa | Business Continuation | Contract Extension | 441278000 | Not stated | Not stated | Not Supported | 2021-09-10 | 2021-11-01 | 2021-12-31 | Finalised | 2021-10-22 |  | 22 | Finalised
100 | Q3 2020/21 | New | 2021-10-07 | 2021-10-07 | Team A | Hudley | Housing Development Agency (HDA) | Provision of payrol solutions | Bakgone Chartered Accountans | Business Continuation | Expansion of scope (time & material) | 390000 | 570 000.00 | Not stated | Supported | 2021-07-15 | Not stated | Not stated | Finalised | 2021-10-22 |  | 15 | Finalised
101 | Q3 2020/21 | New | 2021-09-20 | 2021-09-22 | Team A | Phaladi | National Credit Regulator (NCR) | Legal services | Dlamini attorneys | Business Continuation | Court Order / Litigation | 1000000 | 1000000 | 150000 | Conditional Support | 2021-09-14 | Not stated | Not stated | Finalised | 2021-11-04 |  | 45 | Finalised
102 | Q3 2020/21 | New | 2021-09-20 | 2021-09-22 | Team A | Phaladi | National Credit Regulator (NCR) | Legal services | Nyapotse attorneys | Business Continuation | Court Order / Litigation | 300000 | 490000 | Not stated | Conditional Support | 2021-09-15 | Not stated | Not stated | Finalised | 2021-09-30 |  | 10 | Finalised
103 | Q3 2020/21 | New | 2021-09-22 | 2021-09-24 | Team A | Phaladi | National Lotteries Commission (NLC) | Panel of marketing | Panel | Business Continuation | Business Strategy/operations | 0 | 59757857.85 | 0 | Conditional Support | 2021-09-22 | Not stated | Not stated | Finalised | 2021-09-30 |  | 8 | Finalised
104 | Q3 2020/21 | New | 2021-09-28 | 2021-09-30 | Team A | Phaladi | National Credit Regulator (NCR) | Legal services | Malatji attorneys | Business Continuation | Court Order / Litigation | 300000 | 470000 | 70500 | Conditional Support | 2021-09-13 | Not stated | Not stated | Finalised | 2021-11-15 |  | 48 | Finalised
105 | Q3 2020/21 | New | 2021-09-29 | 2021-09-30 | Team A | Phaladi | National Lotteries Commission (NLC) | Lease agreement | Raymond Gnesin Investements 2 (Pty) Ltd | Finalise the tender process | Extension of Accommodation Leases | 1292361.76 | 3639572.15 | 3418880.64 | Conditional Support | 2021-09-27 | 2021-11-01 | 2022-07-31 | Finalised | 2021-12-21 |  | 83 | Finalised
106 | Q3 2020/21 | New | 2021-10-01 | 2021-10-04 | Team A | Phaladi | National Lotteries Commission (NLC) | Renovations | SRSQS Quantity surveyors | Business Continuation | Extension of Accommodation Leases | 606900 | 510000 | Not stated | Conditional Support | 2021-09-30 | Not stated | Not stated | Finalised | 2021-11-18 |  | 48 | Finalised
107 | Q3 2020/21 | New | 2021-09-23 | 2021-09-23 | Team A | Jefferson | National Empowerment Fund (NEF) | Lease agreement for regional offices | Prostart Investments 40cc | Business Continuation | Extension of Accommodation Leases | 210970 | 597393.6 | 0.00 | Conditional Support | 2021-08-20 | Not stated | Not stated | Finalised | 2021-10-29 |  | 36 | Finalised
108 | Q3 2020/21 | New | 2021-09-29 | 2021-09-29 | Team A | Jefferson | National Prosecuting Authority of South Africa (NPA) | To provide unified telephony services for the NPA for a period of six (6) months | EOH Mthombo (Pty) Ltd | Business Continuation | Contract Extension | 3795636.54 | 50 587 420.19 | 13 084 472.88 | Conditional Support | 2021-09-27 | Not stated | Not stated | Finalised | 2021-10-29 |  | 30 | Finalised
109 | Q3 2020/21 | New | 2021-10-04 | 2021-09-29 | Team A | Jefferson | National Prosecuting Authority of South Africa (NPA) | Provision of Web and Email security gateway to the NPA for a period of twelve (12) months. | XON Systems (Pty) Ltd | Business Continuation | Contract Extension | 1063022.17 | 3 635 520.93. | 0.00 | Not Supported | 2021-10-01 | Not stated | Not stated | Finalised | 2021-10-29 |  | 25 | Finalised
110 | Q3 2020/21 | New | 2021-09-29 | 2021-09-29 | Team A | Jefferson | National Prosecuting Authority of South Africa (NPA) | Provision of enterprise data backup management software solution to the NPA for a period of twelve (12) months. | XON Systems (Pty) Ltd | Business Continuation | Contract Extension | 1324908.27 | 2 081 541.52. | 0.00 | Conditional Support | 2021-10-01 | Not stated | Not stated | Finalised | 2021-10-29 |  | 30 | Finalised
111 | Q3 2020/21 | Rollover | 2021-10-07 | 2021-10-07 | Team A | Bonolo | Eskom Holdings SOC Ltd | Ash Dam Project at Camden and Rail maintainance at Majuba | Tenova | Business Continuation | Poor contract management | 0 | Not applicable | Not applicable | Noting | 2021-10-02 | Not applicable | Not applicable | Finalised | 2021-12-21 |  | 75 | Finalised
112 | Q3 2020/21 | Rollover | 2021-09-16 | 2021-09-16 | Team A | Bonolo | Eskom Holdings SOC Ltd | Refurbishment of Electrostatic Precipators at Kendal Power Station | J&C Engineering | Business Continuation | Contract Extension | 28474584.73 | R260 417 208.04 | 0.00 | Conditional Support | 2021-06-04 | 18 months | 18 months | Finalised | 2021-11-04 |  | 49 | Finalised
113 | Q3 2020/21 | Rollover | 2021-09-17 | 2021-09-17 | Team A | Bonolo | Eskom Holdings SOC Ltd | Coal Transportation | FCA Carriers Transporters | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Noting | 2021-08-02 | Not applicable | Not applicable | Finalised | 2021-11-04 |  | 48 | Finalised
114 | Q3 2020/21 | Rollover | 2021-09-28 | 2021-09-28 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply, Delivery and Off-loading of Coal | Sasol Energy (Pty) Ltd (Sasol), BP Southern Africa (Pty) Ltd (BP), FFS Refiners (Pty) Ltd (FFS), Eco Energy and Trading (Pty) Ltd (Eco Energy) and Refinex (Pty) Ltd (Refinex) | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Conditional Support | 2021-09-28 | Not applicable | Not applicable | Finalised | 2021-11-23 |  | 56 | Finalised
115 | Q3 2020/21 | Rollover | 2021-09-29 | 2021-09-29 | Team A | Bonolo | Eskom Holdings SOC Ltd | Diesel storage and handling for Ankerlig Power Station | Vesquin | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Noting | 2021-09-29 | 5 years | 5 years | Finalised | 2021-11-04 |  | 36 | Finalised
116 | Q3 2020/21 | Rollover | 2021-09-23 | 2021-09-23 | Team A | Bonolo | Eskom Holdings SOC Ltd | Coal supply and ash handling | Eskom Rotek Industries (ERI) | Feedback on NT's conditions | Feedback on NT's conditions | 0 | R8 536 399 767.15 | Not applicable | Noting | 2021-09-22 | Not stated | 2021-12-31 | Finalised | 2021-11-04 |  | 42 | Finalised
117 | Q3 2020/21 | Rollover | 2021-10-12 | 2021-10-12 | Team A | Bonolo | Eskom Holdings SOC Ltd | Construction of Miscellaneous Structures at Kusile Power Station | Stefanutti Stock Basil Read Joint Venture (SSBR-JV) | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Noting | 2021-03-31 | 19 months | 19 months | Finalised | 2021-11-04 |  | 23 | Finalised
118 | Q3 2020/21 | New | 2021-09-23 | 2021-09-23 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of legal services | MMMG Attorneys | Additional scope of work | Contract Extension | 2200000 | R3 925 000.00 | 0.00 | Conditional Support | 2021-09-22 | Not stated | 2024-03-31 | Finalised | 2021-11-15 |  | 53 | Finalised
119 | Q3 2020/21 | Appeal | 2021-10-01 | 2021-10-01 | Team A | Bonolo | Eskom Holdings SOC Ltd | Logistics and safety management services | Eskom Rotek Industries SOC Ltd (ERI) | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Not Supported | 2021-09-30 | 5 months | 5 months | Finalised | 2021-11-04 |  | 34 | Finalised
120 | Q3 2020/21 | New | 2021-10-19 | 2021-10-19 | Team A | Hudley | Armaments Corporation of South Africa SOC Ltd (ARMSCOR) | Design and installation of a standby generator and uniterrupted power supply | Proffesional Service Providers | Business Continuation | Variation of contract | 79427.04 | 271 200.00 | Not applicable | Conditional Support | 2021-10-19 | Not stated | Not stated | Not Finalised |  |  | -44488 | -44488
121 | Q3 2020/21 | New | 2021-10-27 | 2021-10-27 | Team A | Jefferson | South African Social Security Agency (SASSA) | Head Office lease agreement | Colombia Falls Properties (Pty) Ltd | Business Continuation | Variation of contract | 434834.67 | Not stated | Not stated | Conditional Support | 2021-10-22 | Not stated | Not stated | Not Finalised |  |  | -44496 | -44496
122 | Q3 2020/21 | New | 2021-10-27 | 2021-10-27 | Team A | Jefferson | South African Social Security Agency (SASSA) | 70 parking bays for Head Office | Khumza Motheo (Pty) Ltd | Business Continuation | Variation of contract | 55010.2 | Not stated | Not stated | Conditional Support | 2021-10-22 | Not stated | Not stated | Not Finalised |  |  | -44496 | -44496
123 | Q3 2020/21 | New | 2021-10-28 | 2021-10-29 | Team A | Phaladi | National Lotteries Commission (NLC) | General Mantenance and handyman service | Sky Batiment (Pty) Ltd | Unforseen maintenance services | Variation of contract | 150000 | Not stated | Not stated | Conditional Support | 2021-10-26 | Not stated | Not stated | Finalised | 2021-12-06 |  | 39 | Finalised
124 | Q3 2020/21 | New | 2021-10-19 | 2021-10-19 | Team A | Bonolo | Department of Cooperative Governance (DCoG) | Security Services | Wenzile Phaphama Security | Business Continuation | Extensions on current contracts due to new tender processes not concluded in time | 423836.44 | 33 769 546.72. | 4 955 484.74 | Conditional Support | 2021-10-19 | 5 weeks | 5 weeks | Finalised | 2021-11-15 |  | 27 | Finalised
125 | Q3 2020/21 | New | 2021-10-19 | 2021-10-19 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of legal servicesfor Medupi and Kusile power stations | ENS Africa | Preferred supplier | Business continuity | 18406118 | 2 078 119.00 | 0.00 | Conditional Support | 2021-10-19 | Not stated | 2024-03-31 | Finalised | 2021-11-18 |  | 30 | Finalised
126 | Q3 2020/21 | Appeal | 2021-10-25 | 2021-10-25 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of site maintenance for Boiler Feed pump train and Condensate Extraction pumps with their auxiliary equipment at Eskom’s coal fired power stations | Sulzer Pumps South Africa (Pty) Ltd | Finalise the tender process | Business continuity | 33151602 | Not stated | Not stated | Conditional Support | 2021-10-25 | 2022-01-01 | 2022-03-31 | Finalised | 2021-11-25 |  | 31 | Finalised
127 | Q3 2020/21 | Rollover | 2021-10-15 | 2021-10-15 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of Wide Area Network (WAN) (Data Links) | Dark Fibre Africa | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Noting | 2021-10-15 | Not applicable | Not applicable | Finalised | 2021-11-23 |  | 39 | Finalised
128 | Q3 2020/21 | New | 2021-10-12 | 2021-10-12 | Team A | Bonolo | Eskom Holdings SOC Ltd | Engineering Services for the Steam Generator Replacement Project at Koeberg Nuclear Power Station | Tractebel Engineering | Preferred supplier | Poor Planning | 34800584.21 | ZAR21 005 000.22 | ZAR12 839 211.72 | Conditional Support | 2021-10-12 | Not stated | Not stated | Finalised | 2021-11-23 |  | 42 | Finalised
129 | Q3 2020/21 | New | 2021-11-03 | 2021-11-04 | Team A | Hudley | Department of Military Veterans (DMV) | Provision of the compilation of the financial statements | Morar Incorporated | Business Continuation | Contract Extension | 139304.02 | 487 107.60 | Not applicable | Conditional Support | 2021-11-03 | Not applicable | Not applicable | Not Finalised |  |  | -44503 | -44503
130 | Q3 2020/21 | Rollover | 2021-11-03 | 2021-11-04 | Team A | Bonolo | Eskom Holdings SOC Ltd | Medupi Consolidated Building Management System | Honeywell | Business Continuation | Contract Extension | 0 | Not applicable | Not applicable | Noting | 2021-11-09 | Not applicable | Not applicable | Finalised | 2021-12-03 |  | 30 | Finalised
131 | Q3 2020/21 | New | 2021-11-04 | 2021-11-04 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply of Coal from Usutu Colliery to Camden Power Station | Vunene Mining | Depletion of funds | Contract Extension | 292333119.17 | 1746024000 | R5 253 731 056.68 | Conditional Support | 2021-11-04 | 2021-01-22 | 2023-03-31 | Finalised | 2021-11-21 |  | 17 | Finalised
132 | Q3 2020/21 | New | 2021-11-04 | 2021-11-04 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply of coal from Goedgevonden Complex (“GGV”) to Majuba Power Station and/or any other designated Eskom power stations | Glencore | Depletion of funds | Contract Extension | 1319137813.08 | 7 894 892 866.80 | 10 309 675 100.50 | Conditional Support | 2021-11-04 | 2022-01-01 | 2026-06-30 | Finalised | 2021-11-21 |  | 17 | Finalised
133 | Q3 2020/21 | New | 2021-11-20 | 2021-11-20 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply, delivery and off-loading of fuel oil to all Eskom’s coal fired power stations on an as when required basis | Sasol Energy (Pty) Ltd , BP Southern Africa (Pty) Ltd , FFS Refiners (Pty) Ltd , Eco Energy and Trading (Pty) Ltd and Refinex (Pty) Ltd | Complete the tender process | Contract Extension | 1519812828.03 | 3649589688.4 | 4964045688.4 | Conditional Support | 2021-11-19 | 2021-12-01 | 2022-02-28 | Finalised | 2021-11-21 |  | 1 | Finalised
134 | Q3 2020/21 | Rollover | 2021-10-12 | 2021-10-12 | Team A | Bonolo | Eskom Holdings SOC Ltd | Steam Generator Project Plant Daughter Modifications, Packages 2 and 4 | General Electric (GE) | Preferred supplier | Business continuity | 60000000 | R313 836 498.60. | 0.00 | Conditional Support | 2021-10-12 | 6 months | 6 months | Finalised | 2021-10-25 |  | 13 | Finalised
135 | Q3 2020/21 | New | 2021-11-17 | 2021-11-17 | Team A | Bonolo | Eskom Holdings SOC Ltd | Supply, loading and placement of fourteen (14) dual purpose spent fuel dry storage metal casks for use at Koeberg Nuclear Power Station (Phase 1A) | Holtec International | Addiitonal scope of work | Contract Extension | 177963419.37 | 81 771 901.15 | 344 237 152.97 | Conditional Support | 2021-11-17 | 12 months | 12 months | Finalised | 2021-12-03 |  | 16 | Finalised
136 | Q3 2020/21 | New | 2021-11-16 | 2021-11-16 | Team A | Bonolo | Eskom Holdings SOC Ltd | Procurement of Turbine Generator Works at Kusile Power Station Project | GE Steam Power S&E Africa (GE) | Business Continuation | Poor contract management | 293141189.36 | 13 168 322 824.00 | 4 350 083 302.65 | Conditional Support | 2021-11-16 | 12 months | 12 months | Finalised | 2021-12-09 |  | 23 | Finalised
137 | Q3 2020/21 | New | 2021-11-16 | 2021-11-16 | Team A | Bonolo | Eskom Holdings SOC Ltd | Procurement of Phase B - Completion of Unit 5 & 6 DHP, Silo 5 & 6 and associated auxiliary systems | Eskom Rotek Industries SOC Ltd (ERI) | Business Continuation | Poor contract management | 265113171.71 | 118638782.03 | 0.00 | Conditional Support | 2021-11-16 | 2022-03-23 | 2023-05-20 | Finalised | 2021-12-03 |  | 17 | Finalised
138 | Q3 2020/21 | New | 2021-11-24 | 2021-11-24 | Team A | Bonolo | Eskom Holdings SOC Ltd | Boiler maintenances services | Steinmuller Africa (Pty) Ltd, Babcock Ntuthuko Engineering (Pty) Ltd and Actom (Pty) Ltd | Depletion of funds | Contract Extension | 1197409092.53 | 851 000 000.00 | 19225875175.36 | Conditional Support | 2021-11-19 | 2022-01-01 | 2022-03-31 | Finalised | 2021-12-06 |  | 12 | Finalised
139 | Q3 2020/21 | New | 2021-11-22 | 2021-11-22 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of supplementary personnel to support the preparation and execution of outages and outage related maintenance activities | Deros International | Depletion of funds | Poor Planning | 19222572 | 112700000 | 3 544 025.16 | Conditional Support | 2021-11-22 | 36 months | 36 months | Finalised | 2021-12-21 |  | 29 | Finalised
140 | Q3 2020/21 | Appeal | 2021-11-22 | 2021-11-22 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of Logistics and Safety Management Services to Primary Energy Logistics Department | Eskom Rotek Industries SOC Ltd | Complete the tender process | Poor contract management | 623449500 | 1 599 777 921.76 | 0.00 | Conditional Support | 2021-11-19 | 3 months | 2022-03-31 | Finalised | 2021-12-03 |  | 11 | Finalised
141 | Q3 2020/21 | Appeal | 2021-11-26 | 2021-11-26 | Team A | Bonolo | Transnet SOC Ltd | Provision of material handling equipment Port of Richards Bay | High Power Equipment Africa (Pty) Ltd | Complete the tender process | Poor contract management | 82196250 |  | 41098125 | Conditional Support | 2021-11-25 | 2021-12-23 | 2022-06-23 | Finalised | 2021-12-23 |  | 27 | Finalised
142 | Q3 2020/21 | New | 2021-11-30 | 2021-11-30 | Team A | Phaladi | Department of Correctional Services (DCS) | Cleaning services | Afriboom (Pty) Ltd | Complete the tender process | Extensions on current contracts due to new tender processes not concluded in time | 481320.02 | 1443960.06 | 2406600.1 | Conditional Support | 2021-11-30 | 2021-12-01 | 2022-01-02 | Finalised | 2021-12-01 |  | 1 | Finalised
143 | Q3 2020/21 | New | 2021-12-06 | 2021-12-06 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of management, maintenance and operational service for the power station coal supply, coal and ash handling | ERI | Complete the tender process | Poor Planning | 2214294123.89 | R8 536 399 767.15 | 0.00 | Not Supported | 2021-12-05 | 2021-01-01 | 2022-12-31 | Finalised | 2021-12-21 |  | 15 | Finalised
144 | Q3 2020/21 | New | 2021-12-06 | 2021-12-06 | Team A | Bonolo | Eskom Holdings SOC Ltd | Execution of cabling and stringing works at Medupi and Matimba 400kV Yards | Eskom Rotek Industries SOC Ltd | Complete the tender process | Poor contract management | 82196350 | 99187500 | 12 329 437.50 | Conditional Support | 2021-11-25 | 2021-12-23 | 2022-06-23 | Finalised | 2021-12-21 |  | 15 | Finalised
145 | Q3 2020/21 | New | 2021-11-18 | 2021-11-18 | Team A | Jefferson | Department of Justice and Constitutional Development (DoJ&CD) | Cash in transit services | Fidelity Cash Solutions | Complete the tender process | Poor contract management | 106786900.59 | 16 362 651.64. | 14 786 420.19 | Not Supported | 2021-11-15 | 2021-11-19 | 2022-03-31 | Finalised | 2021-11-25 |  | 7 | Finalised
146 | Q3 2020/21 | New | 2021-11-18 | 2021-11-18 | Team A | Jefferson | Legal Aid South Africa | Biometric system software solution | Timetronics Security and Workforce Solutions | Complete the tender process | Poor contract management | 107847 | 26 818.00 | 0 | Not Supported | 2021-09-16 | 2021-12-01 | 2022-01-30 | Finalised | 2021-12-03 |  | 15 | Finalised
147 | Q3 2020/21 | New | 2021-11-15 | 2021-11-15 | Team A | Jefferson | National Prosecuting Authority of South Africa (NPA) | Covert Offices accommodation for Witness Protection (OWP) | not stated | Preferred supplier | Business continuity | 0 | 8 232 336.59 | 7 878 888.90. | Conditional Support | 2021-09-21 | 2021-12-01 | 2022-12-31 | Finalised | 2021-11-18 |  | 3 | Finalised
148 | Q3 2020/21 | New | 2021-11-11 | 2021-11-11 | Team A | Jefferson | National Prosecuting Authority of South Africa (NPA) | Covert residential accommodation for Witness Protection (OWP) | not stated | Preferred supplier | Business continuity | 0 | 13 600 575.50 | not stated | Conditional Support | 2021-09-21 | 2021-12-01 | 2022-12-31 | Finalised | 2021-11-18 |  | 7 | Finalised
149 | Q3 2020/21 | New | 2021-12-08 | 2021-12-08 | Team A | Jefferson | Legal Aid South Africa | Wide Area Network contract | not stated | Complete the tender process | Poor Planning | 0 | not stated | not stated | Not Supported | 2021-12-08 | 2022-01-01 | 2022-05-31 | Finalised | 2021-12-03 |  | -5 | Finalised
150 | Q3 2020/21 | New | 2021-12-07 | 2021-12-07 | Team A | Jefferson | State Security Agency (SSA) | Extension of a contract for the provisioning of office accommodation at Nelspruit SIU office | Vukile Property Fund Group | Complete the tender process | Poor Planning | 7528234.35 | 1,610,120.91 | 3,848,196.94 | Supported | 2021-12-06 | 2022-01-01 | 2022-12-31 | Finalised | 2021-12-20 |  | 13 | Finalised
151 | Q3 2020/21 | New | 2021-12-07 | 2021-12-07 | Team A | Phaladi | Municipal Infrastructure Support Agent (MISA) | Consultancy services for supervision of review design and construction | PSP | Depletion of funds | Exceeding the 15%/R15m or 20%/R20m threshold for expansions (especially SOCs with large projects) | 1341264.84 | 4200000 | 0 | Conditional Support | 2021-12-07 | Not stated | Not stated | Not Finalised |  |  | -44537 | -44537
152 | Q3 2020/21 | Rollover | 2021-12-06 | 2021-12-06 | Team A | Bonolo | Eskom Holdings SOC Ltd | Technical Support and Maintenance Services and the manufacture, supply and delivery of air heater and draught plant fans and spares for (FIFTEEN) Coal Fired Generation Power Stations | Howden Africa | Complete the tender process | Service Delivery Urgency | 172500000 | 441 278 000.00 | 0 | Conditional Support | 2021-12-06 | 2 months | 2 months | Finalised | 2021-12-21 |  | 15 | Finalised
153 | Q3 2020/21 | New | 2021-12-10 | 2021-12-10 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of contract claims services | HKA Global (Pty) Ltd | Additional scope of work | Business continuity | 163072927.49 | 177 441 935.57 | 0.0 | Conditional Support | 2021-12-10 | 2022-04-01 | 2023-01-31 | Finalised | 2021-12-21 |  | 11 | Finalised
154 | Q3 2020/21 | New | 2021-12-10 | 2021-12-10 | Team A | Bonolo | Eskom Holdings SOC Ltd | Legal services | Thipa Attorneys | Additional scope of work | Business continuity | 3450000 | 1 150 000.00 | R 1 150 000.00 | Conditional Support | 2021-12-10 | Not stated | 2024-03-31 | Finalised | 2021-12-21 |  | 11 | Finalised
155 | Q3 2020/21 | Rollover | 2021-09-30 | 2021-09-30 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provison of logistics and safety management services to Primary Energy Department | Eskom Rotek Industries SOC Ltd | Feedback on NT's conditions | Business continuity | 0 | Not applicable | Not applicable | Noting | 2021-09-30 | Not applicable | Not applicable | Finalised | 2021-12-21 |  | 82 | Finalised
156 | Q3 2020/21 | New | 2021-09-30 | 2021-09-30 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of legal services for Medupi and Kusile power stations | ENS Africa | Additional scope of work | Business continuity | 18406118 | 2 078 119.00 | 0.0 | Conditional Support | 2021-10-19 | Not stated | 2024-03-31 | Finalised | 2021-12-14 |  | 75 | Finalised
157 | Q3 2020/21 | New | 2021-11-11 | 2021-11-11 | Team A | Bonolo | Eskom Holdings SOC Ltd | Steam Generator Project Plant Daughter Modifications, Packages 2 and 4 –, for Koeberg Operating Unit | General Electric | Intellectual Property | Business continuity | 79000000 | R313 836 498.60 | 0.0 | Conditional Support | 2021-11-11 | six months | six months | Finalised | 2021-12-21 |  | 40 | Finalised
158 | Q3 2020/21 | New | 2021-11-11 | 2021-12-15 | Team A | Bonolo | Eskom Holdings SOC Ltd | Turbine generator works at Kusile Power Station Projects (P11) | GE Steam Power S&E Africa | Feedback on NT's conditions | Feedback on NT's conditions | 0 | Not applicable | Not applicable | Noting | 2012-12-15 | Not applicable | Not applicable | Finalised | 2021-12-21 |  | 40 | Finalised
159 | Q3 2020/21 | New | 2021-12-10 | 2021-12-15 | Team A | Bonolo | Eskom Holdings SOC Ltd | Outage Services Contracts | Kepco Plant Service & Engineering, Redheads TMS Turbomaschinenservice SA (PTY) LTD, Imbanita Consulting and Engineering Services & C D R Electricac | Depletion of funds | Poor Planning | 421447580.6 | 484 382 228.80 | 0.0 | Not Supported | 2021-12-10 | 4 months | 4 months | Not Finalised |  |  | -44540 | -44540
160 | Q3 2020/21 | Rollover | 2021-12-10 | 2021-12-15 | Team A | Bonolo | Eskom Holdings SOC Ltd | Provision of management, maintenance and operational service for the power station coal supply, coal and ash handling | Eskom Rotek Industries | Failed negotiations | Lack of understanding of procurement legislation | 2214294123.89 | 8536399767.15 | 0.0 | Not Supported | 2021-12-21 | 2022-01-01 | 2022-12-31 | Finalised | 2021-12-23 |  | 13 | Finalised
161 | Q3 2021/22 | Ratification | 2021-09-16 | 2021-09-16 | Team D | Kwena Lengane | Department of Public Works and Infrastructure (DPWI) | Office accomodation for Department of Investigative Directorate Independent Police | Mayula Procurement and Property Management | Additional Space Requirement | Extension of Accommodation Leases | 4260421.52 | 12562525.17 | 0 | Conditional Support | 2020-07-23 | 2020-11-12 | 2029-03-31 | Finalised | 2021-09-30 |  | 14 | Finalised
162 | Q3 2021/22 | New | 2021-09-30 | 2021-09-30 | Team D | Glory Limane | South African National Biodiversity Institute (SANBI) | Price increase on the Afri Guard Security contract for Free State National Botanical Garden, Bloemfontein | Afri Guard Security Company | Price Increase | Poor Planning | 629265.08 | 3520598.7 | 15486.4 | Not Supported | 2021-09-30 | 2018-04-18 | 2023-03-31 | Finalised | 2021-10-04 |  | 4 | Finalised
163 | Q3 2021/22 | New | 2021-10-01 | 2021-10-01 | Team D | Glory Limane | Department of Environment, Forestry and Fisheries (DEFF) | To implement the Working on Fire Programmes | Working on Fire | Business continuity | Poor Planning | 55000000 | 350000000 | 0 | Conditional Support | 2021-10-01 | 2021-10-06 | 2022-01-05 | Finalised | 2021-10-04 |  | 3 | Finalised
164 | Q3 2021/22 | New | 2021-10-06 | 2021-10-05 | Team D | Thabile Khame | Department of Sports, Arts and Culture (DSAC) | Comprehensive Employee Health and Wellness Services | Workforce Health Care | Business continuity | Poor Planning | 158346.75 | 903042 | 152603.58 | Not Supported | 2021-09-27 | 2021-11-01 | 2022-03-31 | Finalised | 2021-11-16 |  | 41 | Finalised
165 | Q3 2021/22 | Appeal | 2021-10-08 | 2021-10-08 | Team D | Glory Limane | South African National Biodiversity Institute (SANBI) | Repairs, renovations and upgrades to various buildings in KwaZulu-Natal Herbarium in Durban | Bartsch Consult | Business continuity | Poor Planning | 1638759.36 | 477660 | 0 | Not Supported | 2021-10-06 | 2021-11-01 | 2023-06-01 | Finalised | 2021-11-04 |  | 27 | Finalised
166 | Q3 2021/22 | New | 2021-10-14 | 2021-10-14 | Team D | Kwena Lengane | Department of Public Works and Infrastructure (DPWI) | Upgrading of Civil Engineering Services: Lenasia Police Station and Lenasia Magistrate Court | Mafafo Building Construction and Kgotsong Namukelwe JV | Re-measurements | Expansion of scope (time & material) | 1368739.2 | 20741692.4 | 3760676.18 | Not Supported | 2021-09-28 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 35 | Finalised
167 | Q3 2021/22 | New | 2021-10-18 | 2021-10-18 | Team D | Thabile Khame | Finance and Accounting Services Sector Education and Training Authority (Fasset)SETA | Information and Communications Technology Systems | Solugrowth | Business continuity | Poor Planning | 5329138.17 | 14220840 | 6829707.62 | Not Supported | 2021-10-15 | 2021-11-01 | 2022-06-30 | Finalised | 2021-11-16 |  | 29 | Finalised
168 | Q3 2021/22 | Appeal | 2021-10-18 | 2021-10-18 | Team D | Kwena Lengane | Department of Public Works and Infrastructure (DPWI) | Various Activities | JFE Empowerment Group (Pty) Ltd | Variation | Poor contract management | 25036328.23 | 159318463.35 | 17750047.68 | Not Supported | 2021-10-15 | Not Stated | Not Stated | Finalised | 2021-12-03 |  | 46 | Finalised
169 | Q3 2021/22 | New | 2021-10-20 | 2021-10-20 | Team D | Glory Limane | South African Weather Service | Additional services to high-speed network access into tertiary and research network of South Africa (SANREN) | TENET | Variation | Resistance to change | 314165.41 | 414000 | 0 | Not Supported | 2021-10-20 | 2021-12-01 | 2023-03-31 | Finalised | 2021-10-22 |  | 2 | Finalised
170 | Q3 2021/22 | New | 2021-10-20 | 2021-10-20 | Team D | Thabile Khame | Pan South African Language Board (PanSALB) | Legal: Labor Related Services | Mosebi Attorneys | Variation | Inadequate market research and analysis | 461719 | 500000 | 0 | Not Supported | 2021-10-07 | 2021-06-02 | 2022-06-30 | Finalised | 2021-11-04 |  | 15 | Finalised
171 | Q3 2021/22 | New | 2021-10-26 | 2021-10-26 | Team D | Thabile Khame | Freedom Park | Facility Management | Tefla Group | Expansion | Poor contract management | 2500000 | 1900000 | 0 | Not Supported | 2021-10-25 | 2020-09-01 | 2025-09-30 | Finalised | 2021-12-14 |  | 49 | Finalised
172 | Q3 2021/22 | New | 2021-10-22 | 2021-10-25 | Team D | Thabile Khame | Agricultural Sector Education and Training Authority (AgriSETA)SETA | ICT Services | Solugrowth | Extension | Poor Planning | 1531227.4 | 34125715 | 29599726.5 | Not Supported | 2021-10-14 | 2021-12-01 | 2022-03-31 | Finalised | 2021-11-23 |  | 32 | Finalised
173 | Q3 2021/22 | New | 2021-10-28 | 2021-10-28 | Team D | Kwena Lengane | Council for Scientific and Industrial Research (CSIR) | Provision of Short Term Insurance Brokerage Services | Marsh (Pty) Ltd | Variation | Contract Extension | 23000000 | 53660608 | 0 | Closed | 2021-05-27 | 2018-04-01 | 2023-03-31 | Closed | 2021-11-30 |  | 33 | Closed
174 | Q3 2021/22 | New | 2021-10-28 | 2021-10-28 | Team D | Kwena Lengane | Council for Scientific and Industrial Research (CSIR) | Management and implementation of the Experiental Training Programme (ETP) - an annual student's placement training programme | Southern African Society for Cooperative Education (SASCE) | Expansion | Contract Extension | 427680 | 8196363 | 0 | Not Supported | 2021-10-26 | 2021-06-01 | 2022-03-31 | Finalised | 2021-11-18 |  | 21 | Finalised
175 | Q3 2021/22 | New | 2021-10-28 | 2021-10-28 | Team D | Glory Limane | Department of Environment, Forestry and Fisheries (DEFF) | National Environmental Monitors Programmer (NEMP) | SANParks | Extension | Contract Extension | 0 | 195000000 | 0 | Conditional Support | 2021-10-27 | 2021-12-01 | 2022-03-31 | Finalised | 2021-11-16 |  | 19 | Finalised
176 | Q3 2021/22 | New | 2021-10-28 | 2021-10-28 | Team D | Glory Limane | Department of Environment, Forestry and Fisheries (DEFF) | National Environmental Monitors Programmer (NEMP) | Isimangaliso | Extension | Contract Extension | 0 | 86000000 | 0 | Conditional Support | 2021-10-27 | 2021-12-01 | 2022-03-31 | Finalised | 2021-11-16 |  | 19 | Finalised
177 | Q3 2021/22 | New | 2021-11-02 | 2021-11-02 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Wellness Services | Workforce Health Care (Pty) Ltd | Extension | Failed tender processes; Restart tender processes | 1570555.23 | 14366935.02 | 2101798.96 | Supported | 2021-10-27 | 2021-11-11 | 2022-03-31 | Finalised | 2021-11-12 |  | 10 | Finalised
178 | Q3 2021/22 | New | 2021-11-02 | 2021-11-02 | Team D | Thabile Khame | Education, Training and Development Practices Sector Education and Training Authority (ETDP SETA)SETA | Accomodation Lease | Ghandi Square Holdings (Pty) Ltd | Extension | Poor Planning | 21087847.12 | 30603538.12 | 23071724 | Not Supported | 2021-10-28 | 2022-07-01 | 2024-06-30 | Finalised | 2021-11-25 |  | 23 | Finalised
179 | Q3 2021/22 | New | 2021-11-04 | 2021-11-04 | Team D | Glory Limane | South African Weather Service | Provision of spares and repair of instrumentation for the highveld Priority Network | Envirocon Instrumentation CC | Variation | Contract Extension | 588000 | 1090000 | 0 | Supported | 2021-11-04 | Not Stated | Not Stated | Finalised | 2021-11-18 |  | 14 | Finalised
180 | Q3 2021/22 | New | 2021-11-15 | 2021-11-15 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Landmark Software Licences | Imagine Communications EMEA (UK) Ltd | Extension | Failed tender processes; Restart tender processes | 15689086.88 | 11109974 | 9961325 | Conditional Support | 2021-11-12 | 2022-01-01 | 2023-06-30 | Finalised | 2021-11-23 |  | 8 | Finalised
181 | Q3 2021/22 | New | 2021-11-15 | 2021-11-15 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | SAP Software Maintenance | SAP South Africa (Pty) Ltd | Extension | Failed tender processes; Restart tender processes | 15320119.23 | 3676828.61 | 0 | Not Supported | 2021-11-14 | 2021-12-01 | 2023-12-31 | Finalised | 2021-11-23 |  | 8 | Finalised
182 | Q3 2021/22 | New | 2021-11-18 | 2021-11-18 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Ku-Band satellite space segment services | Globecast SA (Pty) Ltd | Extension | Failed tender processes; Restart tender processes | 4194234 | 28975449.81 | 3037518 | Conditional Support | 2021-11-18 | 2022-01-01 | 2022-06-30 | Finalised | 2021-11-25 |  | 7 | Finalised
183 | Q3 2021/22 | New | 2021-11-19 | 2021-11-19 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Electronic Newsroom Production System (ENPS) | Inala Broadcast Technologies | Extension | Business Continuity | 17133407.25 | 13479392.65 | 16715526 | Conditional Support | 2021-11-18 | 2021-12-20 | 2022-12-19 | Finalised | 2021-11-25 |  | 6 | Finalised
184 | Q3 2021/22 | New | 2021-12-02 | 2021-12-02 | Team D | Glory Limane | Department of Environment, Forestry and Fisheries (DEFF) | Working on fire programme | Working on Fire | Extension | Business Continuity | 660000000 | 350000000 | 165000000 | Conditional Support | 2021-12-01 | 2022-01-06 | 2023-01-05 | Finalised | 2021-12-02 |  | 0 | Finalised
185 | Q3 2021/22 | Appeal | 2021-12-06 | 2021-12-06 | Team D | Kwena Lengane | Department of Public Works and Infrastructure (DPWI) | Upgrading of Civil Engineering Services: Lenasia Police Station and Lenasia Magistrate Court | Mafafo Building Construction and Kgotsong Namukelwe JV | Re-measurements | Expansion of scope (time & material) | 1368739.2 | 20741692.4 | 3760676.18 | Conditional Support | 2021-09-28 | Not Stated | Not Stated | Finalised | 2021-12-20 |  | 14 | Finalised
186 | Q3 2021/22 | Appeal | 2021-12-07 | 2021-12-07 | Team D | Smanga Zwane | Education, Training and Development Practices Sector Education and Training Authority (ETDP SETA)SETA | Accomodation Lease | Ghandi Square Holdings (Pty) Ltd | Extension | Contract Extension | 21087847.12 | 30603538.12 | 23071724 | Conditional Support | 2021-10-28 | 2022-07-01 | 2024-06-30 | Finalised | 2021-12-20 |  | 13 | Finalised
187 | Q3 2021/22 | Appeal | 2021-12-09 | 2021-12-09 | Team D | Kwena Lengane | Council for Scientific and Industrial Research (CSIR) | Provision of Short Term Insurance Brokerage Services | Marsh (Pty) Ltd | Variation | Contract Extension | 23000000 | 56415736.62 | 0 | Conditional Support | 2021-05-27 | 2018-04-01 | 2023-03-31 | Finalised | 2021-12-21 |  | 12 | Finalised
188 | Q3 2021/22 | New | 2021-12-08 | 2021-12-08 | Team D | Kwena Lengane | National Research Foundation (NRF) | Servicing and refurbishment of a spare Leybold Turbo Mag w 2800/3200 vacuum pump | Intergrated Pump Technology (Pty) Ltd | Variation | Expansion of scope (time & material) | 202118.25 | 264684 | 0 | Conditional Support | 2021-12-08 | Not Stated | Not Stated | Finalised | 2021-12-21 |  | 13 | Finalised
189 | Q3 2021/22 | New | 2021-12-14 | 2021-12-14 | Team D | Glory Limane | Small Enterprise Development Agency (SEDA) | Office Accomodation in Port Shepstone. | MYSY Property Investment CC | Extension | RFQ Process | 1607424.72 | 1688808.6 | 3284140.44 | Conditional Support | 2021-12-06 | 2022-02-01 | 2024-01-31 | Finalised | 2021-12-21 |  | 7 | Finalised
190 | Q3 2021/22 | New | 2021-12-14 | 2021-12-14 | Team D | Smanga Zwane | Department of Environment, Forestry and Fisheries (DEFF) | Hosting, maintenance and technical support services for the South African Atmospheric Emissions Licensing & Inventory Portal (SAAELIP)and the South African Greenhouse Gas Emissions Reporting System (SAGERS) | EnfoTech & Consulting. | Extension | Continuation of the existing services as there are no measures currently in place to migratethe system to the DFFE ICT environment upon expiry of the contract. | 13484015 | 29459088 | 0 | Not Supported | 2021-11-11 | Not Stated | Not Stated | Finalised | 2021-12-21 |  | 7 | Finalised
191 | Q3 2021/22 | New | 2021-12-14 | 2021-12-14 | Team D | Glory Limane | South African Tourism | Office accommodation in Japan | Akasaka Soko | Extension | Business Continuity | 2838000 | Not Stated | 0 | Not Supported | Not Stated | 2022-03-01 | 2024-03-31 | Finalised | 2021-12-21 |  | 7 | Finalised
192 | Q3 2021/22 | New | 2021-12-15 | 2021-12-15 | Team D | Smanga Zwane | South African National Space Agency (SANSA) | Document Management Solution | VM Consulting | Extension | Business Continuity | 4000000 | 10337652.75 | 0 | Conditional Support | 2021-12-15 | Not Stated | Not Stated | Finalised | 2021-12-21 |  | 6 | Finalised
QUARTER 3 2021/2022
[7 empty] | Total number of Expansion/Contract Modification requests received : |  | 192
Incorrect Reporting
[7 empty] | Actual Received |  | 192
[7 empty] | Applications finalised after Q3 |  | 0
[7 empty] | Number of Expansion/Contract Modification - Not Finalised todate: |  | 23
[7 empty] | Total number of Expansion/Contract Modification requests reviewed: |  | 169
88.02%
Signature______________________________________________
Reviewed expansions (Current quarter) |  |  | 135
Reviewed appealed expansions |  |  | 18
Reviewed ratified expansions |  |  | 0
Reviewed expansions (Previous quarter) |  |  | 14
Total reviewed expansions |  |  | 167
Total withdrawn expansions |  |  | 0
Expansions not yet reviewed (BLANK) |  |  | -167
Total number of expansions received: |  |  | 0