## EXPANSIONS REPORT
552 GOVERNANCE MONITORING AND COMPLIANCE: 2022/2023 QUARTER 3 REPORT EXPANSIONS | [23 empty] | EXPANSION SUBMISSIONS TRACKING TOOL | [8 empty] | ADDITIONAL INFORMATION
EXPANSIONS REPORT
Number | Period / Quarter | Rollover / New (Use dropdown List) | Date Received By GMC (yyyy/mm/dd) | Date Cases Allocated To Team Member (yyyy/mm/dd) | Team Allocation (Use dropdown List) | Team Member | Entity/Department (Use dropdown List) | Project Description | Supplier / Service Provider | Reason for Expansion (Use dropdown List) | Root Causes (Use dropdown List) | Value of Contract Expansion [R] | Original Contract Value [R] | Value of Pevious Expansion [] | not supported/not supported/Conditional supported (Use dropdown List) | Award/recommended by AO/ AA date (yyyy/mm/dd) | Contract start date (yyyy/mm/dd) | Contract expiry (yyyy/mm/dd) | Status (Use dropdown List) | Application Signed Date (yyyy/mm/dd) | Comments | Not finalised cases by allocated individual | AGE ANALYSIS NUMBER OF DAYS EXPANSION NOT FINALISED BY ALLOCATED INDIVIDUAL | Date Expansion (yyyy/mm/dd): Submitted to CD: GMC | AGE ANALYSIS: NUMBER OF DAYS SINCE ALLOCATED EXPANSION SUBMITTED TO CD | Expansion Date (yyyy/mm/dd): Checked by Chief Director | AGE ANALYSIS: NUMBER OF DAYS TO FINALISE EXPANSIONS BY CHIEF DIRECTOR: GMC | Comments | Expansion Submission Date (yyyy/mm/dd): To Chief Procurement Officer (CPO) | AGE ANALYSIS NUMBER OF DAYS SINCE SIGNED EXPANSION SUBMITTED TO OCPO | Reviewed Expansion on Return Date (yyyy/mm/dd): From Chief Procurement Officer (CPO) | Comments | Date Signed (yyyy/mm/dd) | Not finalised cases by allocated individual | AGE ANALYSIS NUMBER OF DAYS DEVIATION REPORT RECEIVED | Actual Amount Not Supported | Actual Amount Conditional Supported | Total amount Pending, Noting, Closing & Other | DROPDOWN LISTS
1 | Q3 2022/23 | New | 2022-10-06 | 2022-10-06 | Team A | Jefferson | South African Social Security Agency | Cleaning and Sanitation Services contract between SASSA Head Office and Staza Cleaning Services (PTY) LTD for a period of one month (1 - 31 October 2022 | Staza Cleaning Services | Finalization of procurement process | Extensions on current contracts due to new tender processes not concluded in time | 271084.7 | 2678246.07 | 575693.6 | Noting | 2022-09-23 | 2022-01-10 | 2022-10-30 | Reported
2 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | Government Printing Works | 105 000 Kg of 80gsm 880mm Bond White paper reels | Mondi | Reels only come in one size and cannot be cut | Easy way out (making deviations normal way of procurement) | 18464 | Not stated | Not stated | Within AA/AO mandate Noting | 2022-09-14 | Not stated | Not stated | Reported
3 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | Government Printing Works | 12 000 KG of Sentinel Honey 160gsm white security 45mm certificate paper for Namibia | Enstra | Reels only come in one size and cannot be cut | Easy way out (making deviations normal way of procurement) | 78793.33 | Not stated | Not stated | Within AA/AO mandate Noting | 2022-09-27 | Not stated | Not stated | Reported
4 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | AccPac License | AccTech Systems | Alignment of 2have same ending date before Oracle Fusion ERP system implementation | Poor contract management | 163056.58 | 237172.92 | 0 | Noting | 2022-10-31 | 2019-04-01 | 2022-02-28 | Reported
5 | Q3 2022/23 | New | 2022-10-18 | 2022-10-18 | Team C | Lindani | South African Revenue Service | Acquisition of 32 additional paking bays at the Witbank Banch Office | Uhuu Pofessional Electical Contactos (Pty) Ltd | Staff paking | Easy way out (making deviations nomal way of pocuement) | 576408.75 | 21360419.77 | 30666270.45 | Within AA/AO mandate Noting | 2022-01-08 | 2022-01-08 | 31/07/2024 | Reported
6 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Air Cargo services | Docex | The objective of the request is to extend the contract for Bid Air cargo on a month to month basis whilst the tender process is being finalised | Easy way out (making deviations normal way of procurement) | 1000000 | 1000000 | 1000000 | Within AA/AO mandate Noting | 2022-08-04 | 2022-08-01 | 2023-03-31 | Reported
7 | Q3 2022/23 | New | 2022-10-05 | 2022-10-05 | Team B | Sbusiso | Transport Education Training Authority (TETA)SETA | An Integrated Management Information System (MIS) And Commercially Off-The Shelf (Cots) ERP Solution/s | Solugrowth (Pty) Ltd | Continuity of Service | Business continuity | 5243491.29 | 7026960 | 7504587.8 | Noting | 2022-03-31 | 2022-04-01 | 2022-06-30 | Reported
8 | Q3 2022/23 | New | 2022-10-17 | 2022-10-17 | Team D | Thabile Khame | Ditsong: Museums of Africa | Appointment of a service provider to provide twenty-four hour security service to Ditsong Museums of South Africa (DMSA) for a period of thirty-six (36) months | Senegal Security | DMSA is in discussion with DPWI and are considering working with them for the total facilities management contract which includes soft services- cleaning and security. In light of DPWI's agreement for DMSA to participate in the TFM services, DMSA decided to not procees with the tender for security service | Poor performance (Service delivery and APP targets) | 9886647.83 | 49185196.56 | 0 | Within AA/AO mandate Noting | Not Stated | 2022-11-01 | 2023-04-30 | Reported
9 | Q3 2022/23 | New | 2022-10-17 | 2022-10-17 | Team B | Fikile | Ports Regulator of South Africa | appointment of a service provider to render company secretariat services for a period of four months | Mashobane Advisory services | Recruitment process of the permanent secretariat is underway | Business continuity | 103829.75 | 155744.64 | 51914.88 | Noting | 2022-06-28 | 2022-09-01 | 2022-12-31 | Reported
10 | Q3 2022/23 | New | 2022-10-17 | 2022-10-17 | Team B | Fikile | Ports Regulator of South Africa | appointment of a service provider to render company secretariat services for a period of two months | Mashobane Advisory services | Recruitment process of the permanent secretariat is underway | Business continuity | 51914.88 | 155744.64 | 0 | Noting | 2022-06-28 | 2022-07-01 | 2022-08-31 | Reported
11 | Q3 2022/23 | New | 2022-10-17 | 2022-10-17 | Team D | Thabile Khame | Ditsong: Museums of Africa | APPOINTMENT OF INTERNAL AUDITORS TO UNDERTAKE AN AD HOC ASSIGNMENT / SPECIAL INVESTIGATION INTO SCM FOLLOWING FROM ALLEGATIONS CONTAINED IN THE WHISTLEBLOWER REPORT | OMA CHARTERED ACCOUNANTS | DMSA RECEIVED A WHISTLEBLOWER REPORT AND THE AD HOC ASSIGNMENT / SPECIAL INVESTIGATION SEEKS TO DETERMIINE THE VERACITY OF THE ALLEGATIONS AS THEY RELATE TO SERVICE PROVIDERS WHO MAY STILL BE APPOINTED/CONTRACTED TO DMSA | Preferred Supplier / Single Source | 200427.75 | 5427860.41 | 0 | Within AA/AO mandate Noting | Not Stated | 2022-10-06 | Not Stated | Reported
12 | Q3 2022/23 | New | 2022-11-21 | 2022-11-21 | Team B | Manqoba | Office of the Valuer-General (OVG) | APPOINTMENT OF SUITABLE ICT PROFESSIONAL SERVICE PROVIDER ACCREDITED ON SITA CONTRACT NO 1183 TO PROVIDE HUMAN RESOURCE FOR OVG | Datacentrix | ICT Resource to perform remunerative overtime for the period of 18 August to 18 November 2022 for the recovery and restoration of ERP System | Expansion of scope (time & material) | 147059.72 | 6 998 981,21 | 0,00 | Noting | 2022-08-18 | 2022-08-18 | 2022-11-18 | Reported
13 | Q3 2022/23 | New | 2022-11-21 | 2022-11-21 | Team B | Manqoba | Office of the Valuer-General (OVG) | APPOINTMENT OF SUITABLE ICT PROFESSIONAL SERVICE PROVIDER ACCREDITED ON SITA CONTRACT NO 1183 TO PROVIDE HUMAN RESOURCE FOR OVG | Datacentrix | Contract extension of the current contract for the IT application Support Analyst resource for the period of 01 January until 30 June 2024 | Expansion of scope (time & material) | 0 | 0,00 | 0,00 | Noting | 2022-08-18 | 2022-08-18 | 2024-06-30 | Reported
14 | Q3 2022/23 | New | 2022-09-28 | 2022-09-28 | Team D | Kwena Lengane | Council for the Built Environment (CBE) | Approval granted for a price and period extension of three months for the contract on Internet Services | X-DSL Networking Solutions (Pty) Ltd | The CBE is in the process of planning its office relocation. The contract was extended to ensure that there are internet services whilst the relocation is being finalised. | Business continuity | 33424.46 | 396642.84 | 56670.27 | Within AA/AO mandate Noting | 2022-08-03 | 2022-08-04 | 2022-11-03 | Reported
15 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petros | National Treasury | Approval to increase first year license maintenance fee of the BMC Control M Job Scheduling tool | Blue Turtle Technologies (Pty) Ltd | To increase first year license maintenance fee | Easy way out (making deviations normal way of procurement) | 75169.8 | 841 911,76 | 0,00 | Within AA/AO mandate Noting | 2022-07-28 | 2022-07-31 | 2025-07-30 | Reported
16 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Ash Plant Cleaning for 6 months at Tutuka Power Station | Lesemola Transport and Projects | Contract Extension | Contract Extension | 7776086.74 | R7 120 680.00 | R0.00 | Noting | 2022-09-09 | 2022-06-23 | 2022-12-12 | Reported
17 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Ash Plant Maint Monthly Fixed Cost | African Commodity Handling PRO | Contract Extension | Contract Extension | 9329898.6 | R6 164 262.51 | R2 163 872.48 | Noting | 2022-10-14 | 2022-04-01 | 2022-12-22 | Reported
18 | Q3 2022/23 | New | 2022-12-02 | 2022-12-02 | Team C | Lindani | South African Revenue Service | Benoni TPS office | Growthpoint Securitization Warehouse Trust | Expansion of the lease agreement between SARS and Growthpoint Securitization Warehouse Trust, in relation to the leasing out of office space at the Lakeside Mall, for a period of one (1) year, with an option for early exit. | Easy way out (making deviations normal way of procurement) | 463404 | 564144 | 0,00 | Within AA/AO mandate Noting | 2022-12-01 | 2023-01-01 | 2023-12-31 | Reported
19 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Knowledge | South African Health Products Regulatory Authority (SAPHRA) | Board strategy planning | Travel With Flair | Additioanl conference packaging | Business continuity | 8240 | 34775 | 0 | Noting | 2022-09-26 | 2022-09-29 | 2022-09-30 | Reported
20 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Boiler and Turbine Cleaning at Tutuka Power Station | Lesemola Transport and Projects | Contract Extension | Contract Extension | 8624259.6 | R4 196 522.46 | R0.00 | Noting | 2022.10.05 | 2022.04.07 | 2022.10.06 | Reported
21 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Inkomati-Usuthu Catchment Management Agency (IUCMA) | Bushbuckride office lease | Sheerprops 100 (pty) Ltd | Continuiity of service | Poor Planning | 77326.12 | 258743.52 | 0 | Noting | 2022-10-31 | 2021-11-01 | 2022-10-31 | Reported
22 | Q3 2022/23 | New | 2022-10-06 | 2022-10-06 | Team A | Jefferson | South African Social Security Agency | Call Centre Extension fo 3 months Oct to Dec 2022 Call Centre Extension fo 3 months Oct to Dec 2022 | Ison | Finalization of procurement process | Extensions on current contracts due to new tender processes not concluded in time | 14748750 | 2949500 | 29497500 | Noting | 2022-09-23 | 2022-01-10 | 2022-12-31 | Reported
23 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | Caseware System licences and support for the compilation of Annual Financial Statements | AdaptIT | Extension of the contract due to delay in the finalisation of the ERP tender | Poor Planning | 160725.08 | 963349.5 | 711818 | Noting | 2022-10-31 | 2017-12-01 | 2023-12-01 | Reported
24 | Q3 2022/23 | New | 2022-12-01 | 2022-12-01 | Team C | Lindani | Independent Regulatory Board for Auditors | Catering | The Catering Lark | Variation of Contract | Easy way out (making deviations normal way of procurement) | 2737 | 10 651,00 | 10 651,00 | Within AA/AO mandate Noting | 2022-10-31 | 2022-11-02 | Once Off | reported
25 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cleaning and gardening services -Groblersdal Zone | Utshalomali Cleaning and Hygiene Solutions (Pty) Ltd | Contract Extension | Contract Extension | 474295.06 | 280684.8136 | 0 | Noting | 2022-08-18 | 2022-08-19 | 2022-10-18 | Reported
26 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cleaning and gardening services -Lephalale Zone | Utshalomali Cleaning and Hygiene Solutions (Pty) Ltd | Contract Extension | Contract Extension | 570375.94 | 162939.2073 | 0 | Noting | 2022-08-18 | 2022-08-19 | 2022-10-18 | Reported
27 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cleaning and gardening services -Polokwane Zone | Utshalomali Cleaning and Hygiene Solutions (Pty) Ltd | Contract Extension | Contract Extension | 776406.93 | 86988.7473 | 0 | Noting | 2022-08-18 | 2022-08-19 | 2022-10-18 | Reported
28 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cleaning and gardening services -Thohoyandou Zone | Utshalomali Cleaning and Hygiene Solutions (Pty) Ltd | Contract Extension | Contract Extension | 596158.5 | 106927.875 | 0 | Noting | 2022-08-18 | 2022-08-19 | 2022-10-18 | Reported
29 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cleaning and gardening services -Tzaneen Zone | Utshalomali Cleaning and Hygiene Solutions (Pty) Ltd | Contract Extension | Contract Extension | 493521.04 | 87128.3945 | 0 | Noting | 2022-08-18 | 2022-08-19 | 2022-10-18 | Reported
30 | Q2 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | Cleaning Services | People's Choice Projects (Pty) Ltd | Expand contract on duration and cost: Due to procurement halt and TCTA new office premises | Poor Planning | 560385.51 | 605810.53 | 0 | Noting | 2022-10-31 | 2022-01-01 | 2022-05-31 | Reported
31 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | Cleaning Services | People's Choice Projects (Pty) Ltd | Expand contract on duration and cost: Due to procurement halt and TCTA new office premises | Poor Planning | 364176.31 | 605810.53 | 560385.51 | Noting | 2022-10-31 | 2022-01-01 | 2023-01-31 | Reported
32 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Cooling Towers | Industrial Water Cooling | Mod to increase quantity and value due to estimation on contract award not sufficient | Contract Extension | 157407495.7 | R32 551 873.79 | 0 | Noting | 2022-10-13 | 2021-11-19 | 2025-11-18 | Reported
33 | Q3 2022/23 | New | 2022-11-30 | 2022-12-13 | Team B | Hulisani | Road Accident Fund (RAF) | Countinuation of service | ICAS (Pty)Ltd | Continuity of Service | Business continuity | 1219500 | 15022741.13 | 0 | Noting | 2022-11-15 | 2022-10-15 | 2025-08-31 | Reported
34 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team B | Hulisani | Lepelle Northern Water | Countinuation of service | AECI Water and Indlela Conultants | Continuity of Service | Business continuity | 976888.05 | 35167969.91 | 0 | Noting | 2022-12-15 | Not stated | Not stated | Reported
35 | Q3 2022/23 | New | 2022-11-30 | 2022-12-13 | Team B | Hulisani | Road Accident Fund (RAF) | Countinuation of service | Mphosa Construction Projects (Pty)Ltd T/A Mphosha Security Services | Continuity of Service | Business continuity | 959904.88 | 13347398.03 | 0 | Noting | 2022-11-15 | 2022-11-01 | 2023-06-06 | Reported
36 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team B | Hulisani | Lepelle Northern Water | Countinuation of service | Ndulamiso Auqa Solutions | Continuity of Service | Business continuity | 244061.94 | 35167969.91 | 0 | Noting | 2022-12-15 | Not stated | Not stated | Reported
37 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | Courier Services | Skynet South Africa | NT Transversal Contract could not be utilised as the contract is coming to an end soon. New tender to be advertised before end of November 2022. | Business continuity | 825000 | Per usage of current | Not Stated | Noting | 2022-11-09 | 2019-01-02 | 31/01/2022 | Reported
38 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team B | Manqoba | Department of Transport (DOT) | Development of a public Transport Subsidy Policy | Future of Transport Consulting | Reappointment of Future of Transport Consulting to develop a public Transport subsidy Policy at no cost with the remaining budget of R469 966.61 | Contract Extension | 468966.61 | 4 203 427,91 | 0,00 | Noting | 2022-09-14 | 2022-09-23 | 2023-04-30 | Reported
39 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team B | Manqoba | Department of Transport (DOT) | Development of the White Paper on National Rail Policy and the National Rail Bill | RCS-SMEC-MNS | Cost extension of current contract for a period of five months due to an increase in the scope of work which amounts to 9.7% variation of the original contract price | Contract Extension | 1032516 | 10 600 000,00 | 0,00 | Noting | 2019-03-18 | 2022-08-25 | 2022-12-31 | Reported
40 | Q3 2022/23 | New | 2022-09-22 | 2022-09-23 | Team B | Hulisani | Perishable Products Export Control Board (PPECB) | Dynamics 365 Implementation | Altron Karabina | Revised MCS Proposal | Business continuity | 269098.85 | 25767130 | 1459401.79 | Noting | 2021-06-02 | 2021-07-01 | 2026-06-30 | Reported
41 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Knowledge | South African Health Products Regulatory Authority (SAPHRA) | EMP Tax calculation | Icon Business Solutions | Additional services required to finalise the tax year end process | Business continuity | 143500.24 | 287500 | 0 | Noting | 2022-08-24 | 2022-09-01 | 2023-08-31 | Reported
42 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Engineering and support on the procol P13/P14/PF DCS system on units 1-6 at Arnot Power Station for the period of 36 months | ABB South Africa (Pty) Ltd | Contract Extension | Contract Extension | 38397662.64 | R7 041 948.02 | R0.00 | Noting | 2022-10-13 | 2022-07-01 | 2025-07-01 | Reported
43 | Q3 2022/23 | New | 2022-10-19 | 2022-10-19 | Team C | Lindani | Home Affairs | epositioning Pogamme Management Office (PMO) scope vaiation and esoucing fo the Digitisation poject | SMEC | esoucing of the epositioning PMO team to accommodate the Digitisation poject | Easy way out (making deviations nomal way of pocuement) | 0 | 14513816 | N/A | Within AA/AO mandate Noting | 2021-09-30 | 2021-11-01 | 2024-10-31 | Reported
44 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | ERE Facilities Management Services (non-technical services) for Aliwal North zone. | Ngqutuka Transport Services | Allow time to follow tendering process effectively to establish a new contract | Contract Extension | 8840599.84 | 1199863.84 | R 741 983.51 | Noting | 2019-05-02 | 2019-06-01 | 2023-03-31 | Reported
45 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | ERE Facilities Management Services (non-technical services) for East London zone | Nozinga Group (Pty) Ltd | Allow sufficient time to follow tendering process | Contract Extension | 18031654.33 | 2468959.44 | R 574 763.14 | Noting | 2019-04-04 | 2019-05-03 | 2023-03-31 | Reported
46 | Q3 2022/23 | New | 2022-10-25 | 2022-10-25 | Team C | Lindani | South African Revenue Service | EX 023/2022 - The Renewal of Suse Linux and Suse Manager Maintenance and Support | Axiz PTY LTD | impracticality | Easy way out (making deviations normal way of procurement) | 17035205.82 | Not stated | Not stated | Within AA/AO mandate Noting | 2022-10-20 | 2022-11-01 | 2027-10-31 | Reported
47 | Q3 2022/23 | New | 2022-11-23 | 2022-11-23 | Team C | Petros | Home Affairs | Extension of contract for the provision of legal assistance in Litigation, Negotiating, Drafting and concluding agreements relating to the Gijima Settlement and ABIS / Hanis matters | Edward Nathan Sonnenberg Africa (ENS) | To provide continuity for complex legal matters relating to the Gijima Settlement and ABIS / Hanis matters | Easy way out (making deviations normal way of procurement) | 0 | Usage | Usage | Within AA/AO mandate Noting | 2022-08-29 | 2022-09-01 | 2024-08-31 | Reported
48 | Q3 2022/23 | New | 2022-12-14 | 2022-12-14 | Team C | Petros | Home Affairs | Extension of contract for the provisioning of Biometric Access control management system licences as well as support and maintenance for Twelve (12) Months (1 Year). | Datacentrix-Lawtrust Consortium | To allow for a new tender process that will replace the current BACM solution | Easy way out (making deviations normal way of procurement) | 56996232 | 189 101 961,30 | 0,00 | Within AA/AO mandate Noting | 2022-11-30 | 2022-12-01 | 2023-11-30 | Reported
49 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team B | Sbusiso | Inkomati-Usuthu Catchment Management Agency (IUCMA) | extension of office space for two months | Marxsa properties Pty Ltd | COntinuityof service. the bid has been awarded however pertitioning has not been complated | Business continuity | 1147302.04 | R5661002,40 | R3453966\,60 | Noting | 2022-11-30 | 2022-12-01 | 2023-01-31 | Reported
50 | Q3 2022/23 | New | 2022-12-14 | 2022-12-14 | Team C | Petros | Home Affairs | Extenstion of contract for Provision of security gaurding services in Free State | Mafoko Patrols | To allow for a new open tender process to be finalised | Easy way out (making deviations normal way of procurement) | 548268.44 | 18 851 637,24 | 0,00 | Within AA/AO mandate Noting | 2022-10-31 | 2022-11-01 | 2022-11-30 | Reported
51 | Q3 2022/23 | New | 2022-12-14 | 2022-12-14 | Team C | Petros | Home Affairs | Extenstion of contract for Provision of security gaurding services in Northern Cape | Bamogale | To allow for a new open tender process to be finalised | Easy way out (making deviations normal way of procurement) | 389403.1 | 13 382 827,05 | 0,00 | Within AA/AO mandate Noting | 2022-10-31 | 2022-11-01 | 2022-11-30 | Reported
52 | Q3 2022/23 | New | 2022-11-23 | 2022-11-23 | Team C | Petros | Home Affairs | Extention of contract to manage Front Office processing of Visa and Permit applications in South Africa and abroad | VFS Global | To allow for the completion of a Public Private Partnership process | Easy way out (making deviations normal way of procurement) | 0 | N/A | N/A | Within AA/AO mandate Noting | 2022-10-25 | 2023-01-01 | 2025-12-31 | Reported
53 | Q3 2022/23 | New | 2022-10-14 | 2022-10-14 | Team B | Sbusiso | Inkomati-Usuthu Catchment Management Agency (IUCMA) | External audit services for three financial years, i.e., 2019/20, 2020/21 and 2021/22 | Price Waterhouse Coopers (Pty) Ltd | Extended SCM reviews (Review of Bids over R5mil) | Poor Planning | 103400 | 951895.99 | 126500 | Noting | 2022-09-30 | 2020-07-01 | 2022-08-31 | Reported
54 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Facilities Management in Empangeni | Amile Projects (Pty) Ltd | Include the Newcastle Sites | Contract Extension | 15739253.13 | R4 166 893.32 | R0.00 | Noting | 2021-10-08 | 2021-10-08 | 2024-09-30 | Reported
55 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Facilities Management in PMB | Tefla Group (Pty) Ltd | Include the Area Offices Sites | Contract Extension | 15425612.15 | R8 544 696.83 | R0.00 | Noting | 2021-11-11 | 2021-11-11 | 2024-11-11 | Reported
56 | Q3 2022/23 | New | 2022-11-30 | 2022-12-13 | Team B | Hulisani | Road Accident Fund (RAF) | Finalisation of new tender | Sizwe Africa IT Group (Pty)Ltd | Continuity of Service | Business continuity | 5175371.15 | 49500000 | 0 | Noting | 2022-11-15 | 2022-12-15 | 2023-06-14 | Reported
57 | Q3 2022/23 | New | 2022-09-23 | 2022-09-23 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Forensic Investigation (Whistle Blower Report) | Khumalo and Mabuya | Continuity of Service | Business continuity | 923600 | 0 | 0 | Noting | 2022-08-01 | Not stated | Not Stated | Reported
58 | Q3 2022/23 | New | 2022-10-18 | 2022-10-18 | Team A | Jefferson | Public Protector South Africa | Gardening services for Sibasa Office for a period of ten (10) months | Monabo Hygiene Services CC | Expansion of the scope | Drafting of poor specifications (TORs) and evaluation criteria | 31178.24 | 275814.02 | 0 | Noting | Not stated | Not stated | Not stated | Reported
59 | Q3 2022/23 | New | 2022-12-15 | 2022-12-14 | Team B | Manqoba | Department of Transport (DOT) | Guarding Security Services to the Department of Transport for the period of four (4) months | Eldna Security Services | The Current Contract will expire before a new bidding process is concluded, extending the current contract will allow sufficient time to conclude the new competitive bidding process. | Business continuity | 1116775 | R5,727,352.50 | 0 | Noting | 22/09/2022 | 30/09/2022 | 31/01/2023 | Reported
60 | Q3 2022/23 | New | 2022-10-19 | 2022-10-19 | Team C | Lindani | Home Affairs | HANIS and integated Justice System (IJS) suppot and maintenance | XON Systems | Extension to include Oacle licences suppot and maintenance | Easy way out (making deviations nomal way of pocuement) | 4181298.7 | 298945522.72 | 4074298.81 | Within AA/AO mandate Noting | 2019-03-31 | 2019-04-01 | 2023-03-31 | Reported
61 | Q3 2022/23 | New | 2022-11-02 | 2022-11-02 | Team B | Hulisani | South African Civil Aviation Authority (SACAA) | Head office lease | Redefine and Growth Point | Continuity of Service | Business continuity | 85574539.93 | 56248104.24 | 45586624.23 | Noting | 2022-11-02 | 2023-01-01 | 2025-12-31 | Reported
62 | Q3 2022/23 | New | 2022-11-04 | 2022-11-04 | Team D | Kwena Lengane | National Research Foundation (NRF) | Hiring of off-site research equipment | University of Cape Town | Between July and August 2022, iThemba LABS sent much more samples than anticipated, due to increases of research and the total charges for the Hiring exceeded the remaining value left under the contract. | Expansion of scope (time & material) | 18486 | 100000 | 0 | Within AA/AO mandate Noting | 2022-10-01 | 2021-09-21 | 2022-09-20 | Reported
63 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | HM Security and Armed Response | Physical Security and Guarding FOR Nelspruit Regional Office | Addidtional Guards needed to beef up security services after barglury incidents attempts in the office | Business continuity | 164427 | R962 136.00 | Not Stated | Noting | 2022-11-09 | 17/05/2021 | 16/05/2024 | Reported
64 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Home work home transport for employees | Naremotho Trading Enterprise CC | Modification 1 | Contract Extension | 2072508.48 | Not stated | Not stated | Noting | 2022.06.06 | Not stated | Not stated | Reported
65 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Home work home transport for employees | Naremotho Trading Enterprise CC | Modification 1 | Contract Extension | 15966713 | 4400000 | 2072508.48 | Noting | 2022-06-06 | 2018-09-01 | 2023-08-31 | Reported
66 | Q3 2022/23 | New | 2022-10-18 | 2022-10-18 | Team A | Jefferson | Public Protector South Africa | Hosting, support and maintenance for Mobile Referral Application | The Innovation Hub Management Company | Contract Extension | Drafting of poor specifications (TORs) and evaluation criteria | 66930 | 447434.9 | 0 | Noting | Not stated | Not stated | Not stated | Reported
67 | Q3 2022/23 | New | 2022-09-16 | 2022-09-16 | Team B | Knowledge | National Youth Development Agency (NYDA) | Human Resource Management system which engages new employees, maintains, and updates changes, and termination of employees, VIP Payroll | Sage VIP | Continuity of Service | Exceeding the 15%/R15m or 20%/R20m threshold for expansions (especially SOCs with large projects) | 30778 | 136736.15 | 0 | Noting | 2022-09-01 | 2022-05-01 | 2023-02-28 | Reported
68 | Q3 2022/23 | New | 2022-10-04 | 2022-10-04 | Team C | Lindani | National School of Government | IIC Panel | various suppliers | reconfigaration of organisation structure | Easy way out (making deviations normal way of procurement) | 0 | Not Stated | Not Stated | Within AA/AO mandate Noting | Not Stated | 2022-11-01 | 2023-06-30 | Reported
69 | Q3 2022/23 | New | 2022-10-05 | 2022-10-05 | Team B | Sbusiso | Transport Education Training Authority (TETA)SETA | Increase of Sage Licenses from 250 employees to 400 employees. | Msuthu Technologies | Continuity of Service | Continue using existing software | 99834.66 | 496482.6 | 0 | Noting | 2022-04-08 | Not stated | Not Stated | Reported
70 | Q3 2022/23 | New | 2022-10-05 | 2022-10-05 | Team B | Sbusiso | Transport Education Training Authority (TETA)SETA | Increase on the CTC of the resource as the quotation was percentage based | Okhela Consulting | Continuity of Service | Business continuity | 74905.86 | 367094.14 | 0 | Noting | 2022-09-22 | Not stated | Not Stated | Reported
71 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Insurance Broker | Indwe Risk Services | Possible risk of not attracting a brokering service to service SAPO's portfolio RFP could not be advertised due to Constitutional court verdict in February 2022 | Easy way out (making deviations normal way of procurement) | 927500 | 875000 | - | Within AA/AO mandate Noting | 2022-06-23 | 2022-07-01 | 2023-06-30 | Reported
72 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | IT Security Managed Services | IN2IT | A decision made by SAPO to only increase the contract for a period of 6 months and SAPO to go out on a procurement process | Easy way out (making deviations normal way of procurement) | 2672335 | 26566566 | 16539216 | Within AA/AO mandate Noting | 2022-06-09 | 2022-07-01 | 2022-12-31 | Reported
73 | Q3 2022/23 | New | 2022-12-02 | 2022-12-02 | Team A | Bonolo | South African Forestry Company Limited | JDE Support, Maintenance and Enhancement for a period of two (2) months | EOH Mthombo (Pty Ltd | Business Continuity | Contract Extension | 1176450 | 196075 | 274505 | Noting | 2022-12-01 | 2022-12-08 | 2023-02-07 | Reported
74 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Kendal Power Station Transportation of Coarse Ash | Mphegolle Trading Enterprise (Pty) Ltd | Additional Time and Value | Contract Extension | 15657772.57 | 11417000 | 0 | Noting | 2022-10-12 | 2022-08-01 | 2023-06-30 | Reported
75 | Q3 2022/23 | New | 2022-11-21 | 2022-11-21 | Team B | Manqoba | Office of the Valuer-General (OVG) | LABOUR RATES ADJUSTMENT | Zwiito | Cleaning labour rates | Expansion of scope (time & material) | 0 | 0,00 | 0,00 | Noting | 2022-07-29 | 2023-01-01 | 2024-06-30 | Reported
76 | Q3 2022/23 | New | 2022-10-12 | 2022-10-12 | Team D | Thabile Khame | Department of Sports, Arts and Culture (DSAC) | Maintenance and support on asset management system | Kreston SA Pretorian | Estimated amount bfor Maintemanve support was not included in the SLA between DSAC and Kreston SA | Poor Planning | 59800 | 407906 | 0 | Within AA/AO mandate Noting | 2022-10-03 | 2021-12-01 | 2024-11-30 | Reported
77 | Q3 2022/23 | New | 2022-10-19 | 2022-10-19 | Team C | Lindani | South African Revenue Service | Maintenance and suppot NIIS and CMS | Rakario Properties (Pty) Ltd | Contract extension between SARS and Rakario Properties (Pty) Ltd; in respect of the leasing out of office space for a period of five (5) years, commencing 01 November 2022 to 31 October 2027 with an oContract extension between SARS and Rakario Properties (Pty) Ltd; in respect of the leasing out of office space for a period of five (5) years, commencing 01 November 2022 to 31 October 2027 with an option for early exit | Easy way out (making deviations normal way of procurement) | 61286835 | 298945522.72 | 4074298.81 | Within AA/AO mandate Noting | 2022-06-10 | 2022-01-11 | 31/10/2027 | Reported
78 | Q3 2022/23 | New | 2022-10-19 | 2022-10-19 | Team C | Lindani | Home Affairs | Maintenance and suppot NIIS and CMS | Dimension Data | To allow the continuation fo maitenance and suppot of NIIS and CMS up until a new system has been put in place | Easy way out (making deviations nomal way of pocuement) | 31531816.74 | 105947302 | 124149236.06 | Within AA/AO mandate Noting | 2019-03-31 | 2019-04-01 | 2023-03-31 | Reported
79 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Maintenance of the Blowdown Compressors at Ingula Pumped Storage Scheme | Stocklog | Business Continuity | Contract Extension | 8294227.44 | 10665593.79 | 1210174.51 | Noting | 2020-09-22 | 2020-09-22 | 2020-09-30 | Reported
80 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | Marshal Nights Security | Physical Security and Guarding of Mthatha Regional Offices | Addidtional Guards needed to beef up security services after barglury incident happended in the office | Business continuity | 170274.93 | R1 038 190.80 | Not Stated | Noting | 2022-11-09 | 17/07/2021 | 16/07/2024 | Reported
81 | Q3 2022/23 | New | 2022-12-07 | 2022-12-07 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | MICT SETA website hosting, support, and maintenance services. | Cyberfox CC | The service of hosting of the website is crucial as the website is a critical communication tool with the Stakeholders. The procurement processes through RFQ was at the final stage during the extended period. However, inline with the maximisation of synergies within the state entities, MICT SETA EXCO's resolved that webhosting be completed through state Information Technology Agency’s (SITA) cloud hosting platforms. | Poor Planning | 36846 | R59 074,35 | R14 838,58 | Noting | 2021-09-01 | 2022-12-01 | 2023-02-28 | Reported
82 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | National Linehaul | Arrow Logistics | The DTT Analog switch off project deadline was extended from June 22 to September 2022 by the High court. The new Intergovernmental contract does not make provision for the delivery of pallets which is required for the DTT project. SAPO does not have cash flow as required by NT regulations and therefore cant go out on a RFQ/RFP process | Easy way out (making deviations normal way of procurement) | 11313317 | 226388529 | 69900000 | Within AA/AO mandate Noting | 2022-09-29 | 2022-10-01 | 2022-12-31 | Reported
83 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | National Linehaul | Arrow Logistics | The DTT Analog switch off project delaine was extended from end March 2022 to June 2022 by the High court. The new Intergovernmental contract does not make provision for the delivery of pallets which is required for the DTT project. NT embargo makes it practically impossible for SAPO to go out on a RFQ/RFP process | Easy way out (making deviations normal way of procurement) | 10000000 | 226388529 | 49900000 | Within AA/AO mandate Noting | 2022-04-11 | 2022-04-01 | 2022-06-30 | Reported
84 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | National Linehaul | Arrow Logistics | The DTT Analog switch off project deadline was extended from June 22 to September 2022 by the High court. The new Intergovernmental contract does not make provision for the delivery of pallets which is required for the DTT project. SAPO does not have cash flow as required by NT regulations and therefore cant go out on a RFQ/RFP process | Easy way out (making deviations normal way of procurement) | 10000000 | 226388529 | 59900000 | Within AA/AO mandate Noting | 2022-06-23 | 2022-07-01 | 2022-09-30 | Reported
85 | Q3 2022/23 | New | 2022-12-01 | 2022-12-01 | Team C | Lindani | South African Revenue Service | Nigel Lease extension | Lathitha Properties (Pty) Ltd | Expansion of the Nigel lease between SARS and Lathitha Properties (Pty) Ltd for a further period of one (1) year commencing 1 December 2022 and ending 30 November 2023, with an option for early exit pending relocation to alternative premises. | Easy way out (making deviations normal way of procurement) | 1233497.4 | 5104520,56 | 10,967,126,00 | Within AA/AO mandate Noting | 2022-11-29 | 2022-12-01 | 2023-11-30 | reported
86 | Q3 2022/23 | New | 2022-11-17 | 2022-11-17 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Office Accommodation: Eastern Cape | Mauveine Investments | No successful bidder after several advertisements | Drafting of poor specifications (TORs) and evaluation criteria | 135484.84 | 1049 040,00 | 406454,06 | Noting | 2022-10-31 | 2022-10-01 | 2022-11-30 | Reported
87 | Q3 2022/23 | New | 2022-11-17 | 2022-11-17 | Team B | Sbusiso | Manufacturing, Engineering and Related Services Sector Education and Training Authority (merSETA)SETA | Office Accommodation: Mpumalanga | De Bryn Commercial Property | No succeful bidder after several advertisement | Drafting of poor specifications (TORs) and evaluation criteria | 486578.34 | 449315,56 | 486578,34 | Noting | 2022-10-31 | 2022-10-01 | 2023-03-31 | Reported
88 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | Office accomodation | Central Vision Development | Supply and maintenance of 5x biometric readers, installation of security gates, removal of unactioned furniture, Avaya system upgrade | Poor Planning | 2044865.18 | 76748796.88 | 284175.73 | Noting | 2022-10-31 | 2022-12-01 | 2027-11-30 | Reported
89 | Q3 2022/23 | New | 2022-09-16 | 2022-09-16 | Team B | Knowledge | Road Traffic Infringement Agency (RTIA) | Office lease | Mowana Properties | Procurement process still underway | Extensions on current contracts due to new tender processes not concluded in time | 1050000 | 18000000 | 1800000 | Noting | 2022-09-09 | 2022-08-29 | 2022-11-30 | Reported
90 | Q3 2022/23 | New | 2022-11-08 | 2022-11-08 | Team D | Glory Limane | Small Enterprise Development Agency (SEDA) | Office Lease: Seda Swellendam Branch | Wolfaardt Trust | Seda requested quotation from service providers for benchmarking purposes and the current landlords proposal was the lowest. | Extension of Accommodation Leases | 49498 | 495491 | 386560 | Within AA/AO mandate Noting | 2022-07-25 | 2022-11-01 | 2024-10-31 | Reported
91 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team C | Lindani | South African Revenue Service | Pest Control Management | 1. Kusile Hygiene and Industrial Services 2. Masana Hygiene Services 3. Supercare Hygiene | The extension of RFP 14/2019 – Provision of Integrated Pest Control Management Services for all SARS offices, Nationwide for a period of twelve (12) months effective 01 December 2022 to 30 November 2023 | Easy way out (making deviations normal way of procurement) | 2420273.73 | 6 567 596,80 | 0,00 | Within AA/AO mandate Noting | 2022-11-22 | 2022-12-01 | 2023-11-30 | Reported
92 | Q3 2022/23 | New | 2022-09-20 | 2022-09-20 | Team C | Lindani | Centre for Public Service Innovation | Point to data connectivity service | Ubuntu Technologies | Single source | Preferred Supplier / Single Source | 82828.68 | 82828.7 | 0 | Within AA/AO mandate Noting | 2022-09-19 | Not stated | Not stated | Reported
93 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Preparation of Annual Financial Statements | Kreston Pretoria | The RFP was issued for a period of 2 years and only awarded for a period of 1 year due to the moratorium on multi year contracts. The extension is for the 2nd year | Easy way out (making deviations normal way of procurement) | 3675000 | 3815000 | - | Within AA/AO mandate Noting | 2022-08-30 | 2023-02-01 | 2023-11-30 | Reported
94 | Q3 2022/23 | New | 2022-10-25 | 2022-10-25 | Team C | Lindani | South African Revenue Service | Prinsman Parking lease extension | Octodec Investments Ltd | The extension of a lease agreement between SARS and Octodec Investments Ltd for five (5) parking bays within the Prinsman parking space. The extension will be for a period of five (5) years commencing from 1 October 2022 until 30 September 2027. | Easy way out (making deviations normal way of procurement) | 309504.77 | 231101.31 | Not stated | Within AA/AO mandate Noting | 2022-09-27 | 2022-10-01 | 2027-09-30 | Reported
95 | Q3 2022/23 | New | 2022-10-24 | 2022-10-24 | Team D | Kwena Lengane | National Research Foundation (NRF) | Procurement of an Occupational and Environmental Radiation Protection Dosimetry Service for NRF iThemba Labs in Faure, Western Cape, South Africa | SABS Commercial | The compilation and finalisation of the specification took longer than anticipated and to mitigate any possible delays during the period of evaluation and the process of recommending a bidder, within the last active period of the contract, the End-User is requesting that the current contract for Occupational and Environment Radiation Protection Dosimetry be extended from 01 November 2022 to 31 January 2023, to allow for the completion of the SCM awarding process. | Business continuity | 0 | 237255.3 | 0 | Within AA/AO mandate Noting | 2022-10-17 | 2022-11-01 | 2023-01-31 | Reported
96 | Q3 2022/23 | New | 2022-10-14 | 2022-10-14 | Team B | Sbusiso | Safety and Security Sector Education and Training Authority (SASSETA)SETA | Provision and implementation of an integrated management information system t | Solugrowth (Pty) Ltd | Extension of scope of work to include MER module for effective and efficient reporting of performance information | Expansion of scope (time & material) | 67103 | 8047975.76 | 12544047.28 | Noting | 2022-09-05 | 2022-09-05 | 2023-12-31 | Reported
97 | Q3 2022/23 | New | 2022-09-20 | 2022-09-20 | Team D | Kwena Lengane | National Research Foundation (NRF) | Provision of front-end software development services to complete the implementation of the NRF Connect system | Devson Software Pty Ltd | An expansion on the original contract is requested based on the list of outstanding scope of work in the development inventory. SAWS expanded the scope of the contract to include cross connect services | Lack of understanding of procurement legislation | 293250 | 488750 | 0 | Within AA/AO mandate Noting | 2022-09-13 | 2022-07-05 | 2023-07-31 | Reported
98 | Q3 2022/23 | New | 2022-12-09 | 2022-12-09 | Team B | Knowledge | Water Research Commission (WRC) | Provision of legal services for the office of the CEO and Board | R Masilo Attorneys | Continuity of Service | Business continuity | 750000 | 250000 | 0 | Noting | 2022-10-15 | 2022-10-01 | 2023-09-30 | Reported
99 | Q3 2022/23 | New | 2022-10-18 | 2022-10-18 | Team B | Knowledge | Water Research Commission (WRC) | Provision of legal support support services to the office of the CEO and the Board | R Masilo Attorneys | Continuity of Service | Business continuity | 250000 | 750000 | 0 | Noting | 2022-09-29 | 2022-10-01 | 2023-09-30 | Reported
100 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team C | Lindani | Government Pensions Administration Agency | Provision of multiprotocol label switch services (MPLS) | MTN Business | tender process is underway, through SITA | Extensions on current contracts due to new tender processes not concluded in time | 60205103.39 | 32 380 923,34 | 50 689 314,28 | Within AA/AO mandate Noting | 28/10/2022 | 2022-01-11 | 31/10/2024 | Reported
101 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Provision of office moves and services at Megawatt Park (MWP), Lobedu,ERIC building in Rosherville and Eskom Academy of Learning (EAL | I Moves SA (Pty) Ltd | Modification 1, to increase value | Contract Extension | 1381528.8 | R2 181 528.80 | R0.00 | Noting | 04.05.2022 | 05.05.2022 | 04.05.2025 | Reported
102 | Q3 2022/23 | New | 2022-10-24 | 2022-10-24 | Team D | Kwena Lengane | National Research Foundation (NRF) | Provision of Payroll Management for incumbents of contracted programmes for three years | Foundation for Professional Development | The proposed contract extension will enable the current service provider to run the tax year end reports. Moving to a new Service Provider at the start of the tax calendar year is the ideal time to transition | Resistance to change | 128986 | 1086899 | 0 | Within AA/AO mandate Noting | 2022-10-14 | 2022-11-01 | 2023-02-28 | Reported
103 | Q3 2022/23 | New | 2022-09-22 | 2022-09-22 | Team D | Glory Limane | South African Weather Service | Provision of Proofreading Services for the SAWS Annual Report 2021/2022 | EPICREATIVE | The South African Weather Service (SAWS) appointed EPICREATIVE through a competitive RFQ process for the compilation of a list of acronyms based on 120 pages of MS Word text for parts A to D of the SAWS annual report for 2021/2022. EPICREATIVE satisfactorily did the first round of proofreading, copy editing and text ordening on the MSWord document. The scope of work was extended by 166,5 pages, resulting in a 133% increase in the scope of work. However, EPICREATIVE reduced their costs from R184 to R92 per page for the extended scope that resulted in a 69% variance in the value of the original order | Poor Planning | 15318 | 22080 | 0 | Within AA/AO mandate Noting | 2022-08-16 | Not stated | Not stated | Reported
104 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | Provision of QS Services for period of 12 months | Nelvic Projects | Contract Extension | Contract Extension | 844800 | R352 000.00 | 0 | Noting | 2022-10-18 | 2021-11-01 | 2023-04-01 | Reported
105 | Q3 2022/23 | New | 2022-10-13 | 2022-10-13 | Team D | Glory Limane | South African Weather Service | Provision of SANReN network used by the South African Weather Service | TENET | SAWS expanded the scope of the contract to include cross connect services to save cost,by avoiding that each of the service providers listed below: i. Enterprise APN to Vodacom; ii, Enterprise APN to MTN iii, Hosted PABX for HQ to iConnect Silicon Sky VoIP | Business continuity | 84628.5 | 414400 | 0 | Within AA/AO mandate Noting | 2022-09-29 | 2022-09-29 | 2023-03-31 | Reported
106 | Q3 2022/23 | New | 2022-12-07 | 2022-12-07 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Recruitment services | Mastech General Trading Pty Ltd | The services of temporary finance administarors is crucial for the organisation due to increasing volume of payment requests processed by the organisation leading to incapacitation of the Finance Division. | Poor Planning | 207000 | R414 000,00 | 0 | Noting | 2022-06-01 | 2022-11-01 | 2021-02-28 | Reported
107 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Gqeberha Regional Office | Upview General Trading | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 59965.87 | 1049403,07 | 149914,72 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
108 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Kimberley Regional Office | Randgate Fleet Management | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 102336.38 | 1400200,01 | 255840,96 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
109 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the North West Regional Offices | Randgate Fleet Management | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 109551.23 | 1836646,5 | 275373,08 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
110 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Polokwane Regional Office | Calvary Cleaning Services | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 65442.82 | 1145249,53 | 163607,05 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
111 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Springbok Regional Office | Samagaba Cleaning Services | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 35691.2 | 536935,6 | 89228,01 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
112 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Welkom Regional Office | Calvary Cleaning Services | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 71471.84 | 1250757,4 | 178679,65 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
113 | Q3 2022/23 | New | 2022-11-28 | 11/128/2022 | Team B | Manqoba | Department of Mineral Resources and Energy (DMRE) | Render cleaning services, hygiene services, pest/fumigation control and food service aid in the Witbank Regional Office | Calvary Cleaning Services | Procurement process not finalised prior to expiry of the existing contract | Contract Extension | 70821.18 | 1239370,7 | 177052,96 | Noting | 2019-05-22 | 2019-06-01 | 2023-04-30 | Reported
114 | Q3 2022/23 | New | 2022-11-10 | 2022-11-10 | Team B | Knowledge | Council for Medical Schemes (CMS) | Renewal of lease agreement for a period of 1 year from 1 May 2023 | Faerie Glen Waterpark | Extension of contract while finalising the procurement process | Contract Extension | 15299608.32 | 101136898.01 | 33309113.55 | Noting | 2022-11-09 | 2023-05-01 | 2024-04-30 | Reported
115 | Q3 2022/23 | New | 2022-12-06 | 2022-12-06 | Team B | Manqoba | Central Energy Fund SOC Ltd (CEF) | Renewal of the Sage 300 ERP, BPM, VRM and Assetware system licences and provide support | AccTech System | This extension is an interim solution while Procurement runs the process of sourcing a service provider to renew Sage 300 ERP, BPM, VRM and Assetware licenses and support | Extensions on current contracts due to new tender processes not concluded in time | 352179.18 | 598353,35 | 0 | Noting | 2022-11-25 | 2022-12-01 | 2023-05-31 | Reported
116 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team C | Lindani | Financial Intelligence Centre | Request for approval for the extension of the Microsoft Enterprise agreement for Azure services for a period of three years from 1 June 2025 to 31 May 2028 | Microsft | To allow the FIC to adopt a cost-effective approach to acquire and implement additional services as and when required for periods of three years. | Easy way out (making deviations normal way of procurement) | 0 | 0,00 | 0,00 | Within AA/AO mandate Noting | 2022-12-01 | TBC | TBC | Reported
117 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team C | Lindani | Financial Intelligence Centre | Request for approval for the extension of the panel of service providers for professional services, project management, enterprise architecture and information and communications technology for a period of 12 months from 27 February 2023 to 26 February 2024 | Various Suppliers | To allow service providers that have been appointed for critical projects that are running currently and are anticipated to be finalised beyond the current panel duration, to continue in this position | Easy way out (making deviations normal way of procurement) | 0 | 0,00 | 0,00 | Within AA/AO mandate Noting | 2022-12-01 | TBC | TBC | Reported
118 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team C | Lindani | Financial Intelligence Centre | Request for approval for the extention of the contract of Intellehub for the solutions architect for a period of one year for phase 2 of the Line of Business (LOB) solutions modernisation programme | Intellehub | For a smooth continuation of these services, the contractof Intellehub must be extended for one year to secure the services on the basis thatMr Dzebu will provide these services | Easy way out (making deviations normal way of procurement) | 2313000 | 0,00 | 0,00 | Within AA/AO mandate Noting | 2022-12-02 | TBC | TBC | Reported
119 | Q3 2022/23 | New | 2022-12-13 | 2022-12-13 | Team C | Lindani | Financial Intelligence Centre | Request for the Bid Adjudication Committee to recommend the extension of the 21st Century contract period with twelve months for web-based national salary survey with no additional financial implications | 21st Century | The FIC signed a contract with 21st Century in December 2021, to provide web-based national salary survey for a period of twelve months. Upon the payment stage it was noted that the amount on the contract is not aligned to the pricing conditions as stated in the original approved submission and had to be adjsuted | Easy way out (making deviations normal way of procurement) | 0 | 0,00 | 0,00 | Within AA/AO mandate Noting | 2022-12-05 | TBC | TBC | Reported
120 | Q3 2022/23 | New | 2022-11-18 | 2022-11-18 | Team C | Lindani | Financial Intelligence Centre | Request for variation of cost for the Mondtes Holdings contract to provide payroll services for the Financial Intelligence Centre | Mondtes Holdings | To allow the procurement process to be finalised | Easy way out (making deviations normal way of procurement) | 193459.04 | 454 132,25 | 208 016.49 | Within AA/AO mandate Noting | 2022-10-27 | TBC | TBC | Reported
121 | Q3 2022/23 | New | 2022-12-01 | 2022-12-01 | Team C | Petrus | National Treasury | Request that the acting Director-General grant approval to deviate from the normal procurement process for the renewal of the Stata version upgrade and maintenance of licenses, effective from (1 Nov 22 - 31 Oct 25) | Quantec Enterprises (Pty) Ltd STATA | Quantec is the sole provider of STATA in South Afriac appointed by the original software manufacturers (OSMs) | Sole Supplier – e.g. OEM | 538044.75 | 629 595,10 | 0,00 | Within AA/AO mandate Noting | 2019-10-10 | 2019-10-31 | 2025-10-31 | reported
122 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petrus | National Treasury | Request to approve Amendments to the SITA Service Level Agreement (SLA) signed for 5 years ending 31 March 2022 | SITA (PTY) LTD | SITA verified all the services they offer to NT and found that the services depicted in section 3 hav been omitted from the initial SLA | Easy way out (making deviations normal way of procurement) | 851042.02 | 9 492 322,04 | 0,00 | Within AA/AO mandate Noting | 2022-03-30 | 2022-04-01 | 2027-03-31 | reported
123 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petrus | National Treasury | Request to approve Amendments to the SITA Service Level Agreement (SLA) signed for 5 years ending 31 March 2022 | SITA (PTY) LTD | SITA verified all the services they offer to NT and found that the services depicted in section 3 have been omitted from the initial SLA | Easy way out (making deviations normal way of procurement) | 73910.29 | 4 961 224,77 | 0,00 | Within AA/AO mandate Noting | 2022-03-30 | 2022-04-01 | 2027-03-31 | reported
124 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petrus | National Treasury | Request to approve Amendments to the SITA Service Level Agreement (SLA) signed for 5 years ending 31 March 2022 | SITA (PTY) LTD | SITA verified all the services they offer to NT and found that the services depicted in section 3 hav been omittedfrom the initial SLA | Easy way out (making deviations normal way of procurement) | 1032767 | 53 895 275,54 | 0,00 | Within AA/AO mandate Noting | 2022-03-30 | 2022-04-01 | 2027-03-31 | reported
125 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petrus | National Treasury | Request to approve price escalation for Afswitch under Managed Integrity Evaluation (Pty) Ltd | Managed Integrity Evaluation (Pty) Ltd | Annual price increase for Afiswitch only | Easy way out (making deviations normal way of procurement) | 0 | 0,00 | 0,00 | Within AA/AO mandate Noting | 2022-02-10 | 2022-04-13 | 2025-04-14 | reported
126 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | State Information Technology Agency | Request to extend current contract with SNO cleaning services cc and SITA for the Durban office for the period of four (4) months | SNO Cleaning Services CC | The replacement tender could not be published due to the moratorium on publication of new bids because of the court judgemet on the validity of the Preferential Procurement Regulations | Easy way out (making deviations normal way of procurement) | 80763.36 | 677990.73 | 0 | Within AA/AO mandate Noting | 2022-08-10 | 2022-08-26 | 2022-12-25 | Reported
127 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team C | Lindani | South African Revenue Service | RFP 41/2019 physical security extension | 1. Tshedza Protective Services CC 2. Royal Security CC 3. Fidelity Security Services (PTY) LTD 4. Wenzile Phaphama Trading and Projects CC | The extension of RFP 41/2019A- Armed Guarding, Close Protection and Tactical Response Security Services and RFP 41/2019C- National Guarding Security Services for a period of four (4) months.The extension of RFP 41/2019A- Armed Guarding, Close Protection and Tactical Response Security Services and RFP 41/2019C- National Guarding Security Services for a period of four (4) months. | Easy way out (making deviations normal way of procurement) | 49070408 | 349054385.47 | 0,00 | Within AA/AO mandate Noting | 2022-11-17 | 2022-12-01 | 2023-03-31 | reported
128 | Q3 2022/23 | New | 2022-11-07 | 2022-11-07 | Team B | Manqoba | Railway Safety Regulator (RSR) | SAGE 300 technical support services | Omni Africa | Extension of scope and time | Contract Extension | 72450 | 193200 | 0 | Noting | 2022-10-22 | 20222/11/01 | 2023-07-10 | Reported
129 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | State Information Technology Agency | Scope expansion for the upgrade of access link: psc0001-20 from 10 meg to 20 meg for the office of the public service commission (OPSC) for a period of five (5) years | Telkom SA SOC Limited | Upgrades are required as the existing network is slow and delays the rendereing of servoces to the citizens. | Easy way out (making deviations normal way of procurement) | 644462.85 | 334993.2 | 0 | Within AA/AO mandate Noting | 2021-01-18 | 2022-09-01 | 2026-01-17 | Reported
130 | Q3 2022/23 | New | 2022-10-31 | 2022-10-31 | Team B | Sbusiso | Trans-Caledon Tunnel Authority (TCTA) | Security Services | Phutadichaba Trading Enterprises | Extension to allow for the move completion, tender process and 2 additional guards | Poor Planning | 325256.62 | 6199487.2 | 1047811.54 | Noting | 2022-10-31 | 2019-06-01 | 2023-02-28 | Reported
131 | Q3 2022/23 | New | 2022-10-07 | 2022-10-07 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Security Services | S.K. SeseGolo Security Service (Pty) Ltd- Maaa0207409 | Not proided | Poor contract management | 115996.67 | 187450 | 0 | Noting | 2022-06-14 | 2022-06-15 | 2022-11-30 | Reported
132 | Q3 2022/23 | New | 2022-09-26 | 2022-09-26 | Team B | Hulisani | Road Accident Fund (RAF) | Security services | Mjayeli Security Services | Additional Security Services | Business continuity | 1819335.72 | 1881457.5 | 0 | Noting | 2022-08-01 | 2022-08-01 | 2023-01-31 | Reported
133 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Short term rental | Majories Enterprise and Somams Project JV | The new appointed suppliers required a lead time of 2 - 3 months to deliver the vehicles and the previous supplier withdrew their vehicles. There was not sufficient vehicles to assist operations | Easy way out (making deviations normal way of procurement) | 12000000 | 8500000 | 10000000 | Within AA/AO mandate Noting | 2022-11-03 | 2022-10-01 | 2023-03-31 | Reported
134 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Short term rental | Majories Enterprise and Somams Project JV | The new appointed suppliers required a lead time of 2 - 3 months to deliver the vehicles and the previous supplier withdrew their vehicles. There was not sufficient vehicles to assist operations | Easy way out (making deviations normal way of procurement) | 5000000 | 8500000 | 5000000 | Within AA/AO mandate Noting | 2022-06-23 | 2021-12-01 | 2022-11-30 | Reported
135 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Short term rental | NMP holdings | The contract with the supplier is expanded due to the preferred bidder that withdrew from the process as they could not provide the services in the KZN area | Easy way out (making deviations normal way of procurement) | 2523690 | 4711672 | 782064 | Within AA/AO mandate Noting | 2022-08-03 | 2022-08-22 | 2022-07-23 | Reported
136 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Short term rental | NMP holdings | The contract with the supplier is expanded due to the preferred bidder that withdrew from the process as they could not provide the services in the Mpumalanga area | Easy way out (making deviations normal way of procurement) | 782064 | 4711672 | - | Within AA/AO mandate Noting | 2022-07-28 | 2022-08-22 | 2022-07-23 | Reported
137 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | Short-Term Insurance Broker Services | Bathathu Risk Services | Tender awarded November 2022. extension was necessary due to NT Advisory Note on Preferential Procurement Regulations of 2017, dated 03 March 2022 instructing Public Entities not to advertise tenders but to extend them for 12 months. | Business continuity | 1262887.3 | Per asset register (R3 406 418.27) | Not Stated | Noting | 2022-11-09 | 2019-01-01 | 31/12/2021 | Reported
138 | Q3 2022/23 | New | 2022-11-04 | 2022-11-04 | Team A | Hudley | Armaments Corporation of South Africa Limited | Supply, installation and commissioning 2X rental chiller unit | Power Compressor Exchange Holdings and Pool Construction | Service provider will not be able to complete the work at the stipulated timeframes | Contract Extension | 396000 | 792000 | 0 | Noting | 2022-11-04 | 2022-03-16 | 2022-12-30 | Reported
139 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | Supply, installation and maintenance of hosted VOIP PABX (telephony) and Call Centre Management System | Broadlink (Pty) Ltd) | Tender awarded November 2022. extension was necessary due to NT Advisory Note on Preferential Procurement Regulations of 2017, dated 03 March 2022 instructing Public Entities not to advertise tenders but to extend them for 12 months. Tender was advertised multiple times. | Business continuity | 1652931.7 | R3 305 863.48 | Not Stated | Noting | 2022-11-09 | 2018-01-01 | 30/06/2021 | Reported
140 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | Supply, Installtion and and Maintenance of Wide Area Network | Jurumani Solutions Pty Ltd | Six (6) months extension was necessary so that the new supplier can be afforded time to prepare implementation. Tender was advertised twice with no luck to award timely. | Business continuity | 1822050 | 10932300,06 | Not Stated | Noting | 2022-11-09 | 2022-11-01 | 2022-10-30 | Reported
141 | Q3 2022/23 | New | 2022-10-26 | 2022-10-26 | Team D | Thabile Khame | Department of Sports, Arts and Culture (DSAC) | Support for Silape welness programme | Indingliz Advertising and marketing | Additional funds due to inclusion of athletes to the programme due to merger of Department of Arts and Culture and Sport and recreation | Transfer of strategic decision making to Treasury | 2236935 | 14912901 | 0 | Within AA/AO mandate Noting | 2022-10-21 | 2020-11-01 | 2023-10-30 | Reported
142 | Q3 2022/23 | New | 2022-10-19 | 2022-10-19 | Team C | Lindani | Home Affairs | Tansaction Adviso fo the poposed Public Pivate Patneship (PPP) fo the development of Home Affais consolidated Head Office | Utho Capital | To allow fo the completion of the PPP pocess | Easy way out (making deviations nomal way of pocuement) | 0 | 7550000 | N/A | Within AA/AO mandate Noting | 2019-04-15 | 2019-05-15 | 2025-05-14 | Reported
143 | Q3 2022/23 | New | 2022-11-29 | 2022-11-29 | Team B | Sbusiso | Private Security Industry Regulatory Authority (PSIRA) | TDP Security | Physical Security and Guarding of Centurion Head Office | Additional security guards needed due to threats identified in the top management block of offices | Business continuity | 180000 | R1 080 000.00 | Not Stated | Noting | 2022-11-09 | 17/06/2021 | 16/06/2024 | Reported
144 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30240504 | 960032341 | 120000000 | Within AA/AO mandate Noting | 2022-09-26 | 2022-08-01 | 2022-08-30 | Reported
145 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30000000 | 960032341 | - | Within AA/AO mandate Noting | 2022-10-18 | 2022-04-01 | 31 April 2022 | Reported
146 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30000000 | 960032341 | 30000000 | Within AA/AO mandate Noting | 2022-07-04 | 2022-05-01 | 2022-05-31 | Reported
147 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30000000 | 960032341 | 60000000 | Within AA/AO mandate Noting | 2022-07-30 | 2022-06-01 | 2022-06-30 | Reported
148 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30000000 | 960032341 | 90000000 | Within AA/AO mandate Noting | 2022-08-31 | 2022-07-01 | 2022-07-31 | Reported
149 | Q3 2022/23 | New | 2022-11-14 | 2022-11-14 | Team C | Lindani | South African Post Office Limited | Telkom services | Telkom | Payment of monthly Telkom services invoices for the remainder of the contract period whilst the contract review process is concluded | Easy way out (making deviations normal way of procurement) | 30000000 | 960032341 | 150240504 | Within AA/AO mandate Noting | 2022-10-18 | 2022-09-01 | 2022-09-30 | Reported
150 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team A | Bonolo | Eskom SOC Limited | The Provision of maintenance for the perimeter intrusion monitoring system in and around the Koeberg Owner controlled area at Koeberg Operating Unit | Reutech (Pty) Ltd | Contract Extension | Contract Extension | 6200159 | R1 518 865.00 | 0 | Noting | 2022-10-31 | 2017-11-01 | 2023-10-31 | Reported
151 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team B | Manqoba | Department of Transport (DOT) | To render guarding security services to the Department of Transport for the period of four months | Eldna Security Services | The current contract will expire before a new bidding process is concluded, extending the current contract will allow enough time for a competitive bidding process. | Extensions on current contracts due to new tender processes not concluded in time | 1116775 | 5 727 352,50 | 0,00 | Noting | 2022-09-22 | 2022-09-30 | 2023-01-31 | Reported
152 | Q3 2022/23 | New | 18/11/2022 | 18/11/2022 | Team C | Petrus | National Treasury | To request Acting Director-General's approval for IGR to extend and expand the scope of the current agreement with PriceWaterHouseCoopers Incorporated which is to transform executive leadership and management through coaching | PriceWaterHouseCoopers | Extend and Expand the scope of the current agreement | Easy way out (making deviations normal way of procurement) | 4161091.64 | 3 702 369,80 | 0,00 | Within AA/AO mandate Noting | 2022-02-21 | 2022-05-25 | Not yet finalised | Reported
153 | Q3 2022/23 | New | 2022-10-25 | 2022-10-25 | Team C | Lindani | South African Revenue Service | VAR 32/2022 - Variation of the Smart Access services (0800 Share call number) contract for an amount of R 62 471 829 (VAT Inclusive). | Telkom SA SOC Ltd | Variation of Value | Easy way out (making deviations normal way of procurement) | 62471829 | 241135739 | Not stated | Within AA/AO mandate Noting | 2022-10-20 | 2022-11-01 | 2024-03-31 | Reported
154 | Q3 2022/23 | New | 2022-11-25 | 2022-11-25 | Team B | Manqoba | Department of Transport (DOT) | Variation of additional of four hours for consultation services to complete the review of the Firewall rules Audit Project | Syrex (Pty) Ltd | The outstanding work needs additional four hours to conclude the firewall rules review project | Contract Extension | 5750 | 553 076,85 | 0,00 | Noting | 2022-08-30 | Not stated | Not stated | Reported
155 | Q3 2022/23 | New | 2022-12-07 | 2022-12-07 | Team B | Sbusiso | Insurance Sector Education and Training Authority (Inseta)SETA | Website hosting, maintenance and support services. | Cyberfox CC | The service of hosting of the website is crucial as the website is a critical communication tool with the Stakeholders. , this is to afford the MICT SETA adequate time to conclude the transition process. | Poor Planning | 4992.86 | R59 074,35 | R9 845,72 | Noting | 2021-09-01 | 2022-10-01 | 2022-11-30 | Reported
156 | Q3 2022/23 | New | 2022-10-18 | 2022-10-18 | Team B | Sbusiso | Media, Information and Communication Technologies Sector Education and Training Authority (MICT SETA)SETA | Website hosting, maintenance and support services. | Cyberfox CC | The service of hosting of the website is crucial as the website is a critical communication tool with the Stakeholders. It is important for MICT SETA to extend the current contact with Cyberfox to afford the MICT SETA adequate time to process and conclude the RFQ process. | Poor Planning | 9845.72 | 59074.35 | 0 | Noting | 2022-09-01 | 2022-09-01 | 2022-10-31 | Reported
157 | Q3 2022/23 | New | 2022-12-15 | 2022-12-14 | Team B | Manqoba | Department of Transport (DOT) | Standby Tug Agreement for Pollution Prevention and Emergency Response | African Marine Solutions (AMSOL) | The new bid DOT/01/2022/MT and DOT/02/202225/MT was advertised and evaluated. The Department is as yet not in a position to appoint. The current contract expired on 30 November 2022. It was extended for six (6) months at a 13.05 % variance. | Business continuity | 468966.61 | R 275 880 000.00 | R 34 344 186.78 | Noting | 30/11/2022 | 30/11/2022 | 31/05/2023 | Reported
158 | Q3 2022/23 | New | 2022-12-05 | 2022-12-05 | Team D | Kwena Lengane | National Research Foundation (NRF) | Transpaco Cores & Tubes | Telescope Tubes | SAAO uses these tubes together with lenses when we do the telescope workshops with learners and Educators, to teach them about optics and astronomy awareness curriculum purposes. The original approval was expanded/ varied in accordance with National Treasury recent Instruction Note. | Expansion of scope (time & material) | 72.6 | 8320 | 0 | Within AA/AO mandate Noting | 2022-11-30 | Once off | Once off | reported
159 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Software license extension for Media Planning and Data Analysis Tools | Ask Afrika (TGI) | License renewals | Continue using existing software | 2303095.8 | 6580274.7 | 0 | Within AA/AO mandate Noting | 2022-09-27 | 2022-10-01 | 2023-09-30 | reported
160 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Software license extension for Media Planning and Data Analysis Tools | AGB Nielsen | License renewals | Continue using existing software | 1971622.01 | 8000508.48 | 0 | Within AA/AO mandate Noting | 2022-09-27 | 2022-10-01 | 2023-09-30 | reported
161 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Software license extension for Media Planning and Data Analysis Tools | Telmar Media System | License renewals | Continue using existing software | 3119629.15 | 8417852.4 | 0 | Within AA/AO mandate Noting | 2022-09-27 | 2022-10-01 | 2023-09-30 | reported
162 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Scaffolding equipment Lease | Wreckers Scaffolding Services (Pty) Ltd | Continuity of service while a tender process unfolds | Extensions on current contracts due to new tender processes not concluded in time | 442921.5 | 1771686 | 2657529 | Within AA/AO mandate Noting | 2022-07-08 | 2022-08-01 | 2023-01-31 | reported
163 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Software license upgrade, and support and maintenance | Software AG South Africa (Pty) Ltd | Upgrading of the existing Adabas Natural Environment Software | Expansion of scope (time & material) | 4274999.65 | 4687645.46 | 0 | Within AA/AO mandate Noting | 2022-07-22 | 2022-08-01 | 2023-04-25 | reported
164 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Supply, Installation and Commissioning of the Henley Linking | African Union Communications (South Africa) Pty Ltd | More time to implement the solution | Business continuity | 4369988.5 | 11428581.73 | 0 | Within AA/AO mandate Noting | 2022-08-25 | 2022-09-01 | 2022-12-31 | reported
165 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Eastern Cape Cleaning services | Servest Pty Ltd | Continuity of service while a tender Process unfolds | Extensions on current contracts due to new tender processes not concluded in time | 256066.94 | 3955881.84 | 128033.5 | Within AA/AO mandate Noting | 2022-08-26 | 2022-09-01 | 2022-10-31 | reported
166 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Economic Data services | Refinitive SA Incorporated in Switzerland | Continuity of services | Business continuity | 1672390 | 1146722.04 | 0 | Within AA/AO mandate Noting | 2022-10-05 | 2022-11-01 | 2024-10-31 | reported
167 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | Tshwane Security services | Modise Protection services | Continuity of service while a tender Process unfolds | Extensions on current contracts due to new tender processes not concluded in time | 147554.2 | 1217094.86 | 0 | Within AA/AO mandate Noting | 2022-09-30 | 2022-10-01 | 2022-11-30 | reported
168 | Q3 2022/23 | New | 2022-11-28 | 2022-11-28 | Team D | Kwena Lengane | South African Broadcasting Corporation SOC Limited (SABC) | SABC Free State and Northern Cape Regional Offices - Security Services | Khayalami Security services | Continuity of service while a tender Process unfolds | Extensions on current contracts due to new tender processes not concluded in time | 555808.8 | 2394024 | 1111617.6 | Within AA/AO mandate Noting | 2022-09-20 | 2022-10-01 | 2022-11-30 | reported
169 | Q3 2022/23 | New | 2022-12-02 | 2022-12-02 | Team D | Kwena Lengane | South African National Space Agency (SANSA) | Extenion of Guardhouse | Pancare | Adherence to National Key Point specifications required an adjustment to the design of the roof that was not known at the time of placing the contract on the supplier. | Expansion of scope (time & material) | 428984.12 | 728219.69 | 0 | Within AA/AO mandate Noting | 2022-10-11 | 2022-10-11 | 2023-03-31 | reported
170 | Q3 2022/23 | New | 2022-12-12 | 2022-12-12 | Team D | Glory Limane | South African National Parks (SANParks) | Appointment of a Service Provider for Provision of Security Service to Karoo NP | Jen Foods | SANParks-022873-22 | Poor Planning | 31995.3 | 119814.43 | 0 | Within AA/AO mandate Noting | 2022-10-31 | Not stated | Not stated | reported
171 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team D | Kwena Lengane | Department of Science and Innovation (DSI) | Approve the payment of additional costs anticipated by Meeting Planners International (MPI amounting to R1 289 000 | Meeting Planners International (MPI) | Due to increased number of delegates which resulted in additional management fees among others. | Expansion of scope (time & material) | 1289000 | 4950197.03 | 0 | Within AA/AO mandate Noting | 2022-09-16 | 2022-11-11 | 2023-06-30 | reported
172 | Q3 2022/23 | New | 2022-12-15 | 2022-12-15 | Team B | Manqoba | Petroleum Agency South Africa (PASA) | Appointment of a project management services in respect of office relocation | Khuthazela Total Facilities Management Services (KTFMS) | Due to delays between PASA and Redefine caused KFTMS's services to be extended by two months. | Contract Extension | 330000 | R423 200,00 | R211 000,00 | Within AA/AO mandate Noting | 2022-11-29 | 2022-12-01 | 2023-02-28 | reported
South African Revenue Service
2022/2023 QUARTER 3
[6 empty] | Total number of Expansions received: |  | 172
[6 empty] | Total number of Expansions reviewed: |  | 172
[6 empty] | Pecentage Achieved |  | 100%
Signature______________________________________________
2022-01-06
0
0
0
0
Total reviewed expansions |  |  | 0
Total withdrawn expansions |  |  | 0
Expansions not yet reviewed (BLANK) |  |  | 0
Total number of expansions received: |  |  | 0