## Slide 1
Office of the Director-General
DPWI Q1, Q2 and Q3 Performance Report
Portfolio Committee on Public Works and Infrastructure

## Slide 2
To present the 1st, 2nd and 3rd Quarter Non-Financial and Financial Performance of the Department to Portfolio Committee on Public Works and Infrastructure
Not a Quarter Target (NQT)
Performance Colour Coding Guide
Purpose
Performance is calculated on the Number of Targets Achieved (i.e.. 90% above)
Progress is based on the Actual versus target (it is possible for a programme to be reported as 0% in terms of performance, but progress is reported at 80% - meaning it has moved 80% towards the target but falls short of the 90% level to be regarded achieved)

## Slide 3
Overview of Performance for Q1, Q2 and Q3
The Q1 performance stands at 52%
The Q2 performance stands at 50%
The Q3 performance stands at 32%
Q1. No of targets
29
Q2 No. of targets
32
Targets NA (1) | 2
Targets NA (2) | 7
Targets PA | 9
Targets A | 10
Total | 28
Q3 No. of targets
29
Cumulatively Q1-Q3 | No. Targets | Performance | % Performance
Average | 30 | 13 | 45
Chart: 
| Prog 1 Administration | Prog 2 IGC | Prog 3 EPWP | Prog 4 Policy | Prog 5 Prestige | Prog 6 Finance (PMTE) | Prog 7 REIS | Prog 8 CPM | Prog 9 REMS | Prog 10 REIRS | Prog 11 FM
Q3 2022/23 FY % Performance | 20 | 100 | 25 | 100 | 0 | 0 | 20 | 100 | 33.3333
NQT
NQT

## Slide 4
Programme: Management |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Ethics and Fraud Perception Rating | 41 - 60% | No information provided | Survey questions developed and ready to be administered to participants | NQT | ICT assisting with administering the Questionnaire to the Department 4 main categories developed and 20 questions in total. | N/A | N/A
Compliance Rate (management practices) | 100% | 93% | 93% | 100% | 76% (Preliminary report) | Some compliance matters are affected by delays in concluding matters such as disciplinary cases often being postponed and late submission of information | Assess internal process to ensure full compliance within the specified timelines where possible
Percentage Performance Information Level | 81-100% | 52% | 50% (16 targets achieved above 90% against a total of 32 targets for the quarter) | 81-100% | 32% Cumulative Average Performance (Q1-Q3) = 45% | Number of programmes have not achieved the set targets resulting in low overall percentage performance level | Warning letters have been issued for branches to explain their reasons for under-performance and measures in place to improve performance in Q4 and AR
Percentage Financial Performance Level | 100% | 20% (74% achievement) | 48% (90% achievement) | 87% | 76% | Delays in filling of prioritised vacant funded positions Non-transfer of R362 million for the Non-state Sector Programme by the EPWP due to delay in implementation of the programme which impacted the conditions for the tranche payment. Withholding of the EPWP Integrated Grants for Provinces and Municipalities due to non-compliance to the DoRA. | Filling of vacant positions has been prioritised. Interviews for executive management, including Director General, positions are scheduled for end February 2023. The programme was implemented from October 2022 and the 60% reporting of participants on EPWP-RS was achieved, with funds being planned to be transferred in January 2023 Engagement with the Provinces to ensure compliance for the funds to be rescheduled and transferred to Provinces.

## Slide 5
Programme: Management |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Percentage Vacancy Rate | 11% | 11% | 11% (100% Achievement) | 11% | 10% (91%) |  | -
Designated Groups in SMS Level in the Department (Women and PWD) | Women 40% and PWD 2% | Women in SMS: 40.11% PWD: 1.16% (79% achievement) | Women in SMS: 40.88% and PWD: 1.15% (88,6% achievement) |  | Women 42.13% and PWD 1.08% hybrid percentage | Unavailability of suitable applicants with disabilities. Disparities in remuneration compared to the private sector. | Continue presenting the stats during the recruitment process and implement circular on ring-fencing of positions
Percentage Business Process Automation | 30% | E-Leave Training requirements sent to business for confirmation Fleet Management: design and develop system (database and application) | E-Leave Conducted Training for Head Office HR Officials Draft training plan submitted by HR. and S&T Claims Management: Designed and developed system (Database and Application design) | NQT | There is a draft training plan and system demo for ECO member on E-Leave, and training of management, HR and Pretoria Regional Office officials has taken place. On S&T, there is Design Development (Database and Application design) and Training Plan developed. Fleet Management and User Acceptance Testing | N/A | 
Percentage of business Solutions for Digitisation | 30% | Compiled and Consulted Archibus Functionality Review report | Reviewed memo to support procurement strategy to NBAC. BSC meeting to discuss PA-12 Re-submitted procurement strategy to NBAC | NQT | Re-submitted procurement strategy and supporting documents to NBAC. Strategy Approved by NBAC. Tender advertised.PA25-2 and BEC nomination prepared, submitted to CD SCM and approved. | N/A | 

## Slide 6
Programme: Intergovernmental Coordination |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of Sector Performance Reports | 2 sector performance reports | The annual targets reflected in the Sector Plan Implementation Matrix were reviewed, in consultation with Sector Work Streams to enable progress reporting in outer quarters. | One (1) sector performance report against the Sector Plan targets consolidated. (100% achievement) | NQT | 01 Sector Performance Report Produced | N/A | N/A
Number of Beneficiaries Participating in DPWI Skills Pipeline Intervention Programme | 1100 | 01 Programme Performance Report Produced | 01 Progress Report on Operationalization Public Works Academy | NQT | 1100 Beneficiaries Participating in the DPWI Skills Pipeline Interventions Programmes | N/A | N/A

## Slide 7
Programme: Expanded Public Works Programme |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of progress report produced that reflect the work opportunities reported by public bodies on the EPWP-RS | 4 progress reports produced that reflect the work opportunities reported by public bodies on the EPWP-RS | 1 progress report produced that reflect the work opportunities reported by public bodies on the EPWP-RS (100% achievement) | 1 progress report produced that reflect the work opportunities reported by public bodies on the EPWP-RS (100% achievement) | 1 progress report produced that reflect the work opportunities reported by public bodies on the EPWP-RS | 1 progress report produced that reflect the work opportunities reported by public bodies on the EPWP-RS (100% achievement) (Preliminary WO = 746 792 validated EPWP work opportunities as at 12 January 2023) | Target Achieved | -

## Slide 8
EPWP Performance - Phase IV: 2022/23
The EPWP is currently on track to achieve its 5-year target.
In Q1 of 2022/23, a total of 240 167 work opportunities were reported against the 2022/23 annual target of 1 023 569 work opportunities (23.5% percent attainment of annual target).
As at the end of Q1 of 2022/23, 3190 200 opportunities were reported against the Phase 4 target up to Q1 2022/23 of 3 231 852 (98,7% attainment of the target).
By the end of Q2 of 2022/23, a total of 626 210 work opportunities were reported against the 2022/23 annual target of 1 023 569 work opportunities (61.2% percent attainment of annual target).
As at the end of Q2 of 2022/23, 3 576 243 opportunities were reported against the Phase 4 target up to Q2 2022/23 of 3 487 744 (102.5% attainment of the target).
In the remainder of 2022/23 (i.e. Quarter 4) and 2023/24 the EPWP must create 1 246 499 work opportunities, to reach the 5 million target for Phase IV
By the end of Q3 of 2022/23, a total of 803 468 work opportunities were reported against the 2022/23 annual target of 1 023 569 work opportunities (78.5% percent attainment of annual target).
As at the end of Q3 of 2022/23, 3 753 501 opportunities were reported against the Phase 4 target up to Q3 2022/23 of 3 743 636 (100.3% attainment of the target).

## Slide 9
EPWP Performance against 2022/23 APP Targets
Measures to achieve EPWP objectives and other strategic interventions
Commencement and reporting of the Non-State Sector Non-Profit Organisation Programme.
Continuing analysis on most efficient programmes and advocating the up-scaling of these programmes.
Sign-off of KwaZulu-Natal Protocols by Premier (which is the last signature outstanding).
Sector | 2022/23 WO Target | Quarter 1 |  | Quarter 2 |  | Quarter 3 | 
 |  | WOs Reported | % of Target achieved | WOs Reported | % of Target achieved | WOs Reported | % of Target achieved
Environment and Culture | 193 260 | 51 500 | 26,6% | 97 351 | 50,4% | 133 200 | 68,9%
Infrastructure | 348 819 | 109 025 | 31,3% | 164 784 | 47,2% | 191 543 | 54,9%
Community Work Programme | 252 818 | 0 | 0,0% | 212397 | 84,0% | 213 943 | 84,6%
Non Profit Organisations | 52 198 | 0 | 0,0% | 0 | 0,0% | 85 501 | 163,8%
Social | 176 474 | 79 642 | 45,1% | 151 678 | 85,9% | 179 281 | 101,6%
Total | 1 023 569 | 240 167 | 23,5% | 626 210 | 61,2% | 803 468 | 78,5%
Province | Provincial and Municipal WO Target | Quarter 1 |  | Quarter 2 |  | Quarter 3 | 
 |  | WOs Reported | % of Target achieved | WOs Reported | % of Target achieved | WOs Reported | % of Target achieved
Eastern Cape | 97 764 | 63 569 | 65,0% | 92 047 | 94,2% | 97 629 | 99,9%
Free State | 36 003 | 6 226 | 17,3% | 11 159 | 31,0% | 16 397 | 45,5%
Gauteng | 97 737 | 26 576 | 27,2% | 44 155 | 45,2% | 55 033 | 56,3%
KwaZulu-Natal | 131 831 | 61 818 | 46,9% | 112 020 | 85,0% | 124 050 | 94,1%
Limpopo | 58 852 | 15 065 | 25,6% | 33 204 | 56,4% | 46 039 | 78,2%
Mpumalanga | 45 056 | 6 452 | 14,3% | 16 223 | 36,0% | 26 331 | 58,4%
Northern Cape | 21 263 | 3 392 | 16,0% | 7 251 | 34,1% | 11 551 | 54,3%
North-West | 40 452 | 14 319 | 35,4% | 21 323 | 52,7% | 26 263 | 64,9%
Western Cape | 66 654 | 26 746 | 40,1% | 45 068 | 67,6% | 59 768 | 89,7%
Total | 595 613 | 224 163 | 37,6% | 382 450 | 64,2% | 463 061 | 77,7%

## Slide 10
Programme: Property and Construction Industry Policy and Research |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Public Works Bill submitted to Minister to introduce to Parliament | Public Works Bill Gazetted | New legal drafter appointed | Public Works Bill not gazetted for public comment. | NQT | Draft Public Works Bill developed for additional input and submitted to DPWI on 03 Oct 2022. | N/A | The Bill will be introduced to Parliament before the end of March.
Amendment of the Construction Industry Development Board Act, 2000 (Act 38 of 2000) | CIDB Amendment Bill submitted to Minister. | Draft CIDB Amendment Bill developed. | Consultations with key stakeholders not undertaken, due to revisions required by the OCSLA, which were addressed | Draft CIDB Amendment Bill Revised | CIDB Amendment Bill final consultations with the Departments of Justice and Finance. | The OCSLA’s additional input in September 2022 was considered and responded to & additional inter-departmental consultations held | Bill to be introduced to Cabinet for public comment in March 2023.
Infrastructure Development Act Regulations Gazetted | Infrastructure Development Act Regulations gazetted | - IDA Regulations submitted for consideration at PICC - Draft IDA Regulations gazetted 2nd June 2022 | Target was achieved in Q1 Gazetted Regulations were circulated to all national, provincial and local government stakeholders & ISA for implementation | Target Completed |  | - | -
Infrastructure Development Act amendments submitted to Cabinet | Introduction of Infrastructure Development Amendment Bill to Parliament | Draft Infrastructure Development Amendment Bill developed and the draft Business Case | Draft Infrastructure Development Amendment Bill & Business Case consulted with DPSA & National Treasury | Stakeholder analysis and public consultations report development | Internal stakeholders’ inputs received & incorporated into the Bill & Business Case, in terms of the 2018 guidelines, Public Service Act & PFMA (Executive Authority, NT & DPSA, etc). Public consultations are pre-emptive. | Processes to establishment of ISA as a public entity and the gazetting of the draft Infrastructure Development Amendment Bill had to be aligned, as is prescribed. Bill to go for public consultation once MPSA & MoF approve Business Case | Draft Business Case for the establishment of ISA as Entity and Infrastructure Development Bill will be submitted to the Minister of Public Service and Administration (MPSA) and Minister of Finance (MoF) for consideration & approval by EA in Feb 2023

## Slide 11
Programme: Property and Construction Industry Policy and Research |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of integrated reports on the status of Strategic Integrated Projects (SIPs) | 4 | 1 Integrated Report on the status of Strategic Integrated Projects (SIPs) (100% achievement) | 1 Integrated Report on the status of Strategic Integrated Projects (SIPs) has been developed and submitted (100% achievement) | 1 Integrated Report on the status of Strategic Integrated Projects (SIPs) submitted | 1 Integrated Report on the status of Strategic Integrated Projects (SIPs) has been submitted | Target Achieved | -
NIP 2050 Phase 2: Social and Distributed Infrastructure submitted to Cabinet | 1 | Draft NIP 2050 Phase 2: Social and Distributed Infrastructure developed | Draft NIP 2050 Phase 2: Social and Distributed Infrastructure gazetted for public consultation | NQT | Stakeholder analysis and public consultation report developed. | On Target | N/A

## Slide 12
Programme: Prestige |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of planned state event supported with movable structures | 5 | 1 Event supported with movable structures | 2 Events supported with movable structures | NQT | 2 Events supported with movable structures (Spanish Visit, Special Cabinet Lekgotla) | N/A | N/A
Percentage of movable assets provided within 60 working days | 100% | 100% (2 of 2) | 0 | 100% | 100% | Target Achieved | -
Percentage of provision of moveable assets from a condition assessment register of moveable assets | 80% | 20% | 20% | 20% | 20% | Target Achieved | -

## Slide 13
Programme: PMTE Finance |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Percentage Finance Performance Level | 100% | 21% (78% achievement) | 42% (79% achievement) | 87% | 68% | 70% of the R2.1 billion budget was spent. 499 vacancies in PMTE causing under expenditure.. A straight line projection indicates a possible underspending of R 157m An amount of R 152m was transferred to IDT and ISA through National Treasury due to reprioritization. It is projected that an amount of R 129 million will be underspent. | Filling of vacant positions has been prioritised Procurement process enhanced so that the committed budget is spent by end of the financial year.

## Slide 14
Programme: Real Estate Investment Services |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of Government Precinct Development Plans aligned to NSDF, IUDF and Smart City principles | 1 Government Precinct Development Plans aligned to NSDF, IUDF and Smart City principles | Integrated government precinct proposal revised supporting Smart City Principles for Polokwane Government Precinct Draft | Integrated government precinct proposal revised supporting Smart City Principles for Polokwane Government Precinct Draft | NQT – | 2 costed concept designs for government precincts | N/A | N/A
Number of approved C-AMP submitted to the National Treasury | 1 C-AMP submitted to the National Treasury | The 2024/25 C-AMP Chapters of six (6) Small User Departments were completed by 30 June 2022. | 1 C-AMP submitted to the National Treasury (100% achievement) | NQT | Completion of Custodian Asset Management Plan chapters for 08 Medium User Departments | N/A | N/A

## Slide 15
Programme: Construction Project Management |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of design solutions completed for identified user departments | 85 | 10 (43% achievement) | 19 (76% achievement) | 19 | 13 (Non-Cumulative) 68% | There are project designs for Durban and Mthatha Regional offices that were scheduled to be completed in the quarter under review (quarter 3). The targets could not, however, be achieved due to the delays relating to poor performing consultants and replacement through departmental professionals due to under capacity. | Continuous monitoring of projects and contractor performance throughout the project to ensure that challenges are addressed as early as possible.
Number of project completed within agreed construction period | 75 | 6 (46% achievement) | 7 Completed Projects 24% achievement 13 Cumulatively 44% achievement cumulatively | 47 | 12 Completed Projects 53% Achievement for Q2 25 Cumulative Achievement (33% cumulative achievement) | Target not achieved due to slow performance and financial constraints of the contractors. Under performing contractors placed on performance review. to ensure that the projects are accounted in quarter 4. | 

## Slide 16
Programme: Construction Project Management |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of infrastructure projects completed within approved budget | 125 | 9 (47% achievement) | 19 (47% achievement) 28 Projects cumulatively (70% achievement cumulatively) | 66 | 14 Projects completed within budget (21%) 42 Projects Cumulative 33.6% Cumulative | Poor designed specifications that result in multiple variation orders. Client departments change specifications or delay in releasing budgets, contribute to projects budget over run and escalations. | Joint task teams established with clients to address budget allocations Increased oversight of projects.
Number of infrastructure sites handed over for construction | 90 | 7 (30% achievement) | 19 (82% achievement) | 21 | 12 Sites handed over for construction (57%) 30 Sites handed over cumulatively (42%) | Poor coordination between Branches and Client Departments resulting in delayed site handovers once NBAC approves the infrastructure project Funding approval by client departments after awarding of projects also contribute to the delays in handing over sites for construction. | Development of improved coordination between Branches Regular extra meetings scheduled for the adjudication committee to sit and address backlog of submissions Joint task teams already sitting with clients to address late approval of projects.
Number of infrastructure projects completed | 125 | 10 (50% achievement) | 19 (44% achievement) 29 (67% cumulative achievement) | 72 | 15 Projects completed (21%) 44 Infrastructure projects completed cumulative (35%) | Frequent stoppage of projects by the local business forums contribute to projects budget over run (escalations and standing time) | Development of guidelines underway on how to deal with construction mafias and business forums

## Slide 17
Programme: Real Estate Management Services |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of private leases reduced in the security cluster | 3 private leases reduced within the security cluster | 1 private leases reduced | 4 private leases | NQT | 2 | N/A | N/A
Saving realised on identified private leases | R100 million Savings realised on identified private leases | R45 252 497.48 | R72 613 151.55 | NQT | R 31 114 567,39 | Protracted negotiations of month-to-month leases with landlords | Conclude negotiations as soon as possible with the landlords and the target to be reviewed based on leases that are expiring per financial year
Percentage increase in revenue generation through letting of state-owned properties (excluding harbor properties) | 8% increase in revenue generation through letting of state-owned properties | (R15 120 000) X 1% = R1 512 000) R 115 781 470.20 = 18.3% 20 000/2= R (R2 781 470.20) | 11.11% R15 120 000X 2% = 302 400 . R3 359 649.15/R302 400 =11.11% | 4 | 8% (200%) | Target Achieved More Leases signed than anticipated | Review the target for next financial year linked to the fast tracking of the Implementation of letting out circulars
Number of unutilized vacant state-owned properties let out | 100 unutilised vacant state-owned properties let out | 6 | 8 leases | 60 | 12 leases (20%) (26% Cumulative Target achieved) | Delays in signing of Lease Agreements | A circular on letting-out procedures has been developed and circulated to practitioners to implement. The circular seeks to address the delays experienced in signing leases through delegation of authority

## Slide 18
Programme: Real Estate Management Services |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of unutilised vacant state-owned properties let out for GBV-F purposes | 10 | No information provided | Assessments of 62 buildings, 40 of which have been approved by DSD as suitable. | 5 | 2 (One User Agreement in Free State with two (2) properties) (40%) | All User Agreements signed by the ADG and only 1 signed by User Department | Continuous engagements with User Departments to append their signatures
Percentage of leases awarded to companies with categories A, B and D of the approved Property Empowerment Policy | 35% | R15 120 000X 5% = 756 000. R233 039/R765 000 =0.03% | 50% (7/14 awards made - one award was made during the 1st quarter however this is bi-annual target) | NQT | 67% (2/3) | N/A | N/A
Percentage of new private leases signed with a maintenance plan | 100% | 100% | 100% | 30% | 17% (12 leases signed and 2 were for companies with B-BBEE level 4 and above) | Availability BBBEE landlords in certain areas – linked to lease periods | As and when new leases are concluded, all will have maintenance plan.
Percentage of leases let out to Companies with B-BEEE of 4 and above | 50% | 50% | 25% 2 leases signed out of 8 received | 100% | 0% | No New Leases were signed in Q3 | Engage clients to review lease periods to attract more B-BBEE compliant Landlords
Ha released from the DPWI portfolio for development of Infrastructure programs and socio-economic objectives | 161 913 hectares | 1542,7105 ha | 8,1482 ha | NQT | 1792,0067 hectares (Only 2% of this target has been achieved as at end Q3) | N/A | N/A

## Slide 19
Programme: Real Estate Information Registry Services |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of provincial immovable asset registers assessed for compliance | 9 Provincial immovable asset registers assessed for compliance | 2 Provincial immovable asset registers assessed for compliance (FS and MP) – (100% performance) | 2 Provincial immovable asset registers assessed for compliance (LP and KZN) (100% achievement) | 2 provincial immovable asset registers assessed for compliance | 2 Provincial immovable asset registers assessed for compliance ( WC and NC ) (100%) | Target Achieved | -
Number of immovable Assets physically verified to validate existence and assess conditions | 23 860 immovable assets physically verified to validate existence | 5347 Immovable assets physically verified to validate existence. (89% achievement) performance) | 5380 Immovable Assets physically verified to validate existence, ownership, and access condition. (90% achievement) | 5965 immovable assets physically verified to validate existence | 5687 Immovable Assets physically verified to validate existence, ownership, and access condition. (95%) | Target Achieved | -

## Slide 20
Programme: Facilities Management |  |  |  |  |  |  | 
Performance Indicators | Annual Target | Quarter 1 Performance | Quarter 2 Performance | Quarter 3 Target | Quarter 3 Performance | Reasons for Deviation | Corrective Measures
Number of condition assessments conducted on identified / prioritised properties | 220 | 16 (64% achievement) | 22 (49% achievement) | 75 | 33 (44%) | Delays experienced in the roll-out of the Multi-disciplinary Technical Team Panel. There were 79 facilities targeted for condition assessments, maintenance plans and development of specifications for term contracts implementation. However, the National Bid Adjudication Committee dealt with a significant amount of backlog, which resulted in delays on FM rollout. It is expected that FM to report on those targeted facilities for Q4. | DPWI is currently busy with the procurement of thirteen professionals from various disciplines. These professionals will be deployed to assist the Regions in the implementation of condition assessment and specifications for term contracts implementation. National Bid Adjudication Committee approved the rollout of the Multi-disciplinary Technical Team Panel, to target 79 facilities across the country. FM Branch has received some Management Trainees resources which are assisting with high level FCAs.
Number of critical components assessed to determine the conditions of components (lifts, boilers, HVAC and Gensets and Water systems) | 440 | 87 (174% achievement) | 3 (3% achievement). Conclusion of Q1 achievement. | 145 | 19 (13%) |  | 
Number of preventative term contracts awarded to reduce reactive maintenance level | 180 | No information provided | 29 (48% achievement) | 60 | 90 (150%) | Target Achieved Most of the Term Contracts have now passed various procurement phases and some of them have been awarded. | Continued support to be provided to the regions to ensure that the annual target for Term Contracts is maintained.

## Slide 21
FINANCIAL INFORMATION
DPWI – Main Vote

## Slide 22
Summary – Expenditure per Programme
Programme | Adjusted Budget Allocation 2022/23 | Second quarter expenditure (Cumulative) | Third quarter expenditure (Cumulative) | Variance as at 31 December 2022 | Second quarter expenditure % (Cumulative) | Third quarter expenditure % (Cumulative)
 | R`000 | R`000 | R`000 | R`000 | % | %
Administration | 555 009 | 223 029 | 355 809 | 199 200 | 41% | 64%
Intergovernmental Coordination | 62 205 | 25 935 | 36 869 | 25 336 | 42% | 59%
Expanded Public Works Programme | 3,023,131 | 1 073 880 | 2,019,106 | 1,004,025 | 35% | 67%
Property and Construction Industry Policy and Research | 4,444,519 | 2 589 733 | 3,740,574 | 703,945 | 59% | 84%
Prestige Policy | 67 865 | 18 227 | 35 282 | 32 583 | 26% | 52%
Total | 8 152 729 | 3 930 804 | 6 187 640 | 1 965 089 | 48% | 76%

## Slide 23
Spending Analysis - Programmes
Chart: Expenditure percentage per programme
| Administration | Intergovernmental Coordination | Expanded Public Works Programme | Property and Construction Industry Policy and Research | Prestige Policy
First Quarter | 0.2 | 0.18 | 0.08 | 0.27 | 0.1
Second Quarter | 0.4 | 0.42 | 0.35 | 0.59 | 0.26
Third Quarter | 0.64 | 0.59 | 0.67 | 0.84 | 0.26

## Slide 24
Summary- Expenditure per Economic Classification
Economic Classification | Adjusted Budget Allocation 2022/23 | Second quarter expenditure (Cumulative) | Third quarter expenditure (Cumulative) | Variance as at 31 December 2022 | Second quarter expenditure % (Cumulative) | Third quarter expenditure % (Cumulative)
 | R`000 | R`000 | R`000 | R`000 | % | %
Current payments | 1,078,117 | 397,218 | 642,558 | 435,559 | 37% | 60%
Compensation of employees | 597,158 | 243,740 | 384,864 | 212,294 | 42% | 64%
Goods and Services | 480,959 | 153,478 | 257,695 | 223,264 | 32% | 54%
 |  |  |  | - |  | 
Transfers and Subsidies | 7,055,517 | 3,532,346 | 5,540,753 | 1,514,764 | 50% | 79%
Provinces and Municipalities | 1,636,351 | 691,886 | 1,294,958 | 341,393 | 42% | 79%
Departmental agencies and accounts | 4,087,700 | 2 497,485 | 3,565,936 | 521,764 | 61% | 87%
Foreign governments and international organisations | 28,432 | 28,432 | 28,432 | - | 100% | 100%
Public corporations and private enterprises | 260,675 | 45,187 | 118,781 | 141,894 | 17% | 46%
Non-profit institutions | 1,032,693 | 262,100 | 524,200 | 508,493 | 25% | 51%
Households | 9,666 | 7,256 | 8,446 | 1,220 | 75% | 87%
Payments for capital assets | 19,095 | 1,239 | 4,328 | 14,766 | 6% | 23%
Machinery and equipment | 19,095 | 1,239 | 4,328 | 14,766 | 6% | 23%
Total | 8,152,729 | 3,930,804 | 6,187,640 | 1,965,089 | 48% | 76%

## Slide 25
Spending Analysis – Economic Classifications
Chart: Expenditure percentage per economic classification
| Compensation of employees | Goods and services | Transfers and subsidies | Machinery and equipment
First Quarter | 0.21 | 0.08 | 0.2 | 0.03
Second Quarter | 0.43 | 0.25 | 0.46 | 0.1
Third Quarter | 0.64 | 0.54 | 0.79 | 0.23

## Slide 26: Notes on Expenditure - Summary
Total expenditure for the month ended December 2022 is R6.188 billion and is equivalent to 76% of the total adjusted budget allocation of R8.153 billion. The variance between expenditure and drawings amount to R563 million and spending variance relates to the below economic classification:
Compensation of Employees - expenditure as at the end of December 2022 amount to R384 million and is equivalent to 64% of the adjusted budget allocation of R597 million. The variance of R49 million against approved drawings of R434 million is attributed to delay in filling of vacant priority positions which were planned to be filled effective from April 2022 as well as positions that were vacated during the financial year.
Goods and Services - expenditure as at the end of December 2022 amount to R258 million and is equivalent to 54% of the adjusted budget allocation of R481 million. The variance of R80 million against approved drawings of R338 million mainly relate to:
  Administrative fees - low spending variance is mainly due to payment relating to EPWP Non- State Sector Programme which was not paid as scheduled due to system challenges from IDT that impacted programme delivery and conditions for the tranche payment.
  Computer services – low spending due to delays in finalising of procuring of software licenses and late submission of invoices from SITA.
  Agency and support/outsourced services – low spending due to delays in appointing a service provider for EPWP technical support contracts to departments and municipalities implementing EPWP Infrastructure sector and IDT projects.
  Communication – mainly due to revised usage packages.

## Slide 27: Notes on Expenditure - Summary
Transfers and Subsidies - expenditure as at the end of December 2022 amount to R5.541 billion and is equivalent to 79% of the adjusted budget allocation of R7.056 billion. The variance of R425 million against approved drawings of R5.965 billion mainly relate to:
  R362 million the EPWP Non-State Sector Programme which was withheld due to non-compliance i.e. the provision of the service level agreement signed between IDT and NPO. The agreements has been signed after the conclusion of the induction as per requirement.
  R75 million relating to the EPWP Integrated Grant for Provinces was due to withholding of the second tranche payment for non-compliant departments that failed to spend at least 25% of transferred amount and report all their projects in the EPWP Reporting System.
  R29 million relating to the EPWP Integrated Grant for Municipalities was withheld due to non-compliant departments that failed to spend at least 25% of transferred amount and report all their projects in the EPWP reporting system.
  R4 million spending variance was due to withheld transfer payments for EPWP Social Sector Incentive Grant to Provinces due to non-reporting of grant funded projects and failure to spend 50% of transferred amount.
  Machinery and Equipment - expenditure as of December 2022 amount to R4.3 million and is equivalent to 23% of the adjusted budgeted allocation of R19 million. The positive variance of R9.2 million against approved drawings of R13 million is mainly due to delay in planned acquisition of assets aligned to the projected filling of vacant priority positions.

## Slide 28: Detailed Report for Transfers and Subsidies
Transfers and Subsidies | Adjusted Budget Allocation 2022/23 | Second quarter expenditure (Cumulative) | Third quarter expenditure (Cumulative) | Second quarter expenditure % (Cumulative) | Third quarter expenditure % (Cumulative)
 | R`000 | R`000 | R`000 | % | %
Construction Industry Development Board | 80,012 | 40,006 | 60,009 | 50% | 75%
Council for the Built Environment | 54,495 | 27,248 | 40,872 | 50% | 75%
Agrėment South Africa | 33,951 | 16,975 | 25,463 | 50% | 75%
Property Trading Entity Management | 3,912,823 | 2,412,675 | 3,433,173 | 55% | 88%
Industrial Development Corporation | 190,375 | 45,187 | 67,781 | 28% | 36%
Commonwealth War Graves Commission | 28,432 | 28,432 | 28,432 | 100% | 100%
Construction Education and Training Authority | 581 | 581 | 581 | 100% | 100%
Parliamentary Villages Management Board | 5,838 | - | 5,838 | 0% | 100%
Independent Development Trust | 70,300 | - | 51,000 | 0% | 73%
EPWP Integrated Grant for Provinces | 433,098 | 228,800 | 358,446 | 53% | 83%
EPWP Integrated Grant for Municipalities | 778,395 | 188,778 | 515,606 | 24% | 66%
EPWP Social Sector Incentive Grant for Provinces | 424,848 | 274,308 | 420,906 | 65% | 99%
EPWP Non –State Sector Programme | 1,032,693 | 262,100 | 524,200 | 25% | 51%
Total | 7,045,841 | 3,525,090 | 5,532,307 | 48% | 79%

## Slide 29
FINANCIAL INFORMATION
PMTE

## Slide 30
Budget & Cash Flow Statement Summary
 | Original Budget ENE | Revision | Revised Budget | Actual Performance Q2 (Cumulative) | Actual Performance Q3 (Cumulative) | % Quarter 2 (Cumulative) | % Quarter 3 (Cumulative)
 | R'000 | R'000 | R'000 | R'000 | R'000 |  | 
Receipts | 18 411 506 | -1 122 206 | 17 289 300 | 7 502 466 | 11 572 450 | 42% | 67%
Current/Transfer Expenditure | 13 284 278 | 414 422 | 13 698 700 | 6 419 848 | 9 945 995 | 46% | 73%
Surplus/(Deficit) | 5 127 228 | -1 536 628 | 3 590 600 | 1 082 618 | 1 626 455 | 27% | 45%
Capital Payments | 5 127 228 | -1 536 629 | 3 590 599 | 1 154 062 | 1 858 874 | 29% | 52%
Balance | 0 | 0 | 0 | - 71 444 | - 232 419 | 0% | 0%

## Slide 31
Executive Expenditure Summary
    Revenue/Receipts:
  The entity had invoiced R 8.8 billion of its budgeted R 17.3 billion revenue (excluding municipal services) as at the end of September 2022. This is equivalent to 51% of the total budgeted revenue. Actual receipts in relation to 2022/23 invoices amounted to R 6.7 billion (76% recovery rate). In addition to the budgeted revenue streams, the recovery rate on municipal services was 65%.
  At the end of December, the entity had invoiced R 13.2 billion. This is equivalent to 76% of the total budgeted revenue. Actual receipts in relation to 2022/23 invoices amounted to R 10.7 billion (81% recovery rate). In addition to the budgeted revenue streams, the recovery rate on municipal services was 58%. (which is a decrease for the second quarter)
    Expenditure:
  The total expenditure for the second quarter was R 7.6 billion which represents 42% of the total budget. (50% time lapse)
The total expenditure for the third quarter was R 11.8 billion which represents 68% of the total budget. (75% time lapse)
Spending is in line with the prior financial year, but it is projects that the infrastructure budget will not be fully spent.
Net Position:
      At the end of the Third Quarter, the PMTE had a negative cash flow of R 232 million on budgeted items consisting of a cash surplus of R 1.6 billion for operating activities and a cash outflow of R 1.8 billion from investing activities. This does not include the expenditure on Municipal Services. If that is added, the net cash flow reduces to negative R 1.3 billion. This is in comparison with the end of the second quarter at which time the cash flow was at negative R 72 million

## Slide 32
Budget & Cash Flow Statement Revenue
 | Original Budget ENE | Revision | Revised Budget | Actual Performance Q2 (Cumulative) | Actual Performance Q3 (Cumulative) | % Quarter 2 (Cumulative) | % Quarter 3 (Cumulative)
 | R'000 | R'000 | R'000 | R'000 | R'000 |  | 
Revenue/Receipts Exchange Transactions |  |  |  |  |  |  | 
Accommodation Charges – State Owned | 5 877 897 | 4 560 | 5 882 457 | 1 879 740 | 3 138 461 | 32% | 53%
Accommodation Charges - Client projects | 2 523 618 | - 480 809 | 2 042 809 | 812 099 | 1 227 886 | 40% | 60%
Accommodation Charges – Rental Debtors | 73 468 | 0 | 73 468 | 26 884 | 36 357 | 37% | 49%
Accommodation Charges - Private Leases | 5 197 847 | - 105 110 | 5 092 737 | 2 292 178 | 3 628 639 | 45% | 71%
Municipal Services Management Fees | 255 006 | 0 | 255 006 | 76 102 | 100 884 | 30% | 40%
Other revenue | 30 000 | 0 | 30 000 | 2 787 | 7 049 | 9% | 23%
 | 13 957 836 | - 581 359 | 13 376 477 | 5 089 790 | 8 139 277 | 38% | 61%
Non-exchange Transactions |  |  |  |  |  |  | 
Augmentation – DPWI Transfer | 4 453 670 | - 540 847 | 3 912 823 | 2 412 676 | 3 433 173 | 54% | 88%
Total Revenue | 18 411 506 | -1 122 206 | 17 289 300 | 7 502 466 | 11 572 450 | 42% | 67%

## Slide 33
Budget & Cash Flow Statement Expenditure
 | Original Budget ENE | Revision | Revised Budget | Actual Performance Q2 (Cumulative) | Actual Performance Q3 (Cumulative) | % Quarter 2 (Cumulative) | % Quarter 3 (Cumulative)
 | R'000 | R'000 | R'000 | R'000 | R'000 |  | 
Expenditure Current Payments |  |  |  |  |  |  | 
Cleaning and Gardening | 360 531 | 28 169 | 388 700 | 167 636 | 252 605 | 43% | 65%
Leases | 5 364 450 | - 105 110 | 5 259 340 | 2 756 323 | 4 232 373 | 52% | 80%
Maintenance | 1 415 835 | 814 163 | 2 229 998 | 1 123 858 | 1 698 374 | 50% | 76%
Repair | 1 109 986 | - 150 400 | 959 586 | 243 959 | 410 522 | 25% | 43%
Municipal Services - PMTE | 468 851 | 11 794 | 480 645 | 252 535 | 324 473 | 53% | 68%
Compensation of Employees | 2 161 210 | - 5 650 | 2 155 560 | 954 228 | 1 499 029 | 44% | 70%
Goods and Services | 628 958 | - 146 286 | 482 672 | 183 668 | 258 460 | 30% | 54%
 | 11 509 821 | 446 680 | 11 956 501 | 5 682 207 | 8 675 834 | 47% | 73%
Transfer Payments |  |  |  |  |  |  | 
Property Rates | 1 774 457 | - 32 258 | 1 742 199 | 737 641 | 1 270 160 | 42% | 73%
Total Current / Transfer Expenditure | 13 284 278 | 414 422 | 13 698 700 | 6 419 848 | 9 945 995 | 46% | 73%
Capital Payments |  |  |  |  |  |  | 
Refurbishments | 1 574 936 | - 666 910 | 908 026 | 296 354 | 446 765 | 33% | 49%
DPWI Capital | 985 704 | - 388 910 | 596 794 | 241 768 | 368 014 | 25% | 62%
Machinery and Equipment | 42 970 | 0 | 42 970 | 7 884 | 13 102 | 18% | 30%
Client Capital | 2 523 618 | - 480 809 | 2 042 809 | 608 055 | 1 030 993 | 30% | 50%
 | 5 127 228 | -1 536 629 | 3 590 599 | 1 154 062 | 1 858 874 | 29% | 52%
Total Expenditure | 18 411 506 | -1 122 206 | 17 289 300 | 7 573 910 | 11 804 869 | 42% | 68%

## Slide 34
Cleaning and Gardening:
  This budget was at 43% expenditure against a budget allocation of R 389 m at the end of the second quarter. This increased to 65% at the end of the third quarter. The expenditure is below the guideline, but executing units have confirmed their ability to spend the full budget although some contracts were concluded later than expected.
Private Leases:
  Expenditure was at 52% at the end of the second quarter and increased to 80% at the end of the third quarter. This is due to the moratorium that was placed on the payment of month-to-month leases. These leases were then in arrears and payment were made on outstanding amounts from the last financial year. This caused an increase in the spending trend. The expenditure trend will decrease slightly as the arrears are caught up.
Maintenance:
  This budget was at 50% expenditure against a budget of R 2.2b at the end of the second quarter. This increased to 76% at the end of the third quarter. Reallocations were done during September and an amount of R 814 million was added based on inputs from the Regions. The increase was mainly due to repair projects that were late to implementation (necessitating ongoing maintenance) and accruals from previous years.
Repair:
  25% of the budget was spend at the end of the second quarter and increased to 43% at the end of the third quarter. Delays are being experienced on several projects and an underspending is being projected at this stage. Weekly meeting are being held between Finance and CPM and other units to unblock any bottle necks. The budget was reduced by R 150 m
Budget Analysis

## Slide 35
  Municipal Services:
  53% of the R 480 m budget was spent at the end of the second quarter and increased to 68% at the end of the third quarter. The expenditure is fluctuating based on consumption and the full budget will be spent by the end of the financial year
Compensation of Employees:
  44% of this R 2.1 billion budget was spent at the end of the second quarter and this increased to 70% at the end of the third quarter. Although recruitment are actively filling positions. there are still 499 vacancies as officials are leaving the department due to natural attrition. The expenditure is below the time-lapsed guideline and the budget will not be spent by the end of the financial year.
Goods and Services
30% of this R 2.1 billion budget was spent at the end of the second quarter and this increased to 55% at the end of the third quarter. Several projects are experiencing challenges. The budget was reduced after funding was moved through the Adjustments Estimate to ISA and IDT.
Property Rates:
42% of this R 1.8 billion budget was spent at the end of the second quarter and this increased to 73% at the end of the third quarter. This is just below the guideline, but not a concern at this stage. Regions have indicated that they have not yet received all invoices and in some cases are disputing the valuations of the properties. Expenditure have been steadily increasing
Budget Analysis

## Slide 36
Refurbishments:
  33% of this budget was spent at the end of the second quarter and this increased to 49% at the end of the third quarter. Delays are being experienced on several projects and an underspending is being projected at this stage. The department is looking at possible ways to spend the unallocated funding on value added project e.g. the replacement of redundant lifts. The original allocation has been reduced by R 667 million and this funding was moved to the Maintenance budget.
DPWI Capital Infrastructure:
  33% of this budget was spent at the end of the second quarter and increased to 62% at the end of the third quarter. Delays are being experienced on several projects and an underspending is being projected at this stage. Weekly meeting are being held between Finance and CPM and other units to unblock any bottle necks. The majority of the underspending projection is allocated against PPD in relation to the Salvokop Project.
Machinery and Equipment:
  18% of this budget was spent at the end of the second quarter and this increased to only 30% at the end of the third quarter. This budget was reduced during the ENE process and will be monitored closely. Laptops and other computer equipment are being delivered and expenditure should increase although it is currently significantly lower than the same time last year.
Client Capital:
  30% of this budget was spent at the end of the second quarter and increased to only 55% at the end of the third quarter. Delays are being experienced on several projects and an underspending is being projected at this stage. The budget was reduced by R 480 million during the financial year. Sign-off of the 2023/24 allocations are still outstanding from most Clients.
Budget Analysis cont.

## Slide 37
Quarterly Actual Revenue
Chart: 
| Accommodation Charges – State Owned | Accommodation Charges - Client projects | Accommodation Charges – Rental Debtors | Accommodation Charges - Private Leases | Municipal Services Management Fees | Other | DPWI Transfer
Q1 | 0.05 | 0.24 | 0.18 | 0.18 | 0.13 | 0.08 | 0.27
Q2 | 0.32 | 0.4 | 0.37 | 0.45 | 0.3 | 0.09 | 0.54
Q3 | 0.53 | 0.6 | 0.49 | 0.71 | 0.4 | 0.23 | 0.88

## Slide 38
Quarterly Expenditure
Chart: 
| Cleaning and Gardening | Leases | Maintenance | Repair | Municipal Services - PMTE | Compensation of Employees | Goods and Services | Property Rates | Refurbishments | DPW Capital | Machinery and Equipment | Client Capital
Q1 | 0.23 | 0.24 | 0.33 | 0.08 | 0.29 | 0.23 | 0.11 | 0.23 | 0.11 | 0.11 | 0.06 | 0.17
Q2 | 0.43 | 0.52 | 0.5 | 0.25 | 0.53 | 0.44 | 0.29 | 0.42 | 0.33 | 0.25 | 0.18 | 0.3
Q3 | 0.65 | 0.8 | 0.76 | 0.43 | 0.68 | 0.7 | 0.54 | 0.73 | 0.49 | 0.62 | 0.3 | 0.5

## Slide 39
Budget Adjustments
 | Original Budget ENE | Revision | Revised Budget
 | R'000 | R'000 | R'000
Revenue/Receipts |  |  | 
Accommodation Charges – State Owned | 5 877 897 | 4 560 | 5 882 457
Accommodation Charges - Client projects | 2 523 618 | - 480 809 | 2 042 809
Accommodation Charges - Private Leases | 5 197 847 | - 105 110 | 5 092 737
Augmentation | 4 453 670 | - 540 847 | 3 912 823
Total Revenue | 18 411 506 | -1 122 206 | 17 289 300
Expenditure |  |  | 
Cleaning and Gardening | 360 531 | 28 169 | 388 700
Leases | 5 364 450 | - 105 110 | 5 259 340
Maintenance | 1 415 835 | 814 163 | 2 229 998
Repair | 1 109 986 | - 150 400 | 959 586
Municipal Services - PMTE | 468 851 | 11 794 | 480 645
Compensation of Employees | 2 161 210 | - 5 650 | 2 155 560
Goods and Services | 628 958 | - 146 286 | 482 672
Property Rates | 1 774 457 | - 32 258 | 1 742 199
Refurbishments | 1 574 936 | - 666 910 | 908 026
DPW Capital | 985 704 | - 388 910 | 596 794
Machinery and Equipment | 42 970 | 0 | 42 970
Client Capital | 2 523 618 | - 480 809 | 2 042 809
Total Expenditure | 18 411 506 | -1 122 206 | 17 289 300

## Slide 40: Debtors Age Analysis 30 September 2022 – Quarter 2
Categories | Current | 30 Days | 60 Days+ | Total 2022/23 | Prev Years | Total
 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000
Accommodation (State Owned) | 87 244 | 10 586 | 1 155 677 | 1 253 507 | 1 542 414 | 2 795 921
Accommodation (Private) | 284 182 | 97 266 | 184 180 | 565 628 | 669 585 | 1 235 214
Municipal Services | 323 414 | 147 276 | 393 637 | 864 327 | 4 667 238 | 5 531 565
PACE | 88 644 | 37 703 | 69 000 | 195 346 | 103 536 | 298 883
Recoverable: CA | 3 718 | 6 689 | 3 862 | 14 269 | 207 813 | 222 082
Total | 787 202 | 299 520 | 1 806 356 | 2 893 077 | 7 190 586 | 10 083 666
 |  |  |  | 29% | 71% | 

## Slide 41: Debtors Age Analysis 31 December 2022 – Quarter 3
Categories | Current | 30 Days | 60 Days+ | Total 2022/23 | Prev Years | Total
 | R’000 | R’000 | R’000 | R’000 | R’000 | R’000
Accommodation (State Owned) | 18 712 | 17 334 | 1 493 406 | 1 529 452 | 1 510 133 | 3 039 585
Accommodation (Private) | 352 388 | 66 036 | 273 477 | 691 901 | 634 196 | 1 326 098
Municipal Services | 244 245 | 354 433 | 762 014 | 1 360 692 | 4 657 939 | 6 018 631
PACE | 124 596 | 10 567 | 33 010 | 168 173 | 103 536 | 271 710
Recoverable: CA | 63 753 | 2 063 | 32 839 | 98 655 | 175 762 | 274 417
Total | 803 694 | 450 433 | 2 594 746 | 3 848 873 | 7 081 566 | 10 930 440
 |  |  |  | 35% | 65% | 

## Slide 42
Recommendations
It is recommended that the Portfolio Committee on Public Works and Infrastructure:
Notes the 1st, 2nd and 3rd Quarter Non-Financial and Financial Performance of the Department Public Works and Infrastructure.

## Slide 43
National Department of Public Works and Infrastructure (NDPWI)
Head Office: Public Works and Infrastructure CGO Building 256 Madiba Street Pretoria Central Private Bag X65 Pretoria 0001
Website: http://www.publicworks.gov.za
Thank You
Thank you