## Slide 1: THIRD QUARTERLY REPORT ON THE PERFORMANCE OF THE DEPARTMENT IN MEETING ITS PREDETERMINED OBJECTIVES FOR 2022/23
Portfolio Committee on Basic Education
28 February 2023

## Slide 2: PRESENTATION OUTLINE
PART A
Performance Indicators and Targets
PART B:
Financial Report: Third Quarter Expenditure

## Slide 3
PART A:
Performance Indicators and Targets

## Slide 4: PURPOSE
To report on the Third quarter outputs of the Department against the planned targets of the pre-determined objectives in the Annual Performance Plan for financial year 2022/23.
To report on the Department’s expenditure for the Third quarter of the financial year 2022/23.

## Slide 5: 2022/23 Q2 STATUS BAR FOR INDICATORS
All Annual indicators are WHITE unless fully achieved.
Where 50% of the target has not been achieved, the status is reflected as RED.
Where 50% or more of the target has been realised, the status is reflected as AMBER.
Where the target has been fully achieved, the status is reflected as GREEN.
Programme | No. of indicators per programme | Annual Targets | Biennial Targets | Biannual Targets | Quarterly Targets | Q2 status 2022/23 |  | 
 |  |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 6 | 2 | - | - | 4 | 1 | - | 3
Two | 31 | 29 | - | 1 | 1 | - | - | 2
Three | 11 | 10 | - | - | 1 | - | - | 1
Four | 16 | 15 | 1 | - | - | - | - | -
Five | 6 | 3 | - | - | 3 | - | - | 3
Total distribution | 70 | 59 | 1 | 1 | 9 | 1/10 | 0/10 | 9/10
Percentage distribution | 100% | 84% | 1.4% | 1.4% | 13% | 10% | 0% | 90%
Programme | No. of indicators per programme | Annual Targets | Biennial Targets | Biannual Targets | Quarterly Targets | Q2 status 2021/22 |  | 
 |  |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 5 | 2 | - | - | 3 | - | - | 3
Two | 32 | 30 | - | 1 | 1 | - | - | 2
Three | 12 | 10 | - | - | 2 | 2 | - | -
Four | 16 | 15 | 1 | - | - | - | - | -
Five | 5 | 1 | - | - | 4 | - | - | 4
Total distribution | 70 | 58 | 1 | 1 | 10 | 2/11 | 0/11 | 9/11
Percentage distribution | 100% | 83% | 2% | 2% | 14% | 18% | 0% | 82%

## Slide 6: 2022/23 QUARTER 2 TARGET NOT ACHIEVED
Indicator not achieved:
Programme 1:
  1.1.4 Schedule 4, 5 and 6 Conditional Grants Quarterly Performance Reports are supposed to be submitted to National Treasury (NT) 45 days after the end of each quarter.
  6 reports were submitted on 19 August 2022, 4 days later than 45 days. This was due to late submission of reports by Provincial Education Departments (PEDs) to the DBE.
Report writing sessions will be held in Q3 to ensure that reports are factually accurate and available to the DBE on time. Monitoring of Provincial submissions will be enhanced to ensure compliance to deadlines.

## Slide 7: PIE CHART STATUS
Chart: Q2 status 2021/22
| Not achieved | Partially achieved | Achieved
 | 0.18182 | 0 | 0.81818
Chart: Q2 status 2022/23
| Not achieved | Partially achieved | Achieved
 | 0.1 | 0 | 0.9

## Slide 8: QUARTER 3 MAJOR HIGHLIGHTS
Basic Education Director-General (DG), Mr Mathanzima Mweli, engaged with provincial and district officials as part of the Second Phase of Annual Virtual Engagements for 2022. The engagements commenced with the Western Cape Education Department (WCED) and the North-West Department of Education (NWDoE) on 13 and 14 October 2022, respectively. The DG met with the Northern Cape, Mpumalanga, Limpopo, KwaZulu-Natal and Gauteng Provinces.
A total of 920 934 candidates sat for the November 2022 National Senior Certificate (NSC) examination.
The writing of the November 2022 NSC examination was completed without significant irregularities that could have jeopardised its integrity and credibility.
The reach of the National Deworming Programme in four (4) provinces Gauteng, Mpumalanga, KwaZulu-Natal and Free State in 2022 is 1 124 916.
The preliminary 2022/2023 Funza Lushaka Bursary Programme (FLBP) recommended award list shows that 12 094 FLBP bursaries were awarded for Initial Teacher Education (ITE) by 31 December 2022; this is 294 awards, more than the target.

## Slide 9: PROGRAMMES OF THE DEPARTMENT OF BASIC EDUCATION (DBE)
The ANNUAL PERFORMANCE PLAN summarises the priorities of the DBE as aligned to the 2019-2024 Medium-Term Strategic Framework and the Action Plan to 2024: Towards the Realisation of Schooling 2030.
The activities of the DBE have been structured into five programmes as elaborated in the Annual Performance Plan:
PROGRAMME 1: ADMINISTRATION
PROGRAMME 2: CURRICULUM POLICY, SUPPORT AND MONITORING
PROGRAMME 3: TEACHERS, EDUCATION HUMAN RESOURCES AND INSTITUTIONAL DEVELOPMENT
PROGRAMME 4: PLANNING, INFORMATION AND ASSESSMENT
PROGRAMME 5: EDUCATIONAL ENRICHMENT SERVICES

## Slide 10: 2022/23 Q3 STATUS BAR FOR INDICATORS
All Annual indicators are WHITE unless fully achieved.
Where 50% of the target has not been achieved, the status is reflected as RED.
Where 50% or more of the target has been realised, the status is reflected as AMBER.
Where the target has been fully achieved, the status is reflected as GREEN.
Programme | No. of indicators per programme | Annual Targets | Biennial Targets | Biannual Targets | Quarterly Targets | Q3 status 2022/23 |  | 
 |  |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 6 | 2 | - | - | 4 | - | - | 4
Two | 31 | 29 | - | 1 | 1 | - | - | 1
Three | 11 | 10 | - | - | 1 | - | - | 1
Four | 16 | 15 | 1 | - | - | - | - | -
Five | 6 | 3 | - | - | 3 | 1 | - | 2
Total distribution | 70 | 59 | 1 | 1 | 9 | 1/9 | 0/9 | 8/9
Percentage distribution | 100% | 84% | 1.4% | 1.4% | 13% | 11% | 0% | 89%
Programme | No. of indicators per programme | Annual Targets | Biennial Targets | Biannual Targets | Quarterly Targets | Q3 status 2021/22 |  | 
 |  |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 5 | 2 | - | - | 3 | - | - | 3
Two | 32 | 30 | - | 1 | 1 | - | - | 1
Three | 12 | 10 | - | - | 2 | - | - | 2
Four | 16 | 15 | 1 | - | - | - | - | -
Five | 5 | 1 | - | - | 4 | - | 1 | 3
Total distribution | 70 | 58 | 1 | 1 | 10 | 0 | 1 | 9
Percentage distribution | 100% | 83% | 2% | 2% | 14% | 0% | 10% | 90%

## Slide 11: PIE CHART STATUS
Chart: Q3 status 2021/22
| Not achieved | Partially achieved | Achieved
 | 0 | 0.1 | 0.9
Chart: Q3 status 2022/23
| Not achieved | Partially achieved | Achieved
 | 0.11111 | 0 | 0.88889

## Slide 12: 2022/23 QUARTER 3 TARGET NOT ACHIEVED
Indicator not achieved:
Programme 5:
5.1.5 Number of districts implementing the programme to end school-related gender-based violence
Question 4 in Section D of the monitoring tool: “Number of schools implementing the Programme to End School Related Gender Based Violence (SRGBV)?” is only answered in the following 5 districts:
FS: Lejweleputswa
GP: Sedibeng East
GP: Johannesburg East
GP: Ekurhuleni South
GP: Ekurhuleni North
  The monitoring tool is not adequately completed and signed-off.
  The monitoring tool does not sufficiently accommodate the different Districts as some do not implement the GBV programme.
The Districts that have indicated Zero / NIL response in the area that cannot be evidenced for SRGBV programme implementation are updating their monitoring tools with requisite evidence

## Slide 13: PROGRAMME 1: ADMINISTRATION
The purpose of Programme 1 is to provide strategic leadership, management and support services to the Department.

## Slide 14: PROGRAMME 1 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
PROGRAMME 1: ADMINISTRATION |  |  |  |  |  | 
1.1.1. Percentage of valid invoices paid within 30 days upon receipt by the Department. | Quarterly | 100% |  |  |  | 
 | Q3 | 100% | Q1: 100% 6624/6624 Q2: 100% 10329/10329 Q3: 100% 8343/8343 | No deviation | Not applicable | Not applicable
1.1.2. Number of reports on misconduct cases resolved within 90 days | Quarterly | 4 |  |  |  | 
 | Q3 | 1 | Q1: 1 Q2: 1 Q3: 1 Total: 3 | No deviation | Not applicable | Not applicable
1.1.3 Number of capacity-building programmes offered to the DBE officials | Annually | 14 |  |  |  | 
 | Q3 | - | Q1: 4 Q2: 13 Q3: 14 Total: 31 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 15: PROGRAMME 1 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
1.1.4 Number of Schedule 4, 5 and 6 Conditional Grants Quarterly Performance Reports submitted to National Treasury (NT) 45 days after the end of each quarter | Quarterly | 28 |  |  |  | 
 | Q3 | 7 | Q1: 6 Q2: 0 Q3: 7 Total: 13 | No deviation | Not applicable | Not applicable
1.2.1 The Annual Performance Plan is approved by 31 March each financial year | Annually | 2023/24 APP approved by March 2023 |  |  |  | 
 | Q3 | - | 2023/24 DBE Draft APP submitted to the DPME and NT | Annual Indicator | Annual Indicator | Annual Indicator
1.2.2 Number of Quarterly Performance Reports submitted to National Treasury (NT) and the DPME 30 days after the end of each quarter | Quarterly | 4 |  |  |  | 
 | Q3 | 1 | Q1: 1 Q2: 1 Q3: 1 Total: 3 | No deviation | Not applicable | Not applicable

## Slide 16: PROGRAMME 1...
Human Resource Management and Administration
The Annual Performance Assessments (APA) for the 2021/22 assessment year of all officials within the Department have been completed.
Training and Social Responsibility
71 employees attended skills development training and 15 programmes were conducted.
Internship: The Department appointed 42 interns.
Labour Relations
One (1) grievance was lodged in relation to none payment of medical aid, the matter is still under investigation.
One (1) case of misconduct (disciplinary hearing) is in progress, the case is in relation to gross dereliction of duties.
Task Team meetings on consultation of policies were held on 08 and 13 September 2022.
An awareness session on the code of conduct and labour Relations matters was conducted during the induction session that was held on 20 October 2022.

## Slide 17: PROGRAMME 1...
Financial Management Services
The draft Estimates of National Expenditure 2023/24 database was submitted to National Treasury (NT).
The inputs for the compilation of the Interim Financial Statements (IFS) were received. The second quarter IFS were compiled and submitted to National Treasury as well as the Auditor-General.
Monthly Conditional Grants Expenditure reports from Provincial Education Department (PEDs) were received and submitted to National Treasury.
Public Entities Quarterly Reports and Annual Reports: The quarterly reports were received and analysed in terms of Treasury Regulation 26.1 and 30.2.1. The report of the analyses was submitted to the Executive Authority.

## Slide 18: PROGRAMME 1...
Legal Services
09 cases were received as follows:
Parties/Defending or Not Defending | Cause of Action/brief description of the case | Status
Mabika Mthembiso vs Minister of Basic Education | The matter emanates in Mpumalanga. Plaintiff alleges that he was hit across the face by an educator at the school. | Ongoing
Yves Kadilo and two others vs Park town Boys High School and six (6) others | Professional negligence that resulted in the drowning of a learner during a school activity. or death to the learners. | Ongoing
SA Childcare (Pty)Ltd and others vs Minister of Social Development and Others | The appellant alleges that the defendants breached their constitutional obligation of not paying the ECD subsidy in full despite the non-attendance of learners due to COVID-19 lockdown | Ongoing
Chante Peterson vs Clarissa Venter and three (3) others | The applicant is a learner who alleges that an educator slapped her on the face. | Ongoing
Phuthatshedzo Ndou vs The Minister of The Department of Basic Education | The learner sustained a severe injury to her forefinger, dislocated due to an assault. | Ongoing
Patricia Anne Luckin vs Lungelo Pannuel Ngcobo and another | Plaintiff alleges that a motor vehicle accident occurred whilst the first defendant acted within the course and scope of his employment. | Ongoing
Thokozani Clement Tshomelaobo Onwaba Tshomela vs Minister of Basic Education and others | It is alleged that the learner was first diagnosed with Pneumonia and later tested positive for COVID-19. The principle infringed on the learner’s constitutional right to privacy. | Ongoing
Prophet Shephered Bushiri Ministries NPC vs Milestone Primary School And The Minister of Basic Education. | The Applicant is Prophet Bushiri Ministries NPC and alleges ownership of property Plot 36 R55 Main Road Blue Hills, which the first Respondent currently occupies. | Ongoing
Suid Afrikaanse Onderwysers Unie vs Minister of Basic Education | The Applicant seeks an order to review and set aside regulations 9 (1) and (2) of the Infrastructure Regulations. The Applicant alleges that the Infrastructure regulations misused the PEDs as a mechanism by which a school’s capacity is determined for learners’ placement. | Ongoing

## Slide 19: PROGRAMME 1...
Legislative Services
Basic Education Laws Amendment (BELA Bill): The Portfolio Committee published the Bill for public comment. Oral hearings were conducted from 08 to 29 November 2022.
Regulations pertaining to Special School Hostels: The Task Team has finalised the drafting of the Regulations and a coasting exercise.
Admission Policy for Public Schools: The finalised draft policy to the line function for comments and incorporation. The final task team meeting was held on 08 December 2022. The Policy was presented to National Education Collaboration and Labour Council (NEDLAC).
Regulations relating to minimum uniform norms and standards for public school infrastructure: CEM approved the amendments to the norms and standards for public infrastructure and also agreed to a public participation process.
  The Amendments were published to invite written submission from the public and were translated into Afrikaans, IsiSwati, Tshivenda and IsiNdebele languages.

## Slide 20: PROGRAMME 1…
Security and Assets Management
The State Security Agency (SSA) and the DBE conducted site inspections/audits at PEDs printing, packaging, storage, and distribution sites for National Examination Question papers.
Occupational Health and Safety (OHS): Evac-chair training: Officials received in-house training from the Private Party on how to operate the Evac-chair during an emergency evacuation.
Supply Chain Management
Two (2) Terms of References were finalised by the Bid Specification Committee and recommended to the Bid Adjudication Committee:
  Appointment of a service provider for the development of and support of an improved early learning national assessment application to be used by Early Learning National Assessment (ELNA) assessors during fieldwork.
  Appointment of a service provider for hosting, support, and maintenance of the Education Facility Management System (EFMS).

## Slide 21: PROGRAMME 1…
Project Management
E4E Programme: The TSM Project Steering Committee meeting was facilitated on 19 October 2022. Systemic Improvement Literacy and numeracy in the Foundation Phase (SILN). PSC meeting was held on the 13th of October 2022.
Coding and Robotics: monitored progress and support the pilot in schools.
Attended the Inter-provincial meeting in EC, piloting PEDs and presented Coding and Robotics progress reports for purposes of sharing best practices from 22-23 November 2022.
Parliamentary and Business Processes
113 Parliamentary questions were received:
  75 questions were from the National Assembly (NA); and
  38 from the National Council of Provinces (NCOP).
Portfolio and Select Committee Meetings:
  The Portfolio Committee held eight (8) meetings.
  The Select Committee held two (2) meetings.

## Slide 22: PROGRAMME 1…
Donor Grant Management
Conducted feedback sessions on Annual Performance Evaluation Report on Conditional Grants to the PEDs organised into three (3) clusters on October - November 2022.
Submitted Conditional Grants quarterly report to National Treasury on 15 November 2022.
The approved 2023 Grant Frameworks and allocations for the Conditional Grants were submitted to National Treasury on 02 December 2022.
Participated in planning meetings concerning the work plan and milestones for year 4 of the Government to Government (G2G) project. The DBE convened a Technical Committee Meeting with United States Agency for International Development (USAID) for an update on the G2G project about the milestone achievements for year 3 and the new milestones for year 4.

## Slide 23: PROGRAMME 1…
Intergovernmental and Technical Support
Conducted a meeting with the NT to strengthen the Special Intervention on Overcrowding in Schools (SIPOS).
Provincial visits were conducted in EC, LP and KZN Construction sites to monitor progress as part of accelerating the Sanitation Appropriate for Education (SAFE) projects and ensuring that Implementing Agencies and Contractors are adhering to commitments.
Conditional Grants: Conducted three (3) monthly progress meetings and three (3) reflection meetings with KZN, WC, MP, FS,MP, GP, EC, NW, NC HoDs and officials responsible for Conditional Grants at the National and Provincial level on Conditional Grants expenditure for 2022/23 financial year to track the progress of the budget spent on grants.

## Slide 24: PROGRAMME 1…
Provincial Budget and Monitoring
Year Monitoring Reports as of September 2022 received from all PEDs were analysed and submitted to the Minister on 31 October 2022.
The Conditional Grants transfers to PEDs were analysed versus the spending rates.
Provided Feedback on the parliamentary question that covers whether the Department has sourced funding to build the capacity of Early Childhood Development (ECD).
HEDCOM Sub-Committee on Finance meeting was conducted on 01 December 2022.
A meeting was held with Limpopo PED to discuss the implementation of the school funding norms for Independent Schools.
2023 no fee lists were published on the Departmental website.

## Slide 25: PROGRAMME 1…
International Relations and Multilateral Affairs
The Minister Mrs AM Motshekga, MP delivered a speech on behalf of the country at the Qatar National Day on 29 October 2022.
The Minister and Deputy Minister hosted Ms L Andersson, the Finnish Minister of Education, from 10 to 12 October 2022.
The Director-General Mr. M Mweli met with the World Bank on 4 October 2022. The purpose of the meeting was to provide an update on the DBE-World Bank projects.
The DBE hosted a delegation from the State of Maryland on 16 November 2022, in order to discuss the finalised Memorandum of Understanding (MoU) with the State of Maryland, with a focus on ECD.
The DBE hosted the Permanent Secretary of the Ministry of Primary and Secondary Education of Zimbabwe, from 13 to 15 December 2022. The purpose of the visit was to sign the implementation plan of the MoU between the Government of the Republic of South Africa and the Government of Zimbabwe on Cooperation in the Field of Basic Education.

## Slide 26: PROGRAMME 1…
United Nations Educational, Scientific and Culture Organisation (UNESCO)
Training Program for Secretary Generals and Representatives of National Commissions for United Nations Educational, Scientific and Cultural Organisation (UNESCO) in African countries held in Azerbaijan on 24 September to 08 October 2022.
Virtual International Conference on Global Citizenship Education was held on 03 to 04 November 2022.
Virtual World Conference on Early Childhood Care and Education (WCECCE) was held on 14-16 November 2022.
UNESCO Mahatma Gandhi Institute of Education for peace and Sustainable Development (MGIEP) Decennial celebrations were held from 05-07 December 2022.
World Science Forum was held in Cape Town from 06-09 December 2022.
Capacity-building workshop on UNESCO Global Geoparks in Africa was held from 13-16 December 2022 in Kenya.

## Slide 27: PROGRAMME 1…
COORDINATING MECHANISM | SCHEDULED MEETINGS | MEETINGS HELD | SPECIAL MEETINGS HELD | MEETINGS NOT HELD
BM | 2 | 1 | 0 | 1
CEM | 1 | 0 | 1 | 1
MMM | 0 | 0 | 0 | 0
HEDCOM | 2 | 2 | 3 | 0
SM | 4 | 1 | 3 | 3
SPCHD Cluster | 3 | 2 | 1 | 1
SPCHD Cluster TWG | 3 | 2 | 0 | 1
TOTAL | 15 | 8 | 8 | 7
Coordination and Secretariat Support
01 October – 31 December 2022 meetings were scheduled, eight (8) of which were convened. eight (8) special meetings were held. Of the 16 meetings convened, 13 were virtual, whilst three (3) were face-to-face engagements. Seven (7) scheduled meetings could not be convened and these comprised of one (1) BM, one (1) CEM, three (3) SM, one (1) SPCHD Cluster and one (1) SPCHD Cluster TWG meetings. The DBE has successfully managed the logistical arrangements, agenda-setting and record drafting for all the sixteen (16) convened virtual and physical meetings.

## Slide 28: PROGRAMME 1…
Internal and External Stakeholders
Stakeholders’ meetings on Inclusive Education were held to discuss matters relating to the following:
  Progress on implementation of the recommendations of the Summit on Inclusive Education and terms of Inclusive Education in Early Childhood Development (ECD);
  Implementation of General Education Certificate (GEC);
  Measures taken to ensure safety and security in special schools;
  Status on Infrastructure relating to Special Schools projects, and Update on Bela Bill.
Meeting with Boxfusion, the software vendor managing the digitised submission portal Smartdbe. The purpose of the meeting was to provide feedback to the service provider on the system’s performance as experienced by DBE officials.
The DBE provided the vendor with recommendations on how to improve the platform for a better seamless service to improve the efficiency of the system.

## Slide 29: PROGRAMME 1…
Communications and Research
Photojournalism and videography support was provided to the Ministerial and Departmental events and uploaded onto the Image Bank (26,552 images). These images were also published in Thuto, the DBE Website, and posted on social media platforms.
Videography and Photojournalism were provided for workshops and events: A total of 190 video clips were captured for BELA Bill Oral Presentations, Men’s Parliament and Coding and Robotics Boot Camp and Western Cape University.
Media Liaison
Media Statements: 12 media statements to communicate Departmental messages, programmes, projects and events were issued.
Interviews and media queries: The DBE team handled 119 media interviews with the Minister, Deputy Minister, Director-General, and Departmental Spokesperson.
DBE TV: 12 DBE TV news bulletins were broadcast and streamed live across the DBE YouTube Channel and OpenView Channel 122 this platform has helped the DBE respond to the need to invent new ways of doing things that enable the department and stakeholders to share dependable and unmediated information from the Sector.

## Slide 30: PROGRAMME 1…
Internal Audit Risk Management and Investigations
Internal Audit conducted the following: Mathematics, Science and Technology (MST) Conditional Grant compliance follow-up review, and the report was finalised. National Teacher Awards Adjudication audit review and follow-up were completed.
Performance Information Quarter 2 audit review completed, obtaining management comments and agreed upon action to improve areas with findings.
Risk Management meeting was held to review the progress on the updating of the Operational Risk Register, and Project Risk Register, and monitor progress on areas identified for improvement as per the risk maturity assessment report.
Branch Risk Registers were updated, reviewed, finalised and signed off.
DBSA’s fruitless and wasteful expenditure was finalised to communicate to the Chief Executive Officer (CEO) in writing the findings and corrective action to be taken.

## Slide 31: PROGRAMME 1…
Strategic Planning and Reporting (SPR)
Institutional Reporting: The Departmental second quarter performance report for 2022/23 was submitted to the Department of Planning, Monitoring and Evaluation (DPME) and NT on 31 October 2022, and successfully uploaded to the electronic Quarterly Performance Reporting System (eQPRS) on the same date.
The Public Entities’ second quarterly performance reports were analysed and feedback was provided to the entities on 11 November 2022 through the office of the Chief Financial Officer (CFO).
Branch Reviews: Quarterly reviews were held on 15 to30 November 2022, to support Branches and improve planning and reporting in the Department.
Medium-Term Strategic Framework (MTSF): The first Bi-annual Priority 3 Progress Report was approved and submitted to the DPME on 2 November 2022. Priorities 4 and 6 were also submitted to the DSD and DSAC respectively.
Sector Alignment: The Standardised Output Indicators (SOIs) were approved, however, the sector will not be standardised for the 2023/24 financial year as WC PED did not adopt all SOIs as approved in Heads of Education Department Committee (HEDCOM) Subcom Planning Monitoring and Evaluation Technical Working Group (PM&E TWG).

## Slide 32: PROGRAMME 1…
Research Co-ordination, Monitoring and Evaluation (RCME)
The General Household Survey (GHS) 2021 and 2022 data cleaning and analysis were concluded. The graphs developed from the analysis are currently being consolidated for the final report. The final GHS will be completed in the first quarter of 2023.
ECD Deep Dive: The DBE worked with the LEGO Foundation to conduct a deep dive qualitative study to enhance the sector’s understanding of the current implementation of the National Curriculum Framework (NCF) for Children from birth to four (4) years. Quantitative data was collected in 50 schools and qualitative case studies were conducted in seven (7) ECD programmes.
Engaging Stakeholders: Participated in virtual research sharing meeting on 25 October 2022 with Flemish Association for Development Cooperation and Technical Assistant (VVOB) on Early Grade Reading work in KwaZulu-Natal. The unit also participated and presented at the Eastern Cape reading strategy launch on 04 October 2022.
COVID-19 Support: Participated and presented feedback on the Department of Planning, Monitoring and Evaluation (DPME) Second Edition Covid-19 Country Report on 17 October 2022.

## Slide 33: PROGRAMME 1…
Partnerships
National Teaching Awards: The Partnerships unit secured sponsorship from various partners and sponsors of the DBE, who contributed by sponsoring teachers with cash prizes and Information, Communication and Technology (ICT) gargets, the following partners sponsored: Woolworths, Via Afrika, Vodacom, ECUBED, Massmart, Zenex Foundation and Sasol Foundation.
New Africa Education Foundation in partnership with MANCOSA and The Yusuf Karodia Foundation donated three (3) fully equipped Mobile libraries to Grandmore Primary School, Palmview Primary School, Northland Primary School and Wembley Primary School in Phoenix, KwaZulu-Natal.
Government Information Technology
DBE Service Level Agreement (SLA) Meetings: The purpose of the SLA meetings was to review and report on the services provided by State Information State Agency (SITA) through the signed SLA for each month.
Two (2) DBE SLA meetings were held on 18 October and 15 November 2022.
ICT Steering Committee Meetings: Two (2) meetings were held in October and November 2022 to present ICT critical projects.

## Slide 34: PROGRAMME 2: CURRICULUM POLICY, SUPPORT AND MONITORING
The purpose of Programme 2 is to develop curriculum and assessment policies and monitor and support their implementation.

## Slide 35: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
PROGRAMME 2: CURRICULUM POLICY, SUPPORT AND MONITORING |  |  |  |  |  | 
2.1.1 Number of Technical Schools monitored for implementation of the Curriculum and Assessment Policy Statements (CAPS) | Quarterly | 18 |  |  |  | 
 | Q3 | - | Q1: 6 Q2: 6 Total 12 Q3: No monitoring during examination period in provinces and schools | No deviation | Not applicable | Not applicable
2.1.2 Number of learners obtaining subject passes towards an NSC or extended Senior Certificate (SC), including upgraded NSC, through the Second Chance Matric Programme (SCMP) | Bi-annually | 50000 |  |  |  | 
 | Q3 | - | Q2: 101 507 Q3: Eight (8) Centres were monitored across four (4) provinces namely: Eastern Cape KwaZulu-Natal Western Cape Northern Cape | Bi-annual Indicator | Bi-annual Indicator | Bi-annual Indicator

## Slide 36: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.3 Number of Children/ Learners with Profound Intellectual Disability (C/LPID) using the Learning Programme for C/LPID | Annually | 3927 |  |  |  | 
 | Q3 | - | The subject statements of learning programme for learners with profound intellectual disability for Life Skills and Mathematics were finalised. 9 PEDs were monitored on the implementation of the Learning Programme for LPID Children/ Learners with Profound Intellectual Disability (C/LPID) 2023 PEDs implementing guidelines were developed and orientation was also provided to officials on the utilisation of the guidelines. Support was provided to Grant Manager and Evidence Based Reporting on the end reporting requirements. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 37: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.4 An Annual Sector Report is produced on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention | Annually | Approved Annual National Report on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention |  |  |  | 
 | Q3 | - | For the period under review: 130 108 learners were screened 32 673 were identified as experiencing barriers to learning 15 833 cases were resolved by the schools 11 380 cases referred to the DBSTs, 9215 cases were resolved by the DBSTs, by retaining learners into their current schools and; 2 457 cases resolved by the DBSTs, by referring learners to other schools. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 38: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.5 An Annual National Report is produced on the development of a new funding model for ECD | Annually | Approved Annual National Report on the review of the subsidy payment mechanism |  |  |  | 
 | Q3 | - | In the development of a new funding model for ECD, the World Bank finalised the Public Expenditure and Institutional Report and a workshop was conducted with provinces to review the ECD subsidy guidelines | Annual Indicator | Annual Indicator | Annual Indicator
2.1.6 An Annual National Report is produced on conducting an Early Childhood Development census to inform the integration of ECD into the EMIS. | Annually | Approved Annual National Report on the integration of ECD data into EMIS |  |  |  | 
 | Q3 | - | Memorandum of Agreement (MoA) in progress for the integration of ECD data into EMIS: (1) Ilifa Labantwana for the long-term development of an ECD MIS system; (2) Data Innovators and Nelson Mandela Foundation for the short run use of the Vangasali Registration Management Tool. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 39: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.7 An Annual National Report is produced on developing an Early Childhood Development (ECD) Human Resource Development (HRD) Plan | Annually | Approved National Report on the development of a new ECD service delivery model and its workforce implications |  |  |  | 
 | Q3 | - | The Human Resource Development Plan (HRDP) task team members consisting of different Government and Non-Government ECD stakeholders have been appointed. | Annual Indicator | Annual Indicator | Annual Indicator
2.1.8 Number of districts monitored on implementation of the National Curriculum Statement (NCS) for Grades 10–12 | Annually | 8 |  |  |  | 
 | Q3 | - | Review and amendment of the first draft report of the monitoring of implementation of the National Curriculum Statement (NCS) for Grades 10–12 was conducted. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 40: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.9 Number of provinces monitored for extra-support classes to increase the number of learners achieving Bachelor-level passes | Annually | 9 |  |  |  | 
 | Q3 | - | 91 Spring Schools were monitored in all 9 PEDs. | Annual Indicator | Annual Indicator | Annual Indicator
2.1.10 Number of schools monitored for implementing compulsory entrepreneurship education | Annually | 180 (20 per province) |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 47 Q3: 50 Total: 97 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 41: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.11 An Annual National Report is produced on the implementation of the General Education Certificate (GEC) | Annually | Approved Annual National Report on the implementation of the General Education Certificate (GEC) |  |  |  | 
 | Q3 | - | A Funding Framework for the Three-Stream Model was developed and presented by GTAC at the PSC meeting. Circular S1 OF 2023: Availability of grade 8 and 9 vocational-oriented and years 1 - 4 Occupational subject’s learner and teacher guides on the Department of Basic Education website was developed and approved by the DG. The process plan for training subject advisors and teachers on CAPS practical’s for occupational and vocational subjects at the skills centres was developed | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 42: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.12 An Annual Sector Report is produced on schools that pilot and implement the Vocational Stream and Occupational Stream, respectively | Annually | Approved Annual Sector Report on schools that pilot and implement the Vocational Stream and Occupational Stream, respectively |  |  |  | 
 | Q3 | - | A Funding Framework for the Three-Stream Model was developed and presented by GTAC at the PSC meeting. Circular S1 of 2023: Availability of grade 8 and 9 vocational-oriented and years 1 - 4 Occupational subject’s learner and teacher guides on the Department of Basic Education website was developed and approved by the DG. The process plan for training subject advisors and teachers on CAPS practicals for occupational and vocational subjects at the skills centres was developed | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 43: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.1.13 Number of schools monitored for piloting the coding and robotics curriculum | Annually | 18 schools (2 per piloting Province) |  |  |  | 
 | Q3 | - | Q1: 2 Q2: 10 Q3: 2 Total: 14 | Annual Indicator | Annual Indicator | Annual Indicator
2.2.1 Number of schools monitored on the implementation of the reading norms | Annually | 18 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 10 Q3: 3 Total: 13 | Annual Indicator | Annual Indicator | Annual Indicator
2.2.2 Number of schools monitored on the implementation of the Incremental Introduction to African Languages (IIAL) | Annually | 18 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 11 Q3:2 Total: 13 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 44: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.2.3 Number of underperforming schools monitored on the implementation of the Early Grade Reading Assessment (EGRA) | Annually | 18 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 9 Q3:3 Total: 12 | Annual Indicator | Annual Indicator | Annual Indicator
2.2.4 Number of schools with multi-grade classes monitored for implementing the multi-grade toolkit. | Annually | 32 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 18 Q3:5 Total: 23 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 45: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.2.5 An Annual Sector Report is produced on the implementation of the National Reading Plan | Annually | Approved Annual Sector Report on the implementation of the National Reading Plan |  |  |  | 
 | Q3 | - | An analysis of the Q2 PEDs Reading Reports was conducted, and the report was produced. | Annual Indicator | Annual Indicator | Annual Indicator
2.2.6 An Annual Sector Report is produced on the number of public schools monitored on the availability of readers | Annually | Approved Annual Sector Report on the number of public schools monitored on the availability of readers |  |  |  | 
 | Q3 | - | The provinces were reminded during the Interprovincial meeting held on 7 November 2022 about the deadline to submit PED reports by 28 February 2023. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 46: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.3.1 Number of schools per province monitored for utilisation of Information Communication Technology (ICT) resources | Annually | 27 (3 per province) |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 20 Q3: 6 Total: 26 | Annual Indicator | Annual Indicator | Annual Indicator
2.3.2 Percentage of public schools provided with Home Language workbooks for learners in Grades 1 to 6 per year, after having placed an order | Annually | 100% Annually |  |  |  | 
 | Q3 | - | A total of 16 821 (99.12%) out of 16 971 targeted schools have received volume 1 Grades 1-6 Home Language workbooks. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 47: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.3.3 Percentage of public schools provided with Mathematics workbooks for learners in Grades 1 to 9 per year, after having placed an order | Annually | 100% Annually |  |  |  | 
 | Q3 | - | A total of 22 631 (99.57%) out of 22 728 targeted schools have received volume 1 Grades 1-9 Mathematics workbooks. | Annual Indicator | Annual Indicator | Annual Indicator
2.3.4 Percentage of public schools provided with workbooks for learners in Grades R per year, after having placed an order | Annually | 100% Annually |  |  |  | 
 | Q3 | - | A total of 16 110 (98.78%) out of 16 309 schools offering Grade R received terms 1 and 2 Grade R workbooks. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 48: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.3.5 An Annual Sector Report is produced on the percentage of learners provided with Mathematics and English First Additional Language (EFAL) textbooks in Grades 3, 6, 9 and 12 | Annually | Approved Annual Sector Report on the percentage of learners provided with Mathematics and English First Additional Language (EFAL) textbooks in Grades 3, 6, 9 and 12 |  |  |  | 
 | Q3 | - | A template for the annual sector report on learners provided with Mathematics and EFAL has been developed. Furthermore, letters were sent to provinces, reminding them about the submission of report on 10 February 2023. | Annual Indicator | Annual Indicator | Annual Indicator
2.3.6 Number of schools monitored for home languages in which Literacy Grades 1-3 Lesson Plans have been developed for terms 1 to 4 | Annually | 10 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 4 Q3: 3 Total: 7 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 49: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.3.7 Number of special schools with access to electronic devices | Annually | 70 |  |  |  | 
 | Q3 | - | Q1:16 Q2: 26 Q3: No connectivity was provided in this quarter by mobile operators as part of their social obligations | Annual Indicator | Annual Indicator | Annual Indicator
2.3.8 An Annual Sector Report is produced on the monitoring of procurement and distribution of Information Communication Technology (ICT) devices | Annually | Approved Annual Sector Report on the monitoring of procurement and distribution of Information Communication Technology (ICT) devices |  |  |  | 
 | Q3 | - | Letters were sent to PEDs to submit outstanding and upcoming provincial annual ICT reports as per the submission plan | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 50: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.4.1 An Annual Sector Report is produced on the number of teachers trained on inclusion | Annually | Approved Annual Sector Report on the number of teachers trained on inclusion |  |  |  | 
 | Q3 | - | For the period under review, a national total of 67 teachers were trained in Braille; 284 on SASL; 230 teachers on Autism; and 9982 teachers on inclusive programmes. This means the national total of teachers trained in areas of inclusion during the period under review has reached 10563. | Annual Indicator | Annual Indicator | Annual Indicator
2.4.2 An Annual Sector Report is produced on the number of learners in public special schools | Annually | Approved Annual Sector Report on the number of learners in public special schools |  |  |  | 
 | Q3 | - | For the period under review, 121 065 learners were enrolled in special schools for eight (8) provinces Eastern Cape: 1 023 Free State: 6 603 Gauteng: 58 954 KwaZulu-Natal: 20 887 Limpopo: Nil report Mpumalanga: 4 017 Northern Cape:1 812 North West: 7 839 Western Cape:19 930 National: 121 065 *The line function has arranged as support/intervention session with the Limpopo province to assist them to submit the report. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 51: PROGRAMME 2 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
2.4.3 An Annual Sector Report is produced on the percentage of public special schools serving as resource centres | Annually | Approved Annual Sector Report on the percentage of public special schools serving as resource centres |  |  |  | 
 | Q3 | - | Eight (8) PEDs have designed special schools as resource centres. The data excludes Limpopo Province. The provinces submitted the following percentages of public special schools serving as resource centres: Eastern Cape: 52% Free State: 54% Gauteng: 15.8% KwaZulu-Natal: 31% Limpopo: nil report Mpumalanga: 66% Northern Cape: 100% North West: 13% Western Cape: 38% | Annual Indicator | Annual Indicator | Annual Indicator
2.4.4 An Annual Sector Report is produced on the establishment of focus schools per PED | Annually | Approved Annual Sector Report on the establishment of focus schools per PED |  |  |  | 
 | Q3 | - | Annual Sector Report template and reminder to submit by 28 February 2023 sent to 9 PEDs through DG approved letter | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 52: PROGRAMME 2 ...
Early Childhood Development (ECD)
Additional funding has been allocated to ECD by NT over the next three (3) years and a funding proposal has been put together to indicate how these funds will be allocated.
An ongoing conversation on a Presidential Stimulus Package for ECD and a framework to detail what the package could look like has been developed.
In terms of registration, MOA is in progress with the following bodies: Ilifa Labantwana for the long-term development of an ECD MIS system; Data Innovators and Nelson Mandela Foundation for the short-run use of the Vangasali Registration Management Tool and eight (8) provinces have been trained on Vangasali except for Western Cape.
The tools have been first tested in the Eastern Cape and the Western Cape on October 2022. A workshop was also held on developing the business processes for the Quality Assurance Support System (QASS).
Human Resource Development Plan (HRDP) task team members consisting of different Government and Non-Government ECD stakeholders have been appointed.

## Slide 53: PROGRAMME 2…
Mathematics Science and Technology, E-Learning and Research
Mathematics Grades 10-12 Spring Classes and camps: Supported two (2) provinces Mpumalanga (MP) and Western Cape (WC) during Spring schools. 11 Spring centres in Gert Sibande and Metro North Districts were supported.
Mathematics Grades R-3 Diagnostic Assessments: Developed Grades 1-3 Endline Assessments, Memorandums and recording mark sheets for teachers to assess core Grades specific skills and knowledge.
Monitored two (2) piloting schools on Coding and Robotics.
Convened the Interprovincial meeting for Coding and Robotics in Gqeberha.
Technical Mathematics and Technical Sciences: A total of seven (7) centres were monitored and supported during Spring Classes in FS, NC and EC.
Digitisation of state-owned textbooks: A workshop for quality assurance of Grades 8 and 9 Mathematics content booklets was conducted on 10 –15 October 2022. Digitisation can only take place after the Grades 8 and 9 Mathematics content booklets have been quality assured by the relevant subject specialists.

## Slide 54: PROGRAMME 2…
Rural Education
Three (3) Rural Education Assistants Project reports have been published on the DBE website:
  REAP Research Report: Towards a Framework for the Effective Deployment of Education Assistants in South African Rural Schools;
  REAP Research Report: Towards a Framework for the Effective Deployment of Education Assistants in South African Rural Schools: Executive Summary; and
  REAP in Action: Mind map to effective learning, enhanced teacher well-being and improved livelihoods.
An agreement was reached between DBE and Sešego to extend the Edulution project to Gert Sibande in Mpumalanga and King Cetshwayo in KwaZulu-Natal starting in 2023.
The Inter-Provincial Rural Education Committee (IPREC) meeting was successfully hosted in the North West province.

## Slide 55: PROGRAMME 2…
Enhancement Programmes and Evaluation of School Performance
Volume 1 workbooks:
Printing of the Volume 1 workbooks has been completed, and a total number of 31 024 585 (100%) has been printed for 2023 academic year.
Delivery of Volume 1 has commenced, and a total number of 29 524 440 (99.88%) of 29 582 120 workbooks have been delivered to 22 710 (99.88%) of 22 738 public schools.
Volume 2 workbooks:
Printing of Volume 2 workbooks is in progress, and a total number of 24 369 039 (92%) of 26 537 555 workbooks have been printed.
Delivery of Volume 2 has commenced, and a total number of 3 744 680 (12.66%) of 29 582 120 workbooks have been delivered to of 4 738 (20.84%) of 22 738 schools.

## Slide 56: PROGRAMME 2…
Enhancement Programmes and Evaluation of School Performance
Volume 1: Grades 1 to 9 and (Grade R)
Source: Progress Report 13 January 2023
PROVINCE | TOTAL SCHOOLS ALLOCATED | TOTAL BOOKS ALLOCATED | SCHOOLS DISPATCHED | BOOKS DISPATCHED | SCHOOLS DELIVERED | BOOKS DELIVERED | % SCHOOLS DELIVERED | % BOOKS DELIVERED
 | SUM OF SCHOOLS | SUM OF BOOKS | SUM OF DPSCHOOLS | SUM OF DPBOOKS | SUM OF DELSCHOOLS | SUM OF DELBOOKS | - | -
EC | 4913 | 4114010 | 4913 | 4114010 | 4911 | 4112705 | 99.96% | 99.97%
FS | 938 | 1702650 | 938 | 1702650 | 938 | 1702650 | 100.00% | 100.00%
GP | 2068 | 5147975 | 2068 | 514775 | 2054 | 5109700 | 99.32% | 99.26%
KZN | 5958 | 6187040 | 5958 | 6187040 | 5955 | 6182020 | 99.95% | 99.92%
LP | 3672 | 4003770 | 3672 | 4003770 | 3671 | 3999905 | 99.97% | 99.90%
MP | 1661 | 2981420 | 1661 | 2981420 | 1660 | 2978860 | 99.94% | 99.91%
NC | 545 | 773970 | 545 | 773970 | 540 | 770465 | 99.08% | 99.55%
NW | 1465 | 2028155 | 1465 | 2028155 | 1464 | 2025375 | 99.93% | 99.86%
WC | 1518 | 2643130 | 1518 | 264330 | 1517 | 2642760 | 99.93% | 99.99%
Grand Total | 22738 | 29582120 | 22738 | 29582120 | 22710 | 29524440 | 99.88% | 99.81%

## Slide 57: PROGRAMME 2…
Enhancement Programmes and Evaluation of School Performance
Volume 2: Grades 1-9
Source: Progress Report 13 January 2023
PROVINCE | TOTAL SCHOOLS ALLOCATED | TOTAL BOOKS ALLOCATED | SCHOOLS DISPATCHED | BOOKS DISPATCHED | SCHOOLS DELIVERED | BOOKS DELIVERED | % SCHOOLS DELIVERED | % BOOKS DELIVERED
EC | 4913 | 4114010 | 1712 | 1244585 | 707 | 314215 | 14.39% | 7.64%
FS | 938 | 1702650 | 283 | 370765 | 160 | 142905 | 17.06% | 8.39%
GP | 2068 | 5147975 | 738 | 1199285 | 575 | 748755 | 27.80% | 14.54%
KZN | 5958 | 6187040 | 1922 | 1590405 | 1090 | 610495 | 18.29% | 9.87%
LP | 3672 | 4003770 | 1626 | 1393075 | 1212 | 884195 | 33.01% | 22.08%
MP | 1661 | 2981420 | 527 | 751850 | 329 | 333630 | 19.81% | 11.19%
NC | 545 | 773970 | 234 | 269520 | 39 | 26920 | 7.16% | 3.48%
NW | 1465 | 2028155 | 687 | 717650 | 391 | 364440 | 26.69% | 17.97%
WC | 1518 | 2643130 | 489 | 777750 | 235 | 319125 | 15.48% | 12.07%
Grand Total | 22738 | 29582120 | 8218 | 8314885 | 4738 | 3744680 | 20.84% | 12.66%

## Slide 58: PROGRAMME 2…
Reading
Primary School Reading Improvement Programme (PSRIP): Following the signing of the Service Level Agreement (SLA), a project plan has been agreed upon between the DBE and NECT, this resulted in a circular being crafted, signed and sent to Heads of the Department (HoD’s).
The DBE and NECT held meetings with 17 English First Additional Language (EFAL) Provincial Coordinators (PCs) to communicate potential training dates and plans for PSRIP 5.
The PCs further confirmed Subject Advisers and teacher allocations also submitted Subject Advisers database, except for the Free State and Gauteng.
In preparation for phase 4 of the Reading Champion (RC) programme, the following key meeting engagements have been conducted to unlock key planning processes.
Initial planning meeting with national support partners (Funda Wande, Room to Read, eCUBED and National Education Collaboration Trust (NECT) – Monitoring and Evaluation (M&E) held on 4 October 2022 to reflect on digital support platforms and actionable solutions to drive forward in phase 4.

## Slide 59: PROGRAMME 2…
Curriculum, Implementation and Quality Improvement (GET)
Subject Committee meetings were held for Social Sciences, Life Skills/Life Orientation, Creative Arts, and languages to mediate the 2023 Annual Teaching Plans.
Continuation on the development of Teachers’ Guides to strengthen reading with comprehension for the 10-year-olds and to guide teachers on how to transition learners from Home Language (HL) teaching to the English Language of Learning and Teaching (LoLT) in Social Sciences and Life Skills, was done at workshops held on 30 September to 6 October 2022.
The development and quality assurance of Teacher Guides and Learner Books for Year 1 to Year 4 in the school of skills subjects, Occupational Life Skills, Occupational Creative Arts, Occupational Physical Education, and Occupational English First Additional Language (EFAL) continued at two (2) workshops that were held on October and November 2022 respectively.

## Slide 60: PROGRAMME 2…
Curriculum, Implementation and Quality Improvement (FET)
57 Subject Reports on the evaluation of 2022 National Senior Certificate (NSC) Question Papers were developed and submitted.
91 Centres offering Spring Classes were monitored;
History Ministerial Task Team (MTT) and the Reference Team managed to identify and discuss possible types of tasks informal and formal in preparation for the writing up of Section 4 in Curriculum and Assessment Policy Statement (CAPS).
The final 2022 Evidence-Based Report (EBR) was developed, approved and submitted to Umalusi.
Inclusive Education
LSPID: Online monitoring of the implementation of the Learning Programme for Learners with Profound Intellectual Disability (LPID) and capturing of learner performance information and supporting documents was conducted and monitoring reports were compiled.
Documents that will guide PEDs when implementing the Learning Programme for LPID in 2023 were compiled. 165 officials were orientated to the guiding documents.

## Slide 61: PROGRAMME 2…
Second Chance Matric Programme (SCMP)
The Programme was implemented in two (2) Phases:
  Phase 1 took place from February – June 2022 and;
  Phase 2 was implemented from July – November 2022.
The Programme created job opportunities for 100 unemployed youth who served as cleaners at the centres during the classes. The youth were contracted to ensure that the face-to-face classes are kept clean as most classes happen after hours and at weekends. A total of 80 centre managers were appointed to manage these centres also referred to as face-to-face classes.
In Phase 2, 18 centres were monitored across all nine (9) Provinces and three (3) Ministerial roadshows were organised during the phase.
An Inter-Provincial meeting was held in Gqeberha, Eastern Cape to discuss the implementation of the 2023 academic year on 22-24 November 2022.
  The meeting reviewed the upcoming 2023 activities planned. The face-to-face classes for Phase 2 commenced on 1 July and ended on 30 November 2022.

## Slide 62: PROGRAMME 3: TEACHERS, EDUCATION HUMAN RESOURCES AND INSTITUTIONAL DEVELOPMENT
The purpose of Programme 3 is to promote quality teaching and institutional performance through the effective supply, development and utilisation of human resources.

## Slide 63: PROGRAMME 3 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
PROGRAMME 3: TEACHERS, EDUCATION HUMAN RESOURCES AND INSTIUTIONAL DEVELOPMENT |  |  |  |  |  | 
3.1.1 Percentage of School Governing Bodies (SGBs) that meet the minimum criteria in terms of effectiveness | Annually | 70% of 1 000 sampled schools |  |  |  | 
 | Q3 | - | During the quarter under review, completion of the survey tool and all quality check processes were underway and the statistical analysis of the data process will follow in the next quarter | Annual Indicator | Annual Indicator | Annual Indicator
3.1.2 Percentage of schools producing the minimum set of management documents at a required standard. | Annually | 100% of 1 000 sampled schools |  |  |  | 
 | Q3 | - | During the quarter under review, completion of the survey tool and all quality check processes were underway and the statistical analysis of the data process will follow in the next quarter | Annual Indicator | Annual Indicator | Annual Indicator
3.1.3 Number of Funza Lushaka bursaries awarded to students enrolled for Initial Teacher Education per year | Annually | 11800 |  |  |  | 
 | Q3 | - | 12 094 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 64: PROGRAMME 3 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
3.1.4 Number of quarterly monitoring reports tracking the percentage of Funza Lushaka graduates placed within six (6) months upon confirmation that the bursar has completed studies | Quarterly | 4 |  |  |  | 
 | Q3 | 1 | Q1: 1 Q2: 1 Q3: 1 Total: 3 | No deviation | Not applicable | Not applicable
3.1.5 An Annual National Report is produced on the number of qualified teachers aged 30 and below entering the public service as teachers | Annually | Approved Annual National Report on the number of qualified teachers aged 30 and below entering the public service as teachers |  |  |  | 
 | Q3 | - | Approved third quarter report on the number of qualified teachers aged 30 and below entering the public service as teachers | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 65: PROGRAMME 3 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
3.2.1 An Annual Sector Report is produced on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres | Annually | Approved Annual Sector Report on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres |  |  |  | 
 | Q3 | - | 37 completed monitoring tools and 9 PEDs quarterly reports submitted | Annual Indicator | Annual Indicator | Annual Indicator
3.2.2 An Annual Sector Report is produced on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on Language, Mathematics, Physical Science and Accounting | Annually | Approved Annual Sector Report on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on Language, Mathematics, Physical Science and Accounting |  |  |  | 
 | Q3 | - | Nine (9) PEDs submitted their quarterly reports | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 66: PROGRAMME 3 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
3.2.3 Number of PEDs that had their post provisioning processes assessed for compliance with the post-provisioning norms and standards | Annually | 9 |  |  |  | 
 | Q3 | - | Nine (9) PED letters notifying of HODs of Post provisioning meeting were developed and approved by the DG. Monitoring framework for the implementation of the Post Provisioning Norms for Staffing of Schools was developed Monitoring tool for Template for submission of the profiles of educators declared in addition was developed | Annual Indicator | Annual Indicator | Annual Indicator
3.2.4 An Annual Sector Report on Grade-R practitioners with NQF level 6 and above qualifications produced | Annually | Approved Annual Sector Report on Grade-R practitioners with NQF level 6 and above qualifications produced |  |  |  | 
 | Q3 | - | Four (4) approved monitoring tools were received from NC, MP, KZN, and EC. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 67: PROGRAMME 3 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
3.3.1 Number of PEDs monitored on the implementation of the Quality Management System (QMS) for school-based educators | Annually | 9 |  |  |  | 
 | Q3 | - | Q1: One (1) PED monitored: GP Q2: Three (3) PEDs monitored: FS, NC and WC Q3: Five (5) PEDs monitored: EC, KZN, MP, LP and NW Total: 9 | Annual Indicator | Annual Indicator | Annual Indicator
3.3.2 Number of PEDs monitored on the implementation of Education Management Service: Performance Management and Development System (EMS: PMDS) | Annually | 9 |  |  |  | 
 | Q3 | - | Q1: Three (3) PEDs monitored: KZN, MP and NC Q2: Three (3) PEDs monitored: EC, LP and WC Q3: Three (3) PEDs monitored: GP, FS and NW Total: 9 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 68: PROGRAMME 3 …
Education Labour Relations and Conditions of Service
Labour Management Partnership Project: A collaborative effort to improve Learner performance and achievement and to enhance teaching and the working environment for teachers and school management.
  This partnership is done through institutional partnering of educators and unions in the schooling environment focusing on the impact of collaborative partnerships on educational quality. A Collective Agreement on Labour Management Partnership Project was signed in November 2022 with the implementation date scheduled for February 2022.
The Department of Public service and Administration and Parties to the Public Service Coordinating Bargaining Council (PSCBC) concluded the wage negotiations and signed a Collective Agreement on the 2022 Salary negotiations and implemented same on 17 November 2022.

## Slide 69: PROGRAMME 3 …
Curriculum Research
Digital Skills Programme: 434 teachers were trained in digital skills. 138 Teacher Centre managers trained on the UNESCO Digital Teacher programme. The department collaborated with SchoolNet to train extra 5000 teachers on how to integrate ICTs into teaching and learning.
CPTD online Platform: Teachers registered on the CPTD online platform and training was conducted in two (2) provinces on the administration of the platform.
Self-Diagnostic Assessment: Teachers administered the online self-diagnostic assessments.
Support for District Teacher Development Centres: 31 District Teacher Development Centres received IT interns from UNISA. 12 Teacher Centres received new devices from Vodacom. 130 Teacher Centres received routers and sim cards to strengthen connectivity.
Research and Impact Assessment: The draft proposal for a cost-effective study on teacher programmes has been shared with DPME. One of the programmes identified for this study is the Primary Reading for Primary Schools Programme.

## Slide 70: PROGRAMME 3 …
Education Human Resource Planning, Provisioning and Monitoring
Monitoring and support of the implementation of the educator Post Provisioning Norms: Seven (7) PEDs distributed the school post establishments to schools by the end of September as required. The EC and KZN delayed distribution due to challenges regarding securing sufficient funding for the proposed establishments. They were finally declared in November 2022.
A report on the number of qualified educators aged 30 years and below entering the profession for the first time, covering December was compiled. A total of 2 428 young and qualified educators were appointed to posts in the PEDs 716 were permanent, 1 153 were temporary, and 559 were substitute/ relief appointments.
Monitoring and supporting the placement of Funza Lushaka graduates in PEDs: 68% (2 954 of 4 348) of graduates eligible for placement in 2022 were placed as of the end of December 2022. PEDs that recorded below-average placement are KZN (41%), EC (56%), MP (55%). Above average are LP (95%), NC (88%), NW (88%), WC (79%) FS (72%), and GP (70%)

## Slide 71: PROGRAMME 3
Province | Placed | Unplaced | Grand Total | Percentage
Eastern Cape | 393 | 306 | 699 | 56%
Free State | 193 | 76 | 296 | 72%
Gauteng | 516 | 217 | 733 | 70%
KwaZulu-Natal | 277 | 404 | 681 | 41%
Limpopo | 591 | 31 | 622 | 95%
Mpumalanga | 228 | 189 | 417 | 55%
North West | 166 | 23 | 189 | 88%
Northern Cape | 69 | 9 | 78 | 88%
Western Cape | 521 | 139 | 660 | 79%
Grand Total | 2 954 | 1 394 | 4 348 | 68%
Source: PERSAL, December 2022 and PED Report
Placement of Funza Lushaka graduates

## Slide 72: PROGRAMME 3
Number of qualified educators aged 30 and below appointed at schools for the first- time during the quarter by nature of appointment per province
Province | Relieve | Permanent | Temporary | Total
Eastern Cape | 39 | 46 | 9 | 94
Free State | 0 | 27 | 69 | 96
Gauteng | 0 | 18 | 473 | 491
KwaZulu-Natal | 93 | 302 | 71 | 466
Limpopo Province | 126 | 86 | 20 | 232
Mpumalanga | 39 | 2 | 22 | 63
North West | 43 | 7 | 155 | 205
Northern Cape | 29 | 0 | 19 | 48
Western Cape | 190 | 228 | 315 | 733
Grand Total | 559 | 716 | 1 153 | 2 428
Source: PERSAL December 2022

## Slide 73: PROGRAMME 3 …
Continuing Professional Teacher Development (CPTD)
905 lead teachers have been trained and a total of 17 099 teachers of the 22 500 targeted teachers were trained as of 30 October 2022.
The SHERO Award was held on 5 October 2022 at the Houghton Hotel where 33 finalists for the 5 categories were presented with certificates and the 10 winners were awarded with prizes.
The NTA was held on 20 October 2022 at the CSIR in Pretoria where 40 teachers were awarded in 14 categories.
Educator Performance Management and Development and Whole School Evaluation
Monitoring of the implementation of the Quality Management System (QMS) was finalised in six (6) PEDs – EC, KZN, MP, LP, NW, and WC.
A School Self-Evaluation (SSE) data management system was conceptualized and developed. The system was mediated to six (6) PEDs EC, FS, KZN, MP, NW, and NC for piloting.

## Slide 74: PROGRAMME 3 …
Education Management and Governance Development
The process of verifying 3% of the 1 000 sampled schools on the functionality of School Governing Bodies (SGBs) was conducted in FS, LP, MP, NW, and GP provinces.
The process of verifying 3% of the 1 000 sampled schools on the availability and implementation of the Management Documents (Survey Tool) was conducted in the FS, LP, MP, NW, and GP provinces.
Initial Teacher Education (ITE)
12 094 Funza Lushaka bursaries were awarded for Initial Teacher Education by 31 December 2022.
Orientation sessions for the first years and final years in the 21 universities were held.
Supported all nine (9) PEDs in the recruitment and selection of youth to study through the Funza Lushaka bursary in order to become teachers.
Participated in committees coordinated by the Department of Higher Education and Training (DHET) in the evaluation of teachers’ education qualifications as well as teacher education programmes.

## Slide 75: PROGRAMME 3
Teacher Development Implementation (TDI)
Four (4) LAMAP Professional Learning Committees were established across the district in EC. Participating project schools were used as hubs where neighbouring schools can borrow resources. Nine (9) cluster sessions were held in KZN.
Schools were monitored and learners’ books showed substantial hands-on activities recorded on the September workshop in LP.
Trained 66 Grade 8 Mathematics teachers and 194 Foundation Phase Numeracy teachers on November 2022 in EC.
Trained 130 Grade 7 teachers in Motheo and Thabo Mofutsanyana districts on content and pedagogy on October 2022 in FS. Trained 49 Mathematical Literacy teachers in Motheo on October 2022 in content and School Based Assessment (SBA) matters.
Trained 43 and 215 teachers in Mathematics in October in content, pedagogy, and SBA in Limpopo and KwaZulu-Natal.
Following the September virtual training of all provinces in technical Mathematics and Science, Gauteng continued to train and support nine (9) schools in Technical Science on October 2022.

## Slide 76: PROGRAMME 4: PLANNING, INFORMATION AND ASSESSMENT
The purpose of Programme 4 is to promote quality and effective service delivery in the basic education system through planning, implementation and assessment.

## Slide 77: PROGRAMME 4 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
PROGRAMME 4: PLANNING, INFORMATION AND ASSESSMENT |  |  |  |  |  | 
4.1.1 Number of new schools built and completed through ASIDI | Annually | 30 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 5 Q3: 3 Total: 8 | Annual Indicator | Annual Indicator | Annual Indicator
4.1.2 Number of schools provided with sanitation facilities | Annually | 450 |  |  |  | 
 | Q3 | - | Q1: 45 Q2: 67 Q3: 16 Total: 128 | Annual Indicator | Annual Indicator | Annual Indicator
4.1.3 Number of schools provided with water facilities through ASIDI | Annually | 50 |  |  |  | 
 | Q3 | - | Q1: 0 Q2: 16 Q3: 2 Total: 18 | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 78: PROGRAMME 4 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
4.2.1 Number of General Education and Training (GET) test items developed in Language and Mathematics for Grades 3, 6 and 9 | Annually | 500 |  |  |  | 
 | Q3 | - | 258 | Annual Indicator | Annual Indicator | Annual Indicator
4.2.2 Number of NSC reports produced | Annually | 4 |  |  |  | 
 | Q3 | - | The 4 signed reports will be provided in the fourth quarter | Annual Indicator | Annual Indicator | Annual Indicator
4.2.3 Number of question papers set for June and November examinations | Annually | 320 |  |  |  | 
 | Q3 | - | A total of 96 papers for Languages and a total of 122 papers for Non-Languages were developed. | Annual Indicator | Annual Indicator | Annual Indicator
4.2.4 Percentage of public schools using the South African School Administration and Management System (SA-SAMS) for reporting | Annually | 98% |  |  |  | 
 | Q3 | - | Q3 summary report of public schools in 8 provinces using SA-SAMS, supported with evidence supplied by the PED’s was produced. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 79: PROGRAMME 4 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
4.2.5 An Annual National Report is produced on the number of provinces monitored for implementation of the Learner Unit Record Information and Tracking System (LURITS) and EMIS priorities | Annually | Approved Annual National Report on the number of provinces monitored for implementation of the Learner Unit Record Information and Tracking System (LURITS) and EMIS priorities |  |  |  | 
 | Q3 | - | Monitoring was conducted in 8 PEDS and feedback was provided to the PEDs on the LURITS Readiness Audit. | Annual Indicator | Annual Indicator | Annual Indicator
4.2.6 An Annual National Report is produced on learning outcomes linked to the National Assessment Framework | Annually | Approved Annual National Report on learning outcomes linked to the National Assessment Framework |  |  |  | 
 | Q3 | - | PIRLS quarterly progress report was produced. The main activity for this period revolved around the 8th National Reading Coalition (NRC) meeting, the subsequent postponement of the PIRLS 2021 international results release and the publication of the PIRLs South African Encyclopaedia chapter. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 80: PROGRAMME 4 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
4.2.7 An Annual National Report is produced on the Early Learning National Assessment to determine school readiness | Annually | Approved Annual National Report on the Second Early Learning National Assessment |  |  |  | 
 | Q3 | - | 2022 Early Learning National Assessment (ELNA) Third Quarter Progress Report available. The Terms of Reference document was developed and successfully advertised as a tender | Annual Indicator | Annual Indicator | Annual Indicator
4.3.1 Number of officials from districts that achieved below the national benchmark in the NSC participating in a mentoring programme | Annually | 60 |  |  |  | 
 | Q3 | - | 27 mentees from districts that achieved below the national benchmark in the NSC were supported by the appointed mentors. | Annual Indicator | Annual Indicator | Annual Indicator
4.3.2 Percentage of school principals rating the support services of districts as being satisfactory | Biennially | 75% |  |  |  | 
 | Q3 | - | 818 out of 1 080 survey data collection responses received for capturing and analysis | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 81: PROGRAMME 4 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
4.3.3 Percentage of District Directors that have undergone competency assessment prior to their appointment | Annually | 97% |  |  |  | 
 | Q3 | - | Evidence on the advertisement or appointment of district directors were received from 3 PEDs (NC,WC and GP) | Annual Indicator | Annual Indicator | Annual Indicator
4.3.4 Number of underperforming secondary schools monitored at least twice a year by sector officials | Annually | 1000 |  |  |  | 
 | Q3 | - | 611 (accumulatively) | Annual Indicator | Annual Indicator | Annual Indicator
4.3.5 Number of districts in which teacher development has been conducted as per District Improvement Plans | Annually | 65 |  |  |  | 
 | Q3 | - | 31 signed District Improvement Plans received. | Annual Indicator | Annual Indicator | Annual Indicator
4.3.6 Number of District Director forums held | Annually | 3 |  |  |  | 
 | Q3 | - | No meeting scheduled for the quarter | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 82: PROGRAMME 4
Educational Management Information Systems (EMIS)
The South African School Administration System (SA-SAMS) Helpdesk fixed 260 databases and resolved in access 2000 online queries. Maintenance: Version 22.2.0, containing Examination alignment was released on 29 November 2022 and Version 22.2.1 was released on 9 December 2022 after provincial testing. SA-SAMS Modernisation: The Psybergate investigation into the Modernised SASAMS project was completed and NECT put together an action plan to address the results and also developed detailed recovery plans that were shared with the Project Steering Committee (PSC), the SA-SAMS team, DBE, and SITA.
LURITS Data uploads: Term 3 data was uploaded onto LURITS to monitor the efficiency of the feedback file, ensuring that all learners have a unique number. PED masterlists are maintained and the Masterlist data fields and Masterlist Standards are updated.
Education Data Dissemination and Usage: EMIS responded to 11 Parliamentary questions and 45 data requests from the DBE and stakeholders where EMIS data was utilized.
Submitted data to the Department of Home Affairs (DHA) for all nine (9) provinces for verification of learner IDs and supporting International Collaboration and project to provide Smart ID Cards to learners.

## Slide 83: PROGRAMME 4 ….
Public Examinations
Setting of NSC question papers 152 have been set, internally moderated, and approved by Umalusi.
A total of 96 papers for Languages and a total of 122 papers for Non-Languages were developed and verified by SPR.
Marking and the Marker Audit was completed in September/October for all nine (9) PEDs.
Standardisation of Marking Guidelines for the 2022 NSC November examinations was conducted.
Piloted the e-marking of Accounting Paper 2 across nine (9) PEDs as well as Music Paper 2 in centralised marking.
Conduct of the November 2021 Grade 12 Examination: A total of 920 934 candidates wrote the November 2022 NSC examination.
Writing of the examination commenced on 31 October and concluded on 7 December 2022.
The writing of the examination was completed without any major irregularities that could have jeopardised its integrity and credibility.

## Slide 84: PROGRAMME 4 ….
National Assessment and Public Examinations
SC 2022-06 examination: First bulk certification was completed.
NSC 2022-11 examination: School-Based Assessment (SBA) marks capturing was completed. Standardisation dry-run testing was approved by Umalusi.
SC and NSC 2023-06 examination: Registration for these candidates is open since 1 October 2022. The closing date for both online and manual processes is on 08 February 2023.
System Development and Maintenance: Ongoing development and maintenance are done on the systems to accommodate all the needs of the Department and Provincial users.
Examination and Assessment System Administration
NSC 2022-06: A new stand-alone June NSC open system that allowed candidates from 2008-11 examination year to re-write the June examination was developed and completed successfully. A few provinces still do the final mopping-up on the re-mark/re-check process.
First bulk certification was completed. Busy with the final bulk Certification.

## Slide 85: PROGRAMME 4…
Provincial and District Planning and Implementation Support
A discussion was conducted during the District Coordination, Monitoring and Support (DCMS) HEDCOM Sub-committee on the challenges arising out of the implementation of the minimum district staffing norms as captured in the amended Policy on the Organisation, Roles, and Responsibilities of Education Districts.
Capability building of district officials: The Department has collaborated with the NECT to develop an Integrated District Support Programme. A concept document and questions for a pilot study on a few district officials have been developed. The DBE-NECT collaboration planned to bring in the National School of Governance and a preliminary meeting to this effect was held on 08 December 2022.
District Development Model (DDM): There was a follow-up discussion during the DCMS HEDCOM Sub-committee meeting on 23 November 2022, on the Basic Education sector District Development Model (DDM) Lekgotla that was held at the end of the second quarter. The meeting deliberated on strengthening the implementation of the model in the district and metro municipalities where education districts are located.

## Slide 86: PROGRAMME 4…
School and District Incident Management and Support
2025 School Calendar: The HEDCOM and CEM meeting of 10 October 2022 and 03 November 2022, respectively adopted the 2025 School Calendar and recommended it for the Minister to publish.
Proposed 2026 School Calendar: The Heads of Education Departments Committee (HEDCOM) and Council of Education Ministers (CEM) meetings of 10 October 2022 and 03 November 2022, respectively approved the Proposed 2026 School Calendar and recommended it for the Minister to publish for public comments.

## Slide 87: PROGRAMME 4…
Quality Learning and Teaching Campaign (QLTC)
Campaign and Imbizos: Campaigns were conducted for, SCMP, ECD, Anti-Bullying, Promotion of Learner Pregnancy Policy, School Safety, Presidential Youth Employment Initiative, Rationalisation of schools, Overcrowded schools, Disaster Relief, Parliamentary Reach-out programmes, and Ministerial Community Reach-out programmes.
Inter-Provincial QLTC structures meetings were held.
Implementation and Monitoring
Replacement of Inappropriate Structures: Three (3) projects have reached practical completion.
16 schools have been provided with sanitation facilities.
2 schools have been provided with water facilities.

## Slide 88: PROGRAMME 4
  National Education Evaluation And Development Unit (NEEDU)
27 sharing sessions were held to mediate the report “Teaching every learner to read at an age-appropriate level: How teachers use DBE Rainbow Workbooks to enhance foundational literacy skills.”
The 27 sharing sessions were held in five (5) provinces in seven (7) different districts:
  KZN, Limpopo, Eastern Cape, Northern Cape, and Western Cape.
There were a total of 1 647 participants:
  884 Departmental Heads;
  81 Principals and Deputy Principals;
  673 Foundation phase teachers; and
  Nine (9) Grade-R teachers.

## Slide 89: PROGRAMME 5: EDUCATIONAL ENRICHMENT SERVICES
The purpose of Programme 5 is to develop policies and programmes to improve the quality of learning in schools.

## Slide 90: PROGRAMME 5 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
PROGRAMME 5: EDUCATIONAL ENRICHMENT SERVICES |  |  |  |  |  | 
5.1.1 An Annual Sector Report is produced on the provision of nutritious meals and compliance with feeding requirements | Annually | Approved Annual Sector Report on the provision of nutritious meals and compliance with feeding requirements |  |  |  | 
 | Q3 | - | 13 schools were monitored during the quarter. Q3 monitoring report is submitted. | Annual Indicator | Annual Indicator | Annual Indicator
5.1.2 Number of PEDs with approved annual business plans for the HIV/AIDS Life Skills Education Programme | Annually | 9 |  |  |  | 
 | Q3 | - | 4 schools were monitored during the quarter. | Annual Indicator | Annual Indicator | Annual Indicator
5.1.3 Number of districts monitored in the implementation of the National School Safety Framework (NSSF), Social Cohesion, Sport and Enrichment Programmes | Quarterly | 75 |  |  |  | 
 | Q3 | 20 | 20 | No deviation | Not applicable | Not applicable

## Slide 91: PROGRAMME 5 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
5.1.4 Number of learners, educators, parents, SGBs and other educations stakeholders reached through social cohesion programmes | Quarterly | 3500 |  |  |  | 
 | Q3 | 500 | Q1: 2172 Q2: 2204 Q3: 1314 Total: 5690 | 814 | Collaboration with external stakeholders was beneficial in advocating for Social Cohesion and Equity Programmes. | Not applicable
5.1.5 Number of districts implementing the programme to end school-related gender-based violence | Quarterly | 75 |  |  |  | 
 | Q3 | 20 | 5 | -15 | The monitoring tool is not adequately completed and signed-off. The monitoring tool does not sufficiently accommodate the different Districts as some could not provide evidence of implementation of one of the three programmes. | The DBE is returning to all the Districts that could not provide evidence of implementation of programmes to end SRGBV to source the required evidence so that the monitoring tools can be updated with latest information. It is difficult to confirm if these Districts do indeed implement these programmes without the necessary evidence required from them. For now, it is reported as Zero / NIL.

## Slide 92: PROGRAMME 5 INDICATORS…
Performance Indicator | Frequency | Target for 2022/23 | Validated Milestone/ Output | Deviation | Reason for deviation | Challenges/ Corrective Action
5.1.6 Number of professionals trained in SASCE programmes | Annually | 900 |  |  |  | 
 | Q3 | - | The National Coordinating Committee (NCC) had a meeting on 21/11/2022 at the Tshwane North District Office in Wonderboom Junction to deliberate on the 2023 Participation Rules. Provinces and all the teacher unions that form part of the NCC gave their input on the rules. | Annual Indicator | Annual Indicator | Annual Indicator

## Slide 93: PROGRAMME 5 …
Sport and Enrichment in Education
The Football Mini World Cup Festival was held on 17 November 2022 at the SHAPA Nike Centre in Soweto.
The Implementation Protocol with the Department of Sport Arts and Culture (DSAC) has been finalised.
The SASCE National Coordinating Committee (NCC) had a meeting on 21 November 2022 at the Tshwane North District Office to deliberate on the 2023 participation rules.
Safety in Education
20 districts across three (3) provinces Limpopo, Free State, and Gauteng were monitored for implementation of the National School Safety Framework (NSSF).
Social Cohesion and Equity in Education
The International Day of the Girl Child was commemorated in Limpopo on 11 October 2022.
Consultations on the Guidelines for the socio-educational inclusion of Diverse Sexual Orientations, Gender Identity, Expression and Sex Characteristics (SOGIESC) in schools took place in two (2) provinces Eastern Cape and North West.
The national iNkosi Albert Luthuli Oral History Competition in collaboration with the Luthuli Museum was held from 01 to 02 October 2022 in KwaZulu-Natal province.

## Slide 94: PROGRAMME 5 …
Health Promotion
A total of 37 school monitoring visits have been was conducted were conducted as part of the build-up activities toward World AIDS day Commemoration.
The second draft of the Conditional Grant Framework was developed and presented at the Interprovincial meeting on 25 October 2022, and Treasury on 07 November 2022.
The DBE and North West PED co-hosted a Learner Pregnancy Prevention and Management (LPPM) Policy Provincial Dissemination Workshop on 8 November 2022.
The reported reach of the National deworming programme in 2022 is currently 1 124 916.
The data received from the District Health Information System (DHIS) submitted to DBE by the Department of Health (DoH), 257-568 learners have been reached through health screening from January to October 2022.
The TB Field Guide review process has been completed, and the first draft of the revised TB Field Guide was finalised.
The DBE officials led by the Deputy Minister supported the 2022 World AIDS Day national commemoration held in Free State (Bloemfontein) on 01 December 2022.

## Slide 95: PROGRAMME 5 …
Psycho-social Support
Training of Trainers and training Learner Support Agents (LSAs) on the Guide on providing psychosocial support to learners was conducted.
Resilience training was conducted with Northern Cape District officials and LSAs in collaboration with The University of Pretoria.
School Nutrition
13 schools were monitored on the provision of nutritious meals and compliance with feeding requirements.

## Slide 96: PROGRAMME 5
National School Nutrition Programme (NSNP)
Provincial Performance Indicators | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Number of learners in quintile 1 - 3 primary schools | 1022394 | 375797 | 704025 | 1331209 | 1025379 | 594105 | 120230 | 449640 | 302120 | 5924899
Number of learners in quintile 1 - 3 secondary schools | 595076 | 206049 | 373831 | 793031 | 625877 | 324013 | 60008 | 222950 | 113868 | 3314703
Number of learners in Special Schools | 8613 | 3254 | 38609 | 14751 | 8322 | 1992 | 1824 | 4488 | 12804 | 94657
Number of learners in quintile 4 - 5 primary schools |  |  | 20337 | 125302 |  |  | 18958 |  | 71309 | 235906
Number of learners in quintile 4 - 5 secondary schools |  |  | 13425 | 86896 |  |  | 9202 |  | 9612 | 119135
Total Number of learners reached | 1626083 | 585100 | 1150227 | 2351189 | 1659578 | 920110 | 210222 | 677078 | 509713 | 9689300
October - December 2022

## Slide 97: PART B: Quarter 3 Presentation to Standing Committee on Appropriation for 2022/23 Financial Year

## Slide 98: INTRODUCTION
The total Appropriation budget of the Department for the 2022/23 financial year amounts to R29.560 billion
82% of the budget amounting to R24.663 billion is allocated to transfer payments as follows:
  Conditional Grants: R23.008 billion
  Transfers to Public Entities: R178.0 million
  Other Transfers: R1.477 billion
The remainder of the budget R4.897 billion is allocated to the following:
  Compensation of Employees: R549.3 million
  Goods and Services: R2.247 billion
  Interest on Rent and Land: R40.6 million
  Payments of Capital Assets : R2.060 billion

## Slide 99: INTRODUCTION (cont.)
The total actual expenditure of the Department for the 2022/23 financial year third quarter amounts to R23.796 billion
Expenditure amounting to R20.931 billion is made up of Transfer payments as follows:
  Conditional Grants: R19.321 billion
  Transfers to Public Entities: R134.5 million
  Other Transfers: R1.476 billion
The remainder of the expenditure R1.604 billion from total expenditure is made up as follows:
  Compensation of Employees: R436.8 million
  Goods and Services: R1.3 billion
  Interest on Rent and Land: R30.0 million
  Payments of Capital Assets : R1.1 billion

## Slide 100: ALLOCATION AGAINST EXPENDITURE PER PROGRAMME FOR 2022/23 FINANCIAL YEAR
PROGRAMME | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Administration | 535 184 | 418 068 | 117 116 | 78.12%
Curriculum Policy, Support and Monitoring | 3 280 768 | 2 231 135 | 1 049 633 | 68.01%
Teachers, Education Human Resources and Institutional Development | 1 501 105 | 1 422 805 | 78 300 | 94.78%
Planning, Information and Assessment | 15 416 997 | 12 332 423 | 3 084 574 | 79.99%
Educational Enrichment Services | 8 826 113 | 7 391 258 | 1 434 855 | 83.74%
Total | 29 560 167 | 23 795 689 | 5 764 478 | 80.50%

## Slide 101: REASONS FOR MATERIAL VARIANCES PER PROGRAMME
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Programme 2: Curriculum Policy, Support and Monitoring Spending is lower at 68,01%. | Workbooks The delivery of Workbooks Volume 1 of Grade R to 9 is currently in progress and is expected to be completed during February 2023. A total number of 30,9 million of 32,9 million workbooks were delivered to 21 786 schools for the 2023 academic year.
Programme 3: Teachers, Education Human Resources Development and Institutional Development Spending is higher at 94,78%. | The once-off transfer for Funza Lushaka Bursaries was made to NSFAS on 1 April 2022 as per the approved payment schedule.

## Slide 102: ALLOCATION AGAINST EXPENDITURE PER ECONOMIC CLASSIFICATION FOR 2022/23 FINANCIAL YEAR
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Compensation of Employees | 549 328 | 436 798 | 112 530 | 79.51%
Goods and Services | 2 246 887 | 1 317 584 | 929 303 | 58.64%
Interest on Rent and Land | 40 553 | 29 981 | 10 572 | 73.93%
Transfers and Subsidies | 24 662 313 | 20 931 168 | 3 731 145 | 84.87%
Payments of Capital Assets | 2 061 086 | 1 080 003 | 981 083 | 52.40%
Payments of Financial Assets |  | 155 | -155 | 
Total | 29 560 167 | 23 795 689 | 5 764 478 | 80.50%

## Slide 103: REASONS FOR MATERIAL VARIANCES PER ECONOMIC CLASSIFICATION
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Goods and Services: The bulk of the allocation on this Item is in respect of the Workbooks and Conditional grants. Spending is lower at 58,64%. | Workbooks The delivery of Workbooks Volume 1 of Grade R to 9 is currently in progress and is expected to be completed during February 2023. A total number of 30,9m of 32,9m workbooks were delivered to 21 786 schools for the 2023 academic year.
Payments for Capital Assets: The bulk of the remaining allocation in this programme is for School Infrastructure Backlog grant. Spending is lower at 52,40%. | There is low spending on the ASIDI project due to the delay in the implementation of basic services such as water and sanitation by both the Independent Development Trust (IDT) and Coega Development Corporation (CDC).

## Slide 104: ALLOCATION AGAINST EXPENDITURE PER CONDITIONAL GRANTS 2022/23 FINANCIAL YEAR
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Learners with Profound Disability Grant | 255 521 | 188 521 | 67 000 | 73.78%
Mathematics Science and Technology Grant | 424 793 | 382 316 | 42 477 | 90.00%
Early Childhood Development Grant | 1 192 682 | 894 513 | 298 169 | 75.00%
Education Infrastructure Grant | 12 384 085 | 10 524 128 | 1 859 957 | 84.98%
National School Nutrition Programme | 8 508 321 | 7 137 373 | 1 370 948 | 83.89%
HIV and Allocation Grants | 242 275 | 193 823 | 48 452 | 80.00%
Total | 23 007 677 | 19 320 674 | 3 687 003 | 83.97%

## Slide 105: ALLOCATION AGAINST EXPENDITURE PER DETAILS OF TRANSFER (R’000) FOR 2022/23 FINANCIAL YEAR
Other Transfers | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
UNESCO Membership fees | 17 773 | - | 17 773 | -
ADEA | 1 000 | - | 1 000 | -
Guidance Counselling and Youth Development Centre: Malawi | 204 | 173 | 31 | 84.80%
Childline South Africa | 82 | - | 82 | -
National Education Collaboration Trust | 120 738 | 139 957 | -19 219 | 115.92%
Households |  | 394 | -394 | -
SEACMEQ | 3 816 | 2 835 | 981 | 74.30%
Uhambo Foundation ECD | 2 130 | 1 065 | 1 065 | 50.00%
SA Congress for ECD | 826 | 413 | 413 | 50.00%
Ntataise | 1 083 | 542 | 541 | 50.05%
NSFAS: Funza Lushaka | 1 328 953 | 1 328 953 | - | 100%
Total Other Transfers | 1 476 605 | 1 474 332 | 2 273 | 99.85%

## Slide 106: ALLOCATION AGAINST EXPENDITURE PER DETAILS OF TRANSFER( R’000) FOR 2022/23 FINANCIAL YEAR
Public Entities | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Umalusi | 162 031 | 121 524 | 40 507 | 75.00%
ETDP SETA | 472 | 472 | - | 100%
South African Council for Educators | 15 528 | 12 528 | 3 000 | 80.68%
Total Public Entities | 178 031 | 134 524 | 43 507 | 75.56%

## Slide 107: ALLOCATION AGAINST EXPENDITURE ON SCHOOLS BACKLOGS GRANT (SIBG) FOR 2022/23 FINANCIAL YEAR
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Compensation of Employees | 6 712 | 6 849 | -137 | 102.04%
Goods and Services | 358 735 | 230 784 | 127 951 | 64.33%
Interest & Rent on Land |  | 40 | -40 | -
Households |  | 376 | -376 | -
Building and Other Fixed Structures | 2 037 672 | 1 062 013 | 975 659 | 52.12
Total | 2 403 119 | 1 300 062 | 1 103 057 | 54.10%