## Slide 1
ROAD MAP TO THE PARLIAMENT RESTORATION PROJECT
Joint Presentation to the Joint Standing Committee on Financial Management of Parliament

## Slide 2: TABLE OF CONTENTS
01
04
05
Introduction
Project Description
Implementation of the Project
06
Key Project Milestones
07
Motivating Factors
08
10
Legal Framework
Project Governance
09
Time frames
02
03
Background
Context
11
Financial Implications

## Slide 3: INTRODUCTION
Parliament was visited by the unfortunate fire in January 2022:
  Two Chambers (Old Assembly and New Wing), 17 Committee rooms, and 284 Offices in these buildings were rendered unusable;
  Parliament has been operating from Good Hope Chamber and City Hall for joint sittings;
  Some MPs were accommodated on the 6th Floor of 90 Plein Building;
  The balance of 210 offices still needs to be made available for MPs;
  155 will be created from 4th and 5th floors of 90 Plein Building;
  The balance of 55 offices still needs to be sourced from outside the precinct;
  Parliament needs 46 Committee rooms to function optimally; and
  We currently have 15 committee rooms and we need 17 that were lost in the fire
  We have formally requested the Department of Public Works and Infrastructure (DPWI) to release floors 8 – 14 of the 90 Plein Building.
Parliament approached state entities with the capacity for assistance in managing the restoration project taking into account its lack of built environment project management capacity.

## Slide 4: BACKGROUND
After the January 2021 fire, the Department of Public works and Infrastructure (DPWI) professionals conducted the inspection and came up with detailed terms of reference to that will ensure that the following deliverables are produced:
  Assessment report regarding the structural integrity of the building with a view of determining the safety of the building (Phase 1 – initial assessment).
  Assessment report of the building to determine the extent of the damage, restorative scope, associated cost and time line (Phase 2 – detailed assessment)
Both deliverables were achieved/completed as scheduled: Phase 1 was completed on 14 April 2022; and Phase 2 was completed on 25 May 2022.
The completed reports were delivered and presented to both the Secretary to Parliament and the Speaker of the National Assembly. The final report submitted on 27 May 2022.
The same report was further presented to the Joint Standing Committee on Financial Management of Parliament on 23 September 2022

## Slide 5: THE ROLE OF THE DPWI IN TERMS OF THE GOVERNMENT IMMOVABLE ASSET MANAGEMENT ACT (GIAMA)
DPWI is the custodian of the Parliamentary precinct and villages, Parliament has the option to utilize DPWI or implement projects and related maintenance of its facilities on its own if they have the following:
  Parliament requests the DPWI Minister to devolve the restoration project to Parliament in respect of the four projects described in slide 6.
The Minister of DPWI is considering the transfer of custodial powers to Parliament in line with s19 of the GIAMA.

## Slide 6: RESTORATION PROJECT AND PRECINCT MANAGEMENT SCOPE DESCRIPTION
The project entails four components mainly;
  refurbishment of burnt buildings: Old Assembly, Link building; and New Wing
  Remodeling of the 4th and 5th floors to create 155 offices for MPs;
  Redesign of the Parliament Precinct; and
  Total Facilities Management.

## Slide 7: IMPLEMENTATION OF THE PROJECT
A multi-disciplinary team, comprising Parliament, DBSA, National Treasury and DPWI is needed for successful implementation.
After considerable engagements, DBSA was identified by Parliament as a suitable entity to undertake this task based on its footprint and track record.

## Slide 8: KEY PROJECT MILESTONES
Restoration Of Burnt Buildings:
  Site Hand over from DPWI to Parliament & DBSA by Monday 6 March 2023
  Rubble removal;
  Detailed designs and confirmation of costs;
  Procurement;
  Project execution and close-out; and
  Handover and Liability Period
Remodeling of Offices for MPs
Precinct Redesign
Total Facilities Management

## Slide 9: PROJECT TIME FRAMES
The remodelling of offices on 4th and 5th floors is planned to be completed by April 2023
The refurbishment project is planned to be completed in 24 months

## Slide 10: MOTIVATING FACTORS FOR DBSA AS AN IMPLEMENTING AGENT
Implemented many projects on behalf of government Departments and other entities.
The DBSA has streamlined procurement processes and has the capacity to deliver quickly.
They have a multi-disciplinary team to manage the project implementation.
Their fees are based on a cost recovery model and come way below market rates.
DBSA has relationships with the South African Heritage Resources Agency (SAHRA) which is based on their Facilities Management work at the Union Buildings.

## Slide 11: MOTIVATING FACTORS FOR IMPLEMENTING AGENT cont..
Client | Service description | Combined project budget | Duration
Upgrades and refurbishments |  |  | 
SANRAL | Assisting SANRAL to address their failed procurement process | R17 billion | 60 days
National & Provincial Department of Health | Upgrades, refurbishment, maintenance in various health facilities (hospitals, Community Health Centres, and Clinics) | R3 billion | Avg. 3 years
National & Provincial Department of Education | Refurbishment and maintenance of schools facilities | R5 billion | Phased avg. 3 years
National Department of Defense | Refurbishment of 7th floor at 1 of the Military hospitals into an ICU and high care ward | R151 million | 8 weeks Completed in 7
City of Ekurhuleni | Refurbishment, maintenance, and new construction of various municipal infrastructure | R3 billion | Phased avg. 3 years
New builds |  |  | 
National Department of Health | Major extension and construction of mega hospitals and Community Health Centres | R12 billion | Avg. 4 years
Department of Basic Education | Construction of new schools under the ASIDI programme | R7 billion | Phased avg. 3 years
Total Facilities Management |  |  | 
Department of Public Works & Infrastructure | Total Facilities Management: Union Building Precinct, Agrivaal DPSA building, Civitas building | R819 million | Over 3 years
DBSA EXPERIENCE AND TRACK RECORD

## Slide 12: LEGAL FRAMEWORK
The nature of the Project and urgency requires that Parliament implements in the intervention within the shortest possible time in order to restore services to Members of Parliament
We have examined the supply chain processes in line with the FMPPLA in order to achieve the restoration project
The need for members to return to the precinct necessitates the utilization of these procedures

## Slide 13: PROJECT GOVERNANCE AND IMPLEMENTATION MONITORING FRAMEWORK
The Project will be managed based on the following governance framework:
  Joint Standing Committee on Financial Management of Parliament for Oversight;
  Multi-party Steering Committee for regular feedback on the progress of the implementation;
  Project Steering Committee comprising DGs of Parliament, National Treasury and DPWI, and the Group Executive of DBSA responsible for Infrastructure Delivery; and
  Technical Committee comprising relevant teams from Parliament, DBSA, National Treasury, and DPWI

## Slide 14: FINANCIAL IMPLICATIONS
R118 Million has been allocated by National Treasury to Parliament for the provision of alternative Offices for MPs and for other urgent and unforeseen expenditure occasioned by the fire incident.
R2 Billion is the estimated project cost for restoration to be allocated over the next two financial years from NT, this is subject to the completion of a detailed design and rebasing the costs
A detailed project implementation plan will be developed to outline the deliverables/milestones over the 24-month period.
The project management fees of 4.5% of the total project cost for the implementing agent (this is inclusive of VAT and may be subject to negotiation between Parliament and DBSA)