## Slide 1: SERVICED SITES AND BNG UNITS PRESENTATION TO THE HUMAN SETTLEMENTS PORTFOLIO COMMITTEE

## Slide 2
Introduction
The presentation covers the following:
  Serviced Sites delivered by NMBM for a period of over a decade
  Current services projects underway in the 2022/23 FY
  BNG units under construction in the 2022/23 FY
  NMBM BNG unit absorption capacity

## Slide 3
SERVICED SITES

## Slide 4
UPGRADING OF INFORMAL SETTLEMENTS
Since the 2008/09 FY NMBM has achieved the following in servicing sites:
    38 394 Sites serviced to date.
    56 Informal Settlements Upgraded – In-situ.
    19 Greenfields developed for relocations.
    NMBM has finalized the Upgrading of Informal Settlements Strategy, and is currently implementing the projects according to the plan.

## Slide 5
Chart: USDG - Servicing of Sites
| 2008/2009 | 2009/2010 | 2010/2011 | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/1018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 Mid term
Planned | 3000 | 3000 | 3500 | 2500 | 4000 | 4000 | 4000 | 3000 | 4000 | 3000 | 2000 | 500 | 300 | 300 | 100
Actual | 3144 | 3336 | 3813 | 2743 | 4094 | 4012 | 4035 | 3003 | 4004 | 3009 | 2000 | 500 | 300 | 300 | 101

## Slide 6
Sites Serviced for HSDG/Relocations
Item | Project Name | Type of Development | Project Status | Expected Date of Readiness | No. of Serviced Sites
1 | Motherwell NU 12 | Greenfields | Serviced | Ready | 350
2 | Motherwell NU 30 | Greenfields | Serviced | Ready | 1405
3 | Khayamnandi Ext. Phase 1A&B | Greenfields | Serviced | Ready | 471
4 | Khayamnandi Ext. Phase 2 | Greenfields | Serviced | Ready | 1013
5 | Khayamnandi Ext. Phase 3 | Greenfields | Serviced | Ready | 208
6 | Khayamnandi Ext. Phase 4A | Greenfields | Serviced | Ready | 358
7 | Khayamnandi Ext. Phase 4B | Greenfields | Serviced | Ready | 372
8 | Khayamnandi Ext. Phase 6 North | Greenfields | Serviced | Ready | 402
9 | KwaNobuhle Area 11 Phases 1-3 | Greenfields | Serviced | Ready | 1414
10 | KwaNobuhle Area 11 Phases 4 | Greenfields | Serviced | Ready | 564
11 | Jachvlakte HS5B | Greenfields | Serviced | Ready | 332
12 | Joe Slovo Uitenhage | In-situ | Serviced | Ready | 614
13 | Kwanobuhle Area 7 Ph 4 | In-situ | Serviced | Ready | 244
14 | Kwanobuhle Area 8 Ph 4 | In-situ | Serviced | Ready | 266
15 | Doorenhoek | In-situ | Serviced | Ready | 40
16 | Red Location | In-situ | Serviced | Ready | 172
17 | Motherwell High Density | In-situ | Serviced | Ready | 109
18 | Kwanobuhle erf 8228 | In-situ | Serviced | Ready | 111
19 | Pola Park | In-situ | Serviced | Ready | 117
20 | Rosedale | In-situ | Serviced | Ready | 249
21 | Masekhane Village | In-situ | Serviced | Ready | 125
22 | Kabah Phase 6 | In-situ | Serviced | Ready | 54
23 | Kamesh Erf 3179 | In-situ | Serviced | Ready | 42
24 | Kwanobuhle Erf 12931 & 12872 | In-situ | Serviced | Ready | 65
25 | Joe Modise | In-situ | Serviced | Ready | 15
26 | Mandelaville Uitenhage | In-situ | Serviced | Ready | 121
27 | Kwanobuhle Erf 10015 | In-situ | Serviced | Ready | 12
28 | Dikiza street | In-situ | Serviced | Ready | 8
29 | Ntswahlana street ( Erf 7916) | In-situ | Serviced | Ready | 10
30 | Kwanontshinga | In-situ | Serviced | Ready | 105
31 | Sisulu village Phase 2 | In-situ | Serviced | Ready | 18
32 | Roos street | In-situ | Serviced | Ready | 28
33 | Walmer Q phase 3 | In-situ | Serviced | Ready | 188
34 | Qaqawuli Phase 2 | In-situ | Serviced | Ready | 491
35 | Malabar Extension 6 Phase 2 | Greenfields | Serviced | Ready | 250
36 | Raymond Mhlaba | In-situ | Serviced | Ready | 49
Total |  |  |  |  | 10392
Note :- A large number of these sites have been invaded Housing Delivery finalizing comparison linked to houses constructed |  |  |  |  | 

## Slide 7
Planned Serviced Sites |  |  |  | 
2022/2023 Financial year |  |  |  | 
Project Name | Location |  | Planned Target | Status
 |  |  | 2022/2023 | 
Kwanobuhle Area 11 | -33.814 | 25.354 | 150 sites serviced | Implementation of KNB Ph 5 and 6 is dependent on finalisation of SCM/20-28/C Zone 4. Contract awarded awaiting LOA
Jagvlagte (Chatty 11-14) | -33.845 | 25.436 |  | Implementation of Jagvlagte is dependent on finalisation of SCM/20-28/C Zone 4. Contract awarded awaiting LOA
Connections and water meters | Metro wide |  | 500 – Implemented by | Contractors appointed -
 |  |  | I & E | 
Missionvale | -33.88 | 25.548 | Roads and Stormwater ponds | Contractor appointed for Roadworks and Stormwater Ponds – Implementation underway. Expected Completion after 7 months
 |  |  | Approx. 1.1 km to be completed | 
Malabar Ext 6 Phase 2 | -33.914 | 25.5401 | 50 sites serviced | Currently finalising LOA/assignment for SCM/20-28/C Zone 1-3, Contractor appointed – Contractor on site, expected to start mid Feb 2023.
Kwazakhele: Ekuphumleni | -33.883 | 25.597 | 100 sites serviced | Currently finalising LOA/assignment for SCM/20-28/C Zone 1-3, Contractor on site proceeding well.
Nkatha Seyisi | -33.882 | 25.593 | 50 sites serviced | Currently finalising LOA/assignment for SCM/20-28/C Zone 1-3, , Contractor appointed - expected to start mid Feb 2023..

## Slide 8
Project Name | Location |  | Planned Target | Status
Khayamnandi Phase 5 | -33.82 | 25.493 |  | Implementation of Khaymnandi is dependent on finalisation of SCM/20-28/C Zone 4Contract awarded awaiting LOA
Uitenhage Infill Sites / In Situ | -33.758 | 25,389 | 50 Sites serviced | Implementation of Uitenhage Infill is dependent on finalisation of SCM/20-28/C Zone 4. Contract awarded awaiting LOA
 | -33.737 | 25,375 |  | 
 | -33.753 | 25,398 |  | 
 | -33.725 | 25,347 |  | 
Mandela Village | -33.89 | 25.589 | 10 Sites Serviced. | Currently under construction
Walmer Development | -33.989 | 25.598 | 200 Sites Serviced | 80% (continuation project) Reticulation installed, roadworks outstanding . Contractor proceeding slowly. Possible termination
Kwazakhele Infill Sites | -33.884 | 25.603 | 40 Sites Serviced | Currently finalising LOA/assignment for SCM/20-28/C Zone 1-3, Contractor expected to start March 2023.

## Slide 9
UNITS UNDER CONSTRUCTION

## Slide 10: Units Completed
NMBM PROJECTS STATUS |  |  |  |  |  | 
NO | PROJECT NAME | TARGETED UNITS | Completions |  |  | Comments
 |  |  | In Between Stages | FUR's Issued | Balance | 
1 | PE Qaqawuli 780 (390) | 390 | 193 | 218 | 172 | Contractors on site
2 | Mandela Rholihlahla | 4 | 0 |  | 4 | 
3 | KwaNobuhle Erf 8228 (111) | 55 | 52 |  | 55 | Contractors on site
4 | Doorhook 40 | 34 | 0 |  | 34 | Contractors appointed
5 | Kabah Langa Phase 6 | 40 | 0 |  | 40 | 
6 | Polar Park 81 (50) | 50 | 0 | 50 | 0 | Contractors on site
7 | Motherwell NU 30 (200) | 134 | 0 |  | 134 | Contractors appointed
8 | Eluxolweni 58 | 9 | 0 |  | 9 | 
9 | Masangwanaville 172 | 20 | 0 |  | 20 | 
10 | DiKiza Street 8 | 6 | 6 |  | 6 | Contractors on site
11 | Ntswahlana Street 10 | 6 | 6 |  | 6 | Contractors on site
12 | Uitenhage Joe Slovo 398 | 2 | 0 | 2 | 0 | Project complete
13 | P.E Jagvlagte 353 subs | 83 | 0 |  | 83 | Contractors appointed.
14 | P.E Raymond Mhlaba 49 Subs | 43 | 43 |  | 43 | Contractors on site
TOTALS |  | 876 | 300 | 270 | 606 | 

## Slide 11: Expenditure Report Per Project
NMBM PROJECTS FINANCIAL PERFORMNACE |  |  |  |  |  |  | 
NO | PROJECT NAME | TARGETED UNITS | Financials |  |  |  | Comments
 |  |  | Budget | Funds Received | Expenditure | Balance | 
1 | PE Qaqawuli 780 (390) | 390 | 64,800,944.00 | 64,800,944.00 | 40,639,699.71 | 24,161,244.29 | Project funding recently increased by R18 059 236.59
2 | Mandela Rholihlahla | 4 | 485,552.00 | 189,237.94 |  | 189,237.94 | 
3 | KwaNobuhle Erf 8228 (111) | 55 | 8,271,065.00 | 6,725,533.67 | 2,351,044.72 | 4,374,488.95 | Contractors on site
4 | Doorhook 40 | 34 | 5,113,022.00 | 3,586,842.66 |  | 3,586,842.66 | 
5 | Kabah Langa Phase 6 | 40 | 6,701,320.00 | 5,507,458.40 |  | 5,507,458.40 | 
6 | Polar Park 81 (50) | 50 | 7,894,200.00 | 6,112,638.50 | 7,254,106.39 | -1,141,467.89 | 
7 | Motherwell NU 30 (200) | 134 | 20,894,636.38 | 20,894,636.38 |  | 20,894,636.38 | Project Funding recently increased by R7 428 436.38
8 | Eluxolweni 58 | 9 | 1,372,656.00 |  |  | 0 | 
9 | Masangwanaville 172 | 20 | 3,350,660.00 | 4,743,999.25 |  | 4,743,999.25 | 
10 | DiKiza Street 8 | 6 | 1,220,136.00 | 1,005,195.60 |  | 1,005,195.60 | Contractors on site
11 | Ntswahlana Street 10 | 6 | 1,675,330.00 | 1,005,195.60 | 454,980.82 | 550,214.78 | Contractors on site
12 | Uitenhage Joe Slovo 398 | 2 | 524,000.00 |  | 335,083.82 | -335,083.82 | 
13 | P.E Jagvlagte 353 subs | 83 | 13,905,239.00 | 13,905,205.80 |  | 13,905,205.80 | Contractors appointed.
14 | P.E Raymond Mhlaba 49 Subs | 43 | 7,203,919.00 | 6,701,304.00 | 4,370,193.96 | 2,331,110.04 | Contractors on site
TOTALS |  | 876 | 143,412,679.38 | 135,178,191.80 | 55,405,109.42 | 79,773,082.38 | 

## Slide 12
ABSORPTION CAPACITY

## Slide 13: Absorption Capacity
NMBM PROJECTS STATUS |  |  |  |  |  |  | 
NO | PROJECT NAME | PROJECT SIZE | TARGETED UNITS | Projects Readiness |  |  | Comments
 |  |  |  | Ben Approvals | NHBRC Enrollments | Appointment of Contractors | 
1 | PE Qaqawuli 780 (390) | 780 | 390 | 390 | Enrolled | Service Provider Appointed | Contractors on site
2 | Mandela Rholihlahla | 4 | 4 | 4 |  |  | The units in this project will be included in the Raymond Mhlaba Project to be built by the same contractors appointed there already.
3 | KwaNobuhle Erf 8228 (111) | 111 | 55 | 70 | Enrolled | Service Provider Appointed | Contractors on site
4 | Doorhook 40 | 40 | 34 | 34 | Enrolled | Service Providers Appointed | 
5 | Kabah Langa Phase 6 | 54 | 40 | 51 | Submitted |  | An additional funding submitted due to fill which must be imported to site.
6 | Polar Park 81 (50) | 116 | 50 | 81 | Enrolled | Service Provider Appointed | Contractors on site
7 | Motherwell NU 30 (200) | 1837 | 136 | 156 | Enrolled | Service Provider Appointed | NHBRC has been satisfied, contractors appointed also.
8 | Eluxolweni 58 | 9 | 9 | 9 |  |  | Awaiting for funding agreement
9 | Masangwanaville 172 | 172 | 20 | 39 | Submitted |  | Contractors appointed, busy with costing of units.
10 | DiKiza Street 8 | 8 | 6 | 8 | Enrolled | Service Provider Appointed | Contractors on site
11 | Ntswahlana Street 10 | 10 | 6 | 6 | Enrolled | Service Provider Appointed | Contractors on site
12 | Uitenhage Joe Slovo 398 | 2 |  | 2 | Enrolled | Service Provider Appointed | Work complete
13 | P.E Jagvlagte 353 subs | 353 | 83 | 225 | Enrolled | Service Provider Appointed | Contractors will be introduced on site soon.
14 | P.E Raymond Mhlaba 49 Subs | 43 | 43 | 40 | Enrolled | Service Provider Appointed | Contractors on site
TOTALS |  | 3539 | 876 | 1115 |  |  | 

## Slide 14
THANK YOU

## Slide 15
THANK YOU