## Slide 1
Presentation to Portfolio Committee on Home Affairs
Civic Services Plan to Address the Back Office Backlog
PRESENTED BY: ddg:cs
14 March 2023

## Slide 2
Purpose
Problem Statement
Benefits of digitization of records
Civic Services Branch Mandate and Services
Overview of Civic Services Application Processes
Backlogs at Back Office
Implementation plan
Progress to date
Recommendations
CONTENTS

## Slide 3
Purpose
To brief the Portfolio Committee of Home Affairs on the Department’s Plan to address Back Office backlog for Civic related services.

## Slide 4
In 1994, South Africa inherited a segregated civil registration system and since then we have been trying to de-racialize the ethnically fragmented apartheid system of citizenship and build a common National Population Register based on the principles of restorative justice and one unitary state.
As a result, the racial birth registration and citizenship policies were amongst the first to be dismantled and replaced in order to restore dignity of the South African people.
Decolonisation of civil registration followed a three phase approach:
  Colonialism (1895 to 1960)
  Apartheid (1961 to 1993)
  Democratic South Africa (1994 to date)
  The post apartheid civil registration process still followed the manual approach which is paper based
  The amalgamation of Transkei, Bophuthatswana, Venda and Ciskei (TBVC) States, Self Governing Territories and South Africa posed a major challenge in the administration of records within Department of Home Affairs (DHA).
Problem Statement

## Slide 5
REPOSITORIES | TYPES OF RECORDS | DESCRIPTION | VOLUMES
Rosslyn (manual retrieval | Birth, Marriage and Death records | Manual records of persons born between 1989/04/30 to as early as 1800. | 136.39 mil
BVR (manual and electronic) | HANIS Electronic Fingerprint Records | Fingerprint images and photographs for 1st and reissue ID applications and Passports | 48 Mil
 | Manual Birth (Indexing system) | Records for persons born from 2002/03/01 to date ongoing | 32.23 Mil
Electronic Document Management System (EDMS) | Electronic Birth, Marriage and Death records | Records from 1989/05/01 to 2002/02/28 | 59 Mil
Stats SA E-records (phase 1 and Phase 2) | Amended Birth Records | Records from 1998 to date 2004 | 3,4 Mil
Carfile/Microfiche | Electronic births and marriage records | Microfiche contains images of persons born between 1990 to 1999 | 7840
Brits | Fingerprint Cards and Flimsy Records | Manual Fingerprint Cards containing a full set rolled fingerprints (10 p) and Flimsy Records containing full set flat fingerprints (10 p) | 113.37 Mil
TOTAL |  |  | 392.9 mil
The following are the repositories where CS records are kept which is mainly manual and retrieval of records labour intensive. These records exclude records in provinces.
This is part of digitisation project which will reduce the time spent to retrieve records.
Problem Statement Cont.

## Slide 6
  Considering the mandate of the branch and impact of what we do on the lives of people as well as the economy, digitization is important as it will:
  Enable faster access to information when needed
  Give employees the capacity to rapidly discover information to provide clients with services they need in a timely manner.
  Increase the productivity of our employees and help DHA operate faster
  Lower operational cost as printing, preserving and keeping paper documents is expensive. In the event of disaster (fire, flood, etc), paper may be destroyed leading to loss of valuable information
  Improve security in that it can assist in better control sensitive information about our clients.
  Assist with the automation of business processes.
  Make recovery of information due to disaster possible as it could be readily backed up.
Benefits of digitization of records

## Slide 7
  Civic Services (CS) Branch Mandate and Services
BRANCH MANDATE | AREA | SERVICE
Management of the National Population Register (NPR) | Back Office Status Services | Birth registration, Marriages Deaths registration
Management of Travel Documents and Citizenship: |  | passports and travel documents Citizenship,
Documents Management |  | Amendments, Rectification and Records Management
Management of SA identity documents and Home Affairs National Identification System (HANIS). | ID Back Office Processing | Verification and ingestion of fingerprints and images into HANIS / ABIS
 |  | Processing of green Identity documents (IDs) and Smart ID Cards
 |  | Resolution of duplicates
The provision of Civic Services support to the Branch | Civic Services Support | Financial management Human Resource CS strategy development Business Intelligence Monitoring & Evaluation Mobile Units

## Slide 8
Overview of Civic Services Application Processes
All applications are lodged at Front Offices and in Missions abroad, either manually or electronically (live capture). This entails applications for:
Unabridged birth, marriage and death Certificates,
Vault copies of all above registrations.
Green ID Books,
Duplicates
Smart ID Cards
Amendments/Rectifications,
Passports and Emergency Travel Certificates verifications (Missions)
Late Registration of birth
Citizenship.
All manual applications are dispatched via courier to Head Office whilst live capture applications are delivered electronically
Sort according products
Track &Trace (if not T&T by office, application is returned for non-compliance)
Send to various sections for further processing.
The above diagram is a high level overview of the Civic Services application process from front office to back office and visa versa. Each of the products have its own detailed process flow that goes along with it.
Back Office Postal Receipt
Processing of applications in various sections.
Finalized products are send back to front offices for issuance to clients

## Slide 9
Backlogs at Back Office
Civic Services branch faces high volumes of complaints with regard to timeous delivery of products as well as complaints from front offices and members of the public.
In June 2022, the branch identified areas where backlogs exists:
The table below depicts the level of backlogs identified:
Fifteen (15) areas were identified as areas that required intervention to address backlogs. An implementation plan was developed to address the areas requiring intervention.
The report focusses on the implementation plan to address the backlogs as well as progress made against the implementation.
Category | Number of backlogs identified
Unabridged birth certificates (UBC) | 219 263
Unabridged Marriage certificates (UMC) | 9 392
Unabridged Death certificates (UDC) | 2 240
Amendments minor birth certificates | 90 269
Amendments Major | 11 882
Duplicates | 1 093

## Slide 10
IMPLEMENTATION PLAN

## Slide 11
Implementation Plan
ISSUE | ACTION
BVR storage facility has reached capacity | Create space for newly received records from front offices by identifying records that are not transacted with frequently Source service provider for removal of records Movement of records to the identified storage Locate a central records storage facility where all manual/ paper-based records can be stored
Bottle-necks in workflow process for amendments minor | Implement Track & Trace at critical monitoring areas Perform Diagnostic analysis on Amendment Minors and Majors to determine areas which delay finalization of applications
Non-compliant applications received at Back office to resolve duplicates e.g. Copy of mother’s ID, Copy of Birth certificate etc | Distribute weekly error report on non-compliant applications to provinces. Call-in letters and telephone calls are frequently made to the clients and through offices for submission of additional required documents which prolongs the process due to clients not responding on time.

## Slide 12
Implementation Plan/cont…
…
ISSUE | ACTION
Non-compliant applications received at Back office to resolve duplicates e.g. Copy of mother’s ID, Copy of Birth certificate etc | Distribute weekly error report on non-compliant applications to provinces. Call-in letters and telephone calls are frequently made to the clients and through offices for submission of additional required documents which prolongs the process due to clients not responding on time
No UDC/UMC on the spot | IS to develop system to issue UDC/UMC on the spot. Is to develop Pre-Modification functions for UDC and UMC
System deficiencies. | Develop change requests: for system to link duplicate applications captured using an ID number and date of birth in order to close both applications when finalized. To close vault applications upon finalizing
Misfiled Batches/Records | Re arranging of 96 051 batches from 93 shelves (19 210 200)
Fixing of Death Records Indexing System (Template system) | Develop a new template system Develop functionality for drawing of reports by CS on Batch Header and User Statics.

## Slide 13
Implementation Plan/cont…
ISSUE | ACTION
Lack of automation of marriage and death registration system | IS to develop and roll out live capture system for marriage and death registration.
± 100 000 Marriage records (500 batches) not templated. | Index remaining balance of unindexed records.
Uncollected Smart ID Card in front offices | Create public awareness regarding the disposal of uncollected Smart ID Cards after 1 year. IS to perform status analysis (dead/alive) Recalling of uncollected SIDC of deceased persons from front offices. IS to establish a mechanism to deface Smart ID Cards for deceased persons
Duplicates | Identify records that cannot be finalized due to outstanding records. Training of identified officials and allocation of functions Identify officials to draw records for finalization.

## Slide 14
Implementation Plan/cont…
ISSUE | ACTION
Human Resource Capacity (Staff shortages) | CS identified staff members within the back office where employer initiated transfers can be done. Immediate advertisement of positions that became vacant with effect from 1 April 2022. Include Civic Services Back Office in prioritized posts by funding and filling critical positions.
Collapsed Electronic Document Management System (EDMS) | Find a mechanism to retrieve data stored on the Old Dubox hardware. Service provider will be appointed to try to recover the documents from the old equipment
Inaccessible phase 2 records digitized by Stats SA | IS and Stats SA to change the file format of Phase 2 Digitized records to make it accessible.
Ineffective automated birth registration system (Live Capture) | Investigate inefficiencies and resolve. Roll out Live Capture Birth registration to all offices and Health Facilities( HF) where DHA has connectivity

## Slide 15
PROGRESS TO DATE

## Slide 16
Progress to Date
Births, Marriages, Deaths, Amendments, Rectifications and Duplicates
The branch managed to finalise all 9 392 Unabridged Marriage Certificates (UMC), 2 240 Unabridged Death Certificates (UDC), 90 269 Amendments minor, 11 882 Amendments Major and 1 093 Duplicates backlog.
Out of 105 480 Unabridged Birth Certificates (UBC) backlog identified, 79 053 was finalized with a remaining balance of 26 427.
Additional capacity of 200 has been sourced to assist in retrieving manual records from various archives in order to conclude the backlog.
Digitisation to serve as a solution to assist in automating birth registration process which will ultimately result in issuance of birth certificates on the spot.
The department continues to connect health facilities to allow parents to register births before leaving the health facilitates. So far, 161 are connected of which 41 are of priority 1, and 120 are a combination of priorities 2 & 3.

## Slide 17
Progress to Date /cont...
Digitization of records:
Infrastructure (space) has been secured around Tshwane which will serve as digitization hubs where records will be digitized. Refurbishment of the space to convert same into digitization hubs is underway.
Delivery has been taken of equipment (laptops, printers and scanners) that will be used to digitize records.
A total number of 1 272 unemployed youth has been on boarded and has undergone training to assist with digitization.
Human Resource capacity:
A total number of 652 posts were funded and advertised to capacitate front offices as part of phase 1 of business case. Filling of these positions are underway.
  The Branch is also in the process of re-prioritizing of lower level positions that became vacant through natural attrition, with purpose of funding critical management positions.
  Overtime is also used to assist in tackling the backlog.
  The department is in the processes of concluding phase 2 of the business case which will ultimately increase capacity to 60%

## Slide 18
Progress to Date /cont...
Records management:
A total number of 1 154 430 late registration of birth and marriage records were transferred to the Rosslyn records facility.
96 051 batches (19 210 200 records) in the BVR storage facility have been re-arranged to address the issue of misfiling.
All 100 000 Marriage records (500 batches) which were not indexed (templated) are now indexed.
Full access has been made available to the phase 2 digitized records by Stats SA. In total, we now have access to a total number of 3 173 254 digitized records, inclusive of phase 1 digitized records. Whilst awaiting the bigger digitization project the department is continuously collaborating with Stats SA.

## Slide 19
Progress to Date /cont...
Systems:
The department is currently piloting automation of birth registration through live capture.
The Death Records Indexing System (Template system) was fixed.
System deficiencies around duplicate vault/UBC applications is now resolved as system is now able to link duplicate applications captured using an ID number and date of birth in order to close both applications when finalized and able to remove/close finalized vault copies.
Gaps were identified in the National Population Register as well as the Live capture system to allow automation in the Civic Services environment. This forms part of the departments Annual Performance Plan in 2023/24 financial year.

## Slide 20
Recommendation
It is recommended that the Portfolio Committee on Home Affairs note the implementation plan and the progress made in addressing the backlog at back office.

## Slide 21
Ndi khou livhuha
Dankie
Ke a leboga
Ndiyabulela
Ngiyabonga
Thank you
Inkomu
Ke a leboha