## Slide 1
PRESENTATION ON PERMIT &
VISA BACKLOG
ERADICATION
PLAN TO THE PORTFOLIO COMMITTEE – 14/03/2023

## Slide 2
2
  Purpose
  Problem Statement
  Executive Summary
  PR Applications as at 2016 – 31 May 2022
  PR applications workflow funnel
  Projections for PR backlogs
  Tr applications as at 2021 – October 2023
  Tr application workflow funnel
  Projection for the tr backlogs
  Current interventions
  Additional interventions from 03 april 2023 for PR
  Additional interventions from 03 april 2023 to tr
  Amendment of the delegations and sop’s
  Implementation plan
  Conclusion
  Way forward
  Recommendation
INDEX

## Slide 3
The purpose of the presentation is to provide the Portfolio Committee on the status of the backlogs for Permanent Residence and Temporary Residence and applications.
1. PURPOSE
3

## Slide 4
2. PROBLEM STATEMENT
4
Under the Disaster Management Regulations which was brought about by the Covid19 pandemic, capacity levels within the Permitting unit was vastly reduced capacity due to the requirement of social distancing that was implemented. This contributed to the processing output being low and contributed to the accumulation of the backlog.
During the Covid19 pandemic both applications for Temporary Residence Visas and Permanent Residency permits was suspended. When the suspension was lifted for both, a high influx of applications were experienced, which also contributed to the increased backlog.
Subsequent to the findings of irregularities from the Lubisi Report at both inland applications and applications submitted at the foreign missions, the department implemented strict measures to curb corruption. As a consequence, the Delegations were revised with increased quality assurance and approval levels and were implemented on 12 January 2022.
The capacity at the Permitting unit was also affected with suspensions (1 Director, 2 ASD’s and 1 SAO) and dismissals (1 Chief Director and 1 SAO).

## Slide 5
The Chief Directorate: Permits adjudicates visas and permanent residence permit applications submitted to Home Affairs.
All temporary residence visa applications submitted locally at Visa Application Centres (VACs) of VFS are adjudicated in the CD: Permits at Home Affairs Head Office.
All permanent residence application submitted LOCALLY are adjudicated in the CD: Permits at Home Affairs Head Office. Abroad applications are finalised at the Missions.
The conveyor belt of visa and permit applications does not stop. There are more than 350 TR applications and 50 PR applications coming to Head Office daily, on average.
TEMPORARY RESIDENCE VISAS are considered to be in a backlog if they are not processed within 8 weeks.
PERMANENT RESIDENCE PERMIT applications are considered to be in a backlog if they are not processed with 8 months
Permanent Residence current status
For Permanent Residence, total applications older than 8 Months is at 40 340 as at 01 March 2023. Total applications within the 8 month cycle is standing at 9 145.
In total including the backlog the figure stands at 40 365 + 9164 = 49 529
Temporary Residence current status
For Temporary Residence, in order to have a definite count of the backlog, visa applications that were older than 8 weeks were isolated and locked into a figure of 55 172 2021 October 2022. Total applications received within 8 weeks stands at 23 988 as of 01 March 2023.
In total including the backlog the figure stands at 55 172 + 20 642 = 75 814
3. INTRODUCTION
4

## Slide 6
4. PERMANENT RESIDENCE APPLICATIONS AS AT 2016 -31 MAY 2022
Inbox Stage | Backlog | Current | Grand Total
Ready to be Assigned | 1297 | 6329 | 7626
Still with Adjudicator | 2648 | 1573 | 4221
1st Quality Assurance (ASD) | 18 459 | 610 | 19 069
2nd Quality Assurance (D) | 9377 | 398 | 9775
3rd Quality Assurance (CD) | 5677 | 221 | 5898
4th Quality Assurance (DDG) | 1357 | 2 | 1359
Decision (DG) | 1550 | 31 | 1581
Grand Total | 40 365 | 9164 | 49 529
5
BREAKDOWN OF PERMANENT RESIDENCE BACKLOG |  |  |  |  |  |  | 
2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | TOTAL
3524 | 5187 | 7303 | 10621 | 2968 | 3 | 10759 | 40 365

## Slide 7: 5. PR APPLICATION WORKFLOW FUNNEL
Ready to be assigned
Adjudicator
ASD
DIR
CD
DDG
DG
7626
4221
19 069
9775
5898
1359
1581
6

## Slide 8
6. PROJECTIONS FOR THE PR BACKLOG
There are 40 365 applications that are older than 8 months.
There are 16 PRP Adjudicators in the Central Adjudication hub
Currently, only 8 adjudicate PRP daily, with the other 8 working on eVisas
Each adjudicator has a norm of 7 applications per day x 5 working days = 35 per week per adjudicator. This equals to 280 per week
18 additional adjudicators have been appointed as of 01 March 2023 and are currently on training until 31 March 2023.
They will deployed to the eVisa hub on 03 April 2023 and to assist with new applications received.
The 8 adjudicators who were seconded to eVisa adjudication will return to the PR Section.
If its 16 Adjudicators with 7 applications per day = 112 will be processed = 560 per week
Realistically, the 16 adjudicators at a rate of 112 applications per day will take 360 working days to clear the backlog of 40 365.
7

## Slide 9
7. TEMPORARY RESIDENCE APPLICATIONS AS AT 2021 – OCTOBER 2022
Inbox Stage | Backlog 2021/22 | 2023 | Grand Total
Ready to be assigned | 33649 | 18 402 | 52 051
Adjudicator | 19 082 | 1692 | 20 774
1st Quality Assurance (D) | 1000 | 274 | 1274
2nd Quality Assurance (CD) | 68 | 21 | 89
3rd Quality Assurance (DG) | 1373 | 253 | 1626
Total Applications | 55 172 | 20 642 | 75 814
8

## Slide 10: 8. TR APPLICATION WORKFLOW FUNNEL
Ready to be assigned
Adjudicator
DIR
CD
DG
1000
19 082
33 649
68
9
1373

## Slide 11
9. PROJECTIONS FOR THE TR BACKLOG
The current total pending applications is 78 815.
There are 23 Adjudicators in the Central Adjudication hub
Each adjudicator has a norm of 10 applications per day x 5 working days. 23 Adjudicators with 10 applications per day = 230 per day will be processed = 1150 per week
Realistically, the 23 adjudicators at a rate of 230 applications per day will take 339 working days to clear the backlog of 78 815.
Number of applications received for TR per day is 350 x 22 days = 7 700 per month x 12 = 92 400 per year.
With the current capacity the Department will not be able to finalise this volume within the turnaround time
10

## Slide 12: 10. CURRENT INTERVENTIONS
Staff have been seconded from the Provinces and Head Office to assist at various levels of adjudication.
A PR committee was established during 2022 to assist with finalizing applications and strengthen the quality of decision. This committee comprised of the DDG’s of IMS, CS and HR as well as the PM:WC and CD:Permits.
We have implemented Operational Management which entails daily meetings and monitoring of work to ensure staff are meeting their daily norms.
Data analysis and reconciliation to monitor targets is done on a weekly basis.
A weekly dash board is complied and presented to management to monitor targets and keep track of the backlogs.
The draft amended delegations and standard operating procedures has been submitted for approval which is expected by the end of March 2023.
A workshop for adjudicators to familiarize them with the amended delegations and SOPS’s will also be held
The Regulations has been amended to include the recommendations from the Vulindlela report and is currently being finalized by the Legal team.
The Department is currently undertaking the process of overhauling the immigration policy to address the abuse o the Visa regime.
11

## Slide 13: 11. ADDITIONAL INTERVENTIONS FROM 03 APRIL 2023 FOR PR
Permanent Residence
The use of the 29 foreign office deployment staff is as follows:
  The backlog at adjudicator level is 11 837 - 5 Senior Admin Officers processing 10 applications per day for 60 days will reduce by 3000 by 15 June 2023
  The backlog at first quality assurance (ASD) level is 19 069 – 20 Assistant Directors processing 10 applications per day for 60 days will reduce by 12 000 by 15 June 2023
  The backlog at 2nd quality assurance level is 9775 – 4 Deputy Directors processing 25 applications per day for 60 days will reduce by 6000 by 15 June 2023.
It must be noted that 21 000 applications completed by the officials from the foreign office group will increase the 3rd, 4th and DG inbox.
12

## Slide 14: 12. ADDITIONAL INTERVENTIONS FROM 03 APRIL 2023 FOR TR
The Department is currently training 61 DHA officials for foreign office deployment. Their three month training will end on 31 March 2023.
Official deployment to a mission is on 01 July 2023. We intend using all 61 of the trainees from 11 April to 15 June 2023 to assist with the backlog.
Temporary Residence
The use of the 32 foreign office deployment staff to assist with the TR backlog is as follows:
- The backlog at adjudicator level is 51 633 - 17 Senior Admin Officers processing 10 applications per day for 60 days will reduce the backlog by 10 200 by 15 June 2023
  - The backlog at Assistant Director (ASD) level is currently 519. This will increase by 10500. 15 Assistant Directors processing 10 applications per day for 60 days will reduce by 9 000 by 15 June 2023 (The allocation of ASD’s is in preparation pending the approval of the delegations and work moved from the SAO levels)
It must be noted that 10 200 completed by the officials from the foreign office group will move to the ASD level.
The impact of utilising these 32 officials will reduce the backlog by completion by 2 months
13

## Slide 15: 13. AMENDMENT OF THE DELEGATION AND STANDARD OPERATING PROCEDURES
Prior to the 12 January 2022, the delegation for PR was 6 levels and TR was 1 level.
Subsequent to the Lubisi report where corruption was identified, new delegations were implemented effective 12 January 2022, which increased the TR levels to 4 levels, however PR remained at 6 levels.
The increase in the TR delegations to 4 levels entailed detailed verification and quality assurance and contributed to the increase in backlogs.
The reviewed delegations has now been further amended due to the controls measure put in place to strengthen the verification process. This amended delegation and SOP will still ensure quality assurance at all levels.
The amendments of the delegation will reduce TR levels to 2 and PR will be reduced to 4 levels.
With the amendment of the Delegations as well as the Regulations, the SOPS will be revised accordingly to ensure alignment.
14

## Slide 16: 14. IMPLEMENTATION PLAN
NO. | INTERVENTION | TIMEFRAME | RESPONSIBILITY
1 | Operations Management | On going | Acting CD Permits
2 | Weekly dashboard | On going | ADDG:IMS
3 | Data Recon and monitoring of targets | On going | ADDG:IMS
4 | Amended Delegations approved | 31 March 2023 | ADDG:IMS
5 | Draft Regulations submitted to Minister for approval | 31 May 2023 | ADDG:IMS
6 | Increase in Capacity for 2 months | 3 April 2023 | Acting CD Permits
7 | Creation of eVisa hub to accommodate the 18 additional adjudicators | 3 April 2023 | Acting CD Permits
15

## Slide 17: 15. CONCLUSION
The current focus of utilising the 61 foreign office deployment staff for a period of 60 days will reduce the backlog at adjudication and first level quality assurance.
An assessment will be done in the first week of May 2023 and staff will be seconded to the preceding adjudication levels accordingly.
It is anticipated that with the use of the foreign office staff and the current staff, we will complete the backlog in 15 months ending June 2024
Applications received for the year 2022 is 97 785 for TR.
  This averages to 350 per day x 22 working days x 12 months = 92 400 applications expected for the year 2023
Applications received for the year 2022 is 20 503 for PR.
  This averages to 70 per day x 22 working days x 12 months = 18 480 applications expected for the year 2023
16

## Slide 18: 16. RECOMMENDATION
Portfolio Committee to take note of the interventions and implementation plan to reduce the backlogs within the Permitting Chief Directorate.
17

## Slide 19
Ndo livhuwa
Dankie
Ke a leboga
Ndiyabulela
Ngiyabonga
Thank you
Inkomu
Ke a leboha