## Slide 1
2020-2025 STRATEGIC PLAN MID TERM PRESENTATION

## Slide 2
PURPOSE
DHA MANDATE
DHA CONTRIBUTION TO MTSF PRIORITIES
MID-TERM PROGRESS AGAINST THE 5 YEAR STRATEGIC PLAN TARGETS
CONCLUSION
PRESENTATION OUTLINE

## Slide 3
The Purpose of the presentation is to request the Portfolio Committee to note the:
Mid-term progress report against the 2020- 2025 Strategic Plan; and
Progress Report against the Revised Medium Term Strategic Framework (MTSF) 2019-2024
3

## Slide 4
The DHA’s services are divided into two broad categories: civic services and immigration services.
Mandate 1: Management of citizenship and civil registration
Mandate 2: Management of international migration
Mandate 3: Management of refugee protection
DHA MANDATE

## Slide 5
DHA Contribution to MTSF 2014 to 2019
Vision, Mission, Mandate, Values and Outcomes
Vision
A South Africa where identity, status and citizenship are key enablers of citizen empowerment and inclusivity, economic development and national security
Mission
The DHA carries out its mission in line with its commitment to citizen empowerment and inclusivity, economic development and national security, by:
- Being an efficient and secure custodian of citizenship and civil registration
- Securely and strategically managing international migration
- Efficiently managing asylum seekers and refugees
- Efficiently determining and safeguarding the official identity and status of persons
Mandate
The DHA’s services are divided into two broad categories: civic services and immigration services.
Mandate 1: Management of citizenship and civil registration
Mandate 2: Management of international migration
Mandate 3: Management of refugee protection
Values
The Department of Home Affairs is committed to being:
- People-centred and caring
- Patriotic
- Professional and showing leadership
- Effective, efficient and innovative
- Ethical and having integrity
- Security conscious
- Development oriented
Outcomes
- Secure management of international migration resulting in South Africa’s interests being served and fulfilling international commitments
- Secure and efficient management of citizenship and civil registration to fulfil constitutional and international obligations
- Efficient asylum seeker and refugee system in compliance with domestic and international obligations
- Secure population register to empower citizens, enable inclusivity, economic development and national security
- DHA positioned to contribute positively to a capable and developmental state

## Slide 6
DHA OUTCOMES
The DHA contributes directly to 2 of the 7 MTSF priorities; that is, priority 2 and 6. However, through our mandate, we contribute indirectly to all priorities. For instance, through the International Migration mandate, we contribute to priority 7: A better Africa and World:
Priority 1: A Capable, Ethical and Developmental State
Priority 2: Economic Transformation and Job Creation
Priority 3: Education, Skills and Health
Priority 4: Consolidating the Social Wage through Reliable and Quality Basic Services
Priority 5: Spatial Integration, Human Settlements and Local Government
Priority 6: Social Cohesion and Safe Communities
Priority 7: A better Africa and World
Cross Cutting Focus
Women, Youth & People with Disabilities

## Slide 7
MID-TERM PROGRESS REPORT AGAINST THE 5 YEAR STRATEGIC PLAN TARGETS

## Slide 8
APEX Priority | Revised MTSF Commitment 2024
Economic transformation and job creation | Implementation of a revised visa regime through 95% of visa applications (critical skills) adjudicated within 4 weeks by 2022/23
Social cohesion and safer communities | 100% of selected ports of entry equipped with biometric functionality by March 2024 DHA Automated Biometric Identification System (ABIS) implemented by 2022/23
8
Notes: 8

## Slide 9
MTSF COMMITMENTS 2019 TO 2024
APEX Priority | Link to Outcome | DHA contribution | MTSF Commitment as per 2019-2024 MTSF | Revised MTSF Commitments as per 2019-2024 MTSF
(1) Economic Transformation and Job Creation | Outcome 4 – Decent employment through inclusive economic growth | Securing the identity of citizens and foreigners Design and implementation of the National Identity System (NIS) Issuance of critical skill visas and implementation of a visa regime in support of economic growth | 95% of critical skills visas adjudicated within 4 weeks by 2022 Implementation of revised visa regime | Implementation of a revised visa regime 95% of visa applications adjudicated within 4 weeks by 2022/23
(5) Social Cohesion and Safe Communities | Outcome 3 – All people in SA are and feel safe | Secure the borders of the country through the establishment and operationalisation of the BMA Continue with the implementation of a risk based approach to immigration Provide enabling documents to access rights and services, for example early birth registration and smart ID cards | BMA established by 2020 BMA operational by 2021 at 11 ports of entry and 5 segments of the land borderline ((BMA fully operational by 2024) 100% of selected ports of entry equipped with biometric functionality Implementation of DHA Automated Biometric Information System (ABIS) by 2022/23 | BMA established by 2021/22 BMA operational by 2023/24 at 18 ports of entry; 6 segments of the land border law enforcement area and 1 community crossing point BMA rolled out to an additional 7 ports of entry and 1 additional segment of the land border law enforcement area by 2024 100% of selected ports of entry equipped with biometric functionality by March 2024 DHA Automated Biometric Information System (ABIS) implemented by 2022/23

## Slide 10
MTSF Priority: Economic Transformation and Job Creation, A better Africa and World |  |  | Status
Outcome: Secure management of international migration resulting in South Africa’s interests being served and fulfilling international commitments |  |  | 
Five Year Target (as per Strategic Plan tabled in March 2020) | Five Year Target (Reviewed) – as in the 2022/23 APP | Actual achievement as at 30 September 2022 | 
100% compliance with set service standards for risk-based and strategic issuance of visas and permits to grow the economy by 2024/25 as outlined in the annual performance plans for: Permanent residence permits. Business and general work visas. Critical skill visas. | 95% of critical skill visas adjudicated by 2024/25. |  | 
Critical Skills Visas |  | 
2020/21 | 2021/22 | 2022/23 (Apr-Sep)
91.1% (2 299 out of 2 523) | 57.2% (2 790 out of 4 876) | Q1= 0% (0 out of 1 182) Q2= 2.97% (40 out of 1 344) Q3 = 19% (206 out of 1 106)
A total of 5 129 critical skills visas were adjudicated in 4 weeks within 2 years and half |  | 

## Slide 11
APEX Priority: (5) Social Cohesion and Safe Communities |  | 
Outcome: Secure management of international migration resulting in South Africa’s interests being served |  | 
Revised MTSF Commitment (as per 2022/23 revised APP): BMA operational by 2023/24 at 18 ports of entry; 6 segments of the land border law enforcement area and 1 community crossing point. BMA rolled out to an additional 7 ports of entry and 1 additional segment of the land border law enforcement area by 2024 |  | 
2020/21 | 2021/22 | 2022/23
The BMA Bill, 2016 was adopted by Parliament in March 2020. The Bill was subsequently submitted to the Office of the President for assent and signing. | In 2021/22, the BMA was rolled-out to 5 segments of the land border law enforcement areas: (1) RSA and Zimbabwe, (2) eManguzi, (3) Skukuza, (4) KZN and eSwatini and (5) Mpumalanga and eSwatini. BMA was rolled-out to one (1) community crossing points: Tshidilamolomo | Q1 progress: The Port of Entry roll-out plans have not been finalized for approval. The Risk mitigation plans have not been finalized for approval BMA Border Guards were appointed for deployment along the Free State/Lesotho segment of the land border law enforcement area. The Border Guards were still undergoing induction and training by the end of the quarter Q2 Progress:. The Section 97 Proclamation pertaining to the transfer of functions from the Minister of Agriculture, Land Reform and Rural Development; Health; and the Department of Forestry, Fisheries and the Environment to the Minister of Home Affairs was signed by the President and has been gazetted. Q3 Progress: BMA Border Guards were deployed on 19 September 2022 to the Eastern Cape/Lesotho and KZN/Lesotho land border law enforcement areas; and the deployment is continuing.
11

## Slide 12
APEX Priority: (5) Social Cohesion and Safe Communities |  | 
Outcome: Secure management of international migration resulting in South Africa’s interests being served |  | 
Revised MTSF Commitment (as per 2022/23 revised APP): DHA Automated Biometric Information System (ABIS) implemented by 2022/23 |  | 
2020/21 | 2021/22 | 2022/23
No APP target: The department requested SITA to procure the services of a suitable service provider to design, provision, customise, integrate, migrate existing data, commission, maintain and support ABIS in 2015/16. The bid process was audited at SITA by the AGSA, which raised findings and limitation of scope issues, inter alia because of a missing master file for the accreditation phase. SITA management accepted the AGSA findings and disclosed the transaction as non-compliance to SCM laws and regulations. As the expenditure was incurred by the department, the department disclosed the expenditure as irregular expenditure under investigation in the 2018/19 financial year and as confirmed irregular expenditure in the 2019/20 financial year. | No APP target: The ABIS Project achieved the following deliverables: ABIS Infrastructure (Data Centres and Security Integration) was completed and ready for production. 47mil of the 48 mil Active HANIS Records were migrated from HANIS into ABIS with exception records still under investigation. The development of Applications and Interfaces into ABIS was completed and the Interfaces were performing System Stability & performance testing. Business Process mapping was completed and business users were trained. | ABIS Phase 1 is at 99.99% complete due to the need to cater to people with no fingerprints/amputations, but is complete for the general population. On 21 November 2022, the first release which includes fingerprint capability was deployed to live and this means that the ABIS is functional and the department does not rely on the HANIS anymore and uses ABIS to verify identification. The DHA is in the process of implementing phase 2 which will include additional functionalities such as Iris, infant footprint and palm-print backend recognition capability.
12

## Slide 13
APEX Priority: (5) Social Cohesion and Safe Communities |  | 
Outcome: Secure management of international migration resulting in South Africa’s interests being served |  | 
Revised MTSF Commitment (as per 2022/23 revised APP): 100% of selected ports of entry equipped with biometric functionality by March 2024 |  | 
2020/21 | 2021/22 | 2022/23
The BMCS was tested at 4 international airports. The roll out in the reporting period was not achieved due to contract that was not concluded with service provider to procure IT equipment. | While the target of BMCS partially rolled out to four airports (70%) of counters at each airport) was not achieved in the 2020-21 financial year, the following progress was made: BMCS Servers were installed and configured in two airports User theoretical training was provided Service provider for IT equipment contracted. | Q1 progress: Stabilisation report for airport rollout was signed off by DDG: IMS. The Department visited airports to assess the performance of BMCS and record all the gaps and system errors. Q2 Progress: BMCS was rolled out to Maseru bridge to start testing the performance of the system. Stabilization report for land port compiled based on the findings at the port and was submitted to DDG: IMS. 15 Ports of entry were upgraded to 2MB lines. Q3 Progress: BMCS has been deployed at 16 ports of entry which are: Oshoek, Nerston, Emahlathini, Mahamba, Cape Town, King Shaka, OR Tambo and Lanseria International Airports, Ficksburg, Maseru Bridge, Caledonsport, Golela, Cape Town Harbour, Beitbridge, Ramatlabama and Skilphadhek.
13

## Slide 14
It is recommended that the Portfolio Committee notes the presentation. More efforts will be focused in the following areas in the next financial year.
The process of establishing the BMA as a Schedule 3A entity is at an advanced stage.
The BMA will therefore be a public entity reporting to Minister of Home Affairs effective from 1 April 2023.
The BMA has tabled its new Strategic Plan and Annual Performance Plan in parliament which will be effective from the 1st of April 2023.
The DHA will continue to provide shared services (finance, legal, HR support, etc.) to BMA.
Phase 2 of ABIS will be rolled over to the 2023-24 financial year. The focus will be on the following:
  Iris
  Infant footprint and
  palm-print
CONCLUSION

## Slide 15
Ndo livhuwa
Dankie
Ke a leboga
Ndiyabulela
Ngiyabonga
Thank you
Inkomu
Ke a leboha