## Slide 1: NSF REPORT PCHESI SESSION
29 MARCH 2023

## Slide 2
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update
Summary
PURPOSE
To provide the PCHESI with progress update on:
(a) The implementation of the MTT report recommendations.
(c) The implementation of the forensic report recommendations.
(b) The NSF Audit Action Plan.
BACKGROUND
1. The last session of the PCHESI was held on 26 October 2022.
2. The National Skills Fund presented:
• The report of the NSF Ministerial Task Team (MTT).
• The progress report on the implementation of the forensic investigation report.
• The NSF audit action plan progress report.
3. These are the three areas which PCHESI continues to engage the Accounting Authority of the NSF.

## Slide 3
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update
Summary
DISCUSSION
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
4. The Director-General approved the NSF Task Team that systematic implementation of the in October 2022.
5. To date the NSF Executive Committee constituted the NSF Task Team committee which established four streams in order to give effect to the recommendations of the Ministerial Task Team recommendations. These four implementation streams are:
• Governance stream.
• Business Model, Operating Model and Value Chain stream.
• Strategy, Innovation and Organizational Performance stream.
• Human Resources stream.
• Change Management stream.

## Slide 4
Summary
PROGRESS REPORTS
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
6. To date the Governance stream has:
Set out stream activities to:
• Confirm and finalize the National Treasury conditions on NSF as Schedule 3A Entity.
• Legislative processes on the NSF to subsist as a juristic person.
• Development of the NSF Constitution/Charter.
These are long term outcomes with a timeline of 31 March 2024
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 5
Summary
PROGRESS REPORTS
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
7. To date the Business Model, Operating Model and Value Chain stream has:
Set out stream activities to:
• Consult with all NSF units on the operating model.
• Identify any gaps within the model between current unit operations and proposed operating model.
• Address any gaps through the revision of or development of Standard Operating Procedures (SOPs).
• Collect as-is Business Processes (BPs) and identify gaps that may exist, then consolidate into the NSF value chain.
• Consultation and adoption process.
These are short to medium term outcomes with a timeline of 30 November 2023.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 6
Summary
PROGRESS REPORTS
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
8. To date the Strategy, Innovation and Organizational Performance stream has:
Set out stream activities to:
• Establishment the Research, Planning and M&E Committee.
• Develop an NSF M&E framework.
• Conduct strategic engagement and review the NSF Research and Labour Market Intelligence in conjunction with DHET – Part of Research Agenda of NSF.
• Approved NSF Research Agenda (as aligned to DHET and PSET including NSA to reduce duplication)
• Adopt the proposed strategic priorities recommended by the MTT.
• Undertake research on catalytic mandate concept.
• Undertake research and policy in regard to legislative and policy mandates.
• Utilize research to inform the revision of the NSF theory of change (Mandate, Vision, Mission, Outcomes, and Outputs and Impact statement) linked to 2025/2030 SP period commencing in January 2024 planning cycle.
• Reconfigure the NSF Information Communication Technology (ICT) environment and infrastructure.
These are medium to long term outcomes with a timeline of 31 March 2024.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 7
Summary
PROGRESS REPORTS
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
9. To date the Human Resource stream has:
Set out stream activities to:
• Established as a juristic person in order to effect section 197 of the Labour Relations Act.
• Consult with organized labour on the process of transfer of the NSF function from DHET to the NSF as Schedule 3A entity.
• Effect transfers of staff from DHET to NSF as an independent Schedule 3A entity by issuing contracts of employment to all NSF staff.
• Review recommended organizational structure with existing approved NSF structure to identify gaps / additional posts recommended per unit.
• Review NSF organizational structure, approve and adopt new structure for implementation.
Develop job profiles for recommended new posts aligned to business processes and SOPs per unit.
• Advertise additional / new posts as per recommendations and alignment with work study outcomes, and as per new approved organizational structure.
• Recruit to new / additional posts.
• Establish a fully functional self-sufficient HRM directorate.
These are medium to long term outcomes with a timeline of 31 March 2024.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 8
Summary
PROGRESS REPORTS
PART 1 (The MINISTERIAL TASK TEAM’S report recommendations implementation)
10. To date the Change Management stream has:
Set out stream activities to:
• Draft a communication and consultation plan for internal NSF staff related to changes resulting from MTT report implementation.
• Draft a communication and consultation plan for stakeholders and partners related to changes in the NSF resulting from MTT report implementation.
These are medium term outcomes with a timeline of 30 November 2023.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 9
Summary
PROGRESS REPORTS
PART 2 (The progress report on the implementation of the forensic investigation report)
11. All NSF officials (5) and those outside the NSF (2) (Ekurhuleni West TVET College), implicated in the forensic report were initially served with precautionary suspensions and later served with charge sheets.
12. These officials have responded to the charge sheets, some using their own legal services support.
13. The precautionary suspensions and the charge sheets were prepared by the office of the State Attorney in consultation with the legal firm of Advocate Mokotedi Mpshe.
14. The above processes were facilitated through document preparation from the NSF and the DHET.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 10
Summary
PROGRESS REPORTS
PART 2 (The progress report on the implementation of the forensic investigation report)
15. Upon the finalization of the SCM processes bringing in NEXUS forensic firm as a lead evidence witness who carried out the inspections in loco, the disciplinary session will start before the end of March 2023.
16. On the external front, the Director General had engagements with the Special Investigating Unit (SIU), presided over by Advocate Andy Mothibi. The last engagement was on 14 February 2023 where the scope of engagement on the NSF was discussed.
17. Further discussions were arranged between the Director General and Advocate Mothibi to finalize document exchanges and investigation procedural matters.
18. The Directorate for Priority Crime Investigation (HAWKS) held the initial session with the NSF Acting Executive Officer on 08 December 2022. Subsequently, an affidavit mapping out the full value chain of skills development funding processes was composed.
19. The NSF-HAWKS documentation exchange process will be initiated by the HAWKS once their system is ready.
20. The scope of the HAWKS investigation is on the 10 selected project arising from the forensic report.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 11
Summary
PART 3 (AUDIT ACTION PLAN)
21. Arising from Auditor General South Africa adverse findings on the NSF 2020/21 Annual Report and Financial Statements, the NSF developed an Audit Action Plan which to date reflects the following progress in addressing these key findings:
i. Findings on the recruitment of senior management personnel (60% vacancy rate and slow recruitment process):
To date 35 of the 69 posts for year 2021/22 have been filled (51%). The following Senior Management post have been completed or are at various stages of selection:
Chief Financial Officer was appointed and assumed duty on 01 November 2022.
✓ Director: Fund Management was appointed and assumed duty on 01 October 2022
✓ Director: Information Communication and Technology was appointed and assumed duty on 03 January 2023.
✓ Director: Financial Planning and Reporting interviews scheduled before end of March 2023..
✓ Director: Financial Administration has been advertised.
✓ Director: Work Integrated Learning has been advertised.
✓ Director: Organizational Strategy has been advertised.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 12
Summary
PART 3 (AUDIT ACTION PLAN)
Chief Financial Officer was appointed and assumed duty on 01 November 2022.
Director: Fund Management was appointed and assumed duty on 01 October 2022.
Director: Information Communication and Technology was appointed and assumed duty on 03 January 2023.
Director: Financial Planning and Reporting interviews scheduled before end of March 2023..
✓ Director: Financial Administration has been advertised.
✓ Director: Work Integrated Learning has been advertised.
✓ Director: Organizational Strategy has been advertised.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 13
Summary
PART 3 (AUDIT ACTION PLAN)
ii. Findings on the financial reporting within the GRAP standards (accruals, infrastructure assets, trades and receivables, deferred expenditure, provisions and prior period errors):
Application of the GRAP standards are carried out as advised by the AGSA in the treatment of financial transactions and accounts allocation.
Invoice capturing and reconciliation are done on monthly basis and variance are corrected timeously.
Completed journals are subjected to internal audit review and adjustment carried out were discrepancies are identified.
Review of financial workbooks is continuously carried out before financial statement are adjusted.
SETA levy payment records are now accessed from the Skills Branch in order to reconcile the NSF portion of revenue (> R500K levy payment threshold).
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 14
Summary
PART 3 (AUDIT ACTION PLAN)
iii. Findings on institutional performance information (limitation of scope due to lack of usefulness, misstatements, completeness, non-response to RFIs and COAFs and inadequate IT control environment):
Internal mechanisms have been established to review the Strategic Plan (SP), Annual Performance Plan (APP) and Technical Indicator Descriptors (TID).
✓ SP revised and tabled at parliament.
✓ APP indicators and targets aligned the revised SP.
✓ Poorly defined TID redefined.
✓ Performance information review and validation framework established.
✓ Performance information management process flows have been developed.
The Microsoft Dynamics IT system is gradually being deployed as a platform for a broader NSF MI system.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 15
Summary
PART 3 (AUDIT ACTION PLAN)
iv. Findings on skills development implementation (limitation of scope as a result of misstatements, no project expenditure records, absence of project files):
✓ Internal audit to continuously perform a review on prior year findings.
Framework of supporting evidence for SDPs project portfolio information collection and storage was established and workshops carried out internally with regional project managers.
Consequence management instituted on project managers who failed to reconcile project expenditure and implementation.
TVET College completed infrastructure assets transferred to the respective TVET colleges.
✓ Central project record keeping established and new projects boarded on MS Dynamics.
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update

## Slide 16
Summary
PART 3 (AUDIT ACTION PLAN)
v. Findings on governance, risk and compliance (treatment of irregular expenditure, misstatements from inadequate definition of toolkit):
Internal audit determination test are performed, seven projects have been commissioned to external audit investigation, and results are pending.
Clear definition of a learner toolkit has been developed and implemented in the new projects.
✓ A NSF Risk Register separate from the DHET Risk Register has been developed.
THANK YOU
1. Purpose
2. Background
3. Part 1: Implementation of the MTT Report.
3. Part 2: Implementation of the forensic report recommendations.
4. Audit Action Plan update