## Slide 1
PARLIAMENT RESTORATION AND PRECINCT REDESIGN PROJECT
STATUS REPORT AS AT 9 May 2023

## Slide 2: BACKGROUND
Parliament engaged DBSA as an IA and handover from NDPWI took place on 6 March 2023.
The handover was based on a condition assessment report for restoration of the Old Assembly and the New Wing.
The programme was broken down into work packages for early, medium and long term deliverables.
Column repairs at Old Assembly
Temporary roof at Old Assembly
Furniture removal from burnt buildings
Asset Verification at burnt buildings

## Slide 3: SCOPE DEFINITION
WP A 1.1. Safe access route:- to allow asset verification.
WP A 1.2. Get 3D perspective on buildings affected by fire for viability analysis, design optimisation and documentation
WP A 2. Rubble & debris removal: to allow detailed structural analysis. Will include recovery of furniture, fixing columns in Old Assembly and temporary roof.
WP A 3. Reconfiguration of floors 4 and 5 on 90 Plein for Members that lost offices.
  Includes IT network, telephony, fire detection, CCTV, access control and HVAC
WP B :- Old Assembly and New Wing to include redesign to alignment to NBR, transformative themes and sustainability concepts.
WP C :- Master Plan aimed to integrate all Parliament buildings to improve functionality, allow Members and other users to get better experience, improve barad equity and improve safety.
WP D : - The TFM work package will develop a concept for an integrated system to:
  Improve user experience and interface;
  Systems to be integrated for better control and operability
  Align to technical advancements and security protocol
Early Work Packages
Medium & Long Term Works

## Slide 4: PROGRAMME MILESTONE CHART
Project Handover to DBSA on 6 Mar 2023

## Slide 5: CBE MANDATORY STAGES FOR PROJECTS
Stage 1
Inception
Needs Assessment Preliminary scope & Programme
Stage 2
Concept & Viability
Layouts
Detailed Feasibility (options) & Baseline Risk Assessment
Stage 3
Design Development
Co-ordinate and integrate detailed designs
Stage 4
Documentation
Procurement Plan & Documents.
Manage tender process
Stage 5
Construction
Execution of works & supervision & Contract Administration
Stage 6
Closeout
Commissioning
Final Account, closeout, as-builts & Manuals

## Slide 6: SAFE ACCESS ROUTE
Complete
100%
2
Stage 2
Conducted assessments
Prepared execution plan
3
Stage 3
Assessed structural safety risk.
Mapped areas on layout based on colour coding
4
Stage 4
Stage not applicable
5
Stage 5
Demarcated unsafe areas & put signage
Prepared report
6
Stage 6
Prepared & signed off reports
1
Stage 1
Engaged PSPs.
Gave detailed brief
23/03/2023
01/03/2023
15/03/2023

## Slide 7: SAFE ACCESS ROUTES
Green: Areas with little to no damage. Access with standard PPE.
Yellow: Areas with minor non-structural damage and could have hanging obstacles or trip hazards.
Orange: Areas where there is either structural damage or potential for collapse ceilings, plasterwork and brickwork.
Red: These are NO-GO areas that are unsafe due to potential collapse of the loadbearing structures, brickwork or finishes. These areas may also be hazardous surface due to damp ingress that have caused excessive mold.

## Slide 8: SAFE ACCESS ROUTES

## Slide 9: NO GO AREAS - RED

## Slide 10: NO GO AREAS - RED

## Slide 11: SAFE ACCESS ROUTES - ORANGE

## Slide 12: SAFE ACCESS ROUTES - YELLOW

## Slide 13: SAFE ACCESS ROUTES - GREEN

## Slide 14: ASSETS VERIFICATION

## Slide 15: ASSETS VERIFICATION

## Slide 16: KEY POINTS ON SAFE ACCESS ROUTES
2 x Structural Engineers
1 x Health & Safety Specialist
Asset verification team:
  7 Asset Verifiers
  2 Accountants
Resources deployed
Overall outlook
Safe access route complete
Asset verification commenced on 2/05/2023.
100% completed based on asset count
Risks and Issues
Not applicable as activity is complete
Planned Activities
Submit the asset verification report by 16/05/2023.

## Slide 17: RUBBLE & DEBRIS REMOVAL & ALLIED WORK
Deliverables
Planning
Assessments completed
Design
Engineering specifications & drawings developed
Removal
Start: 9 Jun 2023
Completion: 31 July 2023
APR
Planning
Columns deemed to be safe
MAY
Design
Not applicable
JUN
Repair Work
To be done by roof contractor: 20 June to 26 June 2023
JUL
Planning
Assessments were conducted & risks identified
AUG
Design
Design & documentation in progress
SEP
Construction
20 June 2023 to 17 Jul 2023
OCT
Planning
Assessments completed
NOV
Design
Safe access route mapped out
DEC
Execution
To follow Audit 20 Jun 2023 to 31 Jul 2023
Rubble Removal
Remove burnt fixtures, rubble, debris and scum
Repairs to columns
Rebar and concrete are intact. Only plaster required with bonding a agent
Temporary roof on Old Assembly
A mono pitch corrugated iron roof to be erected including window shields
Recovery of Assets
To be carried out with rubble removal by a demolishing contractor
Remove Rubble & Debris
Fix Columns
Remove Assets & store offsite
Install a temporary roof

## Slide 18: KEY POINTS ON RUBBLE & DEBRIS REMOVAL
Overall outlook
On track
Attended to heritage requirements
Completed engineering specs
Risks and Issues
Walls and metals may collapse during removal. Demolishing contractor to be engaged.
Delays from security screening
Planned Activities
Work on 3D Scanning: 17/05/2023 to 26/07/20 23
Award bid for Rubble Removal on 9/06/2023
Construction: 20/06/2023
Completion: 31/07/2023
2 x Structural Engineers
1 Quantity Surveyor
1 x Mechanical Engineer
1 x Health & Safety Specialist
Resources deployed

## Slide 19: RESTORATION OF OLD ASSEMBLY & NEW WING

## Slide 20: RESTORATION OF OLD ASSEMBLY & NEW WING
Overall outlook
1 week behind
Time to be recovered on evaluation stage
Risks and Issues
Heritage interest groups may interdict some activities.
Structural integrity of the New Win may be affected during demolishing
2 x PM/Lead consultants
2 x Architects
2 x Structural Engineers
2 Quantity Surveyor
2 x Mechanical Engineer
Electrical Engineer
1 x Heritage Architect
1 x Health & Safety Specialist
Resources to be deployed
Planned Activities
Appoint PSPs by 13/06/2023
Pre-qualify construction firms before documentation stage
Pre-qualified firms to compete on prices and B-BBEE
Site Handover: 4/12/2023

## Slide 21: RECONFIGURATION OF 4TH & 5TH FLOORS
% Complete
48%
2
Stage 2
Conducted assessments
Presented options
Prepared layouts
Prepared execution plan
3
Stage 3
Prepared detailed designs
Prepared design reports
4
Stage 4
Prepared BoQs
Prepared tender documents
Advertised bid on shortened tender
5
Stage 5
Construction to start on 18/05/2023
To run on 3 shifts
6
Stage 6
Practical completion: 13//06/2023
Final account: pending
As-builts: pending
O&M Manuals: pending
Handover: 22/06/2023
1
Stage 1
Engaged PSPs on 6/03/2023.
Gave detailed brief
Sourced as-builts
Physical progress:
1/03/2023
1/04/2023
0%
1/05/2023
1/06/2023

## Slide 22: KEY POINTS ON RECONFIGUARATION OF 4TH & 5TH FLOORS
Overall outlook
Behind schedule – due to HVAC options analysis
Tender issued on: 17/04/2023 & to close on 3 May 2023
Risks and Issues
Delays from security screening
Planned Activities
Award bid on 12/05/2023
Construction: 18/05/2023
Completion: 13/06/2023
Handover: 22/06/2023
1 X Architect
1 Quantity Surveyor
1 x Mechanical Engineer
1 x Electrical Engineer
1 x Electronics Engineer
1 x Health & Safety Specialist
Resources deployed

## Slide 23: LAYOUT FOR 4th FLOOR OFFICES

## Slide 24: LAYOUT FOR 5TH FLOOR OFFICES

## Slide 25: 4th and 5th Floors Impressions

## Slide 26: FURNITURE OUT ON TENDER
Current furniture on 6th floor
New spec out on tender for tender. Size limited by space

## Slide 27: PLANNED AWARD VALUE FOR 4TH & 5TH FLOORS
Item | Budget | Projected 2023/24
Construction Costs | R55 978 600.00 | R55 978 600.00
Construction IA Fees | R2 519 037.00 | R2 519 037.00
New Office Furniture | R10 242 545.78 | R10 242 545.78
New Office Furniture IA Fees | R460 914.56 | R460 914.56
Total Excluding Fees | R69 201 097.34 | R69 201 097.34

## Slide 28: MASTER PLAN FOR PARLIAMENT PRECINT
  Stage 1: Procurement of a Professional Team: 80% complete
    Project Manager / Lead Consultant
    Architect
    Heritage Architect
    Space/Urban Planner
    Interior Designer
    Quantity Surveyor
    Civil & Structural Engineer
    Electrical Engineer
    Mechanical Engineer
    Environmental Specialist
    Health & Safety Agent
  DBSA developed a concept document for the envisioned parliament precinct.
    Key domains include:
      Space optimisation
      Functionality of buildings
      Alignment to NBR
      Security in line with NKP dictates
      Green building concepts
      Alignment to transformative parliament theme

## Slide 29: TRANSITIONAL AND LONG-TERM ARRANGEMENTS
  Working with NDPWI on TFM for transitional arrangements and handover for long term.
  Continue to work closely with SAHRA and Western Cape Heritage.
    To prepare a Heritage Conservation Management Plan which will reduce the need for permit applications for future maintenance and minor works.
    Get quick approvals on reconfiguration and upgrades to burnt buildings and introduction of new themes.
  Heritage Agreement to be established with SAHRA.

## Slide 30: PROGRAMME GOVERNANCE
The Programme will be managed based on the following governance framework:
  Joint Standing Committee on Financial Management of Parliament for Oversight.
  Project Steering Committee comprising DGs of Parliament, National Treasury, DPWI and Senior Management from Parliament.
    Provide strategic direction and oversight.
  Technical and Compliance Committee.
    Review and approve project implementations plans.
    Adjudicate and approve variation orders and extension of time claims.
    Provide guidance on contractual dispute resolution.
  An independent Gateway Review Committee comprising sector experts as required by the National Treasury.

## Slide 31: FINANCIAL IMPLICATIONS
R118 Million is committed for the 2023/2024 financial year which will include office accommodation and ancillary work.
R2 Billion is the estimated project cost for restoration work.
DBSA submitted projected cash flows.
These give indicative budgets and set a baseline.
The cash flows exclude work on the master plan and TFM as the process require extensive stakeholder consultation and engagement with NDPWI.
The project management fees of 4.5% of the total project cost for the implementing agent.

## Slide 32: Thank you!