## Slide 1: ECONOMIC RECONSTRUCTION AND RECOVERY PLAN TRANSPORT INPUTS

## Slide 2: FOCUS AREAS
Ensuring energy security
Industrialization/growing the productive economy
Presidential Employment
Infrastructure that meets the goals of NDP
Macro-economic interventions and enablers of growth
Green economy interventions
Agriculture and food security
Reviving the tourism sector

## Slide 3: DASHBOARD
DASHBOARD LEGEND
0-30 | NO PROGRESS AND NEEDS URGENT INTERVENTION
31- 59 | INADEQUATE PROGRESS AND MAY NEED INTERVENTION
60 – 90 | SIGNIFICANT PROGRESS NO INTERVENTION REQUIRED
91-100 | SATISFACTORY PROGRESS

## Slide 4: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Improve movement of goods and passengers within the N3 corridor through proper road alignment. | Reduce travel tine within the corridor. | R8.2 billion, no contribution required for N3 de beers alignment. | Awaiting the Final Alignment and associated Funding decision to proceed. Awaiting the directive i.e. decision to proceed with building the N3 DeBeers Pass Route or with the Van Reenen AC Alternative Route High level Outputs / Targets is linked and to be determined based on the Final Alignment approved and associated Funding. | Transport Projects (SIP 21) A directive awaited from Cabinet on the way forward and chosen N3 New alignment via De Beers Pass in the Free State. The project is included in the newly gazetted sips for review of the status of the project. A directive is awaited from PICC on the way forward and approved route, i.e the N3 DeBeers Pass Route or the Van Reenen AC Alternative Route. This is dependent on the discussions at the PICC taking into the abandonment of Option AC by the Minister and later included in SIP21 in the government gazette by Minister of Public Works & Infrastructure. | Challenges Resistance by the Business Forums and Free State Government against proposed DeBeers Bypass option. Mitigation measures Strategic Engagements/Consultations with relevant stakeholders. Challenges Cost escalation due to delays in implementation has cost implications to Government, the project will also not be able to be implemented within the remaining period of the existing concession contract. Mitigation measures If this cost cannot be funded by Government, the existing concession contract should be amended to factor this. | 

## Slide 5: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Accelerate implementation of shovel ready projects and those identified through the SIDS process as well as regulatory reforms aimed at building broad-based public; private partnerships. | 550 000 job opportunities created Transformation; sustainability, contractor and skills development. | No Budget required. | Maximise job creation in Government through implementation of High impact road projects. | Transport Projects (SIPs) : Government has announced 62 SIPs, among which is the Strategic Integrated Projects SIP 1 (R573 Moloto Project) SIP 2 (N2/3 Corridor – various work packages, commenced between Ashburton and Camperdown. SIP 3 (N2 Wildcoast Freeway)-work in Msikaba bridge is well on schedule. Tender for the Mtentu bridge was awarded in November 2022. Work is expected to commence soon. SIP 21a (N1 Winburg Interchange to Winburg Station Free State) – Completed / 446 Jobs. SIP 21b (N1 Musina Ring Road: Limpopo) – Completed / 800 Jobs SIP 21c (N1 Polokwane Eastern Ring Rd Phase 2: Limpopo) - Completed / 1785 Jobs. SIP 21d (N1 Ventersburg to Kroonstad: Free State (2 projects) - Completed / 775 Jobs. SIP 21e (N2 Mtunzini Toll Plaza to Empangeni T-Junction: KwaZulu Natal - Completed / 510 Jobs. | These projects were gazetted as part of 50 infrastructure projects as SIPs in terms of the Infrastructure Development Act No. 23 of 2014, Challenges Project delays due to procurement processes and compliance requirements. Mitigation measures Automated processes being implemented to create efficiency SANRAL to implement the necessary control measures. Challenges Land acquisition for road purposes. Mitigation measures Expropriation from private land owners when no agreement can be reached Engagements with Tribal Land Owners. | 

## Slide 6: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 |  |  |  |  | SIP 21f (N3 Cato Ridge to Dardanelles: KwaZulu Natal) – In construction /173 Jobs to date. SIP 21g (N3 Dardanelles to Lynnfield Park: KwaZulu Natal) - In construction /369 Jobs to date. SIP 21h (N3 Paradise Valley to Mariann hill Toll Plaza: KwaZulu-Natal) – Delayed, SANRAL Toll borrowing limits not approved by Treasury, cannot proceed. SIP 21i (N2 Edwin Swales to South of EB Cloete Interchange: KwaZulu Natal) – Construction awarded in November and work has commenced in March 2023. SIP 21J (N3 Ashburton Interchange to Murray Road: KwaZulu Natal – Construction tender awarded in November 2022 and work commenced in March 2023. | Challenges Statutory approvals (Environmental Authorisation, SPLUMA Planning approvals, Borrow Pits / Quarries, water licence). Mitigation measures On-going engagement with the approval authorities. Challenges Statutory approvals (Environmental Authorisation, SPLUMA Planning approvals, Borrow Pits / Quarries, water licence). Mitigation measures On-going engagement with the approval authorities. | 

## Slide 7: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 |  |  |  |  | SIP 21 L (N2 EB Cloete Interchange: KwaZulu Natal) - Construction award in November 2023 and construction work started in March 2023. SIP 21K (N3 New alignment via De Beers Pass: Free State) - A directive is still awaited from PICC on the way forward and approved route, i.e the N3 DeBeers Pass Route or the Van Reenen AC Alternative Route. | Challenges Statutory approvals (Environmental Authorisation, SPLUMA Planning approvals, Borrow Pits / Quarries, water licence). Mitigation measures On-going engagement with the approval authorities. Challenges Statutory approvals (Environmental Authorisation, SPLUMA Planning approvals, Borrow Pits / Quarries, water licence). Mitigation measures On-going engagement with the approval authorities. | 

## Slide 8: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Reduce the impact of speed related accidents and overload damage on the Roads. | Improve compliance to speed and loading regulations through effective enforcement using Average Speed Over Distance (ASOD) and Weigh-In-Motion Infrastructure and Technologies. Making use of Average speed over distance and Weigh-In Motion measuring devices for enforcement will enable the installation of over 250 automated enforcement locations that operated 24 hours 365 days in year. | Within SANRAL’s operational budget. | To be introduced in all provinces Introduction of Average Speed Over Distance (ASOD) and Weigh-in-Motion enforcement (WIM) infrastructure and technologies to ensure compliance to speed and weight regulations. Reduction in speed related accidents and fatalities. Pilot project indicted 10 to 25% reduction n high speed crashes.. | The Average Speed Over Distance (ASOD) standard has been approved by National Regulator for Compulsory Specifications. Currently engaging with Public Prosecutors Office to finalize administrative requirements to enable implementation. The draft Weigh-in-Motion enforcement Standards has been published. National Regulator for Compulsory Specifications and the comments provided are being reviewed and this process will be finalized within this financial year 2023/24. Draft Traffic Regulations amendments been prepared to enable ASOD and Wim enforcement. | Challenges Lack of effective law enforcement. Mitigation measures Introduction of Average Speed Over Distance (ASOD) and Weigh-in-Motion (WIM) enforcement infrastructure and technologies to ensure compliance to speed and weight regulations. Challenges No legal instrument to use WIMs for traffic law enforcement purposes. | 

## Slide 9: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Reduce the impact of speed related accidents and overload damage on the Roads. | Improve compliance to speed and loading regulations through effective enforcement using Average Speed Over Distance (ASOD) and Weigh-In-Motion Infrastructure and Technologies. Making use of Average speed over distance and Weigh-In Motion measuring devices for enforcement will enable the installation of over 250 automated enforcement locations that operated 24 hours 365 days in year. | Within SANRAL’s operational budget. | Reduction in accidents involving overloaded vehicles and damage to road by overloaded trucks. |  | Mitigation measures engagements have taken place with the National Regulator for Compulsory Specifications to develop “compulsory speciation’s” for the design, installation, maintenance and use of the weigh-in-motion infrastructure. | 

## Slide 10: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Accelerate implementation of shovel ready projects and those identified through the SIDS process as well as regulatory reforms aimed at building broad-based public; private partnerships. | Improve access and mobility in rural areas through labour intensive method of road construction and maintenance. | R12.9 Billion annually. | Number of kilometers of roads, upgraded, rehabilitee and maintained. | Government developed integrated S`hamba Sonke rollout throughout the country to improve the quality of provincial road network and at the same time create jobs that will benefit Youth and People with Disabilities. Minister and MEC`s launched the National Pothole Repair Programme on the 08 August 2022 to close all potholes on provincial roads. Cabinet appointed SANRAL as the Implementing Agent to coordinate all activities of provinces using pothole detection App. Almost 6 provinces received training on the Pothole reporting App and 7 provinces uploaded their roads data on the SANRAL IT IS System. | Challenges Provinces not providing funding through Equitable share and rely entirely of the Provincial Road Maintenance Grant (PRMG): The department’s attempt to secure R500 Million, to be utilised SANRAL on other road Authorities network was not supported. Mitigation measures Review the Grant condition to include upgrade of rural road to paved standard. Set aside (Allocating) 40% of PRMG for pothole repair through SANRAL as the Implementing Agent. Challenges PRMG is not funding for maintenance on Municipal road network. Mitigation measures Municipalities to sign MOAs with provinces for the maintenance of Municipal roads. | 

## Slide 11
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | R573 Moloto Corridor development to Provide a seamless infrastructure that will prioritise sate of road users across the three provinces | Stimulate the economic activities and growth within the Moloto Development corridor | R5.7 Billion 0ver a 5-year period. | Upgrading and maintenance of entire Moloto road through Mpumalanga, Limpopo and Gauteng provinces | All section of the roads through the three provinces are transferred to SANRAL and declared national roads and SANRAL has already commenced with the upgrading and strengthening of the road sections of both Mpumalanga and Limpopo provinces. Work on the Gauteng section has not yet started pending the road designs that are at an advanced stage. | Challenges Tribal Land Acquisition - Large parts of Moloto road in LP and MP traverse tribal land occupied by rural communities and owned by Government with DALRRD as the custodian. SANRAL has already got support for land acquisition from Traditional Authorities. Addressing relocation of individuals within the road reserve requires extensive community engagements that could not happen during Covid-19 restrictions on gatherings. This has now resumed since January 2022. Mitigation measures None performing contactors were replaced and a new contractor has since been appointed. Phase 3 of the project is now progressing without any disruptions on both LP and MP sections of the road. Challenges Delays in the transfer of Gauteng section of the road delayed the finalization of the designs for the Gauteng portions. Further delays were related to Land owners and encroaching the road reserves that restrict many accesses to the road. | 

## Slide 12: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Upgrading of the N2 Highway greenfield section and the associated bridge structures aimed at providing access and mobility solution, stimulating the socio-economic activities by connecting Eastern Cape and Kwa-Zulu Natal provinces. | Ugrading of 411km of the road with the view to stimulate the socio-economic activities within the corridor and at the same time create the much-needed work opportunities. | Government earmarked over R9.5. billion | Construction work will create about 8 000 direct full-time employment jobs, with a wage bill of about R750 million and between 21 300 and 28 100 indirect jobs Once the road is completed, the ongoing operational work is anticipated to create 900 direct jobs and up to 18 900 indirect jobs. | The R1.65 billion Msikaba bridge is currently under construction. The 580m span, 195m high, cable stay bridge is expected to be completed by May 2024. At the end of July this year, community participation goal (CPG) for targeted labour achieved was 37.06% against 32.2% of work completed. Currently there are 329 local persons employed on site (156 employed by the main contractor, CMEJV, and 173 employed by sub-contractors. | Challenges Msikaba project has been compounded with delays (communities, business forums) demanding 30%. Mtentu bridge projects delayed due to Aveng Strabag Joint Venture (ASJV), appointed to build the R1.65 billion Mtentu bridge terminated its contract. Attempt by SANRAL to speed up implementation further delayed by cancelling tenders to the value of R17.47 billion that included Mtentu. Mitigation measures Tenders for over R17 billion including Mtentu bridge project have been retendered and Mtentu tender closed on the 5th October 2022 and awarded in November 2022. The wor | 

## Slide 13: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Develop and invest in affordable public transport, protect and sustain commuter rail transport infrastructure. | Recovery of high-volume commuter rail corridors Increase in railway capacity, patronage and fare revenue Improvement in passenger security, protection of the rail reserve and railway infrastructure. | R2,25bn (6 months) funding. R4,5bn (12 months) funding. | Mabopane Corridor fully operational | Mabopane Corridor: Limited rail service resumption on 17 January 2022, 70 train trips per day. 5 stations operational. Service resumed on the Dewildt line. Rehabilitation of sub-station and OHTE completed. Overhead Traction System competed 6 additional station rehabilitations are underway, currently standing at 30% completion. Re-signalling project between Mitchell street and Pretoria is undergoing bid evaluation, the project is estimated for completion in 6 months. Contractors were appointed for construction of Perimeter walling for buildings - construction 80% completed. Corridor walling, specifications concluded, tenders advertised and closing on 20 April 2023. Security personnel have been deployed in the corridor to secure the infrastructure. | Contract dispute delaying project implementation. Delay in supply chain appointment and Bid Specification Committees. Availability of components for the Signalling System – 12 month delay in implementation of full service. | 

## Slide 14: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Develop and invest in affordable public transport, protect and sustain commuter rail transport infrastructure | Recovery of high-volume commuter rail corridors Increase in railway capacity, patronage and fare revenue Improvement in passenger security, protection of the rail reserve and railway infrastructure. | R2,25bn (6 months) funding R4,5bn (12 months) funding | Central Line Corridor relocation of illegal settlements Phase 1: relocation planned for 30 November 2022 Phase 2: relocation planned for June 2023 | Central Line Corridor: Relocation Programmme 5195 illegal structures erected in the railway reserve along the Central Line - Langa, Phillipi and Khayelitsha. Implementation Protocol (IP) concluded on 9 March 2022, between key Departments Housing Development Agency(HDA) appointed as implementation agent IP Steering Committee established in March 2022. Enumeration for Phase 1 – Langa (1254) and Phase 2A – Khayelitsha (253) has been completed. Enumeration for Philippi occupants 3 688 households (excluding occupants in the Phillipi staging yard). Various land parcels has been considered without success. Section 68 Application, Emergency Relocation site, in June 2022 in terms of the City of Cape Town Municipal Planning By-Laws was unsuccessful. Currently no land parcel secured. Relocation would require a full rezoning application (with a full public participation process) for the subject properties. | Parcels of land offered by Department of Public Works and Western Cape Provincial Government opposed by receiving community and developers. Section 68, Emergency Declaration delayed at Council. Phase 1 - relocation site opposed by receiving community of Mitchells Plain. Phase 1 – relocation programme delayed indefinitely. Phase 2 – relocation site not secured, proposed relocation site apposed by Macassar community. Delay in securing funding for relocation programme from National and Provincial Department of Human Settlement and City of Cape Town. | 

## Slide 15: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 |  |  |  | Phase 1: Langa - 31 July 2022 Phase 2: Phillipi and Khayelitsha – Nov 2023 | A full rezoning process will take between 6 – 12 months, and can sometimes run beyond 18 months in cases of objections and possible appeals and legal challenges. The new November 2023 Eviction Order Date is unattainable. Department of Human Settlement (DHS) has not confirmed funding for the implementation of the relocation programme. This includes funding for land acquisition, land preparation, provision of basic services and relocation of structures. On 31 March 2023, R111 Million, was transferred to the City of Cape Town by DHS for the 16 priority informal settlements, including PRASA. The funding is for land acquisition and the provision of basic services. Central Line Corridor: Service Recovery Plan Phase 1 A&B: Cape Town to Langa (Via Pinelands) and Langa and Bellville (via Sarepta) – limited services commenced operation on 26 July 2022 The OHTE programme implemented Contractor busy with final works, 3kV energised and snagging. The track and signaling works commence on limited services line Temporary fence: Securing the informal settlement completed in July 2022. Phase 2: Limited services 31 December 2022 Perway screening, stations, walling and fencing hotspots and security. The Perway work will commence once illegal occupants are relocated. | Vandalism, theft on-going, attacks on maintenance crews. Security Technology combined with the walling project. Monitoring Control Room Operations to be implemented for long term command and control. Increased operations in JOINT projects. (SSA,SAPS,CI). | 

## Slide 16: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
1. | Develop and invest in affordable public transport, protect and sustain commuter rail transport infrastructure, | Fully integrated public transport corridors – integrated fare collection | PTN Grant Funding for the cities and DoT transfer to SANRAL for establishment costs | Roll out a single (integrated) ticketing solution based on the SANRAL clearing house platform with Gauteng pilots involving PRASA, Gautrain, Joburg, Tshwane and Ekurhuleni by 2025 | The major outputs of the 2022/3 year were launching the first two live pilots of the Integrated ticketing system in Rustenburg initially, followed by Polokwane. Rustenburg completed over R2m of Fare card top ups and 200 000 transactions on Yarona, since June 2022. In March 2023, Rustenburg performed an average of 2500 Transactions a day. Polokwane moved from Dry Run testing since August 2022 to live Pilot implementation in December 2022. They have since done over R1.37m in top up fare card transaction value as well as 129 000 Fare payment Transactions on Leeto La Polokwane. In March 2023, Polokwane averaged over 2300 Fare Transactions a day. The target is to roll out a Gauteng Pilot. Joburg, Tshwane and Ekurhuleni have been engaged on preparations for the pilot. Next is to engage rail, bus and taxi operators. |  | 

## Slide 17: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Develop and invest in affordable public transport, protect and sustain commuter rail transport infrastructure, | Improved public transport network infrastructure and services that function optimally and are accessible, safe, convenient, affordable, well managed and maintained. | Grant Funding over the 2022/23 MTEF for 10 cities. | 5 cities working towards expanding current services into new corridors/ phases in 2022/23 10 cities : new services launched and expansion of services into townships by 2024/25. | 8 cities are operational: Cape Town, George, Ekurhuleni, Johannesburg, Tshwane, NMB, Polokwane and Rustenburg. 2 cities are still struggling with the launch of new services: Mangaung and eThekwini municipalities | Delays in the launch of new and expansion of services. Mitigation measures Minister will be meeting with MECs and Mayors as an intervention measure in both the two municipalities. eThekwini’s launch is suspended indefinitely due to challenges with the Taxi Industry. Mangaung’s Administration challenges are also contributing to the delays in the implementation of the project. | 

## Slide 18: GREEN ECONOMY INTERVENTIONS
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | GTS (Green Transport Strategy) Implementation | Electric vehicles Regulations Framework | Donor Funded | Draft of EV Framework 2023 February 28 | Draft EV Framework Completed, 2023 February 28 Provincial Consultations Completed Free State Mpumalanga Northern Cape North West Western Cape Eastern Cape Gauteng Limpopo Kwa-Zulu Natal | Stakeholder Engagement slow because of limiting online methodology of meetings Mitigation measures More frequent and intense workshops. | 
 |  | Climate change interventions implemented to achieve GHG emission reduction and maintained kept within the 398 and 614 Mt CO2-eq Peak, Plateau and Decline (PPD) range | In – house | The Pilot stage of National Treasury Climate Budget Tagging for DoT Projects has been completed. The next stage will be rolled out by National Treasury in the near future. |  | Methodology not yet understood Awareness through sponsored National Treasury Service provider | 

## Slide 19: REVIVING THE TOURISM SECTOR
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 | Protection of aviation capacity through operations | Improved visitor experience Increase in the number of domestic holiday trips Increase in international tourist arrivals. | R35m R57m |  | E-gates implemented at Cape Town International, to be rolled out at OR Tambo and King Shaka International Airports Upgraded Flight Information Display Monitors Infrastructure that was mothballed during COVID-19 is being phased back into operation to align to passenger growth Implementation of the Township and Rural strategy to attract a new market to airport precincts |  | 

## Slide 20: INFRASTRUCTURE THAT MEETS THE GOALS OF NDP
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 |  |  |  |  | ACSA is working with both local and international airlines to 1. Restore pre-COVID connectivity and develop new routes with the aim of accelerating the recovery of the tourism and aviation sectors. To date, domestic airlines have continued with their domestic expansion plans. Currently, ACSA’s domestic segment has recovered to 56% of pre-COVID throughput, with the regional and International segments lagging behind. The domestic segment currently accounts for 83% of ACSA’s total traffic in the current FY (the segment accounted for 70% of total traffic pre-COVID). Regional (National) airports saw a faster recovery, largely due to traffic at these airports being driven by leisure and visiting friends and family (VFR) traffic. The MICE and business market segments have been impacted the most due to reduced travel budgets by corporates driven by the rapid development of virtual conferencing and meetings platforms. These segments (incl. government) accounted for over 50% of the traffic at the 3 international airports. |  | 

## Slide 21: REVIVING THE TOURISM SECTOR
No | Intervention | Intended outcome | Funding/ Budget Committed | High Level Outputs /Targets (Specify Time Lines ) | Implementation Progress with quantitative & qualitative analysis including focus on women, youth and persons with disabilities information where applicable | Challenges & Mitigation Measures | Dashboard
 |  |  |  |  | Multiple international airlines have reinstated their pre-COVID routes, particularly airlines from Europe, the US and Australasia. Critical links to Latin America and Hong Kong remain a top priority and ACSA is engaging with all potential airline partners to reestablish this link. ACSA has established collaborative partnerships with various entities within the tourism and aviation value chain, to jointly coordinate air access initiatives. These partnerships have led to the creation of regional airlift/air access structures, which continue to drive airlift initiatives. |  | 

## Slide 22
THANK YOU