## Slide 1: Progress Report to the human settlements portfolio committee: MAWIGA MINISTERIAL PROJECT AND the mawiga FOUR PETITIONERS
24 MAY 2023

## Slide 2: This report was prepared with inputs from the following stakeholders:
National Department of Human Settlements (NDHS)
North West Department of Human Settlements (NWDHS)
Gauteng Department of Human Settlements (GDHS)
North West Housing Corporation (NWHC)
City of Tshwane (COT)
Housing Development Agency (HDA)
The Four Petitioners

## Slide 3: TABLE OF CONTENTS
PURPOSE
INTRODUCTION
BACKGROUND TO THE MAWIGA MINISTERIAL PROJECT
BACKGROUND TO THE MAWIGA FOUR PETITIONERS
PROGRESS REPORT ON THE SUPPORT PROVIDED TO THE FOUR PETITIONERS BY GOVERNMENT
RECOMMENDATIONS

## Slide 4: 1. PURPOSE
    To request members of the Human Settlements Portfolio Committee to:
    Note the Progress Report on the MAWIGA Ministerial Project whereby Phase 1 of 8000 property transfers will commence by June 2023.
    Note the Progress Report on the actions pertaining to the MAWIGA four (04) petitioners’ subsequent to the Portfolio Committee’s oversight visit to the North West Province on the 31 March 2023.
    Notes that the on-going consultation processes with the four (04) Petitioners and relevant stakeholders and that the Department commits to report progress on a quarterly basis to the until the matter is concluded.
    Note that the matter of the psycho-social support for the Petitioners is currently being addressed by the Department, through the appointment of a professional service provider through Goods & Services budget of NDHS.

## Slide 5: 2. INTRODUCTION
  This progress report covers the two components to the matters regarding the MAWIGA Community which the Minister is currently resolving:
  The MAWIGA Ministerial Project aimed at resolving the ownership and transfer of properties to 14 000 households residing in Ga-Rankuwa Units 7 and 8, Mabopane M, S, U and X and Winterveld; and
  The four (04) MAWIGA Petitioners whose properties were illegally sold and transferred by officials in COT and the NWHC.

## Slide 6: 3. THE MAWIGA MINISTERIAL PROJECT
  The MAWIGA Petitions Group consists of representatives of community members in Ga-Rankuwa Units 7 and 8, Mabopane M, S, U and X and Winterveld, who have been trying since 1990 to obtain title deeds to their properties on the basis of a Department of Local Government, Housing, Planning and Development Circular (Ref7/8/2/1) that provided for the disposal of all state owned and subsidized properties constructed before 30 June 1993 in favour of their beneficiaries.
  2. The Minister then declared a Ministerial Project to resolve ownership and transfer for 8 000 uncontested properties as phase 1 of the estimated 14 000 households affected. The project is progressing well with conveyancers appointed and beneficiary verification almost concluded. The first batch of transfers will be lodged by the end of June 2023.

## Slide 7: 4. THE MAWIGA FOUR PETITIONERS
  The four (4) MAWIGA Petitioners are part of the MAWIGA Greater Community whose properties were illegally sold and transferred by officials in the COT and the NWHC. This is the matter over which Parliament’s Human Settlements Portfolio Committee has been engaging the NDHS to resolve. This report provides progress on the action taken following the Portfolio Committee’s Oversight Visit conducted in the North West province on 31 March 2023.
  In 2018, the Public Protector published a report (Public Protector’s Report 14 of 2018) on an investigation into allegations of maladministration by the NWHC and the COT regarding improprieties in the sales and transfers of properties by the Corporation situated within the boundaries of the City of Tshwane.

## Slide 8: 4. THE MAWIGA FOUR PETITIONERS
  The following four Petitioners were the victims of the alleged maladministration, namely:
Mr. Ernest Kgasoe (2281 Unit 8, Ga-Rankuwa).
Mr. Michael Mere (2827 Zone 2, Ga-Rankuwa).
Mr. Bongo Sepeng (992 Zone 7, Ga-Rankuwa).
Ms. Marie Ledingoane (309 Block X, Mabopane).
2. The above-mentioned properties belonged to the Bophuthatswana Homeland, under the Bophuthatswana Housing Corporation, which were later inherited by the NWHC under the new dispensation.

## Slide 9: 4. THE MAWIGA FOUR PETITIONERS
The findings of the Public Protector regarding the above-mentioned investigation were the following:
    The COT Metropolitan Municipality, in failing to conclude township establishment, through the provision of an approved general plan, was guilty of maladministration in respect of all 4 complainants.
    The NHWC, in failing to transfer the properties in the names of the beneficiaries, was guilty of maladministration.
    There was improper conduct on the part of COT in respect of fraudulent sales of three of the beneficiaries’ properties and failure to compensate the beneficiaries.
    The full report on the investigation and findings of the Public Protector is attached.

## Slide 10: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTIVITIES | STATUS
Property Offer: Mr Kgasoe | Mr Kgasoe has accepted vacant land at erf 757 Mogwase Unit 2, measuring at 1441sqm. The land is currently owned by the Department of Public Works (DPW). Attempts by NWHC to engage DPW on fast-tracking the transfer of ownership rights into Mr Kgasoe’s name have not been successful. The matter will be elevated to the MEC for intervention. Once all the transfer processes have been finalized for Mr Kgasoe’s site, he will be issued with a title deed. On 16 May 2023, NWDHS conducted a site visit Mr Kgasoe at the identified stand, to discuss the specifications & designs of the Military Veterans (MV) house. Mr Kgasoe has subsequently raised concerns that properties surrounding his stand are upmarket & he is not satisfied with the MV specs & designs. He is requesting Government to consider offering him higher specs (above MV).

## Slide 11: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Property Offer: Ms Sepeng | Ms Sepeng previously rejected the 2 vacant sites offered to her in Ga Rankuwa Zone 4 (Erf 9063 and 9064 respectively, each measuring 600sqm, totaling 1200sqm. NWHC has confirmed that they are willing to re-open discussions with Ms Sepeng to offer her the stands that she had preferred, that are adjacent to Erfs 9063 and 9064. On 12 May 2023, COT also took Ms Sepeng on a site visit to view several alternative vacant stands at Lady Selbourne, Pretoria. The stand Ms Sepeng was interested in is erf 677 (1172 square meters). The price is more than R700 000. Tshwane has confirmed that if Ms Sepeng accepts this offer, the municipality will not construct a top structure for her. Ms Sepeng has requested the Minister & Mayor to intervene & apply a special dispensation.

## Slide 12: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Property Offers: Mr Mere | Mr. Mere owns property 2877 Zone 2, Ga-Rankuwa. The township Ga-Rankuwa Zone 2 is situated on Farms Oudekraal Sjambok 726 owned by COT, as well farms on Portions 3 Medunsa 237 JR owned by RSA & Portion 4 of Medunsa 237 which is privately owned. Attempts to register the township by NWHC, GDHS & COT were unsuccessful due to complex land consolidation processes related to land ownership. COT has referred the matter to HDA to evaluate the land portions & advise on the most expeditious way forward & is awaiting a report. On 9 May 2023, HDA conducted an evaluation of the property. HDA has raised concerns that COT is not availing information (records / files) on work that had already been initiated by COT to establish the township HDA is unable to review the documents and take the work forward. COT has been advised to urgently appoint a conveyancer & work with the Deeds Office, to expedite this process. COT has also been advised to appoint a specialist property lawyer who understands old order property legislation and new order property legislation, to provide expert legal opinion. Mr Mere has requested Ministerial intervention through the office of the Mayor.

## Slide 13: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Property Offer: Ms Ledingoane | Ms Ledingoane has accepted an offer for Stands No. 12049 and 12050 Block X Mabopane. Each stand is measured 258sqm, totaling 570sqm. COT will take responsibility for the construction of the top structure (MV quantum subsidy & specifications). GDHS has given COT the approval to proceed with construction. COT is in the process of confirming the variation order with GDHS. The matter will be presented at COTs BAC on 23 May 2023. The contractor will discuss the specifications with Ms Ledingoane. COT envisages that construction will begin in July 2023.

## Slide 14: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Ex-Gratia Payments by NWHC to the Petitioners | Mr. Mere, Mr Kgasoe & Ms Ledingoane have received the ex-gratia payments (R10 000) & apology letters from NWHC. Ms Sepeng has not yet received an apology letter. Ms Sepeng had initially rejected the ex-gratia payment. She has subsequently agreed to accept the payment. NWHC will pay R10 000 to Ms Sepeng by 26 May 2023. NWHC has confirmed that regarding the proposed revision of the ex-gratia payments, as previously reported in the last PC meeting, NWHC is unable to reconsider a revision of the R10 000 ex-gratia amount paid to the petitioners.

## Slide 15: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Consultation with Lawyers for Human Rights for losses incurred by petitioners | The Petitioners have requested that the Chairperson of the Human Settlements Portfolio Committee, in consultation with Parliament’s Legal Advisory Services, provides guidance on the most appropriate process to approach Lawyers for Human Rights. The Petitioners request expert legal opinion on losses they have incurred, the revision of the ex-gratia payment amounts based on the losses incurred, and a determination of COT’S responsibility towards further compensating the Petitioners.

## Slide 16: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTION | STATUS
Opening of a Case Against COT for the Illegal Sales of Petitioners’ Properties | On 18 May 2023, the CEO of NWHC wrote a letter to the MM of COT, requesting COT to furnish NWHC with the names of the City officials who effected the illegal sale and transfer of the Petitioners’ properties. NWHC was advised by Mahikeng Police to open the case in Tshwane & provide of where the offense happened, confirmation of who’s names the properties were registered in when the crime happened, and the names of the perpetrators. COT has conducted their own internal investigations & information with the names of the perpetrators, will be availed to NWHC by 26 May 2023. COT still intends to take the Public Protector’s report on review.

## Slide 17: 5. PROGRESS REPORT ON THE FOUR PETITIONERS
ACTIVITIES | STATUS
Th provision of psycho-social counselling services to the four petitioners | According to Government’s policy, the key beneficiaries of the Employee Health Wellness Programme of NDHS is for members of NDHS and their immediate families only. NDHS is assisting by referring the Petitioners to facilities/ institutions located in and around their neighborhoods, e.g. NICRO, Department of Social Development (DSD), Ga-Rankuwa Thusong Center, etc. to access counseling support services at no charge. A request will be made to the Acting DG & Minister for special support for the services, through the appointment of a dedicated service provider through the Goods & Services budget of NDHS, to address the matter of the petitioners.

## Slide 18: 6. RECOMMENDATIONS
  It is recommended that the Portfolio Committee:
    Note the Progress Report on the MAWIGA Ministerial Project whereby Phase 1 of 8000 property transfers will commence by June 2023.
    Note the Progress Report on the actions pertaining to the MAWIGA four (04) petitioners’ subsequent to the Portfolio Committee’s oversight visit to the North West Province on the 31 March 2023.
    Notes that the on-going consultation processes with the four (04) Petitioners and relevant stakeholders and that the Department commits to report progress on a quarterly basis to the until the matter is concluded.
    Note that the matter of the psycho-social support for the Petitioners is currently being addressed by the Department, through the appointment of a professional service provider through Goods & Services budget of NDHS.

## Slide 19
Thank You