## Slide 1: URBAN settlements DEVELOPMENT grant & INFORMAL SETTLEMENTS UPGRADING PARTNERSHIP GRANT PROJECT performance analysis as at 31 may 2023

## Slide 2: (OVERALL USDG) COJ, Mangaung & COT l Performance per Department as at 31 May 2023
  All 3 Cities major infrastructure and service delivery departments are not performing with an unspent funds of R1,5bn.

## Slide 3: (USDG) City of Joburg Municipality per Departmental Performance as at 31 May 2023
Human Settlements, Johannesburg Development Agency and Johannesburg Road Agency have a combined budget of R1bn with lowest expenditure to date.
Human Settlements department was granted an additional budget of R200m thus increasing their budget to R788m.

## Slide 4: (USDG) City of Joburg Municipality Projects Performance as at 31 May 2023
Human Settlements Department top 5 non-performing projects at 0% expenditure;
  Riverside View ext 28 (Diepsloot ext 12) – R140m
  Madala Hostel Redevelopment - R32m
  Elias Motsoaledi Ext1 Township Development (Region D - Ward 24) – R25m
  Klipspruit/Kliptown New Bulk Infrastructure – R25m
  Dube Hostel Renewal Building Alterations DUBE EXT.2 D Ward – R 20m
Johannesburg Development Agency
  Orange Farm Urban Renewal Programme flagship project – R171m is at 68% progress
Johannesburg Roads Agency has 4 projects are below 25% progress;
  Tarring of gravel roads: wards 77, 133, 80 – R17,5m
  Stormwater Conversion: wards 78, 79, 133 – R7m
  Upgrade roads Klipfonteinview – R10,5m
  Khosa Street- - gravel roads and stormwater – R10M

## Slide 5: COJ (ISUPG) PROJECT SUMMARY AS AT 31 MAY 2023
City of Joburg has a total number of 55 projects with a Total Budget value of R684.8m
Zandspruit 84, in Zandspruit Informal Settlement, Construction of permanent Engineering Infrastructure Services(Water ,Sewer,Roads&Stormwater) Expenditure R169 , Variance R62m
-Hopefield Informal Settlement, Roodeport, Construction of permanent Engineering Infrastructure Services(Water ,Sewer,Roads&Stormwater), Expenditure 13.9m
Princess in Princess Informal Settlement, Detail Designs(Phase 2) and Construction of permanent Engineering Infrastructure Services(Water ,Sewer, Roads& Stormwater) (Phase 3 ) Expenditure R30m Variance 17m
Department | Approved Proj Budget | Total No. of Projects | No. of Projects @ 0% | No. of Projects @ 1-85% | No. of Projects >85% | Variance | Actual Expenditure
A (Diepsloot & Midrand) | R30,831 | 18 | 18(R30.8) | 0 | 0 | R30,831 | -
C Roodepoort (Zanndspruit) | R333,646 | 5 | 1(R21.3) | 4(R105) | 0 | R126,251 | R207,395.00
D (Soweto) | R24,785 | 6 | 3(R10.5) | 2(R9.5) | 1 | R18,596 | R6,189.00
E (Aleandra & Sandton) | R44,855 | 8 | 7(R37.7) | 0 | 1 | R37,693 | R7,162.00
F (Inner City | R58,649 | 4 | 3(R50.2) | 1(R5.7) | 0 | R55,941 | R2,708.00
G (Eldorado Park & Orange Farm | R192,131 | 14 | 4(R3.4) | 4(R59.8) | 6 | R59,960 | R132,170.98
total | R684,889 | 55 | 36(R154) | 11(R180) | 8 | R328,634 | R356,255.00

## Slide 6: (USDG) City of Tshwane Municipality per Departmental Performance as at 31 May 2023
Energy & Electricity, Human Settlements and Water & Sanitation Departments have a combined budget of R873m with lowest expenditure to date.

## Slide 7: (USDG) City of Tshwane Municipality Projects Performance as at 31 May 2023
Human Settlements Department top 5 non-performing projects at 0% expenditure;
  Construction of roads & stormwater - Soshanguve South X12 - R5m
  Olievenhoutbosch X60 Bulk Water – R5m
  Water provision - Soshanguve MM – R1,5m
  Construction of roads & stormwater - Fortwest X4&5 – R1,2m
  Development of Saulsville hostels - R1m
Water & Sanitation top 5 non-performing projects at 0% expenditure
  New Parkmore LL Reservoir and HL Reservoir – R10m
  Sewer reticulation Kudube 5 – R10m
  Upgrade water pump station (City Wide) – R10m
  Laboratory Equipment – R 8,8m
  Upgrade of sewerage pump stations (City Wide) - R4m
Energy & Electricity Department top 7 non-performing projects at 0% expenditure;
  Strengthening 11kV Cable network - R6m
  Replacement of Obsolete and Non-functional Equipment - R 2,4m
  Ifafi 88/11kV Substation - R6m
  Monavoni 132/11KV Substation -R1m
  Soshanguve - JJ 132KV Power Line - R2m
  Wildebees 400/132kV, 315MVA Infeed station – R2m
  Network Control Centre Reconfiguration – R21m

## Slide 8
COT (ISUPG) PROJECT SUMMARY AS AT 31 MAY 2023
These projects on which the City is spending on include the following:
- Sewer Reticulation Kudube 5 Informal Settlement, Construction of Permanent Engineering Infrastructure Services(Water & Sanitation), Expenditure R27m
-Construction of roads & stormwater - Thorntree View, Construction of permanent Engineering Infrastructure Services Roads&Stormwater), Expenditure R53m and variance of R73m
Klipgat WWTW: Upgrading of existing infrastructure to 40Ml/d, Construction of permanent Engineering Infrastructure Services(Water& Sanitation) (Phase 3 ) Budget is R70m Actual Expenditure-R 52m with a variance of R17m
Also to Note:
Rooiwal WWTW Phase 1: Upgrading of Existing Infrastructure, Project Budet-R3.4m 0% Expenditure
Department | Approved Proj Budget | Actual Expenditure To Date | Total No. of Projects | No. of Projects @ 0% | No. of Projects @ 1-85% | No. of Projects >85% | % of Total Budget | Actual Achieved
 |  |  |  |  |  |  |  | Expenditure
Energy | R148,317,369.00 | R83,027,389.06 | 13 | 9(R41m) | 2(R12.5m) | 2 | 25% | 56%
Human Settlements | R255,464,585.00 | R106,778,442.29 | 33 | 11(R30m) | 10(R37.7m) | 12 | 43% | 42%
Roads and Stormwater | R58,710,344.00 | R26,628,473.58 | 8 | 2(R1.5m) | 4(R30m) | 2 | 10% | 45%
Water and Sanitation | R101,508,452.00 | R79,524,151.73 | 4 | 2(R3.5m) | 1(R17.8m) | 1 | 17% | 78%
OPSCAP | R29,684,250.00 | R24,720,951.14 | 1 | 0 | 0 | 1 | 5% | 83%
Totals | R593,685,000.00 | R320,679,407.80 | 59 | 24(R76m) | 17(R98m) | 18 |  | 54%

## Slide 9: (USDG) Mangaung Metropolitan Municipality per Departmental Performance as at 31 May 2023
The 2 major infrastructure and service delivery departments in Mangaung are not performing with a budget of R154m.
Roll-over allocation of R125m has largest budget share allocation of 20% with low expenditure of 13%

## Slide 10: (USDG) Mangaung Metropolitan Municipality Project Performance as at 31 May 023
Sanitation Department 4 non-performing projects;
  Sewer master and development plans– R 5,6m at 54%
  Refurbishment of sewer systems – R56,7m at 6%
  Botshabelo main outfall sewer – R1,72m at 79%
  Extension Thaba-nchu WWTW Selosesha Mech/Electr - R5m at 0%
Waste and Fleet has 9 projects and all are at 0% expenditure, top 5 in value;
  New fence at Soutpan landfill site – R10m
  10 Cube Tipper Truck - R5m
  Landfill Compactor R14m & Landfill Dozer - R10,8m
  Refuse Compaction 10 Tonne - R13,2m
Roll Over - Discretionary Grant has 15 projects 9 are below 0% progress, top 5 in value;
  Resealing of streets (roll over - dg) – R20m
  Sterkwater www (roll over - dg) – R10,4m
  Tipper trucks (roll over - dg) – R10,7m
  Maintenance trucks (roll over - dg) – R6,5m
  TLbs (backactors) (roll over - dg) – R8,8m

## Slide 11: MANGAUNG (ISUPG) Projects Summary Per Metropolitan as at 31 May 2023
The City of Mangaung is spending on the following Projects:
Two(2) projects on CENTLEC are spending at R13m of a budget of R21m with an amount of R7.9m unspent
Thirty 30 Project under Human Settlements are only spending on Provision of Permanent Engineering Services Phase 3, with projects such as:
Caleb Motshabi/Kgotsong Informal Settlement,-Main Road & Stormwater, Project Expenditure R25.4m with a Variance of R16m
Botshabelo West Informal Settlement- Main Road & Stormwater, Project Expenditure R11.2 with a variance of R2.6m
Zuma Square Informal Settlement,-Water & Sanitation, Project Expenditure R2.5m with a variance of R 5.4m
DEPARTMENT | BUDGET | % OF TOTAL GRANT | Total Expenditure as at 31 May 2023 | % Total Expenditure as at 31 May 2023 | TOTAL NO. OF PROJECTS | PROJECTS @ 0% EXPENDITURE | PROJECTS @ 1% -85% EXPENDITURE | PROJECTS > 85% EXPENDITURE
CENTLEC | R21,276,390.00 | 10% | R13,312,581.22 | 63% | 2 | 0 | 2(R7.9m) | 0
HUMAN SETTLEMENTS | R176,340,610.00 | 86% | R57,477,906.40 | 33% | 30 | 21(R21) | 8(R95.1m) | 1(R2.7)
5% OPSCAPS | R7,000,000.00 | 3% | - | 0% |  |  |  | 
TOTAL | 204,617,000.00 | 100% | R70,790,487.61 | 35% | 32 | 21(R21m) | 10(R103m) | 1(R2.7m)

## Slide 12: THANK YOU