## Slide 1
DEPARTMENT OF HIGHER EDUCATION AND TRAINING
Briefing on 2021/22 Second and Third Quarter Performance Report (Financial and Non-Financial)
Presentation to the
Portfolio Committee on Higher Education, Science and Technology
Date: 04 March 2022

## Slide 2
Outline of the Presentation
Vision and Mission
Five-year Strategic Plan Outcomes
Significant Developments During the Period Under Review
Programme Performance against 2nd and 3rd Quarter Targets of 2021/22 financial year
Financial Performance

## Slide 3
Vision
An integrated and coordinated PSET system for improved economic participation, and social development of youth and adults.
Mission
To provide strategic leadership to the PSET system through:
Development of appropriate steering mechanisms
Effective oversight, monitoring and evaluation
Funding of PSET institutions and entities
Provision of support services in relation to teaching and learning
Vision and Mission

## Slide 4
Improved quality of PSET provision
A responsive PSET system
Excellent business operations within DHET
Expanded access to PSET opportunities
Improved efficiency and success of the PSET system
Five-year Strategic Plan Outcomes: 2020-2025

## Slide 5
Significant developments during the period under review
Economic Reconstruction and Recovery Plan - Skills Strategy
Developed a Skills Strategy to support the Economic Reconstruction and Recovery Plan given the slow job creation, exacerbated by COVID-19
The Skills Strategy was developed as part of the DHET’s Labour Market Intelligence research project
An Implementation Plan is being finalised with delivery partners
Technical Implementation Forum has been established to oversee implementation

## Slide 6
Significant Development During the Period Under Review
Finalised validation processes on data for student enrolments, completions, etc. for the 2020 academic year
Student enrolments
There were 1 094 808 students enrolled in pubic universities for the 2020 academic year against the planned target of (1 090 000).
NSFAS funded 504 336 students at universities against the planned target of 427 851.
In TVET colleges, enrolments were lower than planned. There were 452 277 headcount enrolments than the planned 610 000.
261 404 (target 310 900) TVET college students received funding through NSFAS (this brings a the total of NSFAS funded students in both universities and TVET colleges to 765 740).
5 250 TVET college students were enrolled in the Pre-vocational Learning Programme (PLP) to improve their chances of success.
There were 142 585 students enrolled in CET colleges. This is lower than the planned target of 220 549.
Chart: NSFAS Funded Students
| Universities | TVET Colleges
2020 Validated | 504336 | 261404
2021 Preliminary | 494932 | 271857
Chart: Student Enrollments
| Universities | TVET Colleges
2020 Validated | 1094808 | 452277
2021 Preliminary | 1039471 | 497123

## Slide 7
Significant Developments During the Period Under Review
  Centres of Specialisation
  Accredited 6 TVET colleges to be trade test centres for occupational qualifications.
  69 artisan learners received training through the Centres of Specialisation.
  This is a ground-breaking skills development initiative that aligns to and supports Artisanal skills needs of industry and the economy at large
  Each college is pursuing partnerships with industry to enable placement of graduates
TVET Lecturer development
10 universities have received accreditation for 11 TVET programmes - seven of these are offering TVET programmes.
3 universities are awaiting CHE accreditation and two universities are engaged with institutional processes.
155 lecturers have registered for professional qualifications at the NMU and TUT.

## Slide 8
Significant Developments During the Period Under Review
Student Funding
The 2022 Guidelines for the DHET bursary scheme for students at public universities and TVET colleges were approved by the Minister.
Public institutions (universities and TVET Colleges) were issued with letters to implement the guidelines.
A Fee Regulatory Framework for the public higher education system was developed and proposed fees based on a Consumer Price Index (CPI) increase for the 2022 academic year has been submitted to the Minister.

## Slide 9: Second Quarter Performance information

## Slide 10
Overall Performance against 2nd and 3rd Quarter Targets
Quarter 2: 2021/22
There were 18 targets during the second quarter of 2021/22
9 (50%) of the targets were achieved
Quarter 3: 2021/22
The third quarter, there were 16 targets
3 (19%) of the targets were achieved within the timeframe
Subsequent achievements: 4
Chart: 2nd Quarter targets Vs Performance
| Number of Targets | Number of Targets Achieved
 | 18 | 9
Chart: 3rd Quarter targets Vs Performance
| Number of Targets | Number of Targets Achieved
 | 16 | 3

## Slide 11
Programme Performance against 2nd Quarter Targets (2021/22)
Programme | Quarter /Milestone Target | Milestone/ Target Achievement | Reason for Deviation
Programme 1: Administration | Percentage of valid invoices received from creditors paid within 30 days (100%) | Target not achieved The Department has managed to pay 99% of all invoices within the 30-day period. | Delays as a result of technical challenges with LOGIS system Pending credit notes
 | 2. Unqualified audit opinion | Target achieved | 
Programme | Quarter Milestone/ Target | Progress Status | Reason for Deviation
Programme 4: TVET | Draft concept on three year enrolment plan with differentiation in programme enrolment circulated to stakeholders for consultation by 30 September 2021 | Target not achieved | Lack of capacity. Additional capacity will be obtained from other Directorates while we await the filling of vacant posts by human resources.
 | Draft framework and guidelines to accommodate students with disabilities circulated to stakeholders for consultation by 30 September 2021 | Target not achieved | The Draft framework and Guidelines were not circulated and consulted on time. The Deputy Director-General’s approval of the revised Framework and Guidelines will be obtained by end of February 2022.

## Slide 12
Programme Performance against 2nd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Progress Status | Reason for Deviation
Programme 4: TVET | Criteria for the selection of TVET colleges circulated to stakeholders for consultation by 30 September 2021 | Target not achieved | Criteria for the selection of TVET colleges was not circulated and consulted to stakeholders in time
 | A draft progress report on cooperation agreement with Germany on SAIVCET work approved by the Deputy Director-General by 30 September 2021 | Target achieved A draft progress report on cooperation on agreement with Germany on SAIVCET work was approved by the Deputy Director-General on 21 September 2021 | N/A
 | Examination results per cycle for qualifying student released in 40 days from last date of exams timetable | Target not achieved | Non-compliance with the reporting standards and guidelines

## Slide 13
Programme Performance against 2nd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Milestone / Target Achievement | Reason for Deviation
Programme 4: TVET | Percentage reduction of certification backlog (100%) | Target not achieved 98.36% | Non-compliance with the reporting standards and guidelines
 | Monitoring report on the conduct, management and administration of TVET college examinations and assessment approved by Director-General by 30 September 2021 | Target achieved Monitoring report on the conduct, management and administration of TVET college examinations and assessment approved by Director-General on 30 September 2021 | N/A
 | Draft standard governance standards for TVET college councils circulated for consultation by 30 September 2021 | Target not achieved | Non-compliance with the reporting standards and guidelines
 | A draft monitoring framework and plan for the implementation of the institutional maturity model consulted by 30 September 2021 | Target achieved A final draft monitoring framework has been compiled and consulted | N/A
 | A progress report on the development of TVET colleges infrastructure maintenance plans for 2022/23 relating to all sites of delivery approved by the Deputy Director-General by 30 September 2021 | Target achieved A progress report on the development of TVET colleges infrastructure maintenance plans for 2022/23 relating to all sites of delivery was approved by the Deputy Director-General by 27 September 2021 | N/A

## Slide 14
Programme Performance against 2nd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Milestone / Target Achievement | Reason for Deviation
Programme 4: TVET | Draft norms for differentiated infrastructure linked to curriculum delivery approve by the Director-General by 30 September 2021 | Target not achieved Draft norms for differentiated infrastructure linked to curriculum delivery was developed and approved by the Deputy Director- General on 27 September 2021; | Gazetting of norms and standards were delayed
Programme 5: Skills Development | Report on the implementation of the NSDS by SETAs approved by the Director-General by 30 September 2021 | Target achieved Report on the implementation of the NSDS by SETAs approved by the Director-General by 23 August 2021 | N/A
 | Average lead time from qualifying trade test applications received until trade test is conducted (40 days) | Target achieved 34 days | N/A

## Slide 15
Programme Performance against 2nd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Milestone / Target Achievement | Reason for Deviation
Programme 6: CET | Service provider for the development of a sustainable funding model for CET colleges appointed by 30 September 2021 | Target not achieved | The process for the approval and advertisement of the tender took longer than expected
 | A report on the implementation of teaching and learning improvement plans at CET colleges approved by the Director-General by 30 September 2021 | Target achieved A submission and report on the implementation of teaching and learning improvement plans at CET was approved by the Acting Director-General on 30 September 2021 | N/A
 | 3. Draft governance standards and regulations for CET college councils approved by the Deputy Director-General by 30 September 2021 | Target achieved Draft governance standards and regulations for CET college councils were approved by the Deputy Director-General: CET on 30 September 2021 | N/A

## Slide 16: Third Quarter Performance Information

## Slide 17
Programme Performance against 3rd Quarter Targets (2021/22)
Programme | Quarter /Milestone Target | Milestone/ Target Achievement | Reason for Deviation
Programme 1: Administration | Percentage of valid invoices received from creditors paid within 30 days (100%) | Target not achieved | Delays as a result of technical challenges with LOGIS system Pending credit notes
Programme 3:University Education | 1. Norms and standards for PSET student housing approved by the Director-General for submission to the Minister for publication as policy by 31 December 2021 | Target not achieved | Student housing norms and standards are being reviewed to include TVET Colleges and the draft review policy was gazetted for public comments on 29 October 2021.
 | 2. Updated Guidelines for the Implementation of the DHET Bursary Scheme for poor and working class students at public universities submitted to the Minister for approval by 31 December 2021 | Target not achieved . | The 2022 Guidelines for the DHET bursary scheme for University Students can only be finalised once certainty about the shortfall from National Treasury is confirmed as this will have an impact on the current student funding policy.
 | 3. A report on the financial health of all public HEIs approved by the Director-General by 31 December 2021 | Target achieved A report on the financial health of all public HEIs was approved by the Director-General on 14 December 2021. | N/A
 | 4. A report on the evaluation of creative and innovation outputs by public universities approved by the Director-General by 31 December 2021 | Target achieved A Report on the evaluation of creative and innovation outputs by public universities was approved by the Director-General on 27 December 2021. | N/A

## Slide 18
Programme Performance against 3rd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Milestone / Target Achievement | Reason for Deviation
Programme 4: TVET | Draft consolidated three-year enrolment plan approved by the Deputy Director-General by 31 December 2021 | Target not achieved There was little development of the three-year enrolment plan with differentiation. | Lack of capacity Can only be achieved in the next financial year
 | 2. Revised guidelines to accommodate students with disabilities approved by the Deputy Director-General by 31 December 2021 | Target not achieved The Draft Framework and Guidelines were revised based on the input received during the regional workshops. | Approval of the DDG was not obtained in time. New target date: end February 2022
 | 3. Nominated TVET Colleges approved by the Deputy Director-General by 31 December 2021 | Target not achieved Four (4) colleges were identified and are being visited to determine whether they meet the set criteria. Final consultations were made with TVET colleges on the draft criteria on establishment of disability support units. | Delays in the identification of colleges to be considered for the nominations
 | Examination results per cycle for qualifying students released in 40 days from last date of exams timetable | Target not achieved Examination results per cycle for qualifying students were released in 49 days | Non-compliance with the reporting standards and guidelines
 | Percentage reduction on certification backlog (80%) | Target not achieved 99.94% | Non-compliance with the reporting standards and guidelines

## Slide 19
Programme Performance against 3rd Quarter Targets (2021/22)
Programme | Quarter Milestone/ Target | Milestone / Target Achievement | Reason for Deviation
Programme 4: TVET | Monitoring report on the conduct, management and administration of TVET college examinations and assessment approved by Director-General by 31 December 2021 | Target not achieved Monitoring report on the conduct, management and administration of TVET college examinations and assessment was compiled | Subsequently achieve: Report signed outside of the reporting timeframe
 | Consolidated draft standard governance standards for TVET college councils approved by the Deputy Director-General by 31 December 2021 | Target not achieved | Poor planning as a result the target has been readjusted
 | Consolidated assessment framework and implementation plan for the institutional maturity model for TVET colleges approved by the Deputy Director-General by 31 December 2021 | Target not achieved Final draft of maturity assessment framework completed, and assessment methodology and reporting templates tested at 2 colleges in the Western Cape. | Assessment framework and the implementation plan were not approved by the Deputy Director General
Programme 5: Skills Development | 1. Report on the implementation of the NSDS by SETAs approved by the Director-General by 31 December 2021 | Target achieved Report on the implementation of the NSDS by SETAs approved by the Director-General by 14 December 2021 | None
 | 2. Average lead time from qualifying trade test applications received until trade test is conducted (40 days) | Target not achieved 42 days | This is a preliminary report which still needs to be validated by end of 4th quarter.
 | 3. Skills Strategy approved by the Minister by 31 December 2021 | Target not achieved | Delays caused by the need to ensure consultations and resultant incorporation of comments

## Slide 20
The Department’s annual appropriation for the 2021/22 financial year amounts to R115.6 billion as follows:
Voted funds R97.784 billion
Skills levy R17.813 billion
The allocation per programme is as follows:
R’million
1: Administration 503.990
2: Planning, Policy and Strategy 230.721
3: University Education 81 223.295
4: TVET 13 096.161
5: Skills Development 18 120.714*
* [Including the Direct Charges (Skills Levy to SETAs
and NSF) amounting to R17 812.863 million]
6: Community Education and Training 2 421.987
2021/22: Overview of Allocations – 2nd Quarter

## Slide 21
2021/22: Overview of Expenditure: 2nd Quarter
Spending at the end of Quarter 2 increased by 63% from R48.757 billion to R79.485 billion.
The total expenditure for the period ending 30 September 2021 of R79.485 billion represents a spending rate of 68.8%, of which R9.233 billion is for the skills levy.
Spending on operational expenditure increased from 11.5% to 27.4% amounting to R187.7 million.
University Education remains the biggest spending programme at an amount of R63.387 billion, followed by Technical and Vocational Education and Training at R5.435 billion and Community Education and Training at R0.970 billion.
Transfer payments (R74.957 billion) and compensation of employees (R4.340 billion) are the biggest spending items on the budget.
With regard to transfer payments, all block grant subsidy payments to universities, TVET Colleges, CET Colleges and public entities are on schedule.
Detail per programme and economic classification is reflected in the next two slides.

## Slide 22
Status of expenditure per programme: 2nd Quarter
Status of Expenditure per Programme | Main Appropriation R’000 | Actual Expenditure (Quarter 2) R’000 | Balance Available R’000
1: Administration | 503 990 | 201 289 | 302 701
2: Planning, Policy and Strategy | 230 721 | 107 216 | 123 505
3: University Education | 81 223 295 | 63 387 537 | 17 835 758
4: Technical and Vocational Education and Training | 13 096 161 | 5 437 087 | 7 659 074
5: Skills Development | 307 851 | 149 075 | 158 776
6: Community Education and Training | 2 421 987 | 969 632 | 1 452 355
Direct Charges ( Skills Levy to SETAs and NSF) | 17 812 863 | 9 233 424 | 8 579 439
Total | 115 596 868 | 79 485 260 | 36 111 608

## Slide 23
Status of expenditure per economic classification: 2nd Quarter
Status of Expenditure per Economic Classification | Main Appropriation R’000 | Actual Expenditure (Quarter 2) R’000 | Balance Available R’000
Compensation of Employees | 10 311 556 | 4 340 423 | 5 971 133
Personnel Expenditure | 10 085 986 | 4 230 133 | 5 855 853
Examiners and Moderators | 225 570 | 110 290 | 115 280
Goods and Services | 666 130 | 183 623 | 482 507
Transfer Payments | 104 601 189 | 74 957 137 | 29 644 052
Capital Expenditure | 17 993 | 4 077 | 13 916
Total | 115 596 868 | 79 485 260 | 36 111 608

## Slide 24
2021/22: Overview of Expenditure: 2nd Quarter
Institution/Entity | Main Appropriation R’000 | Actual Expenditure (Quarter 2) R’000 | Balance Available R’000
Universities | 45 561 915 | 34 297 885 | 11 264 030
Public Entities |  |  | 
National Student Financial Aid Scheme (NSFAS) | 35 456 555 | 29 006 722 | 6 449 833
Council on Higher Education (CHE) | 70 012 | 35 006 | 35 006
South African Qualifications Authority (SAQA) | 82 793 | 41 397 | 41 396
Quality Council for Trades and Occupations (QCTO) | 27 630 | 13 814 | 13 816
Public Services SETA | 120 082 | 60 041 | 60 041
Education and Training Practices SETA | 20 256 | 18 079 | 2 177
Higher Health | 20 075 | 10 771 | 9 304
National Institute for Humanities and Social Sciences | 38 691 | 19 346 | 19 345
TVET Colleges Subsidies | 5 181 549 | 2 100 269 | 3 081 280
CET College Subsidies | 204 602 | 102 305 | 102 297
Foreign Governments and International Organisations | 4 166 | 2 996 | 1 170
Leave Gratuity | - | 15 082 | - 15 082
TOTAL | 86 788 326 | 65 723 713 | 21 064 613
* The reprioritisation of R3.040 billion as approved by National Treasury was not yet included in the above tables |  |  | 

## Slide 25: Third Quarter 2021/22

## Slide 26
The Department’s adjusted appropriation for the 2021/22 financial year amounts to R116.8 billion as follows:
Voted funds R97.889 billion
Skills levy R18.933 billion
The allocation per programme is as follows:
R’million
1: Administration 463.596
2: Planning, Policy and Strategy 239.831
3: University Education 81 925.240
4: TVET 12 440.770
5: Skills Development 19 382.814*
* [Including the Direct Charges (Skills Levy to SETAs
and NSF) amounting to R18 932.767 million]
6: Community Education and Training 2 369.521
2021/22: Overview of Allocations

## Slide 27
Other Adjustments
Description | Amount R’000 | Comment
Compensation of Employees | (65 000) | Reprioritised to NSFAS to fund a core business system
Compensation of Employees | (85 000) | Declared surplus in view of the projected underspending.
Total | (150 000) | 

## Slide 28
Additional Funding
Description | Amount R’000 | Comment
Skills Levy | 1 119 904 | Skills levy adjusted upwards due to the collection trends.
Universities: Graduate Assistants | 90 000 | Presidential Youth Employment Initiative (PYEI) to employ 3000 unemployed university graduates across 26 public universities.
National Skills Fund: Performance model for demand-led skills training | 100 000 | Delivery of demand-led digital skills training with focus on Global Business Services and ICT. This aims to create 4500 new jobs for young people.
Total | 1 309 904 | 

## Slide 29
2021/22: Overview of Expenditure: 3rd Quarter
Spending at the end of Quarter 3 increased with 31.9% from R79.485 billion to R104.874 billion.
The total expenditure for the period ending 31 December 2021 of R104.874 billion represents a spending rate of 89.8%, of which R13.925 billion is for the skills levy.
Spending on operational expenditure increased by 91.6% from R187.7 million in the second quarter to R359.7 million in the third quarter and represents a spending trend of 56.8%.
University Education remains the biggest spending programme at an amount of R80.335 billion, followed by Technical and Vocational Education and Training at R8.325 billion and Community Education and Training at R1.593 billion.
Transfer payments (R97.771 billion) and compensation of employees (R6.743 billion) are the biggest spending items on the budget.
With regard to transfer payments, all block grant subsidy payments to universities, TVET Colleges, CET Colleges and public entities are on schedule.
Detail per programme and economic classification is reflected in the next two slides.

## Slide 30
Status of expenditure per programme: 3rd Quarter
Status of Expenditure per Programme | Adjusted Appropriation R’000 | Actual Expenditure (Quarter 3) R’000 | Balance Available R’000
1: Administration | 463 596 | 311 853 | 151 743
2: Planning, Policy and Strategy | 239 831 | 161 312 | 78 519
3: University Education | 81 925 240 | 80 335 139 | 1 590 101
4: Technical and Vocational Education and Training | 12 440 770 | 8 325 969 | 4 114 801
5: Skills Development | 450 047 | 221 192 | 228 855
6: Community Education and Training | 2 369 521 | 1 592 978 | 776 543
Direct Charges ( Skills Levy to SETAs and NSF) | 18 932 767 | 13 925 436 | 5 007 331
Total | 116 821 772 | 104 873 879 | 11 947 893

## Slide 31
Status of expenditure per economic classification: 3rd Quarter
Status of Expenditure per Economic Classification | Adjusted Appropriation R’000 | Actual Expenditure (Quarter 2) R’000 | Balance Available R’000
Compensation of Employees | 9 640 486 | 6 743 115 | 2 897 371
Personnel Expenditure | 9 407 905 | 6 591 209 | 2 816 696
Examiners and Moderators | 232 581 | 151 906 | 80 675
Goods and Services | 615 280 | 344 268 | 271 012
Transfer Payments | 106 548 013 | 97 771 034 | 8 776 979
Capital Expenditure | 17 993 | 15 462 | 2 531
Total | 116 821 772 | 104 873 879 | 11 947 893

## Slide 32
2021/22: Overview of Expenditure: 3rd Quarter
Institution/Entity | Main Appropriation R’000 | Actual Expenditure (Quarter 2) R’000 | Balance Available R’000
Universities | 43 162 765 | 41 788 039 | 1 374 726
Public Entities |  |  | 
National Student Financial Aid Scheme (NSFAS) | 38 561 555 | 38 420 860 | 140 695
Council on Higher Education (CHE) | 70 012 | 52 509 | 17 503
South African Qualifications Authority (SAQA) | 82 793 | 62 095 | 20 698
Quality Council for Trades and Occupations (QCTO) | 27 630 | 20 722 | 6 908
Public Services SETA | 120 082 | 90 061 | 30 021
Education and Training Practices SETA | 18 079 | 18 079 | 
National Skills Fund (NSF): Demand led skills | 100 000 |  | 100 000
Higher Health | 20 075 | 16 062 | 4 013
National Institute for Humanities and Social Sciences | 38 691 | 29 019 | 9 672
TVET Colleges Subsidies | 5 184 519 | 3 169 910 | 2 014 609
CET College Subsidies | 206 779 | 155 629 | 51 150
Foreign Governments and International Organisations | 4 166 | 2 996 | 1 170
Leave Gratuity | 18 100 | 19 617 | - 1 517
TOTAL | 87 615 246 | 83 845 598 | 3 769 648

## Slide 33: Economic Classifications spending trends: Quarter 1 to Quarter 3
Chart: 
| 1st quarter | 2nd quarter | 3rd quarter
Compensation of Employees | 2091474 | 2248949 | 2402692
Goods and Services | 77832 | 105791 | 160645
Capital Expenditure | 897 | 3180 | 11385

## Slide 34: Spending trends of Transfers and Subsidies: Quarter 1 to Quarter 3
Chart: Spending trend of Transfers and Subsidies
| Transfer Payments (Including Skills Levy)
1st quarter | 46586309
2nd quarter | 28370828
3rd quarter | 22813897

## Slide 35
Thank You