## Sheet1
Province | School Name | Number of classrooms affected | Academic Year when Classrooms were affected | Temporary accommodation provided (Yes or No) Mobile Classrooms | Have the classrooms been Repaired | Safetey Measures to prevent future damage
Eastern Cape
Eastern Cape | Aaron Gqadu P.S | 2 | 2015 | yes | No, School assessed and is on procurement | fencing provided
Eastern Cape | Bayview P.S | 4 | 2015 | No | No, School assessed and is on procurement | Community Engagement
Eastern Cape | Bedford SSS | 4 | 2016 | Yes | Yes | additional renovation work done
Eastern Cape | Eric Mntonga SSS | admin | 2015 | no | yes | Community Engagement
Eastern Cape | Esitiyeni PS | 2 | 2016 | no | Assessment completed | Community Engagement
Eastern Cape | Fihlani PS | 6 | 2016 | no | Assessment completed | Community Engagement
Eastern Cape | Forbes Grant SSS | 2 | 2015 | No | No, School assessed and is on procurement | Fencing project identified
Eastern Cape | Freemantle SSS | 1 | 2015 | no | Yes | Fencing project identified
Eastern Cape | Holomisa SSS | 5 | 2016 | yes | no, Demolished | Fencing installed
Eastern Cape | Luhewini SSS | 10 | 2016 | yes | no, demolished | Fencing installed and matter reported to SAPS for investigation
Eastern Cape | Lungisa | 2 | 2016 | No | Assessment completed | Fencing on tender
Eastern Cape | Mahedi PS | 3 | 2015 | No | yes, on construction | Community Engagement
Eastern Cape | Majali S.S.S | 5 | 2015 | yes | yes | Fencing provided and community engaged and demands resolved
Eastern Cape | Masibambane PS | 2 | 2016 | No | Yes | Community Engagement
Eastern Cape | Mbenge JSS | 5 | 2016 | no | no | Community Engagement
Eastern Cape | Mhlanganisweni SSS | 5 | 2016 | no | no | fencing installed
Eastern Cape | Mjuleni PS | 1 | 2017 | No | No | Community Engagement
Eastern Cape | Nogemane SSS | 5 | 2016 | yes | No | Community Engagement
Eastern Cape | Nombulelo H.School | 0 (toilets) | 2016 | No | No | Community Engagement
Eastern Cape | Noncedo SSS | 3 | 2015 | yes | Yes | fencing being installed
Eastern Cape | Peterson SSS | 3 | 2016 | No | No (under refurbishment by DRPW) | Community Engagement
Eastern Cape | Sandisulwazi SSS | 2 | 2016 | No | No | Community Engagement
Eastern Cape | Thembalesizwe Technical SS | 4 | 2013 | No | No | project on design
Eastern Cape | Vulindlela SSS | 13 | 2016 | No | No | Fencing installed
Eastern Cape | Vulingcobo SSS | 2 | 2016 | No | No | Major realignment project commenced
Free State | None | N/A | N/A | N/A | N/A | N/A
Gauteng | Orlando Secondary School | 8 | 2016 | No | School has been repaired | Security measures are in place
Gauteng | Onverwacht Primary School | 4 | 2017 | No | In progress | Security measures are in place
Gauteng | Marotola Primary School | 4 | 2016 | damage was on the window panes | Yes | Security measures are in place
KwaZulu-Natal | Villa Maria Primary School | Admin Block | 2016 | No | School is prioritised for repairs in the 2017/18 financial year | Security fence erected and stakeholder meeting held
KwaZulu-Natal | Inhlazuka Primary School | Mobile Classrooms | 2015 | Yes | School is prioritised for repairs in the 2017/18 financial year | Community Engagement
KwaZulu-Natal | Richlea Primary School | 5 classrooms | 2016 | Yes | Classrooms have been repaired | Community Engagement
KwaZulu-Natal | Eminyezaneni High School | Admin block | 2017 | Yes | School is prioritised for repairs in the 2018/19 financial year | Community Engagement
KwaZulu-Natal | Imbubu Primary School | Admin block and 1 classroom | 2014 | Yes | School is currently under renovations | Community Engagement
KwaZulu-Natal | Siphumelele Secondary School | 3 mobile classrooms | 2015 | Yes | No | Community Engagement
KwaZulu-Natal | Mpephose Primary School | 2 classrooms and a gate | 2017 | No | School is prioritised for repairs in the 2017/18 financial year | Community Engagement
Limpopo | Gidjana Secondary | 4 classrooms | 2014 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Johannes Ramavhoya Secondary | Admin block plus 5 classrooms | 2014 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Malamulela Secondary | Admin block | 2014 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Nkatini Secondary | 3 classrooms | 2014 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Rhabela Secondary | 4 classrooms | 2014 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Shikundu Secondary | 4 classrooms | 2014 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Humula Secondary | 4 classrooms | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Masakona Primary | 4 classrooms completely burnt down and 3 classrooms partially burnt down | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Thomas Ntshaveni | 4 classrooms | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Avhatondwi Primary | Admin block plus 1 classroom | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Frank Mukhaswakule Primary | 8 classrooms | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Khwara Secondary | Admin block | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Kuruleni Primary | 2 classrooms | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Luambo Secondary | Admin block | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Lupendze Primary | Admin block plus 5 classrooms | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Maligana Wilson Secondary | Admin block | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Mariadze Primary | Admin block plus Guard House | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Mashaa Primary | Doors to admin office and two classrooms | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Mashau Primary | 3 classrooms and Consumer Studies Centre | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Masia Primary | Library | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Matsindevhe Primary | Admin block and 5 classrooms | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Mavhina Primary | 8 classrooms | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Mphagane Primary | Admin block and 2 classrooms | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Munwai Primary | 1 classroom | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Nwaridi Primary | 10 classrooms completely burnt down | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Radzambo Secondary | 2 classrooms burnt. 4 classrooms vandalized (with broken window panes and doors) | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Ramauba Primary | Admin block and Nutrition Centre | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Tshinavhe Secondary | New Admin block completely burnt down | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Tshipakoni Secondary | 2 tables burnt down | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Tshirudzanani Primary | Admin block partially burnt and window panes damaged | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Tshivhade Primary | 5 classrooms completely burnt down. 4 classrooms windows panes broken | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Vhafamadi Secondary | Admin block completely burnt down. 6 classrooms completely burned down. 3 classrooms partially burnt down | 2016 | Yes | Construction Completed (Private Donor funding) | All repaired schools are provided with security fencing
Limpopo | Vhudzani Secondary | Admin block and Science laboratory completely burnt down. 4 classrooms and Consumer Studies Centre completely burnt down. 5 classroom window panes vandalised | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Muvhimbi Primary | 1 classroom | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Ratshikhuthuma Primary | 4 classrooms completely burnt down and 3 classrooms partially burnt down | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Tshinanga Secondary | 1 classroom | 2016 | Yes | Contractor on site | All repaired schools are provided with security fencing
Limpopo | Mawela Primary | 4 classrooms | 2016 | Yes | No | All repaired schools are provided with security fencing
Limpopo | Mugoidwa Secondary | 4 classrooms | 2017 | Yes | No | All repaired schools are provided with security fencing
Mpumalanga | Bakutswe High School | Staff room and computer laboratory. | 2017 | No | Contractor is on site from start of April 2017. | Community engagements were carried out and for three weeks after the damages, security was deployed to the schools and only withdrawn after the situation was back to normal.
Mpumalanga | Lamulelani High School | Staffroom, storeroom and 8 classrooms. | 2017 | No | No. Low enrolment for the school vs undamaged facilities. Department considered not repairing the burnt classrooms. | Community engagements were carried out and for three weeks after the damages, security was deployed to the schools and only withdrawn after the situation was back to normal.
Mpumalanga | Kwanang High School | 3 Classrooms and proncipal's office | 2017 | No | Contractor is on site from start of April 2017. | Community engagements were carried out and for three weeks after the damages, security was deployed to the schools and only withdrawn after the situation was back to normal.
Mpumalanga | Ridzani High School | Only staffroom. | 2017 | No | Contractor is on site from start of April 2017. | Community engagements were carried out and for three weeks after the damages, security was deployed to the schools and only withdrawn after the situation was back to normal.
Mpumalanga | Masana High School | 4 Classrooms | 2017 | No | Contractor is on site from start on May 2017. | Community engagements were carried out and for three weeks after the damages, security was deployed to the schools and only withdrawn after the situation was back to normal.
Northern Cape | Nametsegang High School | administration block | 2014 | No | No, the building was made safe and the school is utilizing the old Administration Block | Engagements with the community and school was held within this time of the protests.
North West | Kelebogile PS | Four Classrooms and Admin Blocks | 2014 | Yes Two Mobile Classrooms | Construction of new classrooms and Office is in progress | School Safety Security awareness Programmes conducted.
North West | Noto Sec | Eight Classrooms and four Offices damaged | 2014 | Yes Nine Mobile Classrooms provided | Construction of new classrooms and Office is in progress | School Safety Security awareness Programmes conducted.
North West | Ramokonyane PS | Six classrooms and Admin Office damaged | 2014 | Yes Mobile Classrooms provided | Construction of new classrooms ,Admin Office and Library is in progress | School Safety Security awareness Programmes conducted.
North West | Volkskool | Hostel burnt | 2015 | No | Construction of new building in progress | School Safety Security awareness Programmes conducted.
North West | NW School for the Deaf | Hostel burnt | 2015 | No | Construction of new building in progress | School Safety Security awareness Programmes conducted.
North West | Mphuphuthe PS | One classroom burnt | 2016 | No | Contractor was able to fix and repair the damage | School Safety Security awareness Programmes conducted.
Western Cape | None | N/A | N/A | N/A | N/A | N/A

## Sheet2
Province | School Name | Number of classrooms affected | Academic Year when Classrooms were affected | Temporary accommodation provided (Yes or No) Mobile Classrooms | Have the classrooms been Repaired | Financial Implications in R’000 | Safetey Measures to prevent future damage