

NATIONAL ASSEMBLY

**FOR WRITTEN REPLY**

**QUESTION NO 2155**

**DATE OF PUBLICATION IN INTERNAL QUESTION PAPER: 14 OCTOBER 2016**

**(INTERNAL QUESTION PAPER NO. 30)**

**2155. Mr L J Basson (DA) to ask the Minister of Water and Sanitation:**

With reference to 16 completed contracts regarding the progress of Phase II of the Lesotho Highlands Water Scheme, what is, in each case, the (a) nature of the work completed, (b) particulars of the parties to the contract, (c) date the contract was entered into, (d) date the work was completed and (e) total amount (i) paid and/or (ii) still payable in terms of the contract NW2475E

---00O00---

**REPLY:**

Refer to **Annexure A** regarding progress of the 16 completed contracts of Phase II of the Lesotho Highlands Water Scheme.

**Annexure A**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Contract #** | **Description** | **Company** | **Date of Award** | **Date**  **completed** | **Contract price (Rand)** | **Cost**  **at completion (Rand)** |
| **Water Transfer Awarded Contracts : Completed** | |  |  |  |  | |
| **2222A-C** | Interim PMU- | JB Barry and Partners (Ireland) | 12-Aug-11 | Jan-14 | 19 459 612 | 19 459 612 |
|
| **2222D** | Interim PMU- | Dr S Turner - Individual Service Contract | 12-Aug-11 | Jan-14 | 4 295 015 | 4 295 015 |
| **4002** | Construction of Access Road to Polihali Weir | MOPS Civil Contractors Pty Ltd (- Lesotho company) | Nov-11 | 31-Mar-12 | 4 136 254 | 4 136 254 |
| **4001** | Construction of Polihali Downstream Weir | LSP Construction (Lesotho company) | 14-May-12 | 17-Oct-13 | 21 714 123 | 21 686 529 |
| **4014** | Tlokoeng Housing Renovations | LSP Construction | Jan-14 | Mar-14 | 1 171 385 | 1 171 385 |
| **3000** | Design and Supervision of PolihaliWeir | AECOM and sub consultants | 07-Dec-10 | Oct-13 | 2 492 652 | 2 493 236 |
| **3003** | LidarSurvey1 | CK Aerial Surveys | 12-Jun-12 | 31-Mar-13 | 1 771 250 | 1 771 250 |
| **3011** | LidarSurvey2 | CK Aerial Surveys | 12-Jun-12 | 30-Sep-13 | 514 298 | 514 298 |
| **3017** | Demarcation of Reservoir Boundary | Maleka, Ntsihlehle, Putsoa ( MNP) | May-14 | 30-Nov-15 | 7 950 100 | 8 215 930 |
| **6001** | Baseline Study-Water Quality and IFR | Institute of Natural Resources | 14-Jan-13 | 31-Aug-14 | 9 206 025 | 9 225 230 |
| **6002** | Baseline Study - Biological, Archeological & Heritage | Coastal and Environmental Services (CES) | 27-Nov-12 | 31-Mar-14 | 2 599 230 | 2 599 230 |
| **6008** | Baseline Study - Public Health | NonyanaHoohlo and Associates | Dec-13 | 09-Jul-15 | 6 740 575 | 6 045 475 |
| **6000** | Baseline Study - Socio-Economic | Coastal and Environmental Services (CES) | 27-Nov-12 | Oct-14 | 4 817 998 | 6 167 998 |
| **6000** | Baseline Study-Socio-Economic | LHDA Inhouse | Inhouse | Dec-14 | 1 480 | 1 480 |
| **6031** | Re-configuration of socio-economic database | GK Consulting | Jan-16 | Feb-16 | 91 256 | 91 256 |
| **9006** | Financing Strategy Consultant | Delloitte&Touche | Sep-14 | Mar-15 | 1 335 907 | 1 335 907 |
|  | **TOTAL** | |  |  | 88 297 160 | 89 210 085 |