

NATIONAL ASSEMBLY

**FOR WRITTEN REPLY**

**QUESTION NO 2156**

**DATE OF PUBLICATION IN INTERNAL QUESTION PAPER: 14 OCTOBER 2016**

**(INTERNAL QUESTION PAPER NO. 30)**

**2156. Mr L J Basson (DA) to ask the Minister of Water and Sanitation:**

With reference to the five contracts regarding the progress of Phase II of the Lesotho Highlands Water Scheme that were awarded, what is, in each case, the (a) nature of the work completed, (b) particulars of the parties to the contract, (c) expected date of completion and (d) projected total value of the contract? NW2476E

---00O00---

**REPLY:**

Refer to **Annexure A** regarding the progress of the five contracts of Phase II of the Lesotho Highlands Water Scheme.

**ANNEXURE A**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Contract #** | **Description** | **Company** | **Date of completion** | | **Tender price (Rand)** | **Cost to date (Rand)** |
|
| **Water Transfer Contracts being implemented** | | | | | | |
| 2223 | Project Management Unit | CDM Smith and Partners | | Dec-2025 | 349 889 571 | 131 625 324 |
| 3009 | Professional Services for the Urban Planning, D&S Project Housing & Associated Infrastructure | Polihali Infrastructure Consultants | | Apr-2021 | 79 365 621 | 14 019 480 |
| 3014 | D&S Polihali North Eastern Access Road | SMEC FMA Joint Venture | | Sep-2016 | 28 453 705 | 4 936 235 |
| 3015 | Professional services for the Evaluation, Optimisation, and Site Supervision of Geotechnical investigations | Jeffares and Green Joint Venture | | Sep-2017 | 19 750 472 | 7 026 482 |
| 6013 | RAP PNEAR and site establishment area(in house) | Inhouse by LHDA | | Jun-2017 | 1 500 000 | - |
| 4016 | Geotechnical investigations-Polihali Tunnel-drilling contractor | Diabor Pty Ltd | | Aug-2017 | 49 238 075 | 12 515 273 |
|  |  |  | | **Totals** | **528 197 444** | **170 122 794** |

D&S = Design and Construction supervision

RAP = Resettlement Action Plan

PNEAR = North East Access Road

D&S = Design and Construction supervision

ESIA = Environmental Social Impact Assessment

RAP = Resettlement Action Plan