**National Assembly**

**Question Number: 2487**

**Mr M S F de Freitas (DA) to ask the Minister of Transport:**

With reference to the reply to question 673 on 23 April 2018 regarding already built infrastructure to date, (a) what infrastructure has already been built, (b) by what date was each completed in each instance, (c) what were the set completion dates against planned dates, (d) what monitoring mechanisms took place in each instance and (e) what (i) did each monitoring report indicate in respect of each location and (ii) were the deficiencies identified?

**NW2680E**

**REPLY:**

(a) what infrastructure has already been built, (b) by what date was each completed in each instance, (c) what were the set completion dates against planned dates, (d) what monitoring mechanisms took place in each instance and (e) what (i) did each monitoring report indicate in respect of each location and (ii) were the deficiencies identified?

| **Plans/****Programme** | **Region** | **a)****Key Milestones** | **c)****Projected Completion Date** | **b)****Completion date** | **d)****Monitoring Mechanism Applied** | **e) i)****Results of monitoring report** | **e) ii)****Deficiencies identified** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Re-Signalling Programme | KwaZulu/Natal (KZN) |  | **07 Dec 2021** |  |  |  |  |
| Phase 1: Pinetown line | Phase 1B - 15 Sept 2018 | Phase 1A – 17 Dec 2017 | Project Progress meetings; | December 2017 - commissioned |  |
| Western Cape (WC) |  | **30 Jan 2020** |  |  |  |  |
| Phase 1.2: Wynberg – Simonstown, Crawford – Diep River | 30 Apr 2018 | 30 Apr 2018 | Project Progress Meeting; Monthly report; | April 2018 commissioned except Simonstown that is delayed to Sep 2018 | Theft and Vandalism is largely destabilizing the implementation |
| Phase 1.3: Salt River - Kenilworth | 18 Mar 2018 | 2 Jul 2018 | Project Progress Meeting; Monthly report; | July 2018 commissioned | Illegal encroachment into the Rail reserve. Security challenges prohibited to work on the central lines. |
| Gauteng |  | **28 Feb 2021** |  |  |  |  |
| Gauteng Nerve Centre (GNC) | 22 May 2015 | 30 Nov 2015 | Project Progress meetings; | Commissioned |  |
| Phase 1: Midway – Residentia | 15 May 2015 | 31 Mar 2016 | Project Progress Meeting; Monthly report | Commissioned |  |
| Phase 2: Kaalfontein – Leralla, Olifantsfontein – Irene | 03 Dec 2015 | 28 Nov 2016 | Project Progress meetings; | Commissioned |  |
| Phase 3: Randfontein – Roodepoort | 05 Mar 2016 | 15 May 2017 | Project Progress Meeting; Monthly report | Commissioned |  |
| Phase 4: Boksburg East – Springs, Daveyton – Alliance | 11 May 2016 | 15 Dec 2017 | Project Progress Meeting; Monthly report | Commissioned |  |
| Phase 5: George Goch – Geldenhuys, Benrose – Kaserne West, Booysens – Crown | 3 Apr 2018 | 26 Jan 2018 | Project Progress Meeting; Monthly report | BOY – CRN:09 Dec 2018Remainder January 2018 commissioned |  |
| **Depot Modernisation****Wolmerton** | Gauteng North | **Phase 1** complete**Phase 2** in testing & commissioning scheduled for completion by end March 2018 | 31 Mar 2018 | 30 Jun 2018 | Project Progress Meeting | Practical Completion certificate issued | Holistic planning for depot cannot be achieved if done in parts. Holistic plan for entire depot’s services will be done in Phase 3 Turnkey project.  |