## Renovation Projects
Parent Project ID | Parent Project Name | Project ID | Project No | Province | Facility Name | Facility No | Local Municipality | Project Status | Commitment Status | Project Start Date | Construction Start Date | Estimated Project Completion Date | Contracted Construction End Date | Estimated Construction End Date | Professional Fees | Construction Costs | Total Project Cost | Primary Funding Source | Nature of Investment
|  | 1812 | EDDP317 | Limpopo | Vhembe - Malamulele cluster circuit office - building works | 915154000 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1777000 | 7109000 | 8886000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1830 | LDPW-B/10091 | Limpopo | Mhluri Primary | 912520696 | Collins Chabane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 1829400 | 7317600 | 9147000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1841 | LE20IDT09007 | Limpopo | Ivy Park Primary School | 904222619 | Molemole | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1680000 | 6720000 | 8400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1847 | EDDP182/1991 | Limpopo | Baropodi Primary | 911360887 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 890000 | 3562000 | 4452000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1866 | EDDP184/237 | Limpopo | LEPHAPANE PRIMARY SCHOOL | 996606706 | Greater Tzaneen | Construction 1% - 25% | Active - Contracted | 2011-04-01 | 2011-07-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2565000 | 10260000 | 12825000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1905 | EDDP184/199 | Limpopo | TSHINANGE SECONDARY | 931520320 | Collins Chabane | Final Completion | Active - Contracted | 2014-04-01 | 2017-12-31 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 4343000 | 17370000 | 21713000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1916 | EDDP184/24 | Limpopo | ASIPHUMELELE SCHOOL | 996606830 | Elias Motsoaledi | Design | Active - Contracted | 2014-04-01 | 2019-04-01 | 2024-03-31 | 2024-04-30 | 2024-04-30 | 30000000 | 120000000 | 150000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1917 | EDDP184/236 | Limpopo | APRIL MAKGAKGA PRIMARY | 922220033 | Polokwane | Design | Active - Contracted | 2014-04-01 |  | 2024-06-30 |  |  | 7088000 | 28351000 | 35439000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1918 | EDDP184/23 | Limpopo | APRIL MAKGAKGA PRIMARY | 922220033 | Polokwane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2019-04-01 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 3620422 | 14481687 | 18102109 | Education Infrastructure Grant | Upgrading and Additions
|  | 1920 | EDDP184/22 | Limpopo | ALF MAKALENG PRIMARY | 922220026 | Polokwane | Final Completion | Active - Contracted | 2014-04-02 | 2015-09-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 5613000 | 22452000 | 28065000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1942 | EDDP184/419 | Limpopo | Setotolwane Special School | 923260659 | Polokwane | Construction 76% - 99% | Active - Contracted | 2013-04-01 | 2013-07-01 | 2024-11-30 | 2024-11-30 | 2025-03-31 | 3777000 | 15107000 | 18884000 | Education Infrastructure Grant | Upgrading and Additions
|  | 1944 | EDDP184/356 | Limpopo | WAYENI PRIMARY | 931521057 | Makhado | Feasibility | Active - Contracted | 2014-04-01 |  | 2024-06-30 |  |  | 2804559 | 13168622 | 15973181 | Education Infrastructure Grant | Upgrading and Additions
|  | 2037 | LE20IDT09014 | Limpopo | Mahwetse secondary | 924640897 | Makhuduthamaga | Construction 51% - 75% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-07-30 | 2024-09-30 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2108 | EDDP184/276A | Limpopo | KGOLOUTHWANE SECONDARY | 920210326 | Blouberg | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2017-09-09 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 5570000 | 22281000 | 27851000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2167 | LE21MON00001 | Limpopo | Rethuseng Special School | 992202502 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2020-04-02 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 0 | 13585820 | 13585820 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2169 | LE21MON00002 | Limpopo | RIVONI SCHOOL FOR THE BLIND | 929332041 | Makhado | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 0 | 13462202 | 13462202 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2204 | EDDP184/271 | Limpopo | HLUVUKA SECONDARY | 912520078 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1592000 | 6369000 | 7961000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2205 | EDDP184/288 | Limpopo | MABOKELELE PRIMARY | N/A | Polokwane | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 4506000 | 18025000 | 22531000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2206 | EDDP184/280 | Limpopo | KHWARA SECONDARY | 930321638 | Collins Chabane | On Hold | Active - Contracted | 2014-04-01 | 2014-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 4328828 | 18820991 | 23149819 | Education Infrastructure Grant | Upgrading and Additions
|  | 2207 | EDDP184/310 | Limpopo | MATLADI HIGH SCHOOL | 921230306 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2022-04-01 | 2026-03-31 | 2026-04-30 | 2026-05-30 | 5762732 | 23050928 | 28813660 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2209 | EDDP184/277 | Limpopo | KGWAREDI PRIMARY | 922220361 | Polokwane | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4563000 | 18254000 | 22817000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2210 | EDDP184/284 | Limpopo | HECTOR PETERSEN PRIMARY | 991104201 | Modimolle/Mookgophong | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4405000 | 17621000 | 22026000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2212 | EDDP184/273 | Limpopo | K.K. MONARE PRIMARY | 921142317 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-12-31 | 2024-12-31 | 4020000 | 16082000 | 20102000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2217 | EDDP184/353 | Limpopo | Tshilwavhusiku Razwimisani Special School | 993304507 | Makhado | Terminated | Active - Contracted | 2015-09-30 | 2016-12-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2383200 | 9532800 | 11916000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2218 | EDDP184/144 | Limpopo | TLOUPHUTI SECONDARY | 925630326 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2013-04-01 | 2017-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 3927000 | 15709000 | 19636000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2219 | EDDP184/274 | Limpopo | TLAME PRIMARY | 924642992 | Makhuduthamaga | Construction 51% - 75% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 7725000 | 30898000 | 38623000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2220 | EDDP184/143 | Limpopo | TJETJE TECHNICAL HIGH SCHOOL | 996606536 | Elias Motsoaledi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2016-04-30 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2357000 | 9428000 | 11785000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2238 | EDDP184/129 | Limpopo | Roedtan Combined | 906021822 | Modimolle/Mookgophong | Practical Completion (100%) | Active - Contracted | 2019-06-30 | 2020-06-30 | 2024-03-31 | 2024-04-30 | 2024-04-30 | 4103494 | 19267688 | 23371182 | Education Infrastructure Grant | Upgrading and Additions
|  | 2241 | EDDP184/219 | Limpopo | Raowele Secondary | 900000000 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2017-09-11 | 2024-03-30 | 2024-03-31 | 2024-04-30 | 4872000 | 19486000 | 24358000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2242 | EDDP184/224 | Limpopo | RALELEDU SECONDARY | 921142355 | Mogalakwena | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1825000 | 7299000 | 9124000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2248 | EDDP184/120 | Limpopo | Nkoshilo Secondary | 923241122 | Polokwane | Site Handed - Over to Contractor | Active - Contracted | 2019-04-01 | 2020-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 6428662 | 25714648 | 32143310 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2252 | EDDP184/119 | Limpopo | NGWANALAKA SECONDARY SCHOOL | 923241108 | Polokwane | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 3475765 | 13903062 | 17378827 | Education Infrastructure Grant | Upgrading and Additions
|  | 2253 | EDDP184/117 | Limpopo | Ngwamorei High | 924650481 | Lepele-Nkumpi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1125000 | 4500000 | 5625000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2259 | EDDP184/108 | Limpopo | Motsepe Primary | 925630258 | Greater Tubatse/Fetakgomo | Final Completion | Active - Contracted | 2013-04-01 | 2013-04-02 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 3849400 | 15397600 | 19247000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2260 | EDDP184/107 | Limpopo | Motloulela Secondary | 926530913 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2710400 | 10841600 | 13552000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2262 | EDDP184/215 | Limpopo | MOSHIRA PRIMARY | 921140847 | Mogalakwena | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1504000 | 6016000 | 7520000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2275 | EDDP184/152 | Limpopo | MATOKANE SECONDARY SCHOOL | 918510576 | Greater Tzaneen | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2190000 | 8760000 | 10950000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2279 | EDDP184/187 | Limpopo | Masha Primary | 925660709 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2017-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 5967000 | 23869000 | 29836000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2287 | EDDP184/82 | Limpopo | MAPANGULA PRIMARY | 922220651 | Polokwane | Design | Active - Contracted | 2014-04-01 |  | 2025-03-31 |  |  | 4413574 | 17654298 | 22067872 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2289 | EDDP184/81 | Limpopo | Manthe Primary School | 923240662 | Polokwane | Design | Active - Contracted | 2014-04-01 |  | 2025-03-31 |  |  | 7991022 | 31964087 | 39955109 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2291 | EDDP184/190 | Limpopo | Manoke Secondary | 925620572 | Greater Tubatse/Fetakgomo | Final Completion | Active - Contracted | 2014-04-01 | 2017-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 5782000 | 23129000 | 28911000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2293 | EDDP184/78 | Limpopo | Mananga Primary | 923240617 | Polokwane | Construction 76% - 99% | Active - Contracted | 0014-04-01 | 2017-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 6712200 | 26848800 | 33561000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2296 | EDDP184/70 | Limpopo | Makgongoana Secondary School | 923240464 | Polokwane | Tender | Active - Contracted | 2014-04-01 |  | 2025-03-31 |  |  | 2659000 | 10635000 | 13294000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2332 | EDDP184/247 | Limpopo | NKGOPOLENG BAKONE HIGH | 922251761 | Polokwane | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2448000 | 9794000 | 12242000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2341 | EDDP184/25 | Limpopo | Baphadima Secondary | 925660037 | Makhuduthamaga | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2018-04-30 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 3047000 | 12188000 | 15235000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2344 | EDDP184/150 | Limpopo | B.K. MATLALA SECONDARY | 922250072 | Polokwane | Site Handed - Over to Contractor | Active - Contracted | 2015-04-01 | 2019-03-31 | 2024-06-30 | 2024-07-30 | 2025-03-31 | 2410308 | 9641232 | 12051540 | Education Infrastructure Grant | Upgrading and Additions
|  | 2363 | LE20IDT09009 | Limpopo | Khudungane Secondary School | 919341800 | Greater Letaba | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-06-30 |  |  | 3214000 | 12856000 | 16070000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2380 | LE18TMT14135 | Limpopo | Boreletsane Primary | 918510057 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 538861 | 4282301 | 4821162 | Education Infrastructure Grant | Upgrading and Additions
|  | 2437 | LDPW-B/10070 | Limpopo | VAALTYN PRIMARY | 921121525 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2011-04-01 | 2011-06-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1661000 | 6642000 | 8303000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2460 | EDDP184/200 | Limpopo | TSHINAVHE SECONDARY | 930321530 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2014-04-10 | 2014-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2624000 | 10495000 | 13119000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2481 | EDDP184/209 | Limpopo | TSHADAMA SECONDARY | 930351524 | Thulamela | Construction 26% - 50% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 3187000 | 12747000 | 15934000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2482 | EDDP182/2062 | Limpopo | TSELAPEDI PRIMARY | 921141345 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2010-12-10 | 2011-03-31 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2061000 | 8244000 | 10305000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2530 | EDDP182/1981 | Limpopo | Supatsela primaryCombined | 996606627 | Rand West City | Construction 51% - 75% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 664000 | 2656000 | 3320000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2564 | EDDP184/269 | Limpopo | DIPOFUNG PRIMARY SCHOOL | 921230030 | Lepele-Nkumpi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2016-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 6721000 | 26883000 | 33604000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2566 | EDDP184/137 | Limpopo | SESHEGO HIGH | 923261324 | Polokwane | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2019-04-01 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 3299548 | 15492812 | 18792360 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2584 | EDDP184/262 | Limpopo | SEPANYA PRIMARY | 920211770 | Blouberg | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2024-06-30 | 992000 | 3969000 | 4961000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2588 | EDDP182/1971 | Limpopo | SEOKE PRIMARY | 925631688 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 657000 | 2627000 | 3284000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2618 | LDPW-B/10068 | Limpopo | SEKGODIWA PRIMARY | 921121426 | Mogalakwena | Final Completion | Active - Contracted | 2011-04-01 | 2011-06-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 1682000 | 6728000 | 8410000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2659 | LDPW-B/10055 | Limpopo | KURHULA PRIMARY SCHOOL | 903420666 | Ba-Phalaborwa | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-29 | 2024-06-29 | 2024-06-30 | 898000 | 3591000 | 4489000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2660 | EDDP182/209 | Limpopo | John Xikundu Primary | 993301300 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2016-08-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2675 | EDDP184/239 | Limpopo | Rita Primary | 915531030 | Greater Tzaneen | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2016-04-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 4884000 | 19537000 | 24421000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2680 | LE20IDT09027 | Limpopo | Riba Primary | 919340807 | Greater Tubatse/Fetakgomo | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1400000 | 5600000 | 7000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2702 | EDDP184/334 | Limpopo | RANTOBENG SECONDARY SCHOOL | 924642572 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2025-03-31 | 10217774 | 40871098 | 51088872 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2731 | LDPW-B/10078 | Limpopo | RAKOPI PRIMARY | 923241207 | Polokwane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 1918000 | 7672000 | 9590000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2733 | EDDP182/11 | Limpopo | RAKGOLOKWANE SECONDARY | 926540379 | Maruleng | Construction 26% - 50% | Active - Contracted | 2009-01-01 | 2009-08-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 340000 | 1360000 | 1700000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2753 | EDDP184/125 | Limpopo | POTLAKE SECONDARY | 925630999 | Greater Tubatse/Fetakgomo | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2019-05-01 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 2400000 | 9600000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2755 | LDPW-B/10084 | Limpopo | Poo Secondary School | 925631596 | Greater Tubatse/Fetakgomo | Final Completion | Active - Contracted | 2011-04-01 | 2011-08-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 1361000 | 5444000 | 6805000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2770 | EDDP184/244 | Limpopo | PHOPHI SECONDARY | 929311397 | Thulamela | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2834000 | 11335000 | 14169000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2771 | EDDP182/1961 | Limpopo | PHOOKO PRIMARY | 996606719 | Elias Motsoaledi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-06-30 | 2023-03-31 | 2023-03-31 | 695000 | 2780000 | 3475000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2779 | EDDP184/122 | Limpopo | PHEEHA PRIMARY | 996606539 | Greater Letaba | Tender | Active - Not Contracted | 2019-03-31 |  | 2024-03-31 |  |  | 3620569 | 17000143 | 20620712 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2791 | EDDP184/121 | Limpopo | PFUNANANI SPECIAL SCHOOL FOR LEARNERS WITH EDUCATIONAL DISABILITY | 994401200 | Greater Giyani | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2020-04-01 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 30000000 | 120000000 | 150000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2795 | LDPW-B/10090 | Limpopo | Pembunuka Primary | 912520887 | Collins Chabane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1307000 | 5226000 | 6533000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2803 | EDDP184/182 | Limpopo | PAEPAE SECONDARY | 925630531 | Greater Tubatse/Fetakgomo | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 2440000 | 9760000 | 12200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2807 | EDDP182/1992 | Limpopo | Onane Primary grade R | 924650528 | Makhuduthamaga | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-04-01 | 2023-06-30 | 2023-06-30 | 854000 | 3414000 | 4268000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2828 | LDPW-B/10092 | Limpopo | NKUZANA PRIMARY | 912520818 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2011-04-01 | 2011-07-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1279000 | 5114000 | 6393000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2866 | EDDP184/196 | Limpopo | NDENGEZA HIGH | 924642862 | Greater Giyani | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 6693188 | 26772750 | 33465938 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2868 | EDDP184/176 | Limpopo | NAPE-A-NGOATO HIGH | 925610384 | Ephraim Mogale | Construction 76% - 99% | Active - Contracted | 2014-03-27 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2167000 | 8666000 | 10833000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2888 | LDPW-B/12005 | Limpopo | MUSWODI PRIMARY SCHOOL | 929310035 | Musina | Final Completion | Active - Contracted | 2008-03-08 | 2008-07-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 340000 | 1361000 | 1701000 | Education Infrastructure Grant | Upgrading and Additions
|  | 2916 | EDDP184/378 | Limpopo | MPUMULANI SECONDARY | N/A | Greater Tzaneen | Construction 26% - 50% | Proposed | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1675000 | 6700000 | 8375000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2924 | EDDP184/111 | Limpopo | MPHETSEBE SECONDARY | 923241078 | Polokwane | Practical Completion (100%) | Proposed | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-03-31 | 2024-03-31 | 3371317 | 15829799 | 19201116 | Education Infrastructure Grant | Upgrading and Additions
|  | 2941 | EDDP184/216 | Limpopo | MPADI SECONDARY | 996606822 | Mogalakwena | Construction 1% - 25% | Proposed | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-03-31 | 2024-03-31 | 4328000 | 17312000 | 21640000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 2947 | EDDP184/392 | Limpopo | MOTSIPA SECONDARY | 918510767 | Greater Letaba | Construction 51% - 75% | Proposed | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 700000 | 2800000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 2982 | EDDP182/1993 | Limpopo | More-o-moso Primary | 996606827 | Ephraim Mogale | Construction 51% - 75% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 655000 | 2619000 | 3274000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3016 | EDDP184/375 | Limpopo | MOKOBOLA SECONDARY | 925620770 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1636000 | 6544000 | 8180000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3027 | LE18DBS02006 | Limpopo | MOHLATLEGO-MACHABA SECONDARY | 918510682 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 3537800 | 14151200 | 17689000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3039 | LDPW-B/10086 | Limpopo | MOGOHLONG PRIMARY | 922211084 | Blouberg | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 1792000 | 7167000 | 8959000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3049 | LDPW-B/10085 | Limpopo | MODULATHOKO PRIMARY | 920211060 | Blouberg | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-31 | 2021-03-31 | 1648000 | 6590000 | 8238000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3054 | EDDP184/371 | Limpopo | MODIPA AGRICULTURAL SCHOOL | 924610131 | Greater Tubatse/Fetakgomo | Construction 51% - 75% | Proposed | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 434000 | 1737000 | 2171000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3074 | EDDP184/252 | Limpopo | MMANTOLE PRIMARY | N/A | Blouberg | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2017-04-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1989000 | 7958000 | 9947000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3078 | LDPW-B/10087 | Limpopo | Mmananya Primary School (Capricorn District) | 921110501 | Polokwane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 1423000 | 5691000 | 7114000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3082 | LDPW-B/10058 | Limpopo | MMAMAKWA PRIMARY | 910130901 | Bela-Bela | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-31 | 2021-03-31 | 1309000 | 5236000 | 6545000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3088 | EDDP184/116 | Limpopo | Mzamani Primary | N/A | Collins Chabane | Final Completion | Active - Contracted | 2014-02-25 | 2014-04-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 2832000 | 11328000 | 14160000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3100 | EDDP184/163 | Limpopo | MBHURENI PRIMARY SCHOOL | 916410621 | Greater Giyani | Final Completion | Active - Contracted | 2014-01-27 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1538000 | 6153000 | 7691000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3117 | EDDP184/154 | Limpopo | MATTHEW PHOSA SECONDARY SCHOOL | 992201304 | Blouberg | Practical Completion (100%) | Active - Contracted | 2014-01-25 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 8754000 | 35014000 | 43768000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3123 | LDPW-B/10088 | Limpopo | MATSIABABA HIGH | 921110587 | Lephalale | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 1489000 | 5955000 | 7444000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3179 | LDPW-B/10075 | Limpopo | MASEALELE PRIMARY | 920210852 | Blouberg | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 1901000 | 7603000 | 9504000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3188 | LDPW-B/10052 | Limpopo | MARUDE SECONDARY (AT VECO COLLEGE) | 905332030 | Thulamela | Terminated | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1729000 | 6918000 | 8647000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3192 | LE19TMT17110 | Limpopo | Marken Primary School | 906111740 | Mogalakwena | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 580878 | 3611344 | 4192222 | Education Infrastructure Grant | Upgrading and Additions
|  | 3246 | LDPW-B/10073 | Limpopo | MANAMELA PRIMARY | 922220637 | Polokwane | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1272000 | 5090000 | 6362000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3256 | EDDP184/255 | Limpopo | MAMOSHIA PRIMARY SCHOOL | 920210739 | Blouberg | Final Completion | Active - Contracted | 2019-06-30 | 2019-08-30 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 708000 | 2834000 | 3542000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3264 | EDDP184/76 | Limpopo | MAMAILA PRIMARY | 919340289 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2015-04-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2749800 | 10999200 | 13749000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3267 | LDPW-B/10076 | Limpopo | Mamabolo Primary - construction | 923240532 | Polokwane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 1601000 | 6403000 | 8004000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3273 | EDDP184/372 | Limpopo | MALOPE PRIMARY | 924641074 | Makhuduthamaga | Construction 26% - 50% | Proposed | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 1769000 | 7077000 | 8846000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3289 | LDPW-B/10077 | Limpopo | MAKOTOPONG PRIMARY | 923240495 | Polokwane | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1892000 | 7568000 | 9460000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3291 | LDPW-B/10064 | Limpopo | MAKOPI SECONDARY | 925631091 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Proposed | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2838000 | 11352000 | 14190000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3300 | EDDP184/394A | Limpopo | MAKHANYA SECONDARY | 915530167 | Greater Tzaneen | Construction 76% - 99% | Active - Contracted | 2013-10-25 | 2013-10-26 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1198000 | 4792000 | 5990000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3323 | EDDP184/232 | Limpopo | MAHWAHWA SECONDARY | 915530150 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2022-04-01 | 2022-07-30 | 2026-03-31 | 2026-04-30 | 2026-05-30 | 9038609 | 36154434 | 45193043 | Education Infrastructure Grant | Maintenance and Repairs
|  | 3326 | EDDP182/1892 | Limpopo | Mahlasedi primary(new site) | 923260505 | Modimolle/Mookgophong | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-06-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 957000 | 3828000 | 4785000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3339 | EDDP184/230 | Limpopo | MAGOZA HIGH | 915530143 | Greater Tzaneen | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 5988000 | 23951000 | 29939000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3359 | EDDP184/395 | Limpopo | MAALOBANA HIGH | N/A | Maruleng | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3382 | LDPW-B/12031 | Limpopo | LEMANA SECONDARY AT LEMANA COLLEGE | 912111542 | Makhado | Terminated | Active - Contracted | 2013-04-01 | 2013-08-15 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 12206000 | 48824000 | 61030000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3387 | EDDP184/58 | Limpopo | LEHWELERE PRIMARY SCHOOL | 996606606 | Elias Motsoaledi | Final Completion | Active - Contracted | 2014-03-11 | 2014-04-20 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 2292000 | 9167000 | 11459000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3398 | EDDP184/55 | Limpopo | LAERSKOOL KOEDOESKOP | 909130536 | Thabazimbi | Construction 76% - 99% | Proposed | 2014-02-06 | 2014-02-07 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 2744000 | 10976000 | 13720000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3399 | EDDP182/1891 | Limpopo | LAERSKOOL ALMA | 907130505 | Modimolle/Mookgophong | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 879000 | 3518000 | 4397000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3405 | LDPW-B/10065 | Limpopo | Kulani Primary (Groot Letaba in Mopani - relocated from Makgamathu Secondary) | 925631084 | Collins Chabane | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-07-30 | 2024-07-31 | 2021-07-31 | 1621000 | 6486000 | 8107000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3414 | EDDP184/258 | Limpopo | KOBE PRIMARY | 920210364 | Blouberg | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-03-30 | 2024-03-30 | 6959000 | 27834000 | 34793000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3419 | EDDP184/220 | Limpopo | KHUTJANG PRIMARY SCHOOL | 991102200 | Mogalakwena | Final Completion | Active - Contracted | 2013-04-01 | 2013-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 172500000 | 750000000 | 922500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3420 | EDDP184/249 | Limpopo | KHUNWANA PRIMARY | 919340807 | Molemole | Final Completion | Active - Contracted | 2014-04-01 | 2017-04-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2703000 | 10814000 | 13517000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3422 | EDDP184/396B | Limpopo | KHUDU HIGH | 926540072 | Maruleng | Practical Completion (100%) | Active - Contracted | 2013-04-01 | 2013-04-02 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 1458000 | 5832000 | 7290000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3423 | EDDP184/396C | Limpopo | KHUDU HIGH | 926540072 | Maruleng | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1404000 | 5616000 | 7020000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3431 | EDDP184/374 | Limpopo | KGWEKGWE SECONDARY | 918510125 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2017-04-01 | 2024-05-30 | 2024-05-30 | 2024-06-30 | 1643000 | 6570000 | 8213000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3443 | LDPW-B/10060 | Limpopo | KGATI YA MOSHATE SEC | 921120478 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 1629000 | 6517000 | 8146000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3445 | EDDP182/145K | Limpopo | KGALADI/SEKWATI PRIMARY (Merging schools) | 924640385 | Makhuduthamaga | Construction 51% - 75% | Active - Contracted | 2016-06-10 | 2016-06-15 | 2024-06-30 | 2024-03-31 | 2024-06-30 | 3184000 | 12736000 | 15920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3473 | EDDP184/181 | Limpopo | ITIRELE SECONDARY | 991104401 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2014-03-27 | 2014-04-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 3220000 | 12879000 | 16099000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3501 | EDDP184/235 | Limpopo | GRAIGEHEAD PRIMARY | 901540546 | Greater Tzaneen | Final Completion | Active - Contracted | 2014-04-01 | 2017-04-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 3509000 | 14035000 | 17544000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3509 | EDDP184/37 | Limpopo | GAWULA SECONDARY | 916410133 | Greater Giyani | Construction 51% - 75% | Active - Contracted | 2014-01-27 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 3098000 | 12394000 | 15492000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3534 | EDDP184/229 | Limpopo | DZJ MTEBULE SECONDARY | 915530075 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2019-03-31 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 3000000 | 12000000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3539 | EDDP184/169 | Limpopo | DUDUDU PRIMARY | 915530457 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-02-25 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 3248212 | 12992847 | 16241059 | Education Infrastructure Grant | Upgrading and Additions
|  | 3547 | EDDP182/52 | Limpopo | District/circuit Office - Tshipise | LP08000 | Musina | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 15497000 | 61987000 | 77484000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3548 | EDDP182/39 | Limpopo | CIRCUIT OFFICE - MAPELA | 11022 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2017-12-31 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 8757000 | 35026000 | 43783000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3557 | LDPW-B/12050 | Limpopo | DINAO SECONDARY | 923260130 | Lepele-Nkumpi | Practical Completion (100%) | Approved | 2014-04-01 | 2017-04-02 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 1435137 | 5740550 | 7175687 | Education Infrastructure Grant | Upgrading and Additions
|  | 3565 | EDDP184/206 | Limpopo | DENGA TSHIVHASE SECONDARY | 930351364 | Thulamela | Final Completion | Active - Contracted | 2014-02-05 | 2014-04-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 3361000 | 13445000 | 16806000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3574 | EDDP182/37 | Limpopo | Circuit Office - Moutse | N/A | Bela-Bela | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 6451000 | 25805000 | 32256000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3584 | EDDP184/377 | Limpopo | CHARLES MATHONSI HIGH | 915530068 | Greater Tzaneen | Final Completion | Active - Contracted | 2013-10-25 | 2013-10-26 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 1744000 | 6974000 | 8718000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 3595 | EDDP184/155 | Limpopo | BORWALATHOTO PRIMARY | 920210074 | Blouberg | On Hold | Active - Contracted | 2014-04-01 | 2021-04-06 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1753000 | 7012000 | 8765000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3599 | EDDP182/49 | Limpopo | Bochum circuit Office | N/A | Polokwane | Construction 51% - 75% | Active - Not Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2023-12-31 | 2024-03-31 | 6715000 | 26860000 | 33575000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 3725 | LE20IDT09002 | Limpopo | Dibeng Primary School | 922250171 | Polokwane | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-30 |  |  | 2496000 | 9984000 | 12480000 | Education Infrastructure Grant | Upgrading and Additions
|  | 3778 | EDDP184/179 | Limpopo | ITSOSENG PRIMARY SCHOOL | 925621247 | Greater Tubatse/Fetakgomo | Construction 1% - 25% | Proposed | 2014-01-28 | 2016-04-20 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1084000 | 4335000 | 5419000 | Education Infrastructure Grant | Upgrading and Additions
|  | 4046 | HS/SGB/2009 | Western Cape | BHEKINKOSI SP (RETENDER) | 500108780 | City of Cape Town | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 |  | 2027-03-31 |  |  | 107376000 | 447817000 | 555193000 | Equitable Share | Upgrading and Additions
|  | 4049 | DTPW02/2010 | Western Cape | BHOBHOBHO P | 500327450 | City of Cape Town | Other - Packaged Ongoing Project | Active - Not Contracted | 2017-04-03 |  | 2025-03-31 |  |  | 46117000 | 290761000 | 336878000 | Education Infrastructure Grant | Upgrading and Additions
|  | 4066 | DTPW35/2011 | Western Cape | DUMAKUDE P | 500124061 | City of Cape Town | Feasibility | Active - Not Contracted | 2014-05-01 |  | 2026-03-31 |  |  | 12500000 | 57000000 | 69500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4076 | DTPW04/2012 | Western Cape | Concordia PS | 100000267 | Knysna | Construction 1% - 25% | Active - Contracted | 2014-01-01 | 2022-04-19 | 2025-03-31 | 2024-03-29 | 2024-01-31 | 17703000 | 78000000 | 95703000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4119 | DTPW031/2012 | Western Cape | HLABA P (RETENDER) | 500155844 | City of Cape Town | Other - Compensation of Employees | Active - Contracted | 2012-11-01 | 2016-04-01 | 2027-03-31 | 2021-03-31 | 2024-03-29 | 206224000 | 33457000 | 239681000 | Education Infrastructure Grant | Non-Infrastructure
|  | 4127 | DTPW002/2014 | Western Cape | Umyezo Wama Apile PS | 500447885 | Theewaterskloof | Construction 76% - 99% | Active - Contracted | 2015-01-01 | 2019-05-29 | 2023-03-31 | 2020-09-15 | 2022-12-30 | 16794000 | 61282000 | 78076000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4132 | DTPW007/2014 | Western Cape | Panorama PS N2 | 500166944 | Saldanha Bay | Construction 51% - 75% | Active - Contracted | 2015-03-02 | 2019-04-03 | 2024-03-29 | 2020-05-15 | 2023-09-29 | 18454000 | 55807000 | 74261000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4133 | DTPW008/2014 | Western Cape | Sir Lowry`s Pass SS | 500167536 | City of Cape Town | Construction 26% - 50% | Active - Contracted | 2017-04-03 | 2021-11-15 | 2025-03-28 | 2023-12-01 | 2023-09-13 | 15086000 | 58000000 | 73086000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4134 | DTPW009/2014 | Western Cape | Sunray PS | 500167610 | City of Cape Town | Construction 76% - 99% | Active - Contracted | 2016-07-28 | 2018-07-04 | 2024-03-31 | 2019-11-18 | 2022-11-30 | 20387000 | 75511000 | 95898000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4140 | DTPW015/2014 | Western Cape | JIRAH P ( PHASE 3) | 500425870 | City of Cape Town | Other - Packaged Ongoing Project | Active - Contracted | 2014-02-03 |  | 2026-03-31 |  |  | 12125000 | 57129000 | 69254000 | Equitable Share | Upgrading and Additions
|  | 4141 | DTPW016/2014 | Western Cape | JOJOSINI P | 500171532 | City of Cape Town | Other - Packaged Ongoing Project | Active - Contracted | 2014-02-01 |  | 2027-03-31 |  |  | 60628000 | 409529000 | 470157000 | Equitable Share | Upgrading and Additions
|  | 4143 | DTPW019/2014 | Western Cape | KANGIKHO P | 500172346 | City of Cape Town | Other - Packaged Ongoing Project | Active - Contracted | 2013-02-01 |  | 2023-03-31 |  |  | 0 | 20351000 | 20351000 | Equitable Share | Maintenance and Repairs
|  | 4171 | DTPW050/2014 | Western Cape | Waveren SS | 500319606 | Witzenberg | Construction 1% - 25% | Active - Contracted | 2015-11-02 | 2022-02-17 | 2025-03-31 | 2023-06-15 | 2023-07-14 | 12114000 | 48000000 | 60114000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4178 | DTPW060/2014 | Western Cape | Moorreesburg HS | 500194435 | Swartland | Construction 76% - 99% | Active - Contracted | 2016-03-01 | 2021-01-08 | 2023-03-31 | 2022-01-14 | 2022-10-06 | 12530000 | 41468000 | 53998000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4183 | DTPW073/2014 | Western Cape | Dal Josaphat PS | 500146964 | Drakenstein | Construction 1% - 25% | Active - Contracted | 2015-01-01 | 2022-02-21 | 2025-03-31 | 2024-02-15 | 2024-09-13 | 17837000 | 73000000 | 90837000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4187 | DTPW078/2014 | Western Cape | Jagtershof SS | 500201317 | City of Cape Town | Feasibility | Active - Not Contracted | 2020-04-30 |  | 2026-03-31 |  |  | 13500000 | 65000000 | 78500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4188 | DTPW079/2014 | Western Cape | Klapmuts HS | 500202464 | Stellenbosch | Feasibility | Proposed | 2020-04-01 |  | 2026-03-31 |  |  | 11500000 | 52000000 | 63500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4217 | DTPW013/2015 | Western Cape | Macassar PS No.2 | 500303437 | City of Cape Town | Construction 1% - 25% | Active - Contracted | 2017-04-03 | 2022-01-21 | 2025-03-31 | 2024-01-15 | 2024-05-07 | 17572000 | 71000000 | 88572000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4226 | WE/000820/2019 | Western Cape | Sonderend PS | 500229585 | City of Cape Town | Feasibility | Active - Not Contracted | 2017-10-31 |  | 2026-03-31 |  |  | 12352000 | 65000000 | 77352000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 4229 | DTPW025/2015 | Western Cape | Sunnyside PS | 500230732 | City of Cape Town | Design | Active - Not Contracted | 2018-04-02 |  | 2026-03-31 |  |  | 13250000 | 65000000 | 78250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 8167 | P0003817 | Eastern Cape | EYABANTU SENIOR SECONDARY SCHOOL | 200100214 | Raymond Mhlaba | Construction 26% - 50% | Active - Contracted | 2018-01-19 | 2018-03-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 6787128 | 39104702 | 45891830 | Education Infrastructure Grant | Upgrading and Additions
|  | 8168 | P9005744 | Eastern Cape | GWEBITYALA SENIOR SECONDARY SCHOOL | 200400250 | Mbhashe | Construction 76% - 99% | Active - Contracted | 2015-03-31 | 2019-04-17 | 2024-03-31 | 2024-03-31 | 2025-03-31 | 4273738 | 11475942 | 15749680 | Education Infrastructure Grant | Upgrading and Additions
|  | 8173 | P0003808 | Eastern Cape | KRAZUKILE HIGH SCHOOL | 200300189 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2017-07-31 | 2025-03-31 | 2026-03-31 | 2027-03-31 | 6912455 | 37909439 | 44821894 | Education Infrastructure Grant | Upgrading and Additions
|  | 8174 | P9005986 | Eastern Cape | MPOZOLO SENIOR SECONDARY SCHOOL | 200300780 | Mbhashe | Construction 26% - 50% | Active - Contracted | 2015-03-20 | 2019-04-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 7642984 | 43320000 | 50962984 | Education Infrastructure Grant | Upgrading and Additions
|  | 8176 | P9011541 | Eastern Cape | SAKHIKAMVA HIGH SCHOOL | 200201033 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 0 | 7794161 | 7794161 | Education Infrastructure Grant | Upgrading and Additions
|  | 8177 | P0003848 | Eastern Cape | TONGANI JUNIOR SECONDARY SCHOOL | 200401061 | Mbhashe | Construction 26% - 50% | Active - Contracted | 2018-04-01 | 2018-05-21 | 2026-03-31 | 2024-03-31 | 2026-03-31 | 6734442 | 45581732 | 52316174 | Education Infrastructure Grant | Upgrading and Additions
|  | 8178 | P0001998 | Eastern Cape | TYALI HIGH SCHOOL | 200300614 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-09-24 | 2026-05-31 | 2026-08-23 | 2027-03-31 | 9667162 | 66678083 | 76345245 | Education Infrastructure Grant | Upgrading and Additions
|  | 8182 | P0003717_ | Eastern Cape | ADELAIDE JUNIOR SECONDARY SCHOOL | 200100014 | Raymond Mhlaba | Construction 26% - 50% | Active - Contracted | 2015-04-01 | 2015-05-10 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 10832770 | 23844237 | 34677007 | Education Infrastructure Grant | Upgrading and Additions
|  | 8185 | P0004317 | Eastern Cape | JAMES NDULULA PRIMARY SCHOOL | 200100348 | Nelson Mandela Bay | Project Initiation | Potential | 2017-01-31 |  | 2026-03-31 |  |  | 5483295 | 42898422 | 48381717 | Education Infrastructure Grant | Upgrading and Additions
|  | 8188 | P0000074 | Eastern Cape | RIETBERG PRIMARY SCHOOL | 200100652 | Sundays River Valley | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2019-04-03 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 3528083 | 5043499 | 8571582 | Education Infrastructure Grant | Upgrading and Additions
|  | 8189 | P0003866 | Eastern Cape | ALICE PRIMARY SCHOOL | 200200006 | Raymond Mhlaba | Final Completion | Active - Contracted | 2017-07-12 | 2017-09-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 10431523 | 10431523 | Education Infrastructure Grant | Upgrading and Additions
|  | 8190 | P0002481 | Eastern Cape | ALICE JUNIOR SECONDARY SCHOOL | 200200007 | Raymond Mhlaba | Construction 51% - 75% | Active - Contracted | 2015-03-20 | 2016-04-16 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2100209 | 5912794 | 8013003 | Education Infrastructure Grant | Upgrading and Additions
|  | 8191 | P0000075 | Eastern Cape | ARCADIA PRIMARY SCHOOL | 200100036 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2019-04-10 | 2026-03-30 | 2024-03-30 | 2024-03-30 | 0 | 20507354 | 20507354 | Education Infrastructure Grant | Upgrading and Additions
|  | 8192 | P0002230 | Eastern Cape | BETHVALE PRIMARY SCHOOL | 200100066 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 16893982 | 16893982 | Education Infrastructure Grant | Upgrading and Additions
|  | 8194 | P9004887 | Eastern Cape | C M VELLEM JUNIOR SECONDARY SCHOOL | 200100100 | Makana | Tender | Active - Not Contracted | 2015-03-20 |  | 2024-03-31 |  |  | 0 | 14718097 | 14718097 | Education Infrastructure Grant | Upgrading and Additions
|  | 8196 | P9005037 | Eastern Cape | CEDARBERG PRIMARY SCHOOL | 200100110 | Nelson Mandela Bay | Construction 1% - 25% | Active - Contracted | 2015-03-20 | 2017-09-15 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 1675388 | 1675388 | Education Infrastructure Grant | Upgrading and Additions
|  | 8198 | P9004964_ | Eastern Cape | E MACEMBE JUNIOR PRIMARY SCHOOL | 200600150 | Inxuba Yethemba | Design | Active - Not Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 0 | 2114983 | 2114983 | Education Infrastructure Grant | Upgrading and Additions
|  | 8204 | P0004116 | Eastern Cape | GRAAFF-REINET PRIMARY SCHOOL | 200100268 | Dr Beyers Naude | Design | Active - Contracted | 2017-11-01 |  | 2025-03-31 |  |  | 0 | 10644479 | 10644479 | Education Infrastructure Grant | Upgrading and Additions
|  | 8206 | P0000071 | Eastern Cape | IBIKA JUNIOR SECONDARY SCHOOL | 200300141 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-07-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2465410 | 6412104 | 8877514 | Education Infrastructure Grant | Upgrading and Additions
|  | 8208 | P0002227 | Eastern Cape | KENTANI JUNIOR SECONDARY SCHOOL | 200300045 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-08-07 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2154035 | 5545631 | 7699666 | Education Infrastructure Grant | Upgrading and Additions
|  | 8209 | P9005556 | Eastern Cape | KROONVALE PRIMARY SCHOOL | 200100413 | Dr Beyers Naude | Design | Active - Contracted | 2015-03-20 |  | 2026-03-31 |  |  | 0 | 11817851 | 11817851 | Education Infrastructure Grant | Upgrading and Additions
|  | 8211 | P0004219 | Eastern Cape | LOUTERWATER JUNIOR SECONDARY SCHOOL | 200100464 | Kou-Kamma | Practical Completion (100%) | Active - Contracted | 2017-07-31 | 2017-09-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4737687 | 10073126 | 14810813 | Education Infrastructure Grant | Upgrading and Additions
|  | 8213 | P9005091 | Eastern Cape | N V CEWU PUBLIC PRIMARY SCHOOL | 200100548 | Makana | Construction 51% - 75% | Active - Contracted | 2015-03-31 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 11045822 | 11045822 | Education Infrastructure Grant | Upgrading and Additions
|  | 8216 | P0001999 | Eastern Cape | PEFFERVILLE PRIMARY SCHOOL | 200200677 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2015-03-31 | 2019-04-03 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 1538857 | 8374828 | 9913685 | Education Infrastructure Grant | Upgrading and Additions
|  | 8217 | P0002218_ | Eastern Cape | SAMUEL NTLEBI PRIMARY SCHOOL | 200100676 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2015-05-10 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 3132443 | 7692171 | 10824614 | Education Infrastructure Grant | Upgrading and Additions
|  | 8219 | P0002572 | Eastern Cape | ZANOKHANYO JUNIOR SECONDARY SCHOOL | 200300680 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-07-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3053600 | 7684665 | 10738265 | Education Infrastructure Grant | Upgrading and Additions
|  | 8234 | P0002200 | Eastern Cape | A B SIWENDU SENIOR PRIMARY SCHOOL | 200300001 | Mbhashe | Design | Active - Contracted | 2015-03-20 |  | 2026-03-31 |  |  | 2099051 | 4686175 | 6785226 | Education Infrastructure Grant | Upgrading and Additions
|  | 8236 | P0000095 | Eastern Cape | CEBE JUNIOR SECONDARY SCHOOL | 200300043 | Mnquma | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2017-11-11 | 2026-10-31 | 2025-10-31 | 2026-10-31 | 8562678 | 49726432 | 58289110 | Education Infrastructure Grant | Upgrading and Additions
|  | 8237 | P9005982 | Eastern Cape | DALASILE PRIMARY SCHOOL | 200600125 | Enoch Mgijima | Construction 26% - 50% | Active - Contracted | 2015-03-20 | 2019-04-17 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 0 | 42506142 | 42506142 | Education Infrastructure Grant | Upgrading and Additions
|  | 8241 | P0003480 | Eastern Cape | MFIKI PRIMARY SCHOOL | 200200466 | Raymond Mhlaba | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2016-08-03 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 6363553 | 29725324 | 36088877 | Education Infrastructure Grant | Upgrading and Additions
|  | 8244 | P0002970_ | Eastern Cape | NONINZI LUZIPHO PRIMARY SCHOOL | 200101025 | Nelson Mandela Bay | Practical Completion (100%) | Active - Contracted | 2011-04-28 | 2016-03-16 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 939453 | 939453 | Education Infrastructure Grant | Upgrading and Additions
|  | 8245 | P0001705 | Eastern Cape | QAKAZANA JUNIOR SECONDARY SCHOOL | 200300542 | Mbhashe | Design | Approved | 2015-03-20 |  | 2026-03-31 |  |  | 1899010 | 2222416 | 4121426 | Education Infrastructure Grant | Upgrading and Additions
|  | 8246 | P9013234 | Eastern Cape | THORNVALE JUNIOR PRIMARY SCHOOL | 200600839 | Enoch Mgijima | Design | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 8247 | P9006079 | Eastern Cape | VUKILE TSHWETE SECONDARY SCHOOL | 200200885 | Amahlathi | Construction 76% - 99% | Active - Contracted | 2015-03-20 | 2018-03-26 | 2026-03-31 | 2025-09-19 | 2026-03-31 | 8511357 | 47806322 | 56317679 | Education Infrastructure Grant | Upgrading and Additions
|  | 8254 | P0000319_ | Eastern Cape | RUFANE DONKIN PRIMARY SCHOOL | 200100667 | Engcobo | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2015-05-11 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 464356 | 464356 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8258 | P9008593_ | Eastern Cape | NTSESHE JUNIOR SECONDARY SCHOOL | 200300515 | Mnquma | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-06-22 | 2023-03-12 | 2024-03-11 | 2025-03-22 | 0 | 461167 | 461167 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8273 | P0001613_ | Eastern Cape | TEMBANI SENIOR PRIMARY SCHOOL | 200600822 | Mnquma | Practical Completion (100%) | Active - Contracted | 2012-04-01 | 2015-06-22 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 555000 | 4384519 | 4939519 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8278 | P0002048 | Eastern Cape | BETHELSDORP ROAD PRIMARY SCHOOL | 200100065 | Nelson Mandela Bay | Design | Active - Not Contracted | 2015-03-31 |  | 2026-03-31 |  |  | 0 | 54239459 | 54239459 | Education Infrastructure Grant | Upgrading and Additions
|  | 8279 | P0003638 | Eastern Cape | BOOYSEN PARK SECONDARY SCHOOL (PHASE II) | 200100079 | Nelson Mandela Bay | Tender | Active - Not Contracted | 2015-03-20 |  | 2026-03-31 |  |  | 0 | 60509693 | 60509693 | Education Infrastructure Grant | Upgrading and Additions
|  | 8281 | P9004884 | Eastern Cape | HENDRIK KANISE COMBINED SCHOOL | 200100300 | Dr Beyers Naude | Tender | Active - Not Contracted | 2015-03-20 |  | 2026-03-31 |  |  | 0 | 54077908 | 54077908 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 8282 | P0004402 | Eastern Cape | INKQUBELA PUBLIC PRIMARY SCHOOL | 200100337 | Nelson Mandela Bay | Construction 26% - 50% | Active - Contracted | 2021-04-01 | 2022-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3989642 | 3989642 | Education Infrastructure Grant | Upgrading and Additions
|  | 8285 | P0004250 | Eastern Cape | MELANI PRIMARY SCHOOL | 200200463 | Raymond Mhlaba | Construction 51% - 75% | Active - Contracted | 2017-09-07 | 2023-11-07 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3972093 | 15767494 | 19739587 | Education Infrastructure Grant | Upgrading and Additions
|  | 8286 | P0001979 | Eastern Cape | MZINGISI JUNIOR PRIMARY SCHOOL | 200200524 | Buffalo City | Feasibility | Active - Contracted | 2015-03-20 |  | 2026-03-31 |  |  | 0 | 55932531 | 55932531 | Education Infrastructure Grant | Upgrading and Additions
|  | 8287 | P0000503 | Eastern Cape | NKULULEKO PUBLIC SECONDARY SCHOOL | 200100572 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2015-03-20 | 2017-08-12 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 0 | 68937719 | 68937719 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 8289 | P9005216_ | Eastern Cape | ARTHUR MFEBE SENIOR SECONDARY SCHOOL | 200601046 | Intsika Yethu | Practical Completion (100%) | Proposed | 2014-10-16 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 75000 | 1126327 | 1201327 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8294 | P9005260_ | Eastern Cape | DALIWONGA SENIOR SECONDARY SCHOOL | 200601092 | Intsika Yethu | Construction 76% - 99% | Approved | 2014-07-07 | 2015-07-08 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 6719 | 6719 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8317 | P9005236_ | Eastern Cape | LUDIDI SENIOR SECONDARY SCHOOL | 200500449 | Matatiele | Construction 76% - 99% | Active - Contracted | 2011-04-28 | 2016-01-13 | 2026-03-31 | 2018-06-05 | 2024-03-31 | 147442 | 1522555 | 1627817 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8328 | P9005956 | Eastern Cape | MASONWABE PRIMARY SCHOOL | 200400506 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-01-16 | 2018-02-16 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2566723 | 68465 | 2635188 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8368 | P9010526 | Eastern Cape | SANDILE JUNIOR SECONDARY SCHOOL | 200400978 | Engcobo | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2015-05-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3126866 | 3126866 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8397 | P0002051 | Eastern Cape | ENOCH MAMBA SENIOR SECONDARY & TECH INSTITUTION | 200300086 | Mbhashe | Design | Active - Not Contracted | 2017-08-09 |  | 2026-03-31 |  |  | 11511284 | 76741896 | 88253180 | Education Infrastructure Grant | Upgrading and Additions
|  | 8398 | P9006345_ | Eastern Cape | STERKSPRUIT SENIOR SECONDARY SCHOOL | 200600801 | Senqu | Practical Completion (100%) | Active - Not Contracted | 2015-04-01 | 2016-05-10 | 2023-03-31 | 2024-03-31 | 2025-03-31 | 0 | 3726807 | 3555807 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8402 | P9003579 | Eastern Cape | HR Strategy Office Capacitation (S&T) | 200999925 | Buffalo City | Construction 76% - 99% | Approved | 2018-04-01 | 2019-04-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 115543000 | 0 | 115543000 | Education Infrastructure Grant | Non-Infrastructure
|  | 8403 | P9006493_ | Eastern Cape | HR Strategy Office Capacitation (COE) | 200999925 | Buffalo City | Other - Compensation of Employees | Approved | 2017-04-01 | 2017-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 115543000 | 0 | 115543000 | Education Infrastructure Grant | Non-Infrastructure
|  | 8413 | P0002195 | Eastern Cape | ESILINDINI JUNIOR SECONDARY SCHOOL | 200600188 | Senqu | Design | Active - Not Contracted | 2017-05-10 | 2017-07-10 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 534334 | 3575927 | 4110261 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8419 | P0002286 | Eastern Cape | LENGENI JUNIOR SECONDARY SCHOOL | 200300211 | Mnquma | Practical Completion (100%) | Active - Contracted | 2016-09-21 | 2016-11-21 | 2025-03-30 | 2021-12-31 | 2021-01-31 | 720799 | 5766388 | 6487187 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8420 | P0002283 | Eastern Cape | MAMFENENI PRIMARY JUNIOR SCHOOL | 200300276 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2017-05-04 | 2017-11-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 444848 | 3558781 | 4003629 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8422 | P0002275 | Eastern Cape | MQANDULI VILLAGE JUNIOR SECONDARY SCHOOL | 200600479 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2015-06-15 | 2017-05-10 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 721105 | 4524245 | 5245350 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8423 | P0002276 | Eastern Cape | MOUNT AYLIFF JUNIOR SECONDARY SCHOOL | 200501391 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2017-05-11 | 2017-05-15 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 465346 | 3114241 | 3579587 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8424 | P0002279 | Eastern Cape | NDLOVAYIPHATHWA SENIOR PRIMARY SCHOOL | 200400723 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2017-05-11 | 2017-07-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 377406 | 3019245 | 3396651 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8426 | P0002271 | Eastern Cape | NTIBANE JUNIOR SECONDARY SCHOOL | 200400857 | Mhlontlo | Final Completion | Active - Contracted | 2017-04-01 | 2017-07-31 | 2024-03-31 | 2019-06-10 | 2023-03-31 | 749253 | 4725996 | 5475249 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8431 | P9005306 | Eastern Cape | HILLBROW SENIOR SECONDARY SCHOOL | 200500293 | Ingquza Hill | Design | Active - Not Contracted | 2018-09-07 |  | 2026-03-31 |  |  | 0 | 269105508 | 269105508 | Education Infrastructure Grant | Upgrading and Additions
|  | 8445 | P9007205 | Eastern Cape | CHRIS HANI PUBLIC PRIMARY SCHOOL | 200600102 | Emalahleni | Feasibility | Active - Not Contracted | 2016-04-01 |  | 2025-03-04 |  |  | 0 | 119595374 | 119595374 | Education Infrastructure Grant | Upgrading and Additions
|  | 8455 | P9006952_ | Eastern Cape | MHLOTSHENI PRIMARY SCHOOL | 200500679 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3303566 | 29210 | 3332776 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8459 | P9009656_ | Eastern Cape | SOUTHBOURNE PREPARATORY SCHOOL | 200600967 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2018-04-02 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 4595511 | 4595511 | Education Infrastructure Grant | Upgrading and Additions
|  | 8460 | P9008282 | Eastern Cape | ZANESIZWE JUNIOR SECONDARY SCHOOL | 200200926 | Intsika Yethu | Construction 76% - 99% | Active - Contracted | 2018-02-08 | 2020-03-09 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 2537146 | 2537146 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8461 | P0001855 | Eastern Cape | AGENT FEES (CDC) | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2022-08-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 802975577 | 0 | 802975577 | Education Infrastructure Grant | Non-Infrastructure
|  | 8462 | P0001856 | Eastern Cape | AGENT FEES (IDT) | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2022-08-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 427913771 | 0 | 427913771 | Education Infrastructure Grant | Non-Infrastructure
|  | 8469 | P9011620 | Eastern Cape | FREEMANTLE AGRICULTURAL SCHOOL - Sanitation | 200600204 | Emalahleni | Design | Active - Contracted | 2016-02-04 |  | 2026-03-31 |  |  | 0 | 5846126 | 5846126 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8472 | P9006093 | Eastern Cape | MOUNT ARTHUR GIRLS HIGH SCHOOL (New Hostel) | 200601142 | Emalahleni | Design | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 12548998 | 119514262 | 132063260 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 8478 | P9006645 | Eastern Cape | A W BARNES PRIMARY SCHOOL | 200200003 | Buffalo City | Design | Active - Not Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 0 | 9734191 | 9734191 | Education Infrastructure Grant | Upgrading and Additions
|  | 8491 | P9006366_ | Eastern Cape | ARCADIA PRIMARY SCHOOL | 200100036 | Nelson Mandela Bay | Feasibility | Approved | 2016-04-28 |  | 2024-03-31 |  |  | 0 | 3833154 | 3833154 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 8494 | P9007276 | Eastern Cape | AUCKLAND PRIMARY SCHOOL | 200200025 | Raymond Mhlaba | Practical Completion (100%) | Active - Not Contracted | 2017-01-20 | 2017-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1617883 | 0 | 1617883 | Education Infrastructure Grant | Upgrading and Additions
|  | 8496 | P9006650_ | Eastern Cape | AYLIFF PRIMARY SCHOOL | 200200027 | Ngqushwa | Practical Completion (100%) | Proposed | 2016-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 313318 | 313318 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8503 | P9006643 | Eastern Cape | BASHEE COMPREHENSIVE HIGH SCHOOL | 200300011 | Mbhashe | Feasibility | Active - Contracted | 2016-04-01 |  | 2025-03-24 |  |  | 7413041 | 60233489 | 67646530 | Education Infrastructure Grant | Upgrading and Additions
|  | 8506 | P9005973_ | Eastern Cape | BEKABANTU JUNIOR SECONDARY SCHOOL | 200400029 | Port St Johns | Construction 76% - 99% | Approved | 2017-04-03 | 2018-04-12 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 87158 | 571371 | 658529 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8511 | P9005812 | Eastern Cape | BETHESDA PRIMARY SCHOOL | 200500031 | Matatiele | Construction 26% - 50% | Active - Contracted | 2017-10-25 | 2017-12-25 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 2269979 | 9587443 | 11857422 | Education Infrastructure Grant | Upgrading and Additions
|  | 8543 | P0003489_ | Eastern Cape | CABAZANA JUNIOR SECONDARY SCHOOL | 200500076 | Umzimvubu | Tender | Active - Not Contracted | 2018-09-21 | 2018-11-09 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1890955 | 19424373 | 21315328 | Education Infrastructure Grant | Upgrading and Additions
|  | 8546 | P9006496 | Eastern Cape | CALA VILLAGE JUNIOR SECONDARY SCHOOL | 200600089 | Sakhisizwe | Design | Active - Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 2683792 | 0 | 2683792 | Education Infrastructure Grant | Upgrading and Additions
|  | 8553 | P9007899_ | Eastern Cape | CHARLES DUNA PUBLIC SCHOOL | 200100112 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2016-01-28 | 2016-04-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 264510 | 2547697 | 2812207 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 8562 | P9007203 | Eastern Cape | COBOSI PRIMARY JUNIOR SCHOOL | 200400085 | Engcobo | Design | Active - Contracted | 2016-04-01 |  | 2025-03-31 |  |  | 0 | 16959170 | 16959170 | Education Infrastructure Grant | Upgrading and Additions
|  | 8576 | P9006656_ | Eastern Cape | DALIBANGO PRIMARY SCHOOL | 200300056 | Mnquma | Construction 51% - 75% | Active - Not Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 293283 | 293283 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8596 | P9008628_ | Eastern Cape | DUNGU JUNIOR SECONDARY SCHOOL | 200500152 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1778445 | 1778445 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8623 | P9007204 | Eastern Cape | ENDUKU PRIMARY JUNIOR SCHOOL | 200400166 | Engcobo | Tender | Active - Contracted | 2016-04-01 |  | 2025-03-31 |  |  | 0 | 5854995 | 5854995 | Education Infrastructure Grant | Upgrading and Additions
|  | 8639 | P9008587 | Eastern Cape | FALAKAHLA JUNIOR SECONDARY SCHOOL | 200300095 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2017-03-20 | 2017-05-20 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 7870712 | 7870712 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8647 | P9003543_ | Eastern Cape | FlORADALE FARM SCHOOL | 200200182 | Buffalo City | Design | Active - Not Contracted | 2019-02-01 |  | 2025-03-31 |  |  | 0 | 21991388 | 21991388 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 8650 | P0000077 | Eastern Cape | FORT GREY PUBLIC SCHOOL | 200200184 | Buffalo City | Design | Active - Not Contracted | 2017-11-30 |  | 2024-03-31 |  |  | 0 | 7006213 | 7006213 | Education Infrastructure Grant | Upgrading and Additions
|  | 8659 | P9013217_ | Eastern Cape | GCINUBUZWE COMBINED SCHOOL | 200100240 | Dr Beyers Naude | Project Initiation | Proposed | 2016-04-01 |  | 2024-03-31 |  |  | 0 | 6982000 | 6982000 | Education Infrastructure Grant | Upgrading and Additions
|  | 8664 | P9006727_ | Eastern Cape | GCUMA SENIOR PRIMARY SCHOOL | 200500248 | Ingquza Hill | Practical Completion (100%) | Active - Contracted | 2022-04-01 | 2022-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 192507 | 192507 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8680 | P9008618_ | Eastern Cape | GOBIZIZWE SENIOR PRIMARY SCHOOL | 200400215 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-07-18 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 462931 | 2501384 | 2964315 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8699 | P9006736_ | Eastern Cape | HAMBURG PRIMARY SCHOOL - Water | 200200235 | Ngqushwa | Practical Completion (100%) | Active - Not Contracted | 2015-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 605065 | 605065 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8727 | P9006800_ | Eastern Cape | IZIBANZINI JUNIOR SECONDARY SCHOOL | 200500327 | Mbizana | Site Handed - Over to Contractor | Active - Contracted | 2020-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 210024 | 210024 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8728 | P9008566_ | Eastern Cape | JERSEY FARM JUNIOR SECONDARY SCHOOL | 200400284 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 112021 | 618949 | 730970 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8730 | P9011544 | Eastern Cape | JOE SLOVO PRIMARY SCHOOL | 200101026 | Nelson Mandela Bay | Design | Active - Not Contracted | 2015-04-01 |  | 2023-06-30 |  |  | 0 | 45310 | 45310 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 8732 | P9006742_ | Eastern Cape | JONGILE NOMPONDO SECONDARY SCHOOL | 200200295 | Amahlathi | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2017-03-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3349730 | 3349730 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8758 | P9013193 | Eastern Cape | KHAYAKHULU PRIMARY SCHOOL | 200100377 | Sundays River Valley | Practical Completion (100%) | Active - Contracted | 2016-03-17 | 2016-05-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 225297 | 736049 | 961346 | Education Infrastructure Grant | Upgrading and Additions
|  | 8763 | P9006750_ | Eastern Cape | KHONJWAYO SENIOR PRIMARY SCHOOL | 200500358 | Ingquza Hill | Site Handed - Over to Contractor | Proposed | 2017-04-01 | 2018-09-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 364170 | 364170 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8767 | P9013248 | Eastern Cape | KOLISAVILLE JUNIOR SECONDARY SCHOOL | 200500363 | Mhlontlo | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8806 | P9013236 | Eastern Cape | LOWER MDUMBI JUNIOR SECONDARY SCHOOL | 200400380 | Nyandeni | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8815 | P9013216 | Eastern Cape | LUKHOZI HIGH SCHOOL | 200200377 | Raymond Mhlaba | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8816 | P9010523 | Eastern Cape | LUKUNI JUNIOR SECONDARY SCHOOL | 200400402 | Nyandeni | Practical Completion (100%) | Proposed | 2015-04-01 | 2015-05-11 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 2970599 | 2970599 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8823 | P9006480 | Eastern Cape | LUTUTU JUNIOR SECONDARY SCHOOL | 200400421 | Elundini | Final Completion | Active - Contracted | 2018-01-08 | 2019-01-31 | 2026-03-31 | 2026-03-31 | 2026-03-01 | 0 | 4855622 | 4855622 | Education Infrastructure Grant | Upgrading and Additions
|  | 8844 | P9013229 | Eastern Cape | MAGIQWENI PRIMARY SCHOOL | 200300264 | Mnquma | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8880 | P9006631 | Eastern Cape | MASIZAME JUNIOR PRIMARY SCHOOL | 200300292 | Mnquma | Final Completion | Approved | 2017-04-01 | 2019-04-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8079008 | 8079008 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 8891 | P9006769_ | Eastern Cape | MBAYI JUNIOR SECONDARY SCHOOL | 200500614 | Ingquza Hill | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2018-10-23 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 214757 | 73971 | 288728 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8892 | P9013197 | Eastern Cape | MBAYI JUNIOR SECONDARY SCHOOL | 200500614 | Ingquza Hill | Practical Completion (100%) | Proposed | 2018-10-23 | 2018-10-28 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 8910 | P9013218 | Eastern Cape | MDABUKWENI JUNIOR SECONDARY SCHOOL | 200400558 | Mhlontlo | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8914 | P0003562_ | Eastern Cape | MDUMAZULU JUNIOR SECONDARY SCHOOL | 200400571 | Nyandeni | Final Completion | Active - Contracted | 2016-04-01 | 2017-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 332000 | 1160747 | 1492747 | Education Infrastructure Grant | Maintenance and Repairs
|  | 8916 | P9008064_ | Eastern Cape | MEHLOMAKULU SENIOR SECONDARY SCHOOL | 200600476 | Senqu | Pre - Feasibility | Proposed | 2018-02-08 |  | 2026-03-31 |  |  | 10302030 | 0 | 10302030 | Education Infrastructure Grant | Upgrading and Additions
|  | 8924 | P9006632 | Eastern Cape | MGOBOZI SENIOR PRIMARY SCHOOL | 200300327 | Mnquma | Design | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 0 | 8262259 | 8262259 | Education Infrastructure Grant | Upgrading and Additions
|  | 8925 | P9005810 | Eastern Cape | MGOMANZI PRIMARY SCHOOL | 200500666 | Mbizana | Tender | Active - Not Contracted | 2018-01-30 |  | 2026-03-31 |  |  | 0 | 62017203 | 62017203 | Education Infrastructure Grant | Upgrading and Additions
|  | 8963 | P9006635 | Eastern Cape | MQAMBELI JUNIOR SECONDARY SCHOOL | 200300373 | Mnquma | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7034577 | 7034577 | Education Infrastructure Grant | Upgrading and Additions
|  | 8964 | P9005805 | Eastern Cape | MQHOKWENI JUNIOR PRIMARY SCHOOL | 200501448 | Mbizana | Construction 51% - 75% | Active - Contracted | 2017-10-26 | 2017-12-26 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 5561866 | 37469309 | 43031175 | Education Infrastructure Grant | Upgrading and Additions
|  | 8990 | P9006636_ | Eastern Cape | NATHANIEL PAMLA HIGH SCHOOL | 200200539 | Ngqushwa | Feasibility | Active - Not Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 6792454 | 56969307 | 63761761 | Education Infrastructure Grant | Upgrading and Additions
|  | 9012 | P9006784_ | Eastern Cape | NGQANDA JUNIOR SECONDARY SCHOOL | 200300438 | Emalahleni | Final Completion | Proposed | 2018-05-18 | 2019-05-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5000 | 5000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9013 | P9006785_ | Eastern Cape | NGQATYANA JUNIOR SECONDARY SCHOOL | 200400754 | Mbhashe | Final Completion | Proposed | 2018-02-21 | 2022-01-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 137428 | 137428 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9031 | P9008553_ | Eastern Cape | NOJOLI SENIOR PRIMARY SCHOOL | 200100576 | Dr Beyers Naude | Project Initiation | Proposed | 2021-04-01 |  | 2023-12-31 |  |  | 0 | 500 | 500 | Education Infrastructure Grant | Upgrading and Additions
|  | 9039 | P9010921 | Eastern Cape | NOMZAMO JUNIOR SECONDARY SCHOOL | 200400821 | Mhlontlo | Practical Completion (100%) | Proposed | 2015-11-19 | 2015-12-29 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 423165 | 1575374 | 1998539 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9054 | P9010914 | Eastern Cape | NTSHILINI SENIOR SECONDARY SCHOOL | 200401329 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-10 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 140000 | 140000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9057 | P9005268_ | Eastern Cape | NTUKAYI SENIOR SECONDARY SCHOOL | 200500985 | Mbizana | Practical Completion (100%) | Active - Contracted | 2014-02-04 | 2015-05-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 390000 | 5162230 | 5552230 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9062 | P9006790_ | Eastern Cape | NXUKHWEBE HIGHER PRIMARY SCHOOL | 200100601 | Raymond Mhlaba | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2017-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 163842 | 163842 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9075 | P9013279 | Eastern Cape | PHAHAMENG PRIMARY SCHOOL | 200600666 | Walter Sisulu | Construction 76% - 99% | Proposed | 2021-12-01 | 2021-12-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 9083 | P9005804 | Eastern Cape | PROSPECT PRIMARY SCHOOL | 200501034 | Matatiele | Tender | Active - Not Contracted | 2018-09-01 |  | 2026-03-31 |  |  | 10158825 | 57122378 | 67281203 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 9089 | P9008812 | Eastern Cape | QHAYIYA PRIMARY SCHOOL | 200100639 | Ndlambe | Pre - Feasibility | Proposed | 2015-04-01 |  | 2025-03-31 |  |  | 0 | 154879 | 154879 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9094 | P9006343_ | Eastern Cape | QOKOLWENI SENIOR SECONDARY SCHOOL | 200401252 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2016-04-03 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1500000 | 1374600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9099 | P9008817 | Eastern Cape | RHODES JUNIOR SECONDARY SCHOOL | 200600709 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 4515876 | 4515876 | Education Infrastructure Grant | Upgrading and Additions
|  | 9122 | P9006482 | Eastern Cape | SILANGWE SENIOR PRIMARY SCHOOL | 200501108 | Mbizana | Construction 26% - 50% | Active - Contracted | 2017-11-14 | 2019-04-24 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 3548345 | 1372807059 | 1376355404 | Education Infrastructure Grant | Upgrading and Additions
|  | 9124 | P9006639_ | Eastern Cape | SIMZAMILE SENIOR SECONDARY SCHOOL | 200200770 | Buffalo City | Design | Active - Not Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 4919158 | 37361643 | 42280801 | Education Infrastructure Grant | Upgrading and Additions
|  | 9125 | P9010947 | Eastern Cape | SINETHEMBA PUBLIC SCHOOL | 200200773 | Amahlathi | Project Initiation | Proposed | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 542941 | 542941 | Education Infrastructure Grant | Upgrading and Additions
|  | 9155 | P9005806_ | Eastern Cape | STANFORD PRIMARY SCHOOL | 200501168 | Mbizana | Tender | Proposed | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 3030000 | 3030000 | Education Infrastructure Grant | Upgrading and Additions
|  | 9162 | P9008646_ | Eastern Cape | TANTSEKA JUNIOR SECONDARY SCHOOL | 200401331 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2015-03-20 | 2015-05-10 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 411108 | 2731168 | 3142276 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9168 | P0003705 | Eastern Cape | TEMBISA SPECIAL SCHOOL (hostels) | 200401048 | King Sabata Dalindyebo | Construction 51% - 75% | Active - Contracted | 2017-05-19 | 2017-07-31 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 35569109 | 173853041 | 209422150 | Education Infrastructure Grant | Upgrading and Additions
|  | 9173 | P9006987_ | Eastern Cape | THEMBALETHU JUNIOR SECONDARY SCHOOL | 200600832 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 597010 | 2388040 | 2985050 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9194 | P9005259_ | Eastern Cape | TSOMO SENIOR SECONDARY SCHOOL | 200300612 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2014-05-19 | 2015-08-11 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 80000 | 1313085 | 1393085 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9199 | P9005308_ | Eastern Cape | TYELINZIMA JUNIOR SECONDARY SCHOOL | 200401081 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-09-03 | 2024-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 11563394 | 11563394 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9200 | P9006344_ | Eastern Cape | TYUTYU PRIMARY SCHOOL | 200200869 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2017-11-01 |  | 2025-03-31 |  |  | 0 | 3762143 | 3762143 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9221 | P9013421 | Eastern Cape | VELILE SECONDARY SCHOOL | 200100814 | Ndlambe | Project Initiation | Proposed | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 9228 | P9008192_ | Eastern Cape | VUMILE PRIMARY SCHOOL | 200600897 | Walter Sisulu | Design | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 0 | 1424383 | 1424383 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9249 | P9005334_ | Eastern Cape | ZANEWONGA JUNIOR SECONDARY SCHOOL | 200300676 | Mnquma | Construction 76% - 99% | Approved | 2017-04-01 | 2018-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 6435063 | 42040441 | 48475504 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9250 | P9011721_ | Eastern Cape | ZANOKHANYO JUNIOR SECONDARY SCHOOL | 200300680 | Mnquma | Feasibility | Approved | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 9266 | P9005933_ | Eastern Cape | ARTHUR MFEBE SENIOR SECONDARY SCHOOL (Hostels) | 200601046 | Intsika Yethu | Tender | Active - Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 3167441 | 0 | 3167441 | Education Infrastructure Grant | Upgrading and Additions
|  | 9267 | P9006080_ | Eastern Cape | ASHERVILLE PUBLIC SCHOOL | 200100041 | Dr Beyers Naude | Construction 1% - 25% | Active - Contracted | 2018-12-07 | 2019-02-07 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 11871563 | 78013949 | 89867410 | Education Infrastructure Grant | Upgrading and Additions
|  | 9268 | P9005924 | Eastern Cape | BULELANI SENIOR SECONDARY SCHOOL | 200600076 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2017-04-06 | 2017-06-06 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 3772947 | 51354763 | 55127710 | Education Infrastructure Grant | Upgrading and Additions
|  | 9269 | P9005930 | Eastern Cape | JIKINDABA SENIOR SECONDARY SCHOOL | 200500334 | Ingquza Hill | Design | Approved | 2015-04-01 |  | 2025-03-31 |  |  | 2213897 | 0 | 2213897 | Education Infrastructure Grant | Upgrading and Additions
|  | 9270 | P9005992 | Eastern Cape | LAERSKOOL GRENS | 200200004 | Buffalo City | Construction 26% - 50% | Active - Not Contracted | 2013-03-31 | 2018-06-30 | 2026-03-31 | 2021-09-20 | 2024-03-31 | 14654483 | 113189131 | 127843614 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9271 | P9005925 | Eastern Cape | LAVELILANGA SENIOR SECONDARY SCHOOL | 200600886 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2017-11-01 | 2018-01-01 | 2024-03-31 | 2024-03-31 | 2026-02-28 | 2776724 | 25244245 | 28020969 | Education Infrastructure Grant | Upgrading and Additions
|  | 9273 | P9005937 | Eastern Cape | LOWER NGQUNGQU JUNIOR SECONDARY SCHOOL | 200400385 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Not Contracted | 2017-11-01 | 2018-01-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 4561792 | 30270902 | 34832694 | Education Infrastructure Grant | Upgrading and Additions
|  | 9276 | P9005938 | Eastern Cape | MASIZAKHE JUNIOR PRIMARY SCHOOL | 200300291 | Enoch Mgijima | Construction 51% - 75% | Active - Contracted | 2017-11-01 | 2018-01-01 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 6502117 | 50464974 | 56967091 | Education Infrastructure Grant | Upgrading and Additions
|  | 9277 | P9005929 | Eastern Cape | MBUQE EXTENSION SENIOR PRIMARY SCHOOL | 200400546 | King Sabata Dalindyebo | Construction 51% - 75% | Active - Contracted | 2017-11-01 | 2018-01-01 | 2024-03-31 | 2024-03-31 | 2026-03-31 | 5932056 | 63250617 | 69182673 | Education Infrastructure Grant | Upgrading and Additions
|  | 9278 | P9005935 | Eastern Cape | MFESANE SECONDARY SCHOOL | 200100509 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2017-04-01 | 2017-06-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4934260 | 82189503 | 87123763 | Education Infrastructure Grant | Upgrading and Additions
|  | 9279 | P9007244_ | Eastern Cape | MZIMVUBU SECONDARY SCHOOL | 200601139 | Intsika Yethu | Practical Completion (100%) | Approved | 2015-04-01 | 2017-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3077941 | 31403 | 3109344 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9280 | P9005927 | Eastern Cape | NGUBENGCUKA SENIOR SECONDARY SCHOOL | 200600576 | Emalahleni | Construction 76% - 99% | Active - Contracted | 2017-11-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2818806 | 25652807 | 28471613 | Education Infrastructure Grant | Upgrading and Additions
|  | 9281 | P9005923 | Eastern Cape | NKWEZANA PUBLIC SCHOOL | 200200589 | Buffalo City | Construction 1% - 25% | Active - Not Contracted | 2015-11-01 | 2016-01-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 6401850 | 50885050 | 57286900 | Education Infrastructure Grant | Upgrading and Additions
|  | 9282 | P9005942 | Eastern Cape | NTSIZWA SENIOR SECONDARY SCHOOL | 200500984 | Matatiele | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2018-06-30 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 6366028 | 39010083 | 45376111 | Education Infrastructure Grant | Upgrading and Additions
|  | 9311 | P9005953_ | Eastern Cape | EDLELWENI PUBLIC PRIMARY SCHOOL | 200600157 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2015-03-24 | 2019-04-01 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 23651364 | 23651364 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9316 | P9005952_ | Eastern Cape | STERKSPRUIT COMMUNITY SCHOOL | 200600798 | Senqu | Construction 76% - 99% | Active - Contracted | 2015-02-18 | 2016-08-08 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 5300377 | 23045318 | 28345695 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9323 | P0003066 | Eastern Cape | JUBILEE PARK PRIMARY SCHOOL | 200100363 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2018-03-18 | 2018-05-18 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 14016832 | 77013582 | 83609758 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9339 | P9005959 | Eastern Cape | DINIZULU HIGH SCHOOL | 200300836 | Elundini | Construction 76% - 99% | Active - Contracted | 2017-02-18 | 2018-01-01 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 9527629 | 40250560 | 49778189 | Education Infrastructure Grant | Upgrading and Additions
|  | 9340 | P9005962 | Eastern Cape | GRAHAMSTOWN PRIMARY SCHOOL | 200100271 | Makana | Construction 76% - 99% | Active - Contracted | 2015-04-16 | 2018-03-31 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 2785359 | 55726641 | 58512000 | Education Infrastructure Grant | Upgrading and Additions
|  | 9342 | P9006104 | Eastern Cape | MHLONTLO JUNIOR SECONDARY SCHOOL | 200500677 | Elundini | Construction 76% - 99% | Active - Not Contracted | 2015-09-01 | 2018-01-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 6249146 | 27170200 | 33419346 | Education Infrastructure Grant | Upgrading and Additions
|  | 9344 | P9005963_ | Eastern Cape | WILO COMPREHENSIVE SENIOR SECONDARY SCHOOL | 200400313 | King Sabata Dalindyebo | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2017-11-01 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 9035307 | 55890089 | 64925396 | Education Infrastructure Grant | Upgrading and Additions
|  | 9347 | P9005965 | Eastern Cape | ATTWELL MADALA HIGH SCHOOL | 200401228 | King Sabata Dalindyebo | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2018-05-01 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 6888705 | 68770289 | 75658994 | Education Infrastructure Grant | Upgrading and Additions
|  | 9348 | P9005966 | Eastern Cape | BETHELSDORP COMPREHENSIVE SCHOOL | 200100064 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2015-01-29 | 2015-05-01 | 2025-04-01 | 2025-04-01 | 2025-03-31 | 3972444 | 82223958 | 86196402 | Education Infrastructure Grant | Upgrading and Additions
|  | 9350 | P9005972 | Eastern Cape | DAVID LIVINGSTONE SECONDARY SCHOOL | 200100151 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2015-09-23 | 2018-06-19 | 2026-03-30 | 2025-03-30 | 2025-03-30 | 5461925 | 71460900 | 76999902 | Education Infrastructure Grant | Upgrading and Additions
|  | 9351 | P9006103 | Eastern Cape | JJ Serfontein (Sakhingcali Maths, Science & Tech) | 200600305 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2015-01-27 | 2017-06-01 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 4464413 | 45396817 | 49861230 | Education Infrastructure Grant | Upgrading and Additions
|  | 9352 | P9005967 | Eastern Cape | KHIBA JUNIOR SECONDARY SCHOOL | 200600332 | Senqu | Construction 76% - 99% | Active - Contracted | 2016-04-18 | 2019-04-15 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 3268678 | 18165643 | 21434321 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9353 | P9005970 | Eastern Cape | MPUMELELO MFUNDISI SENIOR PRIMARY SCHOOL | 200600516 | Walter Sisulu | Construction 51% - 75% | Active - Contracted | 2010-10-19 | 2018-01-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 7625599 | 31773327 | 39398926 | Education Infrastructure Grant | Upgrading and Additions
|  | 9354 | P9005968_ | Eastern Cape | NKOPANE JUNIOR SECONDARY SCHOOL | 200600583 | Senqu | Construction 76% - 99% | Active - Contracted | 2015-02-15 | 2017-02-10 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 8510568 | 35460701 | 43971269 | Education Infrastructure Grant | Upgrading and Additions
|  | 9355 | P9005969 | Eastern Cape | PHAMBILI MZONTSUNDU SECONDARY SCHOOL | 200600670 | Walter Sisulu | Construction 26% - 50% | Active - Contracted | 2014-10-07 | 2018-01-01 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 8815849 | 36732705 | 45548554 | Education Infrastructure Grant | Upgrading and Additions
|  | 9380 | P9009799_ | Eastern Cape | MBIZANA DISTRICT OFFICE | 200999901 | Mbizana | Construction 76% - 99% | Approved | 2018-02-27 | 2018-03-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4404304 | 28155720 | 32560024 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9391 | P9006533_ | Eastern Cape | D M SKOSANA SENIOR SECONDARY SCHOOL | 200600123 | Sakhisizwe | Practical Completion (100%) | Active - Contracted | 2017-04-03 | 2018-03-22 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 3301180 | 0 | 3301180 | Education Infrastructure Grant | Upgrading and Additions
|  | 9392 | P0000081 | Eastern Cape | DINIZULU HIGH SCHOOL | 200300836 | Mbhashe | Design | Active - Not Contracted | 2017-10-02 |  | 2025-03-31 |  |  | 4124891 | 37499007 | 41623898 | Education Infrastructure Grant | Upgrading and Additions
|  | 9396 | P9005974 | Eastern Cape | GOBINAMBA SENIOR SECONDARY SCHOOL | 200300111 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-03-02 | 2019-04-11 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 4710200 | 26436200 | 31146400 | Education Infrastructure Grant | Upgrading and Additions
|  | 9399 | P0002053 | Eastern Cape | ISOLOMZI SENIOR SECONDARY SCHOOL | 200300149 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 5936145 | 53964955 | 59901100 | Education Infrastructure Grant | Upgrading and Additions
|  | 9400 | P9005754 | Eastern Cape | JOUBERT LUDIDI SENIOR SECONDARY SCHOOL | 200400308 | Mhlontlo | Construction 76% - 99% | Active - Contracted | 2017-02-28 | 2017-04-30 | 2026-03-31 | 2026-03-31 | 2026-03-01 | 3931812 | 33320442 | 37252254 | Education Infrastructure Grant | Upgrading and Additions
|  | 9403 | P9005975 | Eastern Cape | kwaMHLONTLO SENIOR SECONDARY SCHOOL | 200600353 | Emalahleni | Practical Completion (100%) | Active - Contracted | 2018-02-19 | 2019-04-11 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 5604500 | 31545300 | 37149800 | Education Infrastructure Grant | Upgrading and Additions
|  | 9407 | P9005757 | Eastern Cape | MANZAMNYAMA SENIOR SECONDARY SCHOOL | 200501408 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 5565306 | 31248210 | 36813516 | Education Infrastructure Grant | Upgrading and Additions
|  | 9408 | P0004090 | Eastern Cape | MATHUMBU SENIOR SECONDARY SCHOOL | 200300295 | Mbhashe | Design | Active - Not Contracted | 2017-04-01 |  | 2026-03-31 |  |  | 5496216 | 62823096 | 68319312 | Education Infrastructure Grant | Upgrading and Additions
|  | 9413 | P0002058 | Eastern Cape | MGOMANZI SENIOR SECONDARY SCHOOL | 200300329 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 4000012 | 36363749 | 40363761 | Education Infrastructure Grant | Upgrading and Additions
|  | 9414 | P9005760 | Eastern Cape | MOKHESENG SENIOR SECONDARY SCHOOL | 200500734 | Matatiele | Practical Completion (100%) | Active - Contracted | 2018-03-01 | 2018-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4319000 | 24205100 | 28524100 | Education Infrastructure Grant | Upgrading and Additions
|  | 9417 | P9005763 | Eastern Cape | MOUNT HARGREAVES SENIOR SECONDARY SCHOOL | 200500748 | Matatiele | Practical Completion (100%) | Active - Contracted | 2018-02-21 | 2019-04-16 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 6776600 | 33191580 | 39968180 | Education Infrastructure Grant | Upgrading and Additions
|  | 9423 | P0002063 | Eastern Cape | NOLITA COMPREHENSIVE TECHNICAL HIGH SCHOOL | 200300472 | Mnquma | Design | Active - Not Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 6002390 | 54567181 | 60569571 | Education Infrastructure Grant | Upgrading and Additions
|  | 9425 | P9005977 | Eastern Cape | NONKQUBELA SENIOR SECONDARY SCHOOL | 200600614 | Emalahleni | Practical Completion (100%) | Active - Contracted | 2018-02-20 | 2019-04-15 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 3844200 | 21751100 | 25595300 | Education Infrastructure Grant | Upgrading and Additions
|  | 9427 | P9005978 | Eastern Cape | NTSONKOTA SECONDARY SCHOOL | 200200658 | Buffalo City | Design | Active - Contracted | 2017-04-01 |  | 2026-03-31 |  |  | 3888512 | 0 | 3888512 | Education Infrastructure Grant | Upgrading and Additions
|  | 9430 | P9005769 | Eastern Cape | RALEBITSO SENIOR SECONDARY SCHOOL | 200501057 | Matatiele | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-05-31 | 2026-03-31 | 2024-03-31 | 2025-03-31 | 3482700 | 19459000 | 22941700 | Education Infrastructure Grant | Upgrading and Additions
|  | 9432 | P0002064 | Eastern Cape | SOPHAKAMA SENIOR SECONDARY SCHOOL | 200300823 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 4148363 | 37712389 | 41860752 | Education Infrastructure Grant | Upgrading and Additions
|  | 9434 | P9005979 | Eastern Cape | TAMBEKILE SENIOR SECONDARY SCHOOL | 200600816 | Emalahleni | Practical Completion (100%) | Active - Contracted | 2018-03-02 | 2020-03-04 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4230800 | 24832200 | 29063000 | Education Infrastructure Grant | Upgrading and Additions
|  | 9435 | P9013191 | Eastern Cape | THEMBALESIZWE COMP TECH SENIOR SECONDARY SCHOOL | 200501195 | Buffalo City | Tender | Approved | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 2397237 | 2397237 | Education Infrastructure Grant | Upgrading and Additions
|  | 9436 | P9005773 | Eastern Cape | TOLENI PRIMARY SCHOOL | 200501216 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2017-06-29 | 2017-08-29 | 2026-03-31 | 2024-03-31 | 2026-03-31 | 7309298 | 43711047 | 51020345 | Education Infrastructure Grant | Upgrading and Additions
|  | 9437 | P9005774 | Eastern Cape | TOLWENI SENIOR SECONDARY SCHOOL | 200501219 | Mhlontlo | Construction 76% - 99% | Active - Contracted | 2017-06-29 | 2017-08-28 | 2026-03-31 | 2024-03-01 | 2026-03-01 | 4773610 | 40454318 | 45227928 | Education Infrastructure Grant | Upgrading and Additions
|  | 9439 | P0002065 | Eastern Cape | UPPER GWADU SENIOR SECONDARY SCHOOL | 200300627 | Mbhashe | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 6461016 | 58736512 | 65197528 | Education Infrastructure Grant | Upgrading and Additions
|  | 9441 | P0002066 | Eastern Cape | VULINGCOBO SENIOR SECONDARY SCHOOL | 200300719 | Mbhashe | Design | Active - Not Contracted | 2017-10-02 |  | 2025-03-31 |  |  | 7772332 | 70657559 | 78429891 | Education Infrastructure Grant | Upgrading and Additions
|  | 9442 | P0002067 | Eastern Cape | VULUHLANGA SENIOR SECONDARY SCHOOL | 200300650 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 4713286 | 42848053 | 47561339 | Education Infrastructure Grant | Upgrading and Additions
|  | 9443 | P0002068 | Eastern Cape | WILLOWVALE SENIOR SECONDARY SCHOOL | 200300764 | Mbhashe | Design | Active - Not Contracted | 2017-10-02 |  | 2025-03-31 |  |  | 6029506 | 54813691 | 60843197 | Education Infrastructure Grant | Upgrading and Additions
|  | 9445 | P9005778 | Eastern Cape | ZAKHELE JUNIOR SECONDARY SCHOOL | 200501302 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2017-06-29 | 2017-08-31 | 2026-03-31 | 2023-03-31 | 2026-03-31 | 0 | 44074700 | 44074700 | Education Infrastructure Grant | Upgrading and Additions
|  | 9451 | P0004241_ | Eastern Cape | BOKAMOSO PRIMARY SCHOOL | 200501588 | Matatiele | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6492000 | 6492000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9453 | P0004254_ | Eastern Cape | MKANZINI JUNIOR SECONDARY SCHOOL | 200400609 | Port St Johns | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-04-02 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 9387946 | 17422978 | 26810924 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9459 | P9006340_ | Eastern Cape | MOSHESH SENIOR SECONDARY SCHOOL (Clsrms) | 200500744 | Matatiele | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 605058 | 434058 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9461 | P9013179 | Eastern Cape | PALMERTON HIGH SCHOOL | 200501006 | Ingquza Hill | Construction 76% - 99% | Approved | 2017-04-01 | 2018-03-26 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 9485 | P9006477 | Eastern Cape | LINGELETHU JUNIOR PRIMARY SCHOOL | 200500413 | Mbizana | Tender | Active - Not Contracted | 2018-02-07 |  | 2026-03-31 |  |  | 2049082 | 8899461 | 10948543 | Education Infrastructure Grant | Upgrading and Additions
|  | 9512 | P0002062 | Eastern Cape | NCEDISIZWE SENIOR SECONDARY SCHOOL | 200300778 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 5819585 | 52905320 | 58724905 | Education Infrastructure Grant | Upgrading and Additions
|  | 9519 | P9005229_ | Eastern Cape | NGWEKAZI SENIOR SECONDARY SCHOOL | 200500897 | Umzimvubu | Final Completion | Active - Contracted | 2014-04-30 | 2017-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 637144 | 637144 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9523 | P9011593 | Eastern Cape | NONKQUBELA SENIOR SECONDARY SCHOOL | 200600614 | Emalahleni | Design | Active - Not Contracted | 2015-02-10 |  | 2026-03-31 |  |  | 0 | 4857604 | 4857604 | Education Infrastructure Grant | Upgrading and Additions
|  | 9541 | P9006489 | Eastern Cape | TOLI SENIOR SECONDARY SCHOOL | 200501217 | Port St Johns | Design | Active - Contracted | 2018-10-12 |  | 2026-03-31 |  |  | 5802003 | 115570326 | 121372329 | Education Infrastructure Grant | Upgrading and Additions
|  | 9558 | P9005121 | Eastern Cape | CHABASA JUNIOR PRIMARY SCHOOL | 200400586 | Port St Johns | Construction 76% - 99% | Active - Contracted | 2016-06-27 | 2016-08-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 87140 | 1571672 | 1658812 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9561 | P9005127_ | Eastern Cape | FUNDANI SENIOR PRIMARY SCHOOL | 200401262 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2015-10-16 | 2015-12-08 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 884482 | 884482 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9565 | P9005124 | Eastern Cape | kwaZIZAMELE JUNIOR SECONDARY SCHOOL | 200500389 | Port St Johns | Construction 26% - 50% | Active - Contracted | 2016-06-27 | 2016-08-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1561505 | 1561505 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9569 | P9005264_ | Eastern Cape | MDENI SENIOR SECONDARY SCHOOL | 200300314 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2014-05-05 | 2015-05-11 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 84000 | 1317085 | 1401085 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9570 | P9005123 | Eastern Cape | MDINA PRIMARY JUNIOR SCHOOL | 200400568 | Nyandeni | Construction 76% - 99% | Active - Contracted | 2016-06-28 | 2016-08-28 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 225000 | 2148003 | 2373003 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9571 | P9005103_ | Eastern Cape | MIDDELPOS PRIMARY SCHOOL | 200600485 | Buffalo City | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-13 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 263118 | 1167087 | 1430205 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9573 | P9005101_ | Eastern Cape | NCEBA PUBLIC SCHOOL | 200600548 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2016-07-04 | 2016-08-03 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 250023 | 1642374 | 1892397 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9582 | P9005049 | Eastern Cape | TLOKWENG SENIOR SECONDARY SCHOOL | 200600849 | Senqu | Final Completion | Active - Contracted | 2016-08-15 | 2016-10-16 | 2023-03-31 | 2025-03-31 | 2025-03-01 | 255505 | 2303958 | 2559463 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9588 | P9005126 | Eastern Cape | ZWELI JUNIOR SECONDARY SCHOOL | 200401209 | King Sabata Dalindyebo | Construction 26% - 50% | Active - Contracted | 2016-06-28 | 2016-08-31 | 2025-01-29 | 2025-01-29 | 2026-01-29 | 273575 | 1974080 | 2247655 | Education Infrastructure Grant | Upgrading and Additions
|  | 9599 | P9010439 | Eastern Cape | MALEPE-LEPE JUNIOR SECONDARY SCHOOL | 200400467 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-10 | 2025-03-30 | 2025-03-31 | 2025-03-31 | 0 | 2540434 | 2540434 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9602 | P9005786 | Eastern Cape | MKANKOMO JUNIOR SECONDARY SCHOOL | 200500691 | Ingquza Hill | Design | Proposed | 2017-11-13 |  | 2026-03-31 |  |  | 0 | 5166629 | 5166629 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9617 | P0002365_ | Eastern Cape | EBLORWENI SENIOR PRIMARY SCHOOL | 200500159 | Mbizana | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3053577 | 3053577 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9619 | P9011536 | Eastern Cape | FlORADALE FARM SCHOOL | 200200182 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-05-10 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 86632 | 86632 | Education Infrastructure Grant | Upgrading and Additions
|  | 9620 | P0003687_ | Eastern Cape | HOMBE JUNIOR SECONDARY SCHOOL | 200500310 | Ingquza Hill | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 5428559 | 5428559 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9621 | P9003551 | Eastern Cape | JONGUHLANGA JUNIOR PRIMARY SCHOOL | 200400305 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2017-05-09 | 2017-05-29 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 16009830 | 16009830 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9624 | P9003564_ | Eastern Cape | NTSHELENI SENIOR PRIMARY SCHOOL | 200500976 | Mhlontlo | Construction 26% - 50% | Active - Contracted | 2014-09-03 | 2014-09-15 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5579275 | 5579275 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9625 | P0003688_ | Eastern Cape | NTSIMBINI JUNIOR SECONDARY SCHOOL | 200500980 | Mbizana | Practical Completion (100%) | Active - Contracted | 2013-02-14 | 2015-06-22 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5371260 | 5371260 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9627 | P9003577 | Eastern Cape | ZILINYAMA JUNIOR PRIMARY SCHOOL | 200401188 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2017-03-29 | 2017-05-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 10592716 | 10592716 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9629 | P9011602 | Eastern Cape | BLYTHSWOOD HIGH SCHOOL - Sanitation | 200300024 | Mnquma | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7113079 | 7113079 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9630 | P9004824_ | Eastern Cape | DALINDYEBO SENIOR SECONDARY SCHOOL (ACM) | 200400106 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2014-07-07 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 15173618 | 15173618 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9633 | P9006529 | Eastern Cape | MAKAULA SENIOR SECONDARY SCHOOL (Hostels) | 200500534 | Umzimvubu | Feasibility | Active - Not Contracted | 2019-03-01 |  | 2026-03-31 |  |  | 29186973 | 246103730 | 275290703 | Education Infrastructure Grant | Upgrading and Additions
|  | 9635 | P0004534_ | Eastern Cape | NGANGELIZWE SENIOR SECONDARY SCHOOL (Hostel) | 200401343 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2013-12-09 | 2016-05-03 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 1505097 | 15626360 | 17131457 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9637 | P0004409_ | Eastern Cape | OSBORN SENIOR SECONDARY SCHOOL (Hostels) | 200501001 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2013-01-23 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 849984 | 4355256 | 5205240 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9639 | P0004403_ | Eastern Cape | SHAWBURY SENIOR SECONDARY SCHOOL (Hostels) | 200400989 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2014-04-02 | 2014-05-01 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 0 | 231000 | 231000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9644 | P9007298_ | Eastern Cape | FREEMANTLE AGRICULTURAL SCHOOL - Water (Phase I) | 200600204 | Enoch Mgijima | Construction 51% - 75% | Active - Contracted | 2018-10-26 | 2018-11-22 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7531837 | 7531837 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9646 | P9004832_ | Eastern Cape | LADY GREY ARTS ACADEMY ( Hostels) | 200600985 | Senqu | Final Completion | Active - Contracted | 2014-03-06 | 2016-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 0 | 5774868 | 5774868 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9647 | P9006756_ | Eastern Cape | LAERSKOOL UNIE - Water | 200600363 | Walter Sisulu | Construction 76% - 99% | Active - Contracted | 2016-06-24 | 2016-10-07 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 2575888 | 2575888 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9651 | P9004821 | Eastern Cape | NTSONKOTHA SENIOR SECONDARY SCHOOL (Hostels) | 200600642 | Emalahleni | Site Handed - Over to Contractor | Active - Not Contracted | 2015-04-01 | 2015-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 28107610 | 198287608 | 226395218 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 9659 | P9004833_ | Eastern Cape | LAERSKOOL UNIE (HOSTEL) | 200600363 | Walter Sisulu | Final Completion | Approved | 2014-03-06 | 2016-07-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 534334 | 8230728 | 8765062 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9663 | P9010995 | Eastern Cape | PHANDULWAZI AGRIC HIGH SCHOOL | 200200684 | Raymond Mhlaba | Design | Active - Contracted | 2017-04-01 |  | 2026-03-31 |  |  | 0 | 32278831 | 32278831 | Education Infrastructure Grant | Upgrading and Additions
|  | 9670 | P0003253_ | Eastern Cape | JONGINGWE SENIOR PRIMARY SCHOOL | 200400296 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2013-02-25 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3428807 | 11732643 | 15161450 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9671 | P0003258_ | Eastern Cape | KULANATHI SS SCHOOL | 200400336 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2013-02-19 | 2015-05-01 | 2025-03-31 | 2016-03-31 | 2022-03-31 | 4498513 | 14488228 | 18986741 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9673 | P0003263_ | Eastern Cape | kwaNOBUHLE SENIOR SECONDARY SCHOOL | 200401300 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-01 | 2023-03-31 | 2024-03-31 | 2024-03-31 | 4292388 | 27569625 | 31862013 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9675 | P0003273_ | Eastern Cape | LUZINI JUNIOR SECONDARY SCHOOL | 200400424 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2013-05-23 | 2015-05-01 | 2025-03-31 | 2022-03-31 | 2022-03-31 | 5611028 | 22918886 | 28529914 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9676 | P0003278_ | Eastern Cape | MAGUBUNGELA SENIOR PRIMARY SCHOOL | 200500518 | Mhlontlo | Final Completion | Active - Contracted | 2013-04-25 | 2015-05-01 | 2026-03-31 | 2022-03-31 | 2022-03-30 | 2054628 | 11828611 | 13883239 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9681 | P0003286 | Eastern Cape | MBENENGENI JUNIOR SECONDARY SCHOOL | 200400532 | Port St Johns | Construction 76% - 99% | Active - Contracted | 2013-04-16 | 2013-06-16 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2981105 | 16555981 | 19537086 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9685 | P0003312_ | Eastern Cape | NDZULUKA PRIMARY SCHOOL | 200400730 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2023-03-31 | 2026-03-31 | 2433000 | 12875921 | 15308921 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 9686 | P0003313_ | Eastern Cape | NGCINGO JUNIOR SECONDARY SCHOOL | 200501356 | Mbizana | Practical Completion (100%) | Active - Contracted | 2013-03-19 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4219494 | 25603955 | 29823449 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9690 | P0003382_ | Eastern Cape | SIXUZULU PRIMARY SCHOOL | 200401012 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2013-05-13 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2778000 | 21019192 | 23797192 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9692 | P0003396_ | Eastern Cape | TANDABANTU PRIMARY SCHOOL | 200501179 | Mbizana | Construction 76% - 99% | Active - Contracted | 2012-12-13 | 2015-05-11 | 2024-03-31 | 2024-03-31 | 2022-03-31 | 3255604 | 17736607 | 20992211 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9695 | P0003430_ | Eastern Cape | ZONNEBLOM JUNIOR PRIMARY SCHOOL | 200401197 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2012-11-23 | 2014-05-01 | 2024-03-31 | 2024-03-31 | 2022-03-31 | 0 | 12922524 | 12922524 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9696 | P0004280_ | Eastern Cape | BALENI JUNIOR SECONDARY SCHOOL | 200500012 | Mbizana | Construction 76% - 99% | Active - Contracted | 2012-05-02 | 2015-06-22 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 210000 | 1541059 | 1751059 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9697 | P9007202 | Eastern Cape | BAZINDLOVU PRIMARY JUNIOR SCHOOL | 200400023 | Engcobo | Design | Active - Not Contracted | 2016-07-27 |  | 2025-03-31 |  |  | 7551491 | 48303669 | 55855160 | Education Infrastructure Grant | Upgrading and Additions
|  | 9715 | P0001583_ | Eastern Cape | MEYISI SENIOR SECONDARY SCHOOL | 200500653 | Amahlathi | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-11 | 2021-03-31 | 2016-03-16 | 2024-03-31 | 0 | 1253072 | 1253072 | Education Infrastructure Grant | Upgrading and Additions
|  | 9716 | P0001642_ | Eastern Cape | NONYIKILA PRIMARY SCHOOL | 200400827 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2008-08-27 | 2015-05-01 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 2602579 | 6936411 | 9538990 | Education Infrastructure Grant | Upgrading and Additions
|  | 9719 | P9011547 | Eastern Cape | XOLOBENI JUNIOR SECONDARY SCHOOL | 200501296 | Mbizana | Feasibility | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 3949314 | 3949314 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9725 | 200600335_ | Eastern Cape | KHWAZA SENIOR SECONDARY SCHOOL | 200600335 | Intsika Yethu | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 0 | 66000 | -333000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9726 | P0004284_ | Eastern Cape | MACIBI PRIMARY SCHOOL | 200200399 | Buffalo City | Practical Completion (100%) | Approved | 2012-05-29 | 2015-05-11 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 463378 | 463378 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9731 | P0004316_ | Eastern Cape | MVENYANE SENIOR SECONDARY SCHOOL (Hostel) | 200500810 | Matatiele | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 14541672 | 57916723 | 72458395 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9732 | P0001286_ | Eastern Cape | MVENYANE SENIOR SECONDARY SCHOOL (Hostels) | 200500810 | Matatiele | Construction 76% - 99% | Active - Contracted | 2007-02-27 | 2015-07-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4617000 | 34168723 | 38785723 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9736 | P0001506 | Eastern Cape | KING SABATA DALINDYEBO (BUILDINGS) | 200700004 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2022-05-01 | 2025-02-28 | 2025-02-28 | 2025-02-28 | 0 | 55570979 | 55570979 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9738 | P0001183_ | Eastern Cape | MT FRERE TECHNICAL COLLEGE (INGWE) | 200501452 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 18517758 | 18517758 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9739 | P9005823_ | Eastern Cape | GAMBLE STREET SECONDARY SCHOOL (HOSTEL) | 200100238 | Nelson Mandela Bay | Pre - Feasibility | Approved | 2015-04-01 |  | 2026-03-31 |  |  | 41509970 | 2000000 | 43509970 | Education Infrastructure Grant | Upgrading and Additions
|  | 9744 | P9010684 | Eastern Cape | NOTINTSILA JUNIOR SECONDARY SCHOOL | 200400834 | Nyandeni | Practical Completion (100%) | Approved | 2018-03-20 | 2018-06-22 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1558415 | 1558415 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9753 | P0001594_ | Eastern Cape | HESHANGOPHONDO PRIMARY SCHOOL (clsrms) | 200200243 | Raymond Mhlaba | Practical Completion (100%) | Approved | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1563478 | 12937062 | 14500540 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9759 | P0001568_ | Eastern Cape | MQANDULI VILLAGE JUNIOR SECONDARY SCHOOL | 200600654 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2009-04-01 | 2015-08-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 5915268 | 11359040 | 17274308 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9760 | P0001569_ | Eastern Cape | MOUNT AYLIFF SENIOR SECONDARY SCHOOL | 200500784 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4424750 | 29254753 | 33679503 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9762 | P0001573_ | Eastern Cape | NONTANGANA SENIOR PRIMARY SCHOOL (clsrms) | 200401357 | Nyandeni | Practical Completion (100%) | Approved | 2012-05-14 | 2015-05-11 | 2023-03-01 | 2024-03-31 | 2022-03-31 | 857000 | 5260694 | 6117694 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9764 | P0001606_ | Eastern Cape | NQEKETO JUNIOR SECONDARY SCHOOL (clsrms) | 200400843 | Nyandeni | Practical Completion (100%) | Approved | 2015-02-02 | 2015-05-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4598920 | 17486479 | 22085399 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9765 | P0001575_ | Eastern Cape | NTSHELE JUNIOR SECONDARY SCHOOL (clsrms) | 200400869 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2012-05-14 | 2015-08-11 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 989000 | 10201248 | 11190248 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9769 | P0001611_ | Eastern Cape | SIJIKA SENIOR PRIMARY SCHOOL | 200501104 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2012-04-10 | 2015-05-11 | 2024-03-31 | 2024-03-31 | 2022-03-31 | 2882387 | 10945955 | 13828342 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9776 | P9004944_ | Eastern Cape | ETWA JUNIOR SECONDARY SCHOOL | 200400176 | Mhlontlo | Final Completion | Active - Contracted | 2014-04-01 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3832257 | 3832257 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9791 | P9005813 | Eastern Cape | BUBESI PRIMARY SCHOOL | 200500061 | Matatiele | Feasibility | Active - Not Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 1335525 | 8515925 | 9851450 | Education Infrastructure Grant | Upgrading and Additions
|  | 9794 | P0003497_ | Eastern Cape | GAMBLE STREET SEC SCHOOL (Phase I) | 200100238 | Nelson Mandela Bay | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2019-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 4150997 | 10078775 | 14229772 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9800 | P9013250 | Eastern Cape | LOWER SEPLAN PRIMARY SCHOOL | 200600387 | Intsika Yethu | Site Handed - Over to Contractor | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9805 | P0002278 | Eastern Cape | MANGUZELA SENIOR SECONDARY SCHOOL | 200500568 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2017-05-11 | 2017-07-11 | 2024-03-31 | 2022-03-31 | 2022-03-31 | 559673 | 3034676 | 3594349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9810 | P9004938_ | Eastern Cape | NKULULEKO SENIOR SECONDARY SCHOOL | 200600589 | Walter Sisulu | Practical Completion (100%) | Active - Contracted | 2016-01-28 | 2016-05-11 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 4395795 | 4395795 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9811 | P0001677 | Eastern Cape | NONINZI LUZIPHO PRIMARY SCHOOL | 200101025 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2015-03-20 | 2017-09-30 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 7774933 | 58999296 | 66774229 | Education Infrastructure Grant | Upgrading and Additions
|  | 9821 | P0002995_ | Eastern Cape | ZANOZUKO SECONDARY SCHOOL | 200200934 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2011-05-04 | 2015-05-01 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 57598 | 178057 | 235655 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9825 | P0003621_ | Eastern Cape | DALUXOLO JUNIOR SECONDARY SCHOOL | 200300060 | Mnquma | Final Completion | Approved | 2015-04-01 | 2015-05-11 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 65000 | 1354510 | 1419510 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9827 | P0003506_ | Eastern Cape | GABAJANA JUNIOR SECONDARY SCHOOL | 200500239 | Ingquza Hill | Construction 76% - 99% | Active - Contracted | 2018-01-17 | 2018-05-19 | 2024-03-31 | 2025-03-01 | 2025-03-31 | 5600000 | 44720745 | 50320745 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9830 | P0003518_ | Eastern Cape | LUJECWENI JUNIOR SECONDARY SCHOOL | 200500458 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2013-05-17 | 2015-05-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 3466000 | 19134615 | 22600615 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9834 | P0003520_ | Eastern Cape | MCITWA SENIOR PRIMARY SCHOOL - ACM | 200300313 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2013-07-26 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2785078 | 13929617 | 16714695 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9839 | P0003530_ | Eastern Cape | QOLOMBANE JUNIOR PRIMARY SCHOOL | 200400951 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2013-05-13 | 2015-05-01 | 2023-03-31 | 2024-04-01 | 2025-03-31 | 2865743 | 16073375 | 18939118 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9841 | P0003532_ | Eastern Cape | RYNO STATE AIDED SCHOOL | 200400973 | Engcobo | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-11 | 2023-03-31 | 2024-03-31 | 2024-03-31 | 0 | 21117434 | 21117434 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9844 | P0003537_ | Eastern Cape | THAKABANNA SENIOR SECONDARY SCHOOL | 200501194 | Elundini | Final Completion | Active - Contracted | 2013-09-13 | 2015-05-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 3468120 | 19299837 | 22767957 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9846 | P9003578_ | Eastern Cape | ZIMBANE VALLEY SECONDARY SCHOOL (NEW WORKS) | 200400403 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2080808 | 22053390 | 24134198 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9848 | P9004560_ | Eastern Cape | DIDI SENIOR PRIMARY SCHOOL | 200500125 | Mbizana | Construction 76% - 99% | Active - Contracted | 2014-02-11 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6491229 | 6491229 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9849 | P9004562_ | Eastern Cape | EMAZWENI JUNIOR PRIMARY SCHOOL | 200500183 | Mbizana | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 9030866 | 9030866 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9850 | P9011585 | Eastern Cape | MACLEAR METHODIST PRIMARY SCHOOL | 200401317 | Elundini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-05-01 | 2023-05-31 | 2023-05-31 | 2026-05-31 | 0 | 12934021 | 12965609 | Education Infrastructure Grant | Upgrading and Additions
|  | 9851 | P9004564_ | Eastern Cape | MT FLETCHER VILLAGE JUNIOR SECONDARY SCHOOL | 200500785 | Elundini | Final Completion | Active - Contracted | 2014-03-19 | 2015-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7836214 | 7836214 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9854 | P9004567_ | Eastern Cape | QUMBU VILLAGE JUNIOR SECONDARY SCHOOL | 200400956 | Mhlontlo | Final Completion | Active - Contracted | 2014-02-07 | 2015-05-11 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 0 | 8851586 | 8851586 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9855 | P9004568_ | Eastern Cape | SIYOYO JUNIOR SECONDARY SCHOOL | 200501131 | Mhlontlo | Final Completion | Active - Contracted | 2014-02-07 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6255577 | 6255577 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9856 | P9004569_ | Eastern Cape | THEMBA MZIZI JUNIOR PRIMARY SCHOOL | 200501600 | Mbizana | Practical Completion (100%) | Active - Contracted | 2014-02-11 | 2016-05-11 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 7930532 | 7930532 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 9858 | P0003615_ | Eastern Cape | BUBESI PRIMARY SCHOOL | 200500061 | Matatiele | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 233956 | 1520434 | 1754390 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9860 | P0003619_ | Eastern Cape | COVE RIDGE PRIMARY SCHOOL | 200200093 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 117000 | 872481 | 989481 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9865 | P0003629_ | Eastern Cape | HILLSIDE JUNIOR SECONDARY SCHOOL | 200500294 | Engcobo | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-11 | 2023-03-31 | 2018-03-20 | 2024-03-31 | 164000 | 1000257 | 1164257 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9866 | P0003631_ | Eastern Cape | IMINGCANGATHELO HIGH SCHOOL | 200200269 | Raymond Mhlaba | Final Completion | Active - Contracted | 2015-04-01 | 2016-03-01 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 112000 | 500438 | 612438 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9867 | P0003635_ | Eastern Cape | kwaNONDUDUMO JUNIOR SECONDARY SCHOOL | 200500385 | Ingquza Hill | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 183000 | 1125918 | 1308918 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9870 | P0003549_ | Eastern Cape | LUDONDOLO JUNIOR SECONDARY SCHOOL | 200300237 | Mbhashe | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-11 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 171026 | 788199 | 959225 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9872 | P0003552_ | Eastern Cape | LUXOMO JUNIOR SECONDARY SCHOOL | 200300803 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-11 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 75000 | 455874 | 530874 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9875 | P0003556_ | Eastern Cape | MARHELEDWANE HIGH SCHOOL | 200200418 | Ngqushwa | Practical Completion (100%) | Active - Contracted | 2012-05-15 | 2015-05-11 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 289611 | 289611 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9877 | P0003558_ | Eastern Cape | MBELO JUNIOR SECONDARY SCHOOL | 200300306 | Buffalo City | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-11 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 105000 | 714429 | 819429 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9878 | P9006481_ | Eastern Cape | MDUMAZULU JUNIOR SECONDARY SCHOOL | 200400571 | Nyandeni | Design | Active - Not Contracted | 2018-09-03 |  | 2026-03-31 |  |  | 0 | 10179725 | 10179725 | Education Infrastructure Grant | Upgrading and Additions
|  | 9881 | P0003565_ | Eastern Cape | MHALA JUNIOR SECONDARY SCHOOL | 200300334 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2012-06-12 | 2015-05-11 | 2023-03-31 | 2024-03-16 | 2025-03-31 | 0 | 1124849 | 1124849 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9886 | P0003572_ | Eastern Cape | MDIBANISO SECONDARY SCHOOL | 200200457 | Raymond Mhlaba | Practical Completion (100%) | Active - Not Contracted | 2015-04-01 | 2015-05-11 | 2022-04-21 | 2022-03-21 | 2024-03-21 | 125000 | 870731 | 995731 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9888 | P0003580_ | Eastern Cape | NOBUMBA PRIMARY SCHOOL | 200200593 | Ngqushwa | Practical Completion (100%) | Active - Contracted | 2012-07-02 | 2015-05-11 | 2023-03-31 | 2024-03-31 | 2025-03-31 | 100000 | 684688 | 784688 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9892 | P0003591_ | Eastern Cape | SAKHIKAMVA HIGH SCHOOL | 200201033 | Buffalo City | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-01 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 230000 | 1403131 | 1633131 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9911 | P0001725_ | Eastern Cape | KwaQONDA JUNIOR SECONDARY SCHOOL | 200500387 | Ingquza Hill | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 5240000 | 50323362 | 55563362 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9913 | P9005721_ | Eastern Cape | SIGCAU SPECIAL SCHOOL (PHASE II) | 200501101 | Ingquza Hill | Practical Completion (100%) | Potential | 2016-06-20 | 2016-09-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1412000 | 9648918 | 11060918 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9914 | P0003724_ | Eastern Cape | SIGCAU SPECIAL SCHOOL (PHASE III) | 200501591 | Matatiele | Feasibility | Approved | 2015-04-01 |  | 2023-03-31 |  |  | 0 | 160189000 | 160189000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9919 | P0003745_ | Eastern Cape | VUKUZENZELE SPECIAL SCHOOL | 200501280 | Mbizana | Practical Completion (100%) | Active - Contracted | 2013-12-17 | 2014-04-03 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 0 | 125789006 | 125789006 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9921 | P0003911 | Eastern Cape | ARTHUR MFEBE SENIOR SECONDARY SCHOOL | 200601046 | Intsika Yethu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 359322 | 359322 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9926 | P9005267_ | Eastern Cape | CHIEF DUMILE SECONDARY SCHOOL | 200501404 | Mbizana | Practical Completion (100%) | Active - Contracted | 2014-03-13 | 2015-06-22 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 410000 | 5182230 | 5592230 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9928 | P9005263_ | Eastern Cape | CWECWENI SENIOR SECONDARY SCHOOL | 200400094 | Engcobo | Practical Completion (100%) | Active - Contracted | 2014-05-19 | 2015-05-11 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 80000 | 1393085 | 1473085 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9938 | P9005275_ | Eastern Cape | ENQABENI SECONDARY SCHOOL | 200500205 | Mbizana | Construction 76% - 99% | Approved | 2014-03-14 | 2015-05-11 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 900000 | 6132748 | 7032748 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9940 | 200300744 | Eastern Cape | Ezingqayi SSS | 200300744 | Mnquma | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-11 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 0 | 144177 | 144177 | Education Infrastructure Grant | Upgrading and Additions
|  | 9941 | P9005328_ | Eastern Cape | EZIZWENI HIGH SCHOOL | 200300093 | Mnquma | Final Completion | Approved | 2014-07-22 | 2015-05-11 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 284173 | 1786443 | 2139489 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9942 | P9005217_ | Eastern Cape | FALO SENIOR SECONDARY SCHOOL | 200600195 | Intsika Yethu | Practical Completion (100%) | Active - Not Contracted | 2015-04-01 | 2015-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 270000 | 3086521 | 3356521 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9947 | P9005274_ | Eastern Cape | GUMZANA SENIOR SECONDARY SCHOOL | 200500278 | Mbizana | Practical Completion (100%) | Approved | 2014-03-31 | 2015-06-22 | 2023-03-31 | 2024-03-11 | 2025-03-31 | 496778 | 5264008 | 5760786 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9955 | P9005220_ | Eastern Cape | ISIVIVANE SENIOR SECONDARY SCHOOL | 200600301 | Emalahleni | Practical Completion (100%) | Approved | 2014-05-14 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 140568 | 1009156 | 1149724 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9961 | P9005218_ | Eastern Cape | JONGIZIZWE NKWENKWEZI SENIOR SECONDARY SCHOOL | 200300804 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2015-05-01 | 2015-05-11 | 2025-03-21 | 2025-03-21 | 2025-03-21 | 0 | 637144 | 637144 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9962 | 200300198 | Eastern Cape | kwaNTOZONKE SS SCHOOL | 200300198 | Mnquma | Construction 76% - 99% | Approved | 2014-07-22 | 2015-05-11 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 579222 | 544954 | Education Infrastructure Grant | Upgrading and Additions
|  | 9971 | P9005807 | Eastern Cape | LUPINDO SENIOR SECONDARY SCHOOL | 200500470 | Matatiele | Tender | Active - Not Contracted | 2018-01-30 |  | 2026-03-31 |  |  | 3520575 | 57610275 | 61130850 | Education Infrastructure Grant | Upgrading and Additions
|  | 9976 | P9005808 | Eastern Cape | MAGADLA SENIOR SECONDARY SCHOOL | 200500512 | Matatiele | Tender | Active - Not Contracted | 2014-04-01 |  | 2026-03-31 |  |  | 7994324 | 60156468 | 68150792 | Education Infrastructure Grant | Upgrading and Additions
|  | 9979 | P9005265_ | Eastern Cape | MANGELENGELE SENIOR SECONDARY SCHOOL | 200300279 | Intsika Yethu | Final Completion | Active - Contracted | 2015-04-01 | 2015-06-22 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 0 | 31485 | 31485 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9982 | P0002089 | Eastern Cape | MBUMBAZI PRIMARY SCHOOL | 200500629 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-05-21 | 2019-10-17 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 276244 | 1841624 | 2117694 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9988 | P9005272_ | Eastern Cape | MPENI SENIOR SECONDARY SCHOOL | 200500754 | Mbizana | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-21 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 780000 | 6392284 | 7172284 | Education Infrastructure Grant | Maintenance and Repairs
|  | 9995 | P9005230_ | Eastern Cape | NDZULULWAZI SENIOR SECONDARY SCHOOL | 200501459 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2014-04-30 | 2015-05-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 637144 | 637144 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10004 | P9005336_ | Eastern Cape | NONDWE SENIOR SECONDARY SCHOOL | 200300488 | Mnquma | Final Completion | Active - Contracted | 2014-03-18 | 2015-04-02 | 2025-03-31 | 2020-03-31 | 2022-03-31 | 275000 | 1714921 | 1989921 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10007 | P9005809 | Eastern Cape | NTUKAYI SENIOR SECONDARY SCHOOL | 200500985 | Mbizana | Tender | Active - Not Contracted | 2018-01-15 |  | 2026-03-31 |  |  | 0 | 89110313 | 89110313 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10009 | P9005234_ | Eastern Cape | NYANISO SENIOR SECONDARY SCHOOL | 200500990 | Matatiele | Final Completion | Active - Contracted | 2015-04-25 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 752989 | 710809 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10012 | P9005232_ | Eastern Cape | PHUMELELE COMP TECH SENIOR SECONDARY SCHOOL | 200501431 | Matatiele | Practical Completion (100%) | Active - Contracted | 2015-04-23 | 2015-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 170000 | 3986085 | 4083125 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10014 | P0003531_ | Eastern Cape | REUBEN NTULI SENIOR SECONDARY SCHOOL | 200401286 | Mhlontlo | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4147377 | 14521646 | 18669023 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10017 | P9013178 | Eastern Cape | SENYUKELE SENIOR SECONDARY SCHOOL | 200501087 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2015-05-11 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 10018 | P9005266_ | Eastern Cape | SHUKUMA SENIOR SECONDARY SCHOOL | 200501090 | Mbizana | Construction 76% - 99% | Active - Contracted | 2014-03-13 | 2015-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 410000 | 4872230 | 5282230 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10019 | P9005269_ | Eastern Cape | SITHUKUTHEZI SECONDARY SCHOOL | 200501123 | Mbizana | Practical Completion (100%) | Approved | 2014-03-14 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 735000 | 6202839 | 6937839 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10037 | P9009749 | Eastern Cape | ZANEWONGA SENIOR SECONDARY SCHOOL | 200300677 | Mbhashe | Final Completion | Active - Contracted | 2018-09-01 | 2019-03-04 | 2026-03-30 | 2025-03-30 | 2026-04-30 | 0 | 48475504 | 48475504 | Education Infrastructure Grant | Upgrading and Additions
|  | 10043 | P9005332_ | Eastern Cape | ZWELIWELILE SENIOR SECONDARY SCHOOL | 200300709 | Mbhashe | Final Completion | Active - Contracted | 2013-11-06 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 257000 | 1599529 | 1856529 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10044 | P9007295_ | Eastern Cape | BYLETTS COMBINED SCHOOL - Water | 200200072 | Great Kei | Construction 51% - 75% | Active - Contracted | 2019-03-31 | 2021-04-04 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2153140 | 5839411 | 7992551 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10049 | P0002072 | Eastern Cape | COLANA SENIOR SECONDARY SCHOOL | 200500098 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2017-11-01 | 2019-04-19 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 450574 | 2699965 | 3150539 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10054 | P0002077 | Eastern Cape | GAVIN JUNIOR SECONDARY SCHOOL | 200400197 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2017-10-02 | 2018-09-12 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 247066 | 1647109 | 1894175 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10056 | P0002079 | Eastern Cape | GWEBINDLALA SENIOR SECONDARY SCHOOL | 200501373 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-10-10 | 2019-04-10 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 252838 | 1685589 | 1938427 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10061 | P0002084 | Eastern Cape | LUNDINI JUNIOR PRIMARY SCHOOL | 200501380 | Mbizana | Practical Completion (100%) | Active - Contracted | 2018-03-26 | 2019-09-19 | 2023-10-02 | 2021-11-17 | 2022-03-31 | 250586 | 1670576 | 1921162 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10062 | P0002085 | Eastern Cape | MAGOBA JUNIOR SECONDARY SCHOOL | 200500515 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-10-08 | 2019-04-02 | 2023-10-02 | 2021-10-27 | 2020-06-30 | 202721 | 1470990 | 1673711 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10064 | P0002087_ | Eastern Cape | MBONGWENI JUNIOR SECONDARY SCHOOL | 200500626 | Ntabankulu | Final Completion | Approved | 2015-04-01 | 2016-05-10 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 0 | 1675300 | 1675300 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10067 | P0002090 | Eastern Cape | MDELWA JUNIOR SECONDARY SCHOOL | 200500640 | Mbizana | Practical Completion (100%) | Active - Contracted | 2018-03-26 | 2019-04-17 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 384983 | 2566553 | 2951536 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10070 | P0002092 | Eastern Cape | MNGCIBE JUNIOR SECONDARY SCHOOL | 200400624 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-11-06 | 2018-12-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 251057 | 1673711 | 1924768 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10073 | P0002094 | Eastern Cape | NOMKOLOKOTO JUNIOR SECONDARY SCHOOL | 200500930 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-05-14 | 2018-12-08 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 511825 | 3713925 | 4225750 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10124 | P9006531 | Eastern Cape | THUBALETHU SECONDARY SCHOOL (Ren Hostels) | 200100908 | Raymond Mhlaba | Construction 76% - 99% | Active - Contracted | 2018-04-02 | 2018-08-23 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 11812261 | 93415867 | 105228128 | Education Infrastructure Grant | Maintenance and Repairs
|  | 10269 | GDE00027 | Gauteng | BRAAMFISCHERVILLE PRIMARY SCHOOL | 700400082 | City of Johannesburg | Construction 1% - 25% | Approved | 2016-04-01 | 2016-08-15 | 2023-04-30 | 2020-04-20 | 2025-03-16 | 30873677 | 124031063 | 154904740 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10276 | GDE00052 | Gauteng | DR MATHOLE MOTSHEKGA PRIMARY SCHOOL | 700400080 | City of Johannesburg | Feasibility | Approved | 2019-04-01 |  | 2026-07-07 |  |  | 5900000 | 29400000 | 35300000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10278 | GDE00054 | Gauteng | DURBAN DEEP PRIMARY SCHOOL | 700251363 | City of Johannesburg | Design | Approved | 2018-07-31 |  | 2025-06-09 |  |  | 11301920 | 59335080 | 70637000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10289 | GDE00133 | Gauteng | KAALFONTEIN PRIMARY SCHOOL | 700400078 | City of Johannesburg | Feasibility | Approved | 2019-09-15 |  | 2026-01-09 |  |  | 6448160 | 33852840 | 40301000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10296 | GDE00224 | Gauteng | MAYIBUYE PRIMARY SCHOOL | N/A | City of Johannesburg | Design | Approved | 2018-08-01 |  | 2024-03-15 |  |  | 28423360 | 149222640 | 177646000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10315 | GDE00275 | Gauteng | PENNYVILLE PRIMARY SCHOOL | 700400534 | City of Johannesburg | Feasibility | Approved | 2017-04-01 |  | 2026-03-07 |  |  | 12325760 | 62904240 | 75230000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10327 | GDE00339 | Gauteng | SIMUNYE SECONDARY SCHOOL | 700400120 | Rand West City | Feasibility | Approved | 2017-04-01 |  | 2026-03-06 |  |  | 22403102 | 106503021 | 128906123 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10329 | GDE00341 | Gauteng | SIZUZILE PRIMARY | 700400401 | City of Ekurhuleni | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-06 |  |  | 8324760 | 43702240 | 52027000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10332 | GDE00346 | Gauteng | Soshanguve South Secondary School | 700400239 | City of Tshwane | Practical Completion (100%) | Approved | 2016-09-30 | 2018-02-02 | 2023-04-26 | 2023-05-27 | 2024-04-12 | 240000 | 1260000 | 1500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10338 | GDE00424 | Gauteng | WESTONARIA PRIMARY SCHOOL | 700270587 | Rand West City | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 11264287 | 59137511 | 70401798 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10343 | GDE00073 | Gauteng | EW HOBBS PRIMARY SCHOOL | 700120113 | City of Johannesburg | Design | Active - Not Contracted | 2016-08-01 |  | 2026-01-09 |  |  | 8045600 | 87539645 | 95585245 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10354 | GDE00193 | Gauteng | LEIHLO PRIMARY SCHOOL | 700121475 | City of Johannesburg | Feasibility | Active - Not Contracted | 2019-09-15 |  | 2026-03-06 |  |  | 5310920 | 27352080 | 32663000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10360 | GDE00247 | Gauteng | Nancefield Primary School | 700120261 | City of Johannesburg | Construction 1% - 25% | Approved | 2019-03-01 | 2019-08-15 | 2025-07-11 | 2025-09-19 | 2026-01-09 | 8194560 | 43021440 | 51216000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10363 | GDE00257 | Gauteng | NOORDGESIG PRIMARY SCHOOL | 700140079 | City of Johannesburg | Practical Completion (100%) | Approved | 2016-09-01 | 2017-04-15 | 2025-03-01 | 2025-03-15 | 2026-01-09 | 24198264 | 107639121 | 131907848 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10370 | GDE00310 | Gauteng | RIVERLEA PRIMARY SCHOOL | 700140103 | City of Johannesburg | Feasibility | Approved | 2019-09-15 |  | 2026-03-15 |  |  | 6054080 | 31783920 | 37838000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10374 | GDE00427 | Gauteng | WILHELMINA HOSKINS PRIMARY SCHOOL | 700141226 | City of Johannesburg | Project Initiation | Approved | 2019-09-15 |  | 2026-03-13 |  |  | 11120000 | 58380000 | 69500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10396 | GDE00301 | Gauteng | REFITHLILE PELE PRIMARY SCHOOL NO 1 | 700241158 | City of Tshwane | Tender | Approved | 2019-04-20 |  | 2025-05-09 |  |  | 4549280 | 57316720 | 61866000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10397 | GDE00332 | Gauteng | SEMPHATO PRIMARY SCHOOL | 700241265 | City of Tshwane | Tender | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 11521000 | 60488400 | 72009400 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10398 | GDE00336 | Gauteng | Setlabotjah Primary | 700321463 | Emfuleni | Tender | Active - Contracted | 2015-07-01 |  | 2023-12-08 |  |  | 13430000 | 70509000 | 83939000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10400 | GDE00368 | Gauteng | THOLIMFUNDO PRIMARY SCHOOL | 700111914 | City of Johannesburg | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 8500000 | 52500000 | 61000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10403 | GDE00175 | Gauteng | LAERSKOOL PARKSIG | 700320143 | Emfuleni | Feasibility | Proposed | 2022-04-15 |  | 2024-07-30 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10444 | GDE00079 | Gauteng | FJL WELLS PRIMARY SCHOOL | 700270710 | Rand West City | Design | Approved | 2019-11-05 |  | 2025-10-17 |  |  | 350000 | 1500000 | 1850000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10446 | GDE00080 | Gauteng | FOREST TOWN LSEN | 700130377 | City of Johannesburg | Feasibility | Active - Contracted | 2021-04-08 |  | 2026-01-16 |  |  | 2000000 | 10000000 | 12000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10535 | GDE00040 | Gauteng | RANT-EN-DAL KLINIEKSKOOL | 700260977 | Mogale City | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 3531040 | 26037960 | 29569000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10603 | GDE00001 | Gauteng | ABRAM HLOPHE PRIMARY SCHOOL | 700340380 | City of Ekurhuleni | Construction 76% - 99% | Active - Contracted | 2016-04-18 | 2017-07-17 | 2024-07-31 | 2024-06-14 | 2024-06-14 | 6060400 | 35571751 | 41632151 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10604 | GDE00005 | Gauteng | AHA-THUTO SECONDARY SCHOOL | 700330696 | City of Johannesburg | Project Initiation | Approved | 2019-09-15 |  | 2025-09-13 |  |  | 855040 | 6366731 | 7221771 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10605 | GDE00004 | Gauteng | AHANANG INTERMEDIATE SCHOOL | 700320267 | City of Johannesburg | Construction 51% - 75% | Active - Contracted | 2016-09-02 | 2016-09-05 | 2025-06-13 | 2025-07-20 | 2026-03-28 | 2717154 | 20861703 | 23578857 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10611 | GDE00007 | Gauteng | AMOS MAPHANGA SECONDARY | 700400398 | City of Ekurhuleni | Construction 1% - 25% | Approved | 2019-04-01 | 2019-06-20 | 2024-02-11 | 2024-02-11 | 2024-02-11 | 0 | 150000 | 150000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10626 | GDE00024 | Gauteng | Bovet Primary School | 700152041 | City of Johannesburg | Feasibility | Approved | 2018-11-28 |  | 2026-03-13 |  |  | 3728000 | 19572000 | 23300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10631 | GDE00029 | Gauteng | Carleton Jones High School | 700270041 | Merafong City | Practical Completion (100%) | Active - Contracted | 2014-03-04 | 2015-05-08 | 2025-03-31 | 2025-04-30 | 2025-06-30 | 377553 | 2097515 | 2475068 | Education Infrastructure Grant | Upgrading and Additions
|  | 10644 | GDE00049 | Gauteng | DITAU PRIMARY SCHOOL | 700132068 | City of Johannesburg | Feasibility | Approved | 2019-04-15 |  | 2025-03-09 |  |  | 3281760 | 17231240 | 20513000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10645 | GDE00051 | Gauteng | DR KNAK PRIMARY SCHOOL | 700152082 | City of Johannesburg | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 242400 | 7772600 | 8015000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10646 | GDE00062 | Gauteng | EDENPARK PRIMARY SCHOOL | 700340018 | City of Ekurhuleni | Construction 76% - 99% | Approved | 2019-03-15 | 2019-06-01 | 2023-12-31 | 2021-03-20 | 2024-03-28 | 109920 | 1177080 | 1287000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10650 | GDE00065 | Gauteng | EKUKHANYISWENI PRIMARY SCHOOL | 700152108 | City of Johannesburg | Feasibility | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1920000 | 10080000 | 12000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10658 | GDE00068 | Gauteng | Emelang Primary School | 700140483 | City of Johannesburg | Feasibility | Approved | 2020-04-01 |  | 2027-03-21 |  |  | 2080000 | 10920000 | 13000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10687 | GDE00222 | Gauteng | Matshediso Primary School | 700340893 | City of Ekurhuleni | Final Completion | Approved | 2017-04-01 | 2017-06-15 | 2022-04-12 | 2022-04-19 | 2022-08-14 | 1323389 | 6947793 | 8271182 | Education Infrastructure Grant | Upgrading and Additions
|  | 10696 | GDE00095 | Gauteng | HECTOR PETERSON PRIMARY SCHOOL | 700252056 | City of Johannesburg | Design | Approved | 2020-01-01 |  | 2026-03-13 |  |  | 242400 | 12272600 | 12515000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10699 | GDE00099 | Gauteng | Hoerskool Birchleigh | 700260109 | City of Ekurhuleni | Tender | Approved | 2019-04-12 |  | 2026-03-13 |  |  | 2752000 | 14448000 | 17200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10710 | GDE00118 | Gauteng | INXIWENI PRIMARY SCHOOL | 700260893 | City of Ekurhuleni | Practical Completion (100%) | Approved | 2016-08-01 | 2016-09-19 | 2022-04-12 | 2022-07-12 | 2022-08-12 | 789760 | 4146240 | 4936000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10722 | GDE00143 | Gauteng | KHULULEKANI PRIMARY SCHOOL | 700261520 | Mogale City | Feasibility | Approved | 2016-10-01 |  | 2026-03-31 |  |  | 6922400 | 36342600 | 43265000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10725 | GDE00149 | Gauteng | KLIPSPRUIT-WES SECONDARY SCHOOL | 700120188 | City of Johannesburg | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2019-05-24 | 2022-04-12 | 2022-06-05 | 2022-12-09 | 926880 | 2136120 | 3063000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10730 | GDE00169 | Gauteng | LAERSKOOL KAMEELFONTEIN | 700241620 | City of Tshwane | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2019-05-30 | 2022-06-15 | 2022-07-24 | 2025-03-19 | 0 | 345454 | 345454 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10732 | GDE00183 | Gauteng | LAERSKOOL VERKENNER | 700310565 | City of Ekurhuleni | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-13 |  |  | 4388800 | 23041200 | 27430000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10737 | GDE00189 | Gauteng | LAKESIDE PRIMARY SCHOOL | 700160044 | City of Ekurhuleni | Construction 1% - 25% | Approved | 2019-08-15 | 2020-12-17 | 2025-07-11 | 2025-09-19 | 2026-03-31 | 5292000 | 27783000 | 33075000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10746 | GDE00202 | Gauteng | Lodirile Primary School | 700261595 | City of Johannesburg | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 1784960 | 9694440 | 11479400 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10749 | GDE00205 | Gauteng | Lyttelton Primary School | 700210914 | City of Tshwane | Feasibility | Approved | 2019-04-20 |  | 2026-03-13 |  |  | 920000 | 4830000 | 5750000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10764 | GDE00230 | Gauteng | Mmabana Primary School | 700240978 | City of Tshwane | Construction 1% - 25% | Approved | 2019-10-01 | 2019-12-10 | 2023-04-13 | 2023-06-05 | 2026-03-13 | 0 | 100000 | 100000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10778 | GDE00165 | Gauteng | LAERSKOOL GENERAAL NICOLAAS SMIT | 700230888 | City of Tshwane | Feasibility | Proposed | 2022-04-01 |  | 2026-03-13 |  |  | 3000000 | 22000000 | 25000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10781 | GDE00256 | Gauteng | Noordgesig Secondary School | 700140087 | City of Johannesburg | Feasibility | Approved | 2019-04-01 |  | 2027-03-21 |  |  | 6917920 | 36319080 | 43237000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10804 | GDE00302 | Gauteng | Refithlile primary | 700911799 | City of Tshwane | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 0 | 8110000 | 8110000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10808 | GDE00317 | Gauteng | Roodepoort Primary | 700262221 | City of Johannesburg | Feasibility | Approved | 2021-04-01 |  | 2026-03-13 |  |  | 312960 | 1643040 | 1956000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10810 | GDE00325 | Gauteng | RUST-TER-VAAL SECONDARY SCHOOL | 700400673 | Emfuleni | Construction 1% - 25% | Approved | 2016-04-13 | 2016-09-15 | 2024-04-01 | 2024-05-09 | 2026-03-13 | 9851800 | 55049200 | 64901000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10825 | GDE00352 | Gauteng | St Asngers | 700152363 | Merafong City | Project Initiation | Approved | 2019-10-01 |  | 2026-03-13 |  |  | 2219520 | 11652480 | 13872000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10832 | GDE00365 | Gauteng | Thembelihle Primary School | 700311282 | City of Ekurhuleni | Design | Active - Not Contracted | 2020-04-01 |  | 2025-08-31 |  |  | 500000 | 3500000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10835 | GDE00372 | Gauteng | Thuto-Ke-Maatla Comprehensive School | 700261362 | City of Ekurhuleni | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 5120000 | 26880000 | 32000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10838 | GDE00376 | Gauteng | Tlhokomelo Primary | 700141044 | City of Johannesburg | Construction 1% - 25% | Approved | 2019-04-01 | 2020-03-01 | 2023-05-15 | 2023-09-09 | 2024-07-14 | 0 | 500000 | 500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10843 | GDE00383 | Gauteng | Tsako Thaba Secondary School | 700221143 | City of Tshwane | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 2080000 | 10920000 | 13000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10846 | GDE00385 | Gauteng | Tshepisa Primary | 700261396 | City of Ekurhuleni | Construction 76% - 99% | Active - Contracted | 2015-09-29 | 2015-11-01 | 2022-05-09 | 2023-05-28 | 2024-06-30 | 706000 | 3706000 | 4412000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10862 | GDE00426 | Gauteng | Westonaria Primary School | 700270587 | Rand West City | Project Initiation | Approved | 2022-07-06 |  | 2026-04-29 |  |  | 1648348 | 8653828 | 10302176 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10867 | GDE00369 | Gauteng | Thubelihle Primary School | 700132159 | City of Johannesburg | Tender | Active - Not Contracted | 2015-06-02 |  | 2023-10-16 |  |  | 4567200 | 23977800 | 28545000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10872 | GDE00403 | Gauteng | General services (Vacant Site Maint, Water supply, Sanitation) | GenMaintServ | City of Ekurhuleni | Construction 76% - 99% | Approved | 2017-04-01 | 2025-04-15 | 2026-03-31 | 2026-03-31 | 2027-03-12 | 0 | 8985000 | 8985000 | Education Infrastructure Grant | Non-Infrastructure
|  | 10874 | GDE00053 | Gauteng | DR. W.K. DU PLESSIS-SKOOL | 700350058 | City of Ekurhuleni | Tender | Approved | 2019-04-09 |  | 2025-05-07 |  |  | 7951840 | 41747160 | 49699000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10876 | GDE00322 | Gauteng | ROTARASKOOL | 700270538 | Merafong City | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 17534240 | 92054760 | 109589000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 10883 | GDE00044 | Gauteng | DELTAPARKSKOOL | 700150391 | City of Johannesburg | Construction 76% - 99% | Active - Contracted | 2015-08-15 | 2017-05-08 | 2022-11-09 | 2022-11-16 | 2025-03-21 | 3460000 | 60751796 | 64211796 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10885 | GDE00078 | Gauteng | Filadelfia LSEN School | 700240689 | City of Tshwane | Construction 1% - 25% | Approved | 2019-09-01 | 2019-09-25 | 2022-04-03 | 2022-07-15 | 2022-12-16 | 2240000 | 14760000 | 17000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10889 | GDE00286 | Gauteng | Prinshof LSEN School | 700232454 | City of Tshwane | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2019-09-15 | 2025-04-30 | 2025-05-15 | 2025-03-09 | 360000 | 1551000 | 1911000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10892 | GDE00122 | Gauteng | ITIRELENG PRIMARY SCHOOL | 700910568 | City of Tshwane | Tender | Active - Not Contracted | 2022-05-01 |  | 2025-12-15 |  |  | 800000 | 4200000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10909 | GDE00157 | Gauteng | LAERSKOOL BOEREFORT | 700230789 | City of Johannesburg | Feasibility | Proposed | 2022-04-01 |  | 2026-03-13 |  |  | 100000 | 900000 | 1000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 10914 | GDE00023 | Gauteng | BOSKOP PRIMARY SCHOOL | 700211300 | City of Tshwane | Tender | Approved | 2016-04-01 |  | 2026-03-13 |  |  | 3028000 | 16266000 | 19294000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10923 | GDE00030 | Gauteng | CHIVIRIKANI PRIMARY SCHOOL | 700340497 | City of Ekurhuleni | Tender | Approved | 2019-04-12 |  | 2026-03-13 |  |  | 1221490 | 14630510 | 15852000 | Education Infrastructure Grant | Upgrading and Additions
|  | 10929 | GDE00043 | Gauteng | Dan Pharasi Primary | 700310961 | City of Ekurhuleni | Project Initiation | Proposed | 2019-04-01 |  | 2025-09-12 |  |  | 1212000 | 4788000 | 6000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10948 | GDE00084 | Gauteng | FREEWAY PARK PRIMARY SCHOOL | 700160440 | City of Ekurhuleni | Feasibility | Approved | 2021-04-01 |  | 2025-07-25 |  |  | 3000 | 13000 | 16000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10981 | GDE00142 | Gauteng | KHOMBINDLELA PRIMARY SCHOOL | 700311191 | City of Ekurhuleni | Project Initiation | Proposed | 2022-04-01 |  | 2026-03-13 |  |  | 1000000 | 5000000 | 6000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 10982 | GDE00055 | Gauteng | EAST RAND SCHOOL OF ARTS LSEN | 700312124 | City of Johannesburg | Feasibility | Proposed | 2022-11-30 |  | 2025-08-08 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10984 | GDE00449 | Gauteng | Electrical @various schools | N/A | City of Ekurhuleni | Feasibility | Proposed | 2022-11-30 |  | 2026-01-09 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10985 | GDE00401 | Gauteng | Sanitation @various schools | N/A | Mogale City | Feasibility | Proposed | 2022-11-30 |  | 2025-07-18 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10986 | GDE00128 | Gauteng | JOHN MITCHELL PRIMARY SCHOOL | 700130690 | City of Ekurhuleni | Feasibility | Proposed | 2022-11-30 |  | 2026-03-13 |  |  | 100000 | 500000 | 600000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 10987 | GDE00111 | Gauteng | HOERSKOOL VANDERBIJLPARK | 700221226 | City of Tshwane | Feasibility | Proposed | 2022-11-30 |  | 2026-03-13 |  |  | 100000 | 900000 | 1000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 10988 | GDE00090 | Gauteng | GOUDWESSKOOL LSEN | 700270082 | City of Johannesburg | Feasibility | Proposed | 2022-11-30 |  | 2024-06-09 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10989 | GDE00404 | Gauteng | Borehole Panel @various schools | N/A | City of Tshwane | Project Initiation | Proposed | 2022-11-30 |  | 2025-05-09 |  |  | 100000 | 900000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10993 | GDE00159 | Gauteng | Laerskool Delville | 700160887 | City of Ekurhuleni | Project Initiation | Proposed | 2022-11-30 |  | 2025-05-09 |  |  | 1000000 | 9000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 10994 | GDE00160 | Gauteng | Laerskool Drie Riviere | 700330357 | Emfuleni | Design | Active - Not Contracted | 2019-05-31 |  | 2026-03-13 |  |  | 2539360 | 13331640 | 15871000 | Education Infrastructure Grant | Upgrading and Additions
|  | 11089 | GDE00314 | Gauteng | Robin Hills Primary | 700151415 | City of Johannesburg | Construction 51% - 75% | Active - Contracted | 2014-11-30 | 2015-04-01 | 2024-03-09 | 2024-03-28 | 2024-07-30 | 3000 | 13000 | 16000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 11124 | GDE00377 | Gauteng | Toekomsrus Primary-grade R | 700270033 | Rand West City | Project Initiation | Proposed | 2019-04-01 |  | 2026-03-13 |  |  | 2720000 | 14280000 | 17000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 11134 | GDE00419 | Gauteng | Villa Liza Primary School | 700160093 | City of Ekurhuleni | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 15520000 | 81480000 | 97000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 11149 | EDU/079/14MP | Mpumalanga | Temporary Accomodation (Mobile Classrooms) AFRICABIN | EDU/079/14MP | Emakhazeni | Site Handed - Over to Contractor | Active - Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 0 | 45178793 | 45178793 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 11152 | MDOE/GS/ALL/EQS/G&S/17-18/002 | Mpumalanga | EFMS | 0 | Emakhazeni | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2021-04-03 | 2025-03-31 | 2023-03-30 | 2023-03-28 | 11889200 | 0 | 11889200 | Education Infrastructure Grant | Non-Infrastructure
|  | 11154 | MDOE/GS/ALL/EIG/G&S/17-18/006 | Mpumalanga | COE | 0 | Emakhazeni | Other - Compensation of Employees | Active - Contracted | 2015-04-01 | 2015-04-02 | 2025-03-31 | 2024-03-31 | 2024-03-31 | 134000000 | 0 | 134000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 11167 | MDOE/GS/ALL/EPWP/G&S/17-18/007 | Mpumalanga | Data Capturing | 0 | Emakhazeni | Construction 26% - 50% | Active - Contracted | 2021-03-02 | 2021-03-07 | 2025-01-31 | 2023-04-01 | 2023-03-31 | 1816560 | 0 | 1816560 | Expanded Public Works Programme Intergrated Grant for Provinces | Non-Infrastructure
|  | 11168 | MDOE/P/NKA/EIG/NEW/17-18/231 ( PWRT/2327/17/MP) | Mpumalanga | New Klarinet Primary School (Mokgalithwa) | PWRT/2327/17/MP | Emalahleni | Construction 76% - 99% | Active - Contracted | 2017-11-23 | 2018-01-18 | 2023-03-31 | 2019-04-04 | 2022-03-31 | 7577000 | 47325895 | 54902895 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 11203 | MDOE//MAIN/116 | Mpumalanga | Izimbali Boarding School | 800035650 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2019-06-03 | 2019-09-11 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 247818 | 3478181 | 3725999 | Education Infrastructure Grant | Maintenance and Repairs
|  | 11556 | EDDP184/321 | Limpopo | MUTSETWENI PRIMARY | 912520740 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2014-05-01 | 2014-05-13 | 2024-12-30 | 2024-12-30 | 2024-12-30 | 1032000 | 4129000 | 5161000 | Education Infrastructure Grant | Upgrading and Additions
|  | 11558 | EDDP184/343 | Limpopo | Sinthumule Secondary School | 928332257 | Makhado | Final Completion | Active - Contracted | 2014-01-31 | 2014-02-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 4764800 | 19059200 | 23824000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12305 | I/500143782/UA | KwaZulu-Natal | EZULWINI PRIMARY SCHOOL | 500289599 | Ubuhlebezwe | Construction 76% - 99% | Active - Contracted | 2014-02-20 | 2017-11-30 | 2023-01-13 | 2022-05-15 | 2023-03-04 | 2329740 | 10613260 | 12943000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12307 | C/500110371/UA | KwaZulu-Natal | BIZIMALI SECONDARY SCHOOL (RE-TENDERED) | 500110371 | Nkandla | Practical Completion (100%) | Active - Contracted | 2013-04-01 | 2014-03-27 | 2023-03-02 | 2022-10-16 | 2023-12-31 | 1562205 | 15622049 | 17184254 | Education Infrastructure Grant | Upgrading and Additions
|  | 12308 | C/500113109/ECD | KwaZulu-Natal | BUHLEBELANGA PRIMARY SCHOOL | 500113109 | Ulundi | Practical Completion (100%) | Active - Contracted | 2012-02-04 | 2012-08-16 | 2023-02-11 | 2023-04-23 | 2023-06-23 | 298000 | 2340395 | 2638395 | Education Infrastructure Grant | Upgrading and Additions
|  | 12318 | C/500120472/ECD | KwaZulu-Natal | DAYISWAYO PRIMARY SCHOOL(RETENDER) | 500120472 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-06-05 | 2016-12-31 | 2023-12-31 | 2023-07-28 | 2023-07-28 | 351000 | 2343187 | 2694187 | Education Infrastructure Grant | Upgrading and Additions
|  | 12321 | C/500123765/UA | KwaZulu-Natal | DUFFS ROAD P (PHASE 2) (RETENDER) | 500123765 | eThekwini | Final Completion | Active - Contracted | 2013-05-15 | 2017-06-20 | 2023-11-20 | 2018-07-20 | 2023-11-20 | 3947647 | 11880641 | 15828288 | Education Infrastructure Grant | Upgrading and Additions
|  | 12327 | C/500126355/NS | KwaZulu-Natal | EBUHLENIBENKOSI INTERMEDIATE SCHOOL | 500126355 | Nongoma | Practical Completion (100%) | Active - Contracted | 2013-04-26 | 2014-04-26 | 2023-10-03 | 2023-10-03 | 2023-12-31 | 4292116 | 36343502 | 40635618 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12336 | C/500129870/ECD | KwaZulu-Natal | ELUDIMBI PRIMARY SCHOOL (RETENDER) | 500129870 | Alfred Duma | Design | Active - Not Contracted | 2015-01-31 |  | 2024-12-31 |  |  | 460360 | 1685703 | 2146063 | Education Infrastructure Grant | Upgrading and Additions
|  | 12340 | C/500132793/ECD | KwaZulu-Natal | EMHLUNGWINI PRIMARY SCHOOL(RETENDER) | 500132793 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2014-02-25 | 2014-07-01 | 2023-02-12 | 2018-05-13 | 2024-12-15 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12341 | C/500133015/ECD | KwaZulu-Natal | EMKHANDLWINI PRIMARY SCHOOL | 500133015 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2013-01-15 | 2013-01-20 | 2023-08-31 | 2021-08-31 | 2023-09-30 | 333000 | 2895610 | 3228610 | Education Infrastructure Grant | Upgrading and Additions
|  | 12342 | C/500134014/UA | KwaZulu-Natal | EMPATHE INTERMEDIATE SCHOOL (RE-TENDER) | 500134014 | Endumeni | Practical Completion (100%) | Active - Contracted | 2010-05-01 | 2013-04-03 | 2023-02-11 | 2017-10-11 | 2023-12-11 | 2000000 | 7000000 | 9000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12344 | C/500444407/ECD | KwaZulu-Natal | EMPOLOMBENI PRIMARY SCHOOL (RETENDER) | 500444407 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2013-05-04 | 2017-01-20 | 2022-12-20 | 2020-08-20 | 2024-12-20 | 500000 | 3853753 | 4353753 | Education Infrastructure Grant | Upgrading and Additions
|  | 12349 | C/500136493/LSEN | KwaZulu-Natal | ENGOLELENI PRIMARY SCHOOL (LSEN) (RETENDER) | 500136493 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2013-02-15 | 2013-11-02 | 2023-08-06 | 2018-06-23 | 2023-08-06 | 1692000 | 7706000 | 9398000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12352 | C/500138787/UA | KwaZulu-Natal | ENTWENI PRIMARY SCHOOL (RETENDER) | 500138787 | Mtubatuba | Final Completion | Active - Contracted | 2014-04-06 | 2015-04-01 | 2023-08-29 | 2018-04-30 | 2023-08-29 | 4018392 | 10609616 | 16187152 | Education Infrastructure Grant | Upgrading and Additions
|  | 12353 | C/500139453/ECD | KwaZulu-Natal | EQHWENI INTERMEDIATE SCHOOL (RETENDER) | 500139453 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2015-08-01 | 2016-04-01 | 2025-06-30 | 2020-03-30 | 2025-06-30 | 708000 | 3707872 | 4415872 | Education Infrastructure Grant | Upgrading and Additions
|  | 12365 | C/500145743/ECD | KwaZulu-Natal | FUNDANI PRIMARY SCHOOL (WEENEN)(RETENDER) | 500145743 | Alfred Duma | Final Completion | Active - Contracted | 2013-03-11 | 2016-04-20 | 2023-08-22 | 2024-10-20 | 2024-12-20 | 514024 | 2627080 | 3141104 | Education Infrastructure Grant | Upgrading and Additions
|  | 12368 | DB/500136641/WS | KwaZulu-Natal | ENGQONDWENI HIGH SCHOOL | 500136641 | Alfred Duma | Design | Active - Not Contracted | 2016-06-22 |  | 2024-03-30 |  |  | 1032408 | 2581020 | 3613428 | Education Infrastructure Grant | Upgrading and Additions
|  | 12369 | C/500150590/UA | KwaZulu-Natal | GOKUL PRIMARY SCHOOL (PHASE 2) | 500150590 | eThekwini | Final Completion | Active - Contracted | 2015-05-21 | 2016-10-20 | 2023-06-20 | 2024-10-20 | 2024-12-20 | 668520 | 3045480 | 3714000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12381 | C/500159507/ECD | KwaZulu-Natal | IFAFA JUNIOR PRIMARY SCHOOL | 500159507 | Umdoni | Practical Completion (100%) | Active - Contracted | 2013-01-10 | 2013-05-18 | 2022-11-10 | 2020-10-10 | 2024-11-10 | 900256 | 4816862 | 5717118 | Education Infrastructure Grant | Upgrading and Additions
|  | 12387 | C/500165390/ECD | KwaZulu-Natal | INQANULA PRIMARY SCHOOL(RETENDER) | 500165390 | Umdoni | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2017-01-20 | 2022-06-20 | 2020-08-20 | 2024-06-20 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12393 | C/500168054/UA | KwaZulu-Natal | ISIKHALASENKOSI JS SCHOOL (PHASE 2) | 500168054 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-02-01 | 2022-08-06 | 2023-03-30 | 2024-03-30 | 2024-09-01 | 761220 | 3467780 | 4229000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12397 | C/500425870/UA | KwaZulu-Natal | JIRAH PRIMARY SCHOOL ( PHASE 3) | 500425870 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2013-06-21 | 2016-05-20 | 2022-09-20 | 2017-10-20 | 2024-09-20 | 700000 | 3235224 | 3935224 | Education Infrastructure Grant | Upgrading and Additions
|  | 12413 | C/500179746/ECD | KwaZulu-Natal | KWAHLONGWA PRIMARY SCHOOL (RETENDER) | 500179746 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2013-08-15 | 2017-01-20 | 2022-11-20 | 2022-01-20 | 2024-11-20 | 669050 | 1672625 | 2341675 | Education Infrastructure Grant | Upgrading and Additions
|  | 12414 | C/500180190/LSEN | KwaZulu-Natal | KWAMADLALA PRIMARY SCHOOL | 500180190 | The Msunduzi | Final Completion | Active - Contracted | 2012-06-01 | 2013-05-27 | 2023-09-01 | 2017-09-01 | 2026-09-01 | 3349315 | 25763958 | 29113273 | Education Infrastructure Grant | Upgrading and Additions
|  | 12417 | C/500183298/ECD | KwaZulu-Natal | KWASENGE PRIMARY SCHOOL (RETENDER) | 500183298 | Umvoti | Final Completion | Active - Contracted | 2012-06-30 | 2015-04-01 | 2023-03-31 | 2020-07-28 | 2024-12-28 | 673063 | 2058392 | 2731455 | Education Infrastructure Grant | Upgrading and Additions
|  | 12420 | C/500184408/ECD | KwaZulu-Natal | KWELIFUPHI PRIMARY SCHOOL (RETENDER) | 500184408 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2014-06-30 | 2016-04-01 | 2023-08-31 | 2018-03-30 | 2024-12-30 | 431460 | 2399215 | 2830675 | Education Infrastructure Grant | Upgrading and Additions
|  | 12426 | C/500190550/UA | KwaZulu-Natal | MACEKANE PRIMARY SCHOOL (RE-TENDER) | 500190550 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2014-02-05 | 2015-11-11 | 2022-06-01 | 2022-06-01 | 2024-06-29 | 2720000 | 12392000 | 15112000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12427 | C/500190846/ECD | KwaZulu-Natal | MACONGCO PRIMARY SCHOOL (RETENDER) | 500190846 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-01-20 | 2016-04-20 | 2023-01-21 | 2022-03-20 | 2024-12-20 | 742670 | 1880178 | 2622848 | Education Infrastructure Grant | Upgrading and Additions
|  | 12434 | C/500426462/ECD | KwaZulu-Natal | MAHOBE JUNIOR SECONDARY SCHOOL (RETENDER) | 500426462 | Umzimkhulu | Final Completion | Active - Contracted | 2014-04-06 | 2016-04-20 | 2023-07-31 | 2018-08-20 | 2024-10-30 | 458117 | 2811628 | 3269745 | Education Infrastructure Grant | Upgrading and Additions
|  | 12451 | C/500504014/NS | KwaZulu-Natal | MBONGELENI PRIMARY SCHOOL | 500204758 | Msinga | Final Completion | Active - Contracted | 2012-06-05 | 2013-05-31 | 2023-09-01 | 2017-09-01 | 2024-12-31 | 4418820 | 20130180 | 24549000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12452 | W/500187886/SDS | KwaZulu-Natal | LOWER TUGELA PRIMARY SCHOOL | 500187886 | Mandeni | Practical Completion (100%) | Active - Contracted | 2011-01-13 | 2012-02-28 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 33998 | 328467 | 362465 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12461 | C/500211529/ECD | KwaZulu-Natal | MJWAYELI PRIMARY SCHOOL | 500211529 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2014-04-09 | 2014-10-30 | 2023-03-15 | 2022-03-19 | 2024-11-30 | 919377 | 3643567 | 4562944 | Education Infrastructure Grant | Upgrading and Additions
|  | 12462 | DB/500211973/SDS | KwaZulu-Natal | MKHOBOSA PRIMARY SCHOOL | 500211973 | uMhlathuze | Design | Active - Contracted | 2017-01-11 |  | 2024-01-29 |  |  | 360000 | 1640000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 12473 | C/500445924/ECD | KwaZulu-Natal | MTHIYANE PRIMARY SCHOOL (RETENDER) | 500445924 | Inkosi Langalibalele | Design | Active - Not Contracted | 2015-05-03 |  | 2024-04-11 |  |  | 399000 | 1821000 | 2220000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12477 | C/500221075/UA | KwaZulu-Natal | MUZIWEPHAHLA SECONDARY SCHOOL | 500221075 | Abaqulusi | Final Completion | Active - Contracted | 2012-02-15 | 2012-07-09 | 2023-06-15 | 2020-01-18 | 2024-03-29 | 1105000 | 5036000 | 7105051 | Education Infrastructure Grant | Upgrading and Additions
|  | 12482 | C/500306064/ECD | KwaZulu-Natal | NGOLOSHINI PRIMARY SCHOOL (RETENDER) | 500306064 | eThekwini | Final Completion | Active - Contracted | 2014-08-31 | 2019-09-28 | 2023-03-31 | 2020-11-20 | 2024-05-20 | 329000 | 2397665 | 2726665 | Education Infrastructure Grant | Upgrading and Additions
|  | 12485 | C/500230436/UA | KwaZulu-Natal | NHLOSHANE PRIMARY SCHOOL | 500230436 | Nkandla | Final Completion | Active - Contracted | 2010-05-01 | 2011-05-01 | 2023-02-28 | 2014-02-28 | 2024-02-28 | 2905134 | 7081376 | 11640878 | Education Infrastructure Grant | Upgrading and Additions
|  | 12489 | C/500232064/UA | KwaZulu-Natal | NKODIBE SECONDARY SCHOOL | 500232064 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2012-03-01 | 2013-03-01 | 2023-11-30 | 2018-11-30 | 2023-11-30 | 1301541 | 3253853 | 4555394 | Education Infrastructure Grant | Upgrading and Additions
|  | 12497 | C/500235061/LSEN | KwaZulu-Natal | NOMPONDO PRIMARY SCHOOL | 500235061 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2012-02-17 | 2013-02-11 | 2023-08-31 | 2022-08-31 | 2023-08-31 | 2580000 | 4523000 | 7103000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12501 | C/500236689/UA | KwaZulu-Natal | NOTHANDO SECONDARY SCHOOL | 500236689 | Umhlabuyalingana | Final Completion | Active - Contracted | 2013-04-05 | 2014-04-05 | 2023-12-01 | 2018-05-07 | 2024-09-07 | 1014000 | 4621000 | 5635000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12522 | C/500245532/ECD | KwaZulu-Natal | OVICENI PRIMARY SCHOOL | 500245532 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2012-11-01 | 2015-11-30 | 2023-09-20 | 2016-09-30 | 2023-12-27 | 321000 | 3016928 | 3337928 | Education Infrastructure Grant | Upgrading and Additions
|  | 12523 | C/500247123/LSEN | KwaZulu-Natal | PETER PAN | 500247123 | The Msunduzi | Construction 76% - 99% | Active - Contracted | 2012-04-01 | 2013-04-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 1747846 | 9710258 | 11458104 | Education Infrastructure Grant | Upgrading and Additions
|  | 12524 | C/500247456/UA | KwaZulu-Natal | PHALANE P (KWADLANGEZWA) | 500247456 | uMhlathuze | Final Completion | Active - Contracted | 2011-02-26 | 2011-05-01 | 2023-03-02 | 2017-03-02 | 2024-10-02 | 5333250 | 13000000 | 19552262 | Education Infrastructure Grant | Upgrading and Additions
|  | 12530 | C/500252340/ECD | KwaZulu-Natal | QANDA PRIMARY SCHOOL (RETENDER) | 500252340 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2014-09-17 | 2016-10-20 | 2023-10-24 | 2017-11-20 | 2023-12-20 | 840440 | 4361395 | 5201835 | Education Infrastructure Grant | Upgrading and Additions
|  | 12550 | C/500272912/ECD | KwaZulu-Natal | SOMANGWE PRIMARY SCHOOL (RETENDER) | 500272912 | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2014-09-03 | 2015-08-21 | 2023-08-31 | 2016-09-29 | 2024-10-20 | 608058 | 2846109 | 3454167 | Education Infrastructure Grant | Upgrading and Additions
|  | 12552 | C/500274022/ECD | KwaZulu-Natal | SOSUKWANA PRIMARY SCHOOL | 500274022 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2013-02-10 | 2020-06-10 | 2023-09-11 | 2020-06-23 | 2023-12-01 | 934426 | 2336065 | 3270491 | Education Infrastructure Grant | Upgrading and Additions
|  | 12565 | C/500440152/LSEN | KwaZulu-Natal | UKUKHANYA KOMSINGA SPECIAL SCHOOL LSEN | 500440152 | Msinga | Practical Completion (100%) | Active - Contracted | 2012-08-26 | 2013-08-21 | 2023-12-31 | 2018-09-02 | 2023-12-31 | 18869000 | 85957000 | 104826000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12569 | C/500288859/NS | KwaZulu-Natal | UMSILINGA PRIMARY SCHOOL | 500288859 | The Msunduzi | Construction 76% - 99% | Active - Contracted | 2012-02-24 | 2018-02-28 | 2023-12-31 | 2021-12-31 | 2023-12-31 | 7505000 | 34192000 | 41697000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12571 | C/500288790/ECD | KwaZulu-Natal | UMSWILILI PRIMARY SCHOOL (RETENDER) | 500288970 | Umzumbe | Final Completion | Active - Contracted | 2014-12-01 | 2017-01-20 | 2023-10-20 | 2017-11-20 | 2024-12-20 | 833102 | 2082756 | 2915858 | Education Infrastructure Grant | Upgrading and Additions
|  | 12576 | DB/500291153/WS | KwaZulu-Natal | VELAKUKHANYA PRIMARY SCHOOL | 500291153 | Jozini | Design | Active - Not Contracted | 2016-06-06 |  | 2025-06-14 |  |  | 373029 | 1008185 | 1381214 | Education Infrastructure Grant | Upgrading and Additions
|  | 12588 | C/500296777/ECD | KwaZulu-Natal | WOLWENI PRIMARY SCHOOL (RETENDER) | 500296777 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2014-06-12 | 2016-06-20 | 2023-11-20 | 2017-11-20 | 2023-11-20 | 519523 | 2826074 | 3345597 | Education Infrastructure Grant | Upgrading and Additions
|  | 12601 | C/500311577/UA | KwaZulu-Natal | ZIZAMELE JUNIOR SECONDARY SCHOOL | 500311577 | eThekwini | Final Completion | Active - Contracted | 2011-06-09 | 2011-07-17 | 2023-12-10 | 2020-11-10 | 2024-12-10 | 4606040 | 9881520 | 15812806 | Education Infrastructure Grant | Upgrading and Additions
|  | 12606 | I/500103748/CU | KwaZulu-Natal | ASHDOWN PRIMARY SCHOOL | 500103748 | The Msunduzi | Design | Active - Contracted | 2015-02-17 |  | 2024-03-16 |  |  | 2300760 | 10956000 | 13256760 | Equitable Share | Upgrading and Additions
|  | 12614 | DB/500414400/WS | KwaZulu-Natal | DLANGAMANDLA PRIMARY SCHOOL | 500414400 | Umzimkhulu | Design | Active - Contracted | 2016-06-06 |  | 2024-03-20 |  |  | 2100000 | 10000000 | 12100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12615 | I/500123654/UA | KwaZulu-Natal | DUDUDU JUNIOR PRIMARY SCHOOL | 500123654 | Umdoni | On Hold | Active - Contracted | 2015-03-01 |  | 2024-03-31 |  |  | 1519056 | 7233600 | 8752656 | Education Infrastructure Grant | Upgrading and Additions
|  | 12616 | I/500407037/UA | KwaZulu-Natal | DUDUZILE SECONDARY SCHOOL | 500407037 | Ray Nkonyeni | Design | Active - Contracted | 2015-02-05 |  | 2026-03-01 |  |  | 1575540 | 7177460 | 8753000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12618 | I/500424612/NS | KwaZulu-Natal | EBUTA JUNIOR SECONDARY SCHOOL | 500424612 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2015-02-11 | 2015-05-06 | 2023-01-02 | 2022-06-29 | 2023-09-06 | 5932000 | 27021000 | 32953000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12627 | I/500152218/UA | KwaZulu-Natal | GROUTVILLE H | 500152218 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2012-10-13 | 2013-10-08 | 2023-12-02 | 2017-12-02 | 2022-12-02 | 6004727 | 28593940 | 34598667 | Education Infrastructure Grant | Upgrading and Additions
|  | 12630 | I/500155807/FSS | KwaZulu-Natal | HIMMELBERG PRIMARY SCHOOL | 500155807 | Umdoni | Project Initiation | Proposed | 2018-01-21 |  | 2024-11-22 |  |  | 403735 | 3130265 | 3534000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12639 | I/500169497/CU | KwaZulu-Natal | ITHALA H | 500169497 | Nkandla | Practical Completion (100%) | Active - Contracted | 2010-08-11 | 2011-10-12 | 2023-01-13 | 2018-01-13 | 2023-10-15 | 1080214 | 4962922 | 6043136 | Equitable Share | Upgrading and Additions
|  | 12647 | IDT/180967/11/NSP | KwaZulu-Natal | NEW KWAMBONAMBI SECONDARY SCHOOL | 500180967 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2012-01-03 | 2022-01-09 | 2023-03-10 | 2022-04-03 | 2023-09-30 | 10898640 | 49649360 | 60548000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12650 | DB/500228623/SDS | KwaZulu-Natal | NGOZA PRIMARY SCHOOL | 500228623 | Ulundi | Practical Completion (100%) | Active - Contracted | 2018-06-22 | 2019-01-08 | 2022-07-07 | 2022-09-30 | 2025-12-31 | 1401929 | 6386567 | 7788496 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12652 | I/500441669/UA | KwaZulu-Natal | LUBELO SECONDARY SCHOOL | 500441669 | Jozini | Practical Completion (100%) | Active - Contracted | 2012-10-15 | 2013-10-10 | 2023-11-26 | 2018-11-26 | 2023-12-31 | 2133094 | 10157591 | 12290685 | Education Infrastructure Grant | Upgrading and Additions
|  | 12654 | I/500191586/UA | KwaZulu-Natal | MADWALENI SECONDARY SCHOOL | 500191586 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2011-09-12 | 2012-09-06 | 2023-06-01 | 2017-06-01 | 2023-06-01 | 2030428 | 9668703 | 11699131 | Education Infrastructure Grant | Upgrading and Additions
|  | 12655 | I/500415066/UA | KwaZulu-Natal | MAHLOKOHLOKO SECONDARY SCHOOL | 500415066 | Msinga | Construction 76% - 99% | Active - Contracted | 2015-05-05 | 2015-08-30 | 2023-05-18 | 2018-02-23 | 2023-05-18 | 3162600 | 14407400 | 17570000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12659 | I/500337144/NS | KwaZulu-Natal | MALUSI HIGH SCHOOL | 500337144 | Ubuhlebezwe | Final Completion | Active - Contracted | 2012-10-03 | 2022-12-28 | 2023-09-03 | 2023-10-03 | 2024-11-03 | 5731395 | 35821942 | 41553337 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12660 | I/500201724/UA | KwaZulu-Natal | MATHIYA PRIMARY SCHOOL | 500201724 | Nkandla | Practical Completion (100%) | Active - Contracted | 2014-09-21 | 2014-10-16 | 2023-08-31 | 2017-09-21 | 2026-03-31 | 3011940 | 13721060 | 16733000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12661 | DB/500315721/WS | KwaZulu-Natal | MATHUBU PRIMARY SCHOOL | 500315721 | uMlalazi | Design | Active - Contracted | 2012-02-16 |  | 2024-10-22 |  |  | 300060 | 1366940 | 1667000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12663 | I/500206349/NS | KwaZulu-Natal | MDOMBOLO PRIMARY SCHOOL | 500206349 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-05-06 | 2023-12-02 | 2023-12-02 | 2024-12-02 | 2024-12-02 | 4760411 | 26070160 | 30830571 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12666 | I/500210382/CU | KwaZulu-Natal | MHLANGEZULU S | 500210382 | Msinga | Construction 76% - 99% | Active - Contracted | 2010-02-13 | 2017-02-08 | 2023-10-01 | 2018-10-01 | 2023-03-31 | 1221791 | 5553593 | 6775384 | Equitable Share | Upgrading and Additions
|  | 12668 | I/500213712/ECD | KwaZulu-Natal | MNTIMANDE P | 500213712 | Newcastle | Practical Completion (100%) | Active - Contracted | 2013-01-09 | 2013-01-16 | 2023-10-19 | 2018-10-19 | 2023-10-19 | 428000 | 1951000 | 2379000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12669 | DB/500217153/WS | KwaZulu-Natal | MPOLWENI SECONDARY SCHOOL | 500217153 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2020-01-11 | 2025-07-05 | 2022-05-20 | 2027-07-05 | 338964 | 1544169 | 1883133 | Education Infrastructure Grant | Upgrading and Additions
|  | 12677 | I/500231731/CU | KwaZulu-Natal | NKANYISO H | 500231731 | Nkandla | Construction 76% - 99% | Active - Contracted | 2013-02-25 | 2013-07-28 | 2023-08-25 | 2017-08-21 | 2023-08-25 | 650540 | 2956999 | 3607539 | Education Infrastructure Grant | Upgrading and Additions
|  | 12679 | I/500407074/UA | KwaZulu-Natal | NONGWINYA P | 500407074 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2014-09-12 | 2015-10-06 | 2023-03-28 | 2018-03-28 | 2023-07-25 | 2374234 | 11305875 | 13680109 | Education Infrastructure Grant | Upgrading and Additions
|  | 12681 | I/500427572/NS | KwaZulu-Natal | NTSHONGO JUNIOR SECONDARY SCHOOL | 500427572 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2015-05-05 | 2022-09-10 | 2022-11-09 | 2023-01-15 | 2023-03-30 | 3342240 | 15345542 | 18687782 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12686 | I/500326488/WS | KwaZulu-Natal | GQOKAMANDLA SECONDARY SCHOOL | 500326488 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-12-01 | 2017-06-30 | 2023-07-01 | 2023-09-01 | 2023-10-30 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12691 | W/500252192/WS | KwaZulu-Natal | QALIMFUNDO PRRIMARY SCHOOL | 500252192 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-05-25 | 2015-06-30 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 213000 | 1828002 | 2041002 | Education Infrastructure Grant | Upgrading and Additions
|  | 12692 | I/500252673/CU | KwaZulu-Natal | QHAMUKA SECONDARY SCHOOL | 500252673 | uMhlathuze | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2016-02-17 | 2023-03-25 | 2016-10-25 | 2023-03-25 | 1148400 | 5231600 | 6380000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12700 | I/500276945/UA | KwaZulu-Natal | ST VICTOR SECONDARY SCHOOL | 500276945 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-10-06 | 2016-10-15 | 2023-03-30 | 2019-03-20 | 2023-03-30 | 4678000 | 21309000 | 25987000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12702 | IDT/MOBILE/Various Districts | KwaZulu-Natal | SUPPLY OF MOBILE CLASSROOMS VARIOUS SCHOOLS | 500000000 | uMngeni | Construction 76% - 99% | Active - Contracted | 2014-04-07 | 2014-04-22 | 2024-12-30 | 2024-12-30 | 2024-12-30 | 89352000 | 613856563 | 703208563 | Equitable Share | Upgrading and Additions
|  | 12713 | W/500101047/RRR | KwaZulu-Natal | ALSTONE PRIMARY SCHOOL | 500101047 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2014-02-05 | 2014-09-30 | 2024-06-01 | 2023-06-30 | 2022-04-20 | 2302167 | 15345541 | 17647708 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12715 | W/500204092/UA | KwaZulu-Natal | MBEKAMUSI PRIMARY SCHOOL | 500204092 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2011-08-20 | 2012-08-14 | 2023-04-01 | 2018-09-01 | 2023-04-01 | 4156000 | 18931000 | 23856314 | Education Infrastructure Grant | Upgrading and Additions
|  | 12716 | W/500262515/UA | KwaZulu-Natal | SIBAMBANEZULU HIGH SCHOOL - ISIPINGO | 500262515 | eThekwini | Practical Completion (100%) | Active - Contracted | 2011-06-27 |  | 2023-06-30 |  |  | 5250000 | 20250000 | 25788094 | Education Infrastructure Grant | Upgrading and Additions
|  | 12717 | W/500267399/UA | KwaZulu-Natal | SIPHESIHLE HIGH SCHOOL | 500267399 | eThekwini | Practical Completion (100%) | Active - Contracted | 2011-10-07 | 2012-10-01 | 2023-06-30 | 2023-04-28 | 2019-03-29 | 4341000 | 19777000 | 25025928 | Equitable Share | Upgrading and Additions
|  | 12718 | W/500333814/UA | KwaZulu-Natal | LANGA JUNIOR SECONDARY SCHOOL | 500333814 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2011-10-24 | 2012-10-18 | 2023-03-03 | 2022-03-03 | 2023-03-03 | 1000000 | 5000000 | 7702432 | Education Infrastructure Grant | Upgrading and Additions
|  | 12719 | W/500205350/UA | KwaZulu-Natal | MBUYISELO HIGH SCHOOL | 500205350 | Mandeni | Practical Completion (100%) | Active - Contracted | 2013-02-15 | 2018-02-01 | 2023-05-31 | 2018-03-30 | 2023-05-31 | 1396000 | 12159000 | 13555000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12723 | W/500302808/UA | KwaZulu-Natal | MANZINI SECONDARY SCHOOL | 500302808 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-02-20 | 2015-09-28 | 2023-03-01 | 2022-03-01 | 2023-03-01 | 1360000 | 6197000 | 7778687 | Education Infrastructure Grant | Upgrading and Additions
|  | 12724 | W/500277648/UA | KwaZulu-Natal | STANMORE SECONDARY SCHOOL | 500277648 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-03-18 | 2015-03-12 | 2023-06-30 | 2016-08-31 | 2023-05-31 | 3122000 | 14221000 | 17343000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12726 | DB/500130573/WS | KwaZulu-Natal | EMAGOVINI PRIMARY SCHOOL | 500130573 | eDumbe | Practical Completion (100%) | Active - Contracted | 2015-12-04 | 2016-07-01 | 2024-03-16 | 2018-01-31 | 2024-03-16 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12728 | W/500294705/UA | KwaZulu-Natal | WATERFALL COMBINED PRIMARY SCHOOL | 500294705 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2016-09-18 | 2022-07-20 | 2022-09-20 | 2027-05-31 | 2430000 | 11075000 | 13505000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12729 | W/500130351/RRR | KwaZulu-Natal | EMAFA PRIMARY SCHOOL | 500130351 | Umhlabuyalingana | Final Completion | Active - Contracted | 2011-10-10 | 2013-11-10 | 2023-11-01 | 2016-11-09 | 2023-11-11 | 5701737 | 25974581 | 31676318 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12734 | W/500222037/UA | KwaZulu-Natal | MZILA PRIMARY SCHOOL | 500222037 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2007-01-31 | 2008-01-31 | 2024-03-30 | 2023-06-30 | 2022-03-18 | 2800000 | 5500000 | 8300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12735 | W/500273874/UA | KwaZulu-Natal | SONYONGWANA HIGH SCHOOL | 500273874 | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2015-07-01 | 2015-10-06 | 2024-03-30 | 2023-06-30 | 2021-05-31 | 2998000 | 13660000 | 16721693 | Education Infrastructure Grant | Upgrading and Additions
|  | 12736 | W/500232730/UA | KwaZulu-Natal | NKOSINATHI SECONDARY SCHOOL | 500232730 | eThekwini | Practical Completion (100%) | Active - Contracted | 2010-10-11 | 2013-12-11 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 745000 | 3395000 | 4903481 | Education Infrastructure Grant | Upgrading and Additions
|  | 12737 | W/500147556/UA | KwaZulu-Natal | GCINIMFUNDO SECONDARY SCHOOL | 500147556 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2011-04-30 | 2013-05-02 | 2023-05-01 | 2018-05-01 | 2024-05-28 | 861000 | 3921000 | 4782000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12738 | W/500274059/UA | KwaZulu-Natal | SOTOBE SECONDARY SCHOOL | 500274059 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-09-28 | 2016-01-12 | 2023-06-30 | 2017-03-31 | 2025-05-31 | 476000 | 2167000 | 2643000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12739 | W/500218707/RRR | KwaZulu-Natal | MSITHA PRIMARY SCHOOL | 500218707 | Msinga | Feasibility | Active - Contracted | 2015-02-11 |  | 2024-03-20 |  |  | 540000 | 2460000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12740 | W/500171643/RRR | KwaZulu-Natal | JONGIMFUNDO PRIMARY SCHOOL (COMPLETION CONTRACT) | 500171643 | Ulundi | Practical Completion (100%) | Active - Contracted | 2014-04-11 | 2014-12-01 | 2023-09-04 | 2023-09-04 | 2023-05-31 | 1046000 | 4763000 | 5809000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12742 | W/500197321/RRR | KwaZulu-Natal | MANQINDI JUNIOR PRIMARY SCHOOL (COMPLETION CONTRACT) | 500197321 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2014-08-11 | 2014-08-31 | 2022-08-31 | 2022-08-31 | 2023-08-31 | 355000 | 1616000 | 1971000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12743 | W/500235357/RRR | KwaZulu-Natal | NONDUMISO SECONDARY SCHOOL | 500235357 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2013-11-26 | 2013-11-30 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 1269000 | 5781000 | 7050000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12745 | DB/500296814/WS | KwaZulu-Natal | WOMBANE PRIMARY SCHOOL | 500296814 | uMlalazi | Design | Active - Contracted | 2017-06-06 |  | 2027-04-30 |  |  | 1505000 | 1825000 | 3330000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12747 | DB/500234876/SDS | KwaZulu-Natal | NOMBUSO HIGH SCHOOL | 50023487 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2017-09-03 | 2018-01-12 | 2024-03-28 | 2024-06-30 | 2025-06-30 | 267953 | 2095047 | 2363000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12748 | W/500414437/UA | KwaZulu-Natal | SEKUSILE PRIMARY SCHOOL | 500414437 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-09-20 | 2016-03-21 | 2022-05-20 | 2018-08-01 | 2023-05-31 | 2088000 | 9512000 | 11600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12754 | W/500296851/UA | KwaZulu-Natal | WOOD AND RAW PRIMARY SCHOOL | 500296851 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2014-06-09 | 2015-06-09 | 2022-11-13 | 2022-01-13 | 2027-05-31 | 360000 | 1640000 | 3843361 | Education Infrastructure Grant | Upgrading and Additions
|  | 12758 | I/500105006/UA | KwaZulu-Natal | BAMBANANI H | 500105006 | uPhongolo | Design | Active - Not Contracted | 2015-11-20 |  | 2026-03-30 |  |  | 6531000 | 29755000 | 36286000 | Equitable Share | Upgrading and Additions
|  | 12760 | DB/500263958/SDS | KwaZulu-Natal | SIDELILE SECONDARY SCHOOL | 500263958 | eThekwini | Construction 76% - 99% | Active - Contracted | 2020-03-06 | 2020-08-14 | 2023-08-25 | 2023-11-23 | 2025-02-20 | 1092994 | 4979195 | 6072189 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12768 | C/500444925/NS | KwaZulu-Natal | VIMBUKHALO PRIMARY SCHOOL | 500292411 | Umhlabuyalingana | Design | Active - Not Contracted | 2016-01-24 | 2022-02-24 | 2022-09-02 | 2022-09-02 | 2025-09-02 | 2496782 | 25592233 | 28089015 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12773 | I/500137677/WS | KwaZulu-Natal | ENKONJENI PRIMARY SCHOOL | 500137677 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-11 | 2016-11-21 | 2023-04-28 | 2017-06-30 | 2023-04-28 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12785 | DB/500262478/SDS | KwaZulu-Natal | SHWASHWENI PRIMARY SCHOOL | 500262478 | Mfolozi | Design | Active - Contracted | 2015-11-20 |  | 2024-09-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12789 | W/500105820/WS | KwaZulu-Natal | BAQAQE PRIMARY SCHOOL | 500105820 | uMlalazi | Tender | Active - Contracted | 2012-12-12 |  | 2025-04-11 |  |  | 69313 | 315761 | 385074 | Equitable Share | Upgrading and Additions
|  | 12790 | DB/500144522/SDS | KwaZulu-Natal | FANGELAKHE PRIMARY SCHOOL | 500144522 | Nkandla | Project Initiation | Active - Contracted | 2017-06-13 |  | 2027-03-30 |  |  | 360000 | 1640000 | 2797550 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12791 | I/500270766/WS | KwaZulu-Natal | SIYEZA PRIMARY SCHOOL | 500270766 | uPhongolo | Construction 76% - 99% | Active - Contracted | 2016-06-23 | 2017-02-28 | 2024-04-10 | 2018-01-31 | 2024-04-10 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12794 | W/500293484/RRR | KwaZulu-Natal | VULEKA SCHOOL FOR THE DEAF | 500293484 | Nkandla | Practical Completion (100%) | Active - Contracted | 2012-04-02 | 2013-04-22 | 2022-11-27 | 2022-10-14 | 2025-04-20 | 3482049 | 13712642 | 17410247 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12806 | DB/500217708/WS | KwaZulu-Natal | MQAMU PRIMARY SCHOOL | 500217708 | Msinga | Construction 76% - 99% | Active - Contracted | 2010-10-11 | 2020-05-31 | 2025-01-30 | 2022-01-30 | 2027-01-30 | 388689 | 1770695 | 2159384 | Education Infrastructure Grant | Upgrading and Additions
|  | 12807 | DB/500239131/WS | KwaZulu-Natal | NTALANTALA S | 231065/ASIDI | Nqutu | Design | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 661860 | 3015140 | 3677000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12808 | DB/500237540/WS | KwaZulu-Natal | NQUMIZWE SECONDARY SCHOOL | 500237540 | uMlalazi | Design | Proposed | 2015-11-20 |  | 2025-03-31 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12809 | DB/500156103/SDS | KwaZulu-Natal | HLALANATHI HIGH SCHOOL | 500156103 | Newcastle | Final Completion | Approved | 2022-05-03 | 2022-05-10 | 2023-05-20 | 2023-05-20 | 2023-08-20 | 463028 | 1741868 | 2204896 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12811 | W/500287305/RRR | KwaZulu-Natal | UMFOLOZI SECONDARY SCHOOL | 500260147 | Umhlabuyalingana | Feasibility | Active - Contracted | 2015-11-20 |  | 2024-03-30 |  |  | 2306000 | 3706000 | 6012000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12815 | W/500257076/SDS | KwaZulu-Natal | SABELA HIGH SCHOOL | 500257076 | Newcastle | Practical Completion (100%) | Active - Contracted | 2006-08-30 | 2007-08-30 | 2023-02-28 | 2011-03-15 | 2023-05-31 | 100000 | 2000000 | 2100000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12816 | W/500261997/RRR | KwaZulu-Natal | SHESHISAMSAMO PRIMARY SCHOOL | 500261997 | Umvoti | Practical Completion (100%) | Active - Contracted | 2007-02-25 | 2007-09-25 | 2024-03-30 | 2023-06-30 | 2019-03-31 | 295000 | 1344000 | 1639000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12831 | DB/500213897/SDS | KwaZulu-Natal | NONDUMO PRIMARY SCHOOL | 500213897 | uMhlathuze | Design | Active - Not Contracted | 2017-10-12 |  | 2024-11-12 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 12842 | DB/500317830/SDS | KwaZulu-Natal | NTABANKULA PRIMARY SCHOOL | 500317830 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-09-23 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 12844 | I/500246679/WS | KwaZulu-Natal | PUALPIETERSBURG PRIMARY SCHOOL | 500246679 | eDumbe | Practical Completion (100%) | Active - Not Contracted | 2015-07-19 | 2016-07-18 | 2023-04-19 | 2017-10-19 | 2023-04-19 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12845 | DB/500343360/SDS | KwaZulu-Natal | NTABENI PRIMARY SCHOOL | 500343360 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-12-28 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 12846 | DB/500242165/SDS | KwaZulu-Natal | NZUZA PRIMARY SCHOOL | 500242165 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-10-28 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 12849 | W/500257631/WS | KwaZulu-Natal | SAKHUMUZI PRIMARY SCHOOL | 500257631 | Ndwedwe | Construction 76% - 99% | Active - Contracted | 2008-02-12 | 2009-02-28 | 2023-06-11 | 2009-06-11 | 2023-04-01 | 1560060 | 7106940 | 8667000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12850 | W/500238613/SDS | KwaZulu-Natal | NSUNGWINI COMBINED SCHOOL | 500238613 | KwaDukuza | Final Completion | Active - Contracted | 2017-09-12 | 2017-12-05 | 2023-08-21 | 2023-08-21 | 2023-08-21 | 559591 | 682429 | 1242020 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12852 | DB/500239686/SDS | KwaZulu-Natal | NTENESHANA PRIMARY SCHOOL | 500239686 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-12-14 |  |  | 1304952 | 5944782 | 7249734 | Equitable Share | Maintenance and Repairs
|  | 12853 | W/500297628/WS | KwaZulu-Natal | THEKELIMFUNDO PRIMARY SCHOOL | 500297628 | Mandeni | Construction 76% - 99% | Active - Contracted | 2016-06-15 | 2019-09-12 | 2023-06-30 | 2023-05-05 | 2025-01-31 | 823788 | 3752814 | 4576602 | Education Infrastructure Grant | Upgrading and Additions
|  | 12858 | ET/500158397/WS | KwaZulu-Natal | HHOMOYI PRIMARY SCHOOL | 500158397 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2017-03-04 | 2019-09-10 | 2023-07-31 | 2025-04-30 | 2025-08-30 | 604082 | 2751927 | 3356009 | Education Infrastructure Grant | Upgrading and Additions
|  | 12863 | W/500424945/WS | KwaZulu-Natal | EMVUBUKAZI JUNIOR SECONDARY SCHOOL | 500424945 | Umzimkhulu | Tender | Active - Not Contracted | 2016-01-01 |  | 2026-06-30 |  |  | 1356568 | 6179921 | 7536489 | Education Infrastructure Grant | Upgrading and Additions
|  | 12870 | W/500217264/RRR | KwaZulu-Natal | MPOPHOMENI HIGH SCHOOL | 500217264 | uMngeni | Project Initiation | Active - Not Contracted | 2006-01-13 |  | 2024-01-19 |  |  | 1861000 | 2181000 | 4042000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12873 | W/500274984/UA | KwaZulu-Natal | ST ANNES PRIMARY SCHOOL | 500274984 | Umdoni | Project Initiation | Active - Not Contracted | 2015-05-10 |  | 2023-06-30 |  |  | 1382654 | 7691741 | 9074395 | Education Infrastructure Grant | Upgrading and Additions
|  | 12874 | DB/500128242/SDS | KwaZulu-Natal | EKUBUSISWENI PRIMARY SCHOOL | 500128242 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2010-10-11 | 2019-07-31 | 2023-02-26 | 2023-06-26 | 2023-12-26 | 620638 | 5042454 | 5663092 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12879 | DB/500280645/WS | KwaZulu-Natal | THANDUXOLO PRIMARY SCHOOL | 500280645 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2015-11-20 |  | 2024-03-29 |  |  | 920354 | 4192725 | 5113079 | Education Infrastructure Grant | Upgrading and Additions
|  | 12886 | W/500105783/UA | KwaZulu-Natal | BAPHUMILE PRIMARY SCHOOL | 500105783 | Umzumbe | Design | Active - Contracted | 2010-12-12 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12891 | DB/500160210/SDS | KwaZulu-Natal | ILENGE PRIMARY SCHOOL | 500160210 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2018-09-12 |  | 2024-03-30 |  |  | 1044333 | 4757518 | 5801851 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12893 | W/500266215/SDS | KwaZulu-Natal | SINAMUVA PRIMARY SCHOOL | 500266215 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2015-04-01 |  | 2023-11-30 |  |  | 43460 | 197986 | 241446 | Education Infrastructure Grant | Upgrading and Additions
|  | 12894 | W/500298109/WS | KwaZulu-Natal | YISE SECONDARY SCHOOL | 500298109 | Ubuhlebezwe | Design | Active - Contracted | 2011-10-18 |  | 2024-03-30 |  |  | 478980 | 2182020 | 2661000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12897 | W/500227587/RRR | KwaZulu-Natal | NGCEDOMHLOPHE HIGH SCHOOL | 500227587 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2010-12-12 | 2013-11-12 | 2023-06-30 | 2023-02-26 | 2022-03-21 | 1794000 | 8174000 | 10072738 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12905 | DB/500203574/WS | KwaZulu-Natal | MBAMBALALA PRIMARY SCHOOL | 500203574 | Ubuhlebezwe | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 88560 | 403440 | 492000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12918 | W/500120768/RRR | KwaZulu-Natal | DENVER ZOAR P | 500120768 | Ray Nkonyeni | Project Initiation | Active - Contracted | 2010-10-11 | 2013-12-11 | 2023-11-12 | 2015-12-11 | 2024-03-12 | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12919 | W/500235875/WS | KwaZulu-Natal | NONTSHUNTSHA PRIMARY SCHOOL | 500235875 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2009-02-15 |  | 2023-01-01 |  |  | 432000 | 3374312 | 3806312 | Education Infrastructure Grant | Upgrading and Additions
|  | 12926 | I/500211196/SDS | KwaZulu-Natal | MINYA P | 500211196 | Nongoma | Design | Active - Not Contracted | 2010-10-11 |  | 2023-12-12 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12930 | W/500275798/RRR | KwaZulu-Natal | ST JOACHIMS SP | 500275798 | Umzumbe | Project Initiation | Active - Not Contracted | 2008-02-13 |  | 2023-06-30 |  |  | 1382654 | 7691741 | 9074395 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12931 | DB/500246309/SDS | KwaZulu-Natal | PARKLANDS PRIMARY SCHOOL | 500246309 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-10-11 | 2018-12-11 | 2023-06-10 | 2023-05-25 | 2025-05-29 | 1328108 | 6050272 | 7378380 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12932 | DB/500441003/SDS | KwaZulu-Natal | PHEMBISIZWE PRIMARY SCHOOL | 500441003 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-09-12 | 2018-04-05 | 2023-10-05 | 2023-05-05 | 2025-07-31 | 323515 | 2128485 | 2452000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12941 | W/500153402/SDS | KwaZulu-Natal | HAMBAYEDWA PRIMARY SCHOOL | 500153402 | Nkandla | Practical Completion (100%) | Active - Contracted | 2008-10-30 | 2022-03-30 | 2023-03-30 | 2024-04-30 | 2025-04-30 | 727853 | 3315777 | 4043630 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12945 | DB/500442927/WS | KwaZulu-Natal | ZIMELE PRIMARY SCHOOL | 500442927 | Nongoma | Design | Active - Contracted | 2017-06-06 |  | 2024-03-29 |  |  | 2798000 | 3118000 | 5916000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12947 | W/500240352/SDS | KwaZulu-Natal | NTONTONTO JUNIOR PRIMARY SCHOOL | 500240352 | Umzumbe | Construction 76% - 99% | Active - Contracted | 2017-09-12 | 2017-12-13 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2460000 | 3000000 | 5460000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12948 | W/500260998/SDS | KwaZulu-Natal | PENNINGTON PRIMARY SCHOOL | 500260998 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-11-09 | 2021-02-26 | 2023-06-30 | 2023-02-26 | 2022-03-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12958 | DB/500211640/SDS | KwaZulu-Natal | MKHALIPHI HIGH SCHOOL | 500211640 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2022-01-10 | 2022-02-09 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 770215 | 11567524 | 12337739 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12962 | DB/500234062/SDS | KwaZulu-Natal | NOKHALELA HIGH SCHOOL | 500234062 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-10-15 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 12963 | W/500241869/SDS | KwaZulu-Natal | NYONI PRIMARY SCHOOL | 500241869 | eThekwini | Tender | Active - Contracted | 2017-09-25 |  | 2025-03-25 |  |  | 1165108 | 5330660 | 6495768 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12964 | W/500164465/RRR | KwaZulu-Natal | SENZAKAHLE P (IXOPO) | 500164465 | Ubuhlebezwe | Project Initiation | Proposed | 2014-02-03 |  | 2023-10-30 |  |  | 4481280 | 20414720 | 24896000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12967 | W/500236134/RRR | KwaZulu-Natal | NORTHBURY PARK SECONDARY SCHOOL | 500236134 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2014-07-08 | 2014-12-11 | 2023-06-30 | 2023-02-26 | 2022-03-29 | 1335000 | 6082000 | 7417000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12970 | W/500212713/RRR | KwaZulu-Natal | MLINGANISWA PRIMARY SCHOOL | 500212713 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-01-04 | 2016-05-24 | 2023-01-29 | 2018-10-27 | 2023-01-29 | 1062000 | 4838000 | 5900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12971 | W/500280978/RRR | KwaZulu-Natal | THE GROVE COMBINE SCHOOL | 500280978 | Mpofana | Practical Completion (100%) | Active - Contracted | 2010-08-20 | 2011-08-15 | 2023-06-30 | 2018-06-14 | 2023-03-29 | 360000 | 1640000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 12976 | W/500143634/RRR | KwaZulu-Natal | EZINQOLENI JS | 500143634 | Ray Nkonyeni | Design | Active - Not Contracted | 2010-04-25 | 2012-05-24 | 2023-02-06 | 2015-05-08 | 2024-06-08 | 1158589 | 5691525 | 6850114 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12978 | W/500160358/RRR | KwaZulu-Natal | IMBALENCANE P | 500160358 | Umzumbe | Project Initiation | Active - Contracted | 2015-11-20 |  | 2024-09-30 |  |  | 208800 | 951200 | 1160000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 12980 | DB/500246457/SDS | KwaZulu-Natal | PARLOCK PRIMARY SCHOOL | 500246457 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-09-12 | 2019-10-31 | 2023-03-30 | 2024-08-31 | 2025-08-31 | 1255363 | 5718874 | 6974237 | Education Infrastructure Grant | Maintenance and Repairs
|  | 12982 | W/500162245/NS | KwaZulu-Natal | NEW INDALENI PRIMARY SCHOOL | 500162245 | Richmond | Practical Completion (100%) | Active - Contracted | 2013-02-23 | 2022-05-23 | 2022-09-02 | 2022-09-02 | 2025-05-31 | 5874360 | 47052724 | 52927084 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 12987 | W/500161690/UA | KwaZulu-Natal | KHETHOKUHLE SECONDARY SCHOOL | 500447478 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2014-04-07 |  | 2024-05-27 |  |  | 3545000 | 1615000 | 5160000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12988 | W/500115440/UA | KwaZulu-Natal | CELUBUHLE SENIOR PRIMARY SCHOOL | 500115440 | eThekwini | Practical Completion (100%) | Active - Contracted | 2010-03-15 | 2011-03-10 | 2024-03-29 | 2020-08-31 | 2024-03-29 | 2662000 | 12127000 | 14888085 | Equitable Share | Upgrading and Additions
|  | 12989 | W/500185592/UA | KwaZulu-Natal | LANGKLOOF PRIMARY SCHOOL | 500185592 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2014-08-13 | 2015-03-18 | 2023-03-29 | 2022-07-23 | 2023-03-29 | 2413000 | 10951000 | 13834147 | Equitable Share | Upgrading and Additions
|  | 12992 | W/500115070/UA | KwaZulu-Natal | CECILIA PRIMARY SCHOOL | 500115070 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2011-02-05 | 2012-01-31 | 2022-04-03 | 2022-04-03 | 2024-03-29 | 1794833 | 10105894 | 11948154 | Equitable Share | Upgrading and Additions
|  | 12996 | W/500306582/UA | KwaZulu-Natal | BHEKUKWAZI SECONDARY SCHOOL | 500306582 | uMhlathuze | Project Initiation | Active - Contracted | 2013-06-08 |  | 2024-03-30 |  |  | 7100800 | 32348200 | 39449000 | Equitable Share | Upgrading and Additions
|  | 12997 | W/500198394/UA | KwaZulu-Natal | MAPHINDELA PRIMARY SCHOOL | 500198394 | Jozini | Practical Completion (100%) | Active - Contracted | 2013-01-21 | 2014-01-16 | 2023-03-02 | 2022-03-02 | 2023-03-02 | 3445000 | 15697000 | 19142000 | Equitable Share | Upgrading and Additions
|  | 12998 | W/500266723/UA | KwaZulu-Natal | ST PHILIPS PRIMARY SCHOOL | 500266723 | Jozini | Practical Completion (100%) | Active - Contracted | 2012-07-01 | 2013-06-26 | 2023-06-30 | 2017-12-02 | 2023-05-31 | 6341000 | 28887000 | 35228000 | Education Infrastructure Grant | Upgrading and Additions
|  | 12999 | W/500281200/UA | KwaZulu-Natal | THELAMAMA PRIMARY SCHOOL | 500281200 | Jozini | Practical Completion (100%) | Active - Contracted | 2013-01-21 | 2014-01-16 | 2023-06-30 | 2018-03-02 | 2025-05-31 | 4426000 | 20164000 | 24590000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13002 | W/500339771/UA | KwaZulu-Natal | SANYWANA SECONDARY SCHOOL | 500339771 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2008-02-04 | 2008-02-27 | 2023-06-30 | 2018-12-04 | 2023-04-01 | 421000 | 1920000 | 2341000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13007 | W/500338476/UA | KwaZulu-Natal | NAZARETH PRIMARY SCHOOL | 500338476 | eThekwini | Practical Completion (100%) | Active - Contracted | 2011-03-20 | 2012-03-14 | 2024-06-30 | 2023-02-26 | 2022-03-11 | 4770000 | 21732000 | 29406913 | Education Infrastructure Grant | Upgrading and Additions
|  | 13008 | W/500323972/UA | KwaZulu-Natal | JOEL PRIMARY SCHOOL | 500323972 | Maphumulo | Design | Active - Not Contracted | 2008-06-01 |  | 2024-07-29 |  |  | 1568742 | 5130124 | 6854652 | Education Infrastructure Grant | Upgrading and Additions
|  | 13010 | W/500246124/RRR | KwaZulu-Natal | PANORAMA COMBINED PRIMARY SCHOOL | 500246124 | The Msunduzi | Construction 51% - 75% | Active - Contracted | 2016-07-21 | 2021-02-26 | 2022-10-28 | 2021-04-30 | 2022-03-30 | 4065000 | 22651000 | 26716000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13011 | C/500162319/ECD | KwaZulu-Natal | INDANYANA P | 500162319 | Okhahlamba | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13014 | W/500108706/RRR | KwaZulu-Natal | BHEKINDLELA HIGH SCHOOL | 500108706 | Jozini | Practical Completion (100%) | Active - Contracted | 2010-05-11 | 2017-05-12 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 1526000 | 6952000 | 8478000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13016 | ET/500235320/WS | KwaZulu-Natal | NONDABULA PRIMARY SCHOOL | 500235320 | Ndwedwe | Final Completion | Active - Contracted | 2018-08-01 | 2018-11-14 | 2022-09-13 | 2020-01-20 | 2023-09-13 | 943322 | 4297358 | 6295492 | Education Infrastructure Grant | Upgrading and Additions
|  | 13024 | W/500308247/RRR | KwaZulu-Natal | MAVANGANA SECONDARY SCHOOL | 500308247 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2012-01-03 | 2012-01-19 | 2023-03-29 | 2018-02-10 | 2023-03-29 | 684000 | 3116000 | 3877194 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13027 | W/500251452/RRR | KwaZulu-Natal | PRESTBURY PRIMARY SCHOOL | 500251452 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2014-02-17 | 2014-11-30 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 1348000 | 6139000 | 7568394 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13028 | W/500289969/UA | KwaZulu-Natal | UNOBHALA HIGH SCHOOL | 500289969 | Mkhambathini | Practical Completion (100%) | Active - Contracted | 2016-02-17 | 2016-07-19 | 2023-06-30 | 2023-03-02 | 2023-04-01 | 735310 | 3639436 | 4530215 | Education Infrastructure Grant | Upgrading and Additions
|  | 13034 | W/500266955/RRR | KwaZulu-Natal | SIPHAKAMILE PRIMARY SCHOOL | 500266955 | Ray Nkonyeni | Design | Active - Not Contracted | 2014-09-15 |  | 2023-06-30 |  |  | 1669190 | 7203688 | 9050247 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13039 | W/500239760/RRR | KwaZulu-Natal | INTENGO PRIMARY SCHOOL | 500239760 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2010-10-11 | 2013-11-12 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 45000 | 3014000 | 3059000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13046 | W/500256521/RRR | KwaZulu-Natal | ROSEVILLE SECONDARY SCHOOL | 500256521 | Umdoni | Practical Completion (100%) | Active - Contracted | 2014-04-20 | 2014-05-01 | 2023-04-01 | 2018-02-02 | 2023-04-01 | 457000 | 2082000 | 2539000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13047 | W/500109076/RRR | KwaZulu-Natal | BHEKUKUPHIWA PRIMARY SCHOOL | 500109076 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2010-10-11 | 2013-12-11 | 2024-03-29 | 2022-12-12 | 2024-03-29 | 813000 | 3703000 | 4710967 | Equitable Share | Upgrading and Additions
|  | 13048 | DB/500200984/WS | KwaZulu-Natal | MASIMDUMISE HIGH SCHOOL | 500200984 | Impendle | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 2249000 | 3529000 | 5778000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13050 | W/500131387/RRR | KwaZulu-Natal | EMANYONINI SECONDARY PRIMARY SCHOOL | 500131387 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2012-02-09 | 2012-04-02 | 2025-03-29 | 2018-08-31 | 2025-03-29 | 540000 | 2460000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13051 | W/500132127/RRR | KwaZulu-Natal | EMBONINI PRIMARY SCHOOL | 500132127 | eThekwini | Practical Completion (100%) | Active - Contracted | 2010-05-15 | 2011-05-10 | 2024-04-29 | 2018-08-31 | 2024-04-29 | 462000 | 2103000 | 2641860 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13052 | W/500134717/RRR | KwaZulu-Natal | EMTHALENI PRIM SCHOOL | 500134717 | Mandeni | Practical Completion (100%) | Active - Contracted | 2010-05-10 | 2018-04-27 | 2023-06-29 | 2020-03-29 | 2023-06-29 | 525000 | 2391000 | 2916000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13053 | W/500136567/RRR | KwaZulu-Natal | ENGONYAMENI PRIMARY SCHOOL | 500136567 | eThekwini | Practical Completion (100%) | Active - Contracted | 2010-05-15 | 2011-05-10 | 2022-12-01 | 2015-12-01 | 2022-12-01 | 234881 | 1904130 | 2139011 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13054 | W/500140822/RRR | KwaZulu-Natal | ESINDI PRIMARY SCHOOL | 500140822 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2013-03-30 | 2014-06-25 | 2024-03-30 | 2023-06-30 | 2022-05-29 | 584000 | 2658000 | 3352119 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13056 | W/500167351/RRR | KwaZulu-Natal | ISAVIYO PRIMARY SCHOOL | 500167351 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2014-02-17 | 2014-08-13 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 143444 | 1889910 | 2126745 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13064 | W/500192511/WS | KwaZulu-Natal | MAGONGOLO PRIMARY SCHOOL | 500192511 | Ndwedwe | Tender | Active - Not Contracted | 2014-03-12 |  | 2025-03-11 |  |  | 796505 | 3628521 | 4425026 | Education Infrastructure Grant | Upgrading and Additions
|  | 13065 | ET/500196766/WS | KwaZulu-Natal | MANGETHE PRIMARY SCHOOL | 500196766 | Mandeni | Construction 76% - 99% | Active - Contracted | 2014-02-23 | 2014-12-01 | 2023-02-15 | 2023-05-22 | 2023-06-23 | 638297 | 3287203 | 3925500 | Education Infrastructure Grant | Upgrading and Additions
|  | 13072 | W/500343952/RRR | KwaZulu-Natal | BETHULO SECONDARY SCHOOL | 500343952 | Msinga | Practical Completion (100%) | Active - Contracted | 2012-10-12 | 2017-02-12 | 2023-07-12 | 2018-12-12 | 2022-07-26 | 400000 | 1822000 | 2222000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13078 | W/500106597/RRR | KwaZulu-Natal | BAZANENI PRIMARY SCHOOL | 500106597 | Big Five Hlabisa | Project Initiation | Proposed | 2014-05-22 | 2017-12-01 | 2023-12-01 | 2018-12-15 | 2024-09-30 | 330000 | 1505000 | 1835000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13079 | W/500338772/RRR | KwaZulu-Natal | BHAMU HIGH SCHOOL | 500338772 | Nkandla | Project Initiation | Proposed | 2011-02-11 | 2013-06-12 | 2023-02-12 | 2015-12-11 | 2024-03-29 | 417000 | 1902000 | 2319000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13080 | W/500115699/RRR | KwaZulu-Natal | CEREMONY PRIMARY SCHOOL | 500115699 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2011-10-11 | 2013-11-12 | 2023-04-26 | 2018-11-12 | 2023-04-26 | 505000 | 2298000 | 2803000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13087 | W/500229178/WS | KwaZulu-Natal | NGWANE SECONDARY SCHOOL | 500167129 | Abaqulusi | Design | Active - Not Contracted | 2013-08-28 |  | 2023-03-09 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13089 | W/500183446/RRR | KwaZulu-Natal | KWASHUKELA PRIMARY SCHOOL | 500183446 | Jozini | Practical Completion (100%) | Active - Contracted | 2013-09-06 | 2014-08-31 | 2023-06-30 | 2015-08-31 | 2025-08-31 | 366923 | 1667833 | 2034756 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13094 | W/500200392/RRR | KwaZulu-Natal | MASHINGA HIGH SCHOOL | 500200392 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-15 | 2023-03-30 | 2022-03-30 | 2023-03-29 | 262000 | 1193000 | 1455000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13117 | W/500113294/UA | KwaZulu-Natal | BUHLEBEZWE HIGH SCHOOL | 500113331 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2013-01-12 | 2014-09-03 | 2024-03-29 | 2022-03-01 | 2024-03-29 | 1436000 | 6544000 | 7980000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13119 | W/500124505/RRR | KwaZulu-Natal | DUMISA PRIMARY SCHOOL | 500124505 | Ubuhlebezwe | Project Initiation | Proposed | 2010-10-11 |  | 2023-11-12 |  |  | 1048671 | 4766688 | 5815359 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13123 | W//500308210/WS | KwaZulu-Natal | MASAMENI SECONDARY SCHOOL | 500308210 | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2016-03-11 | 2018-08-31 | 2022-08-31 | 2022-08-31 | 2023-08-31 | 1165380 | 5308951 | 6474331 | Education Infrastructure Grant | Upgrading and Additions
|  | 13130 | W/500266622/RRR | KwaZulu-Natal | SINGELE HIGH SCHOOL | 500266622 | eThekwini | Final Completion | Active - Contracted | 2014-08-08 | 2014-09-03 | 2024-03-30 | 2023-06-30 | 2021-05-31 | 1490000 | 6790000 | 8280000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13131 | W/500269175/RRR | KwaZulu-Natal | SIVELILE SECONDARY SCHOOL | 500269175 | Umdoni | Practical Completion (100%) | Active - Contracted | 2013-09-03 | 2014-09-03 | 2024-03-30 | 2023-06-30 | 2019-03-29 | 1114000 | 5067000 | 6181000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13135 | ET/500248492/WS | KwaZulu-Natal | PHEZUKOMKHONO HIGH SCHOOL | 500248492 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2015-01-20 | 2022-05-19 | 2023-05-19 | 2024-05-19 | 2024-05-19 | 828000 | 3772000 | 4600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13144 | ET/500268620/WS | KwaZulu-Natal | SITHEBE PRIMARY SCHOOL | 500268620 | Mandeni | Final Completion | Active - Contracted | 2017-11-23 | 2019-06-18 | 2023-05-29 | 2021-05-29 | 2023-08-29 | 0 | 3653000 | 3653000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13145 | ET/500183964/WS | KwaZulu-Natal | KWAVUSIMUZI HS | 500183964 | Mandeni | Final Completion | Active - Contracted | 2012-11-09 | 2013-11-04 | 2023-05-01 | 2014-05-01 | 2023-08-01 | 200000 | 3532 | 203532 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13149 | I/500302882/WS | KwaZulu-Natal | PHUZULWAZI | 500302882/WS | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2013-03-03 | 2014-02-26 | 2023-07-18 | 2014-07-18 | 2023-10-20 | 0 | 1570000 | 1570000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13154 | ET/500245162/WS | KwaZulu-Natal | OTTAWA PRIMARY SCHOOL | 500245162 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-05-01 | 2023-05-19 | 2023-05-19 | 2024-05-19 | 2025-05-19 | 971241 | 4424540 | 5395781 | Education Infrastructure Grant | Upgrading and Additions
|  | 13161 | ET/500136567/WS | KwaZulu-Natal | ENGONYAMENI PRIMARY SCHOOL (SIKHWAMA S) | 500136567 | eThekwini | Final Completion | Active - Contracted | 2012-11-09 | 2013-11-04 | 2023-09-19 | 2021-12-30 | 2023-12-30 | 400000 | 1500000 | 2136415 | Education Infrastructure Grant | Upgrading and Additions
|  | 13164 | ET/MAINTENANCE/PINETOWN&UMLAZI DISTRICT MAINTENANCE | KwaZulu-Natal | MAINTENANCE | 500000000 | eThekwini | Site Handed - Over to Contractor | Active - Contracted | 2015-07-21 | 2016-05-19 | 2023-03-30 | 2023-05-20 | 2024-12-31 | 2347556 | 71202868 | 73550424 | Education Infrastructure Grant | Maintenance and Repairs
|  | 13169 | MTW/000193/WS | KwaZulu-Natal | MAGQEZULANA JS | 500321345 | Ulundi | Practical Completion (100%) | Active - Contracted | 2012-07-07 | 2012-11-10 | 2023-09-01 | 2016-10-30 | 2025-11-29 | 44162 | 295680 | 409334 | Education Infrastructure Grant | Upgrading and Additions
|  | 13177 | DB/500444481/WS | KwaZulu-Natal | NYENDE PRIMARY SCHOOL | 500444481 | Endumeni | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 2755000 | 3075000 | 5868220 | Education Infrastructure Grant | Upgrading and Additions
|  | 13187 | MTW/000400/WS | KwaZulu-Natal | MACHIBINI P | 500190698 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2010-12-10 | 2011-12-10 | 2023-08-30 | 2015-08-30 | 2023-10-30 | 38932 | 812440 | 862700 | Education Infrastructure Grant | Upgrading and Additions
|  | 13189 | MTW/000402/WS | KwaZulu-Natal | MAKHOWE P | 500194805 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2010-12-10 | 2012-12-10 | 2023-08-30 | 2018-08-30 | 2025-08-30 | 38932 | 796176 | 846436 | Education Infrastructure Grant | Upgrading and Additions
|  | 13193 | DB/500281459/WS | KwaZulu-Natal | THEMBALETHU PRIMARY SCHOOL | 500281459 | eThekwini | Design | Active - Contracted | 2017-06-06 |  | 2024-03-15 |  |  | 2022000 | 2342000 | 4364000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13199 | W/500121619/SDS | KwaZulu-Natal | DINUNTULI PRIMARY SCHOOL | 500121619 | Nkandla | Construction 1% - 25% | Active - Contracted | 2012-03-18 |  | 2025-06-30 |  |  | 85 | 385 | 75533 | Equitable Share | Upgrading and Additions
|  | 13205 | DB/500147593/WS | KwaZulu-Natal | GCININHLIZIYO COMBINED PRIMARY SCHOOL | 500147593 | uMlalazi | Construction 76% - 99% | Active - Contracted | 2010-05-16 | 2020-05-31 | 2025-03-30 | 2022-03-22 | 2027-03-30 | 1291110 | 5881722 | 7172832 | Education Infrastructure Grant | Upgrading and Additions
|  | 13211 | MTW/000374/WS | KwaZulu-Natal | MASOKA PS | 500201132 | Ulundi | Practical Completion (100%) | Active - Contracted | 2011-12-10 | 2013-12-10 | 2023-08-30 | 2024-08-30 | 2025-08-30 | 28625 | 1074553 | 1170424 | Education Infrastructure Grant | Upgrading and Additions
|  | 13214 | DB/500235283/WS | KwaZulu-Natal | NONDENISA SECONDARY SCHOOL | 500235283 | uMshwathi | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 655368 | 2985568 | 3679156 | Education Infrastructure Grant | Upgrading and Additions
|  | 13223 | ED/500123728/UA | KwaZulu-Natal | DUDUZANI PRIMARY SCHOOL | 500123728 | eThekwini | Construction 76% - 99% | Active - Contracted | 2008-04-01 | 2009-04-01 | 2023-03-02 | 2022-11-02 | 2023-03-02 | 3418920 | 15575080 | 18994000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13225 | DB/500200429/WS | KwaZulu-Natal | MASHINGIZELA HIGH SCHOOL | 500200429 | Umvoti | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 270000 | 330000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13226 | DB/500200947/WS | KwaZulu-Natal | MASIJABULE SECONDARY SCHOOL | 500200947 | uMshwathi | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2020-09-12 | 2023-01-31 | 2023-05-05 | 2027-04-20 | 905188 | 4123633 | 5028821 | Education Infrastructure Grant | Upgrading and Additions
|  | 13232 | ET/500199356/WS | KwaZulu-Natal | MARIAM PATEL JUNIOR PRIMARY SCHOOL | 500199356 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-06-12 | 2019-09-10 | 2022-06-30 | 2025-01-31 | 2025-03-30 | 753448 | 3432373 | 4185821 | Education Infrastructure Grant | Upgrading and Additions
|  | 13233 | ET/500167092/WS | KwaZulu-Natal | IQABAVU PRIMARY SCHOOL | 500167092 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2018-03-12 | 2019-09-10 | 2023-04-29 | 2025-04-30 | 2025-03-31 | 702614 | 3200795 | 3903409 | Education Infrastructure Grant | Upgrading and Additions
|  | 13234 | DB/500161246/SDS | KwaZulu-Natal | IMPOLWANE HIGH SCHOOL | 500161246 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2017-09-12 | 2020-02-28 | 2022-12-02 | 2022-11-30 | 2025-10-30 | 2502164 | 11398748 | 13900912 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13237 | I/500222777/UA | KwaZulu-Natal | MZWILILI PRIMARY SCHOOL | 500222777 | eThekwini | Practical Completion (100%) | Active - Contracted | 2001-04-10 | 2020-01-12 | 2026-03-14 | 2023-10-15 | 2023-10-15 | 10144440 | 47909110 | 58053550 | Education Infrastructure Grant | Upgrading and Additions
|  | 13238 | I/500221926/NS | KwaZulu-Natal | MZAMO SECONDARY SCHOOL | 500221926 | Newcastle | Final Completion | Active - Contracted | 2014-04-15 | 2022-10-20 | 2022-11-03 | 2022-11-20 | 2023-04-30 | 8259000 | 37625000 | 45884000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13239 | I/500162134/UA | KwaZulu-Natal | INCOPHELELO JUNIOR PRIMARY SCHOOL | 500162134 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-02-02 | 2016-03-05 | 2023-11-01 | 2022-11-30 | 2023-04-15 | 3219660 | 14667340 | 17887000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13240 | ET/500496281/NS | KwaZulu-Natal | SOLOMON MAHLANGU PRIMARY SCHOOL (New CORNUBIA #1 P) | 500496281 | eThekwini | Construction 51% - 75% | Active - Contracted | 2014-09-01 | 2019-09-10 | 2023-09-02 | 2021-04-30 | 2023-04-30 | 10820000 | 49292000 | 60112000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13244 | W/500202575/RRR | KwaZulu-Natal | MAVUMENGWANE HIGH SCHOOL | 500202575 | uMlalazi | Construction 1% - 25% | Active - Contracted | 2015-01-31 | 2018-04-27 | 2023-05-31 | 2018-09-01 | 2023-05-31 | 2385512 | 10867332 | 13252844 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13245 | W/500212787/UA | KwaZulu-Natal | MLOKOTHWA HIGH SCHOOL | 500212787 | Nongoma | Tender | Active - Not Contracted | 2017-06-20 |  | 2023-01-03 |  |  | 6744586 | 30725334 | 37469920 | Equitable Share | Upgrading and Additions
|  | 13246 | W/500263070/UA | KwaZulu-Natal | SIBOMVU PRIMARY SCHOOL | 500263070 | Nkandla | Tender | Active - Not Contracted | 2014-06-20 |  | 2023-06-30 |  |  | 6044250 | 24177000 | 30221250 | Equitable Share | Upgrading and Additions
|  | 13248 | W/500297850/NS | KwaZulu-Natal | XOLOXOLO PRIMARY SCHOOL | 500297850 | Greater Kokstad | Construction 76% - 99% | Active - Contracted | 2015-02-08 | 2015-06-15 | 2024-03-30 | 2023-06-30 | 2022-06-30 | 13367629 | 60896977 | 74264606 | Equitable Share | New or Replaced Infrastructure
|  | 13249 | I/500206571/WS | KwaZulu-Natal | MDUMELA SECONDARY SCHOOL | 500206571 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-12-01 | 2016-09-23 | 2024-01-19 | 2017-06-30 | 2024-01-19 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13251 | I/Zululand Harvesting Project | KwaZulu-Natal | ZULULAND SPECIAL PROJECTS, WATER HARVESTING | 500000000 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2010-09-10 | 2020-01-12 | 2031-08-14 | 2031-10-15 | 2031-10-15 | 711000 | 68053856 | 68764856 | Equitable Share | Upgrading and Additions
|  | 13255 | ED/Furniture/FUR | KwaZulu-Natal | FURNITURE NEW INFRASTRUCTURE | Programme | uMngeni | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-09 | 2024-03-31 | 2024-03-31 | 2025-05-31 | 0 | 209907756 | 209907756 | Equitable Share | Non-Infrastructure
|  | 13258 | I/500105191/UA | KwaZulu-Natal | BANGAMAYE PRIMARY SCHOOL | 500105191 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-01-01 | 2015-09-16 | 2023-12-30 | 2019-02-28 | 2023-12-30 | 8577360 | 39074640 | 47652000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13262 | I/500171014/UA | KwaZulu-Natal | JAMES NXUMALO HIGH | 500171014 | Ulundi | Practical Completion (100%) | Active - Contracted | 2014-09-22 | 2015-10-29 | 2022-11-15 | 2023-09-07 | 2024-11-15 | 7015558 | 38975323 | 45990881 | Education Infrastructure Grant | Upgrading and Additions
|  | 13264 | I/500283975/UA | KwaZulu-Natal | TINLEY MANOR PRIMARY SCHOOL | 500283975 | KwaDukuza | Construction 76% - 99% | Active - Contracted | 2015-03-15 | 2017-03-30 | 2023-06-30 | 2022-03-20 | 2023-06-20 | 4434415 | 20235124 | 24669539 | Education Infrastructure Grant | Upgrading and Additions
|  | 13265 | W/500196100/RRR | KwaZulu-Natal | MANDLAKAYISE PRIMARY SCHOOL | 500196100 | eThekwini | Design | Active - Not Contracted | 2015-04-09 |  | 2024-11-30 |  |  | 877320 | 3996680 | 4874000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13269 | IDT/500000000/2022-23 | KwaZulu-Natal | SCHOOL DESLUDGING PROGRAMME | Programme |  | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2022-03-03 | 2024-03-03 | 2023-02-03 | 2024-04-03 | 10012500 | 251601323 | 261613823 | Equitable Share | Maintenance and Repairs
|  | 13270 | I/500308987/UA | KwaZulu-Natal | NQOBANI P | 500308987 | Ulundi | Construction 1% - 25% | Active - Contracted | 2014-09-03 | 2016-10-20 | 2023-02-01 | 2018-03-20 | 2023-08-20 | 360000 | 1640000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 13278 | W/500201798/RRR | KwaZulu-Natal | MATHOLE HIGH SCHOOL | 500201798 | Ulundi | Construction 26% - 50% | Active - Contracted | 2015-08-05 |  | 2024-06-30 |  |  | 12602656 | 57412097 | 70014753 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 13279 | I/500201946/WS | KwaZulu-Natal | MATHUNJWA SECONDARY SCHOOL | 500201946 | Abaqulusi | Construction 76% - 99% | Active - Contracted | 2015-09-12 | 2016-09-12 | 2023-06-01 | 2017-06-01 | 2024-03-31 | 852000 | 1840000 | 2692000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13281 | W/500212787/RRR | KwaZulu-Natal | MLOKOTHWA HIGH SCHOOL | 500212787 | Nongoma | Practical Completion (100%) | Active - Contracted | 2014-06-20 | 2017-03-30 | 2023-02-03 | 2018-01-30 | 2023-02-03 | 8656000 | 39432000 | 48088000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13282 | DB/500114404/WS | KwaZulu-Natal | CANDABUTHULE SECONDARY SCHOOL | 500114404 | Umvoti | Construction 51% - 75% | Active - Contracted | 2014-09-12 | 2020-05-31 | 2023-03-25 | 2022-03-22 | 2025-03-25 | 392927 | 12905039 | 13297966 | Education Infrastructure Grant | Upgrading and Additions
|  | 13283 | W/500233433/UA | KwaZulu-Natal | NOBAMBA HIGH SCHOOL | 500233433 | Ray Nkonyeni | Design | Active - Not Contracted | 2015-07-08 |  | 2024-06-01 |  |  | 1980000 | 9020000 | 11000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13284 | I/500260221/WS | KwaZulu-Natal | SELINDE PRIMARY SCHOOL | 500260221 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2019-05-03 | 2019-06-11 | 2023-03-30 | 2022-01-28 | 2024-03-30 | 441000 | 2804000 | 3245000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13285 | I/500249750/UA | KwaZulu-Natal | PHUMANYOVA HIGH SCHOOL | 500249750 | Nongoma | Construction 76% - 99% | Active - Contracted | 2013-02-15 | 2016-10-20 | 2023-03-30 | 2018-03-31 | 2023-03-30 | 9296746 | 51648587 | 60945333 | Education Infrastructure Grant | Upgrading and Additions
|  | 13288 | W/500422947/WS | KwaZulu-Natal | SUNSHINE PRIMARY SCHOOL | 500422947 | Umhlabuyalingana | Tender | Active - Not Contracted | 2014-06-15 |  | 2026-06-30 |  |  | 829232 | 57378661 | 58207893 | Education Infrastructure Grant | Upgrading and Additions
|  | 13289 | W/ADMIN/W | KwaZulu-Natal | TRURO HOUSE OFFICE | 500284789 | eThekwini | Design | Active - Not Contracted | 2015-05-01 |  | 2023-06-30 |  |  | 2219940 | 12540393 | 14760333 | Equitable Share | Upgrading and Additions
|  | 13290 | W/500293299/UA | KwaZulu-Natal | VUKUZAKHE HIGH SCHOOL | 500293299 | eThekwini | Design | Active - Not Contracted | 2015-09-01 |  | 2024-08-31 |  |  | 3240000 | 14760000 | 18000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13291 | MAINTENANCE DOPW 2016/2017 | KwaZulu-Natal | Maintenance : DISTRICTS | Maintenance |  | Other - Packaged Ongoing Project | Active - Contracted | 2018-04-06 | 2018-12-11 | 2023-03-30 | 2023-03-30 | 2024-03-30 | 74160000 | 337840000 | 412000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 13296 | W/500110371/H | KwaZulu-Natal | BIZIMALI HIGH SCHOOL HOSTEL | 500110371 | Nkandla | Design | Active - Not Contracted | 2015-09-07 |  | 2024-06-30 |  |  | 1260000 | 5740000 | 7000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13297 | W/NEW/NS | KwaZulu-Natal | DUNGAMBILI PRIMARY SCHOOL | New | Abaqulusi | Feasibility | Active - Contracted | 2014-02-16 |  | 2026-02-02 |  |  | 5400000 | 24600000 | 30000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13298 | I/500496244/NS | KwaZulu-Natal | UMTAMTENGWAYO PRIMARY SCHOOL | 500000000/30 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2015-09-20 | 2018-04-03 | 2024-03-03 | 2024-03-03 | 2024-03-03 | 6840000 | 53703000 | 60543000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13301 | DB/500173271/UA | KwaZulu-Natal | KHANDISA PRIMARY SCHOOL | 500173271 | uMhlathuze | Design | Active - Not Contracted | 2014-09-12 |  | 2027-12-01 |  |  | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13302 | C/500341880/UA | KwaZulu-Natal | MT PLEASANT PRIMARY SCHOOL | 500341880 | uMngeni | On Hold | Active - Not Contracted | 2014-09-12 |  | 2023-09-01 |  |  | 2517000 | 11467000 | 13984000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13304 | I/500207015/UA | KwaZulu-Natal | MEHLOKAZULU HIGH SCHOOL | 500207015 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2014-04-18 | 2016-10-20 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 5885830 | 32699055 | 38584885 | Education Infrastructure Grant | Upgrading and Additions
|  | 13306 | DB/500113738/WS | KwaZulu-Natal | BURFORD PRIMARY SCHOOL | 500113738 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2014-09-12 | 2020-05-31 | 2025-03-25 | 2022-03-22 | 2025-03-25 | 560063 | 2551400 | 3111463 | Education Infrastructure Grant | Upgrading and Additions
|  | 13310 | ED/-/HR | KwaZulu-Natal | HR Capacitation | 500000000 |  | Other - Compensation of Employees | Active - Contracted | 2014-04-01 | 2019-08-27 | 2023-03-30 | 2023-11-30 | 2025-07-30 | 18829800 | 85780200 | 104610000 | Equitable Share | Non-Infrastructure
|  | 13312 | W/500220298/UA | KwaZulu-Natal | MTHWALUME HIGH SCHOOL | 500220335 | Umdoni | Construction 26% - 50% | Active - Contracted | 2015-10-05 |  | 2024-02-23 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13313 | W/500192104/UA | KwaZulu-Natal | MAGAYE PRIMARY SCHOOL | 500192104 | Ray Nkonyeni | Design | Proposed | 2016-01-10 |  | 2024-06-30 |  |  | 1080000 | 4920000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13322 | I/500321789/WS | KwaZulu-Natal | INTATHAKUSA PRIMARY SCHOOL | 500321789 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-05-01 | 2022-01-25 | 2023-03-31 | 2022-08-09 | 2023-10-15 | 248000 | 1556776 | 1804776 | Education Infrastructure Grant | Upgrading and Additions
|  | 13323 | DB/500109964/WS | KwaZulu-Natal | BHUQWINI HIGH SCHOOL | 500109964 | Nkandla | Construction 1% - 25% | Active - Contracted | 2014-10-12 | 2024-03-11 | 2024-03-25 | 2024-06-11 | 2025-12-01 | 941000 | 4287000 | 5228000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13325 | W/500209309/RRR | KwaZulu-Natal | MGAZINI LOWER PRIMARY SCHOOL | 500209309 | uPhongolo | Design | Active - Not Contracted | 2016-04-01 |  | 2024-01-30 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13328 | W/500310171/RRR | KwaZulu-Natal | MBALEKELWA PRIMARY SCHOOL | 500310171 | Jozini | Project Initiation | Active - Not Contracted | 2016-06-23 |  | 2023-05-01 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13329 | W/500257779/RRR | KwaZulu-Natal | SAMBANE PRIMARY SCHOOL | 500257779 | Jozini | Practical Completion (100%) | Active - Contracted | 2015-02-11 | 2018-04-27 | 2023-04-01 | 2018-09-01 | 2023-04-01 | 457000 | 2081000 | 2538000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13330 | W/500268657/RRR | KwaZulu-Natal | SITHEKU H | 500268657 | Mthonjaneni | Construction 76% - 99% | Active - Contracted | 2016-02-02 |  | 2023-06-30 |  |  | 1904940 | 8678060 | 10583000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13331 | W/500273208/RRR | KwaZulu-Natal | SOMOPHO P | 500273208 | uMhlathuze | Project Initiation | Active - Not Contracted | 2016-08-02 |  | 2023-06-30 |  |  | 1904940 | 8678060 | 10583000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13333 | W/500116698/RRR | KwaZulu-Natal | CIBILILI C | 500116698 | Abaqulusi | Design | Active - Not Contracted | 2014-10-12 |  | 2024-03-12 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13336 | W/500261109/ECD | KwaZulu-Natal | S H GUMEDE PRIMARY SCHOOL | 500261109 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2014-11-13 | 2017-12-01 | 2023-05-31 | 2018-08-31 | 2023-04-01 | 241000 | 1100000 | 1341000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13342 | W/500154549/UA | KwaZulu-Natal | HEAVITREE P | 500154549 | Inkosi Langalibalele | Design | Active - Not Contracted | 2015-02-08 |  | 2024-05-30 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13345 | W/500122396/UA | KwaZulu-Natal | DNC COMBINED SCHOOL | 500122396 | Dannhauser | Practical Completion (100%) | Active - Contracted | 2015-04-06 | 2016-04-22 | 2024-05-31 | 2022-11-30 | 2024-05-31 | 4681438 | 21326552 | 26007990 | Education Infrastructure Grant | Upgrading and Additions
|  | 13346 | W/500186517/UA | KwaZulu-Natal | LIMEHILL SECONDARY SCHOOL | 500186517 | Alfred Duma | Design | Active - Not Contracted | 2017-03-08 |  | 2024-07-30 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13348 | W/500200281/UA | KwaZulu-Natal | MASHESHELENG PRIMARY SCHOOL | 500200281 | Nqutu | Tender | Active - Not Contracted | 2016-04-01 |  | 2025-03-30 |  |  | 1850000 | 7401000 | 9251000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13349 | W/500447293/UA | KwaZulu-Natal | SIYABONGA SECONDARY SCHOOL | 500447293 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-02-16 | 2017-01-24 | 2024-03-30 | 2023-06-30 | 2021-05-31 | 3632691 | 16548927 | 20181618 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13353 | W/500308765/RRR | KwaZulu-Natal | SIHAYO HIGH SCHOOL | 500308765 | Nqutu | Design | Active - Not Contracted | 2016-03-26 |  | 2023-06-01 |  |  | 541080 | 2464920 | 3006000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13354 | W/500141710/RRR | KwaZulu-Natal | ESTCOURT H (MARTIN RD) | 500141710 | Inkosi Langalibalele | Design | Active - Not Contracted | 2017-04-01 |  | 2024-12-02 |  |  | 540000 | 2460000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13355 | W/500495578/NS | KwaZulu-Natal | NEW MKHAMBA GARDENS PRIMARY SCHOOL | 500495578 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2015-03-01 | 2022-02-05 | 2023-02-05 | 2022-11-05 | 2024-02-05 | 7638572 | 34797941 | 42436513 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13357 | W/500173604/UA | KwaZulu-Natal | KHANYISA SECONDARY SCHOOL | 500173604 | Ndwedwe | Design | Active - Not Contracted | 2016-04-01 |  | 2024-11-30 |  |  | 1228686 | 5597346 | 6826032 | Education Infrastructure Grant | Upgrading and Additions
|  | 13358 | W/500443371/NS | KwaZulu-Natal | UMHLALI COLLEGE | 500443371 | KwaDukuza | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 6109380 | 27831620 | 33941000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13364 | W/500143560/UA | KwaZulu-Natal | EZINDLOVINI P | 500143560 | Ndwedwe | Tender | Active - Not Contracted | 2016-04-01 |  | 2024-04-30 |  |  | 452160 | 2059840 | 2512000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13368 | W/500174677/UA | KwaZulu-Natal | KHOMBA PRIMARY SCHOOL | 500174677 | Maphumulo | Design | Active - Not Contracted | 2016-04-01 |  | 2024-11-30 |  |  | 1255860 | 5721140 | 6977000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13369 | W/500175269/UA | KwaZulu-Natal | KHULULEKANI PRIMARY SCHOOL | 500175269 | Mandeni | Design | Active - Not Contracted | 2016-03-01 |  | 2024-11-30 |  |  | 1511820 | 6887180 | 8399000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13370 | W/500176564/RRR | KwaZulu-Natal | KLOOF HIGH SCHOOL | 500176564 | eThekwini | Feasibility | Active - Not Contracted | 2016-04-14 |  | 2024-10-02 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13371 | W/500183964/UA | KwaZulu-Natal | KWAVUSUMUZI H | 500183964 | Mandeni | Design | Active - Not Contracted | 2016-04-01 |  | 2024-11-30 |  |  | 3226860 | 14700140 | 17927000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13372 | I/500187294/UA | KwaZulu-Natal | LLOYDS PRIMARY SCHOOL | 500187294 | KwaDukuza | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2018-04-01 | 2023-10-30 | 2022-08-30 | 2023-10-30 | 10879727 | 51617750 | 62497477 | Education Infrastructure Grant | Upgrading and Additions
|  | 13375 | W/500205572/RRR | KwaZulu-Natal | MCATHU PRIMARY SCHOOL | 500205572 | Ndwedwe | Feasibility | Active - Not Contracted | 2016-01-16 |  | 2024-03-30 |  |  | 1062360 | 4839640 | 5902000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13376 | W/500218411/UA | KwaZulu-Natal | MSHIYANE HIGH SCHOOL | 500218411 | Ndwedwe | Design | Active - Contracted | 2015-08-18 |  | 2024-02-09 |  |  | 719460 | 3277540 | 3997000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13377 | W/500326599/UA | KwaZulu-Natal | NDUKENDE S | 500326599 | Maphumulo | Design | Active - Not Contracted | 2017-10-22 |  | 2024-03-22 |  |  | 788000 | 3588000 | 4376000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13378 | W/500227698/UA | KwaZulu-Natal | NGCOLOSI SECONDARY SCHOOL | 500227698 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2015-03-30 | 2018-02-01 | 2024-03-30 | 2023-06-30 | 2022-03-09 | 1185000 | 5281000 | 6466000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13380 | W/500237244/RRR | KwaZulu-Natal | NQAKATHELA SECONDARY SCHOOL | 500237244 | Ndwedwe | Design | Active - Not Contracted | 2010-10-11 |  | 2024-12-12 |  |  | 1124640 | 5123360 | 6248000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13382 | W/500248492/UA | KwaZulu-Natal | PHEZUKOMKHONO HIGH SCHOOL | 500248492 | Maphumulo | Feasibility | Active - Not Contracted | 2016-08-21 |  | 2026-11-30 |  |  | 414000 | 1888000 | 2302000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13383 | W/500262663/UA | KwaZulu-Natal | SIBANISETHU PRIMARY SCHOOL | 500262663 | Maphumulo | Design | Active - Not Contracted | 2016-03-23 |  | 2023-11-30 |  |  | 998820 | 4550180 | 5549000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13386 | W/500288933/RRR | KwaZulu-Natal | UMSUNDUZE HIGH PRIMARY SCHOOL | 500288933 | Ndwedwe | Feasibility | Active - Not Contracted | 2019-08-21 |  | 2023-06-30 |  |  | 388800 | 1771200 | 2160000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13389 | W/500211603/RRR | KwaZulu-Natal | MKHABELA PRIMARY SCHOOL | 500211603 | Ndwedwe | Design | Active - Contracted | 2015-07-06 |  | 2024-01-02 |  |  | 460800 | 2099200 | 2560000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13390 | W/500336996/RRR | KwaZulu-Natal | NDABAZAMANINA SECONDARY SCHOOL | 500336996 | Big Five Hlabisa | Project Initiation | Active - Not Contracted | 2017-03-01 |  | 2023-03-31 |  |  | 203000 | 923320 | 1126320 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13398 | W/500186221THS | KwaZulu-Natal | LETHITHEMBA S | 500186221 | KwaDukuza | Tender | Active - Contracted | 2016-04-01 |  | 2023-10-02 |  |  | 344880 | 1571120 | 1916000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 13409 | W/500108299/ECD | KwaZulu-Natal | BHEKAMANGWANE PRIMARY SCHOOL | 500108299 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2011-10-11 | 2012-12-12 | 2024-03-30 | 2023-06-30 | 2022-04-01 | 241000 | 1099000 | 1340000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13410 | W/500109187/UA | KwaZulu-Natal | BHEKUMUSA PRIMARY SCHOOL | 500321789 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2015-01-11 | 2023-06-01 | 2024-03-30 | 2023-06-30 | 2024-03-30 | 238466 | 1067328 | 1305794 | Education Infrastructure Grant | Upgrading and Additions
|  | 13411 | W/500121323/ECD | KwaZulu-Natal | DINABANYE PRIMARY SCHOOL | 500121323 | Jozini | Practical Completion (100%) | Active - Contracted | 2010-10-11 | 2016-08-05 | 2023-03-29 | 2023-03-31 | 2024-05-31 | 366000 | 1669000 | 2035000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13415 | W/500128760/ECD | KwaZulu-Natal | EKULINGENI PRIMARY SCHOOL | 500128760 | Jozini | Tender | Active - Not Contracted | 2015-01-11 |  | 2026-03-30 |  |  | 196020 | 1585204 | 1781224 | Equitable Share | Upgrading and Additions
|  | 13417 | W/500131313/ECD | KwaZulu-Natal | EMANQAYINI PRIMARY SCHOOL | 500131313 | Jozini | Practical Completion (100%) | Active - Contracted | 2015-01-11 | 2017-03-30 | 2023-10-02 | 2018-09-01 | 2023-05-31 | 307000 | 1399000 | 1706000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13418 | W/500132312/ECD | KwaZulu-Natal | EMBUYISELO PRIMARY SCHOOL | 500132312 | Jozini | Practical Completion (100%) | Active - Contracted | 2015-01-11 | 2017-03-30 | 2024-05-31 | 2018-01-30 | 2024-05-31 | 296000 | 1350000 | 1646000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13419 | W/500132460/ECD | KwaZulu-Natal | EMFIHLWENI PRIMARY SCHOOL | 500132460 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-01-11 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 313000 | 1424000 | 1737000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13420 | W/500136049/ECD | KwaZulu-Natal | ENDOMBENI PRIMARY SCHOOL | 500136049 | Mtubatuba | Tender | Active - Not Contracted | 2015-01-11 |  | 2026-03-30 |  |  | 196020 | 1676094 | 1872114 | Equitable Share | Upgrading and Additions
|  | 13422 | W/500152736/ECD | KwaZulu-Natal | GWALIWENI PRIMARY SCHOOL | 500152736 | Jozini | Tender | Active - Not Contracted | 2014-01-11 |  | 2026-03-31 |  |  | 196020 | 2110445 | 2306465 | Equitable Share | Upgrading and Additions
|  | 13425 | W/500111407/ECD | KwaZulu-Natal | KHULANGOLWAZI PRIMARY SCHOOL | 500111407 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2013-12-31 | 2017-05-15 | 2025-05-31 | 2018-10-02 | 2025-05-31 | 321000 | 1464000 | 1785000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13437 | W/500280386/ECD | KwaZulu-Natal | THANDIZWE PRIMARY SCHOOL | 500280386 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-01-11 | 2016-04-01 | 2023-05-31 | 2018-01-30 | 2023-05-31 | 344000 | 1565000 | 1909000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13441 | W/500441854/ECD | KwaZulu-Natal | MANKUNZI PRIMARY SCHOOL | 500441854 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2015-04-01 | 2022-10-02 | 2022-10-02 | 2023-10-02 | 269000 | 1226000 | 1495000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13447 | C/500442150/NS | KwaZulu-Natal | HHOYE SECONDARY SCHOOL | 500442150 | Jozini | Practical Completion (100%) | Active - Contracted | 2014-03-15 | 2016-09-20 | 2023-11-30 | 2020-11-30 | 2024-08-30 | 3212483 | 24711408 | 27923891 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13448 | C/500160062/UA | KwaZulu-Natal | IKUSASALETHU S | 500160062 | Mtubatuba | Final Completion | Active - Not Contracted | 2016-05-20 | 2022-03-31 | 2023-05-20 | 2022-05-31 | 2024-12-20 | 470160 | 2141840 | 2612000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13450 | C/500490324/ECD | KwaZulu-Natal | ITHUBALETHU PRIMARY SCHOOL | 500490324 | Msinga | Practical Completion (100%) | Active - Contracted | 2017-03-20 | 2020-09-01 | 2023-10-02 | 2022-04-30 | 2024-06-30 | 556507 | 2167493 | 2724000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13452 | C/500444629/NS | KwaZulu-Natal | KHINDI JOBE SECONDARY SCHOOL | 500444629 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2011-03-03 | 2021-12-31 | 2022-10-30 | 2022-11-30 | 2026-12-31 | 4989000 | 22725000 | 27714000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13458 | C/500446664/UA | KwaZulu-Natal | MACINGWANE S | 500446664 | Msinga | On Hold | Active - Not Contracted | 2015-03-20 |  | 2024-10-02 |  |  | 4023000 | 18328000 | 22351000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13461 | C/500215118/UA | KwaZulu-Natal | MORNINGSIDE C | 500215118 | Endumeni | Design | Active - Not Contracted | 2016-03-02 |  | 2026-04-02 |  |  | 4939020 | 22499980 | 27439000 | Equitable Share | Upgrading and Additions
|  | 13464 | C/500233100/LSEN | KwaZulu-Natal | NKUNYANA P | 500233100 | Nqutu | Design | Active - Not Contracted | 2016-11-20 |  | 2026-04-20 |  |  | 1792440 | 8165560 | 9958000 | Equitable Share | Upgrading and Additions
|  | 13468 | C/500440596/ECD | KwaZulu-Natal | OSUTHU P | 500440596 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-30 | 2020-08-01 | 2023-04-02 | 2022-08-27 | 2023-04-01 | 350640 | 1597360 | 1948000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13469 | C/500440633/ECD | KwaZulu-Natal | PHUMELA PRIMARY SCHOOL | 500440633 | Msinga | Terminated | Active - Not Contracted | 2016-06-29 | 2016-09-29 | 2023-10-02 | 2023-06-29 | 2023-04-29 | 351000 | 3346156 | 3697156 | Education Infrastructure Grant | Upgrading and Additions
|  | 13470 | C/500440670/UA | KwaZulu-Natal | PHUMELELA SECONDARY SCHOOL | 500440670 | Msinga | Final Completion | Active - Contracted | 2015-03-01 | 2016-09-26 | 2023-11-02 | 2018-04-02 | 2023-11-02 | 3422483 | 26326789 | 29749272 | Equitable Share | Upgrading and Additions
|  | 13472 | C/500442076/NS | KwaZulu-Natal | SIYAKHULA SECONDARY SCHOOL | 500442076 | Umhlabuyalingana | On Hold | Active - Not Contracted | 2015-02-20 |  | 2025-04-30 |  |  | 2500000 | 10140000 | 12640000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13473 | C/500277315/LSEN | KwaZulu-Natal | STANGER MANOR S | 500277315 | KwaDukuza | On Hold | Active - Not Contracted | 2016-10-13 |  | 2025-04-02 |  |  | 161205 | 1585749 | 1746954 | Education Infrastructure Grant | Upgrading and Additions
|  | 13474 | C/500277574/LSEN | KwaZulu-Natal | STANGER TRAINING CENTRE | 500277574 | KwaDukuza | Design | Active - Not Contracted | 2014-04-01 |  | 2026-10-02 |  |  | 161205 | 1585749 | 1746954 | Education Infrastructure Grant | Upgrading and Additions
|  | 13475 | C/500282643/FSS | KwaZulu-Natal | THOLINHLANHLA P | 500282643 | Umvoti | Feasibility | Active - Not Contracted | 2015-04-01 | 2017-04-01 | 2023-11-30 | 2017-11-30 | 2023-11-30 | 830039 | 4611330 | 5441369 | Education Infrastructure Grant | Upgrading and Additions
|  | 13476 | C/500283050/UA | KwaZulu-Natal | THONGWANA JUNIOR SECONDARY SCHOOL | 500283050 | Umhlabuyalingana | On Hold | Active - Not Contracted | 2020-05-12 |  | 2023-04-02 |  |  | 4049000 | 18446000 | 22495000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13477 | C/500298220/LSEN | KwaZulu-Natal | YWCA SPECIAL SCHOOL | 500298220 | Newcastle | Construction 76% - 99% | Active - Contracted | 2015-11-20 | 2019-12-01 | 2022-10-02 | 2022-08-30 | 2023-12-31 | 13502160 | 61509840 | 75012000 | Equitable Share | Upgrading and Additions
|  | 13479 | C/500442039/NS | KwaZulu-Natal | ZIMELE SECONDARY SCHOOL | 500442039 | Jozini | Practical Completion (100%) | Active - Contracted | 2022-04-01 |  | 2025-11-30 |  |  | 5268000 | 24000000 | 29268000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13480 | I/500268842/UA | KwaZulu-Natal | SITHOBELUMTHETHO SENIOR PRIMARY SCHOOL | 500268842 | Newcastle | Practical Completion (100%) | Active - Contracted | 2012-02-25 | 2017-10-12 | 2023-11-30 | 2022-09-01 | 2023-12-31 | 6519600 | 29700400 | 36220000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13481 | I/500318126/UA | KwaZulu-Natal | ZAMA S | 500318126 | Newcastle | Feasibility | Active - Not Contracted | 2012-02-23 |  | 2026-03-31 |  |  | 3331680 | 16658400 | 19990080 | Education Infrastructure Grant | Upgrading and Additions
|  | 13482 | W/500224442/SDS | KwaZulu-Natal | NDABOMUHLE PRIMARY SCHOOL | 500224442 | eThekwini | Tender | Active - Contracted | 2017-09-20 |  | 2025-02-24 |  |  | 189460 | 1050602 | 1240062 | Education Infrastructure Grant | Maintenance and Repairs
|  | 13485 | I/500286602/UA | KwaZulu-Natal | UKUPHUMULA SECONDARY SCHOOL | 500286602 | Nqutu | On Hold | Active - Not Contracted | 2016-09-29 |  | 2023-11-30 |  |  | 3308000 | 15073000 | 18381000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13488 | DB/500187590/ECD | KwaZulu-Natal | LOOTSHOEK P | 500187590 | Umvoti | Tender | Active - Contracted | 2015-11-20 |  | 2025-11-30 |  |  | 500000 | 1781506 | 2281506 | Education Infrastructure Grant | Upgrading and Additions
|  | 13492 | W/500281940/WS | KwaZulu-Natal | THIMUNI PRIMARY SCHOOL | 500281940 | Mkhambathini | Design | Active - Not Contracted | 2016-04-15 |  | 2024-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13494 | W/500174529/WS | KwaZulu-Natal | KHIPHUNYAWO SENIOR PRIMARY SCHOOL | 500174529 | uPhongolo | Tender | Active - Contracted | 2016-11-20 |  | 2025-10-30 |  |  | 90000 | 410000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13499 | DB/500272838/WS | KwaZulu-Natal | SOLOKOHLO PRIMARY SCHOOL | 500272838 | Dr Nkosazana Dlamini Zuma | Design | Potential | 2015-11-20 |  | 2024-04-16 |  |  | 27000 | 123000 | 150000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13502 | W/500234062/RRR | KwaZulu-Natal | NOKHALELA SECONDARY SCHOOL | 500234062 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2017-02-01 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 1505000 | 6840000 | 8345000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13504 | ED/-/HR/ PMU | KwaZulu-Natal | HR CAPACITATION PROGRAMME MANAGEMENT UNIT | 50000000 | uMngeni | Project Initiation | Active - Contracted | 2016-04-01 |  | 2025-03-31 |  |  | 0 | 28276000 | 28276000 | Equitable Share | New or Replaced Infrastructure
|  | 13518 | W/500225959/NS | KwaZulu-Natal | MANDLA MTHWEMTHWA COMPREHENSIVE HIGH SCHOOL(NDUMO NEW MODEL | 500225959 | Jozini | Design | Active - Contracted | 2013-02-02 |  | 2023-02-17 |  |  | 5413000 | 220158327 | 225571327 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13519 | W/500495356/NS | KwaZulu-Natal | NTULABAKAYISE HIGH SCHOOL | 500495356 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2012-11-07 | 2022-10-28 | 2023-10-28 | 2023-10-28 | 2023-10-28 | 7719000 | 35165000 | 42884000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13520 | W/500252895/UA | KwaZulu-Natal | QHOSHEYIPHETHE JUNIOR PRIMARY SCHOOL | 500252895 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-05-07 | 2015-09-02 | 2023-06-30 | 2017-03-25 | 2023-06-30 | 3444000 | 15691000 | 19135000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13522 | W/500228475/RRR | KwaZulu-Natal | NGONO SECONDARY SCHOOL | 500228475 | Nkandla | Practical Completion (100%) | Active - Contracted | 2013-08-18 | 2014-08-13 | 2023-03-31 | 2016-05-17 | 2023-03-20 | 9073000 | 33583000 | 42656000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13523 | W/500279165/WS | KwaZulu-Natal | ZWELITHULI PRIMARY SCHOOL | 500279165 | Msinga | Final Completion | Active - Contracted | 2015-11-20 | 2021-02-26 | 2025-06-30 | 2025-02-28 | 2025-03-31 | 592058 | 2697151 | 3289209 | Education Infrastructure Grant | Upgrading and Additions
|  | 13524 | C/500207903/UA | KwaZulu-Natal | MERLEWOOD INTERMEDIATE SCHOOL | 500207903 | Ray Nkonyeni | Construction 51% - 75% | Active - Contracted | 2014-01-28 | 2016-08-25 | 2023-07-02 | 2023-07-02 | 2025-11-03 | 7756000 | 35334000 | 43090000 | Equitable Share | Upgrading and Additions
|  | 13538 | W/500210715/WS | KwaZulu-Natal | MHUBHENI HIGH SCHOOL | 500210715 | Inkosi Langalibalele | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-06-01 | 2023-03-30 | 2022-03-30 | 2023-03-30 | 509985 | 2323265 | 2833250 | Education Infrastructure Grant | Upgrading and Additions
|  | 13542 | C/500490731/NS | KwaZulu-Natal | KHUBA SECONDARY SCHOOL | 500490731 | uMhlathuze | Project Initiation | Potential | 2021-10-06 |  | 2026-05-20 |  |  | 2700000 | 12300000 | 15000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13544 | DPW/NON SCHOOL MAINTENANCE/ALL DISTRICT | KwaZulu-Natal | NON SCHOOL MAINTENANCE | MAINTENANCE | uMngeni | Other - Packaged Ongoing Project | Active - Contracted | 2016-04-01 | 2020-06-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 7029810 | 83958930 | 90988740 | Education Infrastructure Grant | Maintenance and Repairs
|  | 13550 | BOREHOLE DOE | KwaZulu-Natal | BOREHOLE EDUCATION PROGRAMME | BOREHOLE DOE | The Msunduzi | Other - Packaged Ongoing Project | Potential | 2016-03-30 | 2022-06-02 | 2023-06-30 | 2023-03-01 | 2023-03-01 | 0 | 7630100 | 7630100 | Education Infrastructure Grant | Upgrading and Additions
|  | 13555 | C/MOBILE/ALL DISTRICTS | KwaZulu-Natal | MOBILE CLASSROOMS | MOBILE CLASSROOMS | eThekwini | Other - Packaged Ongoing Project | Potential | 2019-06-02 | 2020-06-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 0 | 128994200 | 128994200 | Equitable Share | Upgrading and Additions
|  | 13564 | I/500110815/UA | KwaZulu-Natal | Bombolo Combined | 500110815 | Nongoma | On Hold | Potential | 2014-05-17 | 2020-04-16 | 2023-08-02 | 2023-04-12 | 2024-03-04 | 4248000 | 19352000 | 23600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13565 | I/500184482/RRR | KwaZulu-Natal | DR J L DUBE SECONDARY SCHOOL | 500184482 | eThekwini | Design | Proposed | 2015-11-20 |  | 2024-03-30 |  |  | 6372000 | 29028000 | 35400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13566 | I/500429829/UA | KwaZulu-Natal | SIBUTHA SECONDARY SCHOOL | 500429829 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2013-10-25 | 2013-12-20 | 2023-02-10 | 2016-05-10 | 2024-08-31 | 2370780 | 10800220 | 13171000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13568 | I/500206904/NS | KwaZulu-Natal | MEADOWSWEET COMBINED SCHOOL | 500206904 | Okhahlamba | Design | Approved | 2016-04-06 |  | 2024-02-22 |  |  | 4248000 | 19352000 | 23600000 | Equitable Share | Upgrading and Additions
|  | 13574 | I/500444962/NS | KwaZulu-Natal | PHUTHINI S | I/500444962/UA | Okhahlamba | Tender | Active - Contracted | 2014-07-06 |  | 2024-03-03 |  |  | 4248000 | 19352000 | 23600000 | Equitable Share | New or Replaced Infrastructure
|  | 13576 | IDT/230732/15/UP | KwaZulu-Natal | nikela primary | 500230732 | Alfred Duma | Project Initiation | Potential | 2013-08-06 |  | 2023-09-23 |  |  | 6210000 | 28290000 | 34500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13587 | DB/500110667/WS | KwaZulu-Natal | BLUE MOUNTAIN PRIMARY SCHOOL | 500110667 | Emadlangeni | Practical Completion (100%) | Active - Contracted | 2010-10-05 | 2024-03-11 | 2024-03-21 | 2024-07-30 | 2025-09-30 | 175680 | 800320 | 976000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13595 | DB/500109039/RRR | KwaZulu-Natal | BHEKOKUHLE PRIMARY SCHOOL | 500109039 | eThekwini | Design | Active - Not Contracted | 2016-01-20 |  | 2026-03-29 |  |  | 1500279 | 6834606 | 8334885 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13629 | DB/500130684/SDS | KwaZulu-Natal | EMAHLEKWANE JUNIOR PRIMARY SCHOOL | 500130684 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2017-02-09 | 2020-04-30 | 2024-03-30 | 2021-02-28 | 2024-03-30 | 1996222 | 7509598 | 9505820 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13631 | DB/500131646/WS | KwaZulu-Natal | emaweleni primary | 500128131 | uMuziwabantu | Construction 26% - 50% | Active - Contracted | 2014-07-12 | 2021-01-15 | 2024-03-25 | 2024-03-30 | 2025-03-25 | 1980 | 9020 | 11000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13641 | C/500425426/ECD | KwaZulu-Natal | GLENGARRY JUNIOR SECONDARY SCHOOL | 500425426 | Umzimkhulu | Final Completion | Active - Contracted | 2014-03-25 | 2019-10-20 | 2023-12-30 | 2020-10-20 | 2024-12-20 | 726506 | 1990428 | 2716934 | Education Infrastructure Grant | Upgrading and Additions
|  | 13648 | W/500111296/SDS | KwaZulu-Natal | BONGUCELE JS | 500111296 | Umzumbe | Project Initiation | Active - Not Contracted | 2014-11-10 |  | 2024-03-10 |  |  | 836180 | 2164820 | 3001000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 13666 | C/500197839/UA | KwaZulu-Natal | MANYUSWA PRIMARY SCHOOL | 500197839 | eThekwini | Project Initiation | Potential | 2021-11-19 |  | 2023-06-16 |  |  | 2680000 | 12220000 | 14900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13672 | C/500197136/ECD | KwaZulu-Natal | MANKONJANE | 5001971136 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2015-08-01 | 2016-04-30 | 2023-05-29 | 2019-06-29 | 2024-10-29 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13690 | DB/500341917/WS | KwaZulu-Natal | BHAMBATHA SECONDARY SCHOOL | 500341917 | Msinga | Construction 26% - 50% | Active - Contracted | 2014-11-30 | 2020-05-31 | 2025-03-24 | 2023-03-20 | 2025-03-24 | 85634 | 674112 | 759746 | Education Infrastructure Grant | Upgrading and Additions
|  | 13691 | DB/500113701/WS | KwaZulu-Natal | BUNYEBETHU HIGH SCHOOL | 500113701 | Msinga | Construction 26% - 50% | Active - Contracted | 2014-11-10 | 2020-05-31 | 2024-03-25 | 2022-03-22 | 2024-03-25 | 274614 | 1251020 | 1525634 | Education Infrastructure Grant | Upgrading and Additions
|  | 13696 | C/500413882/LSEN | KwaZulu-Natal | NSIMBINI PRIMARY SCHOOL (MAYVILLE) | 500413882 | eThekwini | Practical Completion (100%) | Active - Contracted | 2013-05-30 | 2013-06-13 | 2026-09-03 | 2017-09-03 | 2026-09-03 | 2580000 | 4523000 | 7103000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13705 | C/500259814/UA | KwaZulu-Natal | SEATIDES COMBINED SCHOOL | 500259814 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-11-10 | 2016-01-09 | 2023-09-09 | 2018-09-09 | 2023-09-09 | 799000 | 3640000 | 4439000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13706 | DB/500263070/ECD | KwaZulu-Natal | SIBOMVU PS | 500263070 | Nkandla | Design | Potential | 2014-11-10 |  | 2026-03-31 |  |  | 1386000 | 554000 | 1940000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13711 | DB/500266030/ECD | KwaZulu-Natal | SIMANJALO PRIMARY SCHOOL | 500266030 | Nqutu | Design | Active - Contracted | 2014-08-02 |  | 2024-05-15 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13726 | IDT/500000000/CHEM FY | KwaZulu-Natal | CHEMICAL TOILETS | CHEMICAL TOILETS | uMngeni | Other - Packaged Ongoing Project | Active - Contracted | 2013-04-01 | 2014-04-01 | 2023-07-31 | 2022-07-31 | 2022-10-31 | 3690000 | 16810000 | 20500000 | Equitable Share | Maintenance and Repairs
|  | 13834 | new sch | North West | New Schweizer Reneke Primary | 600000000 | Tswaing | Construction 26% - 50% | Active - Contracted | 2013-08-01 | 2022-10-01 | 2025-03-31 | 2023-12-30 | 2025-03-31 | 7380720 | 33623280 | 41004000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13838 | 100303 | North West | Dirang Ka Natla Primary | 600100303 | City of Matlosana | Design | Active - Contracted | 2015-07-01 |  | 2026-03-31 |  |  | 6300000 | 28700000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13858 | 100667 | North West | Kgabalatsane Primary | 600100667 | Local Municipality of Madibeng | Construction 76% - 99% | Active - Contracted | 2020-03-04 | 2021-07-25 | 2025-02-04 | 2025-03-24 | 2025-03-31 | 4025000 | 19975000 | 24000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13860 | 102036 | North West | Stinkhoutboom Primary | 600102036 | Mafikeng | Feasibility | Active - Contracted | 2015-03-21 |  | 2026-03-01 |  |  | 6300000 | 28700000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13862 | 600100679 | North West | Kgetleng Primary | 600000000 | Kgetlengrivier | Construction 26% - 50% | Active - Contracted | 2015-03-02 |  | 2026-03-31 |  |  | 6300000 | 28700000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13864 | NEW TLAKGAMENG | North West | Tlakgameng Primary | 600000000 | Kagisano | Construction 76% - 99% | Active - Contracted | 2015-03-21 | 2021-01-25 | 2026-03-31 | 2022-11-23 | 2026-03-31 | 7200000 | 32800000 | 40000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13866 | TIGANE | North West | Tigane Secondary | 600000000 | City of Matlosana | Construction 1% - 25% | Active - Contracted | 2015-03-29 | 2023-10-30 | 2026-03-01 | 2023-12-30 | 2026-03-31 | 9000000 | 41000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13871 | 101312 | North West | Mokala Primary School | 600000000 | Ratlou | Tender | Active - Contracted | 2019-01-03 |  | 2026-03-31 |  |  | 5400000 | 24600000 | 30000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13875 | 102397 | North West | Rekgonne - Bapo Special | 600102397 | Local Municipality of Madibeng | Feasibility | Active - Contracted | 2014-01-01 |  | 2026-03-15 |  |  | 13860000 | 69140000 | 83000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13877 | 100516 | North West | Coligny Special | 600100516 | Ditsobotla | Feasibility | Active - Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 6210000 | 28290000 | 34500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13889 | 100528 | North West | Ikaneng High | 600100528 | Moretele | Feasibility | Active - Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 3366252 | 11969748 | 15336000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13891 | 101221 | North West | Mamodibo High | 600101221 | Moretele | Construction 76% - 99% | Active - Contracted | 2018-04-01 | 2026-01-12 | 2026-02-24 | 2026-03-24 | 2026-03-24 | 29329492 | 89594580 | 118924072 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13900 | 100766 | North West | Kosea Moeka Primary | 600100766 | Moretele | Tender | Active - Contracted | 2013-01-07 |  | 2025-03-31 |  |  | 2054160 | 9357840 | 11412000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13909 | 101902 | North West | Sediko Primary School | 600101902 | City of Matlosana | Construction 1% - 25% | Active - Contracted | 2015-05-01 |  | 2025-03-31 |  |  | 5000000 | 25000000 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13923 | 100612 | North West | Kagiso Barolong Secondary | 600100612 | Ratlou | Construction 76% - 99% | Active - Contracted | 2015-03-01 |  | 2026-03-31 |  |  | 0 | 73052000 | 73052000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13932 | 101357 | North West | Monchusi Secondary | 600101357 | Kagisano | Design | Active - Contracted | 2015-03-29 |  | 2026-03-31 |  |  | 0 | 69000000 | 69000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13936 | 101358 | North West | Monnamere Primary | 600101358 | Ramotshere Moiloa | Construction 26% - 50% | Active - Contracted | 2015-03-01 |  | 2026-03-31 |  |  | 0 | 83971000 | 83971000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13944 | 102040 | North West | Suping Primary | 600102040 | Ramotshere Moiloa | Final Completion | Active - Contracted | 2013-09-02 | 2021-10-20 | 2026-03-29 | 2026-03-05 | 2026-03-31 | 380700 | 1734300 | 2115000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13947 | 100116 | North West | Bloemhof Primary | 600100116 | Lekwa-Teemane | Practical Completion (100%) | Active - Contracted | 0209-07-18 | 2021-12-19 | 2026-03-29 | 2023-08-29 | 2026-03-30 | 323000 | 4396000 | 4719000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 13956 | 102132 1 | North West | Tiang Primary | 600102132 | City of Matlosana | Practical Completion (100%) | Active - Contracted | 2018-01-12 | 2022-11-30 | 2026-01-15 | 2025-03-01 | 2026-03-31 | 0 | 3535000 | 3535000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13965 | 600100014 | North West | Agisanang Primary | 600100014 | Maquassi Hills | Project Initiation | Active - Contracted | 2020-04-01 |  | 2025-03-15 |  |  | 446000 | 2033000 | 2479000 | Education Infrastructure Grant | Upgrading and Additions
|  | 13980 | FS 2017/18 | North West | Full Service schools for 2017/18 | 600000000 | Mafikeng | Pre - Feasibility | Active - Contracted | 2017-04-03 |  | 2025-03-15 |  |  | 4813000 | 21927000 | 26740000 | Education Infrastructure Grant | Upgrading and Additions
|  | 14006 | 102218 | North West | Tshedimoso Primary | 600102218 | Mafikeng | Tender | Active - Contracted | 2020-03-20 |  | 2025-03-31 |  |  | 0 | 30000000 | 30000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 14075 | 100423 | North West | Gaseitsiwe High | 600100423 | Moretele | Tender | Active - Contracted | 2019-04-01 |  | 2025-03-01 |  |  | 0 | 30000000 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 14094 | 101824 | North West | Relebogile Primary | 600101824 | Moretele | Tender | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14138 | 102388(1) | North West | Moedwil Combined | 600102388 | Kgetlengrivier | Design | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 83410000 | 296590000 | 380000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14139 | 101996 | North West | Signal Hill Primary | 600101996 | Mafikeng | Pre - Feasibility | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 828000 | 3772000 | 4600000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14175 | 102163 | North West | Tlhalefang Primary | 600102163 | Ditsobotla | Construction 26% - 50% | Active - Contracted | 2015-02-03 | 2019-05-15 | 2026-03-31 | 2024-12-31 | 2026-03-31 | 2572020 | 11716980 | 14289000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14185 | 101846 | North West | Retshegeditse Primary | 600101846 | Greater Taung | Pre - Feasibility | Active - Contracted | 2015-02-28 |  | 2026-03-31 |  |  | 0 | 2003000 | 2003000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14240 | 102109 | North West | Thulare High | 600102109 | Moretele | Construction 51% - 75% | Active - Contracted | 2017-08-01 | 2020-11-10 | 2024-03-01 | 2022-05-09 | 2022-05-09 | 14174166 | 78745364 | 92919530 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14245 | 1021611 | North West | Tlhakajeng Primary | 600102161 | Ratlou | Feasibility | Active - Contracted | 2020-01-01 |  | 2026-03-15 |  |  | 630000 | 2870000 | 3500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14308 | 102199 | North West | Treasure Trove Primary | 600102199 | Ditsobotla | Pre - Feasibility | Active - Contracted | 2017-03-01 |  | 2025-03-31 |  |  | 0 | 14000000 | 14000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 14341 | 102181 | North West | Tlokwe Secondary | 600102181 | Ventersdorp/Tlokwe | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2021-01-12 | 2026-02-23 | 2026-02-24 | 2026-03-25 | 25742355 | 68582056 | 94324411 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14372 | 100734(1) | North West | Klerksdorp Hoer Tegniese | 600100734 | City of Matlosana | Practical Completion (100%) | Active - Contracted | 2014-01-02 | 2014-10-30 | 2025-03-31 | 2017-07-30 | 2025-03-31 | 0 | 5144000 | 5144000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 14399 | CORPO | North West | CORPORATE | 600000000 | Mafikeng | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2024-03-04 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 0 | 70000000 | 70000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 14400 | MAINT BOJ | North West | BOJANALA DISTRICT OFFFICE | 600000000 | Rustenburg | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2015-11-30 | 2026-03-31 | 2019-12-31 | 2026-03-31 | 0 | 12000000 | 12000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 14401 | MAINT NGAKA2 | North West | Ngaka Office | 600000000 | Mafikeng | Construction 51% - 75% | Active - Contracted | 2015-03-31 | 2015-05-01 | 2026-03-31 | 2019-03-01 | 2026-03-31 | 0 | 12000000 | 12000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 14402 | MAINT DRRSM | North West | DR RUTH S MOMPATI DISTRICT | 600000000 | Naledi | Construction 51% - 75% | Active - Contracted | 2015-03-29 | 2015-05-02 | 2026-03-31 | 2017-03-31 | 2026-03-31 | 0 | 12000000 | 12000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 14403 | MAINT DRKK1 | North West | DR KENNETH KAUNDA DISTRICT | 600000000 | Ventersdorp/Tlokwe | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-05-31 | 2026-03-31 | 2019-03-31 | 2026-03-31 | 0 | 12000000 | 12000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 14405 | EPWP | North West | EPWP PROGRAMME | 600000000 | Mafikeng | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2020-04-10 | 2024-03-31 | 2022-04-05 | 2025-03-31 | 0 | 2008000 | 2008000 | Expanded Public Works Programme Intergrated Grant for Provinces | Non-Infrastructure
|  | 14406 | COMPENSATION | North West | Funding through EIG as per DORA | 600000000 | Mafikeng | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2015-04-02 | 2026-03-31 | 2023-03-31 | 2026-03-31 | 0 | 62000000 | 62000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 14884 | DOE1/13/14 | Free State | REHOPOTSWE PRIMARY | 445802154 | Dihlabeng | Practical Completion (100%) | Active - Contracted | 2013-04-01 | 2015-03-05 | 2023-07-30 | 2023-03-31 | 2023-03-31 | 8012000 | 55107000 | 66924747 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14885 | DOE2/13/14 | Free State | TLHOLO | BOTSHABELO | Mangaung | Construction 51% - 75% | Active - Contracted | 2013-04-01 | 2015-03-03 | 2023-07-30 | 2023-03-31 | 2023-03-31 | 5167000 | 46507000 | 51674000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14887 | DOE1/15/16 | Free State | DR SELLO | VILJOENSKROON | Matjhabeng | Construction 26% - 50% | Active - Contracted | 2015-04-01 | 2019-02-18 | 2024-03-31 | 2020-10-18 | 2024-03-31 | 12500000 | 37500000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14888 | DOE2/14/15 | Free State | MALEBOGO PRIMARY SCHOOL | HERTZORGVILLE | Tokologo | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2015-03-04 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 12386000 | 37160000 | 49546000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14891 | DOE2/15/16 | Free State | GM POLORI | HOOPSTAD | Tswelopele | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-09-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 9219000 | 52656000 | 61875000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14895 | DOE3/13/14 | Free State | FINAL ACCOUNTS | BLOEMFONTEIN | Mangaung | Not Applicable | Active - Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 72998000 | 72998000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14897 | DOE07/14/15 | Free State | BOITUMELONG SPECIAL | THABA NCHU | Mangaung | Design | Active - Contracted | 2014-04-01 |  | 2026-03-31 |  |  | 10000000 | 40000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14900 | DOE04/15/16 | Free State | THEMBALIHLE PRIMARY | VREDE | Phumelela | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-09-01 | 2023-03-30 | 2023-03-31 | 2023-03-31 | 14525000 | 59574000 | 74099000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14901 | DOE05/15/16 | Free State | RUANG TSEBO PRIMARY | CLOCOLAN | Setsoto | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-09-01 | 2023-03-30 | 2023-03-31 | 2023-03-31 | 15000000 | 61367000 | 76367000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14902 | DOE06/15/16 | Free State | TROPMSBURG SPECIAL SCHOOL | TROMPSBURG | Kopanong | Design | Active - Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 23750000 | 66250000 | 90000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14903 | DOE07/15/16 | Free State | MOOIFONTEIN PRIMARY FARM | MOOIFOTEIN | Mohokare | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-09-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 14009000 | 62026000 | 76035000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14904 | DOE08/15/16 | Free State | Leboneng Special School | Lejweleputswa | Matjhabeng | Design | Active - Contracted | 2015-04-01 |  | 2024-03-31 |  |  | 5000000 | 45000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14905 | DOE09/15/16 | Free State | BREDA PRIMARY FARM | THABO MOFUTSANYANA | Dihlabeng | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2015-04-15 | 2024-03-31 | 2021-03-31 | 2024-03-31 | 10000000 | 61519920 | 71519920 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14906 | DOE10/15/16 | Free State | ORANJEKRAG PRIMARY FARM | XHARIEP | Tswelopele | Design | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 10000000 | 61151992 | 71151992 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 14907 | DOE11/15/16 | Free State | Meqheleng | conversions | Setsoto | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2019-02-18 | 2025-04-01 | 2024-03-31 | 2024-01-31 | 0 | 6000000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 14910 | DOE2/13/14P | Free State | EUREKA EXAM PRINTING CENTRE | BLOEMFONTEIN | Mangaung | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2015-11-02 | 2024-03-31 | 2019-02-28 | 2021-03-31 | 0 | 37971000 | 37971000 | Education Infrastructure Grant | Upgrading and Additions
|  | 15335 | DOE22/13/14 | Free State | MAINTENACE AND REPAIRS (SCHOOLS) | VARIOUS | Masilonyana | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2015-04-30 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 0 | 403614000 | 403614000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 15336 | DOE1/13/14P | Free State | MAINTENACE AND REPAIRS ( BUILDINGS) | VARIOUS | Masilonyana | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-04-30 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 0 | 34461000 | 34461000 | Infrastructure Enhancement Allocation | Maintenance and Repairs
|  | 15337 | DOE40/13/14 | Free State | KAGISHO SHANDUKA TRUST | VARIOUS | Masilonyana | Not Applicable | Active - Contracted | 2015-11-01 |  | 2025-04-01 |  |  | 0 | 200000000 | 200000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 15338 | DOE08/17/18 | Free State | boiphihlelo | lab | Ngwathe | Other - Packaged Ongoing Project | Active - Contracted | 2014-09-03 | 2016-01-11 | 2025-04-01 | 2024-03-31 | 2024-03-31 | 1230505 | 31757577 | 32988082 | Education Infrastructure Grant | Upgrading and Additions
|  | 15339 | DOE06/13/14 | Free State | schools office | admin block | Mangaung | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2016-12-01 | 2025-04-01 | 2024-03-31 | 2024-01-31 | 3702857 | 45812834 | 49515691 | Education Infrastructure Grant | Upgrading and Additions
|  | 15340 | DOE07/13/14 | Free State | additional classrooms | classroom | Moqhaka | Project Initiation | Active - Contracted | 2015-04-01 |  | 2025-04-01 |  |  | 9121970 | 113886246 | 123008216 | Education Infrastructure Grant | Upgrading and Additions
|  | 15341 | DOE08/13/14 | Free State | ntswanatsatsi | toilet block | Mafube | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2016-12-01 | 2025-04-01 | 2024-10-25 | 2025-01-31 | 2972102 | 16790838 | 19762940 | Education Infrastructure Grant | Upgrading and Additions
|  | 15342 | DOE08/14/15 | Free State | phetogane sec school | connections | Mangaung | Other - Packaged Ongoing Project | Active - Contracted | 2014-04-01 | 2016-12-01 | 2025-03-31 | 2024-03-31 | 2024-03-31 | 0 | 34998000 | 34998000 | Education Infrastructure Grant | Upgrading and Additions
|  | 15344 | DOE10/13/14 | Free State | dibaseholo | Grade R | Ngwathe | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2016-12-01 | 2025-04-01 | 2024-03-31 | 2024-03-31 | 5888864 | 46855870 | 52744734 | Education Infrastructure Grant | Upgrading and Additions
|  | 15346 | DOE13/13/14 | Free State | TSHEDISO XOLANI | Nutrition | Mafube | Construction 51% - 75% | Active - Contracted | 0201-11-01 | 2016-12-01 | 2024-03-31 | 2024-10-25 | 2024-03-31 | 5462927 | 70503444 | 75966371 | Education Infrastructure Grant | Upgrading and Additions
|  | 15672 | DOE14/13/14 | Free State | Mokwallo | fence | Ngwathe | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2016-12-01 | 2025-04-01 | 2024-10-25 | 2025-01-31 | 0 | 101250000 | 101250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 16136 | DOE03NCAR002 | Northern Cape | BARKLEY ROOILAND (NEW SCHOOL) | NEW | Dikgatlong | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2019-04-24 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 27022821 | 94123375 | 121146196 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16137 | DOE01NCAR051 | Northern Cape | BATLHARO TLHAPING SECONDARY SCHOOL | 300100095 | Ga-Segonyana | Practical Completion (100%) | Active - Contracted | 2013-10-02 | 2013-10-04 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 3712186 | 24747907 | 43693739 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16192 | DOE03NCAR017 | Northern Cape | ISAGONTLE PRIMARY SCHOOL | 300100555 | Ga-Segonyana | Practical Completion (100%) | Approved | 2015-04-01 | 2017-07-12 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 2540628 | 5203140 | 7743768 | Education Infrastructure Grant | Upgrading and Additions
|  | 16195 | ABLUTION BLOCK TBD1 | Northern Cape | ITOTLENG COMMERCIAL SECONDARY SCHOOL | 300100573 | Joe Morolong | Feasibility | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1313059 | 1313059 | Education Infrastructure Grant | Upgrading and Additions
|  | 16196 | DOE01NCAR064 | Northern Cape | NEW SCHOOL VALSPAN SECONDARY SCHOOL | NEW | Phokwane | Practical Completion (100%) | Active - Contracted | 2014-07-21 | 2014-07-22 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 17241106 | 51789683 | 69030789 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16202 | DOE03NCAR004 | Northern Cape | JTG (NEW SCHOOL AND HOSTEL) | NEW | Joe Morolong | Construction 26% - 50% | Approved | 2016-04-01 | 2016-06-02 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 56997149 | 198527167 | 255524316 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16209 | DOE03NCAR001 | Northern Cape | REPLACEMENT SCHOOL-KHIBA MIDDLE SCHOOL | 300100707 | Ga-Segonyana | Practical Completion (100%) | Approved | 2016-04-01 | 2016-05-18 | 2025-05-16 | 2025-05-30 | 2025-06-27 | 9696694 | 65651464 | 94040984 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16214 | DOE03NCAR022 | Northern Cape | KONING PRIMARY SCHOOL | 300100754 | Joe Morolong | Practical Completion (100%) | Approved | 2015-04-01 | 2015-04-10 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1449223 | 3607076 | 5056299 | Education Infrastructure Grant | Upgrading and Additions
|  | 16216 | DOE03NCAR012 | Northern Cape | KP TOTO TECHNICAL AND COMMERCIAL SECONDARY SCHOOL | 300100769 | Ga-Segonyana | Practical Completion (100%) | Approved | 2015-04-01 | 2019-06-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1900000 | 2507309 | 4407309 | Education Infrastructure Grant | Upgrading and Additions
|  | 16227 | JTGDT013/2018 | Northern Cape | LEARAMELE SPECIAL SCHOOL FOR THE SMH | 300102379 | Ga-Segonyana | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 4411277 | 5046436 | Education Infrastructure Grant | Upgrading and Additions
|  | 16231 | DOE01NCAR060 | Northern Cape | LESEDI SECONDARY SCHOOL | 300100873 | Ga-Segonyana | Construction 26% - 50% | Active - Contracted | 2013-10-03 | 2013-10-04 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 9000150 | 25238948 | 36186682 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16235 | DRPW:TBD. | Northern Cape | LUCRETIA INTERMEDIATE SCHOOL | 300014206 | Sol Plaatjie | Feasibility | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 479149 | 3000000 | 3479149 | Education Infrastructure Grant | Upgrading and Additions
|  | 16240 | DOE03NCAR013 | Northern Cape | MAKGOLOKWE SECONDARY SCHOOL | 300101030 | Ga-Segonyana | Practical Completion (100%) | Approved | 2015-04-01 | 2017-07-05 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2314460 | 3154041 | 5468501 | Education Infrastructure Grant | Upgrading and Additions
|  | 16247 | DOE03NCAR009 | Northern Cape | MOHOLENG PRIMARY SCHOOL | 300101304 | Ga-Segonyana | Practical Completion (100%) | Approved | 2015-04-01 | 2016-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1854658 | 2273292 | 4127950 | Education Infrastructure Grant | Upgrading and Additions
|  | 16251 | DOE03NCAR025 | Northern Cape | NAMETSEGANG SECONDARY SCHOOL | 300101486 | Joe Morolong | Practical Completion (100%) | Approved | 2016-01-01 | 2017-06-08 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 4910537 | 4910537 | Education Infrastructure Grant | Upgrading and Additions
|  | 16261 | JTGDT001/28 | Northern Cape | AJ FERREIRA SEKONDERE SKOOL | 300041401 | Dawid Kruiper | Construction 76% - 99% | Active - Contracted | 2019-06-06 | 2019-11-12 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 591646 | 236911 | 828557 | Education Infrastructure Grant | Upgrading and Additions
|  | 16265 | DRPW TBD | Northern Cape | GN PRESSLY INTERMEDIATE SCHOOL | 300013203 | Dikgatlong | Feasibility | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 938025 | 5211251 | 6149276 | Education Infrastructure Grant | Upgrading and Additions
|  | 16277 | DOE03NCAR023 | Northern Cape | PERTH PRIMARY SCHOOL | 300101614 | Joe Morolong | Practical Completion (100%) | Approved | 2015-04-01 | 2016-09-06 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 3940822 | 2869452 | 6810274 | Education Infrastructure Grant | Upgrading and Additions
|  | 16300 | DOE03NCAR018 | Northern Cape | REKGARATLHILE HIGH SCHOOL | 300101821 | Ga-Segonyana | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-07 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1339301 | 6087736 | 8482793 | Education Infrastructure Grant | Upgrading and Additions
|  | 16301 | DOE03NCAR029 | Northern Cape | RELEKILE PRIMARY SCHOOL | 300101827 | Ga-Segonyana | Practical Completion (100%) | Approved | 2016-04-01 | 2016-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1242431 | 2487233 | 3729664 | Education Infrastructure Grant | Upgrading and Additions
|  | 16311 | DOE01NCAR066 | Northern Cape | ROODEPAN SECONDARY SCHOOL (NEW) | NEW | Sol Plaatjie | Practical Completion (100%) | Active - Contracted | 2014-05-14 | 2014-05-15 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 11259919 | 53774695 | 69456953 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16327 | DOE03NCAR011 | Northern Cape | TSHIMOLOGO INTERMEDIATE SCHOOL | 300102234 | Ga-Segonyana | Practical Completion (100%) | Approved | 2015-04-01 | 2017-05-04 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1770706 | 2729675 | 4500381 | Education Infrastructure Grant | Upgrading and Additions
|  | 16332 | DOE03NCAR021 | Northern Cape | VAN ZYLSRUS INTERMEDI?RE SKOOL | 300045213 | Joe Morolong | Practical Completion (100%) | Approved | 2015-04-01 | 2017-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 4079958 | 7071756 | 11151714 | Education Infrastructure Grant | Upgrading and Additions
|  | 16340 | DOE01NCAR056 | Northern Cape | WRENCHVILLE PRIMERE SKOOL | 300045218 | Ga-Segonyana | Practical Completion (100%) | Active - Contracted | 2014-06-02 | 2014-06-03 | 2022-09-09 | 2022-10-28 | 2022-11-30 | 10049035 | 65380692 | 75429727 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 16365 | P9010996 | Eastern Cape | NOMATHEMBA PUBLIC SCHOOL | 200200605 | Amahlathi | Project Initiation | Proposed | 2015-04-01 |  | 2024-03-31 |  |  | 0 | 1689732 | 1689732 | Education Infrastructure Grant | Upgrading and Additions
|  | 16376 | DOE-SAL-2015/16 | Free State | DORA FUNDED POSTS | VARIOUS | Masilonyana | Not Applicable | Active - Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 114688000 | 0 | 114688000 | Education Infrastructure Grant | Non-Infrastructure
|  | 19135 | DB/500224183/SDS | KwaZulu-Natal | NDABAYAKHE PRIMARY SCHOOL | 500224183 | uMhlathuze | Design | Active - Not Contracted | 2017-09-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 19155 | W/500154734/UA | KwaZulu-Natal | HENRYVILLE PRIMARY SCHOOL | 500154734 | The Msunduzi | Final Completion | Active - Contracted | 2015-05-01 | 2015-07-01 | 2025-05-31 | 2017-06-30 | 2025-05-31 | 4931000 | 22461000 | 27392000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19159 | W/500327191/WS | KwaZulu-Natal | POTSHINI SECONDARY SCHOOL | 500327191 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-03-01 | 2018-04-27 | 2024-03-30 | 2023-06-30 | 2021-09-30 | 491000 | 15807637 | 16298637 | Education Infrastructure Grant | Upgrading and Additions
|  | 19162 | W/500113553/RRR | KwaZulu-Natal | BUKIMVELO HIGH SCHOOL(Retender) | 500113553 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2014-04-06 | 2015-04-01 | 2024-03-30 | 2016-03-30 | 2021-03-31 | 21600 | 98400 | 120000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19169 | W/500161838/NS | KwaZulu-Natal | INANDA SPECIAL SCHOOL | 500161838 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-09-21 | 2018-04-27 | 2023-08-31 | 2019-03-29 | 2023-05-31 | 38600640 | 175847360 | 214448000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19234 | W/500148555/SDS | KwaZulu-Natal | GIBA PRIMARY SCHOOL | 500148555 | Msinga | Tender | Active - Not Contracted | 2014-04-06 | 2022-04-30 | 2023-03-30 | 2024-03-30 | 2025-04-30 | 276935 | 8927344 | 9204279 | Education Infrastructure Grant | Maintenance and Repairs
|  | 19268 | W/500142524/RRR | KwaZulu-Natal | ETSHENI PRIMARY SCHOOL | 500142524 | Umzumbe | Final Completion | Active - Contracted | 2014-07-30 | 2014-10-28 | 2023-12-28 | 2024-12-28 | 2024-05-31 | 2111000 | 9615000 | 11726000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19274 | W/500141340/RRR | KwaZulu-Natal | ESIQIWINI SECONDARY SCHOOL | 500141340 | Mtubatuba | Design | Active - Not Contracted | 2014-07-29 |  | 2023-11-30 |  |  | 1078560 | 4913440 | 5992000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19276 | W/500155622/RRR | KwaZulu-Natal | Hillview PS | 500155622 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-05-21 | 2015-12-20 | 2025-05-30 | 2017-03-30 | 2025-05-30 | 675000 | 5176000 | 5851000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19280 | W/500563852/SDS | KwaZulu-Natal | LETHUKUTHULA PRIMARY SCHOOL | 500186221 | Dannhauser | Construction 1% - 25% | Active - Contracted | 2014-07-30 | 2014-12-05 | 2023-09-10 | 2023-09-10 | 2023-09-10 | 665 | 3028 | 3693 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19282 | W/500341251/RRR | KwaZulu-Natal | Magemfane High School | 500341251 | uMlalazi | Tender | Active - Not Contracted | 2015-06-20 |  | 2025-12-18 |  |  | 474000 | 2158000 | 2632000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19291 | DOE MAINTENANCE | KwaZulu-Natal | UMGUNGUNDLOVU | MAINTENANCE | uMlalazi | Construction 26% - 50% | Active - Not Contracted | 2016-04-06 | 2020-06-01 | 2023-03-30 | 2022-03-30 | 2024-03-30 | 0 | 76000000 | 76000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 19294 | C/500164798/LSEN | KwaZulu-Natal | INKAZIMULO PRIMARY SCHOOL | 500164798 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-04-06 | 2015-04-01 | 2023-06-30 | 2020-06-30 | 2024-12-30 | 841000 | 3833000 | 4674000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19758 | DB/500175565/SDS | KwaZulu-Natal | KHUTHALA PRIMARY SCHOOL | 500175565 | eThekwini | Practical Completion (100%) | Active - Contracted | 2018-10-06 | 2019-01-17 | 2022-06-30 | 2023-05-05 | 2027-06-30 | 859317 | 3914668 | 4773985 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19772 | C/500427054/NS | KwaZulu-Natal | Mthwane SS | 500427054 | Umzimkhulu | Design | Active - Contracted | 2012-04-06 |  | 2026-02-05 |  |  | 250000 | 4968000 | 5218000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 19774 | DB/500221963/SDS | KwaZulu-Natal | KHULANGOLWAZI SPECIAL SCHOOL | 500221963 | eThekwini | Final Completion | Approved | 2014-05-04 | 2018-05-02 | 2023-08-29 | 2023-08-29 | 2025-08-29 | 476332 | 2169958 | 2646290 | Education Infrastructure Grant | Maintenance and Repairs
|  | 19778 | W/500158767/WS | KwaZulu-Natal | COSMO PRIMARY SCHOOL | 500158767 | uMngeni | Construction 51% - 75% | Approved | 2017-09-01 | 2019-09-28 | 2023-03-29 | 2022-03-29 | 2023-03-29 | 875000 | 2000000 | 2875000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19787 | DB/500124468/WS | KwaZulu-Natal | DUMILE PRIMARY SCHOOL | 500124468 | Umhlabuyalingana | Design | Active - Contracted | 2011-10-21 |  | 2025-03-25 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 19796 | DB/500222481/SDS | KwaZulu-Natal | MZOMUHLE PRIMARY SCHOOL | 5000000 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-09-01 | 2018-12-10 | 2023-06-08 | 2023-06-08 | 2023-07-31 | 986192 | 4492654 | 5478846 | Education Infrastructure Grant | Maintenance and Repairs
|  | 19820 | DB/500124098/SDS | KwaZulu-Natal | DUMANGOBUHLE PRIMARY SCHOOL | 500124098 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2018-07-10 | 2019-10-01 | 2024-03-20 | 2020-09-30 | 2027-03-20 | 1447027 | 6592010 | 8039037 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 19864 | I/500168091/UA | KwaZulu-Natal | Isikhalisezwe H | 500168091 | Newcastle | Design | Active - Contracted | 2011-03-06 |  | 2026-03-31 |  |  | 1166726 | 5555840 | 6722566 | Education Infrastructure Grant | Upgrading and Additions
|  | 19867 | DB/500427979/SDS | KwaZulu-Natal | SIZAKANCANE PRIMARY SCHOOL | 500427979 | Newcastle | Final Completion | Approved | 2016-06-06 | 2016-12-20 | 2023-06-07 | 2019-08-20 | 2025-10-20 | 419096 | 1576600 | 1995696 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20004 | DB/500268361/ECD | KwaZulu-Natal | SISIZAKELE PRIMARY SCHOOL | 500268361 | Newcastle | Tender | Active - Contracted | 2014-11-01 |  | 2025-12-01 |  |  | 811260 | 2500000 | 3311260 | Education Infrastructure Grant | Upgrading and Additions
|  | 20006 | C/500426536/ECD | KwaZulu-Natal | MANDLAZI JUNIOR SECONDARY SCHOOL | 500426536 | Mfolozi | Tender | Active - Contracted | 2014-03-28 |  | 2026-03-31 |  |  | 519000 | 2452190 | 2971190 | Education Infrastructure Grant | Upgrading and Additions
|  | 20111 | W/Admin/RRR | KwaZulu-Natal | DOKKIES, OFFICES | W/Admin/RRR | eThekwini | Design | Active - Not Contracted | 2014-05-20 |  | 2024-06-30 |  |  | 59693999 | 271939328 | 331633327 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 20112 | W/500413845/NS | KwaZulu-Natal | J G ZUMA SECONDARY SCHOOL | 500413845 | eThekwini | Construction 26% - 50% | Active - Contracted | 2015-05-08 | 2015-06-15 | 2024-12-30 | 2026-12-30 | 2024-12-30 | 16406689 | 90996611 | 107403300 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 20115 | W/500254116/RRR | KwaZulu-Natal | QUEENSBURGH HIGH SCHOOL | 500254116 | eThekwini | Feasibility | Active - Not Contracted | 2014-11-29 |  | 2023-06-21 |  |  | 1321155 | 6018595 | 7339750 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20116 | W/STANGER DISTRICT/RRR | KwaZulu-Natal | NEW STANGER DISTRICT OFFICE | STANGER DISTRICT | KwaDukuza | Project Initiation | Active - Contracted | 2016-05-14 |  | 2024-03-22 |  |  | 1301000 | 2581000 | 3882000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 20118 | W/500119214/RRR | KwaZulu-Natal | DABEKA SECONDARY SCHOOL | 500119214 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-06-04 | 2015-07-04 | 2023-05-31 | 2017-05-04 | 2023-05-31 | 2028000 | 9240000 | 11268000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20119 | W/500169719/RRR | KwaZulu-Natal | ITHWELENYE PRIMARY SCHOOL | 500169719 | eThekwini | Tender | Active - Contracted | 2014-10-01 |  | 2023-06-30 |  |  | 4899181 | 22318492 | 27217673 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20197 | EDDP184/325 | Limpopo | Maboko Nkomo Secondary | 994401403 | Greater Giyani | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2017-05-15 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2680000 | 10720000 | 13400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20198 | EDDP184/294 | Limpopo | Mahumani Secondary | EDDP 184/294 | Greater Giyani | Construction 1% - 25% | Active - Contracted | 2015-04-01 |  | 2025-03-31 |  |  | 2180000 | 8720000 | 10900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20199 | EDDP184/318 | Limpopo | Mpelegeng Primary | EDDP 184/318 | Makhuduthamaga | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2021-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 3340000 | 13360000 | 16700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20202 | EDDP184/282 | Limpopo | LEKOMETSE PRIMARY | EDDP184/282 | Ephraim Mogale | Final Completion | Active - Contracted | 2015-04-01 | 2015-05-01 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 4150000 | 16598000 | 20748000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20212 | EDDP184/367 | Limpopo | MMAZWI-A-NAPE PRIMARY | 996603501 | Ephraim Mogale | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2016-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1247000 | 4988000 | 6235000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20218 | EDDP184/319 | Limpopo | MPHARENG JUNIOR PRIMARY SCHOOL | EDDP184/319 | Polokwane | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2015-05-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 8939866 | 35759464 | 44699330 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20219 | EDDP184/291 | Limpopo | Magaedisha Secondary | EDDP 184/291 | Polokwane | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2016-04-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4793000 | 19173000 | 23966000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20221 | EDDP184/298 | Limpopo | MAMOTHALO PRIMARY | 923240587 | Polokwane | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2016-04-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 6049000 | 24194000 | 30243000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20222 | LE20IDT00159 | Limpopo | Ramphelane High School | 925661139 | Makhuduthamaga | Feasibility | Active - Contracted | 2020-01-04 |  | 2025-03-31 |  |  | 154000 | 617000 | 771000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20223 | EDDP184/300 | Limpopo | mang le mang primary | EDDP184/300 | Elias Motsoaledi | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2019-03-31 | 2024-07-31 | 2022-03-31 | 2025-03-31 | 2383000 | 9534000 | 11917000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20227 | W/Umk.New12/001/NS | KwaZulu-Natal | NEW MAHLABENI PRIMARY SCHOOL | 56450 | Jozini | Practical Completion (100%) | Active - Contracted | 2014-04-06 | 2022-03-31 | 2023-03-31 | 2023-07-31 | 2023-03-31 | 8740729 | 39818878 | 48559607 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 20229 | EDDP184/316 | Limpopo | MONYONG SECONDARY SCHOOL | 922222466 | Polokwane | Construction 1% - 25% | Active - Contracted | 2015-04-01 | 2019-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2227000 | 8907000 | 11134000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20234 | P9010491 | Eastern Cape | MTETUVUMILE SENIOR SECONDARY SCHOOL | 200601096 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3875000 | 3875000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 20306 | W/500166056/UA | KwaZulu-Natal | INTANDOYESIZWE SECONDARY SCHOOL | 500166056 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-11 | 2015-12-04 | 2023-03-31 | 2018-02-23 | 2023-03-29 | 307000 | 1860000 | 2167000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20307 | W/500180560/RRR | KwaZulu-Natal | KWAMANQONDO PRIMARY SCHOOL | 500180560 | Nkandla | Practical Completion (100%) | Active - Contracted | 2015-03-15 | 2018-04-27 | 2025-09-30 | 2019-03-29 | 2025-09-30 | 1195000 | 5443000 | 6638000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20311 | W/500401931/UA | KwaZulu-Natal | SIPHUMELELE COMBINED PRIMARY SCHOOL | 500401931 | Newcastle | Construction 51% - 75% | Active - Contracted | 2015-08-22 |  | 2023-06-30 |  |  | 8178090 | 37255746 | 45433836 | Equitable Share | Upgrading and Additions
|  | 20315 | C/Umg.New12/012/NS | KwaZulu-Natal | New MATSHAHENI Area PRIMARY SCHOOL | umg.new12/012 | uMngeni | Design | Active - Not Contracted | 2014-09-08 |  | 2026-04-06 |  |  | 2356583 | 18127560 | 20484143 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 20330 | LE20IDT09031 | Limpopo | THOMO PRIMARY 1 SCHOOL | 916411099 | Greater Giyani | Feasibility | Active - Not Contracted | 2014-04-01 |  | 2024-03-31 |  |  | 2856000 | 11424000 | 14280000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20362 | LE19TMT17002 | Limpopo | BALENI PRIMARY | EDDP182/214 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2018-02-03 |  | 2024-03-30 |  |  | 648897 | 5015546 | 5664443 | Education Infrastructure Grant | Upgrading and Additions
|  | 20449 | EDDP184/306 | Limpopo | MASOBE PRIMARY | 923240785 | Polokwane | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 5872000 | 23487000 | 29359000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20524 | EDDP184/417 | Limpopo | SEFAHONE PRIMARY | 184/397/311 | Greater Letaba | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-06-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 959507 | 3838026 | 4797533 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20539 | W/500238354/RRR | KwaZulu-Natal | NSONGENI SECONDARY SCHOOL | 500238354 | Mkhambathini | Design | Active - Contracted | 2015-08-12 |  | 2024-11-12 |  |  | 413000 | 2682941 | 3095941 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 20547 | W/500326264/ECD | KwaZulu-Natal | IZWI LESIZWE PRIMARY SCHOOL | 500326264 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2015-05-12 | 2015-06-30 | 2023-05-12 | 2016-05-01 | 2022-05-31 | 831000 | 3786000 | 4617000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20599 | GDE00232 | Gauteng | MOGOBENG PRIMARY SCHOOL | 700340901 | City of Ekurhuleni | Construction 76% - 99% | Active - Contracted | 2016-04-20 | 2016-07-20 | 2023-10-31 | 2019-06-15 | 2024-03-12 | 5396480 | 28122520 | 33519000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20608 | GDE00292 | Gauteng | RAMOSUKULA PRIMARY SCHOOL | 700321372 | Emfuleni | Feasibility | Approved | 2018-07-13 |  | 2026-03-13 |  |  | 9647680 | 59820680 | 69468360 | Education Infrastructure Grant | Upgrading and Additions
|  | 20610 | GDE00371 | Gauteng | THUTO PELE SECONDARY SCHOOL | 700400203 | Mogale City | Practical Completion (100%) | Approved | 2018-10-11 | 2018-12-20 | 2023-04-12 | 2023-10-20 | 2024-04-30 | 0 | 759000 | 759000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20614 | GDE00008 | Gauteng | ASTON MANOR PRIMARY SCHOOL | 700260018 | City of Ekurhuleni | Final Completion | Approved | 2015-07-17 | 2015-07-19 | 2022-05-15 | 2022-05-22 | 2022-09-11 | 3929261 | 20623373 | 24552634 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20615 | GDE00009 | Gauteng | ATHLONE GIRLS` HIGH SCHOOL | 700130112 | City of Johannesburg | Tender | Approved | 2019-09-15 |  | 2026-08-15 |  |  | 5334680 | 28010320 | 33345000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20616 | GDE00153 | Gauteng | KWADEDANGENDLALE SECONDARY SCHOOL | 700110510 | City of Johannesburg | On Hold | Approved | 2016-06-30 | 2018-03-01 | 2024-06-15 | 2024-08-06 | 2024-08-21 | 2088160 | 11909840 | 13998000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20617 | DID/700320127/R&R/2018/20617 | Gauteng | LAERSKOOL NOORDHOEK | 700320127 | Emfuleni | Tender | Approved | 2019-04-01 |  | 2025-03-21 |  |  | 2049320 | 10669680 | 12719000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20618 | GDE00212 | Gauteng | Malvern Primary school | 700130872 | City of Johannesburg | Construction 1% - 25% | Active - Contracted | 2016-06-30 | 2017-04-15 | 2022-04-30 | 2022-05-31 | 2023-03-19 | 1158080 | 6591920 | 7750000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20619 | GDE00283 | Gauteng | Pitseng Primary School | 700321273 | Emfuleni | Tender | Approved | 2021-03-12 |  | 2025-03-12 |  |  | 235680 | 1237320 | 1473000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20673 | GDE00152 | Gauteng | KRUGERLAANSKOOL | 700330316 | Emfuleni | Construction 26% - 50% | Approved | 2016-07-07 | 2016-10-20 | 2023-04-30 | 2023-07-31 | 2023-12-14 | 2535960 | 28376652 | 30912612 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20787 | ET/500283975/WS | KwaZulu-Natal | TINLEY MANOR PRIMARY SCHOOL | 500283975 | KwaDukuza | Final Completion | Active - Contracted | 2013-01-20 | 2016-10-20 | 2023-10-20 | 2018-12-01 | 2023-12-01 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20836 | DB/SAFE/500104858/WS | KwaZulu-Natal | BALDASKRAAL PRIMARY SCHOOL | 500104858 | Alfred Duma | Practical Completion (100%) | Active - Not Contracted | 2014-11-18 | 2019-03-01 | 2024-04-19 | 2024-03-30 | 2025-05-03 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20870 | W/500264624/ECD | KwaZulu-Natal | SIGWEJE HIGH SCHOOL | 500264624 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-12-01 | 2021-02-26 | 2023-08-25 | 2022-02-28 | 2022-03-31 | 657000 | 2992000 | 3649000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20910 | ET/500302845/WS | KwaZulu-Natal | EKUPHAKAMENI PRIMARY SCHOOL | 500302845 | eThekwini | Final Completion | Active - Contracted | 2016-05-15 | 2017-05-04 | 2023-08-03 | 2020-04-30 | 2023-03-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20923 | ET/500286306/WS | KwaZulu-Natal | OHLANGE SECONDARY SCHOOL | 500286306 | eThekwini | Final Completion | Active - Contracted | 2012-04-06 | 2019-08-10 | 2022-06-30 | 2021-01-31 | 2023-03-30 | 496450 | 2480167 | 2976617 | Education Infrastructure Grant | Upgrading and Additions
|  | 20925 | I/500156658/UA | KwaZulu-Natal | HLAZANE PRIMARY SCHOOL | 500156658 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-06-13 | 2015-06-18 | 2023-11-01 | 2022-11-02 | 2023-11-30 | 2313000 | 10537000 | 12850000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20932 | DB/500133866/SDS | KwaZulu-Natal | EMPANGENI HIGH SCHOOL | 500133866 | uMhlathuze | Final Completion | Approved | 2014-04-23 | 2017-02-20 | 2023-02-10 | 2022-06-20 | 2020-07-20 | 1946845 | 7323846 | 9270691 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20941 | DB/500233248/SDS | KwaZulu-Natal | NKWE PRIMARY SCHOOL | 500272468 | Msinga | Design | Approved | 2015-01-20 |  | 2024-09-20 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20948 | DB/500319976/WS | KwaZulu-Natal | MABHODLA P | 500319976 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2011-01-07 | 2020-05-31 | 2025-01-31 | 2021-01-31 | 2027-01-31 | 202121 | 2216677 | 2418798 | Education Infrastructure Grant | Upgrading and Additions
|  | 20950 | DB/500170459/SDS | KwaZulu-Natal | IZINGOLWENI EDUCATION CENTRE | 500170459 | Ray Nkonyeni | Design | Active - Not Contracted | 2014-08-22 |  | 2024-02-28 |  |  | 472099 | 2150673 | 2622772 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20951 | W/500187220/RRR | KwaZulu-Natal | LIVANGELI PRIMARY SCHOOL | 500187220 | Endumeni | Practical Completion (100%) | Active - Contracted | 2016-01-10 | 2018-05-24 | 2023-03-30 | 2022-03-30 | 2023-03-30 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 20981 | EDDP184/320 | Limpopo | Molai Jubilee | 918510712 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-04-02 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 2384000 | 9536000 | 11920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20983 | EDDP184/287 | Limpopo | MR Mamaila Primary School | EDDP184/287 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2019-04-01 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 0 | 4799965 | 4799965 | Education Infrastructure Grant | Upgrading and Additions
|  | 20984 | EDDP184/313 | Limpopo | Mawa Primary School | EDDP184/313 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2015-09-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 5042000 | 20170000 | 25212000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20985 | EDDP184/329 | Limpopo | Phakeng Primary School | EDDP 184/329 | Greater Letaba | Construction 76% - 99% | Active - Contracted | 2016-11-15 | 2016-11-16 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4965000 | 19859000 | 24824000 | Education Infrastructure Grant | Upgrading and Additions
|  | 20998 | EDDP184/292 | Limpopo | Magolersa Secondary School | 918510279 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-06-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 80000 | 321000 | 401000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 21004 | EDDP184/279 | Limpopo | Khumelong Primary | EDDP184/279 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 1777000 | 7110000 | 8887000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21006 | Various/ | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2015-04-01 |  | 2027-03-31 |  |  | 9346000 | 20993000 | 30339000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 21019 | EDDP184/281 | Limpopo | KOLOBETONA SECONDARY SCHOOL | 919341039 | Greater Letaba | Construction 1% - 25% | Active - Not Contracted | 2014-04-01 | 2014-06-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21112 | DOE14/15/16 | Free State | Xhariep | 18-19/005 | Letsemeng | Other - Packaged Ongoing Project | Active - Contracted | 2015-11-01 | 2016-12-01 | 2026-03-31 | 2024-10-25 | 2024-03-31 | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21142 | DOE15/15/16 | Free State | WITSIESHOEK:MAKABELANE HOSTEL | 445109002 | Maluti a Phofung | Other - Packaged Ongoing Project | Active - Contracted | 2015-12-01 | 2016-12-01 | 2025-04-01 | 2024-03-31 | 2024-03-31 | 0 | 33000000 | 33000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21387 | GDE00172 | Gauteng | LAERSKOOL LOUIS LEIPOLDT | 700210732 | City of Tshwane | Feasibility | Approved | 2019-04-15 |  | 2025-03-21 |  |  | 800000 | 4200000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 21393 | GDE00273 | Gauteng | Parkview Senior School | 700131193 | City of Johannesburg | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-13 |  |  | 5865680 | 30794320 | 36660000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 21395 | GDE00315 | Gauteng | Rodney Mokoena Sec | 700911609 | City of Tshwane | Design | Active - Not Contracted | 2020-04-01 |  | 2026-03-13 |  |  | 1600000 | 8400000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 21396 | GDE00334 | Gauteng | Seotloana Primary School | 700261198 | City of Ekurhuleni | Tender | Approved | 2019-04-20 |  | 2026-03-13 |  |  | 456960 | 12801040 | 13258000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 21458 | EDDP182/1962 | Limpopo | SEREME COMBINED | 996606727 | Elias Motsoaledi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-06-30 | 2023-12-31 | 2023-03-31 | 701000 | 2804000 | 3505000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21468 | P9010677 | Eastern Cape | LUCWABA JUNIOR SECONDARY SCHOOL | 200500445 | Mbizana | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 93714 | 93714 | Education Infrastructure Grant | Maintenance and Repairs
|  | 21566 | W/500257076/WS | KwaZulu-Natal | SABELA SECONDARY SCHOOL | 500257076 | Newcastle | On Hold | Approved | 2015-11-09 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 21602 | DB/500226366/SDS | KwaZulu-Natal | NEW FOREST HIGH SCHOOL | 500226366 | eThekwini | Construction 1% - 25% | Active - Contracted | 2017-09-01 | 2020-05-29 | 2023-08-22 | 2023-02-26 | 2023-03-15 | 677788 | 3087701 | 3765489 | Education Infrastructure Grant | Maintenance and Repairs
|  | 21975 | DB/500293410/WS | KwaZulu-Natal | VUKUZITHATHELE PRIMARY SCHOOL | 500293410 | Okhahlamba | Design | Active - Contracted | 2017-06-06 |  | 2024-05-30 |  |  | 2791000 | 3111000 | 5902000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22116 | GDE00226 | Gauteng | Mdelwa Hlongwane Primary | 700121541 | City of Johannesburg | Design | Active - Not Contracted | 2015-07-01 |  | 2026-03-09 |  |  | 16118720 | 84623280 | 100742000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 22160 | GDE00198 | Gauteng | Lethabong Secondary School | 700240895 | City of Tshwane | Tender | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 4395000 | 23072000 | 27467000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22163 | GDE00182 | Gauteng | LAERSKOOL VENTERSPOS | 700270389 | Rand West City | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 8629280 | 45303720 | 53933000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22198 | GDE00041 | Gauteng | Daleview Secondary School | 700110015 | City of Johannesburg | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 1868290 | 22300710 | 24169000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22208 | GDE00104 | Gauteng | Hoerskool Elandspoort | 700230326 | City of Tshwane | Feasibility | Approved | 2019-11-05 |  | 2026-03-21 |  |  | 3600000 | 18900000 | 22500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22209 | GDE00105 | Gauteng | Hoerskool Elsburg | 700160580 | City of Ekurhuleni | Feasibility | Approved | 2021-05-01 |  | 2026-03-13 |  |  | 104320 | 547680 | 652000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22210 | GDE00106 | Gauteng | Hoerskool President | 700120576 | City of Johannesburg | Feasibility | Approved | 2020-01-31 |  | 2026-03-20 |  |  | 800000 | 4200000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22223 | GDE00146 | Gauteng | Kibler Park Secondary School | 700400584 | City of Johannesburg | Design | Approved | 2019-04-01 |  | 2026-01-09 |  |  | 2880000 | 15120000 | 18000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 22299 | GDE00056 | Gauteng | EBOMINI PRIMARY SCHOOL | 700260695 | City of Johannesburg | Design | Active - Not Contracted | 2019-04-01 |  | 2025-04-18 |  |  | 1795000 | 9425000 | 11220000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22446 | GDE00176 | Gauteng | LAERSKOOL PIET VAN VUUREN | 700140277 | City of Johannesburg | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2024-07-30 |  |  | 200000 | 1000000 | 1200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22498 | GDE00201 | Gauteng | Lewisham Primary School | 700252817 | Mogale City | Final Completion | Approved | 2016-04-01 | 2017-03-30 | 2022-04-01 | 2022-04-30 | 2022-09-16 | 52160 | 273840 | 326000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22525 | P9011726 | Eastern Cape | J A CALATA SECONDARY SCHOOL | 200600304 | Inxuba Yethemba | Tender | Active - Not Contracted | 2017-04-03 | 2017-08-02 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 22540 | GDE00179 | Gauteng | LAERSKOOL SWARTKOP | 700210815 | Mogale City | Feasibility | Approved | 2022-04-01 |  | 2026-03-13 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22624 | GDE00091 | Gauteng | Graceland Education Centre | 700161794 | City of Ekurhuleni | Feasibility | Active - Not Contracted | 2016-04-01 |  | 2026-03-13 |  |  | 4000000 | 15000000 | 19000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22659 | GDE00013 | Gauteng | BARCELONA PRIMARY SCHOOL | 700400277 | City of Ekurhuleni | Feasibility | Approved | 2019-04-01 |  | 2025-08-22 |  |  | 10000800 | 60064200 | 70065000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 22661 | GDE00115 | Gauteng | IKUSASA COMPREHENSIVE SCHOOL | 700260836 | City of Ekurhuleni | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2025-06-09 |  |  | 480000 | 2520000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22712 | GDE00127 | Gauteng | Johannesburg Secondary School | 700130062 | City of Johannesburg | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2025-04-30 |  |  | 115360 | 605640 | 721000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22718 | GDE00130 | Gauteng | JORDAN SECONDARY SCHOOL | 700320671 | Emfuleni | Feasibility | Approved | 2016-04-01 |  | 2026-03-13 |  |  | 2039760 | 16615240 | 18655000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 22729 | GDE00137 | Gauteng | KENILWORTH SECONDARY SCHOOL | 700400107 | City of Johannesburg | Feasibility | Active - Contracted | 2019-04-01 |  | 2026-03-13 |  |  | 345000 | 2950000 | 3295000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22764 | P0001640_ | Eastern Cape | MPOFINI JUNIOR SECONDARY SCHOOL | 200500761 | Matatiele | Final Completion | Active - Contracted | 2015-04-01 | 2016-04-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 1161670 | 6866498 | 8028168 | Education Infrastructure Grant | Maintenance and Repairs
|  | 22783 | P9009658_ | Eastern Cape | NCHAFATSO PRIMARY SCHOOL | 200600550 | Walter Sisulu | Construction 76% - 99% | Active - Contracted | 2018-04-01 | 2019-07-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 5725611 | 5725611 | Education Infrastructure Grant | Upgrading and Additions
|  | 22811 | P9013256 | Eastern Cape | LAERSKOOL SOMERSET`S GIFT | 200100714 | Kou-Kamma | On Hold | Active - Contracted | 2013-04-09 | 2013-04-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 441349 | 441349 | Education Infrastructure Grant | Upgrading and Additions
|  | 22819 | P9005329_ | Eastern Cape | DONDASHE HIGH SCHOOL | 200300071 | Mnquma | Practical Completion (100%) | Approved | 2014-07-21 | 2014-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 140000 | 140000 | Education Infrastructure Grant | Upgrading and Additions
|  | 22830 | P0002052 | Eastern Cape | GWADANA SENIOR SECONDARY SCHOOL | 200300123 | Mbhashe | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 3465355 | 31503223 | 34968578 | Education Infrastructure Grant | Upgrading and Additions
|  | 22919 | P9005750 | Eastern Cape | BELE-ZINGCUKA TECHNICAL SENIOR SECONDARY SCHOOL | 200400034 | Mhlontlo | Construction 76% - 99% | Active - Contracted | 2017-04-01 | 2017-07-28 | 2026-03-31 | 2023-12-30 | 2023-12-30 | 6538556 | 36712834 | 43251390 | Education Infrastructure Grant | Upgrading and Additions
|  | 22943 | P0001619_ | Eastern Cape | BLACK DIAMOND PRIMARY SCHOOL | 200500042 | Matatiele | Construction 76% - 99% | Proposed | 2009-04-30 | 2015-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 852423 | 4803913 | 5656336 | Education Infrastructure Grant | Upgrading and Additions
|  | 22954 | P9005768 | Eastern Cape | QUMBU VILLAGE SENIOR SECONDARY SCHOOL | 200400958 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2017-06-29 | 2017-08-30 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 8186493 | 57140555 | 65327048 | Education Infrastructure Grant | Upgrading and Additions
|  | 22989 | P0003598_ | Eastern Cape | TEMBELANI HIGH SCHOOL | 200200831 | Buffalo City | Final Completion | Active - Contracted | 2015-04-02 | 2015-05-20 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 0 | 20000 | 20000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23112 | P9006173 | Eastern Cape | AGENT FEES (DBSA) | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2017-02-23 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 604444206 | 0 | 604444206 | Education Infrastructure Grant | Non-Infrastructure
|  | 23289 | P9013279_ | Eastern Cape | PHAHAMENG PRIMARY SCHOOL | 200600666 | Senqu | Construction 51% - 75% | Active - Not Contracted | 2015-04-01 | 2017-04-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 25193959 | 25193959 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 23294 | P9011733 | Eastern Cape | GERMAN VILLAGE JUNIOR SECONDARY SCHOOL | 200200205 | Ngqushwa | Project Initiation | Proposed | 2016-04-01 |  | 2026-03-31 |  |  | 0 | 548987 | 548987 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23323 | P9008612_ | Eastern Cape | LUGXOGXO JUNIOR SECONDARY SCHOOL | 200400399 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-10 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 564217 | 3318972 | 3883189 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23378 | P9013181 | Eastern Cape | THEMBALESIZWE PRIMARY SCHOOL | 200100778 | Port St Johns | Project Initiation | Active - Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 23382 | GDE00190 | Gauteng | Lanndlulwazi Secondary School | 700340810 | City of Ekurhuleni | Feasibility | Active - Contracted | 2021-03-01 |  | 2026-03-13 |  |  | 500000 | 6500000 | 7000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 23407 | P9005338_ | Eastern Cape | NGUBESIZWE SENIOR SECONDARY SCHOOL - Butterworth | 200300443 | Mnquma | Final Completion | Active - Contracted | 2014-03-19 | 2014-04-19 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 135000 | 866583 | 1001583 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23417 | P9009807_ | Eastern Cape | JONGIMISHINI SENIOR PRIMARY SCHOOL | 200300170 | Intsika Yethu | Feasibility | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 1609362 | 1609362 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23428 | P9013261 | Eastern Cape | TSITSIKAMA PRIMARY SCHOOL | 200600856 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23463 | P9006507 | Eastern Cape | AGENT FEES (AW) | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2022-08-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 49793018 | 0 | 49793018 | Education Infrastructure Grant | Non-Infrastructure
|  | 23474 | P9011590 | Eastern Cape | ATTWELL MADALA HIGH SCHOOL | 200401228 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2015-04-02 | 2025-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 15916640 | 15916640 | Education Infrastructure Grant | Upgrading and Additions
|  | 23540 | GDE00196 | Gauteng | Leshata Secondary School | 700330969 | City of Johannesburg | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 200000 | 0 | 200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 23604 | GDE00203 | Gauteng | Lotus Gardens Secondary School | 700400154 | City of Tshwane | Feasibility | Active - Not Contracted | 2019-11-05 |  | 2026-03-13 |  |  | 580000 | 3095000 | 3675000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 23654 | P0002059 | Eastern Cape | MTAWELANGA HIGH SCHOOL | 200300383 | Mnquma | Design | Active - Not Contracted | 2023-04-02 |  | 2026-03-31 |  |  | 5616779 | 51061626 | 56678405 | Education Infrastructure Grant | Upgrading and Additions
|  | 23803 | P9010498 | Eastern Cape | GQUMAHASHE JUNIOR PRIMARY SCHOOL | 200200217 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2015-04-02 |  | 2026-03-31 |  |  | 0 | 548987 | 548987 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23808 | P9010489 | Eastern Cape | TYELINZIMA HIGH SCHOOL | 20040086 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-17 | 2018-04-27 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7075641 | 7075641 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23813 | GDE00221 | Gauteng | Matla Combined School | 700270918 | Mogale City | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2026-03-13 |  |  | 300000 | 1000000 | 1300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 23839 | P9006333_ | Eastern Cape | AEROVILLE SECONDARY SCHOOL | 200100018 | Dr Beyers Naude | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 650812 | 2632890 | 3283702 | Education Infrastructure Grant | Maintenance and Repairs
|  | 23893 | WE 000561/2017 | Western Cape | Mfuleni HS | 107008031 | City of Cape Town | Tender | Active - Not Contracted | 2017-04-03 |  | 2025-03-31 |  |  | 15857000 | 68000000 | 83857000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 23914 | GDE00241 | Gauteng | Mphethi Mahlatsi | 700331950 | City of Johannesburg | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2026-03-13 |  |  | 96320 | 505680 | 602000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 23961 | GDE00261 | Gauteng | Oakdale Secondary School | 700111815 | City of Johannesburg | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2026-03-13 |  |  | 2720000 | 14280000 | 17000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 24359 | WE/000689/2018 | Western Cape | Graafwater PS | 136476420 | Cederberg | Construction 1% - 25% | Active - Contracted | 2018-04-02 | 2022-06-29 | 2027-03-31 | 2023-08-01 | 2025-01-30 | 8046000 | 27000000 | 35046000 | Education Infrastructure Grant | Upgrading and Additions
|  | 24394 | GDE00291 | Gauteng | PRUDENS SECONDARY SCHOOLPrudence Secondary School | 700111195 | City of Johannesburg | Feasibility | Proposed | 2019-04-01 |  | 2025-07-11 |  |  | 1381760 | 7960240 | 9342000 | Education Infrastructure Grant | Upgrading and Additions
|  | 24398 | 631108 /2016 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 238725000 | 1082594000 | 1321319000 | Equitable Share | Maintenance and Repairs
|  | 24409 | GDE00294 | Gauteng | Rantailane Secondary School | 700911749 | City of Tshwane | Feasibility | Active - Not Contracted | 2019-06-19 |  | 2026-04-01 |  |  | 48160 | 252840 | 301000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 24450 | 60000002 | North West | RELOCATION OF MOBILES | 60000002 | Mafikeng | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2024-03-05 | 2024-03-21 | 2024-03-31 | 2025-03-31 | 0 | 2500000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 24685 | GDE00311 | Gauteng | Riverlea Secondary School | 700140111 | City of Johannesburg | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2026-03-13 |  |  | 11200000 | 58800000 | 70000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 24692 | GDE00320 | Gauteng | Roshnee Secondary School | 700330043 | Emfuleni | Feasibility | Active - Not Contracted | 2019-04-03 |  | 2026-03-13 |  |  | 160000 | 840000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 24695 | 631108/2016 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-02 |  | 2026-03-31 |  |  | 546433000 | 2569464000 | 3115897000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 24708 | 60000 | North West | Goodwill Primary | 6000000011 | Mafikeng | Project Initiation | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 9000000 | 41000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 24716 | 453627/2015 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 |  | 2027-03-31 |  |  | 169683000 | 588927000 | 758610000 | Equitable Share | Maintenance and Repairs
|  | 24727 | 600000017 | North West | Trotsville Primary | 600000017 | Maquassi Hills | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2022-06-08 | 2025-03-31 | 2023-05-02 | 2025-03-31 | 4538160 | 20673840 | 25212000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 24831 | MDOE/P/BOH/EIG/UPG/18-19/001 (PWRT/2283/17/MP) | Mpumalanga | Godide Primary School | 800035154 | Bushbuckridge | Tender | Active - Not Contracted | 2017-04-01 |  | 2025-03-31 |  |  | 4629492 | 17469399 | 22098891 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25051 | DPWRT/SAN/130/20/MP LIGUGULETFU --------- | Mpumalanga | Ligugulethu Primary School | 800010926 | Nkomazi | Tender | Active - Contracted | 2020-09-19 |  | 2024-04-19 |  |  | 153763 | 1098313 | 1252076 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25069 | DPWRT/109/18/MP(LONG TOM SEC)------------ | Mpumalanga | LONGTOM HIGH SCHOOL | new | Thaba Chweu | Design | Active - Not Contracted | 2019-01-30 |  | 2025-03-31 |  |  | 7209352 | 31166956 | 38376308 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25138 | MDOE/P/BOH/EIG/NEW/18-19/001 (PWRT/2273/17/MP) | Mpumalanga | Mapaleni Primary School | 800035102 | Bushbuckridge | Construction 1% - 25% | Active - Contracted | 2017-02-01 | 2019-08-15 | 2024-04-30 | 2022-05-01 | 2020-07-31 | 5550797 | 30837707 | 36388504 | Education Infrastructure Grant | Upgrading and Additions
|  | 25208 | DOE02/16/17 | Free State | New school complete with classrooms, admin block, laboratory and ablutions | 440304242 | Dihlabeng | Construction 26% - 50% | Active - Contracted | 2016-04-01 | 2016-06-30 | 2025-03-31 | 2022-03-31 | 2025-03-31 | 5000000 | 45000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25230 | DOE15/13/4-1 | Free State | PROJECT MANAGEMENT | HEAD OFFICE | Masilonyana | Not Applicable | Active - Contracted | 2015-04-01 | 2016-10-20 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 53589000 | 0 | 53589000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25231 | DOE15/13/4-2 | Free State | PM FEES MPS COSULTING | DOE15/134-2 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 16821000 | 0 | 16821000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25232 | DOE23/ | Free State | QWAQWA WITSIESHOEK | QWAQWA | Maluti a Phofung | Not Applicable | Active - Contracted | 2016-04-01 |  | 2025-04-01 |  |  | 0 | 7500000 | 7500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25248 | PWRT/2371/18/MP | Mpumalanga | Aerorand Primary School | PWRT/2371/18/MP | Steve Tshwete | Practical Completion (100%) | Active - Contracted | 2016-01-11 | 2017-06-07 | 2023-03-31 | 2020-03-25 | 2022-03-30 | 6402217 | 57756565 | 64158782 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25267 | GDE00381 | Gauteng | Trinity Secondary | 700110338 | City of Johannesburg | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2026-03-13 |  |  | 2720000 | 14280000 | 17000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25286 | GDE00394 | Gauteng | Umqhele Secondary School | 700261420 | City of Johannesburg | Feasibility | Approved | 2019-12-01 |  | 2026-03-13 |  |  | 160000 | 840000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25407 | GDE00282 | Gauteng | PINEGROVE PRIMARY SCHOOL | 700350405 | City of Ekurhuleni | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 2500000 | 22500000 | 25000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25462 | GDE00123 | Gauteng | Itumeleng School for Severely Mentally Handicapped | 700271304 | Rand West City | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2026-03-13 |  |  | 260640 | 1368360 | 1629000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25679 | DOE03NCAR032 | Northern Cape | GAMOHANA INTERMEDIATE SCHOOL | 300100404 | Ga-Segonyana | Practical Completion (100%) | Approved | 2017-04-01 | 2017-04-05 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1993287 | 2055031 | 4048318 | Education Infrastructure Grant | Upgrading and Additions
|  | 25690 | ST051/2022-23 | Northern Cape | SENGAE PRIMARY SCHOOL | 300101955 | Joe Morolong | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2023-03-29 |  |  | 0 | 1544399 | 1544399 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25833 | DB/500282680/SDS | KwaZulu-Natal | THOLISU PRIMARY SCHOOL | 500282680 | eThekwini | Final Completion | Approved | 2014-11-19 | 2017-01-20 | 2023-11-26 | 2019-04-20 | 2025-06-20 | 466806 | 1756080 | 2222886 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25874 | DB/500212269/SDS | KwaZulu-Natal | MKHUNJINI PRIMARY SCHOOL | 500212269 | uPhongolo | Final Completion | Approved | 2015-02-15 | 2022-01-20 | 2023-08-10 | 2023-03-20 | 2023-04-20 | 920493 | 3462808 | 4383301 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25880 | W/500441373/WS | KwaZulu-Natal | SOBETHU PRIMARY SCHOOL | 500441373 | Abaqulusi | Tender | Active - Contracted | 2016-03-06 |  | 2026-06-30 |  |  | 426000 | 2000000 | 2426000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25891 | W/500273245/SDS | KwaZulu-Natal | SOMOTHA PRIMARY SCHOOL | 500273245 | Mfolozi | Design | Active - Not Contracted | 2015-11-20 |  | 2023-06-30 |  |  | 1440120 | 6560545 | 8000665 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25893 | W/500440115/UA | KwaZulu-Natal | UMZILA PRIMARY SCHOOL | 500440115 | Dannhauser | Design | Active - Not Contracted | 2015-05-11 |  | 2023-06-30 |  |  | 803000 | 3660000 | 4463000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25895 | W/500137085/SDS | KwaZulu-Natal | ENHLANZINI PRIMARY SCHOOL | 500137085 | Mfolozi | Final Completion | Approved | 2016-02-19 | 2022-05-28 | 2023-05-27 | 2023-03-31 | 2023-08-19 | 508978 | 2865535 | 3374513 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25898 | DOE/MAINTENANCE/ALLDISTRICT | KwaZulu-Natal | MAINTENANCE DOE DISTRICT | 50000000 | The Msunduzi | Site Handed - Over to Contractor | Active - Contracted | 2015-11-20 | 2016-01-22 | 2023-03-01 | 2023-03-01 | 2024-03-01 | 0 | 144380001 | 144380001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25900 | W/500214008/RRR | KwaZulu-Natal | MNYAMANA HIGH SCOLL | 500214008 | Ulundi | Feasibility | Active - Not Contracted | 2016-02-19 |  | 2024-02-19 |  |  | 1125000 | 5125000 | 6250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25902 | IDT/ALL DISTRICTS/FEN | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-20 |  | 2023-03-20 |  |  | 0 | 50112721 | 50112721 | Education Infrastructure Grant | Upgrading and Additions
|  | 25905 | W/500268139/SDS | KwaZulu-Natal | SIQONGWENI SECONDARY SCHOOL | 500268139 | The Msunduzi | Construction 26% - 50% | Active - Contracted | 2016-02-19 | 2017-03-30 | 2023-06-30 | 2018-01-30 | 2023-04-01 | 2000000 | 5000000 | 7000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25910 | W/500281755/RRR | KwaZulu-Natal | THEMBOKUHLE LOWER PRIMARY SCHOOL | 500281755 | Alfred Duma | Feasibility | Active - Not Contracted | 2016-02-19 |  | 2023-06-30 |  |  | 4454000 | 20293000 | 24747000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25911 | W/500233285/UA | KwaZulu-Natal | NKWELETSHENI PRIMARY SCHOOL | 500233285 | Greater Kokstad | Design | Active - Contracted | 2016-04-20 |  | 2026-06-30 |  |  | 300000 | 5040000 | 5340000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25912 | W/500283605/WS | KwaZulu-Natal | THULWANA SECONDARY SCHOOL | 500283605 | Nongoma | Final Completion | Active - Contracted | 2016-02-19 | 2019-09-12 | 2023-06-30 | 2023-05-05 | 2025-01-31 | 214000 | 1017000 | 1231000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25914 | W/500287860/RRR | KwaZulu-Natal | UMHLOLUTHINI HIGH SCHOOL | 500287860 | Ulundi | Final Completion | Active - Contracted | 2016-02-19 | 2021-02-26 | 2022-06-30 | 2022-02-28 | 2025-03-31 | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25915 | W/500123913/ECD | KwaZulu-Natal | DULIKHULU PRIMARY SCHOOL | 500123913 | Big Five Hlabisa | Tender | Active - Not Contracted | 2015-05-01 |  | 2026-03-31 |  |  | 348480 | 1587520 | 1936000 | Equitable Share | Upgrading and Additions
|  | 25922 | W/500127502/ECD | KwaZulu-Natal | EGUJINI PRIMARY SCHOOL | 500127502 | Jozini | Practical Completion (100%) | Active - Contracted | 2015-05-01 | 2017-03-30 | 2024-05-31 | 2022-03-30 | 2024-05-31 | 307000 | 1398000 | 1705000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25924 | W/500297110/NS | KwaZulu-Natal | WOODLANDS PRIMARY SCHOOL | 500297110 | uMngeni | Construction 1% - 25% | Active - Contracted | 2017-04-06 |  | 2026-06-30 |  |  | 11684650 | 53230074 | 64914724 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 25926 | W/500161172/SDS | KwaZulu-Natal | IMPAPHALA PRIMARY SCHOOL | 500182373 | uMlalazi | Tender | Active - Contracted | 2015-02-19 |  | 2025-03-27 |  |  | 957363 | 4361319 | 5318682 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25929 | W/500315461/RRR | KwaZulu-Natal | KHISHWA P | 500315461 | Mfolozi | Feasibility | Active - Not Contracted | 2016-02-19 |  | 2024-02-19 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25930 | W/500169127/SDS | KwaZulu-Natal | ISMONT HIGH SCHOOL | W/500169127/SDS | Mkhambathini | Tender | Active - Contracted | 2016-02-01 |  | 2025-03-31 |  |  | 739249 | 3367691 | 4106940 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25940 | W/500163355/RRR | KwaZulu-Natal | INGOGO P | W/500163355/RRR | Newcastle | Design | Active - Not Contracted | 2010-10-01 |  | 2024-10-02 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25942 | DB/500146853/SDS | KwaZulu-Natal | GAMALAKHE COMM HIGH SCHOOL | 500146853 | Ray Nkonyeni | Practical Completion (100%) | Approved | 2017-04-06 | 2018-04-04 | 2023-08-07 | 2023-08-06 | 2027-03-30 | 1047395 | 4771468 | 5818863 | Education Infrastructure Grant | Maintenance and Repairs
|  | 25945 | W/500320531/RRR | KwaZulu-Natal | DR BW VILAKAZI JUNIOR PRIMARY SCHOOL | 500320531 | KwaDukuza | Design | Active - Not Contracted | 2017-05-01 |  | 2024-04-30 |  |  | 386000 | 1756000 | 2142000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25955 | W/500281311/WS | KwaZulu-Natal | THEMANE COMBINED SCHOOL | 500281311 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-09-14 | 2018-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 644000 | 2934000 | 3578000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25957 | DB/500138824/SDS | KwaZulu-Natal | ENUNGWINI PRIMARY SCHOOL | 500138824 | Mthonjaneni | Design | Active - Not Contracted | 2015-03-06 |  | 2027-03-30 |  |  | 798633 | 3638215 | 4436848 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25959 | W/500164206/RRR | KwaZulu-Natal | INHLOKOZI HIGH SCHOOL | 500164206 | Maphumulo | Design | Active - Not Contracted | 2015-09-20 |  | 2024-08-30 |  |  | 0 | 100000 | 100000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25968 | W/500244755/WS | KwaZulu-Natal | OSHABENI PRIMARY SCHOOL | 500244755 | Jozini | Design | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 64000 | 291000 | 355000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25971 | W/500162726/WS | KwaZulu-Natal | INDONSA SECONDARY SCHOOL | DB/500162726/WS | Newcastle | Design | Active - Not Contracted | 2015-02-11 |  | 2024-03-27 |  |  | 294568 | 1341921 | 1636489 | Education Infrastructure Grant | Upgrading and Additions
|  | 25975 | W/500198135/RRR | KwaZulu-Natal | MANZIMAKHULU PRIMARY SCHOOL | 500198135 | Nongoma | Design | Active - Contracted | 2015-08-03 |  | 2024-06-28 |  |  | 549720 | 2504280 | 3054000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25980 | W/500342694/RRR | KwaZulu-Natal | SIPHOSETHU SECONDARY SCHOOL | 500342694 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2015-09-20 | 2017-05-01 | 2024-03-30 | 2023-06-30 | 2019-09-30 | 1307000 | 5955000 | 7262000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 25984 | W/500192585/WS | KwaZulu-Natal | MAGUBULUNDU SECONDARY SCHOOL | 500192585 | eDumbe | Tender | Active - Contracted | 2015-10-12 |  | 2026-11-05 |  |  | 300000 | 1218000 | 1518000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25986 | W/500186961/WS | KwaZulu-Natal | LINGANI PRIMARY SCHOOL | 500186961 | Newcastle | On Hold | Active - Not Contracted | 2015-05-10 |  | 2023-08-19 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 25993 | W/500279646/WS | KwaZulu-Natal | TAYSIDE PRIMARY SCHOOL | 500279646 | Endumeni | Tender | Active - Not Contracted | 2015-03-10 |  | 2026-06-30 |  |  | 300000 | 1296000 | 1596000 | Equitable Share | Upgrading and Additions
|  | 25994 | W/500289599/RRR | KwaZulu-Natal | UMZINTOVALE PRIMARY SCHOOL | 500289599 | Umdoni | Practical Completion (100%) | Active - Contracted | 2015-08-20 | 2016-06-18 | 2024-03-30 | 2023-06-30 | 2019-03-29 | 69000 | 315000 | 384000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26021 | C/FENCE/ALLDISTRICT | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-06-13 |  | 2024-03-20 |  |  | 0 | 93218000 | 93218000 | Equitable Share | Upgrading and Additions
|  | 26033 | W/500223628/SDS | KwaZulu-Natal | NCIBIDWANE PRIMARY SCHOOL | 500223628 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2012-10-07 | 2012-10-10 | 2023-03-31 | 2023-03-31 | 2023-03-29 | 461024 | 2100219 | 2561243 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26037 | W/500112776/SDS | KwaZulu-Natal | BRUYNSHILL PRIMARY SCHOOL | 500112776 | uMshwathi | Final Completion | Active - Contracted | 2016-04-19 | 2016-10-05 | 2023-09-28 | 2023-09-28 | 2023-09-28 | 180000 | 2800463 | 2980463 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26050 | W/500228327/WS | KwaZulu-Natal | NGOME PRIMARY SCHOOL - GREYTOWN | 500228327 | Msinga | Construction 26% - 50% | Active - Contracted | 2015-03-10 | 2015-04-16 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 652123 | 2970780 | 3622903 | Education Infrastructure Grant | Upgrading and Additions
|  | 26058 | I/500288415/ECD | KwaZulu-Natal | UMLWANE PRIMARY SCHOOL | 500288415 | Emadlangeni | On Hold | Active - Not Contracted | 2015-11-20 | 2016-06-13 | 2023-09-19 | 2022-01-28 | 2024-03-30 | 424800 | 1935200 | 2360000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26065 | DB/500303511/SDS | KwaZulu-Natal | MNYANDA PRIMARY SCHOOL | 500170903 | Newcastle | Final Completion | Approved | 2015-07-01 | 2017-02-20 | 2023-04-19 | 2023-02-20 | 2023-06-20 | 248869 | 936220 | 1185089 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26070 | I/500213860/UA | KwaZulu-Natal | MNTWANUNGAMIZIZWE SECONDARY SCHOOL | 500213860 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-07-03 | 2017-10-12 | 2023-04-30 | 2018-03-20 | 2023-04-30 | 5372331 | 29846538 | 35218869 | Education Infrastructure Grant | Upgrading and Additions
|  | 26076 | W/500199282/WS | KwaZulu-Natal | MARIA MEMORIAL SENIOR PRIMARY SCHOOL | 500199282 | uMngeni | Practical Completion (100%) | Active - Contracted | 2015-05-12 | 2018-08-21 | 2022-08-23 | 2022-08-23 | 2025-08-23 | 270000 | 1730000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26081 | W/500224775/WS | KwaZulu-Natal | NDELESHANE PRIMARY SCHOOL | 500224775 | The Msunduzi | Design | Active - Contracted | 2015-03-10 |  | 2023-03-10 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26087 | I/500134199/UA | KwaZulu-Natal | EMPILWENI JUNIOR SECONDARY SCHOOL | 500134199 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-04-06 | 2016-06-15 | 2023-11-30 | 2018-11-30 | 2023-11-30 | 5302000 | 24153000 | 29455000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26093 | DB/500245458/SDS | KwaZulu-Natal | OVERPORT SECONDARY SCHOOL | DB/500245458/SDS | eThekwini | Final Completion | Approved | 2015-03-10 | 2016-04-20 | 2023-08-25 | 2019-04-20 | 2025-06-20 | 328783 | 1236849 | 1565632 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26099 | I/500113442/WS | KwaZulu-Natal | BUHLEBUZILE PRIMARY SCHOOL | 500113442 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-12-05 | 2017-06-16 | 2023-03-31 | 2017-11-20 | 2024-03-30 | 351000 | 1600000 | 1951000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26101 | I/Pin.New019/12/NS | KwaZulu-Natal | Dlulumuzi | I/Pin.New019/12/NS | eThekwini | Project Initiation | Active - Contracted | 2017-11-15 |  | 2026-03-31 |  |  | 3600000 | 16400000 | 20000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 26104 | DB/500312761/WS | KwaZulu-Natal | MATOMELA HIGH SCHOOL | 500312761 | Impendle | Construction 26% - 50% | Active - Contracted | 2017-04-01 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 745449 | 3395933 | 4141382 | Education Infrastructure Grant | Upgrading and Additions
|  | 26110 | DB/500212787/WS | KwaZulu-Natal | MLOKOTHWA HIGH SCHOOL | 500212787 | Nongoma | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 3030000 | 3350000 | 6380000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26114 | I/500265401/UA | KwaZulu-Natal | SILIMELE PRIMARY SCHOOL | 500265401 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-10-20 | 2023-03-30 | 2018-03-20 | 2023-03-30 | 1765000 | 8038000 | 9803000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26115 | I/500423687/NS | KwaZulu-Natal | BLOEMFONTEIN PRIMARY SCHOOL | I/500423687/NS | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-06-20 | 2022-10-20 | 2022-11-26 | 2023-06-20 | 2023-08-01 | 3597682 | 16389442 | 19987124 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 26139 | W/School Maintenance/UMZI | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Proposed | 2017-04-01 |  | 2024-06-30 |  |  | 0 | 18774000 | 18774000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26141 | DB/500222851/SDS | KwaZulu-Natal | NAGARI PRACHARNI PRIMARY SCHOOL | DB/500222851/SDS | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-09-16 | 2019-01-17 | 2023-07-17 | 2020-07-17 | 2023-07-17 | 771895 | 3516412 | 4288307 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26144 | DB/500271506/SDS | KwaZulu-Natal | SIZODELA PRIMARY SCHOOL | 500271506 | eDumbe | Final Completion | Approved | 2014-02-03 | 2016-02-20 | 2023-10-10 | 2019-06-20 | 2025-10-20 | 1083533 | 4076150 | 5159683 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26148 | DB/500230843/SDS | KwaZulu-Natal | NINGIZIMU PRIMARY SCHOOL | 500230843 | Ulundi | Design | Active - Not Contracted | 2017-03-10 |  | 2024-02-25 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26149 | DB/500197691/UA | KwaZulu-Natal | MANYAMPISI PRIMARY SCHOOL | 500197691 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2011-03-10 | 2011-05-18 | 2022-09-12 | 2022-09-12 | 2027-09-12 | 2271361 | 10347312 | 12618673 | Education Infrastructure Grant | Upgrading and Additions
|  | 26150 | DB/500264291/WS | KwaZulu-Natal | SIFISOKUHLE PRIMARY SCHOOL | 500264291 | Okhahlamba | Tender | Active - Contracted | 2017-06-06 |  | 2025-01-29 |  |  | 380579 | 1733749 | 2114328 | Education Infrastructure Grant | Upgrading and Additions
|  | 26155 | I/500443704/NS | KwaZulu-Natal | KWANGOZA S | 500443704 | KwaDukuza | Design | Proposed | 2015-10-01 |  | 2023-04-19 |  |  | 1415400 | 5324600 | 6740000 | Equitable Share | New or Replaced Infrastructure
|  | 26158 | I/500425944/NS | KwaZulu-Natal | Khayeka P | I/500425944/NS | Dr Nkosazana Dlamini Zuma | Feasibility | Active - Contracted | 2016-06-21 |  | 2026-03-31 |  |  | 4200000 | 15800000 | 20000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 26162 | W/500245569/RRR | KwaZulu-Natal | OVUKANENI PRIMARY SCHOOL | 500245569 | Nongoma | Design | Active - Not Contracted | 2015-06-01 |  | 2024-03-30 |  |  | 752000 | 3428000 | 4180000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26163 | DB/500308062/ECD | KwaZulu-Natal | Amandlalanathi P School (to get the replacement) | I/500283975/ECD | Umdoni | Design | Active - Not Contracted | 2016-06-20 |  | 2026-03-31 |  |  | 205200 | 934800 | 1140000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26164 | I/500429570/NS | KwaZulu-Natal | ZIZAMELE PRIMARY SCHOOL | 500300995 | Umzimkhulu | Design | Active - Not Contracted | 2016-04-27 |  | 2026-03-31 |  |  | 6300000 | 28700000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 26165 | I/500424353/NS | KwaZulu-Natal | Dovedale J.S.S | I/500424353/NS | Umzimkhulu | Feasibility | Active - Contracted | 2017-04-20 |  | 2026-03-31 |  |  | 1041000 | 4747000 | 5788000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 26169 | I/500238983/WS | KwaZulu-Natal | NTABASUKA SECONDARY SCHOOL | 500238983 | Ulundi | Practical Completion (100%) | Active - Contracted | 2014-10-01 | 2016-04-10 | 2023-03-31 | 2018-03-31 | 2023-03-31 | 299000 | 1363000 | 1662000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26171 | I/500184038/RRR | KwaZulu-Natal | KWAZAMOKUHLE P | I/500184038/RRR | Umzumbe | Project Initiation | Proposed | 2016-04-01 |  | 2026-03-31 |  |  | 540000 | 2460000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26173 | DB/500104599/WS | KwaZulu-Natal | BABANANGO P | 500104599 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-02-19 | 2022-06-01 | 2022-10-26 | 2024-03-30 | 2025-05-30 | 360837 | 1643814 | 2004651 | Education Infrastructure Grant | Upgrading and Additions
|  | 26175 | I/500241832/UA | KwaZulu-Natal | Nyonebomvu HP | 500241832 | Nongoma | Project Initiation | Active - Not Contracted | 2017-11-15 |  | 2026-03-31 |  |  | 420000 | 1580000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26176 | DB/500159433/WS | KwaZulu-Natal | IDLEBE P | I/500159433/RRR | Ulundi | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 460476 | 3457096 | 3917572 | Education Infrastructure Grant | Upgrading and Additions
|  | 26177 | W/500229400/RRR | KwaZulu-Natal | NGWENYA SECONDARY SCHOOL | 500229400 | uMlalazi | Feasibility | Active - Not Contracted | 2015-07-06 |  | 2024-03-13 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26178 | I/500337403/RRR | KwaZulu-Natal | MTHINGANA JS | I/500337403/RRR | eDumbe | Project Initiation | Active - Contracted | 2017-04-01 |  | 2026-03-31 |  |  | 540 | 2460 | 3000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26179 | DB/500117882/ECD | KwaZulu-Natal | CONISTON PRIMARY SCHOOL | 500117882 | Ray Nkonyeni | Tender | Active - Contracted | 2015-09-01 |  | 2025-01-18 |  |  | 455400 | 2380440 | 2835840 | Education Infrastructure Grant | Upgrading and Additions
|  | 26182 | DB/500101750/ECD | KwaZulu-Natal | I/500213712/ECD | Amandawe P | Umdoni | Design | Active - Not Contracted | 2015-09-01 |  | 2026-03-31 |  |  | 3650622 | 16630613 | 20281235 | Education Infrastructure Grant | Upgrading and Additions
|  | 26184 | DB/500253154/ECD | KwaZulu-Natal | QHUBIMFUNDO PRIMARY SCHOOL | 500253154 | Newcastle | Tender | Active - Contracted | 2015-09-01 |  | 2025-03-20 |  |  | 320850 | 5174730 | 5495580 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26192 | W/School Maintenance/UTHUN | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Proposed | 2018-01-04 |  | 2024-06-30 |  |  | 1912000 | 35221000 | 37133000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26193 | ET/500288526/WS | KwaZulu-Natal | UMNINI MEMORIAL SP | ET/500288526/WS | eThekwini | Design | Active - Contracted | 2016-03-01 |  | 2023-03-31 |  |  | 0 | 400000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26197 | DB/500324305/WS | KwaZulu-Natal | MASOYI SECONDARY SCHOOL | 500324305 | Okhahlamba | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 152000 | 694000 | 846000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26203 | ET/500132941/WS | KwaZulu-Natal | EMKHAMBENI PRIMARY SCHOOL | 500132941 | KwaDukuza | Final Completion | Active - Contracted | 2016-09-20 | 2017-05-04 | 2023-09-19 | 2018-11-05 | 2023-03-25 | 30000 | 270000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26204 | W/School Maintenance/ZUL | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Proposed | 2018-01-04 |  | 2024-06-30 |  |  | 2340000 | 65363000 | 67703000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26205 | DB/500166796/WS | KwaZulu-Natal | INYANINGA PRIMARY SCHOOL | 500166796 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-11-11 | 2019-09-12 | 2023-09-03 | 2024-05-05 | 2027-05-20 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26215 | I/500193436/ECD | KwaZulu-Natal | MAHLEKEHLATHINI PRIMARY SCHOOL | 500193436 | Newcastle | On Hold | Active - Not Contracted | 2016-02-19 | 2019-04-15 | 2023-08-19 | 2024-03-03 | 2024-08-31 | 424800 | 1935200 | 2360000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26217 | I/500297480/WS | KwaZulu-Natal | WOZOBONA PRIMARY SCHOOL | 500297480 | Impendle | Construction 76% - 99% | Active - Contracted | 2016-10-25 | 2017-04-06 | 2023-10-01 | 2023-01-31 | 2023-03-30 | 100000 | 400000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26218 | DB/500212121/SDS | KwaZulu-Natal | MKHONJANE PRIMARY SCHOOL | 500212121 | Nqutu | Feasibility | Active - Not Contracted | 2015-10-24 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26236 | DB/500338254/WS | KwaZulu-Natal | MALANGENI SECONDARY SCHOOL | 500338254 | Umdoni | Design | Active - Contracted | 2016-12-06 |  | 2027-12-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26240 | I/Chemical Toilets/WS/Sisonke/No.44 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-02-19 |  | 2024-04-19 |  |  | 0 | 50000000 | 50000000 | Equitable Share | Maintenance and Repairs
|  | 26241 | W/500173086/RRR | KwaZulu-Natal | W/500173086/RRR | KHAMBULA COMBINED | eDumbe | Design | Active - Not Contracted | 2013-05-10 |  | 2024-11-12 |  |  | 522000 | 3122000 | 3644000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26242 | C/500229474/LSEN | KwaZulu-Natal | NGXONGWANE PRIMARY SCHOOL | 500229474 | Nongoma | On Hold | Active - Contracted | 2012-01-30 |  | 2023-05-31 |  |  | 1301000 | 5931000 | 7232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26244 | I/Chemical Toilets/WS/Ugu/No.43 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-02-19 |  | 2024-04-19 |  |  | 0 | 76870000 | 76870000 | Equitable Share | Maintenance and Repairs
|  | 26249 | C/500222148/LSEN | KwaZulu-Natal | MZINGAZI P | 500222148 | Mfolozi | Design | Active - Not Contracted | 2013-01-10 |  | 2025-10-23 |  |  | 829800 | 19454726 | 20284526 | Education Infrastructure Grant | Upgrading and Additions
|  | 26257 | I/500262256/WS | KwaZulu-Natal | SHONGOLOLO COMBINED SCHOOL | 500262256 | Abaqulusi | On Hold | Active - Contracted | 2016-11-06 | 2017-08-01 | 2023-10-03 | 2018-01-31 | 2023-04-16 | 276000 | 1257000 | 1533000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26260 | W/500283087/WS | KwaZulu-Natal | THORNER PRIMARY SCHOOL | 500283087 | Mkhambathini | Design | Active - Contracted | 2012-11-01 |  | 2025-06-30 |  |  | 270000 | 1730000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26261 | I/Chemical Toilets/WS/Ilembe/No.50 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-02-19 |  | 2024-04-19 |  |  | 0 | 65100000 | 65100000 | Equitable Share | Maintenance and Repairs
|  | 26263 | I/Chemical Toilets/WS/Umg/No.61 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-04 |  | 2024-04-04 |  |  | 0 | 70850000 | 70850000 | Equitable Share | Maintenance and Repairs
|  | 26267 | W/500119140/WS | KwaZulu-Natal | CWEMBE PRIMARY SCHOOL | 500119140 | Alfred Duma | Tender | Active - Contracted | 2012-05-10 |  | 2026-02-03 |  |  | 383000 | 1824000 | 2207000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26268 | I/Chemical Toilets/WS/Umlazi/No.6 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-04-04 |  | 2024-10-31 |  |  | 0 | 52000000 | 52000000 | Equitable Share | Maintenance and Repairs
|  | 26269 | DB/500308950/WS | KwaZulu-Natal | ZAMIMPILO SPECIAL SCHOOL | 500308950 | Ulundi | Design | Active - Contracted | 2017-06-06 |  | 2024-04-16 |  |  | 3143000 | 3463000 | 6606000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26271 | I/Chemical Toilets/WS/Umziny/No.46 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-04 |  | 2024-12-04 |  |  | 0 | 65460000 | 65460000 | Equitable Share | Maintenance and Repairs
|  | 26272 | DB/500230473/WS | KwaZulu-Natal | NHLOSOKUHLE HIGH SCHOOL | 500230473 | Newcastle | Construction 26% - 50% | Active - Not Contracted | 2017-06-06 | 2024-01-01 | 2025-01-29 | 2026-06-20 | 2027-03-30 | 118270 | 603862 | 722132 | Education Infrastructure Grant | Upgrading and Additions
|  | 26289 | I/Chemical Toilets/WS/Uthukela/ No.85 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-04 |  | 2024-12-11 |  |  | 0 | 54900000 | 54900000 | Equitable Share | Maintenance and Repairs
|  | 26290 | ET/500156917/WS | KwaZulu-Natal | HLENGISIZWE JUNIOR PRIMARY SCHOOL | 500156917 | eThekwini | Final Completion | Active - Contracted | 2015-05-01 | 2017-07-01 | 2023-03-31 | 2019-12-31 | 2023-04-30 | 235799 | 1684281 | 1920080 | Education Infrastructure Grant | Upgrading and Additions
|  | 26295 | W/500102860/WS | KwaZulu-Natal | AMATSHEZULU SECONDARY SCHOOL | 500102860 | eThekwini | Final Completion | Active - Contracted | 2016-05-03 | 2019-07-11 | 2023-06-30 | 2023-02-28 | 2024-02-01 | 472279 | 2151495 | 2623774 | Education Infrastructure Grant | Upgrading and Additions
|  | 26304 | DOPW Various BOREHOLE | KwaZulu-Natal | BOREHOLE MAINTENANCE | ALL DISTRICTS | The Msunduzi | Feasibility | Active - Not Contracted | 2018-01-18 |  | 2024-06-30 |  |  | 0 | 27034000 | 27034000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26305 | ET/500296222/WS | KwaZulu-Natal | WILIWILI PRIMARY SCHOOL | 500296222 | eThekwini | Feasibility | Active - Contracted | 2016-03-01 |  | 2023-03-20 |  |  | 0 | 400000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26311 | ET/500258630/WS | KwaZulu-Natal | SAPHUMELELA PRIMARY SCHOOL | 500258630 | eThekwini | Final Completion | Active - Contracted | 2015-05-01 | 2016-03-24 | 2023-03-24 | 2019-12-31 | 2023-03-31 | 225475 | 1610543 | 1836018 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26312 | ET/500111851/WS | KwaZulu-Natal | BOTHA`S HILL PRIMARY SCHOOL | 500111851 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-03-06 | 2021-01-01 | 2024-12-20 | 2025-12-20 | 2025-12-20 | 1653753 | 7533763 | 9187516 | Education Infrastructure Grant | Upgrading and Additions
|  | 26325 | I/Chemical Toilets/WS/Umkh/No.65 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-18 |  | 2024-12-21 |  |  | 0 | 80071562 | 80071562 | Equitable Share | Maintenance and Repairs
|  | 26336 | I/Chemical Toilets/WS/Uthungulu/ No.33 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-05-10 |  | 2023-04-12 |  |  | 0 | 70712500 | 70712500 | Equitable Share | Maintenance and Repairs
|  | 26349 | W/500200799/WS | KwaZulu-Natal | MASIBONISANE SECONDARY SCHOOL | 500200799 | Umhlabuyalingana | Tender | Active - Not Contracted | 2013-08-02 |  | 2025-03-11 |  |  | 100000 | 100000 | 200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26352 | ET/500265734/WS | KwaZulu-Natal | SILVERDALE PRIMARY SCHOOL | 500265734 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-05-03 | 2023-03-30 | 2023-03-30 | 2024-03-30 | 2025-03-30 | 168185 | 1464172 | 1632357 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 26354 | W/500279905/WS | KwaZulu-Natal | THABELA SECONDARY SCHOOL | 500279905 | eThekwini | Tender | Active - Not Contracted | 2016-05-03 |  | 2026-06-30 |  |  | 672698 | 3064512 | 3737210 | Education Infrastructure Grant | Upgrading and Additions
|  | 26360 | I/Chemical Toilets/WS/Amajuba/No.22 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-01-11 |  | 2024-09-01 |  |  | 1500000 | 30570000 | 32070000 | Equitable Share | Maintenance and Repairs
|  | 26361 | I/Chemical Toilets/WS/Zululand/No.67 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-08-20 |  | 2024-10-20 |  |  | 0 | 77920000 | 77920000 | Equitable Share | Maintenance and Repairs
|  | 26365 | MDOE/UPG/180/19-20(DPWRT/204/19/MP) | Mpumalanga | Ekuphileni Primary School | 800003285 | Thembisile | Construction 51% - 75% | Active - Contracted | 2017-04-03 | 2017-04-04 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 379295 | 2137660 | 2516955 | Education Infrastructure Grant | Upgrading and Additions
|  | 26375 | I/500140859/WS | KwaZulu-Natal | ESINQENI PRIMARY SCHOOL | 500140859 | uPhongolo | Tender | Active - Contracted | 2013-05-10 |  | 2026-03-31 |  |  | 90000 | 412000 | 502000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26377 | W/500109335/WS | KwaZulu-Natal | BHEKUZULU PRIMARY SCHOOL | 500109335 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-06-02 | 2019-04-15 | 2024-04-01 | 2024-06-01 | 2025-06-01 | 828000 | 3773000 | 4601000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26378 | DB/500113072/WS | KwaZulu-Natal | BUHLEBAMANGWE PRIMARY SCHOOL | 500113072 | Nqutu | Construction 1% - 25% | Active - Contracted | 2011-03-06 | 2020-05-31 | 2025-03-31 | 2025-03-22 | 2027-03-25 | 347957 | 1585136 | 1933093 | Education Infrastructure Grant | Upgrading and Additions
|  | 26379 | W/500147519/WS | KwaZulu-Natal | GCINA PRIMARY SCHOOL | 500147519 | Mkhambathini | Design | Active - Not Contracted | 2016-09-12 |  | 2024-04-03 |  |  | 2219000 | 3499000 | 5718000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26380 | W/School Maintenance/UTHKL | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Proposed | 2017-04-01 |  | 2024-06-30 |  |  | 1227000 | 21541000 | 22768000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 26389 | W/500145373/UA | KwaZulu-Natal | FORT LOUIS PRIMARY SCHOOL | 500145373 | Nkandla | Design | Active - Not Contracted | 2016-05-12 |  | 2024-09-23 |  |  | 4200000 | 20000000 | 24200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 26392 | W/500193214/RRR | KwaZulu-Natal | W/MAHLABATHINI SECONDARY SCHOOL | 500193214 | eThekwini | Design | Active - Not Contracted | 2013-08-10 |  | 2024-06-30 |  |  | 1440000 | 6560000 | 8000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27516 | I/500191660/ECD | KwaZulu-Natal | MANDLAMASHA INTERMEDIATE SCHOOL | 500191660 | Dannhauser | On Hold | Active - Not Contracted | 2016-04-01 | 2019-04-15 | 2024-03-30 | 2024-08-15 | 2024-08-31 | 424800 | 1935200 | 2360000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27517 | I/500153846/UA | KwaZulu-Natal | HARDING SECONDARY SCHOOL | 500153846 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2013-08-08 | 2013-10-31 | 2023-10-11 | 2016-11-08 | 2022-12-10 | 4171000 | 19003000 | 23174000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27530 | DB/500425648/WS | KwaZulu-Natal | HILLTOP JUNIOR SECONDARY SCHOOL | 500425648 | Ulundi | Design | Active - Contracted | 2016-02-11 |  | 2024-03-25 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27548 | DB/500266659/WS | KwaZulu-Natal | SINKONKONKO HIGH SCHOOL | 500266659 | Nongoma | Design | Active - Contracted | 2016-02-19 |  | 2024-03-01 |  |  | 1230660 | 5606340 | 6837000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27554 | DB/500168942/SDS | KwaZulu-Natal | ISITHINTA PRIMARY SCHOOL | 500168942 | Mthonjaneni | Final Completion | Approved | 2016-06-10 | 2017-03-30 | 2023-02-17 | 2022-01-30 | 2025-04-20 | 26723 | 121738 | 148461 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27555 | DB/500161098/SDS | KwaZulu-Natal | IMPANDE SECONDARY SCHOOL | 500242461 | uMlalazi | Final Completion | Approved | 2016-06-10 | 2016-12-20 | 2025-03-30 | 2019-01-20 | 2025-03-30 | 53590 | 244132 | 297722 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27556 | I/500423761/UA | KwaZulu-Natal | BOMVINI PRIMARY SCHOOL | 500423761 | Umzimkhulu | Construction 76% - 99% | Active - Contracted | 2010-01-02 | 2010-06-19 | 2023-10-27 | 2016-11-08 | 2023-12-09 | 6828000 | 31105000 | 37933000 | Equitable Share | Upgrading and Additions
|  | 27557 | W/500306545/SDS | KwaZulu-Natal | MVUNDLANA PRIMARY SCHOOL | 500306545 | Mthonjaneni | Tender | Active - Not Contracted | 2016-02-19 |  | 2023-02-17 |  |  | 200000 | 4103774 | 4303774 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27565 | DB/500172457/SDS | KwaZulu-Natal | KATI PRIMARY SCHOOL | DB/500172457/SDS | uMhlathuze | Final Completion | Approved | 2016-06-13 | 2017-02-20 | 2025-08-20 | 2019-05-20 | 2025-08-20 | 97578 | 444522 | 542100 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27567 | W/500199874/SDS | KwaZulu-Natal | MARKLANDS SECONDARY SCHOOL | 500199874 | eThekwini | Tender | Active - Not Contracted | 2016-06-19 |  | 2023-12-01 |  |  | 1298716 | 8093388 | 9392104 | Equitable Share | Upgrading and Additions
|  | 27568 | DB/500140341/SDS | KwaZulu-Natal | ESIGAGANENI PRIMARY SCHOOL | 500140341 | Mfolozi | Final Completion | Active - Contracted | 2016-06-10 | 2022-12-20 | 2023-03-31 | 2022-12-30 | 2027-12-20 | 274578 | 1250854 | 1525432 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27569 | W/500312576/SDS | KwaZulu-Natal | MANYONYO JUNIOR PRIMARY SCHOOL | 500312576 | Umvoti | Design | Active - Not Contracted | 2015-09-20 |  | 2024-06-30 |  |  | 300000 | 1400000 | 1700000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27570 | MDOE//MAIN/111 | Mpumalanga | Libangeni Circuit Office | Circuits Offices | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-05-01 |  |  | 231759 | 1655428 | 1887187 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27571 | DB/500144744/SDS | KwaZulu-Natal | FEZOKUHLE PRIMARY SCHOOL | 500144744 | The Msunduzi | Project Initiation | Active - Not Contracted | 2016-06-09 |  | 2027-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27574 | DB/500235172/SDS | KwaZulu-Natal | NOMYACA HIGH SCHOOL | 500235172 | uMlalazi | Design | Active - Not Contracted | 2016-06-10 |  | 2024-02-26 |  |  | 1322137 | 6023071 | 7345208 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27577 | DB/500139823/SDS | KwaZulu-Natal | ESHOWE SECONDARY SCHOOL | 500139823 | uMlalazi | Final Completion | Approved | 2016-06-10 | 2017-03-30 | 2023-10-31 | 2022-09-01 | 2019-03-29 | 60392 | 275118 | 335510 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27578 | DB/500200614/SDS | KwaZulu-Natal | MASHOBA COMBINED PRIMARY SCHOOL | 500200614 | Mthonjaneni | Design | Active - Not Contracted | 2016-06-23 |  | 2024-01-29 |  |  | 925413 | 4215773 | 5141186 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27581 | W/500125282/SDS | KwaZulu-Natal | DURBAN GIRLS SECONDARY SCHOOL | 500125282 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-19 | 2017-07-01 | 2023-12-01 | 2023-08-31 | 2024-03-31 | 600000 | 2000000 | 2600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27582 | DB/500237799/SDS | KwaZulu-Natal | NSABEKHULUMA SECONDARY SCHOOL | 500237799 | Ulundi | Final Completion | Approved | 2016-06-10 | 2016-12-20 | 2023-10-20 | 2019-04-20 | 2025-06-20 | 1687108 | 6346740 | 8033848 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27583 | DB/500133755/SDS | KwaZulu-Natal | EMOYENI PRIMARY SCHOOL | 500133755 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-01-16 | 2023-07-16 | 2023-07-16 | 2024-03-30 | 584064 | 2660735 | 3244799 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27584 | C/500120213/UA | KwaZulu-Natal | DAWEDE P | 500120213 | eThekwini | Design | Active - Not Contracted | 2017-05-11 |  | 2026-04-30 |  |  | 3110000 | 14169000 | 17279000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27585 | DB/500204536/SDS | KwaZulu-Natal | MSIZI HIGH SCHOOL | 500204536 | Nkandla | Design | Active - Not Contracted | 2016-06-30 |  | 2024-05-31 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27586 | DB/500319310/SDS | KwaZulu-Natal | EMKHAYIDENI TECHNICAL HIGH SCHOOL | 500319310 | Mfolozi | Final Completion | Approved | 2016-06-10 | 2016-12-20 | 2022-11-30 | 2023-05-20 | 2023-03-20 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27587 | W/500106264/WS | KwaZulu-Natal | BATSHAZWAYO SECONDARY SCHOOL | 500106264 | Msinga | Final Completion | Active - Contracted | 2016-02-19 | 2021-02-26 | 2023-06-30 | 2023-02-28 | 2024-05-31 | 548703 | 2709573 | 3258276 | Education Infrastructure Grant | Upgrading and Additions
|  | 27589 | W/500115366/SDS | KwaZulu-Natal | CELIMFUNDO PRIMARY SCHOOL | 500115366 | Msinga | Final Completion | Active - Contracted | 2016-02-19 | 2021-02-26 | 2023-03-31 | 2023-02-28 | 2023-03-31 | 108932 | 1398823 | 1507755 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27592 | DB/500226292/SDS | KwaZulu-Natal | NETHEZEKA HIGH SCHOOL | 500226292 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-05-02 | 2020-06-01 | 2023-02-26 | 2023-02-26 | 2025-03-31 | 724500 | 3452500 | 4177000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27593 | DB/500175195/SDS | KwaZulu-Natal | KHULEKANI PRIMARY SCHOOL | 500175195 | Umvoti | Final Completion | Approved | 2016-01-23 | 2016-04-13 | 2023-04-13 | 2023-04-13 | 2025-04-13 | 742000 | 3380000 | 4122000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27595 | W/500429052/SDS | KwaZulu-Natal | VULAMEHLO PRIMARY SCHOOL | 500429052 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2016-09-20 |  | 2024-07-01 |  |  | 486490 | 2216210 | 2702700 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27597 | DB/500169164/SDS | KwaZulu-Natal | ISNEMBE SECONDARY SCHOOL | 500169164 | Ndwedwe | Design | Active - Not Contracted | 2016-06-13 |  | 2024-10-19 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27604 | W/500296471/SDS | KwaZulu-Natal | SIYABUSA PRIMARY SCHOOL | 500296471 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-02-19 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 361811 | 1648249 | 2010060 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27606 | I/500192622/WS | KwaZulu-Natal | MAGUDU P | DOE12KZNR077 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2013-02-10 | 2013-04-05 | 2024-03-31 | 2018-03-10 | 2024-03-31 | 87183 | 484348 | 571531 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27609 | DB/500215747/WS | KwaZulu-Natal | MOWBRAY PRIMARY SCHOOL | DPW/500215747/SDS | Msinga | Design | Active - Contracted | 2016-02-19 |  | 2024-12-01 |  |  | 72000 | 221621 | 293621 | Education Infrastructure Grant | Upgrading and Additions
|  | 27611 | W/5002238983/SDS | KwaZulu-Natal | NTABASUKA SECONDARY SCHOOL | 500238983 | Ulundi | Tender | Active - Not Contracted | 2016-02-19 |  | 2023-03-01 |  |  | 905364 | 4540501 | 5445865 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27614 | DB/500108595/SDS | KwaZulu-Natal | BHEKIKUSASA HIGH SCHOOL | 500108595 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2017-06-10 | 2019-01-14 | 2023-06-10 | 2023-06-10 | 2027-06-10 | 818390 | 3728220 | 4546610 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27615 | DB/500159026/SDS | KwaZulu-Natal | HULSUG PRIMARY SCHOOL | 500159026 | KwaDukuza | Feasibility | Active - Not Contracted | 2016-06-16 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27617 | W/500426203/SDS | KwaZulu-Natal | LERNFORD BALENI PRIMARY SCHOOL | 500426203 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2015-09-20 |  | 2024-07-01 |  |  | 2892523 | 13177051 | 16069574 | Equitable Share | Upgrading and Additions
|  | 27618 | W/500290709/SDS | KwaZulu-Natal | UYENGO HIGH SCHOOL | 500290709 | Mfolozi | Construction 26% - 50% | Active - Contracted | 2015-02-26 |  | 2025-03-17 |  |  | 1764751 | 8039422 | 9804173 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27619 | W/500111074/SDS | KwaZulu-Natal | BONGIMFUNDO PRIMARY SCHOOL | 500111074 | KwaDukuza | Final Completion | Active - Contracted | 2016-06-16 | 2016-08-30 | 2023-04-30 | 2022-04-30 | 2023-04-30 | 94335 | 1864662 | 1958997 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27621 | DB/500230510/SDS | KwaZulu-Natal | NHLOYA PRIMARY SCHOOL | 500230510 | Nqutu | Final Completion | Approved | 2016-06-10 | 2017-09-20 | 2023-11-30 | 2023-04-20 | 2025-06-20 | 570570 | 2599265 | 3169835 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27622 | W/500129352/SDS | KwaZulu-Natal | EKWAKHENI PRIMARY SCHOOL | 500129352 | Mtubatuba | Design | Active - Not Contracted | 2016-06-06 |  | 2024-06-30 |  |  | 458598 | 2089169 | 2547767 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27623 | W/500292522/SDS | KwaZulu-Natal | VOGELVLEI PRIMARY SCHOOL | 500292522 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2015-09-20 |  | 2024-07-01 |  |  | 48649 | 221621 | 270270 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27624 | DB/500135864/SDS | KwaZulu-Natal | ENDANDATHWENI SECONDARY SCHOOL | 500135864 | Maphumulo | Feasibility | Active - Not Contracted | 2016-06-16 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27625 | DB/500236985/SDS | KwaZulu-Natal | NOVUNULA PRIMARY SCHOOL | 500236985 | Mfolozi | Final Completion | Approved | 2016-06-23 | 2016-12-20 | 2023-05-25 | 2019-04-20 | 2025-06-20 | 538134 | 2024410 | 2562544 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27626 | W/500264069/SDS | KwaZulu-Natal | SIDUMILE PRIMARY SCHOOL | 500264069 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2015-06-20 | 2016-04-01 | 2023-04-30 | 2018-01-30 | 2023-05-31 | 1680000 | 3653000 | 5333000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27627 | W/500290117/SDS | KwaZulu-Natal | UPHINDO SECONDARY SCHOOL | 500290117 | uMlalazi | Tender | Active - Contracted | 2016-02-19 |  | 2025-03-01 |  |  | 992251 | 4520254 | 5512505 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27628 | DB/500201909/SDS | KwaZulu-Natal | MATHUNGELA PRIMARY SCHOOL | 500201909 | uMlalazi | Practical Completion (100%) | Approved | 2016-06-10 | 2017-07-02 | 2025-05-20 | 2021-04-20 | 2025-05-20 | 33518 | 152692 | 186210 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27630 | W/500205683/SDS | KwaZulu-Natal | MCELENI PRIMARY SCHOOL | 500205683 | Umdoni | Project Initiation | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 1919000 | 3319000 | 5238000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27631 | W/500286269/SDS | KwaZulu-Natal | UGOME SECONDARY SCHOOL | 500286269 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-02-19 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 351685 | 4078593 | 4430278 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27632 | DB/500204351/SDS | KwaZulu-Natal | MBHEKAPHANSI HIGH SCHOOL | DB/500204351/SDS | Maphumulo | Final Completion | Approved | 2016-06-16 | 2017-04-20 | 2023-08-16 | 2023-12-20 | 2023-05-20 | 474127 | 1783622 | 2257749 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27633 | W/500426092/SDS | KwaZulu-Natal | KUKHANYENI JUNIOR SECONDARY SCHOOL | 500426092 | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2015-09-20 | 2022-03-30 | 2024-07-01 | 2024-09-30 | 2025-03-30 | 950250 | 4328915 | 5279165 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27634 | DB/500242461/SDS | KwaZulu-Natal | OBUKA SECONDARY SCHOOL | DB/500238576/SDS | Mthonjaneni | Final Completion | Approved | 2016-06-16 | 2017-01-20 | 2022-04-20 | 2022-04-20 | 2025-08-20 | 24286 | 110637 | 134923 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27636 | DB/500440263/WS | KwaZulu-Natal | FISOKUHLE PRIMARY SCHOOL | 500440263 | Msinga | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 340921 | 1553086 | 1894007 | Education Infrastructure Grant | Upgrading and Additions
|  | 27637 | W/500197691/SDS | KwaZulu-Natal | MANYAMPISI PRIMARY SCHOOL | 500197691 | Umhlabuyalingana | Feasibility | Active - Not Contracted | 2016-06-06 |  | 2024-11-30 |  |  | 122940 | 560060 | 683000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27640 | DB/500341214/SDS | KwaZulu-Natal | PHEMBOKUHLE PRIMARY SCHOOL | 500341214 | uMhlathuze | Feasibility | Active - Not Contracted | 2016-06-20 |  | 2024-04-28 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27641 | DB/500440411/SDS | KwaZulu-Natal | NKAYISHANA PRIMARY SCHOOL | 500440411 | Msinga | Final Completion | Approved | 2015-02-19 | 2017-01-20 | 2025-02-20 | 2019-05-30 | 2025-02-20 | 96000 | 435000 | 531000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27642 | W/500235579/SDS | KwaZulu-Natal | NONGOMA PRIMARY SCHOOL | 500235579 | Abaqulusi | Tender | Active - Contracted | 2016-02-19 |  | 2025-03-30 |  |  | 8867479 | 10813999 | 19681478 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27643 | DB/500235320/SDS | KwaZulu-Natal | NONDABULA PRIMARY SCHOOL | DB/500235320/SDS | Ndwedwe | Final Completion | Approved | 2016-06-16 | 2016-10-13 | 2023-04-20 | 2019-03-05 | 2025-04-26 | 819760 | 3083859 | 3903619 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27644 | DB/500126133/SDS | KwaZulu-Natal | EBOMVANENI PRIMARY SCHOOL | 500126133 | uMlalazi | Final Completion | Approved | 2016-06-10 | 2018-08-16 | 2023-11-30 | 2023-12-09 | 2023-04-10 | 477292 | 1193230 | 1670522 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27646 | DB/500262811/SDS | KwaZulu-Natal | SIBHAKUZA SECONDARY SCHOOL | 500262811 | uMlalazi | Final Completion | Approved | 2016-06-23 | 2016-12-20 | 2023-04-21 | 2019-04-20 | 2025-10-20 | 827840 | 3114256 | 3942096 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27647 | W/500204906/SDS | KwaZulu-Natal | MBOVU PRIMARY SCHOOL | 500204906 | eThekwini | Tender | Active - Not Contracted | 2016-08-20 |  | 2023-03-01 |  |  | 200000 | 3649182 | 3849182 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27648 | DB/500284900/SDS | KwaZulu-Natal | TSHANA HIGH SCHOOL | DB/500284900/SDS | Mandeni | Feasibility | Active - Not Contracted | 2016-06-16 |  | 2024-10-26 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27650 | W/500220668/SDS | KwaZulu-Natal | MUNTU HIGH SCHOOL | 500220668 | Msinga | Tender | Active - Contracted | 2016-02-19 |  | 2023-03-31 |  |  | 496999 | 2264105 | 2761104 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27651 | W/500414992/WS | KwaZulu-Natal | ENJABULWENI PRIMARY SCHOOL | 500273208 | uMlalazi | Design | Active - Not Contracted | 2015-07-01 |  | 2023-06-01 |  |  | 1091214 | 4971085 | 6062299 | Education Infrastructure Grant | Upgrading and Additions
|  | 27654 | DB/500272801/SDS | KwaZulu-Natal | SOKHULU PRIMARY SCHOOL | 500272801 | Mfolozi | Final Completion | Approved | 2016-06-23 | 2016-12-20 | 2023-05-18 | 2019-10-20 | 2025-12-20 | 1014569 | 3816713 | 4831282 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27657 | W/500197728/SDS | KwaZulu-Natal | MANYANDENI PRIMARY SCHOOL | 500197728 | Abaqulusi | Tender | Active - Not Contracted | 2016-02-19 |  | 2023-03-17 |  |  | 1380917 | 6290844 | 7671761 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27658 | DB/500276686/SDS | KwaZulu-Natal | ST PAUL PRIMARY SCHOOL | 500276686 | Mthonjaneni | Feasibility | Active - Not Contracted | 2016-06-23 |  | 2024-05-19 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27659 | W/500181855/WS | KwaZulu-Natal | KWAMTHOLO PRIMARY SCHOOL | 500181855 | Umhlabuyalingana | Tender | Active - Contracted | 2015-08-20 |  | 2026-11-01 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Upgrading and Additions
|  | 27664 | W/500429015/SDS | KwaZulu-Natal | VUKANI JUNIOR SECONDARY SCHOOL | 500429015 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2015-08-20 | 2017-03-30 | 2023-02-01 | 2023-01-30 | 2023-09-30 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27669 | W/500174418/SDS | KwaZulu-Natal | KHETHWAYO PRIMARY SCHOOL | 500174418 | Jozini | Design | Active - Not Contracted | 2016-06-06 |  | 2024-12-15 |  |  | 1016216 | 4629427 | 5645643 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27670 | W/500211455/WS | KwaZulu-Natal | MJINDI SECONDARY SCHOOL | 500211455 | Jozini | Tender | Active - Contracted | 2016-06-06 |  | 2025-02-10 |  |  | 776115 | 3535633 | 4311748 | Education Infrastructure Grant | Upgrading and Additions
|  | 27671 | W/500290598/SDS | KwaZulu-Natal | UTRECH PRIMARY SCHOOL | 500290598 | Emadlangeni | Design | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 2329544 | 10612366 | 12941910 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27673 | W/500116846/RRR | KwaZulu-Natal | CLAIRWOOD PRIMARY SCHOOL | 500116846 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2023-03-30 |  |  | 24000 | 520000 | 544000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27674 | DB/500267140/WS | KwaZulu-Natal | SIPHEPHEME SECONDARY SCHOOL | 500267140 | Ubuhlebezwe | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 539139 | 2456078 | 2995217 | Education Infrastructure Grant | Upgrading and Additions
|  | 27679 | W/500198504/SDS | KwaZulu-Natal | MAMPONJWANA PRIMARY SCHOOL | 500198504 | Okhahlamba | Final Completion | Active - Contracted | 2016-06-06 | 2018-02-01 | 2023-04-26 | 2023-04-26 | 2023-04-26 | 584151 | 5691434 | 6275585 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27680 | DB/500247197/SDS | KwaZulu-Natal | PETEZI PRIMARY SCHOOL | DB/500247197/SDS | Maphumulo | Final Completion | Approved | 2016-06-13 | 2016-12-20 | 2023-10-19 | 2019-10-20 | 2025-11-20 | 687023 | 2584514 | 3271537 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27681 | DB/500123062/SDS | KwaZulu-Natal | DOUGLAS P | DB/500294668/SDS | Msinga | Feasibility | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27683 | W/500266511/SDS | KwaZulu-Natal | SINENHLANHLA PRIMARY SCHOOL | 500266511 | eThekwini | Design | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27687 | DB/500196766/SDS | KwaZulu-Natal | MANGETHE PRIMARY SCHOOL | 500196766 | Mandeni | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2024-11-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27688 | W/500134495/SDS | KwaZulu-Natal | EMPUNGENI PRIMARY SCHOOL | 500134495 | uMhlathuze | Tender | Active - Not Contracted | 2016-06-06 |  | 2024-12-15 |  |  | 1555372 | 19803971 | 21359343 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27690 | DB/500186258/SDS | KwaZulu-Natal | LETHUXOLO SECONDARY SCHOOL | 500186258 | Maphumulo | Final Completion | Approved | 2016-06-13 | 2017-01-20 | 2023-11-14 | 2019-06-20 | 2024-10-20 | 540855 | 2034643 | 2575498 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27691 | DB/500230954/SDS | KwaZulu-Natal | NIZAM ROAD PRIMARY SCHOOL | DB/500230954/SDS | eThekwini | Design | Active - Contracted | 2016-06-13 |  | 2024-11-30 |  |  | 1131000 | 5153000 | 6284000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27692 | W/500218670/SDS | KwaZulu-Natal | MSINGA HIGH SCHOOL | 500218670 | Msinga | Tender | Active - Contracted | 2016-02-19 |  | 2025-03-26 |  |  | 360370 | 3876247 | 4236617 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27693 | W/500113442/SDS | KwaZulu-Natal | BUHLEBUZILE PRIMARY SCHOOL | 500113442 | uPhongolo | Tender | Proposed | 2016-02-19 |  | 2025-06-30 |  |  | 347164 | 2884720 | 3231884 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27699 | W/500275428/SDS | KwaZulu-Natal | ST CHRISTOPHER SPECIAL SCHOOL | 500275428 | The Msunduzi | Tender | Active - Not Contracted | 2015-08-20 |  | 2023-06-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27703 | DB/500201872/SDS | KwaZulu-Natal | MATHUBESIZWE SECONDARY SCHOOL | DB/500201872/SDS | Mandeni | Final Completion | Approved | 2016-06-13 | 2017-02-20 | 2023-10-26 | 2022-12-13 | 2024-03-20 | 1490254 | 5606194 | 7096448 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27704 | W/500177600/SDS | KwaZulu-Natal | KUFANELESIBONGE JUNIOR SECONDARY SCHOOL | 500177600 | Msinga | Final Completion | Active - Contracted | 2016-02-19 | 2018-04-27 | 2023-12-31 | 2023-12-29 | 2025-12-29 | 513923 | 3575536 | 4089459 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27708 | DB/500281718/SDS | KwaZulu-Natal | THEMBENI PRIMARY SCHOOL | DB/500281718/SDS | KwaDukuza | Design | Active - Not Contracted | 2016-06-13 |  | 2024-11-17 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27709 | DB/500108410/SDS | KwaZulu-Natal | BHEKAPHAMBILI | 500108410 | eThekwini | Practical Completion (100%) | Approved | 2017-06-13 | 2018-01-12 | 2022-06-04 | 2022-06-04 | 2025-06-04 | 168669 | 1990331 | 2159000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27710 | DB/500152884/SDS | KwaZulu-Natal | GWIJA PRIMARY SCHOOL | 500152884 | Nqutu | Final Completion | Approved | 2016-02-19 | 2017-03-20 | 2022-12-01 | 2022-05-20 | 2025-06-20 | 33518 | 152692 | 186210 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27711 | W/500218263/SDS | KwaZulu-Natal | MSENI PRIMARY SCHOOL | 500218263 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-02-19 |  | 2023-02-16 |  |  | 49000 | 1177467 | 1226467 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27712 | W/500282347/SDS | KwaZulu-Natal | THOKOZWAYO SECONDARY SCHOOL | 500282347 | Richmond | Design | Active - Contracted | 2015-08-20 |  | 2025-06-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27713 | W/500136530/SDS | KwaZulu-Natal | ENGONWENI PRIMARY SCHOOL | 500136530 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2020-04-20 | 2023-12-15 | 2024-04-02 | 2024-04-19 | 110105 | 5831903 | 5942008 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27714 | DB/500212232/WS | KwaZulu-Natal | MKHULUNYELWA PRIMARY SCHOOL | 500212232 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2020-05-31 | 2025-01-30 | 2022-01-30 | 2027-01-30 | 449949 | 2049768 | 2499717 | Education Infrastructure Grant | Upgrading and Additions
|  | 27715 | DB/500203315/SDS | KwaZulu-Natal | MAZISI NTULI PRIMARY SCHOOL | 500203315 | Maphumulo | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2024-04-27 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27716 | W/500170496/SDS | KwaZulu-Natal | IZINTAMBANE PRIMARY SCHOOL | 500170496 | Big Five Hlabisa | Final Completion | Active - Contracted | 2017-02-19 |  | 2023-03-01 |  |  | 787943 | 4424824 | 5212767 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27717 | W/500128020/SDS | KwaZulu-Natal | EKHOMBELA PRIMARY SCHOOL | 500128020 | eDumbe | Tender | Active - Not Contracted | 2016-02-19 |  | 2023-06-30 |  |  | 595778 | 3691185 | 4286963 | Education Infrastructure Grant | Upgrading and Additions
|  | 27718 | DB/500120731/SDS | KwaZulu-Natal | DENDETHU PRIMARY SCHOOL | 500120731 | Mandeni | Final Completion | Approved | 2016-06-13 | 2017-01-11 | 2023-02-20 | 2019-03-15 | 2019-04-05 | 279566 | 1273576 | 1553142 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27719 | DB/500261257/SDS | KwaZulu-Natal | SHALLCROSS PRIMARY SCHOOL | 500261257 | eThekwini | Final Completion | Approved | 2016-06-13 | 2017-03-30 | 2023-11-30 | 2018-09-01 | 2025-10-31 | 301264 | 1133325 | 1434589 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27720 | C/ELECTRICITY/ALL DISTRICTS | KwaZulu-Natal | lakeside ps | 500184926 | Abaqulusi | Feasibility | Proposed | 2016-02-19 |  | 2026-02-17 |  |  | 0 | 22162100 | 22162100 | Education Infrastructure Grant | Upgrading and Additions
|  | 27721 | W/500141044/SDS | KwaZulu-Natal | ESIPHETHWINI SENDIZA PRIMARY SCHOOL | 500141044 | uMngeni | Design | Active - Contracted | 2016-06-06 | 2017-12-01 | 2023-12-15 | 2018-12-12 | 2023-05-30 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27722 | W/500116624/SDS | KwaZulu-Natal | COSH PRIMARY SCHOOL | 500116624 | Msinga | Tender | Active - Not Contracted | 2016-02-19 |  | 2025-03-30 |  |  | 73894 | 1268306 | 1342200 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27724 | W/500152477/SDS | KwaZulu-Natal | GUDU SECONDARY SCHOOL | 500152477 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-02-19 | 2022-03-30 | 2023-05-17 | 2024-03-30 | 2025-04-30 | 1719423 | 7832926 | 9552349 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27725 | DB/500338513/SDS | KwaZulu-Natal | PLATT DRIVE PRIMARY SCHOOL | DB/500338513/SDS | eThekwini | Final Completion | Approved | 2016-06-13 | 2018-01-12 | 2025-06-05 | 2018-06-05 | 2025-06-05 | 227732 | 4524504 | 4752236 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27727 | DB/500209568/SDS | KwaZulu-Natal | MGOMBANE PRIMARY SCHOOL | 500209568 | Msinga | Final Completion | Approved | 2016-02-19 | 2016-08-06 | 2025-03-20 | 2018-02-20 | 2025-03-20 | 749110 | 3412610 | 4161720 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27728 | DB/500101380/SDS | KwaZulu-Natal | AMAGCINO SECONDARY SCHOOL | 500101380 | eThekwini | Practical Completion (100%) | Approved | 2017-09-19 | 2018-04-05 | 2025-05-03 | 2018-10-03 | 2027-05-03 | 861634 | 6225366 | 7087000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27729 | DB/500335516/SDS | KwaZulu-Natal | UKUZAMAKWETHU SECONDARY SCHOOL | 500335516 | Ndwedwe | Final Completion | Approved | 2016-06-13 | 2018-12-01 | 2022-10-04 | 2022-11-02 | 2025-12-06 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27732 | DB/500442964/WS | KwaZulu-Natal | KHULANGOLWAZI SECONDARY SCHOOL | 500442964 | Umhlabuyalingana | Design | Active - Contracted | 2016-02-19 |  | 2024-12-01 |  |  | 720000 | 2216210 | 2936210 | Education Infrastructure Grant | Upgrading and Additions
|  | 27733 | I/500189847/WS | KwaZulu-Natal | MABASO JUNIOR PRIMARY SCHOOL | 500189847 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-10-20 | 2023-03-31 | 2018-03-20 | 2023-03-31 | 245910 | 1366172 | 1612082 | Education Infrastructure Grant | Upgrading and Additions
|  | 27737 | W/500215747/SDS | KwaZulu-Natal | MOWBRAY PRIMARY SCHOOL | 500215747 | Msinga | Tender | Active - Not Contracted | 2016-02-19 |  | 2024-01-01 |  |  | 1220431 | 5559740 | 6780171 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27738 | W/500145077/SDS | KwaZulu-Natal | FLORENCE BOOTH INTERMEDIATE SCHOOL | 500145077 | Inkosi Langalibalele | Tender | Active - Contracted | 2016-06-06 |  | 2025-12-15 |  |  | 723202 | 3294587 | 4017789 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27739 | DB/500411070/SDS | KwaZulu-Natal | Zibambele P | 500411070 | Mthonjaneni | Final Completion | Approved | 2016-06-22 | 2016-12-20 | 2023-05-19 | 2023-12-20 | 2023-10-20 | 324281 | 1477279 | 1801560 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27741 | DB/500303585/SDS | KwaZulu-Natal | IMPOPHOMA PRIMARY SCHOOL | 500303585 | Msinga | Final Completion | Approved | 2016-02-19 | 2016-06-19 | 2022-12-01 | 2022-08-31 | 2025-03-15 | 23740 | 108148 | 131888 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27744 | DB/500195989/SDS | KwaZulu-Natal | KEARSNEY PRIMARY SCHOOL | 500195989 | KwaDukuza | Final Completion | Approved | 2016-06-13 | 2017-01-20 | 2023-10-27 | 2019-10-20 | 2024-02-20 | 1390930 | 5232546 | 6623476 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27750 | DB/500109483/SDS | KwaZulu-Natal | BHIDAKHONA PRIMARY SCHOOL | 500109483 | Maphumulo | Final Completion | Approved | 2016-06-13 | 2019-11-20 | 2023-11-10 | 2023-12-20 | 2023-05-20 | 1146349 | 4312457 | 5458806 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27753 | DB/500114108/WS | KwaZulu-Natal | CABANGOKUHLE HIGH SCHOOL | 500114108 | Msinga | Construction 26% - 50% | Active - Contracted | 2016-02-19 | 2020-05-31 | 2025-03-25 | 2022-03-22 | 2025-03-25 | 516523 | 2353051 | 2869574 | Education Infrastructure Grant | Upgrading and Additions
|  | 27754 | DB/500148703/SDS | KwaZulu-Natal | GIJIMANA SECONDARY SCHOOL | 500148703 | Mfolozi | Design | Active - Not Contracted | 2016-06-16 |  | 2027-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27756 | W/500275687/SDS | KwaZulu-Natal | ST FRANCIS PRIMARY SCHOOL | 500275687 | Umdoni | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-09-10 | 2022-06-30 | 2020-08-30 | 2023-03-15 | 800000 | 2216210 | 3016210 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27763 | W/500119399/SDS | KwaZulu-Natal | DALALA PRIMARY SCHOOL | 500116624 | Msinga | Tender | Active - Not Contracted | 2016-02-19 |  | 2025-04-26 |  |  | 202056 | 1981565 | 2183621 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27766 | DB/500170311/SDS | KwaZulu-Natal | IZIBUKO SECONDARY SCHOOL | DB/500170311/SDS | uMlalazi | Final Completion | Approved | 2016-06-23 | 2016-12-20 | 2025-10-20 | 2019-05-20 | 2025-10-20 | 882460 | 2020100 | 2902560 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27767 | DB/500306175/SDS | KwaZulu-Natal | ENKANYISWENI PRIMARY SCHOOL | 500338513 | eThekwini | Final Completion | Approved | 2016-06-13 | 2017-10-04 | 2023-11-30 | 2023-12-14 | 2023-03-14 | 50223 | 228795 | 279018 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27768 | W/500427165/SDS | KwaZulu-Natal | MZOKHANYAYO JUNIOR SECONDARY SCHOOL | 500427165 | Ubuhlebezwe | Tender | Active - Not Contracted | 2016-02-19 |  | 2023-03-24 |  |  | 1198000 | 2478000 | 3676000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27770 | DB/500117549/WS | KwaZulu-Natal | NOMZAMO PRIMARY SCHOOL | 500117549 | Greater Kokstad | Construction 1% - 25% | Active - Contracted | 2016-06-13 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 544611 | 2481005 | 3025616 | Education Infrastructure Grant | Upgrading and Additions
|  | 27772 | W/500175380/WS | KwaZulu-Natal | KHUMBULANI PRIMARY SCHOOL | 500205165 | Umvoti | Tender | Active - Contracted | 2016-02-20 |  | 2026-06-30 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Upgrading and Additions
|  | 27773 | W/500340178/SDS | KwaZulu-Natal | ENKOMOKAZINI PRIMARY SCHOOL | 500340178 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2016-01-01 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-06-30 | 1524006 | 5733164 | 7257170 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27774 | DB/500174899/SDS | KwaZulu-Natal | KHOZA HIGH SCHOOL | 500174899 | uPhongolo | Final Completion | Approved | 2016-06-13 | 2017-10-02 | 2023-11-30 | 2023-12-20 | 2023-08-20 | 809305 | 3044528 | 3853833 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27777 | W/500113331/WS | KwaZulu-Natal | BUHLEBEZWE PRIMARY SCHOOL | 500113294 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-02-01 | 2023-09-29 | 2020-03-31 | 2024-05-31 | 594213 | 2706970 | 3301183 | Education Infrastructure Grant | Upgrading and Additions
|  | 27779 | W/500213860/SDS | KwaZulu-Natal | MNTANUNGAMZIZWE HIGH SCHOOL | 500213860 | Umzumbe | Project Initiation | Active - Contracted | 2016-02-19 |  | 2023-02-16 |  |  | 1923000 | 3323000 | 5246000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27782 | DB/500120694/WS | KwaZulu-Natal | DELIHLAZO COMBINED SCHOOL | DB/500120694/SDS | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2022-06-01 | 2024-03-20 | 2024-03-30 | 2025-05-30 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27783 | DB/500241018/SDS | KwaZulu-Natal | NTUTHUNGA PRIMARY SCHOOL | DB/500241018/SDS | Mfolozi | Final Completion | Approved | 2016-05-12 | 2016-08-20 | 2025-05-20 | 2019-02-20 | 2025-05-20 | 577429 | 2630512 | 3207941 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27785 | DB/500100455/SDS | KwaZulu-Natal | ADDINGTON PRIMARY SCHOOL | 500100455 | eThekwini | Design | Active - Not Contracted | 2017-10-06 |  | 2024-01-20 |  |  | 541968 | 2468965 | 3010933 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27786 | DB/500158249/SDS | KwaZulu-Natal | HOLWANE PRIMARY SCHOOL | DB/500158249/SDS | Msinga | Final Completion | Approved | 2016-06-13 | 2017-08-20 | 2025-03-30 | 2019-08-20 | 2025-03-30 | 434000 | 1979000 | 2413000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27789 | DB/500232582/SDS | KwaZulu-Natal | NKOSAZANA PRIMARY SCHOOL | 500232582 | uMhlathuze | Design | Active - Not Contracted | 2017-06-13 |  | 2024-11-24 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 27791 | DB/500169534/SDS | KwaZulu-Natal | ITHEMBANI PRIMARY SCHOOL | 500169534 | Msinga | Final Completion | Approved | 2016-02-19 | 2017-03-30 | 2025-04-20 | 2018-03-30 | 2025-04-20 | 100000 | 545000 | 645000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27793 | DB/500237059/SDS | KwaZulu-Natal | NOYIBEWU PRIMARY SCHOOL | DB/500237059/SDS | Nkandla | Final Completion | Approved | 2016-06-29 | 2016-12-20 | 2023-04-28 | 2019-05-20 | 2025-06-20 | 164337 | 618219 | 782556 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27795 | DB/500176305/SDS | KwaZulu-Natal | KLAARWATER PRIMARY SCHOOL | 500176305 | eThekwini | Final Completion | Approved | 2016-06-13 | 2017-09-20 | 2023-11-30 | 2023-12-20 | 2023-06-10 | 1253982 | 4717362 | 5971344 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27796 | DB/500138935/SDS | KwaZulu-Natal | ENYANISWENI PRIMARY SCHOOL | 500138935 | Ray Nkonyeni | Final Completion | Approved | 2016-06-13 | 2018-12-01 | 2023-10-27 | 2023-05-05 | 2023-03-04 | 960822 | 3614521 | 4575343 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27797 | DB/500137640/SDS | KwaZulu-Natal | ENKONENI PRIMARY SCHOOL | 500137640 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-01-15 | 2023-03-31 | 2023-12-05 | 2023-03-30 | 1380231 | 6287721 | 7667952 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27801 | DB/500307581/SDS | KwaZulu-Natal | UMPHEZENI SECONDARY SCHOOL | 500307581 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2017-06-24 | 2019-01-15 | 2023-07-15 | 2023-05-05 | 2023-03-04 | 997930 | 4546125 | 5544055 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27802 | DB/500142561/SDS | KwaZulu-Natal | ETSHENILIKASHOBA PRIMARY SCHOOL | 500142561 | Ray Nkonyeni | Final Completion | Approved | 2016-06-13 | 2016-10-20 | 2023-11-16 | 2022-04-20 | 2022-08-20 | 801580 | 3015469 | 3817049 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27804 | W/500303881/SDS | KwaZulu-Natal | DALTON BRIDGE PRIMARY SCHOOL | 500303881 | Msinga | Tender | Active - Not Contracted | 2016-02-19 |  | 2025-06-30 |  |  | 60539 | 1209661 | 1270200 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27805 | W/500206238/SDS | KwaZulu-Natal | MDLAZI PRIMARY SCHOOL | 500206238 | Umzumbe | Practical Completion (100%) | Active - Not Contracted | 2017-11-20 | 2019-08-27 | 2023-03-31 | 2022-03-31 | 2023-03-31 | 1085000 | 5065000 | 6150000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27807 | DB/500285677/SDS | KwaZulu-Natal | UBIZO PRIMARY SCHOOL | 500285677 | uMhlathuze | Feasibility | Active - Contracted | 2016-06-24 |  | 2024-11-28 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27808 | DB/500166722/SDS | KwaZulu-Natal | INYANDEZULU PRIMARY SCHOOL | 500166722 | Ray Nkonyeni | Final Completion | Approved | 2016-06-13 | 2016-12-20 | 2023-11-10 | 2019-05-20 | 2025-06-20 | 1868493 | 7029093 | 8897586 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27809 | DB/500159618/SDS | KwaZulu-Natal | IGUGULABANGUNI PRIMARY SCHOOL | 500159618 | eThekwini | Final Completion | Approved | 2016-06-13 | 2018-03-13 | 2023-03-30 | 2023-04-04 | 2023-07-11 | 451778 | 1699546 | 2151324 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27811 | W/500424242/WS | KwaZulu-Natal | DEEPDALE JUNIOR SECONDARY SCHOOL | 500244242 | eThekwini | Final Completion | Active - Contracted | 2015-09-20 | 2019-03-21 | 2023-03-21 | 2022-03-21 | 2023-03-21 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27812 | DB/500104710/SDS | KwaZulu-Natal | BADELILE PRIMARY SCHOOL | 500104710 | eThekwini | Final Completion | Approved | 2017-06-13 | 2020-05-29 | 2022-05-29 | 2023-05-29 | 2025-05-29 | 1258152 | 5788848 | 7047000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27816 | W/500229548/WS | KwaZulu-Natal | NHLABAMKHOSI PRIMARY SCHOOL | 500229548 | Nqutu | Tender | Active - Contracted | 2016-02-19 |  | 2025-01-25 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27818 | DB/500181485/SDS | KwaZulu-Natal | KWAMPHELELWA PRIMARY SCHOOL | 500181485 | Ray Nkonyeni | Final Completion | Approved | 2016-06-13 | 2016-11-20 | 2023-11-17 | 2019-02-20 | 2022-05-20 | 1079096 | 4059458 | 5138554 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27820 | DB/500299700/SDS | KwaZulu-Natal | ZIBONE PRIMARY SCHOOL | 500299700 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2020-01-06 | 2020-03-14 | 2022-06-07 | 2022-08-10 | 2027-10-28 | 818882 | 3730463 | 4549345 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27826 | W/500303696/WS | KwaZulu-Natal | OKHULANA PRIMARY SCHOOL | 500303696 | Msinga | Tender | Active - Contracted | 2016-02-19 |  | 2025-06-30 |  |  | 515000 | 2453000 | 2968000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27830 | DB/500240500/SDS | KwaZulu-Natal | NTSHIBANTSHIBA PRIMARY SCHOOL | DB/500240500/SDS | Abaqulusi | Final Completion | Approved | 2016-06-30 | 2016-12-20 | 2023-05-18 | 2019-05-20 | 2025-06-20 | 1730292 | 6509193 | 8239485 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27831 | DB/500175084/SDS | KwaZulu-Natal | KHULANGOLWAZI SENIOR PRIMARY SCHOOL | 500175084 | Mtubatuba | Final Completion | Approved | 2016-06-13 | 2017-05-20 | 2024-06-20 | 2019-02-20 | 2024-06-20 | 271000 | 1234000 | 1505000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27832 | W/500288785/SDS | KwaZulu-Natal | UMQONGQOTHO PRIMARY SCHOOL | 500288785 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-09-20 | 2018-02-28 | 2023-06-30 | 2020-12-30 | 2025-03-15 | 486490 | 2216210 | 2702700 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27836 | DB/500212898/SDS | KwaZulu-Natal | MLONDE SECONDARY SCHOOL | DB/500212898/SDS | Ray Nkonyeni | Final Completion | Approved | 2016-06-13 | 2016-11-20 | 2023-10-27 | 2023-04-20 | 2023-06-20 | 1979806 | 7447841 | 9427647 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27837 | W/500180745/WS | KwaZulu-Natal | KWAMASOSHA SECONDARY SCHOOL | 500180745 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-02-01 | 2023-03-11 | 2019-03-29 | 2025-09-30 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27840 | DB/500265956/SDS | KwaZulu-Natal | SIMANDLANGENTSHA PRIMARY SCHOOL | 500265956 | uPhongolo | Feasibility | Active - Not Contracted | 2016-06-22 |  | 2024-04-28 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27841 | DB/500276131/SDS | KwaZulu-Natal | ST MARTINS DU PORRES PRIMARY SCHOOL | 500276131 | Ray Nkonyeni | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2024-10-27 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27842 | DB/500138121/SDS | KwaZulu-Natal | ENQOLENI PRIMARY SCHOOL | 500138121 | uMlalazi | Design | Active - Not Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27853 | DB/500276797/SDS | KwaZulu-Natal | ST THERESA PRIMARY SCHOOL | 500276797 | eThekwini | Final Completion | Approved | 2016-06-13 | 2016-09-20 | 2023-10-27 | 2019-02-20 | 2025-08-20 | 1117454 | 4203755 | 5321209 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27856 | DB/500283605/SDS | KwaZulu-Natal | THULWANA HIGH SCHOOL | 500283605 | Nongoma | Final Completion | Approved | 2016-06-17 | 2016-12-20 | 2023-04-28 | 2019-05-20 | 2024-11-20 | 1212350 | 4560744 | 5773094 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27858 | DB/500138306/SDS | KwaZulu-Natal | ENTABENI PRIMARY SCHOOL | 500138306 | Ray Nkonyeni | Terminated | Active - Contracted | 2016-06-06 | 2020-04-30 | 2025-03-30 | 2020-11-30 | 2027-03-30 | 1648372 | 7509250 | 9157622 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27860 | W/500200318/SDS | KwaZulu-Natal | MASHESHISA PRIMARY SCHOOL (LADYSMITH) | 500200318 | Alfred Duma | Final Completion | Active - Contracted | 2016-02-19 | 2018-04-27 | 2023-08-31 | 2023-10-30 | 2023-11-11 | 518807 | 3425506 | 3944313 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27861 | W/500136234/SDS | KwaZulu-Natal | ENDWEBU COMPREHENSIVE PRIMARY SCHOOL | 500136234 | Ubuhlebezwe | Practical Completion (100%) | Proposed | 2016-11-20 | 2018-03-30 | 2024-05-31 | 2021-01-31 | 2024-05-31 | 400000 | 700000 | 1100000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27866 | W/500204610/SDS | KwaZulu-Natal | MBOKO PRIMARY SCHOOL | 500204610 | eThekwini | Tender | Active - Not Contracted | 2016-02-19 |  | 2025-06-01 |  |  | 588121 | 2679216 | 3267337 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27868 | DB/500301476/WS | KwaZulu-Natal | ZUZICEBO HIGH SCHOOL | 500301476 | uMuziwabantu | Design | Active - Contracted | 2016-06-13 |  | 2025-09-23 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27870 | DB/500335072/SDS | KwaZulu-Natal | GEORGE CALTEX PRIMARY SCHOOL | 500335072 | Umhlabuyalingana | Feasibility | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27872 | DB/500222444/SDS | KwaZulu-Natal | Mziyonke P | DPW/500222444/SDS | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2017-02-19 | 2020-05-29 | 2025-03-20 | 2021-02-15 | 2025-03-20 | 1306688 | 5952689 | 7259377 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27873 | W/500179376/SDS | KwaZulu-Natal | KWAFICA HIGH SCHOOL | 500179376 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2022-03-30 | 2023-07-01 | 2024-03-30 | 2025-03-30 | 1684270 | 7672783 | 9357053 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27874 | DB/500159359/WS | KwaZulu-Natal | IDIDIMA PRIMARY SCHOOL | 500159359 | Okhahlamba | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-12-15 | 2023-12-15 | 2027-12-15 | 457953 | 2086232 | 2544185 | Education Infrastructure Grant | Upgrading and Additions
|  | 27879 | W/500138306/SDS | KwaZulu-Natal | ENTABENI CP | 5002138306 | Umzumbe | Tender | Active - Not Contracted | 2016-11-20 |  | 2023-07-01 |  |  | 2616429 | 11919286 | 14535715 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27880 | W/500446775/SDS | KwaZulu-Natal | KHULANI PRIMARY SCHOOL | 500446775 | eThekwini | Final Completion | Active - Contracted | 2016-06-06 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2024-06-30 | 307386 | 1753003 | 2060389 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27884 | W/500268953/SDS | KwaZulu-Natal | SITHOLINHLANHLA PRIMARY SCHOOL | 500268953 | Ulundi | Final Completion | Active - Contracted | 2015-02-19 |  | 2023-06-30 |  |  | 2504925 | 11411324 | 13916249 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27886 | W/500301513/SDS | KwaZulu-Natal | ZUZIMFUNDO PRIMARY SCHOOL | 500301513 | Alfred Duma | Tender | Active - Not Contracted | 2016-02-19 |  | 2025-12-01 |  |  | 513976 | 2341445 | 2855421 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27887 | DB/500217375/SDS | KwaZulu-Natal | MPUKUNYONI SP | DB/500217375/SDS | Umhlabuyalingana | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27888 | W/500169645/SDS | KwaZulu-Natal | ITHONGASI PRIMARY SCHOOL | 500169645 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2017-12-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 700000 | 1300000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27891 | W/500115625/RRR | KwaZulu-Natal | CENTENARY SECONDARY SCHOOL | 500115625 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2024-03-15 |  |  | 4080000 | 6455000 | 10535000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27894 | W/500325267/WS | KwaZulu-Natal | ZWILENKOSI JUNIOR SECONDARY SCHOOL | 500325267 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-02-19 | 2016-06-19 | 2023-06-30 | 2021-06-30 | 2023-03-30 | 679674 | 3096291 | 3775965 | Education Infrastructure Grant | Upgrading and Additions
|  | 27895 | W/500262885/SDS | KwaZulu-Natal | SIBHANGWANA PRIMARY SCHOOL | 5002652885 | Ray Nkonyeni | Tender | Active - Not Contracted | 2015-11-20 |  | 2023-11-29 |  |  | 925942 | 4218180 | 5144122 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27898 | DB/500222037/SDS | KwaZulu-Natal | MZILA SP | DB/500222037/SDS | Umhlabuyalingana | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2024-11-29 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27900 | DB/500138750/SDS | KwaZulu-Natal | ENTUTHUKWENI PRIMARY SCHOOL | DB/500138750/SDS | eThekwini | Final Completion | Approved | 2015-11-20 | 2018-01-15 | 2023-07-18 | 2023-07-18 | 2024-03-30 | 1100609 | 5013885 | 6114494 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27907 | W/500160617/SDS | KwaZulu-Natal | IMBIZANE PRIMARY SCHOOL | 500160617 | Ray Nkonyeni | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 1736690 | 7911586 | 9648276 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27908 | DB/500167536/SDS | KwaZulu-Natal | ISIBONGO PRIMARY SCHOOL | 500167536 | uMngeni | Feasibility | Active - Contracted | 2016-06-06 |  | 2024-12-15 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27910 | DB/500342213/SDS | KwaZulu-Natal | NCEKUYA PRIMARY SCHOOL | 500342213 | uMhlathuze | Design | Active - Contracted | 2017-09-20 |  | 2024-10-26 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 27911 | W/500165279/SDS | KwaZulu-Natal | INKUTHU PRIMARY SCHOOL | 500165279 | Alfred Duma | Final Completion | Active - Contracted | 2016-02-19 | 2016-06-19 | 2023-03-29 | 2022-05-29 | 2023-03-29 | 564924 | 2573545 | 3138469 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27913 | DB/500211048/SDS | KwaZulu-Natal | MIDDLEFIELD PRIMARY SCHOOL | 500211048 | Mpofana | Feasibility | Active - Contracted | 2016-06-06 |  | 2024-12-15 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27914 | W/500489954/SDS | KwaZulu-Natal | THEMBINKOSI PRIMARY SCHOOL | 500489954 | Newcastle | Design | Active - Not Contracted | 2016-09-21 |  | 2023-06-30 |  |  | 48649 | 221621 | 270270 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27915 | DB/500288193/SDS | KwaZulu-Natal | UMLAMBOZANA PRIMARY SCHOOL | 500288193 | Big Five Hlabisa | Project Initiation | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 72000 | 328000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27916 | W/500494357/SDS | KwaZulu-Natal | ERIC MTSHALI SECONDARY SCHOOL | 500494357 | eThekwini | Practical Completion (100%) | Proposed | 2017-01-01 | 2017-11-20 | 2023-05-29 | 2023-07-31 | 2023-03-31 | 161144 | 734102 | 895246 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27927 | W/500444962/WS | KwaZulu-Natal | PHUTHINI SECONDARY SCHOOL | 500444962 | Okhahlamba | Design | Active - Not Contracted | 2016-02-19 |  | 2024-06-28 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27930 | DB/500284678/WS | KwaZulu-Natal | TRIANDRA PRIMARY SCHOOL | 500284678 | The Msunduzi | Design | Active - Not Contracted | 2016-02-19 |  | 2024-12-10 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27931 | DB/500299811/SDS | KwaZulu-Natal | ZICABANGELE PRIMARY SCHOOL | 500299811 | uMhlathuze | Final Completion | Approved | 2016-02-19 | 2018-04-13 | 2023-12-01 | 2023-12-12 | 2023-03-19 | 1309834 | 4927473 | 6237307 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27934 | W/500138861/SDS | KwaZulu-Natal | ENXOLOLENI PRIMARY SCHOOL | 500138861 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-11-20 | 2020-04-20 | 2023-04-30 | 2020-06-30 | 2023-04-30 | 700000 | 2216210 | 2916210 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27935 | W/500224849/WS | KwaZulu-Natal | NDENGETHO SECONDARY SCHOOL | 500224849 | eThekwini | On Hold | Active - Not Contracted | 2016-06-20 |  | 2023-03-24 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27936 | DB/500101306/SDS | KwaZulu-Natal | AMABUYE PRIMARY SCHOOL | 500101306 | uMhlathuze | Design | Active - Not Contracted | 2017-09-20 |  | 2027-02-28 |  |  | 930505 | 4238967 | 5169472 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27937 | W/500137640/SDS | KwaZulu-Natal | ENKONENI P | 500137640 | Umzumbe | Tender | Active - Not Contracted | 2015-11-20 |  | 2023-09-01 |  |  | 1868253 | 8510930 | 10379183 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27938 | DB/500105894/UA | KwaZulu-Natal | BAQULUSINI COMBINED SCHOOL | 500105894 | eDumbe | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-12-11 | 2025-12-01 | 2020-05-05 | 2025-12-01 | 5210210 | 23735403 | 28945613 | Education Infrastructure Grant | Upgrading and Additions
|  | 27939 | W/500256484/SDS | KwaZulu-Natal | ROSETTENVILLE PRIMARY SCHOOL | 500256484 | Umzumbe | Construction 76% - 99% | Active - Contracted | 2015-11-20 |  | 2023-06-30 |  |  | 1174998 | 5352771 | 6527769 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27949 | W/500264624/SDS | KwaZulu-Natal | SIGWEJE SECONDARY SCHOOL | 500264624 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-30 | 2023-06-01 | 2022-06-17 | 2023-06-30 | 2024-03-30 | 1295761 | 5902912 | 7198673 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27955 | W/500136678/WS | KwaZulu-Natal | ENGUDUMENI INTERMEDIATE SCHOOL | 500136678 | Endumeni | Tender | Active - Not Contracted | 2016-03-01 |  | 2026-05-01 |  |  | 376237 | 1713969 | 2090206 | Education Infrastructure Grant | Upgrading and Additions
|  | 27958 | W/500210086/WS | KwaZulu-Natal | MHLABANGULE PRIMARY | 500210086 | Msinga | Design | Active - Contracted | 2017-06-06 |  | 2023-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27962 | W/500221556/SDS | KwaZulu-Natal | MVUTHULUKA SECONDARY SCHOOL | 500221556 | Umzumbe | Feasibility | Active - Not Contracted | 2016-06-27 |  | 2024-03-22 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27963 | W/500220113/SDS | KwaZulu-Natal | MTUMASELI HIGH SCHOOL | 500220113 | Umzumbe | Feasibility | Active - Not Contracted | 2016-06-20 |  | 2024-03-21 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27966 | W/500191734/WS | KwaZulu-Natal | MAFITLENG PRIMARY SCHOOL | 500191734 | Msinga | Tender | Active - Not Contracted | 2016-12-18 |  | 2026-06-30 |  |  | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27967 | W/500169312/SDS | KwaZulu-Natal | Isonto | 500169312 | Alfred Duma | Design | Active - Not Contracted | 2015-12-18 |  | 2024-12-01 |  |  | 0 | 270000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27968 | W/500131424/SDS | KwaZulu-Natal | Emanzimnyama Primary School | 500131424 | Dannhauser | Design | Active - Not Contracted | 2016-12-18 |  | 2024-12-01 |  |  | 757000 | 6000000 | 6757000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27969 | W/500131831/SDS | KwaZulu-Natal | Embabe Lower Primary School | 500131831 | Mfolozi | Design | Active - Not Contracted | 2016-12-18 |  | 2023-12-01 |  |  | 215100 | 30148567 | 30363667 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27970 | W/500134088/SDS | KwaZulu-Natal | Empembeni Primary School | 500134088 | Abaqulusi | Design | Active - Not Contracted | 2016-12-18 |  | 2023-12-01 |  |  | 557460 | 77462207 | 78019667 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27974 | DB/500295593/WS | KwaZulu-Natal | WESSELSNEK COMBINED SCHOOL | 500295593 | Alfred Duma | Design | Active - Contracted | 2017-06-06 |  | 2024-03-15 |  |  | 2797000 | 3117000 | 5914000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27975 | DB/500207052/SDS | KwaZulu-Natal | MEHLOKUBHEKA PRIMARY SCHOOL | 500207052 | Mtubatuba | Final Completion | Approved | 2016-06-13 | 2022-02-20 | 2022-11-30 | 2023-12-20 | 2024-05-20 | 992995 | 3735553 | 4728548 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27976 | W/500152847/RRR | KwaZulu-Natal | GWEGWEDE PRIMARY SCHOOL | 500152847 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-03-30 | 2023-03-31 | 2018-01-30 | 2025-04-30 | 1533000 | 6983000 | 8516000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27977 | DB/500252118/SDS | KwaZulu-Natal | QALAKANCANE PRIMARY SCHOOL | 500252118 | Mtubatuba | Final Completion | Approved | 2016-06-13 | 2017-08-24 | 2023-04-04 | 2018-08-09 | 2025-01-05 | 1138247 | 4281977 | 5420224 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27978 | DB/500178969/RRR | KwaZulu-Natal | KWABULAWAYO H | 500178969 | Big Five Hlabisa | Design | Active - Not Contracted | 2016-06-06 |  | 2027-04-27 |  |  | 1429306 | 6511281 | 7940587 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27979 | W/500336071/WS | KwaZulu-Natal | MAGWEGWANA SECONDARY SCHOOL | 500336071 | Abaqulusi | Tender | Active - Not Contracted | 2016-12-18 |  | 2026-02-28 |  |  | 90000 | 410000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27982 | DB/500140563/SDS | KwaZulu-Natal | ESIKHAWINI HIGH SCHOOL | 500140563 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-04-19 | 2017-01-31 | 2023-03-27 | 2023-11-20 | 2027-03-30 | 957230 | 4360716 | 5317946 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27983 | W/500169534/WS | KwaZulu-Natal | ITHEMBANI PRIMARY SCHOOL | 500169534 | Umvoti | Tender | Active - Not Contracted | 2016-05-14 |  | 2026-03-30 |  |  | 442000 | 2104000 | 2546000 | Education Infrastructure Grant | Upgrading and Additions
|  | 27985 | W/500246827/RRR | KwaZulu-Natal | PELHAM PRIMARY SCHOOL | 500246827 | uMngeni | Feasibility | Active - Not Contracted | 2016-01-06 |  | 2023-09-01 |  |  | 1260000 | 5740000 | 7000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27989 | W/500140674/SDS | KwaZulu-Natal | ESIKHUTHWANENI PRIMARY SCHOOL | W/500140674/SDS | Nongoma | Tender | Active - Not Contracted | 2017-06-06 |  | 2025-06-30 |  |  | 227249 | 4393751 | 4621000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 27990 | W/500239649/WS | KwaZulu-Natal | NTENDENI PRIMARY SCHOOL | 500239649 | Ndwedwe | Construction 51% - 75% | Active - Contracted | 2016-12-18 |  | 2023-06-30 |  |  | 441208 | 2009945 | 2451153 | Education Infrastructure Grant | Upgrading and Additions
|  | 27992 | W/500101195/WS | KwaZulu-Natal | A M MOOLA SECONDARY SCHOOL | 500101195 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2020-06-01 | 2024-03-30 | 2023-06-30 | 2022-03-30 | 851825 | 3880537 | 4732362 | Education Infrastructure Grant | Upgrading and Additions
|  | 27993 | DB/500142117/SDS | KwaZulu-Natal | ETHAFENI PRIMARY SCHOOL | 500142117 | KwaDukuza | Design | Active - Not Contracted | 2012-11-06 |  | 2027-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 27995 | C/500173641/UA | KwaZulu-Natal | KHANYISANI P | 500173641 | eThekwini | On Hold | Active - Not Contracted | 2015-03-11 |  | 2024-03-30 |  |  | 3638000 | 16578000 | 20216000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28000 | W/500100233/WS | KwaZulu-Natal | ABANTUNGWA SECONDARY SCHOOL | 500100233 | Inkosi Langalibalele | On Hold | Active - Contracted | 2020-02-20 |  | 2026-04-29 |  |  | 520183 | 2974267 | 3494450 | Education Infrastructure Grant | Upgrading and Additions
|  | 28001 | C/500140785/UA | KwaZulu-Natal | ESIMOZOMENI SP | 500140785 | Richmond | On Hold | Active - Not Contracted | 2016-06-06 |  | 2023-10-18 |  |  | 1287000 | 5865000 | 7152000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28003 | W/500441299/WS | KwaZulu-Natal | NGQEKWANE SECONDARY SCHOOL | 500441299 | uMhlathuze | Design | Active - Contracted | 2016-11-14 |  | 2025-03-31 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28004 | W/500247974/WS | KwaZulu-Natal | PHATHIZWE SECONDARY SCHOOL | 500247974 | Msinga | Final Completion | Active - Contracted | 2015-03-06 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-30 | 605000 | 2757000 | 3362000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28007 | c/500174973/ua | KwaZulu-Natal | khula hs | c/500174973/ua | uMhlathuze | On Hold | Active - Not Contracted | 2015-11-19 |  | 2024-03-20 |  |  | 865000 | 3942000 | 4807000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28009 | DB/500239168/ECD | KwaZulu-Natal | Ntambanane JP | C/500239168/ECD | eThekwini | Tender | Active - Contracted | 2011-11-24 |  | 2025-03-30 |  |  | 343965 | 1509541 | 1853506 | Education Infrastructure Grant | Upgrading and Additions
|  | 28010 | C/500175306/UA | KwaZulu-Natal | KHULUMA INTERMEDIATE | 500175306 | Dr Nkosazana Dlamini Zuma | On Hold | Active - Not Contracted | 2015-11-20 |  | 2024-03-22 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28016 | W/500326930/WS | KwaZulu-Natal | MHLAZANE PRIMARY SCHOOL | 500326930 | Endumeni | Practical Completion (100%) | Active - Contracted | 2016-11-08 | 2018-04-27 | 2023-01-31 | 2019-03-29 | 2023-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28017 | DB/500343804/WS | KwaZulu-Natal | MAYE PRIMARY SCHOOL | 500343804 | Okhahlamba | Design | Active - Contracted | 2017-04-01 |  | 2024-10-01 |  |  | 2724000 | 3044000 | 5768000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28019 | W/500279350/WS | KwaZulu-Natal | TABHANE SECONDARY SCHOOL | 500279350 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-12-03 | 2018-04-27 | 2023-06-30 | 2018-09-01 | 2023-05-31 | 859000 | 3911000 | 4770000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28020 | DB/500254819/WS | KwaZulu-Natal | RANTJIESVLAKTE PRIMARY SCHOOL | 500254819 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2016-04-06 |  | 2024-12-01 |  |  | 48649 | 221621 | 270270 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28022 | W/500173308/SDS | KwaZulu-Natal | KHANGELANI PRIMARY SCHOOL | 500173308 | uMlalazi | Tender | Active - Contracted | 2016-12-18 |  | 2025-12-01 |  |  | 1694949 | 7721433 | 9416382 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28024 | W/500111814/WS | KwaZulu-Natal | BOTATE PRIMARY SCHOOL | 500111814 | eThekwini | On Hold | Active - Contracted | 2014-11-02 |  | 2023-07-31 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28029 | DB/500257298/RRR | KwaZulu-Natal | SAHLUMBE H | DB/500257298/RRR | Ndwedwe | Design | Active - Not Contracted | 2016-04-07 |  | 2025-02-01 |  |  | 953162 | 4342182 | 5295344 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28033 | W/500207311/SDS | KwaZulu-Natal | ETHUBALETHU PRIMARY SCHOOL | 500207311 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-01-17 | 2022-03-02 | 2023-05-30 | 2024-08-02 | 2025-09-30 | 457950 | 2086216 | 2544166 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28035 | C/500142117/LSEN | KwaZulu-Natal | ETHAFENI | 500142117 | KwaDukuza | Design | Active - Not Contracted | 2016-06-06 |  | 2026-12-30 |  |  | 4844000 | 23903000 | 28747000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28036 | C/500211418/ECD | KwaZulu-Natal | MJILA P | 500211418 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2015-09-24 | 2016-07-14 | 2023-04-20 | 2023-07-15 | 2023-12-20 | 298000 | 1848000 | 2146000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28037 | DB/500142746/SDS | KwaZulu-Natal | EVERGREEN PRIMARY SCHOOL | 500142746 | eThekwini | Design | Active - Not Contracted | 2017-10-16 |  | 2027-03-30 |  |  | 300000 | 300000 | 600000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28039 | DB/500324675/WS | KwaZulu-Natal | SILETHUKUKHANYA HIGH SCHOOL | 500324675 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 852084 | 3881715 | 4733799 | Education Infrastructure Grant | Upgrading and Additions
|  | 28044 | C/500429274/UA | KwaZulu-Natal | ZAKHELE PRIMARY SCHOOL | 500429274 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2015-10-16 | 2015-10-22 | 2023-10-07 | 2023-03-07 | 2023-10-07 | 3709717 | 11697881 | 15407598 | Education Infrastructure Grant | Upgrading and Additions
|  | 28046 | W/500111259/WS | KwaZulu-Natal | BONGUBUHLE SENIOR PRIMARY SCHOOL | 500111259 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2020-07-01 | 2022-06-30 | 2023-07-31 | 2024-08-30 | 740119 | 3371653 | 4111772 | Education Infrastructure Grant | Upgrading and Additions
|  | 28047 | W/500308099/WS | KwaZulu-Natal | ALBERT SECONDARY SCHOOL | 500308099 | Ray Nkonyeni | On Hold | Active - Contracted | 2016-06-14 |  | 2025-05-30 |  |  | 788367 | 3591450 | 4379817 | Education Infrastructure Grant | Upgrading and Additions
|  | 28048 | DB/500208606/WS | KwaZulu-Natal | MFIHLELWANE PRIMARY SCHOOL | 500208606 | Nqutu | Design | Active - Contracted | 2016-06-13 |  | 2024-05-31 |  |  | 800000 | 3200000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28050 | DB/500100751/SDS | KwaZulu-Natal | ALENCON PRIMARY SCHOOL | 500211529 | eThekwini | Practical Completion (100%) | Approved | 2017-10-01 | 2018-12-11 | 2023-06-10 | 2022-06-10 | 2027-07-10 | 895791 | 4080824 | 4976615 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28053 | DB/500142968/SDS | KwaZulu-Natal | EXHAPHOZINI PRIMARY SCHOOL | 500142968 | uMhlathuze | Design | Active - Not Contracted | 2015-11-20 |  | 2027-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28054 | DB/500131017/SDS | KwaZulu-Natal | EMALAHLENI PRIMARY SCHOOL | 500131017 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-12-11 | 2023-06-09 | 2021-05-05 | 2024-03-04 | 2257901 | 8494008 | 10751909 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28056 | W/500205609/SDS | KwaZulu-Natal | MCATSHANGELWA PRIMARY SCHOOL | 500205609 | Mandeni | Final Completion | Active - Contracted | 2017-11-20 | 2019-04-27 | 2024-03-30 | 2023-06-30 | 2022-03-30 | 20150 | 3019515 | 3039665 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28058 | C/500145299/UA | KwaZulu-Natal | FOREST VIEW PRIMARY SCHOOL | 500145299 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2026-12-31 |  |  | 4924000 | 22432000 | 27356000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28059 | DB/500167462/SDS | KwaZulu-Natal | ISIBANKWA HIGH SCHOOL | 500303400 | Alfred Duma | Final Completion | Approved | 2011-02-03 | 2011-06-19 | 2023-02-12 | 2019-03-15 | 2025-08-06 | 1404473 | 6398153 | 7802626 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28060 | DB/500143005/SDS | KwaZulu-Natal | EZAKHELENI SECONDARY SCHOOL | 500143005 | uMlalazi | Design | Active - Not Contracted | 2016-03-11 |  | 2027-03-30 |  |  | 724500 | 7371500 | 8096000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28061 | C/500178821/UA | KwaZulu-Natal | kwabazothini hs | 500178821 | eThekwini | Design | Active - Not Contracted | 2016-04-13 |  | 2026-03-20 |  |  | 3616000 | 16478000 | 20094000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28062 | W/500101565/SDS | KwaZulu-Natal | AMAHUKU PRIMARY SCHOOL | 500101565 | Alfred Duma | Practical Completion (100%) | Active - Not Contracted | 2016-06-15 |  | 2023-02-21 |  |  | 2137060 | 9735498 | 11872558 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28063 | DB/500270840/SDS | KwaZulu-Natal | Sivukile High School | DB/500270840/RRR | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2019-10-05 | 2020-02-17 | 2025-04-30 | 2021-02-05 | 2025-04-30 | 1953301 | 8898373 | 10851674 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28065 | C/500178044/UA | KwaZulu-Natal | KWADINABAKUBO C | 500178044 | eThekwini | Design | Active - Not Contracted | 2016-04-21 |  | 2026-03-20 |  |  | 3261000 | 14859000 | 18120000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28068 | DB/500425167/ECD | KwaZulu-Natal | ENYANISWENI PRIMARY SCHOOL | C/500425167/ECD | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2016-08-09 |  | 2027-03-21 |  |  | 464000 | 1434712 | 1898712 | Education Infrastructure Grant | Upgrading and Additions
|  | 28069 | W/500111185/SDS | KwaZulu-Natal | BONGINHLANHLA SECONDARY SCHOOL | 500111185 | uPhongolo | Design | Active - Not Contracted | 2016-06-13 |  | 2024-11-30 |  |  | 1495482 | 6812749 | 8308231 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28071 | W/500219225/SDS | KwaZulu-Natal | MTHIYAQHWA SECONDARY SCHOOL | 500219225 | Nkandla | Design | Active - Contracted | 2015-12-18 |  | 2025-03-29 |  |  | 1740584 | 7929328 | 9669912 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28072 | C/500217042/ECD | KwaZulu-Natal | MPOFINI PRIMARY SCHOOL | 500217042 | Ubuhlebezwe | Construction 76% - 99% | Active - Contracted | 2015-05-01 | 2017-07-20 | 2023-04-20 | 2023-07-15 | 2023-12-20 | 449000 | 2045000 | 2494000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28074 | DB/500144152/SDS | KwaZulu-Natal | FAIRVALE SECONARY SCHOOL | DB/500144152/SDS | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-01-16 | 2023-07-16 | 2023-07-16 | 2027-03-16 | 1327490 | 6047453 | 7374943 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28075 | W/500101787/WS | KwaZulu-Natal | AMANCAMAKAZANA PRIMARY SCHOOL | 500101787 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2018-02-01 | 2023-09-01 | 2018-03-30 | 2023-09-30 | 941000 | 4289000 | 5230000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28076 | DB/500000000/SDS | KwaZulu-Natal | EMANGANGENI SECONDARY SCHOOL | 500000000 | uMhlathuze | Final Completion | Active - Contracted | 2016-06-06 | 2021-01-15 | 2024-03-30 | 2024-03-25 | 2024-03-30 | 839000 | 2934000 | 3773000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28077 | C/500241018/ECD | KwaZulu-Natal | NTUTHUNGA PRIMARY SCHOOL | 500241018 | Mfolozi | Tender | Active - Not Contracted | 2016-06-30 |  | 2026-03-31 |  |  | 500000 | 2800000 | 3300000 | Equitable Share | Upgrading and Additions
|  | 28080 | C/500179154/ECD | KwaZulu-Natal | KWADINDA PRIMARY SCHOOL | 500179154 | Msinga | Practical Completion (100%) | Active - Contracted | 2014-11-20 | 2015-10-27 | 2023-10-30 | 2023-03-30 | 2023-10-30 | 714965 | 1810037 | 2525002 | Education Infrastructure Grant | Upgrading and Additions
|  | 28085 | W/500145891/SDS | KwaZulu-Natal | FUNDOKUHLE PRIMARY SCHOOL | 500145891 | The Msunduzi | On Hold | Active - Not Contracted | 2017-01-01 |  | 2023-05-01 |  |  | 600000 | 2000000 | 2600000 | Equitable Share | Maintenance and Repairs
|  | 28087 | DB/500320235/SDS | KwaZulu-Natal | GALA HIGH SCHOOL | 500320235 | Dr Nkosazana Dlamini Zuma | Project Initiation | Proposed | 2016-01-01 |  | 2027-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28088 | W/500111000/WS | KwaZulu-Natal | BONGASPOORT PRIMARY SCHOOL | 500111000 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2020-06-01 | 2024-11-30 | 2024-11-30 | 2025-03-30 | 537484 | 2559449 | 3096933 | Education Infrastructure Grant | Upgrading and Additions
|  | 28089 | DB/500146816/SDS | KwaZulu-Natal | GALENI HIGH SCHOOL | 500146816 | Ray Nkonyeni | Terminated | Active - Contracted | 2014-07-24 | 2020-01-31 | 2023-09-14 | 2023-08-31 | 2027-03-30 | 1342410 | 8004800 | 9347210 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28091 | DB/500242609/ECD | KwaZulu-Natal | OCILWANA PRIMARY SCHOOL | 500242609 | Mthonjaneni | Project Initiation | Active - Contracted | 2016-09-24 |  | 2026-03-31 |  |  | 344000 | 1567000 | 1911000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28092 | DB/500102120/SDS | KwaZulu-Natal | AMANGWE SECONDARY SCHOOL | 500102120 | uMhlathuze | Practical Completion (100%) | Approved | 2017-10-24 | 2019-01-16 | 2023-05-20 | 2021-01-31 | 2027-05-20 | 1315224 | 5991575 | 7306799 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28093 | DB/500271765/WS | KwaZulu-Natal | SIZWE PRIMARY SCHOOL | 500271765 | Newcastle | Design | Active - Contracted | 2016-03-07 |  | 2024-11-01 |  |  | 800000 | 3200000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28094 | W/500241832/SDS | KwaZulu-Natal | NYONEBOMVU HIGH PRIMARY SCHOOL | 500241832 | Nongoma | Design | Active - Not Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 603874 | 2750980 | 3354854 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28095 | W/500210234/SDS | KwaZulu-Natal | MHLAKOTHI HIGH SCHOOL | 500210234 | Msinga | Final Completion | Active - Contracted | 2017-06-06 | 2019-08-27 | 2023-03-13 | 2023-01-31 | 2023-03-31 | 2573000 | 3973000 | 6546000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28096 | W/500102009/WS | KwaZulu-Natal | AMANDUS HILL PRIMARY SCHOOL | 500102009 | Richmond | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2017-05-01 | 2022-05-30 | 2024-03-31 | 2024-03-31 | 1178561 | 5368999 | 6547560 | Education Infrastructure Grant | Upgrading and Additions
|  | 28099 | DB/500207829/SDS | KwaZulu-Natal | GARDENIA PRIMARY SCHOOL | 500207829 | eThekwini | Project Initiation | Proposed | 2013-03-01 |  | 2027-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 28100 | W/500102120/WS | KwaZulu-Natal | AMANGWE SECONDARY SCHOOL | 500102120 | uMhlathuze | Construction 76% - 99% | Active - Contracted | 2016-06-15 | 2017-05-01 | 2023-06-30 | 2024-03-31 | 2024-03-31 | 1001480 | 4562298 | 5563778 | Education Infrastructure Grant | Upgrading and Additions
|  | 28101 | DB/500147482/SDS | KwaZulu-Natal | GCILIMA PRIMARY SCHOOL | 500147482 | Ray Nkonyeni | Practical Completion (100%) | Approved | 2016-06-06 | 2018-01-15 | 2022-07-15 | 2022-06-07 | 2027-06-07 | 517686 | 3233314 | 3751000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28103 | W/500277500/RRR | KwaZulu-Natal | STANGER SECONDARY SCHOOL | 500277500 | KwaDukuza | Design | Active - Not Contracted | 2016-03-07 |  | 2023-06-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28105 | DB/500441040/SDS | KwaZulu-Natal | ANJUMAN ISLAMIC PRIMARY SCHOOL | 500441040 | eThekwini | Practical Completion (100%) | Approved | 2016-10-20 | 2019-02-11 | 2022-10-20 | 2022-08-10 | 2025-09-10 | 254907 | 1161241 | 1416148 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28107 | C/500244126/LSEN | KwaZulu-Natal | OPEN GATE SPECIAL SCHOOL | C/500244126/LSEN | uMngeni | Construction 51% - 75% | Active - Not Contracted | 2016-09-20 | 2018-09-20 | 2023-12-20 | 2026-12-20 | 2026-12-20 | 6766676 | 52051350 | 58818026 | Education Infrastructure Grant | Upgrading and Additions
|  | 28108 | W/500423761/SDS | KwaZulu-Natal | BOMVINI COMBINED SCHOOL | 500423761 | Umzimkhulu | Design | Active - Not Contracted | 2016-06-13 |  | 2025-11-30 |  |  | 48649 | 270000 | 318649 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28109 | W/500102527/ECD | KwaZulu-Natal | AMAQHAWE PRIMARY SCHOOL | 500102527 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-04-20 | 2016-05-02 | 2024-03-30 | 2023-06-30 | 2021-12-31 | 468000 | 2132000 | 2600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28112 | W/500110704/WS | KwaZulu-Natal | BLUEBANK PRIMARY SCHOOL | 500110704 | Alfred Duma | Design | Active - Not Contracted | 2015-11-20 |  | 2023-03-31 |  |  | 72000 | 328000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28113 | DB/500288748/RRR | KwaZulu-Natal | UMQHELE S | DB/500288748/RRR | KwaDukuza | Design | Active - Not Contracted | 2016-06-13 |  | 2024-05-31 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28114 | W/500102638/WS | KwaZulu-Natal | AMATHULI PRIMARY SCHOOL | 500102638 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2017-05-01 | 2022-06-30 | 2024-03-31 | 2024-03-31 | 1283624 | 5847621 | 7131245 | Education Infrastructure Grant | Upgrading and Additions
|  | 28118 | W/500110556/SDS | KwaZulu-Natal | BLESSED LUANDA PRIMARY SCHOOL | 500110556 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-05-31 | 2020-03-31 | 2023-05-31 | 486490 | 2216210 | 2702700 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28120 | W/500103008/WS | KwaZulu-Natal | AMAZIZI SECONDARY SCHOOL | 500103008 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-02-01 | 2023-03-30 | 2022-09-01 | 2024-05-31 | 434000 | 1979000 | 2413000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28121 | W/500110408/WS | KwaZulu-Natal | BLAAUWBOSCH PRIMARY SCHOOL | 500110408 | Newcastle | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-05-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28123 | W/500442742/SDS | KwaZulu-Natal | ANDREW ZONDO PRIMARY SCHOOL | 500442742 | eThekwini | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-06-30 |  |  | 485824 | 2213196 | 2699020 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28124 | W/500147815/SDS | KwaZulu-Natal | GCWALAMOYA PRIMARY SCHOOL | 500147815 | Mandeni | Design | Active - Not Contracted | 2016-06-13 |  | 2024-05-30 |  |  | 600000 | 2000000 | 2600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28128 | W/500110260/SDS | KwaZulu-Natal | BISLEY PARK PRIMARY SCHOOL | 500110260 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-04-01 | 2018-09-01 | 2023-04-01 | 48649 | 221621 | 270270 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28129 | W/500103230/WS | KwaZulu-Natal | ANNIEVILLE SENIOR PRIMARY SCHOOL | 500103230 | Dannhauser | On Hold | Active - Contracted | 2016-06-14 |  | 2023-03-11 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28130 | W/500127169/WS | KwaZulu-Natal | EFUYENI PRIMARY SCHOOL | 500127169 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-07-01 | 2023-06-30 | 2022-06-30 | 2024-06-30 | 930015 | 4236733 | 5166748 | Education Infrastructure Grant | Upgrading and Additions
|  | 28131 | DB/500148666/SDS | KwaZulu-Natal | GIJIMA PRIMARY SCHOOL | 500148666 | eThekwini | Design | Active - Not Contracted | 2015-11-20 |  | 2027-03-30 |  |  | 300000 | 2876000 | 3176000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28134 | DB/500148851/SDS | KwaZulu-Natal | GINGINDLOVU PRIMARY SCHOOL | 500148851/SDS | uMlalazi | Design | Active - Not Contracted | 2016-06-14 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28136 | C/500137566/ECD | KwaZulu-Natal | ENKELABANTWANA PRIMARY SCHOOL | 500137566 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-09-24 | 2022-03-31 | 2024-03-31 | 2024-03-31 | 2024-12-31 | 594000 | 2040000 | 2634000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28138 | W/500113183/SDS | KwaZulu-Natal | BUHLEBENTUTHUKO PRIMARY SCHOOL | 500113183 | Newcastle | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-06-30 |  |  | 180000 | 2486200 | 2666200 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28143 | C/500133718/NS | KwaZulu-Natal | EMOYENI PRIMARY SCHOOL | 500133718 | Mthonjaneni | On Hold | Active - Not Contracted | 2015-10-24 |  | 2024-03-20 |  |  | 4680000 | 21320 | 4701320 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28145 | DB/500308839/ECD | KwaZulu-Natal | BHOBHE PRIMARY SCHOOL | 500308839 | Nkandla | Design | Active - Contracted | 2016-06-13 |  | 2024-03-25 |  |  | 247860 | 1129140 | 1377000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28147 | W/500161764/WS | KwaZulu-Natal | INANDA PRIMARY SCHOOL | 500161764 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-06-13 | 2021-02-26 | 2023-03-29 | 2022-11-25 | 2025-02-01 | 1130082 | 5148150 | 6278232 | Education Infrastructure Grant | Upgrading and Additions
|  | 28148 | W/500109520/WS | KwaZulu-Natal | BHIDLA PRIMARY SCHOOL | 500109520 | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-02-01 | 2023-11-30 | 2023-11-30 | 2024-07-30 | 249000 | 1403170 | 1652170 | Education Infrastructure Grant | Upgrading and Additions
|  | 28152 | C/500132904/UA | KwaZulu-Natal | EMJALISWENI PRIMARY SCHOOL | 500132904 | Umzumbe | Construction 76% - 99% | Active - Contracted | 2014-10-24 | 2018-12-02 | 2023-11-20 | 2023-02-20 | 2023-11-20 | 2638221 | 20294006 | 22932227 | Education Infrastructure Grant | Upgrading and Additions
|  | 28153 | W/500444370/WS | KwaZulu-Natal | BHEVU SECONDARY SCHOOL | 5004444370 | Alfred Duma | Design | Active - Not Contracted | 2016-06-13 |  | 2023-09-29 |  |  | 372000 | 2989000 | 3361000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28155 | W/500161838/RRR | KwaZulu-Natal | INANDA SPECIAL SCHOOL FOR LSEN | 500161838 | eThekwini | Design | Active - Contracted | 2016-06-13 |  | 2024-05-31 |  |  | 38601000 | 175847000 | 214448000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28157 | C/500188108/ECD | KwaZulu-Natal | LUCAS MEMORIAL PRIMARY SCHOOL (RETENDER) | 500188108 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2014-08-20 | 2016-04-01 | 2022-08-29 | 2018-03-30 | 2024-08-29 | 842899 | 2252854 | 3095753 | Education Infrastructure Grant | Upgrading and Additions
|  | 28158 | W/500270914/RRR | KwaZulu-Natal | SIZAKANCANE PRIMARY SCHOOL | 500270914 | Newcastle | Practical Completion (100%) | Approved | 2016-06-14 |  | 2023-06-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28159 | W/500301143/SDS | KwaZulu-Natal | ZOMBIZWE HIGH SCHOOL | 500301143 | Jozini | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-03-30 |  |  | 4356000 | 19844000 | 24200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28160 | DB/500205387/SDS | KwaZulu-Natal | MBUYISENI SECONDARY SCHOOL | 500205387 | eThekwini | Design | Proposed | 2016-01-12 |  | 2024-03-20 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 28161 | W/500109224/WS | KwaZulu-Natal | BHEKUNDI SENIOR PRIMARY SCHOOL | 500109224 | Inkosi Langalibalele | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-03-11 |  |  | 7200000 | 32800000 | 40000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28163 | C/500189255/ECD | KwaZulu-Natal | LUVISI PRIMARY SCHOOL(RETENDER) | 500189255 | Msinga | Practical Completion (100%) | Active - Contracted | 2014-10-09 | 2015-10-26 | 2022-11-30 | 2018-03-30 | 2024-11-30 | 624028 | 1579818 | 2203846 | Education Infrastructure Grant | Upgrading and Additions
|  | 28166 | W/500301143/RRR | KwaZulu-Natal | Zombizwe H | 500301143 | Jozini | Design | Active - Not Contracted | 2016-06-14 |  | 2024-05-31 |  |  | 1250000 | 5000000 | 6250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28167 | DB/500116439/WS | KwaZulu-Natal | CHIEVELEY ISLAMIC SA PRIMARY SCHOOL | 500116439 | Inkosi Langalibalele | Design | Active - Not Contracted | 2016-02-02 |  | 2025-03-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28168 | W/500104821/UA | KwaZulu-Natal | BALCOMB`S HILL P | 500104821 | Maphumulo | Design | Approved | 2016-06-15 |  | 2024-03-30 |  |  | 1347000 | 6141000 | 7488000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28169 | W/500112776/WS | KwaZulu-Natal | BRUYNSHILL PRIMARY SCHOOL | 500112776 | uMshwathi | Practical Completion (100%) | Approved | 2016-12-13 | 2019-05-31 | 2022-11-30 | 2023-10-30 | 2024-10-30 | 2198000 | 3478000 | 5676000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28170 | DB/500319902/SDS | KwaZulu-Natal | AQUADENE SECONDARY SCHOOL | 500319902 | uMhlathuze | Design | Active - Not Contracted | 2015-11-20 |  | 2024-10-17 |  |  | 570303 | 2598045 | 3168348 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28171 | W/500327635/RRR | KwaZulu-Natal | ZOMBODE P | 500327635 | Ulundi | Feasibility | Active - Not Contracted | 2016-06-14 |  | 2024-05-31 |  |  | 2500000 | 10000000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28173 | W/500104821/WS | KwaZulu-Natal | BALCOMB`S HILL PRIMARY SCHOOL | 500104821 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2017-05-01 | 2023-04-21 | 2024-03-31 | 2024-03-31 | 1125040 | 5125183 | 6250223 | Education Infrastructure Grant | Upgrading and Additions
|  | 28176 | DB/500400599/WS | KwaZulu-Natal | LOZI PRIMARY SCHOOL | 500400599 | uMngeni | Construction 1% - 25% | Active - Not Contracted | 2016-06-14 | 2017-01-01 | 2023-08-30 | 2024-12-01 | 2027-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28177 | W/500301402/WS | KwaZulu-Natal | ZUNGWINI PRIMARY SCHOOL | 500301402 | eDumbe | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-03-30 |  |  | 159000 | 759000 | 918000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28178 | DB/500151552/SDS | KwaZulu-Natal | GRANTHAM PARK PRIMARY SCHOOL | 500151552 | uMhlathuze | Design | Active - Not Contracted | 2017-01-01 |  | 2024-03-30 |  |  | 300000 | 2654000 | 2954000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28179 | W/500210345/SDS | KwaZulu-Natal | MHLANGAMKHULU PRIMARY SCHOOL | 50021035 | Umzumbe | Construction 76% - 99% | Active - Not Contracted | 2017-11-20 |  | 2024-03-30 |  |  | 1921000 | 3321000 | 5242000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28180 | W/500115588/WS | KwaZulu-Natal | CENGESI PRIMARY SCHOOL | 500115588 | Alfred Duma | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-04-30 |  |  | 711000 | 3238000 | 3949000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28181 | DB/SAFE/500105080/WS | KwaZulu-Natal | BAMBE PRIMARY SCHOOL | 500105080 | Inkosi Langalibalele | Practical Completion (100%) | Active - Not Contracted | 2016-06-14 | 2024-03-11 | 2024-03-11 | 2024-06-11 | 2025-05-11 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28182 | C/500429792/UA | KwaZulu-Natal | EBUNGUNI | C/500429792/UA | The Msunduzi | On Hold | Active - Not Contracted | 2015-10-24 |  | 2023-04-20 |  |  | 1287000 | 5865000 | 7152000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28183 | W/500172790/WS | KwaZulu-Natal | KHABAZELA SECONDARY SCHOOL | 500109076 | eThekwini | Tender | Active - Contracted | 2016-06-13 |  | 2025-11-30 |  |  | 1147929 | 5229452 | 6377381 | Education Infrastructure Grant | Upgrading and Additions
|  | 28184 | W/500165057/SDS | KwaZulu-Natal | INKULU PRIMARY SCHOOL | 500165057 | Ray Nkonyeni | Tender | Active - Not Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 1750767 | 7975718 | 9726485 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28185 | W/500301550/RRR | KwaZulu-Natal | ZUZULWAZI SECONDARY SCHOOL | 500301550 | The Msunduzi | Project Initiation | Proposed | 2017-02-20 |  | 2024-05-31 |  |  | 1876000 | 2196000 | 4072000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28186 | W/500108928/SDS | KwaZulu-Natal | BHEKITHEMBA PRIMARY SCHOOL | 500108928 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 48649 | 3416138 | 3464787 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28187 | W/500162541/WS | KwaZulu-Natal | INDLOZANA SECONDARY SCHOOL | 500162541 | Msinga | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 591000 | 2000000 | 2591000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28188 | W/500268657/SDS | KwaZulu-Natal | SITHEKU HIGH SCHOOL | 500268657 | Mthonjaneni | Construction 76% - 99% | Active - Contracted | 2015-03-12 |  | 2023-06-30 |  |  | 1669305 | 7604614 | 9273919 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28189 | DB/500314944/SDS | KwaZulu-Natal | VELABUSHA PRIMARY SCHOOL | 500314944 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2020-03-06 | 2020-10-10 | 2023-06-08 | 2023-06-15 | 2027-07-14 | 1217151 | 5544799 | 6761950 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28190 | DB/500401820/SDS | KwaZulu-Natal | GWEJOBOMVU HIGH SCHOOL | 500401820 | eThekwini | Design | Active - Contracted | 2016-09-20 |  | 2024-03-30 |  |  | 300000 | 2143000 | 2443000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28192 | DB/500251489/SDS | KwaZulu-Natal | HEUWELAND PRIMARY SCHOOL | 500251489 | uMhlathuze | Design | Active - Not Contracted | 2015-04-07 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28195 | DB/500156214/SDS | KwaZulu-Natal | HLAMVANA HIGH SCHOOL | 500156214 | uMhlathuze | Design | Proposed | 2014-02-18 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28199 | C/500309949/UA | KwaZulu-Natal | MANHLENGA JUNIOR SECONDARY SCHOOL | 500309949 | Mtubatuba | Final Completion | Active - Contracted | 2013-11-23 | 2018-11-28 | 2023-08-29 | 2023-03-30 | 2023-08-29 | 349746 | 2057327 | 2407073 | Education Infrastructure Grant | Upgrading and Additions
|  | 28200 | I/500202390/WS | KwaZulu-Natal | MATSHITSHOLO HIGH SCHOOL | 500202390 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-11-13 | 2016-12-18 | 2023-12-09 | 2018-03-20 | 2023-12-09 | 323548 | 1797466 | 2121014 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28202 | C/500205831/UA | KwaZulu-Natal | MCONJWANA SECONDARY SCHOOL | 500205831 | The Msunduzi | Design | Active - Not Contracted | 2015-10-23 |  | 2026-04-30 |  |  | 1888000 | 8602000 | 10490000 | Equitable Share | Upgrading and Additions
|  | 28203 | DB/500206164/WS | KwaZulu-Natal | mdlangaswa hs | 500206164 | Umzumbe | Construction 26% - 50% | Active - Not Contracted | 2015-09-07 | 2018-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 595920 | 2714745 | 3310665 | Education Infrastructure Grant | Upgrading and Additions
|  | 28206 | C/500209013/UA | KwaZulu-Natal | MGAI P | 500209013 | Umzumbe | Construction 51% - 75% | Active - Contracted | 2015-09-14 | 2020-01-01 | 2023-04-01 | 2020-01-02 | 2023-04-01 | 5148000 | 23452000 | 28600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28207 | W/500208384/RRR | KwaZulu-Natal | MFANEFILE PRIMARY SCHOOL | 500208384 | Mthonjaneni | Feasibility | Active - Not Contracted | 2015-02-03 |  | 2024-01-20 |  |  | 1582000 | 2862000 | 4444000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28208 | C/500205683/ECD | KwaZulu-Natal | MCELENI PRIMARY SCHOOL (RETENDER) | 500205683 | Umzumbe | Final Completion | Active - Contracted | 2019-12-09 | 2020-04-04 | 2023-12-30 | 2023-11-30 | 2023-12-30 | 869087 | 2172717 | 3041804 | Education Infrastructure Grant | Upgrading and Additions
|  | 28209 | W/500157324/SDS | KwaZulu-Natal | HLOMISA PRIMARY SCHOOL | 500157324 | Nqutu | Final Completion | Active - Contracted | 2016-10-23 | 2022-03-30 | 2023-03-27 | 2023-03-30 | 2024-03-30 | 550257 | 2506729 | 3056986 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28210 | W/500159248/SDS | KwaZulu-Natal | HYMAN PRIMARY SCHOOL | 500159248 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-03-15 | 2018-08-30 | 2022-04-17 | 2022-04-17 | 2025-04-17 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28211 | DB/500159507/SDS | KwaZulu-Natal | IFAFA PRIMARY SCHOOL | 500159507 | Umdoni | Design | Active - Not Contracted | 2017-01-17 | 2019-03-01 | 2024-03-30 | 2024-03-30 | 2025-03-30 | 394086 | 1795279 | 2189365 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28212 | DB/500159544/SDS | KwaZulu-Natal | IGAGASI SECONDARY SCHOOL | 500159544 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-04-03 | 2023-10-03 | 2023-03-05 | 2023-03-05 | 2013598 | 9173060 | 11186658 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28213 | DB/500160173/SDS | KwaZulu-Natal | ILEMBE PRIMARY SCHOOL | 500160173 | uMhlathuze | Design | Proposed | 2016-07-14 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28214 | C/500338180/UA | KwaZulu-Natal | manqoba s | 500338180 | Msinga | On Hold | Active - Contracted | 2015-11-20 | 2017-07-20 | 2024-03-29 | 2018-07-27 | 2024-06-30 | 157000 | 719000 | 876000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28215 | W/500211492/SDS | KwaZulu-Natal | MJOJI PRIMARY SCHOOL | 500211492 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-02-06 | 2019-08-27 | 2023-02-13 | 2022-03-19 | 2023-03-19 | 144396 | 657806 | 802202 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28216 | W/500103674/SDS | KwaZulu-Natal | ASANDE HIGH SCHOOL | 500103674 | Umzumbe | Design | Active - Not Contracted | 2014-09-09 |  | 2024-10-27 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28217 | W/500180042/WS | KwaZulu-Natal | KWAKHWELA PRIMARY SCHOOL | 500180042 | eThekwini | Final Completion | Active - Contracted | 2015-11-20 | 2017-02-01 | 2023-03-11 | 2022-03-11 | 2024-03-11 | 418575 | 1906841 | 2325416 | Education Infrastructure Grant | Upgrading and Additions
|  | 28218 | W/500156177/WS | KwaZulu-Natal | HLAMBANYATHI PRIMARY SCHOOL | 500156177 | Jozini | Tender | Active - Contracted | 2016-02-09 |  | 2026-04-29 |  |  | 0 | 2795000 | 2795000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28219 | C/500247641/LSEN | KwaZulu-Natal | PHANGINDAWO PRIMARY SCHOOL | 500247641 | uMngeni | Practical Completion (100%) | Active - Contracted | 2015-10-23 | 2015-11-05 | 2023-11-01 | 2019-09-27 | 2023-11-01 | 4184100 | 19060900 | 23245000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28220 | C/500284113/ECD | KwaZulu-Natal | VUSINDABA P | 500294113 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-09-24 | 2022-03-31 | 2024-03-20 | 2023-07-31 | 2024-12-20 | 486000 | 2886000 | 3372000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28221 | W/500156140/WS | KwaZulu-Natal | HLALELE PRIMARY SCHOOL | 500156140 | Msinga | Tender | Active - Not Contracted | 2016-04-28 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-04-30 | 775717 | 3533822 | 4309539 | Education Infrastructure Grant | Upgrading and Additions
|  | 28223 | W/500293632/SDS | KwaZulu-Natal | VULINGQONDO PRIMARY SCHOOL | 500293632 | uMlalazi | Design | Active - Not Contracted | 2016-01-19 |  | 2024-03-30 |  |  | 882900 | 4022100 | 4905000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28225 | W/500235172/WS | KwaZulu-Natal | NOMYACA SECONDARY SCHOOL | 500235172 | uMlalazi | Tender | Active - Contracted | 2016-12-18 |  | 2025-03-31 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 28226 | W/500204129/WS | KwaZulu-Natal | MBHEKWA SECONDAY SCHOOL | 500204129 | uPhongolo | On Hold | Active - Not Contracted | 2016-04-01 |  | 2023-03-29 |  |  | 101000 | 458000 | 559000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28227 | DB/500160321/SDS | KwaZulu-Natal | ILLOVO PRIMARY SCHOOL | 500160321 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-10-26 | 2019-10-31 | 2023-02-20 | 2023-12-01 | 2025-03-30 | 1125148 | 28570789 | 29695937 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28229 | W/500155918/WS | KwaZulu-Natal | HLABENI PRIMARY SCHOOL | 500155918 | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-03-15 | 2018-04-27 | 2023-03-29 | 2019-03-29 | 2025-02-01 | 242000 | 1103000 | 1345000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28232 | DB/500160802/SDS | KwaZulu-Natal | IMFIHLO PRIMARY SCHOOL | 500160802 | uMlalazi | Design | Proposed | 2016-01-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28233 | W/500303955/UA | KwaZulu-Natal | HLABANE PRIMARY SCHOOL | 500303955 | Okhahlamba | Design | Active - Not Contracted | 2015-03-18 |  | 2024-04-28 |  |  | 1260000 | 5740000 | 7000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28236 | C/500449217/NS | KwaZulu-Natal | SEBENZILE PS | 500449217 | Newcastle | Project Initiation | Proposed | 2015-11-20 |  | 2023-04-04 |  |  | 2556000 | 11648000 | 14204000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28237 | DB/500160987/SDS | KwaZulu-Natal | IMIZIKAYIFANI PRIMARY SCHOOL | 500160987 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-12-11 | 2023-06-10 | 2023-06-10 | 2023-03-30 | 1754016 | 7990519 | 9744535 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28238 | C/500445073/NS | KwaZulu-Natal | NCUNJANA PRIMARY SCHOOL | 500445073 | Alfred Duma | Design | Active - Not Contracted | 2014-05-01 |  | 2026-03-20 |  |  | 3756000 | 17116000 | 20872000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28239 | DB/500449254/WS | KwaZulu-Natal | SHEPSTONE LAKE PRIMARY SCHOOL | 500449254 | Newcastle | Design | Active - Contracted | 2015-11-20 |  | 2024-03-20 |  |  | 2556000 | 11648000 | 14204000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28242 | DOE01/16/17 | Free State | MORENA TSOHISI MOLOI | DOE01/16/17 | Maluti a Phofung | Design | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 5000000 | 45000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28245 | W/500162652/WS | KwaZulu-Natal | INDONDOKAZULU PRIMARY SCHOOL | 500162652 | Abaqulusi | Tender | Active - Contracted | 2016-06-14 |  | 2026-05-31 |  |  | 1018400 | 4639000 | 5657400 | Education Infrastructure Grant | Upgrading and Additions
|  | 28246 | C/500274022/UA | KwaZulu-Natal | Sosuwana P | C/500274022/UA | Umzumbe | On Hold | Active - Not Contracted | 2015-11-20 |  | 2025-03-20 |  |  | 691000 | 3150000 | 3841000 | Equitable Share | Upgrading and Additions
|  | 28253 | W/500105154/SDS | KwaZulu-Natal | BAMBISANDLA PRIMARY SCHOOL | 500105154 | eThekwini | Final Completion | Approved | 2016-06-15 |  | 2023-03-30 |  |  | 1629713 | 7424248 | 9053961 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28254 | DB/500118918WS | KwaZulu-Natal | CURRAGH PRIMARY SCHOOL | 500118918 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-06-01 | 2024-03-30 | 2024-06-30 | 2025-05-03 | 0 | 300000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28258 | DB/500276501/ECD | KwaZulu-Natal | ST ODILO PRIMARY SCHOOL (RETENDER) | 500276501 | Umzumbe | Design | Active - Contracted | 2022-04-01 |  | 2027-03-30 |  |  | 200000 | 983898 | 1183898 | Education Infrastructure Grant | Upgrading and Additions
|  | 28259 | W/500186961/SDS | KwaZulu-Natal | LINGANI PRIMARY SCHOOL | W/500186961/SDS | Newcastle | Tender | Active - Not Contracted | 2016-11-20 |  | 2025-05-31 |  |  | 604793 | 4749816 | 5354609 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28262 | W/500108484/WS | KwaZulu-Natal | BHEKATHINA SECONDARY SCHOOL | 500108484 | Inkosi Langalibalele | Tender | Active - Contracted | 2016-06-14 |  | 2026-05-30 |  |  | 523000 | 3000000 | 3523000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28263 | W/500105487/WS | KwaZulu-Natal | BANGUMUZI PRIMARY SCHOOL | 500105487 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2018-04-27 | 2024-05-31 | 2022-04-01 | 2024-05-31 | 565000 | 2576000 | 3141000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28264 | DB/500283790/SDS | KwaZulu-Natal | THUTHUKANI SPECIAL SCHOOL | 500283790 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2020-01-05 | 2020-02-17 | 2022-07-14 | 2022-08-25 | 2025-09-05 | 1727020 | 7867534 | 9594554 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28266 | C/500126096/ECD | KwaZulu-Natal | EBATHENI PRIMARY SCHOOL | 500126096 | Okhahlamba | Practical Completion (100%) | Active - Not Contracted | 2012-11-14 | 2013-06-25 | 2023-03-30 | 2018-03-30 | 2023-03-30 | 333000 | 1522000 | 1855000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28267 | W/500108336/WS | KwaZulu-Natal | BHEKAMATSHE PRIMARY SCHOOL | 500108336 | The Msunduzi | Construction 76% - 99% | Active - Contracted | 2016-06-14 | 2018-07-01 | 2023-07-28 | 2024-07-28 | 2025-07-28 | 631557 | 2877091 | 3508648 | Education Infrastructure Grant | Upgrading and Additions
|  | 28268 | W/500196655/SDS | KwaZulu-Natal | IMPUMELELO YETHU PRIMARY SCHOOL | 500196655 | Umdoni | Design | Proposed | 2017-06-06 |  | 2024-06-13 |  |  | 1356480 | 6179520 | 7536000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28269 | W/500162763/WS | KwaZulu-Natal | INDUDUZO PRIMARY SCHOOL | 500162763 | Abaqulusi | Construction 76% - 99% | Active - Contracted | 2016-06-14 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-04-30 | 474146 | 2159997 | 2634143 | Education Infrastructure Grant | Upgrading and Additions
|  | 28270 | DB/500305620/SDS | KwaZulu-Natal | FUNDINDUKU SECONDARY SCHOOL | 500305620 | eThekwini | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-03-01 | 2023-03-01 | 2024-03-30 | 2027-05-30 | 1129522 | 5145599 | 6275121 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28271 | DB/500110852/SDS | KwaZulu-Natal | BANAMUVA PRIMARY SCHOOL | 500110852 | uMhlathuze | Design | Active - Not Contracted | 2016-02-20 |  | 2025-02-26 |  |  | 1680867 | 7657284 | 9338151 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28272 | W/500108225/WS | KwaZulu-Natal | BHEKAMAKHOSI PRIMARY SCHOOL | 5001082225 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-06-14 | 2021-07-20 | 2023-03-27 | 2022-05-20 | 2024-05-05 | 917424 | 4179378 | 5096802 | Education Infrastructure Grant | Upgrading and Additions
|  | 28276 | W/500290302/WS | KwaZulu-Natal | BUSEKHAYA SECONDARY SCHOOL | 500290302 | Abaqulusi | Tender | Active - Contracted | 2016-06-14 |  | 2026-03-30 |  |  | 0 | 500000 | 500000 | Equitable Share | Upgrading and Additions
|  | 28278 | W/500320494/UA | KwaZulu-Natal | BANGUNI SENIOR SECONDARY | 500320494 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2016-08-05 | 2024-05-31 | 2022-03-30 | 2024-05-31 | 3394000 | 15461000 | 18855000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28279 | DB/500428349/WS | KwaZulu-Natal | STRAALHOEK PRIMARY SCHOOL | 500428349 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2016-09-26 |  | 2025-03-21 |  |  | 376000 | 1713000 | 2089000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28280 | DB/500104377/SDS | KwaZulu-Natal | AUSTERVILLE PRIMARY SCHOOL | 500104377 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2017-06-03 | 2018-12-11 | 2022-06-10 | 2022-12-10 | 2027-06-10 | 1030190 | 4693087 | 5723277 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28281 | C/500445887/NS | KwaZulu-Natal | GOODHOME SECONDARY SCHOOL | 500445887 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-09-14 | 2023-10-01 | 2020-10-01 | 2024-12-31 | 5187000 | 23632000 | 28819000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28282 | W/500162911/WS | KwaZulu-Natal | INDUMA JUNIOR SECONDARY SCHOOL | 500162911 | Umzumbe | Tender | Active - Contracted | 2016-06-14 |  | 2023-05-31 |  |  | 1088051 | 4956676 | 6044727 | Education Infrastructure Grant | Upgrading and Additions
|  | 28284 | W/500320494/WS | KwaZulu-Natal | BANGUNI SENIOR SECONDARY SCHOOL | 500320494 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2017-02-23 | 2024-05-31 | 2022-03-01 | 2024-05-31 | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28286 | W/500317904/SDS | KwaZulu-Natal | BHEKABELUNGU JUNIOR SECONDARY SCHOOL | 500317904 | uMlalazi | Design | Active - Not Contracted | 2016-06-14 |  | 2024-03-24 |  |  | 6240 | 28427 | 34667 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28287 | W/500225811/SDS | KwaZulu-Natal | INDOSI PRIMARY SCHOOL | 500225811 | Nkandla | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 218339 | 1359661 | 1578000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28288 | W/500311059/WS | KwaZulu-Natal | JABULISANI PRIMARY SCHOOL | 500311059 | Abaqulusi | Tender | Active - Contracted | 2017-11-20 |  | 2026-06-30 |  |  | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28289 | C/iLe,New12/NS | KwaZulu-Natal | New ULOVU Area SECONDARY SCHOOL | C/500000000/NS | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-01-03 | 2016-05-20 | 2023-04-27 | 2018-06-20 | 2024-12-31 | 6684000 | 37723596 | 44407596 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28290 | W/500306027/WS | KwaZulu-Natal | BANIYENA PRIMARY SCHOOL | 500306027 | Mkhambathini | Design | Active - Not Contracted | 2016-06-15 |  | 2023-05-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28291 | W/500163022/SDS | KwaZulu-Natal | INDUNDUMA PRIMARY SCHOOL | 500163022 | Umdoni | Design | Active - Not Contracted | 2016-06-14 |  | 2024-03-31 |  |  | 600000 | 1600000 | 2200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28292 | W/500113886/WS | KwaZulu-Natal | BUTHANANI PRIMARY SCHOOL | 500113886 | uMlalazi | Tender | Active - Contracted | 2016-06-14 |  | 2025-03-30 |  |  | 0 | 2680000 | 2680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28293 | W/500153661/WS | KwaZulu-Natal | HARBURG INTERMEDIATE SCHOOL | 500153661 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-01-13 | 2016-04-29 | 2023-06-30 | 2021-06-30 | 2025-06-30 | 1366032 | 6223036 | 7589068 | Education Infrastructure Grant | Upgrading and Additions
|  | 28294 | W/500446701/WS | KwaZulu-Natal | BHEKABANTU SECONDARY SCHOOL | 500446701 | Msinga | Practical Completion (100%) | Approved | 2016-06-14 | 2017-07-06 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 90000 | 624474 | 714474 | Education Infrastructure Grant | Upgrading and Additions
|  | 28295 | W/500130499/WS | KwaZulu-Natal | EMAFUSINI SENIOR PRIMARY SCHOOL | 500130499 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-02-05 | 2024-05-31 | 2023-02-04 | 2024-05-31 | 564000 | 2569000 | 3133000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28296 | W/500153476/WS | KwaZulu-Natal | HAMROOK PRIMARY SCHOOL | 500153476 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-02-25 | 2018-03-05 | 2023-03-29 | 2019-03-29 | 2025-09-30 | 303677 | 1383415 | 1687092 | Education Infrastructure Grant | Upgrading and Additions
|  | 28298 | W/500105635/WS | KwaZulu-Natal | BANTUBANINGI SECONDARY SCHOOL | 500105635 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2017-05-01 | 2023-06-30 | 2024-03-31 | 2024-03-31 | 793381 | 3614291 | 4407672 | Education Infrastructure Grant | Upgrading and Additions
|  | 28301 | W/500229067/WS | KwaZulu-Natal | INGUTSHANA PRIMARY SCHOOL | 500229067 | uMhlathuze | Tender | Active - Contracted | 2016-06-21 |  | 2026-06-29 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28303 | W/500325341/WS | KwaZulu-Natal | BUYANI PRIMARY SCHOOL | 500325341 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-06-01 |  | 2026-06-26 |  |  | 517488 | 2357444 | 2874932 | Education Infrastructure Grant | Upgrading and Additions
|  | 28306 | W/500153365/WS | KwaZulu-Natal | HAMBANGENDLELA SECONDARY SCHOOL | 500153365 | Abaqulusi | Tender | Active - Contracted | 2016-02-16 |  | 2026-03-29 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28312 | W/500153143/WS | KwaZulu-Natal | HALADU PRIMARY SCHOOL | 500153143 | Msinga | Tender | Active - Contracted | 2016-02-09 |  | 2025-06-30 |  |  | 1000000 | 2276000 | 3276000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28320 | W/500171532/WS | KwaZulu-Natal | JOJOSINI PRIMARY SCHOOL | 500171532 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-01-20 | 2019-03-29 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 616381 | 2807958 | 3424339 | Education Infrastructure Grant | Upgrading and Additions
|  | 28321 | W/500301920/WS | KwaZulu-Natal | ZWELINJANI SECONDARY SCHOOL | 500301920 | Msinga | On Hold | Active - Not Contracted | 2016-06-15 | 2021-02-26 | 2024-03-30 | 2025-06-30 | 2025-03-01 | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28324 | W/500158064/WS | KwaZulu-Natal | HOFFENTHAL PRIMARY SCHOOL | 500158064 | Okhahlamba | Design | Active - Not Contracted | 2017-03-03 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28325 | DB/500164391/SDS | KwaZulu-Natal | INJABULOYESIZWE PRIMARY SCHOOL | 500164391 | uMhlathuze | Design | Proposed | 2016-03-16 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28326 | W/500130758/WS | KwaZulu-Natal | EMAKHABELENI PRIMARY SCHOOL | 500130758 | Umvoti | Final Completion | Active - Contracted | 2015-11-20 | 2020-06-30 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 503916 | 2295615 | 2799531 | Education Infrastructure Grant | Upgrading and Additions
|  | 28328 | W/500114034/WS | KwaZulu-Natal | BUZUBONA INTERMEDIATE SCHOOL | 500114034 | Nqutu | Design | Active - Not Contracted | 2016-06-14 |  | 2023-03-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28334 | DB/500296518/WS | KwaZulu-Natal | WINDY HILL PRIMARY SCHOOL | 500296518 | uMshwathi | Design | Active - Not Contracted | 2016-06-15 |  | 2025-04-29 |  |  | 0 | 5000 | 5000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28335 | W/500446701/NS | KwaZulu-Natal | BHEKABANTU SECONDARY SCHOOL | 500446701 | Msinga | Design | Active - Not Contracted | 2016-06-14 |  | 2025-03-29 |  |  | 8100000 | 36900000 | 45000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28339 | W/500442261/WS | KwaZulu-Natal | BUZULWAZI PRIMARY SCHOOL | 500442261 | The Msunduzi | Design | Active - Not Contracted | 2016-04-01 |  | 2024-05-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28340 | W/500339253/WS | KwaZulu-Natal | ZWELISHA PRIMARY SCHOOL | 500339253 | Abaqulusi | Tender | Active - Not Contracted | 2016-06-17 |  | 2025-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28341 | W/500425463/SDS | KwaZulu-Natal | GLOUCESTER JUNIOR SECONDARY SCHOOL | 500425463 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2016-01-19 |  | 2024-03-30 |  |  | 0 | 270000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28343 | W/500150405/WS | KwaZulu-Natal | GOBUME SECONDARY SCHOOL | 500150405 | Umzumbe | Tender | Active - Contracted | 2016-01-21 |  | 2026-06-30 |  |  | 464066 | 2114078 | 2578144 | Equitable Share | Upgrading and Additions
|  | 28345 | DB/500119954/WS | KwaZulu-Natal | DARGLE PRIMARY SCHOOL | 500119954 | uMngeni | Design | Active - Not Contracted | 2016-03-10 |  | 2024-03-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28347 | W/500108114/WS | KwaZulu-Natal | BHEKABANTU PRIMARY SCHOOL | 500108114 | Umhlabuyalingana | Construction 51% - 75% | Active - Contracted | 2016-06-14 | 2018-06-04 | 2025-03-29 | 2022-03-29 | 2025-03-29 | 811498 | 3696826 | 4508324 | Education Infrastructure Grant | Upgrading and Additions
|  | 28348 | W/500424242/SDS | KwaZulu-Natal | DEEPDALE JUNIOR SECONDARY SCHOOL | 500424242 | The Msunduzi | Design | Active - Not Contracted | 2016-03-24 |  | 2024-06-30 |  |  | 26369 | 120126 | 146495 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28351 | W/500297332/WS | KwaZulu-Natal | WOSIYANE SECONDARY SCHOOL | 500297332 | Ndwedwe | Design | Active - Not Contracted | 2016-06-15 |  | 2027-04-26 |  |  | 200000 | 1500000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28352 | W/500150516/WS | KwaZulu-Natal | GOGOVUMA PRIMARY SCHOOL | 500150516 | KwaDukuza | Tender | Active - Contracted | 2016-01-29 |  | 2026-05-11 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28354 | W/500171606/WS | KwaZulu-Natal | JONASE SCONDARY SCHOOL | 500171606 | KwaDukuza | Tender | Active - Contracted | 2016-04-01 |  | 2026-05-31 |  |  | 874177 | 3982360 | 4856537 | Education Infrastructure Grant | Upgrading and Additions
|  | 28356 | W/500125652/RRR | KwaZulu-Natal | DWALENI SECONDARY SCHOOL | 500125652 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2016-10-26 | 2024-05-31 | 2022-06-30 | 2024-05-31 | 5930000 | 27012000 | 32942000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28357 | W/500151145/WS | KwaZulu-Natal | GORDON MEMORIAL SECONDARY SCHOOL | 500151145 | Msinga | Tender | Active - Contracted | 2016-02-18 |  | 2025-06-30 |  |  | 1000000 | 1956000 | 2956000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28358 | W/500423983/WS | KwaZulu-Natal | CABANE JUNIOR SECONDARY SCHOOL | 50042983 | Umzimkhulu | Design | Active - Not Contracted | 2016-04-01 |  | 2023-03-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28361 | W/500326488/SDS | KwaZulu-Natal | GQOKAMANDLA HIGH SCHOOL | 500326488 | Abaqulusi | Final Completion | Active - Contracted | 2016-01-21 | 2022-03-30 | 2023-05-30 | 2024-04-30 | 2025-08-30 | 1213965 | 5530285 | 6744250 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28362 | DB/500307322/SDS | KwaZulu-Natal | NCOMBO PRIMARY SCHOOL | 500307322 | uMhlathuze | Design | Active - Contracted | 2015-10-24 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28365 | DB/500297591/SDS | KwaZulu-Natal | WYKOM PRIMARY SCHOOL | 500297591 | Abaqulusi | Final Completion | Approved | 2016-06-15 | 2018-04-13 | 2022-04-01 | 2022-12-28 | 2023-05-11 | 1111016 | 4179538 | 5290554 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28366 | W/500164613/SDS | KwaZulu-Natal | INKANYEZI YAMACHI PRIMARY SCHOOL | 500164613 | uMuziwabantu | Design | Proposed | 2017-06-06 |  | 2024-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28370 | I/500298516/WS | KwaZulu-Natal | ZALIZWI PRIMARY SCHOOL | 500298516 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2022-03-31 | 2023-11-30 | 2023-07-31 | 2023-12-20 | 1 | 1 | 2 | Education Infrastructure Grant | Upgrading and Additions
|  | 28371 | C/500282680/UA | KwaZulu-Natal | THOLISU P | DBSA/500282680 - SDS | eThekwini | Design | Active - Not Contracted | 2016-04-20 |  | 2026-03-20 |  |  | 2750000 | 12529000 | 15279000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28372 | W/500425500/WS | KwaZulu-Natal | GQWALU COMBINED SCHOOL | 500425500 | Dr Nkosazana Dlamini Zuma | Tender | Active - Contracted | 2016-01-27 |  | 2026-05-31 |  |  | 758073 | 3453445 | 4211518 | Education Infrastructure Grant | Upgrading and Additions
|  | 28373 | W/500173086/WS | KwaZulu-Natal | KHAMBULA COMBINED SCHOOL | 500173086 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2026-03-25 |  |  | 0 | 1777000 | 1777000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28374 | W/500131498/RRR | KwaZulu-Natal | AMASAKENI PRIMARY SCHOOL | 5000131498 | Umhlabuyalingana | Project Initiation | Active - Not Contracted | 2016-01-21 |  | 2024-11-30 |  |  | 0 | 270000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28375 | W/500308358/WS | KwaZulu-Natal | BHANOYI SECONDARY SCHOOL | 500308358 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2021-02-26 | 2022-11-30 | 2022-02-28 | 2024-04-01 | 250000 | 1500000 | 1750000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28376 | DB/500223887/SDS | KwaZulu-Natal | NCOTSHANE SENIOR PRIMARY SCHOOL | DB/500307322/SDS | uPhongolo | Final Completion | Approved | 2016-09-20 | 2017-01-20 | 2023-04-30 | 2022-12-20 | 2023-08-20 | 676681 | 2545609 | 3222290 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28378 | W/500120731/WS | KwaZulu-Natal | DENDETHU PRIMARY SCHOOL | 500120731 | Mandeni | Practical Completion (100%) | Active - Contracted | 2016-03-30 | 2022-06-30 | 2023-06-30 | 2025-06-30 | 2025-08-30 | 90000 | 1187000 | 1277000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28379 | W/500106042/WS | KwaZulu-Natal | BASHISE PRIMARY SCHOOL | 500106042 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2017-05-01 | 2023-06-30 | 2024-03-31 | 2024-03-31 | 1469164 | 6692858 | 8162022 | Education Infrastructure Grant | Upgrading and Additions
|  | 28380 | W/500320494/SDS | KwaZulu-Natal | BANGUNI SENIOR SECONDARY | 500320494 | KwaDukuza | Design | Active - Not Contracted | 2017-06-06 |  | 2024-06-13 |  |  | 1249000 | 2649000 | 3898000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 28381 | W/500131054/WS | KwaZulu-Natal | EMALANGENI PRIMARY SCHOOL | 500131054 | Umhlabuyalingana | Design | Active - Not Contracted | 2016-04-01 |  | 2023-08-01 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28383 | W/500152514/WS | KwaZulu-Natal | GUGULESIZWE SECONDARY SCHOOL | 500152514 | Umdoni | Construction 76% - 99% | Active - Contracted | 2016-02-17 | 2016-08-24 | 2023-06-30 | 2021-06-30 | 2025-06-30 | 18000 | 1253343 | 1271343 | Education Infrastructure Grant | Upgrading and Additions
|  | 28385 | W/500152699/WS | KwaZulu-Natal | GWADU ZENEX PRIMARY SCHOOL | 500152699 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-21 | 2021-02-26 | 2023-03-29 | 2023-11-30 | 2024-05-01 | 1148038 | 5229949 | 6377987 | Education Infrastructure Grant | Upgrading and Additions
|  | 28386 | W/500311392/WS | KwaZulu-Natal | BHANGANOMO PRIMARY SCHOOL | 500311392 | Nongoma | Construction 1% - 25% | Active - Contracted | 2016-06-14 | 2017-05-01 | 2023-06-30 | 2024-03-31 | 2024-06-30 | 1284891 | 5853394 | 7138285 | Education Infrastructure Grant | Upgrading and Additions
|  | 28387 | DB/500164872/SDS | KwaZulu-Natal | INKONGOZELO PRIMARY SCHOOL | 500164872 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-03-30 | 2018-04-06 | 2023-10-05 | 2023-05-05 | 2025-06-04 | 426147 | 1941338 | 2367485 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28388 | W/500114145/WS | KwaZulu-Natal | CACA PRIMARY SCHOOL | 500114145 | Dannhauser | Design | Active - Not Contracted | 2016-04-01 |  | 2023-07-25 |  |  | 15011 | 68381 | 83392 | Education Infrastructure Grant | Upgrading and Additions
|  | 28389 | W/500131091/WS | KwaZulu-Natal | EMANDLENI PRIMARY SCHOOL | 500131091 | Abaqulusi | Tender | Active - Not Contracted | 2016-11-20 |  | 2026-06-30 |  |  | 1000000 | 1145000 | 2145000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28395 | W/500106153/WS | KwaZulu-Natal | BATHEMBU SECONDARY SCHOOL | 500106153 | Msinga | On Hold | Active - Not Contracted | 2016-06-15 |  | 2024-06-30 |  |  | 250000 | 2000000 | 2250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28402 | W/500106227/WS | KwaZulu-Natal | BATLOKOA SECONDARY SCHOOL | 500106227 | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2016-06-15 | 2019-11-23 | 2022-06-30 | 2022-06-30 | 2024-06-30 | 1043275 | 4752699 | 5795974 | Education Infrastructure Grant | Upgrading and Additions
|  | 28403 | DB/500105672/SDS | KwaZulu-Natal | BANTUVUKANI PRIMARY SCHOOL | 500105672 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-12-01 | 2023-01-31 | 2020-05-05 | 2027-01-31 | 808725 | 4440275 | 5249000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28404 | DB/500128834/SDS | KwaZulu-Natal | EKUPHELENI SECONDARY SCHOOL | 500128834 | Mfolozi | Feasibility | Active - Not Contracted | 2015-11-20 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28408 | W/500120509/WS | KwaZulu-Natal | DEWAAR PRIMARY SCHOOL | 500120509 | Msinga | Design | Active - Not Contracted | 2016-11-20 |  | 2024-06-30 |  |  | 54000 | 246000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28409 | I/500293928/UA | KwaZulu-Natal | VUMOKUHLE PRIMARY SCHOOL | 500293928 | eThekwini | Project Initiation | Active - Contracted | 2016-04-01 |  | 2027-03-30 |  |  | 100000 | 400000 | 500000 | Equitable Share | Upgrading and Additions
|  | 28410 | W/500149591/RRR | KwaZulu-Natal | GLENHILLS COMBINED SCHOOL | 500149591 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2014-07-16 | 2015-08-18 | 2024-05-31 | 2023-05-31 | 2024-05-31 | 1002000 | 4568000 | 5570000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28411 | C/uTh.New12/002/NS | KwaZulu-Natal | New EHAWINI SECONDARY SCHOOL | uTh.New12/NS | Alfred Duma | Design | Active - Not Contracted | 2015-01-01 |  | 2023-04-20 |  |  | 5277000 | 24044000 | 29321000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28412 | C/500155844/ECD | KwaZulu-Natal | HLABA PRIMARY SCHOOL (RETENDER) | 500155844 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2023-06-13 | 2020-10-01 | 2024-12-31 | 1208207 | 3020518 | 4228725 | Education Infrastructure Grant | Upgrading and Additions
|  | 28414 | W/500131202/WS | KwaZulu-Natal | EMANGWENI PRIMARY SCHOOL | 500131202 | Inkosi Langalibalele | Design | Active - Not Contracted | 2015-11-20 |  | 2024-03-25 |  |  | 1000000 | 2452000 | 3452000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28416 | W/500114811/WS | KwaZulu-Natal | CATHULANI PRIMARY SCHOOL | 500114811 | Newcastle | On Hold | Active - Not Contracted | 2016-06-14 |  | 2023-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28417 | DB/500425389/WS | KwaZulu-Natal | GINYIQHINGA SECONDARY SCHOOL | 500425389 | Umzimkhulu | Construction 26% - 50% | Active - Contracted | 2014-04-08 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 114533 | 561729 | 676262 | Education Infrastructure Grant | Upgrading and Additions
|  | 28418 | DB/500224923/SDS | KwaZulu-Natal | NDESHENI HIGH SCHOOL | 500223887 | uMhlathuze | Feasibility | Active - Not Contracted | 2015-11-20 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28419 | W/500121730/WS | KwaZulu-Natal | DIVAL PRIMARY SCHOOL | 500121730 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-04-02 | 2024-09-30 | 2022-09-30 | 2024-09-30 | 636000 | 2895000 | 3531000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28421 | I/500162208/WS | KwaZulu-Natal | INDABIKHULUNYWAYO PRIMARY SCHOOL | 500162208 | Nongoma | Construction 26% - 50% | Active - Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 320400 | 1510600 | 1831000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28423 | W/500173197/WS | KwaZulu-Natal | KHANDANE PRIMARY SCHOOL | 500173197 | Umhlabuyalingana | Tender | Active - Contracted | 2015-01-13 |  | 2025-03-29 |  |  | 896917 | 4085957 | 4982874 | Education Infrastructure Grant | Upgrading and Additions
|  | 28424 | W/500306767/SDS | KwaZulu-Natal | INKOSENHLE PRIMARY SCHOOL | 500306767 | Mtubatuba | Final Completion | Active - Contracted | 2016-06-06 | 2017-06-10 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 477125 | 20924875 | 21402000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28426 | W/500495467/SDS | KwaZulu-Natal | INKOSI JIYANE PRIMARY SCHOOL | 500495467 | Nkandla | Terminated | Active - Contracted | 2016-11-20 | 2018-03-30 | 2024-03-30 | 2023-06-30 | 2022-03-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28428 | W/500297591/WS | KwaZulu-Natal | WYKOM PRIMARY SCHOOL | 500297591 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2021-05-31 | 2024-03-30 | 2023-06-30 | 2027-04-30 | 498026 | 2268787 | 2766813 | Education Infrastructure Grant | Upgrading and Additions
|  | 28429 | I/500339401/ECD | KwaZulu-Natal | LETHUMFUNDO PRIMARY SCHOOL | I/500339401/ECD | Mthonjaneni | Design | Active - Not Contracted | 2015-09-30 |  | 2024-03-30 |  |  | 648000 | 2295200 | 2943200 | Education Infrastructure Grant | Upgrading and Additions
|  | 28430 | DB/500165575/SDS | KwaZulu-Natal | INSELELE PRIMARY SCHOOL | 500165575 | eThekwini | Final Completion | Approved | 2014-06-06 | 2017-05-20 | 2023-06-16 | 2023-02-20 | 2024-04-30 | 1422678 | 6481090 | 7903768 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28431 | W/500173308/RRR | KwaZulu-Natal | KHANGELANI PRIMARY SCHOOL | 500173308 | uMlalazi | Feasibility | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 1716300 | 7818700 | 9535000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28433 | W/500343952/WS | KwaZulu-Natal | BETHULO PRIMARY SCHOOL | 500343952 | Msinga | Tender | Active - Contracted | 2016-06-14 |  | 2026-04-30 |  |  | 478000 | 2274000 | 2752000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28434 | W/500297665/WS | KwaZulu-Natal | XASANA PRIMARY SCHOOL | 500297665 | Ulundi | Tender | Active - Not Contracted | 2016-06-15 |  | 2027-05-30 |  |  | 0 | 500 | 500 | Education Infrastructure Grant | Upgrading and Additions
|  | 28435 | W/500164132/UA | KwaZulu-Natal | INHLASANA PRIMARY SCHOOL | 500164132 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2014-02-19 | 2015-04-14 | 2023-08-16 | 2018-03-30 | 2025-04-26 | 1580000 | 7199000 | 8779000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28436 | C/500159507/LSEN | KwaZulu-Natal | IFAFA JUNIOR PRIMARY SCHOOL | 500159507 | Umdoni | Practical Completion (100%) | Active - Contracted | 2015-06-02 | 2016-06-10 | 2022-12-29 | 2020-10-01 | 2024-12-29 | 2449000 | 11160000 | 13609000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28437 | W/500186480/WS | KwaZulu-Natal | LILANI PRIMARY SCHOOL | 500186480 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2017-03-30 | 2023-03-30 | 2022-03-30 | 2023-03-30 | 522000 | 4591973 | 5113973 | Education Infrastructure Grant | Upgrading and Additions
|  | 28438 | DB/500142265/LSEN | KwaZulu-Natal | ETHEL MTHIYANE SPECIAL | ED/500142265/LSEN | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2015-06-20 | 2018-04-05 | 2024-03-30 | 2025-12-20 | 2027-03-30 | 6357019 | 28959753 | 35316772 | Education Infrastructure Grant | Upgrading and Additions
|  | 28441 | W/500173456/WS | KwaZulu-Natal | KHANYAKHWEZI PRIMARY SCHOOL | 500173456 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2021-03-31 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 1060762 | 4832361 | 5893123 | Education Infrastructure Grant | Upgrading and Additions
|  | 28442 | W/500107781/WS | KwaZulu-Natal | BETHANGWE PRIMARY SCHOOL | 500107778 | Mtubatuba | Tender | Active - Not Contracted | 2016-06-14 |  | 2026-06-01 |  |  | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28443 | W/500297702/SDS | KwaZulu-Natal | XHONYWA PRIMARY SCHOOL | 500297702 | Ray Nkonyeni | Tender | Active - Not Contracted | 2016-06-15 |  | 2027-04-30 |  |  | 1656929 | 7548231 | 9205160 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28444 | W/500164206/WS | KwaZulu-Natal | INHLOKOZI HIGH SCHOOL | 500164206 | KwaDukuza | Construction 26% - 50% | Active - Contracted | 2016-06-14 | 2022-03-30 | 2023-03-29 | 2024-03-30 | 2025-04-30 | 676134 | 3080166 | 3756300 | Education Infrastructure Grant | Upgrading and Additions
|  | 28446 | DB/500228142/SDS | KwaZulu-Natal | NGILOSI JUNIOR PRIMARY SCHOOL | DB/500224923/SDS | eThekwini | Final Completion | Active - Contracted | 2015-10-24 | 2016-07-08 | 2023-04-30 | 2022-12-06 | 2023-10-24 | 1239888 | 4664342 | 5904230 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28449 | W/500173715/WS | KwaZulu-Natal | KHANYISELUZULU SECONDARY SCHOOL | 500173715 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2026-03-29 |  |  | 366198 | 1743801 | 2109999 | Education Infrastructure Grant | Upgrading and Additions
|  | 28451 | W/500107744/WS | KwaZulu-Natal | BETHAMOYA HIGH SCHOOL | 500107744 | Newcastle | On Hold | Active - Not Contracted | 2016-06-14 |  | 2023-06-17 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28452 | DB/500340252/WS | KwaZulu-Natal | THEMBOKUHLE PRIMARY SCHOOL | 500340252 | Alfred Duma | Design | Active - Not Contracted | 2017-04-01 |  | 2024-04-25 |  |  | 2781000 | 3101000 | 5882000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28453 | I/500164650/WS | KwaZulu-Natal | INKANYEZI YESIZWE PRIMARY SCHOOL | 500164650 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2011-06-05 | 2018-05-01 | 2023-03-31 | 2023-05-10 | 2023-07-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28454 | W/500160062/WS | KwaZulu-Natal | IKUSASALETHU SECONDARY SCHOOL | 500160062 | Mtubatuba | Tender | Active - Contracted | 2016-06-06 |  | 2026-10-01 |  |  | 1912500 | 8712500 | 10625000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28455 | DB/500228327/SDS | KwaZulu-Natal | NGOME PRIMARY SCHOOL | 500228142 | Umvoti | Final Completion | Approved | 2015-09-20 | 2017-02-16 | 2025-08-22 | 2019-05-03 | 2025-08-22 | 346000 | 1574000 | 1920000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28458 | I/500201169/LSEN | KwaZulu-Natal | Mason Lincoln | I/500201169/LSEN | eThekwini | Design | Active - Not Contracted | 2015-08-23 |  | 2026-03-31 |  |  | 16200000 | 73800000 | 90000000 | Equitable Share | Upgrading and Additions
|  | 28459 | I/500103082/WS | KwaZulu-Natal | AMOIBE PRIMARY SCHOOL | I/500103082/WS | Msinga | Practical Completion (100%) | Active - Contracted | 2017-06-17 | 2017-12-20 | 2023-01-31 | 2022-03-20 | 2023-03-30 | 234000 | 1064000 | 1298000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28460 | C/500312724/UA | KwaZulu-Natal | IMBALI JS SCHOOL | 500312724/UA | The Msunduzi | On Hold | Active - Not Contracted | 2016-06-06 |  | 2024-10-01 |  |  | 624000 | 2848000 | 3472000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28462 | W/500206127/WS | KwaZulu-Natal | MDLADLA HIGH SCHOOL | 500206127 | Jozini | Construction 76% - 99% | Active - Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 1041056 | 4742587 | 5783643 | Education Infrastructure Grant | Upgrading and Additions
|  | 28463 | W/500173937/WS | KwaZulu-Natal | KHAWULEZA PRIMARY SCHOOL | 500173937 | Abaqulusi | Construction 76% - 99% | Active - Contracted | 2016-08-01 |  | 2023-06-30 |  |  | 487000 | 1500000 | 1987000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28467 | W/500269286/WS | KwaZulu-Natal | SIVULINDLELA INTERMEDIATE SCHOOL | 500269286 | Abaqulusi | Tender | Proposed | 2017-03-01 |  | 2024-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28468 | C/500160802/ECD | KwaZulu-Natal | IMFIHLO PRIMARY SCHOOL | 500160802 | uMlalazi | Design | Active - Not Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 162000 | 1156000 | 1318000 | Equitable Share | Upgrading and Additions
|  | 28469 | W/500341547/WS | KwaZulu-Natal | CEBOLESIZWE INTERMEDIATE SCHOOL | 500341547 | Mpofana | Design | Active - Not Contracted | 2016-04-01 |  | 2023-05-31 |  |  | 0 | 500000 | 500000 | Equitable Share | Upgrading and Additions
|  | 28470 | C/500326227/UA | KwaZulu-Natal | IMPUMELELO SENIOR PRIMARY SCHOOL | 500326227 | Umdoni | Practical Completion (100%) | Approved | 2016-06-06 | 2016-06-10 | 2023-06-13 | 2021-10-01 | 2024-10-05 | 2798000 | 12747000 | 15545000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28471 | W/500323195/WS | KwaZulu-Natal | KHETHUKUTHULA SECONDARY SCHOOL | 500323195 | Abaqulusi | Tender | Active - Contracted | 2017-05-01 |  | 2026-03-29 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28472 | W/500165168/WS | KwaZulu-Natal | INKUNZI PRIMARY SCHOOL | 50016516 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2018-04-02 | 2023-03-31 | 2020-02-01 | 2023-03-31 | 1655100 | 2539900 | 4195000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28473 | W/500107633/WS | KwaZulu-Natal | BERNICA PRIMARY SCHOOL | 500107633 | Abaqulusi | Tender | Active - Not Contracted | 2016-06-13 |  | 2024-06-30 |  |  | 769033 | 3503375 | 4272408 | Education Infrastructure Grant | Upgrading and Additions
|  | 28474 | DB/500423613/WS | KwaZulu-Natal | Antioch JSS | I/500423613/NS | Umzimkhulu | Practical Completion (100%) | Active - Not Contracted | 2016-06-20 |  | 2024-05-30 |  |  | 4200000 | 20000000 | 24200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28475 | W/500196026/SDS | KwaZulu-Natal | MANDENI PRIMARY SCHOOL | 500196026 | Mandeni | Tender | Active - Not Contracted | 2017-04-01 |  | 2025-10-23 |  |  | 1215526 | 5537395 | 6752921 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28476 | W/500264143/SDS | KwaZulu-Natal | SIDUNGE PRIMARY SCHOOL | 500264143 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2021-02-26 | 2023-05-31 | 2023-06-30 | 2023-05-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28478 | DB/500168498/SDS | KwaZulu-Natal | ISIPHINGO PRIMARY SCHOOL | 500168498 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2016-06-14 | 2019-01-15 | 2023-12-15 | 2022-09-05 | 2023-03-04 | 660128 | 3624872 | 4285000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28479 | W/500297961/SDS | KwaZulu-Natal | YARROW PRIMARY SCHOOL | 500297961 | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2017-12-01 | 2024-03-30 | 2023-06-30 | 2022-06-01 | 486490 | 2221621 | 2708111 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28484 | W/500499352/NS | KwaZulu-Natal | ESIFISWENI SECONDARY SCHOOL (NEW MANGOSUTHU AREA) | 500499352 | Abaqulusi | Feasibility | Active - Not Contracted | 2018-01-01 |  | 2023-08-01 |  |  | 6480000 | 29520000 | 36000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28486 | W/500449291/WS | KwaZulu-Natal | CELANI PRIMARY SCHOOL | 500449291 | Impendle | Design | Active - Not Contracted | 2016-11-19 |  | 2024-04-30 |  |  | 265365 | 1208884 | 1474249 | Education Infrastructure Grant | Upgrading and Additions
|  | 28488 | W/500174418/WS | KwaZulu-Natal | KHETHWAYO PRIMARY SCHOOL | 500174418 | Umhlabuyalingana | Design | Active - Not Contracted | 2016-04-01 |  | 2025-03-31 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28491 | W/500165427/WS | KwaZulu-Natal | INQOLAYOLWAZI SENIOR PRIMARY SCHOOL | 500165427 | uMngeni | Design | Active - Not Contracted | 2016-06-14 |  | 2024-08-31 |  |  | 7200000 | 32800000 | 40000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28492 | W/500297961/WS | KwaZulu-Natal | YARROW PRIMARY SCHOOL | 500297961 | uMngeni | Design | Active - Not Contracted | 2016-06-15 |  | 2025-09-29 |  |  | 0 | 500 | 500 | Education Infrastructure Grant | Upgrading and Additions
|  | 28495 | DB/500195693/SDS | KwaZulu-Natal | MAMBUKA PRIMARY SCHOOL | 500195693 | uMhlathuze | Design | Active - Not Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 28496 | W/500165649/WS | KwaZulu-Natal | INSIKA JUNIOR SECONDARY SCHOOL | 500165649 | The Msunduzi | Tender | Active - Contracted | 2016-06-14 |  | 2026-06-30 |  |  | 770520 | 3510148 | 4280668 | Education Infrastructure Grant | Upgrading and Additions
|  | 28499 | I/500425426/UA | KwaZulu-Natal | GLENNGARRY PRIMARY SCHOOL | 500425426 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-06-20 | 2022-04-28 | 2022-04-28 | 2023-04-28 | 2023-04-28 | 7502000 | 41680000 | 49182000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28502 | W/500131239/WS | KwaZulu-Natal | EMANJOKWENI PRIMARY SCHOOL | 500131239 | Inkosi Langalibalele | Tender | Active - Contracted | 2015-10-27 |  | 2026-03-29 |  |  | 766000 | 2000000 | 2766000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28503 | DB/500207570/SDS | KwaZulu-Natal | MENDU HIGH SCHOOL | 500207570 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2024-02-23 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 28504 | C/500227735/UA | KwaZulu-Natal | CONGCO HIGH SCHOOL | 500227735 | uMngeni | On Hold | Active - Not Contracted | 2015-11-20 |  | 2025-04-20 |  |  | 1287000 | 5865000 | 7152000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28506 | W/500326340/WS | KwaZulu-Natal | CELIMPILO PRIMARY SCHOOL | 500326340 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2020-10-20 | 2023-06-30 | 2023-12-15 | 2024-12-15 | 842916 | 3839953 | 4682869 | Education Infrastructure Grant | Upgrading and Additions
|  | 28507 | I/500228882/WS | KwaZulu-Natal | Inqolothi P | I/500228882/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-06-08 | 2016-04-01 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 203000 | 923000 | 1126000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28508 | W/500191919/WS | KwaZulu-Natal | MAGABENG SECONDARY SCHOOL | 500191919 | Nqutu | Tender | Active - Not Contracted | 2016-02-01 |  | 2025-06-30 |  |  | 0 | 2241000 | 2241000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28510 | W/500307692/SDS | KwaZulu-Natal | YETHENI PRIMARY SCHOOL | 500307692 | uMlalazi | Final Completion | Active - Contracted | 2016-06-15 | 2016-08-05 | 2023-03-30 | 2023-05-30 | 2023-05-30 | 601033 | 4042497 | 4643530 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28513 | W/500244237/AU | KwaZulu-Natal | OPHOFINI SECONDARY SCHOOL | 500244237 | Umvoti | Feasibility | Active - Not Contracted | 2017-11-20 |  | 2023-03-29 |  |  | 1134900 | 4567000 | 5701900 | Education Infrastructure Grant | Upgrading and Additions
|  | 28514 | DB/500301550/SDS | KwaZulu-Natal | ZUZULWAZI JUNIOR SECONDARY SCHOOL | 500301550 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2020-05-30 | 2020-12-04 | 2023-01-13 | 2022-02-09 | 2027-03-23 | 416396 | 1896913 | 2313309 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28517 | W/500106708/WS | KwaZulu-Natal | BEAULAH PRIMARY SCHOOL | 500106708 | Umzumbe | Construction 51% - 75% | Active - Contracted | 2016-06-13 | 2017-05-01 | 2023-06-30 | 2024-03-31 | 2024-05-31 | 1283387 | 5846541 | 7129928 | Education Infrastructure Grant | Upgrading and Additions
|  | 28518 | W/500134088/WS | KwaZulu-Natal | EMPEMBENI PRIMARY SCHOOL | 500134088 | uMhlathuze | Tender | Active - Contracted | 2016-02-12 |  | 2026-08-17 |  |  | 660043 | 3143060 | 3803103 | Education Infrastructure Grant | Upgrading and Additions
|  | 28519 | W/500122026/WS | KwaZulu-Natal | DLEMUDLEMU SECONDARY SCHOOL | 500122026 | Mfolozi | Construction 51% - 75% | Active - Contracted | 2016-11-19 | 2019-06-30 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 90000 | 906000 | 996000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28520 | W/500131350/WS | KwaZulu-Natal | EMANYISENI PRIMARY SCHOOL | 500131350 | Jozini | Practical Completion (100%) | Active - Contracted | 2015-01-05 | 2019-05-30 | 2023-05-30 | 2023-05-30 | 2024-05-30 | 1214824 | 5534200 | 6749024 | Education Infrastructure Grant | Upgrading and Additions
|  | 28521 | W/500324453/WS | KwaZulu-Natal | CELUKUPHIWA PRIMARY SCHOOL | 500324453 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2016-04-01 |  | 2026-03-30 |  |  | 892000 | 3000000 | 3892000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28522 | DB/500229585/SDS | KwaZulu-Natal | NHLABANE PRIMARY SCHOOL | DB/500288919/SDS | Mfolozi | Final Completion | Approved | 2015-10-23 | 2016-01-20 | 2023-02-04 | 2023-03-15 | 2025-04-05 | 406809 | 1853239 | 2260048 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28525 | DB/500181072/WS | KwaZulu-Natal | LIONS RIVER PRIMARY SCHOOL | 500181072 | uMngeni | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-31 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28526 | I/500414400/RRR | KwaZulu-Natal | DLANGAMANDLA S | I/500414400/RRR | Msinga | Final Completion | Active - Contracted | 2010-11-03 | 2013-09-23 | 2023-06-17 | 2015-03-31 | 2023-03-23 | 21778080 | 9921000 | 31699080 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28527 | DB/500168646/SDS | KwaZulu-Natal | ISIPHINGO PRIMARY SCHOOL | 500168498 | eThekwini | Final Completion | Approved | 2017-06-06 | 2018-12-01 | 2023-06-13 | 2023-05-05 | 2025-03-29 | 568818 | 6877226 | 7446044 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28530 | W/500191993/WS | KwaZulu-Natal | MAGADLELA PRIMARY SCHOOL | 500191993 | uPhongolo | Tender | Active - Not Contracted | 2017-06-01 |  | 2026-09-02 |  |  | 368000 | 1753000 | 2121000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28531 | DB/500225515/SDS | KwaZulu-Natal | NDLUYESILO HIGH SCHOOL | 500225515 | uMhlathuze | Design | Active - Not Contracted | 2017-05-01 |  | 2024-03-20 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28532 | DB/500429126/WS | KwaZulu-Natal | VULINDLELA PRIMARY SCHOOL | 500429126 | Umdoni | Practical Completion (100%) | Active - Contracted | 2015-09-02 |  | 2024-03-29 |  |  | 100000 | 400000 | 500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28533 | DB/500106597/ECD | KwaZulu-Natal | BAZANENI PRIMARY SCHOOL | 500106597 | Big Five Hlabisa | Tender | Active - Contracted | 2016-06-13 |  | 2025-10-31 |  |  | 1074780 | 4896220 | 5971000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28534 | W/500184038/SDS | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-05-09 |  | 2024-03-30 |  |  | 700000 | 2300000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28535 | W/500122211/WS | KwaZulu-Natal | DLOLWANE PRIMARY SCHOOL | 500122211 | Nkandla | Tender | Active - Contracted | 2016-04-01 |  | 2024-03-31 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28537 | W/500166130/WS | KwaZulu-Natal | INTATHAKUSA COMBINED SCHOOL | 500166130 | Abaqulusi | Tender | Active - Contracted | 2016-06-14 |  | 2026-03-31 |  |  | 201700 | 919200 | 1120900 | Education Infrastructure Grant | Upgrading and Additions
|  | 28539 | DB/500229695/SDS | KwaZulu-Natal | NHLALAKAHLE PRIMARY | DB/500229659/RRR | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2017-09-20 | 2020-06-01 | 2025-03-10 | 2021-02-26 | 2025-03-10 | 1394317 | 6351888 | 7746205 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28540 | C/500114441/LSEN | KwaZulu-Natal | CARRISBROOKE PRIMARY SCHOOL | 500114441 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2016-12-18 | 2023-12-20 | 2022-11-01 | 2023-12-20 | 3896000 | 17752000 | 21648000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28541 | W/500115736/WS | KwaZulu-Natal | CEZA PRIMARY SCHOOL | 500115736 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-11-30 | 2023-11-30 | 2024-11-15 | 2024-11-30 | 1351435 | 6156537 | 7507972 | Education Infrastructure Grant | Upgrading and Additions
|  | 28542 | I/500105154/UA | KwaZulu-Natal | BAMBISANDLA PRIMARY SCHOOL | 500105154 | eThekwini | Feasibility | Active - Not Contracted | 2016-06-20 |  | 2026-03-31 |  |  | 3600000 | 16400000 | 20000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28544 | W/500131461/WS | KwaZulu-Natal | EMAPHAYINI PRIMARY SCHOOL | 500131461 | eDumbe | Tender | Active - Contracted | 2015-02-18 |  | 2024-04-30 |  |  | 0 | 3097 | 3097 | Education Infrastructure Grant | Upgrading and Additions
|  | 28546 | DB/500234728/SDS | KwaZulu-Natal | ISULOMPHAKATHI SECONDARY SCHOOL | 500234728 | Mfolozi | Design | Active - Not Contracted | 2017-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28547 | W/500298294/WS | KwaZulu-Natal | ZABALAZA INTERMEDIATE SCHOOL | 500298294 | Newcastle | On Hold | Active - Not Contracted | 2016-06-15 | 2023-06-01 | 2024-03-30 | 2023-06-30 | 2024-03-30 | 0 | 500 | 500 | Education Infrastructure Grant | Upgrading and Additions
|  | 28548 | W/500106708/SDS | KwaZulu-Natal | INTATHAKUSA P | 500321789 | Abaqulusi | Tender | Active - Contracted | 2016-06-14 |  | 2025-07-31 |  |  | 700000 | 2700000 | 3400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28551 | DB/500160950/WS | KwaZulu-Natal | IMIZAMO HIGH SCHOOL | 500160950 | Abaqulusi | Tender | Active - Not Contracted | 2016-03-15 |  | 2023-03-30 |  |  | 540000 | 2460000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28552 | W/500268509/WS | KwaZulu-Natal | SITHANDENE PRIMARY SCHOOL | 500268509 | Nqutu | On Hold | Active - Not Contracted | 2016-02-20 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 79000 | 20000 | 99000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28553 | W/500131572/WS | KwaZulu-Natal | EMASUNDWINI PRIMARY SCHOOL | 500131572 | uMlalazi | Tender | Active - Contracted | 2015-04-27 |  | 2024-04-11 |  |  | 0 | 2601 | 2601 | Education Infrastructure Grant | Upgrading and Additions
|  | 28555 | DB/500106375/SDS | KwaZulu-Natal | BAVUMILE PRIMARY SCHOOL | 500106375 | eThekwini | Practical Completion (100%) | Active - Contracted | 2018-01-08 | 2018-04-03 | 2023-05-31 | 2018-10-06 | 2027-05-31 | 1263805 | 5757334 | 7021139 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28559 | W/500122507/WS | KwaZulu-Natal | DOLO COMBINED SCHOOL | 500122507 | Umvoti | Design | Active - Not Contracted | 2017-03-20 |  | 2024-06-30 |  |  | 514933 | 2345804 | 2860737 | Education Infrastructure Grant | Upgrading and Additions
|  | 28562 | DB/500172013/SDS | KwaZulu-Natal | JUNAGARTH PRIMARY SCHOOL | 500172013/SDS | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-05-30 | 2023-10-01 | 2023-05-20 | 2023-07-01 | 668152 | 271189848 | 271858000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28563 | W/500268398/WS | KwaZulu-Natal | SISTER JOANS SECONDARY SCHOOL | 500268398 | Ray Nkonyeni | Construction 76% - 99% | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 627568 | 2858919 | 3486487 | Education Infrastructure Grant | Upgrading and Additions
|  | 28564 | W/500131609/WS | KwaZulu-Natal | EMASWAZINI PRIMARY SCHOOL | 500131609 | The Msunduzi | Tender | Active - Not Contracted | 2015-02-17 |  | 2024-03-31 |  |  | 648101 | 2952462 | 3600563 | Education Infrastructure Grant | Upgrading and Additions
|  | 28565 | W/500245162/UA | KwaZulu-Natal | OTTAWA PRIMARY SCHOOL | 500245162 | eThekwini | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 745000 | 3394000 | 4139000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28566 | DB/500341362/WS | KwaZulu-Natal | NHLANGE JS | DB/500341362/RRR | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-10-24 |  | 2024-02-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28567 | W/500315462/SDS | KwaZulu-Natal | KHISHWA PRIMARY SCHOOL | 500315462 | Mthonjaneni | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 642613 | 2927457 | 3570070 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28568 | I/500214415/NS | KwaZulu-Natal | MONA PRIMARY SCHOOL (Completion Contract) | 500214415 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-06-20 | 2016-09-26 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 5987000 | 27273000 | 33260000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28569 | DB/500247308/SDS | KwaZulu-Natal | PHAKATHI SECONDARY SCHOOL | 500247308 | eThekwini | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2020-06-01 | 2023-10-01 | 2023-02-26 | 2025-02-26 | 999255 | 4552163 | 5551418 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28572 | W/500335294/WS | KwaZulu-Natal | CHIEF NGONYAMA SECONDARY SCHOOL | 500335294 | Ndwedwe | Tender | Active - Not Contracted | 2016-04-01 |  | 2024-06-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28574 | W/500304917/WS | KwaZulu-Natal | KHOBONGO JUNIOR PRIMARY SCHOOL | 500304917 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-05-06 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 493331 | 2247395 | 2740726 | Education Infrastructure Grant | Upgrading and Additions
|  | 28575 | DB/500241067/WS | KwaZulu-Natal | NTOKOZWENI PRIMARY SCHOOL | 500241067 | eThekwini | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 518920 | 2363968 | 2882888 | Education Infrastructure Grant | Upgrading and Additions
|  | 28577 | DB/500170200/SDS | KwaZulu-Natal | IXOPO VILLAGE PRIMARY SCHOOL | 500170274 | Ubuhlebezwe | Feasibility | Active - Not Contracted | 2016-06-06 | 2016-07-10 | 2023-10-01 | 2018-11-30 | 2024-04-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28578 | W/500131942/WS | KwaZulu-Natal | EMBETHA JUNIOR SECONDARY SCHOOL | 500131942 | Umhlabuyalingana | Tender | Active - Not Contracted | 2015-01-20 |  | 2026-04-29 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28580 | DB/500172346/SDS | KwaZulu-Natal | KANGIKHO PRIMARY SCHOOL | 500172346 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-20 | 2017-12-01 | 2023-05-31 | 2023-05-05 | 2024-06-12 | 948316 | 4320106 | 5268422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28581 | W/500174640/WS | KwaZulu-Natal | KHOLOKAZANA PRIMARY SCHOOL | 500174640 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-11-01 | 2018-02-01 | 2025-09-30 | 2019-03-29 | 2025-09-30 | 232000 | 1055000 | 1287000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28582 | DB/500229881/SDS | KwaZulu-Natal | NHLANGENYUKE PRIMARY SCHOOL | 55229585 | uMhlathuze | Design | Active - Not Contracted | 2016-04-20 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28585 | W/500109187/ECD | KwaZulu-Natal | BHEKUMUSA PRIMARY SCHOOL | 500321789 | Mtubatuba | Tender | Active - Not Contracted | 2016-06-14 |  | 2026-03-31 |  |  | 135000 | 615000 | 750000 | Equitable Share | Upgrading and Additions
|  | 28586 | W/500250638/RRR | KwaZulu-Natal | HOERSKOOL PIONIER SCHOOL | 500250638 | Abaqulusi | Feasibility | Active - Not Contracted | 2016-04-01 |  | 2024-04-30 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28589 | DB/500112591/WS | KwaZulu-Natal | BROOKFIELD PRIMARY SCHOOL | 500112591 | Nkandla | Design | Active - Not Contracted | 2016-05-11 |  | 2025-03-22 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28590 | W/500166204/WS | KwaZulu-Natal | INTINYANE PRIMARY SCHOOL | 500166204 | eThekwini | Tender | Active - Contracted | 2016-06-14 |  | 2026-03-31 |  |  | 572465 | 2607895 | 3180360 | Education Infrastructure Grant | Upgrading and Additions
|  | 28593 | DB/500319014/SDS | KwaZulu-Natal | KHABA JUNIOR SECONDARY SCHOOL | 500319014 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2018-01-15 | 2023-03-28 | 2023-03-28 | 2025-03-28 | 442560 | 2016106 | 2458666 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28595 | DB/500425944/SDS | KwaZulu-Natal | KAYEKA PRIMARY SCHOOL | 500425944 | Umzimkhulu | Final Completion | Approved | 2014-04-20 | 2016-06-18 | 2023-12-30 | 2022-09-01 | 2022-03-30 | 1257153 | 4729289 | 5986442 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28596 | I/500189144/ECD | KwaZulu-Natal | LUTHILUNYE PRIMARY SCHOOL | 500189144 | Emadlangeni | Design | Active - Not Contracted | 2016-06-20 |  | 2026-03-31 |  |  | 424800 | 1935200 | 2360000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28598 | I/500142894/CU | KwaZulu-Natal | EWUBWINI PRIMARY SCHOOL | 500142894 | Umzumbe | Design | Active - Not Contracted | 2016-02-16 |  | 2024-03-29 |  |  | 280000 | 7237000 | 7517000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28599 | W/500166315/UA | KwaZulu-Natal | INTSHISEKELO SECONDARY SCHOOL | 500166315 | eThekwini | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-31 |  |  | 2689920 | 12254080 | 14944000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28601 | W/500192215/WS | KwaZulu-Natal | MAAGENQEZA PRIMARY SCHOOL | 500192215 | Nongoma | Tender | Active - Not Contracted | 2016-02-21 |  | 2026-03-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28602 | W/500132238/WS | KwaZulu-Natal | EMBUSWENI PRIMARY SCHOOL | 500132238 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2015-03-17 | 2016-04-01 | 2024-03-30 | 2023-06-30 | 2022-06-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28603 | I/500423798/UA | KwaZulu-Natal | BONGINCEBA SENIOR PRIMARY SCHOOL | 500423798 | Ubuhlebezwe | On Hold | Active - Not Contracted | 2012-09-21 |  | 2024-01-01 |  |  | 3237000 | 14747000 | 17984000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28604 | DB/500174714/SDS | KwaZulu-Natal | KHOMBINDLELA HIGH SCHOOL | 500174714 | uMhlathuze | Design | Active - Not Contracted | 2016-06-06 |  | 2025-06-13 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28607 | W/500166389/WS | KwaZulu-Natal | INTUMBANE PRIMARY SCHOOL | 500166389 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-05-02 | 2018-04-27 | 2023-03-31 | 22023-03-31 | 2023-03-31 | 1094000 | 4985000 | 6079000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28608 | C/500113516/ECD | KwaZulu-Natal | BUKELAKITHI PRIMARY SCHOOL | 500113516 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2013-01-15 | 2017-06-25 | 2023-02-21 | 2023-02-21 | 2023-03-20 | 287000 | 1309000 | 1596000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28609 | DB/500174973/SDS | KwaZulu-Natal | SIYAKHULA SECONDARY SCHOOL | 500174973 | Mtubatuba | Design | Active - Not Contracted | 2016-06-06 |  | 2025-06-13 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28610 | DB/500319532/WS | KwaZulu-Natal | FRANKLIN SECONDARY SCHOOL | 500319532 | Dr Nkosazana Dlamini Zuma | Construction 76% - 99% | Active - Contracted | 2016-03-23 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 114533 | 561729 | 676262 | Education Infrastructure Grant | Upgrading and Additions
|  | 28611 | DB/500209346/SDS | KwaZulu-Natal | MGEBISE PRIMARY SCHOOL | 500209346 | uMlalazi | Design | Active - Not Contracted | 2016-01-03 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 28612 | W/500147038/SDS | KwaZulu-Natal | GANGEYANA PRIMARY SCHOOL | 500147038 | Msinga | Design | Active - Not Contracted | 2015-11-19 |  | 2024-05-11 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28613 | DB/500222259/SDS | KwaZulu-Natal | MZINGWENYA PRIMARY SCHOOL | 500222259 | uMhlathuze | Design | Active - Not Contracted | 2017-11-20 |  | 2023-10-01 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28616 | DB/500108521/SDS | KwaZulu-Natal | BHEKESHOWE SECONDARY SCHOOL | 500108521 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-12-01 | 2022-05-15 | 2022-12-05 | 2023-05-15 | 1039513 | 4735561 | 5775074 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28618 | W/500192252/WS | KwaZulu-Natal | MAGENWINI PRIMARY SCHOOL | 500192252 | Alfred Duma | Design | Active - Not Contracted | 2016-01-10 |  | 2024-03-30 |  |  | 410000 | 1000000 | 1410000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28619 | I/500148259/CU | KwaZulu-Natal | GEORGEDALE PRIMARY SCHOOL | 500148259 | eThekwini | Design | Active - Not Contracted | 2016-01-28 |  | 2024-03-29 |  |  | 104000 | 35461000 | 35565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28620 | W/500174751/WS | KwaZulu-Natal | KHOMO PRIMARY SCHOOL | 500174751 | Mthonjaneni | Tender | Active - Contracted | 2016-11-20 |  | 2026-03-29 |  |  | 0 | 2340000 | 2340000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28621 | DB/500207977/SDS | KwaZulu-Natal | MERRYHILL PRIMARY SCHOOL | 500207977 | eThekwini | Final Completion | Approved | 2012-02-10 | 2018-04-06 | 2023-08-29 | 2023-08-29 | 2025-08-29 | 866573 | 3947720 | 4814293 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28622 | DB/500176120/SDS | KwaZulu-Natal | KINGSLEY SIVANANDA COMBINED SCHOOL | 500176120 | Emadlangeni | Final Completion | Approved | 2016-06-06 | 2016-10-20 | 2023-10-01 | 2023-04-20 | 2023-10-20 | 382043 | 1437210 | 1819253 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28623 | W/500166759/WS | KwaZulu-Natal | INYANGANYE PRIMARY SCHOOL | 500166759 | KwaDukuza | Construction 51% - 75% | Active - Contracted | 2016-06-14 | 2016-08-31 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 671556 | 3059310 | 3730866 | Education Infrastructure Grant | Upgrading and Additions
|  | 28624 | W/500325674/WS | KwaZulu-Natal | LETHITHEMBA PRIMARY SCHOOL | 500325674 | Ulundi | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-11-30 |  |  | 0 | 1763000 | 1763000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28626 | DB/500134902/SDS | KwaZulu-Natal | EMTHONJENI PRIMARY SCHOOL | 500134902 | Jozini | Final Completion | Approved | 2016-06-06 | 2016-08-18 | 2023-10-01 | 2022-12-15 | 2023-06-12 | 714863 | 2689245 | 3404108 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28627 | DB/500158915/WS | KwaZulu-Natal | HUBA HIGH SCHOOL | 500158915 | Richmond | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-03-01 | 2024-03-30 | 2024-03-30 | 2025-03-30 | 3383000 | 15414000 | 18797000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28629 | W/500187294/SDS | KwaZulu-Natal | LLOYD PRIMARY SCHOOL | 500187294 | KwaDukuza | Project Initiation | Active - Not Contracted | 2017-01-17 |  | 2024-02-21 |  |  | 600000 | 2000000 | 2600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28631 | W/500166833/SDS | KwaZulu-Natal | INYATHI PRIMARY SCHOOL | 500166833 | uMlalazi | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-03-31 |  |  | 851923 | 3204852 | 4056775 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28632 | W/500192326/WS | KwaZulu-Natal | MAGIDIGIDI PRIMARY SCHOOL | 500192252 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2018-02-01 | 2023-03-31 | 2021-04-30 | 2025-03-31 | 253000 | 1153000 | 1406000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28633 | W/500176231/WS | KwaZulu-Natal | KIRKINTULLOCH PRIMARY SCHOOL | 500176231 | Alfred Duma | Design | Active - Not Contracted | 2016-06-06 |  | 2024-05-29 |  |  | 72000 | 328000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28635 | W/500206919/SDS | KwaZulu-Natal | MDUNGANDLOVU PRIMARY SCHOOL | 500206919 | Umhlabuyalingana | Project Initiation | Active - Not Contracted | 2017-01-15 |  | 2024-03-30 |  |  | 2325000 | 3725000 | 6050000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28638 | W/500175195/WS | KwaZulu-Natal | KHULEKANI PRIMARY SCHOOL | 50017195 | Msinga | Design | Active - Not Contracted | 2016-03-20 |  | 2024-12-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28639 | W/500176527/WS | KwaZulu-Natal | KLIPWAL PRIMARY SCHOOL | 500176527 | uPhongolo | Tender | Active - Contracted | 2016-06-06 |  | 2025-10-01 |  |  | 72000 | 328000 | 400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28640 | I/500154882/WS | KwaZulu-Natal | HESHE SECONDARY SCHOOL | 500154882 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-02-08 | 2017-10-12 | 2023-03-10 | 2023-05-20 | 2023-07-30 | 204000 | 929000 | 1133000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28641 | DB/500232693/SDS | KwaZulu-Natal | NKOSIBOMVU PRIMARY | DB/500440411/SDS | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-02-06 | 2016-03-10 | 2023-02-10 | 2019-04-11 | 2025-07-19 | 1630004 | 6131918 | 7761922 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28642 | C/500444370/NS | KwaZulu-Natal | BHEVU SECONDARY SCHOOL | 500444370 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-09-20 | 2017-08-20 | 2023-03-20 | 2023-03-20 | 2023-08-20 | 8638000 | 39350000 | 47988000 | Equitable Share | New or Replaced Infrastructure
|  | 28644 | W/500196840/SDS | KwaZulu-Natal | MANGQAKAZA PRIMARY SCHOOL | 500196840 | Mandeni | Practical Completion (100%) | Active - Contracted | 2017-01-29 | 2019-04-27 | 2023-02-23 | 2022-02-23 | 2023-02-23 | 181816 | 837307 | 1019123 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28646 | I/500124394/WS | KwaZulu-Natal | DUMENKUNGWINI PRIMARY SCHOOL | 500124394 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-01-20 | 2016-12-18 | 2023-03-31 | 2018-03-31 | 2023-03-31 | 155000 | 707000 | 862000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28647 | W/500175232/WS | KwaZulu-Natal | KHULUBONE PRIMARY SCHOOL | 500175232 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 799083 | 3640267 | 4439350 | Education Infrastructure Grant | Upgrading and Additions
|  | 28649 | DB/500157065/WS | KwaZulu-Natal | HLOBANI PRIMARY SCHOOL (HLOBANE (MINE) P) | 500157065 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2015-09-22 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 330947 | 1507648 | 1838595 | Education Infrastructure Grant | Upgrading and Additions
|  | 28650 | I/500157509/WS | KwaZulu-Natal | HLOPHEKHULU PRIMARY SCHOOL | 500157509 | Ulundi | Practical Completion (100%) | Active - Contracted | 2013-12-10 | 2015-04-14 | 2022-11-30 | 2018-03-30 | 2023-11-30 | 261000 | 1190000 | 1451000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28651 | W/500323898/WS | KwaZulu-Natal | MAGOJOLO PRIMARY SCHOOL | 500323898 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2015-08-02 | 2019-08-19 | 2022-08-30 | 2022-08-30 | 2023-08-30 | 862327 | 3928378 | 4790705 | Education Infrastructure Grant | Upgrading and Additions
|  | 28652 | W/500175491/WS | KwaZulu-Natal | KHUMOLENI PRIMARY SCHOOL | 500175491 | Abaqulusi | Tender | Active - Contracted | 2017-06-01 |  | 2025-06-30 |  |  | 693536 | 3159443 | 3852979 | Education Infrastructure Grant | Upgrading and Additions
|  | 28653 | DB/500187960/SDS | KwaZulu-Natal | LUBANA PRIMARY SCHOOL | 5001877960 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2017-09-03 | 2019-09-30 | 2022-06-30 | 2022-06-30 | 2023-06-30 | 798048 | 3635552 | 4433600 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28655 | W/500206201/UA | KwaZulu-Natal | MDLANGATHI SENIOR SECONDARY SCHOOL | 500206201 | uMuziwabantu | Design | Active - Not Contracted | 2015-09-30 |  | 2024-03-30 |  |  | 8394000 | 38239000 | 46633000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28661 | W/500169497/WS | KwaZulu-Natal | ITHALA SECONDARY SCHOOL | 500169497 | Nkandla | Construction 76% - 99% | Active - Contracted | 2011-06-15 | 2011-12-15 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 748051 | 3407790 | 4155841 | Education Infrastructure Grant | Upgrading and Additions
|  | 28662 | W/500187775/SDS | KwaZulu-Natal | LOUISIAN PRIMARY SCHOOL | 500187775 | Ray Nkonyeni | Project Initiation | Active - Not Contracted | 2017-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28665 | W/500167055/WS | KwaZulu-Natal | IPHUPHUMA PRIMARY SCHOOL | 500167055 | Msinga | Tender | Active - Not Contracted | 2016-01-14 |  | 2026-03-30 |  |  | 643000 | 2000000 | 2643000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28666 | W/500175861/RRR | KwaZulu-Natal | KING BHEKUZULU HIGH SCHOOL | 500175935 | Abaqulusi | Design | Active - Contracted | 2016-04-29 | 2022-03-30 | 2023-03-30 | 2023-08-30 | 2024-01-30 | 474000 | 2162000 | 2636000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28668 | DB/500209420/SDS | KwaZulu-Natal | MGEZENI SECONDARY SCHOOL | 500209420 | eThekwini | Design | Proposed | 2016-06-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28669 | W/500185444/WS | KwaZulu-Natal | LANGAZELA SECONDARY SCHOOL | 500185444 | Nqutu | Tender | Active - Not Contracted | 2015-11-13 |  | 2026-09-29 |  |  | 0 | 386000 | 386000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28672 | DB/500207866/SDS | KwaZulu-Natal | MEREBANK SECONDARY SCHOOL | 500207866 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2019-01-16 | 2023-07-16 | 2023-06-22 | 2023-06-25 | 1191112 | 5426176 | 6617288 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28674 | DB/500233618/SDS | KwaZulu-Natal | NOBUZWE PRIMARY SCHOOL | 500233248 | Umzumbe | Final Completion | Approved | 2016-05-20 | 2016-08-03 | 2023-04-30 | 2019-01-03 | 2025-04-03 | 519889 | 1955772 | 2475661 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28675 | I/500343101/WS | KwaZulu-Natal | JOKO HIGH SCHOOL | 500343101 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-06-10 | 2016-04-01 | 2023-03-31 | 2018-03-30 | 2023-03-31 | 95000 | 720000 | 815000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28677 | W/500183779/RRR | KwaZulu-Natal | KWATHATHANI SECONDARY SCHOOL (COMPLETION) | 500183779 | Ubuhlebezwe | Design | Active - Not Contracted | 2016-06-13 |  | 2024-06-30 |  |  | 877725 | 3998524 | 4876249 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28680 | I/500447182/WS | KwaZulu-Natal | DUMABEMSOLA PRIMARY SCHOOL | I/500447182/WS | Msinga | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-02-15 | 2023-03-30 | 2018-02-12 | 2023-03-30 | 211964 | 1177581 | 1389545 | Education Infrastructure Grant | Upgrading and Additions
|  | 28681 | DB/500319754/SDS | KwaZulu-Natal | NOGABISELA HIGH SCHOOL | DB/500233618/SDS | uMlalazi | Final Completion | Approved | 2015-11-20 | 2018-12-01 | 2025-03-04 | 2021-05-05 | 2025-03-04 | 43820 | 199625 | 243445 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28682 | I/500172531/UA | KwaZulu-Natal | KEATE STREET P | 500172531 | Alfred Duma | Design | Active - Contracted | 2016-06-15 |  | 2026-03-31 |  |  | 4084000 | 18606000 | 22690000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28684 | W/500185259/WS | KwaZulu-Natal | LANGALAKHE SECONDARY SCHOOL | 500185259 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-07-01 | 2024-12-30 | 2024-12-30 | 2024-12-30 | 852000 | 3882000 | 4734000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28685 | DB/500197728/SDS | KwaZulu-Natal | DB/500197728/SDS: MANYANDENI PRIMARY SCHOOL | 500197728 | Abaqulusi | Tender | Active - Not Contracted | 2016-04-01 |  | 2025-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28686 | I/500172568/WS | KwaZulu-Natal | KEATES DRIFT P | I/500172568/WS | Msinga | Construction 26% - 50% | Active - Contracted | 2016-06-21 | 2021-02-03 | 2022-08-30 | 2022-06-05 | 2023-08-30 | 450000 | 2616000 | 3066000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28688 | I/500178784/WS | KwaZulu-Natal | KWA BANAKILE P | I/500178784/WS | Abaqulusi | Design | Proposed | 2016-06-14 |  | 2024-03-30 |  |  | 117180 | 533820 | 651000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28689 | DB/500311725/SDS | KwaZulu-Natal | NOMAQONI JUNIOR SECONDARY SCHOOL | DB/500148555/SDS | uMlalazi | Final Completion | Approved | 2016-02-20 | 2016-05-03 | 2025-03-14 | 2019-02-07 | 2025-03-14 | 639891 | 2915059 | 3554950 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28692 | W/500321752/WS | KwaZulu-Natal | MANZEZULU PRIMARY SCHOOL | 500321752 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2016-10-07 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28693 | I/500173678/UA | KwaZulu-Natal | KHANYISANI PRIMARY SCHOOL | 500173678 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-20 | 2017-10-12 | 2023-03-30 | 2018-09-30 | 2023-03-30 | 5488380 | 25002620 | 30491000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28694 | W/500191549/SDS | KwaZulu-Natal | MADUNDUBALA PRIMARY SCHOOL | 500191549 | eThekwini | Tender | Active - Contracted | 2017-04-01 |  | 2025-09-30 |  |  | 140400 | 741510 | 881910 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28697 | I/500181300/WS | KwaZulu-Natal | KWAMLIMISI PRIMARY SCHOOL | I/500181300/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-14 | 2021-02-03 | 2023-01-15 | 2022-01-05 | 2023-01-15 | 275940 | 1257060 | 1533000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28699 | I/500198135/WS | KwaZulu-Natal | MANZIMAKHULUAP | I/500198135/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-05-12 | 2024-03-30 | 2018-03-09 | 2024-03-30 | 542900 | 2505100 | 3048000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28700 | DB/500102453/SDS | KwaZulu-Natal | AMAPHUTHU HIGH SCHOOL | 500102453 | Nkandla | Design | Active - Not Contracted | 2015-10-23 |  | 2024-01-31 |  |  | 569746 | 2595511 | 3165257 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28701 | ET/500242905/WS | KwaZulu-Natal | OGAGWINI PRIMARY SCHOOL | 500242905 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2013-06-13 | 2018-08-20 | 2022-04-30 | 2024-04-30 | 2025-04-30 | 843298 | 6428490 | 7271788 | Education Infrastructure Grant | Upgrading and Additions
|  | 28703 | I/500126170/UA | KwaZulu-Natal | EBOMVINI P | I/500126170/UA | Ray Nkonyeni | Construction 76% - 99% | Active - Contracted | 2013-11-30 | 2015-02-05 | 2023-02-06 | 2017-06-19 | 2023-11-30 | 5250000 | 19750000 | 25000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28705 | W/500193140/WS | KwaZulu-Natal | MAHLABA PIMARY SCHOOL | 500193140 | Msinga | On Hold | Active - Not Contracted | 2016-04-01 |  | 2024-06-30 |  |  | 1800000 | 820000 | 2620000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28707 | C/500103563/LSEN | KwaZulu-Natal | ARTHUR BLAXALL SPECIAL SCHOOL | C/500103563/LSEN | The Msunduzi | On Hold | Active - Contracted | 2016-09-20 |  | 2024-03-31 |  |  | 2520000 | 11485000 | 14005000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28709 | W/500447663/WS | KwaZulu-Natal | MAPHAMBILI PRIMARY SCHOOL | 500447663 | Abaqulusi | Tender | Active - Not Contracted | 2016-11-20 |  | 2025-03-29 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28710 | W/500184926/SDS | KwaZulu-Natal | LAKESIDE PRIMARY SCHOOL | 500184926 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 625146 | 3709745 | 4334891 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28712 | I/500340511/ECD | KwaZulu-Natal | EMTHUNZINI PRIMARY SCHOOL | 500340511 | Newcastle | Design | Active - Not Contracted | 2013-10-28 |  | 2024-05-14 |  |  | 648000 | 2295200 | 2943200 | Education Infrastructure Grant | Upgrading and Additions
|  | 28713 | DB/500252673/SDS | KwaZulu-Natal | QHAMUKA HIGH SCHOOL | 500252673 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2020-05-29 | 2025-03-10 | 2021-02-26 | 2025-03-10 | 1516915 | 6910392 | 8427307 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28714 | DB/500337477/SDS | KwaZulu-Natal | JIKANE PRIMARY SCHOOL | DB/500337477/SDS | Nkandla | Final Completion | Approved | 2016-09-20 | 2016-12-20 | 2023-02-21 | 2019-03-20 | 2024-05-20 | 1041031 | 3916261 | 4957292 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28715 | W/500191734/SDS | KwaZulu-Natal | MAFITLENG PRIMARY SCHOOL | 500191734 | Nqutu | Final Completion | Active - Contracted | 2017-06-21 | 2019-04-27 | 2022-11-27 | 2022-11-27 | 2025-11-27 | 493318 | 2247340 | 2740658 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28716 | W/500193214/WS | KwaZulu-Natal | W/MAHLABATHINI SECONDARY SCHOOL | 500193214 | eThekwini | Tender | Active - Not Contracted | 2017-03-01 |  | 2025-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28718 | W/500325783/WS | KwaZulu-Natal | MATHUKULULA SECONDARY SCHOOL | 500325783 | Endumeni | Tender | Active - Not Contracted | 2016-01-22 |  | 2025-06-30 |  |  | 500000 | 1379000 | 1879000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28719 | W/500339179/WS | KwaZulu-Natal | EKUPHAKAMENI PRIMARY SCHOOL | 500339179 | Mthonjaneni | Tender | Active - Not Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 1032205 | 4702268 | 5734473 | Education Infrastructure Grant | Upgrading and Additions
|  | 28721 | I/500321308/WS | KwaZulu-Natal | Kwabhamu H | I/500321308/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-09-01 | 2023-03-31 | 2018-03-30 | 2023-03-31 | 48000 | 906000 | 954000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28722 | DB/500110371/WS | KwaZulu-Natal | BIZIMALI HIGH SCHOOL | 500110371 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2024-03-11 | 2023-03-25 | 2024-07-30 | 2025-05-11 | 500000 | 1000000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28723 | W/500198505/WS | KwaZulu-Natal | MAPHOVELA HIGH SCHOOL | 500198505 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-03-01 | 2017-11-29 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 1127139 | 5134743 | 6261882 | Education Infrastructure Grant | Upgrading and Additions
|  | 28724 | W/500400673/WS | KwaZulu-Natal | KWENZOKUHLE PRIMARY SCHOOL | 500400673 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2015-11-12 |  | 2025-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28725 | DB/500237540/SDS | KwaZulu-Natal | NQUMIZWE HIGH SCHOOL | 500237540 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2015-10-24 | 2019-01-15 | 2023-07-15 | 2023-07-15 | 2025-07-15 | 935282 | 4260730 | 5196012 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28726 | W/500201946/UA | KwaZulu-Natal | MATHUNJWA SECONDARY SCHOOL | 500201946 | Abaqulusi | Design | Active - Not Contracted | 2016-06-22 |  | 2024-04-30 |  |  | 2160000 | 9840000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28727 | W/500184297/WS | KwaZulu-Natal | KWAZIHLAKANIPHELE PRIMARY SCHOOL | 500184297 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 506000 | 2409000 | 2915000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28728 | W/500193473/WS | KwaZulu-Natal | MAHLOKOMANE PRIMARY SCHOOL | 500193473 | Maphumulo | Design | Active - Not Contracted | 2016-11-20 |  | 2024-06-30 |  |  | 347000 | 1651000 | 1998000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28732 | I/500129093/WS | KwaZulu-Natal | EKUTHOKOZENI PRIMARY SCHOOL | 500129093 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-05-26 | 2023-03-30 | 2018-02-02 | 2024-03-30 | 392000 | 2906650 | 3298650 | Education Infrastructure Grant | Upgrading and Additions
|  | 28733 | W/500202094/WS | KwaZulu-Natal | MATIWANESKOP PRIMARY SCHOOL | W/500202094/WS | Alfred Duma | Design | Active - Not Contracted | 2016-06-21 |  | 2024-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28734 | I/500158767/NS | KwaZulu-Natal | COSMO PRIMARY SCHOOL | I/500158767/NS | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2022-11-24 | 2022-12-22 | 2023-06-29 | 2023-08-04 | 9424260 | 66357874 | 75782134 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28736 | DB/500240537/SDS | KwaZulu-Natal | NTSHIDI P | DB/500239057/SDS | uMlalazi | Final Completion | Approved | 2015-11-20 | 2016-12-20 | 2023-04-30 | 2023-05-20 | 2025-10-20 | 377937 | 1721715 | 2099652 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28737 | W/500184186/WS | KwaZulu-Natal | KWAZIBI P | W/500184186/WS | Umhlabuyalingana | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 357831 | 1703956 | 2061787 | Education Infrastructure Grant | Upgrading and Additions
|  | 28738 | W/500202131/WS | KwaZulu-Natal | MATSHAMHLOPHE PRIMARY SCHOOL | 500202131 | Big Five Hlabisa | Tender | Active - Contracted | 2016-06-23 |  | 2023-06-30 |  |  | 702880 | 3202009 | 3904889 | Education Infrastructure Grant | Upgrading and Additions
|  | 28739 | W/500193621/WS | KwaZulu-Natal | MAHLUBIMANGWE PRIMARY SCHOOL | 500193621 | Okhahlamba | Final Completion | Active - Contracted | 2015-10-20 | 2019-04-20 | 2024-10-30 | 2024-10-30 | 2025-10-30 | 90000 | 410000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28740 | W/500167129/WS | KwaZulu-Natal | IQHAWELESIZWE COMBINED SCHOOL | 500167129 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-11-20 | 2017-03-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28741 | I/500129574/WS | KwaZulu-Natal | ELANDSBERG PRIMARY SCHOOL | 500129574 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-04-04 | 2017-02-09 | 2023-03-30 | 2018-02-12 | 2023-03-30 | 224707 | 1248373 | 1473080 | Education Infrastructure Grant | Upgrading and Additions
|  | 28743 | W/500198764/WS | KwaZulu-Natal | MAQHINGA MEMORIAL SCHOOL | 500198764 | Msinga | Design | Active - Not Contracted | 2017-03-20 |  | 2024-09-29 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28745 | W/500184112/WS | KwaZulu-Natal | KWAZENZELE SECONDARY SCHOOL | 500184112 | Msinga | Final Completion | Active - Contracted | 2015-11-20 | 2017-08-03 | 2023-03-30 | 2022-03-30 | 2025-03-30 | 580384 | 2643970 | 3224354 | Education Infrastructure Grant | Upgrading and Additions
|  | 28746 | DB/500241314/SDS | KwaZulu-Natal | NXENJANE PRIMARY SCHOOL | 500240685 | uMlalazi | Design | Active - Not Contracted | 2016-03-20 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 28747 | W/500167166/WS | KwaZulu-Natal | ISAMBULO PRIMARY SCHOOL | 500167166 | Umhlabuyalingana | Tender | Active - Contracted | 2017-02-20 |  | 2025-03-31 |  |  | 90000 | 1265000 | 1355000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28749 | I/500424723/CU | KwaZulu-Natal | ELUKOLWENI JUNIOR SECONDARY SCHOOL | 500424723 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2017-04-30 |  | 2024-03-30 |  |  | 46000 | 22055000 | 22101000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28750 | DB/500193658/WS | KwaZulu-Natal | MAHLUTSHINI PRIMARY SCHOOL | 500193658 | Impendle | Construction 26% - 50% | Active - Contracted | 2016-01-02 | 2018-09-12 | 2024-03-31 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28751 | I/500118511/WS | KwaZulu-Natal | Cranham P | I/500118511/WS | Umvoti | Construction 51% - 75% | Active - Contracted | 2016-06-21 | 2020-03-30 | 2023-05-10 | 2023-06-10 | 2024-03-30 | 320400 | 1698791 | 2019191 | Education Infrastructure Grant | Upgrading and Additions
|  | 28752 | W/500202945/WS | KwaZulu-Natal | MAVUBANE JS | W/500202945/WS | uMlalazi | Project Initiation | Active - Not Contracted | 2016-06-22 |  | 2023-03-30 |  |  | 0 | 2898000 | 2898000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28753 | W/500306360/WS | KwaZulu-Natal | MAQHUTSHANA JUNIOR SECONDARY SCHOOL | 500306360 | eThekwini | On Hold | Active - Contracted | 2016-04-01 |  | 2023-03-29 |  |  | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28754 | I/500334036/WS | KwaZulu-Natal | KWAGOQO P | I/500334036/WS | Abaqulusi | Project Initiation | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 58000 | 958000 | 1016000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28755 | DB/500338328/SDS | KwaZulu-Natal | BEKEZELANI JUNIOR SECONDARY SCHOOL | 500106264 | Dr Nkosazana Dlamini Zuma | Final Completion | Approved | 2015-10-24 | 2016-10-19 | 2023-04-26 | 2022-04-26 | 2023-07-05 | 625087 | 2351519 | 2976606 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28756 | I/500129981/WS | KwaZulu-Natal | EMABHEKAZI COMBINED SCHOOL | I/500129981/WS | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2017-02-23 | 2023-03-30 | 2018-02-23 | 2024-03-30 | 247000 | 1124000 | 1371000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28757 | W/500193695/WS | KwaZulu-Natal | MOHELELA PRIMARY SCHOOL | 500193695 | Nqutu | Tender | Active - Not Contracted | 2016-05-12 |  | 2025-06-30 |  |  | 496147 | 2260224 | 2756371 | Education Infrastructure Grant | Upgrading and Additions
|  | 28758 | DB/500289673/SDS | KwaZulu-Natal | UMZOKHANYAYO PRIMARY SCHOOL | 500289673 | uMuziwabantu | Construction 76% - 99% | Active - Not Contracted | 2017-06-22 | 2019-06-30 | 2023-01-03 | 2022-02-07 | 2027-03-14 | 1023059 | 4660602 | 5683661 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28760 | W/500202834/WS | KwaZulu-Natal | MAWELE SECONDARY SCHOOL | 500202834 | Msinga | On Hold | Active - Not Contracted | 2016-06-29 |  | 2023-03-29 |  |  | 47000 | 680000 | 727000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28762 | W/500309357/WS | KwaZulu-Natal | MAQIYANA PRIMARY SCHOOL | 500309357 | Abaqulusi | Tender | Active - Not Contracted | 2016-08-01 |  | 2025-03-29 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28763 | W/500111481/SDS | KwaZulu-Natal | BONGUZWANE SECONDARY SCHOOL | 500111481 | Umzumbe | Project Initiation | Active - Not Contracted | 2016-06-13 |  | 2024-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28765 | W/500194065/WS | KwaZulu-Natal | MAKATEESKOP PRIMARY SCHOOL | 500194065 | eDumbe | Construction 26% - 50% | Active - Contracted | 2015-11-12 | 2017-11-20 | 2024-06-30 | 2024-06-30 | 2025-06-30 | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28766 | W/500203315/WS | KwaZulu-Natal | MAZISI NTULI PRIMARY SCHOOL | 500203315 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2017-03-31 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 969766 | 4617934 | 5587700 | Education Infrastructure Grant | Upgrading and Additions
|  | 28767 | I/Sis.New15/001/NS | KwaZulu-Natal | NEW EMADUNGENI SECONDARY SCHOOL | I/Sis.New15/001/NS | Greater Kokstad | Final Completion | Active - Contracted | 2015-11-12 | 2022-10-12 | 2022-12-20 | 2022-12-30 | 2023-03-30 | 5400000 | 27158905 | 32558905 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28768 | I/500180227/WS | KwaZulu-Natal | KWAMADUMA P | I/500180227/WS | Abaqulusi | Project Initiation | Proposed | 2016-04-01 |  | 2024-03-31 |  |  | 123660 | 563340 | 687000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28770 | DB/500309098/WS | KwaZulu-Natal | QHOBO JUNIOR SSECONDARY SCHOOL | 500309098 | Nqutu | Design | Active - Contracted | 2021-06-13 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28771 | W/500203352/WS | KwaZulu-Natal | MAZONGO PRIMARY SCHOOL | 500203352 | Ubuhlebezwe | Tender | Active - Not Contracted | 2016-06-29 |  | 2023-03-30 |  |  | 500000 | 500000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28772 | W/500198949/WS | KwaZulu-Natal | MAQOQA SECONDARYB SCHOOL | 500198949 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-11-21 | 2017-12-07 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28773 | DB/500108151/SDS | KwaZulu-Natal | BHEKABATHEMBU HIGH SCHOOL | 500107966 | Alfred Duma | Final Completion | Active - Contracted | 2015-11-20 | 2016-11-04 | 2023-04-26 | 2022-09-20 | 2023-06-20 | 389930 | 1466880 | 1856810 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28774 | I/500130388/WS | KwaZulu-Natal | Emafakathini P | I/500130388/WS | The Msunduzi | Construction 51% - 75% | Active - Contracted | 2016-04-01 |  | 2023-03-30 |  |  | 320400 | 1617600 | 1938000 | Equitable Share | Upgrading and Additions
|  | 28775 | W/500190513/SDS | KwaZulu-Natal | MACEBO PRIMARY SCHOOL | 500190513 | Umdoni | Tender | Active - Not Contracted | 2017-06-20 |  | 2023-02-23 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28777 | W/500176749/WS | KwaZulu-Natal | KNOOPAAN PRIMARY SCHOOL | 500176749 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2026-10-01 |  |  | 292122 | 1391056 | 1683178 | Education Infrastructure Grant | Upgrading and Additions
|  | 28779 | W/500176823/WS | KwaZulu-Natal | KOHLOKOLO PRIMARY SCHOOL | 500176823 | Nongoma | Tender | Active - Contracted | 2016-06-06 |  | 2026-10-01 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28780 | W/500177082/WS | KwaZulu-Natal | KONFOOR COMBINED SCHOOL | 500177082 | Ulundi | Tender | Active - Contracted | 2016-06-06 |  | 2026-06-13 |  |  | 1000000 | 2200000 | 3200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28782 | W/500177193/WS | KwaZulu-Natal | KOPLEEGTE PRIMARY SCHOOL | 500177193 | Okhahlamba | Design | Active - Not Contracted | 2015-11-06 |  | 2024-10-01 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28785 | DB/500192548/SDS | KwaZulu-Natal | MAGQAMA HIGH SCHOOL | 500192548 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-01-15 | 2022-07-15 | 2022-09-15 | 2027-07-15 | 1166208 | 5312726 | 6478934 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28787 | W/500177304/WS | KwaZulu-Natal | KOTO PRIMARY SCHOOL | 500177304/WS | eDumbe | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-30 | 2023-10-01 | 2024-03-30 | 2025-04-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28788 | W/500210530/SDS | KwaZulu-Natal | MHLUMAYO PRIMARY SCHOOL | 500210530 | Alfred Duma | Final Completion | Approved | 2017-11-20 | 2018-06-16 | 2023-01-30 | 2023-02-28 | 2023-02-01 | 2833000 | 4233000 | 7066000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28790 | C/500227587/UA | KwaZulu-Natal | NGCEDOMHLOPHE H | 500227587 | The Msunduzi | On Hold | Active - Not Contracted | 2015-04-01 |  | 2023-04-20 |  |  | 2040000 | 9297000 | 11337000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28792 | W/500298442/SDS | KwaZulu-Natal | ZAKHELENI PRIMARY SCHOOL | 500298442 | Ulundi | Practical Completion (100%) | Active - Not Contracted | 2016-06-15 | 2016-08-05 | 2023-06-30 | 2021-06-30 | 2024-06-30 | 727996 | 3316426 | 4044422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28793 | W/500268250/WS | KwaZulu-Natal | SISHONGANI PRIMARY SCHOOL | 500268250 | Abaqulusi | Construction 76% - 99% | Active - Not Contracted | 2017-03-01 |  | 2023-06-30 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 28794 | W/500123099/WS | KwaZulu-Natal | DOVER COMBINED SCHOOL | 500123099 | uMhlathuze | Tender | Active - Contracted | 2016-11-19 |  | 2026-03-30 |  |  | 0 | 3064000 | 3064000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28797 | W/500194361/WS | KwaZulu-Natal | MAKHAPHA PRIMARY SCHOOL | 500194361 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-02 | 2018-04-27 | 2023-05-31 | 2018-09-01 | 2025-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28798 | C/500231657/ECD | KwaZulu-Natal | NKANYEZI PRIMARY SCHOOL (KWAMBONAMBI) | 500231657 | Mfolozi | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 2800000 | 3300000 | 6100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28799 | W/500268213/WS | KwaZulu-Natal | SISEBENZILE SECONDARY SCHOOL | 500268213 | Ndwedwe | Tender | Proposed | 2016-04-01 |  | 2023-06-30 |  |  | 1032150 | 4702016 | 5734166 | Education Infrastructure Grant | Upgrading and Additions
|  | 28800 | W/500424205/WS | KwaZulu-Natal | DRC SECONDARY SCHOOL | 500424205 | Umzimkhulu | Final Completion | Active - Contracted | 2016-03-30 | 2017-01-20 | 2024-03-30 | 2023-06-30 | 2022-03-04 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28802 | W/500305990/SDS | KwaZulu-Natal | MARIANHILL PRIMARY SCHOOL | 500305990 | eThekwini | Design | Active - Not Contracted | 2016-04-01 |  | 2023-05-30 |  |  | 1483632 | 6758767 | 8242399 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28803 | W/500132275/WS | KwaZulu-Natal | EMBUYENI PRIMARY SCHOOL | 500132275 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-09-28 | 2020-01-01 | 2024-03-30 | 2021-05-28 | 2022-04-26 | 770947 | 3512093 | 4283040 | Education Infrastructure Grant | Upgrading and Additions
|  | 28804 | DB/500241647/SDS | KwaZulu-Natal | NYANISWENI PRIMARY SCHOOL | DB/500241314/SDS | eThekwini | Final Completion | Approved | 2015-11-20 | 2016-06-22 | 2023-01-09 | 2019-02-20 | 2025-03-12 | 536000 | 2440000 | 2976000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28806 | W/500298627/WS | KwaZulu-Natal | ZAMANGOTHANDO SECONDARY SCHOOL | 500298627 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-06-15 | 2020-12-01 | 2023-06-30 | 2021-01-01 | 2023-03-13 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 28807 | W/500268102/WS | KwaZulu-Natal | SIQONDOKUHLE PRIMARY SCHOOL | 500268102 | Ndwedwe | Construction 26% - 50% | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 930950 | 4240995 | 5171945 | Education Infrastructure Grant | Upgrading and Additions
|  | 28810 | W/500194472/WS | KwaZulu-Natal | MAKHATHINI PRIMARY SCHOOL | 500194472 | Nkandla | Tender | Active - Not Contracted | 2016-05-02 |  | 2025-02-28 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28812 | DB/500104599/NS | KwaZulu-Natal | BABANANGO PRIMARY SCHOOL | 500104599 | Ulundi | Design | Proposed | 2016-06-06 |  | 2024-10-01 |  |  | 1432000 | 2968000 | 4400000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28813 | W/500429311/WS | KwaZulu-Natal | ZAMANI SENIOR PRIMARY SCHOOL | 500429311 | Greater Kokstad | Tender | Active - Not Contracted | 2016-06-15 |  | 2023-06-30 |  |  | 666641 | 3036920 | 3703561 | Education Infrastructure Grant | Upgrading and Additions
|  | 28814 | W/500177896/SDS | KwaZulu-Natal | KUMKANI PRIMARY SCHOOL | 500177896 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-06-06 |  | 2025-10-01 |  |  | 914760 | 4167240 | 5082000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28817 | DB/500327154/SDS | KwaZulu-Natal | OHLALWINI PRIMARY SCHOOL | 500327154 | Jozini | Feasibility | Active - Not Contracted | 2015-10-24 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28818 | W/500199504/SDS | KwaZulu-Natal | MARIANNPARK PRIMARY SCHOOL | 500199504 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-05-06 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 972160 | 4428730 | 5400890 | Education Infrastructure Grant | Upgrading and Additions
|  | 28819 | W/500194324/WS | KwaZulu-Natal | MAKHANYEZI PRIMARY SCHOOL | 500194324 | Nkandla | Tender | Active - Not Contracted | 2016-01-02 |  | 2026-06-30 |  |  | 924881 | 4213347 | 5138228 | Education Infrastructure Grant | Upgrading and Additions
|  | 28820 | W/500132386/UA | KwaZulu-Natal | EMFANELA PRIMARY SCHOOL (COMPLETION CONTRACT ) | 500132386 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2015-09-29 | 2018-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 1685000 | 7674000 | 9359000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28821 | W/500177859/WS | KwaZulu-Natal | SINOTHILE PRIMARY SCHOOL (KUNENINGI P) | 500177859 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 605648 | 2759063 | 3364711 | Education Infrastructure Grant | Upgrading and Additions
|  | 28822 | W/500298664/WS | KwaZulu-Natal | ZAMANI PRIMARY SCHOOL (NONGOMA) | 500298664 | Greater Kokstad | Practical Completion (100%) | Active - Contracted | 2016-06-15 |  | 2023-06-30 |  |  | 859316 | 3914663 | 4773979 | Education Infrastructure Grant | Upgrading and Additions
|  | 28824 | W/500407037/WS | KwaZulu-Natal | DUDUZILE SECONDARY SCHOOL | 500407037 | Ray Nkonyeni | Construction 76% - 99% | Active - Contracted | 2016-03-30 | 2020-07-30 | 2023-06-30 | 2023-11-30 | 2024-10-15 | 90000 | 647000 | 737000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28825 | W/500307951/SDS | KwaZulu-Natal | KHUPHUKA PRIMARY SCHOOL | 500307951 | Umdoni | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2017-02-01 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 300000 | 1700000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 28826 | W/500298738/WS | KwaZulu-Natal | ZAMAZISA PRIMARY SCHOOL | 500298738 | Maphumulo | On Hold | Active - Not Contracted | 2016-06-15 |  | 2024-06-30 |  |  | 87000 | 1413000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28827 | W/500193584/SDS | KwaZulu-Natal | MUHLUBE SECONDARY SCHOOL | 500193584 | Ndwedwe | Project Initiation | Active - Contracted | 2017-11-20 |  | 2024-03-30 |  |  | 1000448 | 4885744 | 5886192 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28828 | DB/500212861/SDS | KwaZulu-Natal | MLOMOKAZULU JUNIOR SCHOOL | 500212861 | uPhongolo | Final Completion | Approved | 2016-09-20 | 2016-12-20 | 2023-02-21 | 2022-09-20 | 2023-05-20 | 845779 | 3181740 | 4027519 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28829 | W/500194139/WS | KwaZulu-Natal | MAKHAMBANE PRIMARY SCHOOL | 5001941139 | Mtubatuba | Tender | Active - Not Contracted | 2016-04-09 |  | 2023-03-30 |  |  | 0 | 3137000 | 3137000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28830 | I/500180634/WS | KwaZulu-Natal | Kwamaphumulo P | I/500180634/WS | uMngeni | Design | Active - Not Contracted | 2016-06-15 |  | 2024-03-30 |  |  | 195300 | 889700 | 1085000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28831 | ET/500325672/WS | KwaZulu-Natal | KUSAKUSA PRIMARY SCHOOL | 500325672 | eThekwini | Final Completion | Approved | 2016-06-06 | 2017-05-04 | 2023-03-31 | 2022-03-30 | 2023-03-30 | 756338 | 3445542 | 4201880 | Education Infrastructure Grant | Upgrading and Additions
|  | 28832 | W/500343989/WS | KwaZulu-Natal | KWAVULAMEHLO PRIMARY SCHOOL | 500343938 | Msinga | Tender | Active - Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 0 | 1843000 | 1843000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28833 | W/500199948/WS | KwaZulu-Natal | MARSHMOUNT PRIMARY SCHOOL | 500199948 | Umzumbe | Tender | Active - Not Contracted | 2016-04-01 |  | 2023-06-29 |  |  | 1168726 | 5324197 | 6492923 | Education Infrastructure Grant | Upgrading and Additions
|  | 28834 | W/500123876/WS | KwaZulu-Natal | DUKUZA PIRMARY SCHOOL | 500123876 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-11-19 | 2018-02-01 | 2024-05-31 | 2020-03-29 | 2024-05-31 | 1000000 | 2653000 | 3653000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28835 | W/500429422/SDS | KwaZulu-Natal | ZAMOKUHLE SECONDARY SCHOOL | 500429422 | Umzimkhulu | Design | Active - Not Contracted | 2016-06-15 |  | 2024-11-30 |  |  | 6969600 | 31750400 | 38720000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28836 | W/500219447/SDS | KwaZulu-Natal | MTHOMBOWOLWAZI PRIMARY SCHOOL | 500219447 | uMngeni | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-01 |  |  | 2107000 | 3507000 | 5614000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28838 | W/500132460/WS | KwaZulu-Natal | EMFIHLWENI PRIMARY SCHOOL | 500132460 | Umhlabuyalingana | Tender | Active - Contracted | 2015-08-26 |  | 2025-06-30 |  |  | 681852 | 3106213 | 3788065 | Education Infrastructure Grant | Upgrading and Additions
|  | 28840 | DB/500109631/WS | KwaZulu-Natal | BHOKOZA PRIMARY SCHOOL | 500109631 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2024-03-11 | 2024-02-12 | 2024-07-30 | 2025-05-11 | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28841 | W/500194287/WS | KwaZulu-Natal | MAJHANKANA INTERMADIATE SCHOOL | 500194287 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-11-02 | 2018-02-01 | 2022-05-31 | 2022-09-01 | 2025-09-30 | 441000 | 2010000 | 2451000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28842 | DB/500200022/WS | KwaZulu-Natal | MARYHELP PRIMARY SCHOOL | 500200022 | Dr Nkosazana Dlamini Zuma | Tender | Active - Contracted | 2016-04-01 |  | 2025-12-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28843 | W/500203463/WS | KwaZulu-Natal | MBALANE PRIMARY SCHOOL | 500203463 | Umvoti | On Hold | Approved | 2016-06-22 |  | 2023-03-30 |  |  | 21000 | 95000 | 116000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28844 | W/500298960/WS | KwaZulu-Natal | ZAMOKUHLE PRIMARY SCHOOL | 500298960 | Impendle | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2016-08-05 | 2022-08-05 | 2022-08-05 | 2023-08-05 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28845 | W/500178636/WS | KwaZulu-Natal | KWA MNGOTHO PRIMARY SCHOOL | 500178636 | uPhongolo | Tender | Active - Contracted | 2016-06-06 |  | 2025-10-30 |  |  | 763833 | 3479682 | 4243515 | Education Infrastructure Grant | Upgrading and Additions
|  | 28846 | W/500440263/SDS | KwaZulu-Natal | FISOKUHLE PRIMARY SCHOOL | 500440263 | Abaqulusi | Final Completion | Active - Contracted | 2016-06-13 | 2017-08-30 | 2023-05-29 | 2024-03-30 | 2024-08-30 | 487000 | 2222000 | 2709000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28848 | W/500192104/SDS | KwaZulu-Natal | MAGAYE PRIMARY SCHOOL | 500192104 | Ray Nkonyeni | Project Initiation | Proposed | 2017-06-06 |  | 2024-02-23 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28853 | W/500183631/RRR | KwaZulu-Natal | Kwasoni Primary School | 500183631 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-09-01 | 2022-12-30 | 2022-12-30 | 2025-12-30 | 2333000 | 10626000 | 12959000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28854 | W/500299034/WS | KwaZulu-Natal | ZAMOKWAKHE SECONDARY SCHOOL | 500299034 | Nqutu | Tender | Active - Not Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 0 | 2015 | 2015 | Education Infrastructure Grant | Upgrading and Additions
|  | 28855 | W/500310171/WS | KwaZulu-Natal | MBALEKELWA PRIMARY SCHOOL | 500310171 | Jozini | Tender | Active - Contracted | 2016-06-22 |  | 2023-06-30 |  |  | 721237 | 3285633 | 4006870 | Education Infrastructure Grant | Upgrading and Additions
|  | 28856 | DB/500113294/SDS | KwaZulu-Natal | BUHLEBEZWE PRIMARY SCHOOL | 500113294 | Ray Nkonyeni | Final Completion | Approved | 2015-11-20 | 2016-12-20 | 2023-02-21 | 2022-09-20 | 2019-11-20 | 138059 | 628937 | 766996 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28858 | W/500299071/SDS | KwaZulu-Natal | ZAMUKUZAKHA PRIMARY SCHOOL | 500299071 | Ray Nkonyeni | Tender | Active - Not Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 1627704 | 7415097 | 9042801 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28859 | W/500267880/WS | KwaZulu-Natal | SIPHUMELELE PRIMARY SCHOOL | 500267880 | Newcastle | On Hold | Approved | 2016-02-20 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28860 | W/500308210/WS | KwaZulu-Natal | MASAMENI SECONDARY SCHOOL | 500308210 | Dr Nkosazana Dlamini Zuma | Tender | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 1165380 | 5308951 | 6474331 | Education Infrastructure Grant | Upgrading and Additions
|  | 28861 | W/500197654/WS | KwaZulu-Natal | MANYALA PRIMARY SCHOOL | 500197654 | Abaqulusi | Tender | Active - Not Contracted | 2015-11-26 |  | 2025-03-29 |  |  | 872175 | 3973240 | 4845415 | Education Infrastructure Grant | Upgrading and Additions
|  | 28862 | W/500178710/SDS | KwaZulu-Natal | KWASOKOYI PRIMARY SCHOOL | 500178710 | Abaqulusi | Final Completion | Active - Contracted | 2016-06-13 | 2022-03-30 | 2023-06-30 | 2023-08-30 | 2024-03-30 | 576501 | 2626281 | 3202782 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28864 | I/500182114/CU | KwaZulu-Natal | KWANDUNGE SECONDARY SCHOOL | 500182114 | Msinga | Construction 76% - 99% | Active - Contracted | 2012-02-29 | 2012-12-03 | 2023-09-07 | 2018-01-30 | 2023-07-31 | 938142 | 4467344 | 5405486 | Equitable Share | Upgrading and Additions
|  | 28865 | W/500178969/WS | KwaZulu-Natal | KWABULAWAYO SECONDARY SCHOOL | 500178969 | Big Five Hlabisa | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 701959 | 3197813 | 3899772 | Education Infrastructure Grant | Upgrading and Additions
|  | 28867 | W/500203426/WS | KwaZulu-Natal | MASHESHA JUNIOR SECONDARY SCHOOL | 500203426 | Umzumbe | Design | Active - Contracted | 2016-04-01 |  | 2023-05-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28868 | W/500178044/WS | KwaZulu-Natal | KWADINABAKUBO SECONDARY SCHOOL | 500178044 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-30 | 2023-05-31 | 2024-04-30 | 2025-04-30 | 899504 | 4097741 | 4997245 | Education Infrastructure Grant | Upgrading and Additions
|  | 28869 | I/500132793/WS | KwaZulu-Natal | EMHLUNGWINI PRIMARY SCHOOL | I/500132793/WS | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-11-12 | 2023-03-30 | 2017-05-21 | 2023-03-30 | 334000 | 1522000 | 1856000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28876 | W/500183557/WS | KwaZulu-Natal | KWASIMAMANE PRIMARY SCHOOL | 500183557 | Ndwedwe | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2022-03-30 | 2023-03-11 | 2024-04-30 | 2025-04-30 | 1116876 | 5087991 | 6204867 | Education Infrastructure Grant | Upgrading and Additions
|  | 28878 | W/500200577/WS | KwaZulu-Natal | MASHIZA PRIMARY SCHOOL | 5000200577 | KwaDukuza | On Hold | Active - Contracted | 2016-04-01 |  | 2023-03-11 |  |  | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28882 | W/500132682/WS | KwaZulu-Natal | EMHLANGENI SENIOR PRIMARY SCHOOL | 500132682 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-04-20 |  | 2023-06-30 |  |  | 732875 | 3338655 | 4071530 | Education Infrastructure Grant | Upgrading and Additions
|  | 28883 | DB/500185333/SDS | KwaZulu-Natal | LANGALETHU PRIMARY SCHOOL | 500185333 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2018-04-01 | 2020-01-23 | 2023-07-01 | 2023-09-30 | 2025-10-30 | 2258724 | 10289743 | 12548467 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28884 | W/500299515/WS | KwaZulu-Natal | ZENZELENI MASHAMASE SECONDARY SECONDARY | 500299515 | eThekwini | Tender | Active - Not Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 522000 | 3861815 | 4383815 | Education Infrastructure Grant | Upgrading and Additions
|  | 28885 | I/500133422/WS | KwaZulu-Natal | EMNGCELENI PRIMARY SCHOOL | I/500133422/WS | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-03-19 | 2023-03-15 | 2019-06-12 | 2023-08-09 | 487000 | 2708000 | 3195000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28887 | W/500215858/SDS | KwaZulu-Natal | MOYAMUHLE PRIMARY SCHOOL | 500133866 | Maphumulo | Final Completion | Active - Contracted | 2017-03-30 | 2019-08-27 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 89075 | 420973 | 510048 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28888 | W/500132904/WS | KwaZulu-Natal | EMJALISWENI PRIMARY SCHOOL | 500132904 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2015-01-21 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2021-05-31 | 353000 | 1609000 | 1962000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28889 | W/500203722/WS | KwaZulu-Natal | MBAMBUYA PRIMARY SCHOOL | 500203722 | uMuziwabantu | Construction 51% - 75% | Active - Contracted | 2016-06-23 | 2017-01-27 | 2023-05-30 | 2023-05-30 | 2023-05-30 | 803997 | 3662653 | 4466650 | Education Infrastructure Grant | Upgrading and Additions
|  | 28890 | W/500299663/WS | KwaZulu-Natal | PRINCE ZIBHEBHU SECONDARY SCHOOL | 500299663 | Nongoma | Tender | Active - Contracted | 2016-06-15 |  | 2025-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28892 | W/500183372/WS | KwaZulu-Natal | KWASHANGASE PRIMARY SCHOOL | 500183372 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-06-14 | 2022-03-30 | 2023-02-21 | 2024-04-30 | 2025-04-30 | 847843 | 3862396 | 4710239 | Education Infrastructure Grant | Upgrading and Additions
|  | 28896 | DB/500240204/SDS | KwaZulu-Natal | NTOLWANE PRIMARY SCHOOL | 500240204 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-09-20 | 2019-01-15 | 2023-07-15 | 2023-07-15 | 2025-07-15 | 1226894 | 5589186 | 6816080 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28900 | W/500203944/SDS | KwaZulu-Natal | MBATSHAZWA HIGH SCHOOL | 500203944 | Nkandla | Final Completion | Active - Contracted | 2016-06-30 |  | 2023-03-26 |  |  | 965557 | 4398651 | 5364208 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28907 | W/500195878/WS | KwaZulu-Natal | MANA HIGH SCHOOL | 500195878 | Newcastle | On Hold | Active - Not Contracted | 2016-03-16 |  | 2023-06-30 |  |  | 200000 | 1500000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28910 | W/500203981/WS | KwaZulu-Natal | MBAVA PRIMARY SCHOOL | 500203981 | uMshwathi | Tender | Active - Not Contracted | 2016-06-23 |  | 2025-03-30 |  |  | 738000 | 500000 | 1238000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28913 | W/500200688/WS | KwaZulu-Natal | MASHUNKA PRIMARY SCHOOL | 500200688 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-02-01 | 2023-03-29 | 2022-03-29 | 2023-05-31 | 564000 | 2572000 | 3136000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28914 | C/500440411/UA | KwaZulu-Natal | NKAYISHANA P | 500440411 | Msinga | Design | Active - Not Contracted | 2014-04-01 |  | 2026-04-30 |  |  | 3242000 | 14772000 | 18014000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28919 | W/500204055/WS | KwaZulu-Natal | MBEKA PRIMARY SCHOOL | 500204055 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2017-02-24 | 2023-07-27 | 2023-07-27 | 2023-07-27 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28920 | W/500335257/UA | KwaZulu-Natal | MANABA SECONDARY SCHOOL | 500335257 | Ndwedwe | Design | Active - Not Contracted | 2016-08-28 |  | 2024-03-30 |  |  | 248000 | 1135000 | 1383000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28924 | W/500227772/WS | KwaZulu-Natal | NGCONGCOSI SECONDARY SCHOOL | 500227772 | Okhahlamba | Design | Active - Contracted | 2016-06-20 |  | 2024-02-20 |  |  | 732000 | 3333000 | 4065000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28927 | W/500200762/WS | KwaZulu-Natal | MASIBHEKANE SECONDARY SCHOOL | 500200762 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2017-11-29 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28929 | W/500490361/WS | KwaZulu-Natal | MBEKWANE SECONDARY SCHOOL | 500490361 | Umhlabuyalingana | Feasibility | Active - Contracted | 2016-06-22 |  | 2024-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28931 | W/500183076/WS | KwaZulu-Natal | KWAPHUZA SENIOR PRIMARY SCHOOL | 500183076 | Umzumbe | Tender | Active - Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 81795 | 1064121 | 1145916 | Education Infrastructure Grant | Upgrading and Additions
|  | 28932 | W/500216783/SDS | KwaZulu-Natal | MPILONDE PRIMARY SCHOOL | 500216783 | Endumeni | Final Completion | Active - Contracted | 2017-01-01 | 2019-08-27 | 2023-03-14 | 2023-03-30 | 2023-03-30 | 2575000 | 3975000 | 6550000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28933 | DB/500119399/WS | KwaZulu-Natal | DALALA PRIMARY SCHOOL | 500116624 | Nqutu | Tender | Active - Contracted | 2016-04-20 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28934 | W/500335257/WS | KwaZulu-Natal | MANABA SECONDARY SCHOOL | 500335257 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2016-02-16 | 2017-07-19 | 2023-03-31 | 2022-03-31 | 2025-03-31 | 707447 | 3222815 | 3930262 | Education Infrastructure Grant | Upgrading and Additions
|  | 28935 | W/500200910/WS | KwaZulu-Natal | MASIHLANGANE SECONDARY SCHOOL | 500200910 | Abaqulusi | Construction 1% - 25% | Active - Contracted | 2017-05-01 | 2017-11-29 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 727840 | 3315716 | 4043556 | Education Infrastructure Grant | Upgrading and Additions
|  | 28937 | W/500227846/WS | KwaZulu-Natal | NGEBHUZANA HIGH SCHOOL | 500227846 | eDumbe | Practical Completion (100%) | Active - Contracted | 2016-06-20 | 2016-09-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1166056 | 5312032 | 6478088 | Education Infrastructure Grant | Upgrading and Additions
|  | 28938 | W/500179265/WS | KwaZulu-Natal | KWADOMBA HIGH SCHOOL | 500179265 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 871379 | 3969614 | 4840993 | Education Infrastructure Grant | Upgrading and Additions
|  | 28939 | W/500499611/SDS | KwaZulu-Natal | KWANZIMAKWE PRIMARY SCHOOL | 500499611 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-09-10 | 2024-04-30 | 2024-03-30 | 2025-03-30 | 700000 | 2500000 | 3200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28940 | W/500337366/WS | KwaZulu-Natal | MANANJALO PRIMARY SCHOOL | 500337366 | Abaqulusi | Tender | Active - Not Contracted | 2016-02-15 |  | 2025-03-29 |  |  | 0 | 1017000 | 1017000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28941 | W/500167462/WS | KwaZulu-Natal | ISIBANKWA PRIMARY SCHOOL | 500167462 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-05-20 | 2019-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 652000 | 2970000 | 3622000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28942 | W/500179339/WS | KwaZulu-Natal | KWADOPHI PRIMARY SCHOOL | 500179339 | Nqutu | Tender | Active - Contracted | 2015-11-06 |  | 2026-06-30 |  |  | 500000 | 636000 | 1136000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28944 | W/500307063/WS | KwaZulu-Natal | MBILINI PRIMARY SCHOOL | 500307063 | Mtubatuba | Tender | Active - Contracted | 2016-06-22 |  | 2023-03-31 |  |  | 791472 | 3605593 | 4397065 | Education Infrastructure Grant | Upgrading and Additions
|  | 28945 | W/500320346/WS | KwaZulu-Natal | MANDAWE PRIMARY SCHOOL | 500320346 | uMhlathuze | Tender | Active - Not Contracted | 2016-10-29 |  | 2026-03-29 |  |  | 200000 | 900000 | 1100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28946 | W/500183917/WS | KwaZulu-Natal | KWANYONI PRIMARY SCHOOL | 500183917 | Ulundi | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 314517 | 1497700 | 1812217 | Education Infrastructure Grant | Upgrading and Additions
|  | 28947 | W/500133163/WS | KwaZulu-Natal | EMKHUPHULA PRIMARY SCHOOL | 500133163 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-02-17 | 2019-03-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 548000 | 2497000 | 3045000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28948 | W/500219706/SDS | KwaZulu-Natal | MTHWADLANA PRIMARY SCHOOL | W/500219706/SDS | Ulundi | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2016-06-10 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 513000 | 2337000 | 2850000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28949 | W/500309417/UA | KwaZulu-Natal | ZICOLE S | 500309417 | Nqutu | Design | Active - Not Contracted | 2016-06-15 |  | 2027-05-30 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28950 | I/500444407/WS | KwaZulu-Natal | EMPOLOMBENI PRIMARY SCHOOL | 500444407 | Okhahlamba | Construction 51% - 75% | Active - Contracted | 2016-04-30 | 2020-06-18 | 2023-03-30 | 2023-05-18 | 2024-03-07 | 320400 | 1459600 | 1780000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28952 | W/500179376/WS | KwaZulu-Natal | KWAFICA SECONDARY SCHOOL | 500179376 | Umzumbe | Tender | Active - Contracted | 2016-06-06 |  | 2026-05-01 |  |  | 454000 | 2067000 | 2521000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28953 | W/500339882/WS | KwaZulu-Natal | MASIMDUMISE PRIMARY SCHOOL | 500339882 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-08 | 2023-07-26 | 2023-07-26 | 2023-07-26 | 882714 | 4021252 | 4903966 | Education Infrastructure Grant | Upgrading and Additions
|  | 28954 | W/500179450/WS | KwaZulu-Natal | KWAGAMAKAZI PRIMARY SCHOOL | 500179450 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2026-11-29 |  |  | 282000 | 1344000 | 1626000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28955 | DB/500124542/SDS | KwaZulu-Natal | DUMISA PRIMARY SCHOOL | 500124542 | Ray Nkonyeni | Feasibility | Active - Not Contracted | 2015-10-24 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28956 | W/500182780/WS | KwaZulu-Natal | KWANYEZI PRIMARY SCHOOL | 500182780 | Nqutu | Site Handed - Over to Contractor | Active - Contracted | 2015-11-14 |  | 2025-06-30 |  |  | 1000000 | 1941000 | 2941000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28957 | I/500158138/UA | KwaZulu-Natal | HOLINYOKA PRIMARY SCHOOL | I/500158138/UA | Nongoma | Practical Completion (100%) | Approved | 2016-02-10 | 2016-05-10 | 2023-03-25 | 2022-05-23 | 2023-09-12 | 7381000 | 33626000 | 41007000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 28960 | W/500133422/WS | KwaZulu-Natal | Emngceleni Primary School | 500133422 | Jozini | Tender | Active - Not Contracted | 2015-02-23 |  | 2025-06-30 |  |  | 1023660 | 4663340 | 5687000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28963 | W/500204462/WS | KwaZulu-Natal | MBITANE PRIMARY SCHOOL | 500204462 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2018-02-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 945371 | 4306691 | 5252062 | Education Infrastructure Grant | Upgrading and Additions
|  | 28965 | W/500227994/WS | KwaZulu-Natal | NGIBONGELENI SECONDARY SCHOOL | 500227994 | Inkosi Langalibalele | On Hold | Active - Contracted | 2016-06-21 |  | 2023-01-18 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28968 | W/500334258/WS | KwaZulu-Natal | MBIZOYAMASWAZI PRIMARY SCHOOL | 500334258 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-11-22 | 2018-04-27 | 2023-03-30 | 2018-09-30 | 2023-03-30 | 355000 | 1616000 | 1971000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28969 | W/500326969/WS | KwaZulu-Natal | MASOKANENI PRIMARY SCHOOL | 500326969 | Abaqulusi | Construction 1% - 25% | Active - Contracted | 2017-04-03 | 2017-11-30 | 2023-06-30 | 2024-06-30 | 2025-06-30 | 738516 | 3364353 | 4102869 | Education Infrastructure Grant | Upgrading and Additions
|  | 28970 | W/500179709/WS | KwaZulu-Natal | KWAGWEGWE PRIMARY SCHOOL | 500179709 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-30 | 2023-10-01 | 2024-03-30 | 2025-04-30 | 568455 | 2589629 | 3158084 | Education Infrastructure Grant | Upgrading and Additions
|  | 28971 | W/500306915/WS | KwaZulu-Natal | KWANYAMAZANE PRIMARY SCHOOL | 500306915 | Mtubatuba | Tender | Active - Contracted | 2016-06-13 |  | 2023-08-28 |  |  | 374000 | 980000 | 1354000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28972 | W/500132608/WS | KwaZulu-Natal | EMNGWENYA INTERMEDIATE SCHOOL | 500132608 | Mpofana | Tender | Active - Contracted | 2015-02-17 |  | 2025-09-29 |  |  | 479210 | 2183067 | 2662277 | Education Infrastructure Grant | Upgrading and Additions
|  | 28973 | W/500191660/WS | KwaZulu-Natal | MANDLAMASHA INTERMEDIATE SCHOOL | 500191660 | Newcastle | On Hold | Active - Not Contracted | 2016-02-09 |  | 2023-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28974 | W/500309417/WS | KwaZulu-Natal | ZICOLE SECONDARY SCHOOL | 500309417 | Nqutu | Design | Active - Not Contracted | 2016-06-15 |  | 2023-03-30 |  |  | 311000 | 2000000 | 2311000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28977 | W/500178118/WS | KwaZulu-Natal | KWAGXABA SECONDARY SCHOOL | 500178118 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 564428 | 2571284 | 3135712 | Education Infrastructure Grant | Upgrading and Additions
|  | 28978 | DB/500167610/WS | KwaZulu-Natal | ISIBUKOSABASHA PRIMARY SCHOOL | 500167610 | Msinga | Construction 26% - 50% | Active - Not Contracted | 2016-02-01 | 2018-09-13 | 2025-09-16 | 2021-06-15 | 2027-09-16 | 516803 | 2354323 | 2871126 | Education Infrastructure Grant | Upgrading and Additions
|  | 28979 | W/500182632/WS | KwaZulu-Natal | KWANSELE PRIMARY SCHOOL | 500182632 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2022-03-30 | 2023-03-30 | 2024-03-30 | 2025-04-30 | 885881 | 4035681 | 4921562 | Education Infrastructure Grant | Upgrading and Additions
|  | 28980 | W/500299959/WS | KwaZulu-Natal | ZIHLALO PRIMARY SCHOOL | 500299959 | Ulundi | Tender | Active - Not Contracted | 2016-06-15 |  | 2027-03-30 |  |  | 758250 | 3033000 | 3791250 | Education Infrastructure Grant | Upgrading and Additions
|  | 28981 | W/500402005/WS | KwaZulu-Natal | MATABETULU PRIMARY SCHOOL | 500402005 | eThekwini | Final Completion | Active - Contracted | 2016-04-01 | 2017-04-08 | 2023-03-31 | 2022-03-31 | 2023-03-31 | 826247 | 3934509 | 4760756 | Education Infrastructure Grant | Upgrading and Additions
|  | 28982 | DB/500197987/SDS | KwaZulu-Natal | MANZAMNYAMA PRIMARY SCHOOL | 500197987 | uMlalazi | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 28983 | W/500204573/WS | KwaZulu-Natal | MBODLA PRIMARY SCHOOL | 500204573 | Jozini | Design | Active - Not Contracted | 2016-06-23 |  | 2025-03-29 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28984 | W/500182595/WS | KwaZulu-Natal | KWANQOKOTHO PRIMARY SCHOOL | 500182595 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2022-03-30 | 2024-03-30 | 2024-04-30 | 2025-03-30 | 471283 | 2244206 | 2715489 | Education Infrastructure Grant | Upgrading and Additions
|  | 28985 | W/500311836/WS | KwaZulu-Natal | MANDLANA PRIMARY SCHOOL | 500311836 | Abaqulusi | Tender | Active - Not Contracted | 2016-02-16 |  | 2025-06-30 |  |  | 908466 | 4138565 | 5047031 | Education Infrastructure Grant | Upgrading and Additions
|  | 28986 | DB/500121582/WS | KwaZulu-Natal | DINGUKWAZI SECONDARY SCHOOL | 500121582 | uPhongolo | Construction 1% - 25% | Active - Contracted | 2016-06-20 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-30 | 0 | 1193000 | 1193000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28987 | W/500220816/SDS | KwaZulu-Natal | MURCHISON C PRIMARY SCHOOL | 500220816 | Ulundi | Design | Active - Contracted | 2017-11-15 |  | 2024-03-29 |  |  | 1927000 | 3327000 | 5254000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28988 | W/500320568/SDS | KwaZulu-Natal | LETHITHEMBA SECONDARY SCHOOL | 500320568 | KwaDukuza | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2017-06-10 | 2022-11-23 | 2022-11-23 | 2023-11-23 | 655628 | 5824919 | 6480547 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28990 | DB/500127169/SDS | KwaZulu-Natal | EFUYENI PRIMARY SCHOOL | 500127169 | Mfolozi | Feasibility | Active - Not Contracted | 2016-04-20 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28993 | W/500182373/RRR | KwaZulu-Natal | KWANOGCOYI SP | 500182373 | Nongoma | Project Initiation | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28994 | DB/500186702/SDS | KwaZulu-Natal | LINDELANI PRIMARY SCHOOL | 500186702 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-06-08 | 2023-10-05 | 2022-09-05 | 2022-01-05 | 748612 | 4155388 | 4904000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 28995 | W/500114996/WS | KwaZulu-Natal | CEBELIHLE PRIMARY SCHOOL | 500114996 | Newcastle | On Hold | Active - Not Contracted | 2016-04-01 |  | 2023-02-28 |  |  | 25000 | 562000 | 587000 | Education Infrastructure Grant | Upgrading and Additions
|  | 28997 | DB/500127502/SDS | KwaZulu-Natal | EGUJINI PS | DB/500127169/SDS | Jozini | Feasibility | Active - Not Contracted | 2015-11-20 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 28998 | W/500232138/WS | KwaZulu-Natal | NKOMBABANTU PRIMARY SCHOOL | 500232138 | Nongoma | Tender | Active - Contracted | 2015-11-20 |  | 2026-08-30 |  |  | 650000 | 2589000 | 3239000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29000 | DB/500339401/SDS | KwaZulu-Natal | LETHIMFUNDO PRIMARY SCHOOL | 500339401 | Dannhauser | Design | Active - Not Contracted | 2016-06-06 |  | 2024-02-28 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29003 | W/500232175/WS | KwaZulu-Natal | NKOMIDLI PRIMARY SCHOOL | 500232175 | Mandeni | On Hold | Active - Contracted | 2016-06-21 |  | 2023-06-30 |  |  | 100000 | 680000 | 780000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29005 | W/500180079/WS | KwaZulu-Natal | KWALAMLELA PRIMARY SCHOOL | 500180079 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2026-10-01 |  |  | 393515 | 1873883 | 2267398 | Education Infrastructure Grant | Upgrading and Additions
|  | 29008 | W/500182336/WS | KwaZulu-Natal | KWANKULU PRIMARY SCHOOL | 500182336 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 0 | 1693000 | 1693000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29009 | W/500167795/WS | KwaZulu-Natal | ISIGCINO PRIMARY SCHOOL | 500167795 | Umhlabuyalingana | Tender | Active - Contracted | 2016-04-01 |  | 2026-03-27 |  |  | 496946 | 2263865 | 2760811 | Education Infrastructure Grant | Upgrading and Additions
|  | 29012 | W/500232582/WS | KwaZulu-Natal | NKOSAZANA PRIMARY SCHOOL | 500232582 | uMhlathuze | Tender | Active - Contracted | 2016-11-20 |  | 2025-03-30 |  |  | 0 | 1478000 | 1478000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29014 | W/500201576/WS | KwaZulu-Natal | MATHANDA PRIMARY SCHOOL | 500201576 | Mthonjaneni | Tender | Active - Not Contracted | 2015-11-30 |  | 2024-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29016 | DB/500136419/WS | KwaZulu-Natal | ENGOBHIYENI PRIMARY SCHOOL | 500136419 | uMshwathi | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 353970 | 1612530 | 1966500 | Education Infrastructure Grant | Upgrading and Additions
|  | 29017 | W/500180338/WS | KwaZulu-Natal | KWAMAJOLA PRIMARY SCHOOL | 500180338 | Umvoti | Design | Active - Not Contracted | 2016-06-06 |  | 2024-03-11 |  |  | 505399 | 2807771 | 3313170 | Education Infrastructure Grant | Upgrading and Additions
|  | 29019 | W/500167832/WS | KwaZulu-Natal | ISIGODI PRIMARY SCHOOL | 500167832 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29020 | W/500178414/SDS | KwaZulu-Natal | KWANGQULU PRIMARY SCHOOL | 500178414 | Msinga | Final Completion | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-03-31 | 2023-03-31 | 2024-03-31 | 809508 | 4026872 | 4836380 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29021 | W/500198320/SDS | KwaZulu-Natal | MAPHAYA PRIMARY SCHOOL | 500198320 | Jozini | Tender | Active - Not Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29022 | W/500282865/WS | KwaZulu-Natal | ZIMISELENI JUNIOR SECONDARY SCHOOL | 500282865 | Endumeni | Practical Completion (100%) | Active - Contracted | 2016-06-15 | 2018-04-27 | 2023-05-31 | 2018-09-01 | 2023-05-31 | 415000 | 1891000 | 2306000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29023 | DB/500232767/SDS | KwaZulu-Natal | NKOSITHANDILE SECONDARY SCHOOL | DB/500232767/SDS | uMhlathuze | Design | Active - Not Contracted | 2017-11-02 |  | 2024-11-03 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 29024 | W/500180486/WS | KwaZulu-Natal | KWAMANANDI PRIMARY SCHOOL | 500180486 | Mtubatuba | Tender | Active - Contracted | 2016-06-06 |  | 2026-02-28 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29025 | W/500181781/WS | KwaZulu-Natal | KWAMSINGA PRIMARY SCHOOL | 500181781 | The Msunduzi | Final Completion | Active - Contracted | 2016-06-13 | 2017-08-03 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 1333805 | 6076224 | 7410029 | Education Infrastructure Grant | Upgrading and Additions
|  | 29026 | W/500201687/WS | KwaZulu-Natal | MATHINANTA PRIMARY SCHOOL | 500201687 | Msinga | Tender | Active - Contracted | 2016-11-20 |  | 2025-03-30 |  |  | 0 | 270000 | 270000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29029 | W/500167869/WS | KwaZulu-Natal | ISIGUDU JUNIOR PRIMARY SCHOOL | 500167869 | KwaDukuza | Construction 26% - 50% | Active - Contracted | 2016-04-01 | 2016-09-18 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 496946 | 2263865 | 2760811 | Education Infrastructure Grant | Upgrading and Additions
|  | 29030 | W/500257224/RRR | KwaZulu-Natal | OAKFORD PRIMARY SCHOOL | 500257224 | eThekwini | Design | Active - Not Contracted | 2015-11-02 |  | 2025-04-30 |  |  | 15525000 | 70725000 | 86250000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 29031 | W/500185037/SDS | KwaZulu-Natal | LAMBOTHI PRIMARY SCHOOL | 500185037 | Mandeni | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-06-10 | 2022-12-30 | 2022-12-30 | 2023-12-30 | 283180 | 1560097 | 1843277 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29033 | W/500204647/WS | KwaZulu-Natal | MBOLOBA PRIMARY SCHOOL | 500204647 | Abaqulusi | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2017-03-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29036 | I/500343323/WS | KwaZulu-Natal | ENHLANHLENI SECONDARY SCHOOL | 500343323 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-11-12 | 2023-03-30 | 2017-08-23 | 2023-03-30 | 293641 | 1232702 | 1526343 | Education Infrastructure Grant | Upgrading and Additions
|  | 29037 | W/500446812/WS | KwaZulu-Natal | ZIZI PRIMARY SCHOOL | 500446812 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-11-15 | 2018-04-27 | 2023-03-31 | 2018-09-01 | 2023-03-31 | 547000 | 2490000 | 3037000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29038 | W/500233026/WS | KwaZulu-Natal | NKUNGWINI PRIMARY SCHOOL | 500233026 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-06-27 | 2016-07-29 | 2023-05-31 | 2024-06-16 | 2025-06-20 | 529893 | 2413959 | 2943852 | Education Infrastructure Grant | Upgrading and Additions
|  | 29039 | W/500204684/WS | KwaZulu-Natal | MBONDWENI PRIMARY SCHOOL | 500204684 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2018-02-01 | 2023-03-30 | 2018-09-01 | 2023-03-30 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29040 | W/500180745/SDS | KwaZulu-Natal | KWAMASOSHA HIGH SCHOOL | 500180745 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-30 | 2023-10-01 | 2024-04-30 | 2025-04-30 | 1432763 | 6527029 | 7959792 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29041 | W/500167906/WS | KwaZulu-Natal | ISIHLAHLASENKOSI HIGH SCHOOL | W/500167906/WS | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29043 | W/500178377/SDS | KwaZulu-Natal | KWAMQADI PRIMARY SCHOOL | 500178377 | Umzumbe | Tender | Active - Contracted | 2016-06-13 |  | 2025-12-30 |  |  | 1185697 | 5401507 | 6587204 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29045 | W/500180893/WS | KwaZulu-Natal | KWAMBOMA PRIMARY SCHOOL | 500180893 | Umhlabuyalingana | Tender | Active - Contracted | 2016-04-06 |  | 2025-03-29 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29046 | W/500204869/WS | KwaZulu-Natal | MBOPHA SECONDARY SCHOOL | 500204869 | Big Five Hlabisa | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2017-01-26 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 743771 | 3388289 | 4132060 | Education Infrastructure Grant | Upgrading and Additions
|  | 29047 | W/500304732/WS | KwaZulu-Natal | KWAMPUNZI PRIMARY SCHOOL | 500304732 | Abaqulusi | Tender | Active - Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 871178 | 3968702 | 4839880 | Education Infrastructure Grant | Upgrading and Additions
|  | 29048 | W/500311355/WS | KwaZulu-Natal | KWAMFEMFENI PRIMARY SCHOOL | 500311355 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 744083 | 3613713 | 4357796 | Education Infrastructure Grant | Upgrading and Additions
|  | 29050 | W/500233100/WS | KwaZulu-Natal | NKUNYANA PRIMARY SCHOOL | 500233100 | Nqutu | Tender | Active - Contracted | 2016-06-27 |  | 2025-06-30 |  |  | 256000 | 1221000 | 1477000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29051 | W/500181078/SDS | KwaZulu-Natal | KWAMGABO PRIMARY SCHOOL | 500181078 | Alfred Duma | Tender | Active - Contracted | 2016-06-06 |  | 2025-10-01 |  |  | 325291 | 1481880 | 1807171 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29053 | W/500181633/RRR | KwaZulu-Natal | KWAMPUZANA COMPREHENSIVE PRIMARY SCHOOL | 500181633 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-09-01 | 2023-03-30 | 2022-03-30 | 2025-03-30 | 3050000 | 13892000 | 16942000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29055 | W/500327189/WS | KwaZulu-Natal | MBOPHENI PRIMARY SCHOOL | 500327189 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-22 | 2018-02-01 | 2025-12-30 | 2018-09-01 | 2025-12-30 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29056 | W/500181189/NS | KwaZulu-Natal | KWAMIYA PRIMARY SCHOOL | 500181189 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-09-01 | 2016-06-10 | 2022-06-30 | 2022-06-30 | 2023-06-30 | 7016422 | 31963699 | 38980121 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29058 | W/500233211/WS | KwaZulu-Natal | NKWAMBAZI PRIMARY SCHOOL | 500233211 | Abaqulusi | Tender | Active - Contracted | 2016-06-29 |  | 2025-06-30 |  |  | 246000 | 1108520 | 1354520 | Education Infrastructure Grant | Upgrading and Additions
|  | 29059 | W/500181411/WS | KwaZulu-Natal | KWAMNYAYIZA HIGH SCHOOL | 500181411 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2026-10-01 |  |  | 0 | 2796000 | 2796000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29060 | W/500269767/SDS | KwaZulu-Natal | SIYAKHONA PRIMARY SCHOOL | 500269767 | Umzumbe | Tender | Active - Not Contracted | 2016-06-22 |  | 2023-06-30 |  |  | 995142 | 4533425 | 5528567 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29061 | W/500181448/SDS | KwaZulu-Natal | KWAMONDI PRIMARY SCHOOL | 500181448 | uMlalazi | Tender | Active - Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 1136987 | 5179608 | 6316595 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29062 | W/500303400/WS | KwaZulu-Natal | ISIKHALISETHU PRIMARY SCHOOL | 500303400 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-05-20 | 2016-06-20 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 790866 | 3602835 | 4393701 | Education Infrastructure Grant | Upgrading and Additions
|  | 29063 | W/500161468/SDS | KwaZulu-Natal | IMVULENI PRIMARY SCHOOL | 500161468 | Dr Nkosazana Dlamini Zuma | Construction 26% - 50% | Active - Contracted | 2014-06-27 | 2016-11-16 | 2022-06-23 | 2022-08-23 | 2025-03-27 | 600000 | 2100000 | 2700000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29064 | W/500205239/WS | KwaZulu-Natal | MBUTHISWENI PRIMARY SCHOOL | 500205239 | Richmond | On Hold | Active - Contracted | 2017-06-22 |  | 2023-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29066 | I/500185185/WS | KwaZulu-Natal | LANDOKWAKHE SECONDARY SCHOOL | 500185185 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2023-03-31 | 2017-10-01 | 2023-03-31 | 122384 | 1407384 | 1529768 | Education Infrastructure Grant | Upgrading and Additions
|  | 29068 | W/500233470/WS | KwaZulu-Natal | NOBANDA PRIMARY SCHOOL | 500233470 | The Msunduzi | Tender | Active - Contracted | 2016-06-22 |  | 2026-08-31 |  |  | 300000 | 1500000 | 1800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29070 | W/500196322/WS | KwaZulu-Natal | MANDLENDODA SENIOR PRIMARY SCHOOL | 500196322 | Umzumbe | Tender | Active - Not Contracted | 2016-01-27 |  | 2025-06-30 |  |  | 117576 | 896487 | 1014063 | Education Infrastructure Grant | Upgrading and Additions
|  | 29071 | W/500196359/WS | KwaZulu-Natal | MANDLENI INTERMEDIATE SCHOOL | 500196359 | Msinga | Design | Active - Not Contracted | 2016-03-14 |  | 2023-03-29 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29072 | W/500196396/WS | KwaZulu-Natal | MANDLENYOSI PRIMARY SCHOOL | 500196396 | Msinga | Design | Active - Not Contracted | 2016-02-15 |  | 2023-06-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29073 | W/500196433/WS | KwaZulu-Natal | MANDLETHU PRIIMARY SCHOOL | 500196433 | Msinga | Design | Active - Not Contracted | 2016-02-15 |  | 2024-06-30 |  |  | 1000000 | 2585000 | 3585000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29074 | W/500196544/WS | KwaZulu-Natal | MANDOSI COMBINE SCHOOL | 500196544 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2017-05-23 | 2024-03-30 | 2023-06-30 | 2022-06-30 | 1570327 | 7153712 | 8724039 | Education Infrastructure Grant | Upgrading and Additions
|  | 29075 | W/500401450/SDS | KwaZulu-Natal | EMGANGENI SECONDARY SCHOOL | 500404150 | eThekwini | Tender | Active - Not Contracted | 2016-04-01 |  | 2025-04-30 |  |  | 350000 | 2314000 | 2664000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29076 | W/500324083/UA | KwaZulu-Natal | MANGONGO PRIMARY SCHOOL | 500324083 | KwaDukuza | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 1225000 | 5583000 | 6808000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29078 | W/500195212/WS | KwaZulu-Natal | MALIPHUME PRIMARY SCHOOL | 500195212 | uMngeni | Tender | Active - Not Contracted | 2015-04-22 |  | 2023-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29079 | W/500195323/WS | KwaZulu-Natal | MALIZAYO PRIMARY SCHOOL | 500195323 | uMngeni | Construction 76% - 99% | Active - Contracted | 2015-06-25 | 2016-10-03 | 2023-06-30 | 2023-06-30 | 2025-06-30 | 630524 | 2872388 | 3502912 | Education Infrastructure Grant | Upgrading and Additions
|  | 29081 | W/500194472/SDS | KwaZulu-Natal | MAKHATHINI PRIMARY SCHOOL | 500194472 | Mthonjaneni | Tender | Active - Contracted | 2016-04-01 |  | 2025-11-30 |  |  | 636252 | 2898482 | 3534734 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29082 | W/500239575/WS | KwaZulu-Natal | NTATSHANA PRIMARY SCHOOL | 500239575 | Mthonjaneni | Tender | Active - Contracted | 2016-11-20 |  | 2024-06-29 |  |  | 450000 | 2290000 | 2740000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29083 | W/500194546/WS | KwaZulu-Natal | MAKHEDAMA SECONDARY SCHOOL | 500194546 | Msinga | On Hold | Active - Not Contracted | 2016-02-24 |  | 2023-06-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29084 | I/500185740/WS | KwaZulu-Natal | LELIESHOEK PRIMARY SCHOOL | 500184704 | Abaqulusi | Practical Completion (100%) | Approved | 2016-06-06 | 2017-06-13 | 2023-03-31 | 2017-12-01 | 2023-03-31 | 93000 | 428000 | 521000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29088 | W/500194694/WS | KwaZulu-Natal | MAKHOSONKE S | 500224369 | Abaqulusi | On Hold | Active - Not Contracted | 2016-03-23 |  | 2023-03-29 |  |  | 0 | 1824000 | 1824000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29089 | W/500233544/WS | KwaZulu-Natal | NOBIYA SECONDARY SCHOOL | 500233544 | Jozini | Tender | Active - Contracted | 2016-06-20 |  | 2026-06-26 |  |  | 1663124 | 7576453 | 9239577 | Education Infrastructure Grant | Upgrading and Additions
|  | 29092 | DB/500184038/SDS | KwaZulu-Natal | KWAZAMOKUHLE PRIMARY SCHOOL | 500184038 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2012-02-10 | 2018-01-16 | 2023-09-04 | 2023-09-04 | 2025-09-04 | 456269 | 2078560 | 2534829 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29094 | W/500233692/WS | KwaZulu-Natal | NODINEKA JUNIOR SECONDARY SCHOOL | 500233692 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2016-09-27 | 2023-06-30 | 2024-06-30 | 2024-09-27 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29095 | W/500194990/WS | KwaZulu-Natal | MALAMBA PRIMARY SCHOOL | 500194990 | Abaqulusi | Tender | Active - Not Contracted | 2016-03-22 |  | 2026-03-29 |  |  | 0 | 726000 | 726000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29096 | W/500205609/WS | KwaZulu-Natal | MCATSHANGELWA PRIMARY SCHOOL | 500205609 | Mandeni | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2017-03-30 | 2022-06-30 | 2022-06-30 | 2023-06-30 | 1229562 | 5601338 | 6830900 | Education Infrastructure Grant | Upgrading and Additions
|  | 29097 | W/500195138/SDS | KwaZulu-Natal | MALANGA SENIOR PRIMARY SCHOOL | 500195138 | Mthonjaneni | Tender | Active - Contracted | 2016-04-01 |  | 2024-12-30 |  |  | 1172451 | 5341165 | 6513616 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29098 | W/500167943/UA | KwaZulu-Natal | ISIHLANGUSABASHA PRIMARY SCHOOL | 500167943 | eThekwini | Design | Active - Not Contracted | 2016-06-28 |  | 2024-07-27 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Upgrading and Additions
|  | 29099 | W/500196877/WS | KwaZulu-Natal | MANGQASHA PRIMARY SCHOOL | 500196877 | Okhahlamba | Design | Active - Not Contracted | 2016-02-09 |  | 2024-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29103 | W/500326858/WS | KwaZulu-Natal | NOJU SECONDARY SCHOOL | 500326858 | Nongoma | Tender | Active - Contracted | 2016-06-20 |  | 2026-10-26 |  |  | 356354 | 1696924 | 2053278 | Education Infrastructure Grant | Upgrading and Additions
|  | 29104 | W/500196951/WS | KwaZulu-Natal | MANGQWASHU PRIMARY SCHOOL | 500196951 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-02-26 | 2017-11-20 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 773448 | 3523487 | 4296935 | Education Infrastructure Grant | Upgrading and Additions
|  | 29106 | W/500197062/WS | KwaZulu-Natal | MANHLANHLE PRIMARY SCHOOL | 500197062 | Abaqulusi | Tender | Active - Not Contracted | 2016-03-23 |  | 2025-03-29 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29107 | W/500440596/WS | KwaZulu-Natal | OSUTHU PRIMARY SCHOOL | 500440596 | Msinga | Design | Active - Not Contracted | 2016-06-22 |  | 2023-03-30 |  |  | 548000 | 2495000 | 3043000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29108 | W/500209457/WS | KwaZulu-Natal | MGIDLA SECONDARY SCHOOL | 500209457 | Abaqulusi | Tender | Active - Not Contracted | 2016-06-22 |  | 2025-01-31 |  |  | 522000 | 2532000 | 3054000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29109 | W/500309949/WS | KwaZulu-Natal | manhlenga js | 500309949 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-03-23 | 2017-11-06 | 2023-03-29 | 2023-03-29 | 2025-03-29 | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29110 | DB/500441669/SDS | KwaZulu-Natal | LUBELO SECONDARY SCHOOL | 500441669 | Alfred Duma | Final Completion | Approved | 2016-06-06 | 2016-06-10 | 2023-06-13 | 2022-10-01 | 2023-12-05 | 427048 | 1606514 | 2033562 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29113 | W/500234136/WS | KwaZulu-Natal | NOKUBUSA PRIMARY SCHOOL | 500234136 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2017-02-23 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 517606 | 3351374 | 3868980 | Education Infrastructure Grant | Upgrading and Additions
|  | 29114 | W/500323861/WS | KwaZulu-Natal | MANKAYIYANA PRIMARY SCHOOL | 500323861 | Maphumulo | Final Completion | Active - Contracted | 2015-10-20 | 2017-09-12 | 2024-03-30 | 2023-06-30 | 2022-06-30 | 557359 | 2539081 | 3096440 | Education Infrastructure Grant | Upgrading and Additions
|  | 29115 | W/500447256/WS | KwaZulu-Natal | NTENESHANA PRIMARY SCHOOL | 500447256 | Msinga | Tender | Active - Contracted | 2015-03-17 |  | 2025-06-30 |  |  | 0 | 1516000 | 1516000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29118 | W/500499722/WS | KwaZulu-Natal | MANKULUMANE PRIMARY SCHOOL | 500499722 | Abaqulusi | Tender | Active - Not Contracted | 2016-03-21 |  | 2025-06-30 |  |  | 727125 | 3312460 | 4039585 | Education Infrastructure Grant | Upgrading and Additions
|  | 29120 | I/500188811/WS | KwaZulu-Natal | LUNGISILE PRIMARY SCHOOL | 500188811/WS | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2023-03-30 | 2022-10-01 | 2023-03-30 | 304000 | 3122000 | 3426000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29123 | DB/500270766/SDS | KwaZulu-Natal | SIYEZA PRIMARY SCHOOL | 500270766 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2020-03-06 | 2020-06-21 | 2023-10-01 | 2023-05-05 | 2025-03-04 | 1198426 | 5459494 | 6657920 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29124 | W/500441854/WS | KwaZulu-Natal | MANKUNZI PRIMARY SCHOOL | 500441854 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-02-16 |  | 2025-03-29 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29126 | W/500197395/WS | KwaZulu-Natal | MANQONDO PRIMARY SCHOOL | 500197395 | KwaDukuza | Tender | Active - Not Contracted | 2016-02-08 |  | 2023-04-26 |  |  | 392000 | 1867000 | 2259000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29127 | I/500415029/UA | KwaZulu-Natal | MABASO SECONDARY SCHOOL | 50015029 | Inkosi Langalibalele | On Hold | Approved | 2016-02-15 | 2019-10-01 | 2024-03-30 | 2026-03-30 | 2026-03-31 | 2500000 | 12500000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29129 | W/500197395/SDS | KwaZulu-Natal | MANQONDO PRIMARY SCHOOL | 500197395 | KwaDukuza | Tender | Active - Contracted | 2016-03-15 |  | 2025-06-30 |  |  | 336973 | 1535098 | 1872071 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29130 | W/500448366/WS | KwaZulu-Natal | NTILIKI PRIMARY SCHOOL | 500448366 | Umhlabuyalingana | On Hold | Active - Not Contracted | 2016-12-05 |  | 2024-06-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29131 | W/500187331/WS | KwaZulu-Natal | LOCKHAT SECONDARY SCHOOL | 500187331 | eThekwini | Practical Completion (100%) | Active - Contracted | 2014-01-05 | 2017-01-20 | 2022-05-28 | 2022-05-05 | 2023-03-04 | 427000 | 1947000 | 2374000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29132 | w/500338180/ws | KwaZulu-Natal | manqoba s | 500338180 | Msinga | Design | Active - Not Contracted | 2016-03-22 |  | 2024-03-29 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29133 | W/500197580/UA | KwaZulu-Natal | MANTULELA PRIMARY SCHOOL | 500197580 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2013-10-24 | 2014-08-15 | 2024-03-30 | 2023-06-30 | 2022-11-27 | 792000 | 3607000 | 4399000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29136 | I/500239834/UA | KwaZulu-Natal | NTILINGWE HIGH SCHOOL | 500239834 | Abaqulusi | Design | Active - Not Contracted | 2017-11-20 |  | 2023-07-29 |  |  | 4500000 | 20500000 | 25000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29139 | I/500189958/WS | KwaZulu-Natal | MABEKA PRIMARY SCHOOL | 500189958/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2023-03-31 | 2018-04-20 | 2023-03-31 | 48000 | 919000 | 967000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29140 | W/500147593/SDS | KwaZulu-Natal | GCININHLIZIYO PRIMARY SCHOOL | 500147593 | uMlalazi | Final Completion | Active - Contracted | 2016-03-01 |  | 2023-05-30 |  |  | 488560 | 2610574 | 3099134 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 29143 | I/500309135/WS | KwaZulu-Natal | MABHIDLA HIGH SCHOOL | 500309135/WS | Ulundi | Practical Completion (100%) | Approved | 2016-04-01 | 2021-05-10 | 2023-03-31 | 2022-10-01 | 2023-11-01 | 249300 | 1135700 | 1385000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29144 | DB/500136974/SDS | KwaZulu-Natal | ENHLANGWINI PRIMARY SCHOOL | 500136271 | Mfolozi | Final Completion | Approved | 2015-10-24 | 2016-12-20 | 2023-04-30 | 2022-05-20 | 2022-10-20 | 304878 | 1146922 | 1451800 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29145 | W/500141895/RRR | KwaZulu-Natal | ESTHER PAYNE SECONDARY SCHOOL | 500141895 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-27 | 2023-03-30 | 2019-03-29 | 2025-09-30 | 1937600 | 6055000 | 7992600 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29146 | W/500240426/WS | KwaZulu-Natal | NTSHANGASE PRIMARY SCHOOL | 500240426 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-09-01 |  | 2023-03-29 |  |  | 0 | 639000 | 639000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29147 | W/500299404/RRR | KwaZulu-Natal | ZEMBENI SENIOR PRIMARY SCHOOL | 500299404 | Umdoni | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-01 | 2025-03-31 | 2018-03-30 | 2025-03-31 | 2027000 | 9234000 | 11261000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29149 | I/500190032/CU | KwaZulu-Natal | MABHILA INTERMEDIATE SCHOOL | 500190032 | eThekwini | Design | Approved | 2016-04-01 |  | 2024-03-30 |  |  | 4500000 | 27318000 | 31818000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29150 | W/500240537/WS | KwaZulu-Natal | NTSHIDI P | 500240537 | uMlalazi | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-29 |  |  | 120000 | 573000 | 693000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29153 | W/500197802/SDS | KwaZulu-Natal | MANYONI PRIMARY SCHOOL | 500197802 | Nongoma | Design | Active - Contracted | 2017-04-01 |  | 2024-03-08 |  |  | 2095281 | 9545167 | 11640448 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29154 | DB/500191364/SDS | KwaZulu-Natal | Madonela P | 500191364 | Umhlabuyalingana | Project Initiation | Active - Not Contracted | 2016-04-01 |  | 2027-06-10 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29155 | W/500239501/WS | KwaZulu-Natal | NTATHAKUSA PRIMARY SCHOOL | 500239501 | Ndwedwe | Construction 76% - 99% | Active - Contracted | 2016-06-13 |  | 2025-05-31 |  |  | 824270 | 3755007 | 4579277 | Education Infrastructure Grant | Upgrading and Additions
|  | 29160 | DB/500490583/WS | KwaZulu-Natal | SIPHIWAYINKOSI PRIMARY SCHOOL | 500490583 | uMhlathuze | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 270000 | 330000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29161 | W/500240574/WS | KwaZulu-Natal | NTSHISHILI PRIMARY SCHOOL | 500240574 | Msinga | Practical Completion (100%) | Active - Contracted | 2017-02-11 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 549000 | 2501000 | 3050000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29162 | W/500342768/SDS | KwaZulu-Natal | MMOYENI JUNIOR PRIMARY SCHOOL | 500342768 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-04-01 |  | 2023-03-13 |  |  | 1922000 | 3322000 | 5244000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29163 | W/500168831/WS | KwaZulu-Natal | ISIQULWANE PRIMARY SCHOOL | 500168831 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-01-20 | 2017-03-20 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 618384 | 2817085 | 3435469 | Education Infrastructure Grant | Upgrading and Additions
|  | 29164 | I/500192400/WS | KwaZulu-Natal | MAGODA PRIMARY SCHOOL | 500192400 | Richmond | Practical Completion (100%) | Approved | 2016-06-06 | 2021-01-21 | 2023-03-30 | 2022-10-01 | 2023-02-01 | 320400 | 1510600 | 1831000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29169 | DB/500112850/WS | KwaZulu-Natal | BUBU PRIMARY SCHOOL | 500112850 | Umvoti | Design | Active - Contracted | 2016-06-14 |  | 2024-03-25 |  |  | 500000 | 1200000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29170 | I/500192770/WS | KwaZulu-Natal | MAGUTSHWA HIGH SCHOOL | 500192770 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-04-04 | 2016-06-23 | 2024-03-31 | 2017-10-30 | 2024-03-31 | 2030428 | 11699131 | 13729559 | Education Infrastructure Grant | Upgrading and Additions
|  | 29174 | W/500181707/SDS | KwaZulu-Natal | KWAMSHAYA PRIMARY SCHOOL | 500181707 | Mtubatuba | Tender | Active - Contracted | 2017-04-01 |  | 2025-11-29 |  |  | 854522 | 3892823 | 4747345 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29175 | W/500169127/RRR | KwaZulu-Natal | ISMONT SECONDARY SCHOOL | 500169127 | uMngeni | Design | Active - Not Contracted | 2016-07-03 |  | 2024-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29178 | W/500240648/WS | KwaZulu-Natal | NTSHIYANGIBONE PRIMARY SCHOOL | 500240648 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-11-20 |  | 2024-08-29 |  |  | 389086 | 1852788 | 2241874 | Education Infrastructure Grant | Upgrading and Additions
|  | 29179 | W/500326155/WS | KwaZulu-Natal | NTSONYANE PRIMARY SCHOOL | 500326155 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-12-05 |  | 2023-06-30 |  |  | 735849 | 3352202 | 4088051 | Education Infrastructure Grant | Upgrading and Additions
|  | 29180 | I/500240796/WS | KwaZulu-Natal | NTSWALAKAHLA SP | 500240796 | Abaqulusi | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2021-03-01 | 2024-03-31 | 2024-08-15 | 2024-09-05 | 233820 | 1065180 | 1299000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29181 | W/500245125/UA | KwaZulu-Natal | OTIMATI PRIMARY SCHOOL | 500245125 | Maphumulo | Design | Active - Not Contracted | 2016-06-30 |  | 2024-03-30 |  |  | 757000 | 3454000 | 4211000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29182 | W/500245125/WS | KwaZulu-Natal | OTIMATI PRIMARY SCHOOL | 500245125 | Maphumulo | Tender | Active - Contracted | 2016-06-30 |  | 2025-03-30 |  |  | 1418085 | 6460163 | 7878248 | Education Infrastructure Grant | Upgrading and Additions
|  | 29185 | W/500245384/WS | KwaZulu-Natal | OUTFALL PRIMARY SCHOOL | 500245384 | Endumeni | On Hold | Active - Not Contracted | 2016-06-30 |  | 2024-03-30 |  |  | 38000 | 172000 | 210000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29186 | W/500240907/SDS | KwaZulu-Natal | NTUMBENI PRIMARY SCHOOL | 500240904 | Mthonjaneni | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 654280 | 2980607 | 3634887 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29188 | W/500241129/SDS | KwaZulu-Natal | NTWELA PRIMARY SCHOOL | 500214129 | eThekwini | Tender | Active - Contracted | 2016-04-01 |  | 2025-03-30 |  |  | 880727 | 4012203 | 4892930 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29189 | W/500234432/WS | KwaZulu-Natal | NOMAGEJE PRIMARY SCHOOL | 500234432 | Umzumbe | Tender | Active - Contracted | 2016-06-21 |  | 2025-06-30 |  |  | 1158000 | 5277000 | 6435000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29191 | W/500241277/WS | KwaZulu-Natal | NWABI SECONDARY SCHOOL | 500241277 | eThekwini | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 697740 | 3178591 | 3876331 | Education Infrastructure Grant | Upgrading and Additions
|  | 29192 | W/500245717/WS | KwaZulu-Natal | OZWATHINI PRIMARY SCHOOL | 500245717 | Ndwedwe | On Hold | Active - Not Contracted | 2016-06-24 | 2021-02-26 | 2023-05-31 | 2023-03-30 | 2023-04-01 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29194 | W/500234469/WS | KwaZulu-Natal | NOMAHAYE PRIMARY SCHOOL | 500234469 | Msinga | Tender | Active - Contracted | 2016-02-20 |  | 2026-06-30 |  |  | 0 | 3230000 | 3230000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29195 | W/500311725/WS | KwaZulu-Natal | NOMAQONI JUNIOR SECONDARY SCHOOL | 500311725 | uMlalazi | Tender | Active - Contracted | 2015-12-20 |  | 2026-03-30 |  |  | 344000 | 1637000 | 1981000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29196 | W/500440448/WS | KwaZulu-Natal | NOMAQULU PRIMARY SCHOOL | 500440448 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-01-20 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 300000 | 2314000 | 2614000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29197 | W/500343508/WS | KwaZulu-Natal | NOMASHAKA PRIMARY SCHOOL | 500343508 | Msinga | Design | Active - Not Contracted | 2016-02-20 |  | 2024-06-30 |  |  | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29198 | W/500245754/WS | KwaZulu-Natal | OZWENI PRIMARY SCHOOL | 500245754 | uPhongolo | Tender | Active - Contracted | 2016-06-30 |  | 2025-05-25 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29199 | W/500245939/WS | KwaZulu-Natal | PALMIET PRIMARY SCHOOL (KOKSTAD) | 500245939 | eThekwini | On Hold | Active - Not Contracted | 2016-06-24 | 2021-02-26 | 2023-04-01 | 2023-03-01 | 2023-04-01 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29200 | W/500334110/WS | KwaZulu-Natal | PANO SECONDARY SCHOOL | 500334110 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-23 | 2019-02-01 | 2023-03-11 | 2020-03-31 | 2023-05-31 | 587000 | 2672000 | 3259000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29201 | W/500118887/WS | KwaZulu-Natal | CUNGCWANA PRIMARY SCHOOL | 500118887 | Nkandla | Tender | Active - Contracted | 2016-06-29 |  | 2026-10-29 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29203 | W/500246679/RRR | KwaZulu-Natal | PAULPIETERSBURG PRIMARY SCHOOL (DUMBE) | 500246679 | eDumbe | Feasibility | Active - Not Contracted | 2016-06-24 |  | 2023-06-24 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29205 | W/500246679/WS | KwaZulu-Natal | PAULPIETERSBURG PRIMARY SCHOOL (DUMBE) | 500246679 | eDumbe | On Hold | Active - Not Contracted | 2016-06-23 |  | 2024-03-30 |  |  | 1000000 | 2980000 | 3980000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29206 | W/500247197/WS | KwaZulu-Natal | PETEZI PRIMARY SCHOOL | 500247197 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2016-06-30 |  | 2024-06-30 |  |  | 964476 | 4393724 | 5358200 | Education Infrastructure Grant | Upgrading and Additions
|  | 29208 | W/500247493/WS | KwaZulu-Natal | PHAMBELA PRIMARY SCHOOL | 500247493 | Ndwedwe | Construction 51% - 75% | Active - Contracted | 2016-06-22 |  | 2023-06-30 |  |  | 1047000 | 4769000 | 5816000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29210 | W/500247937/WS | KwaZulu-Natal | PHATHENI PRIMARY SCHOOL | 500247937 | Richmond | Design | Active - Contracted | 2016-06-23 |  | 2023-04-30 |  |  | 845000 | 3850000 | 4695000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29211 | W/500248233/WS | KwaZulu-Natal | PHEMBUMUZI PRIMARY SCHOOL | 500248233 | Nongoma | Tender | Active - Contracted | 2016-06-20 |  | 2026-12-20 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29212 | DB/500248270/WS | KwaZulu-Natal | PHENDUKA PRIMARY SCHOOL | 500248270 | Msinga | Design | Active - Contracted | 2016-06-24 |  | 2025-03-11 |  |  | 551000 | 2510000 | 3061000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29213 | ET/500323676/WS | KwaZulu-Natal | KHULAMBEDU JUNIOR PRIMARY SCHOOL | 500323676 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2019-06-22 | 2019-09-10 | 2023-06-30 | 2025-10-24 | 2025-04-30 | 767290 | 3495431 | 4262721 | Education Infrastructure Grant | Upgrading and Additions
|  | 29214 | W/500427609/WS | KwaZulu-Natal | NYAKA JUNIOR SECONDARY SCHOOL | 500427609 | Ubuhlebezwe | Tender | Active - Contracted | 2016-04-01 |  | 2025-08-31 |  |  | 1125122 | 5125557 | 6250679 | Education Infrastructure Grant | Upgrading and Additions
|  | 29215 | W/500185000/RRR | KwaZulu-Natal | LALELANI PRIMARY SCHOOL | 500185000 | eThekwini | Feasibility | Active - Contracted | 2016-06-22 |  | 2024-11-22 |  |  | 1321155 | 6018595 | 7339750 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29216 | ET/500323713/WS | KwaZulu-Natal | INKOLOVUZANE PRIMARY SCHOOL | 500323713 | Maphumulo | Final Completion | Approved | 2018-06-12 | 2019-09-10 | 2022-04-30 | 2020-12-30 | 2023-06-30 | 728344 | 3318012 | 4046356 | Education Infrastructure Grant | Upgrading and Additions
|  | 29217 | W/500103896/WS | KwaZulu-Natal | ASIBAMBISANE PRIMARY SCHOOL | 500103896 | Nqutu | Final Completion | Active - Contracted | 2016-06-24 | 2017-05-01 | 2023-02-28 | 2024-03-31 | 2024-03-31 | 709948 | 3234206 | 3944154 | Education Infrastructure Grant | Upgrading and Additions
|  | 29218 | W/500248973/WS | KwaZulu-Natal | PHIWAMANDLA SECONDARY SCHOOL | 500248973 | Mtubatuba | Tender | Active - Contracted | 2016-07-14 |  | 2025-06-30 |  |  | 791000 | 3603000 | 4394000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29219 | W/500241388/UA | KwaZulu-Natal | Nyakana Combined Primary School | 500241388 | KwaDukuza | Design | Active - Not Contracted | 2017-04-01 |  | 2024-03-30 |  |  | 1440000 | 6560000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29221 | C/500249380/UA | KwaZulu-Natal | PHOLELA SPECIAL SCHOOL | W/500448921/WS | Dr Nkosazana Dlamini Zuma | Construction 76% - 99% | Active - Contracted | 2016-06-01 | 2019-01-01 | 2023-12-01 | 20123-02-01 | 2023-04-01 | 6800000 | 20500000 | 27300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29222 | W/500338032/WS | KwaZulu-Natal | PHOWANE PRIMARY SCHOOL | 500338032 | Msinga | Tender | Active - Contracted | 2016-06-03 |  | 2026-06-30 |  |  | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29223 | W/500249750/WS | KwaZulu-Natal | PHUMANYOVA SECONDARY SCHOOL | 500249750 | Nongoma | Tender | Active - Not Contracted | 2016-06-16 |  | 2023-06-30 |  |  | 432000 | 2622085 | 3054085 | Education Infrastructure Grant | Upgrading and Additions
|  | 29224 | W/500443334/NS | KwaZulu-Natal | DLILANGA HIGH SCHOOL | 500443334 | Umhlabuyalingana | Construction 1% - 25% | Active - Contracted | 2016-06-28 |  | 2024-03-30 |  |  | 1500000 | 4800000 | 6300000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29225 | W/500241462/WS | KwaZulu-Natal | NYALAZI PRIMARY SCHOOL | 500241462 | Umhlabuyalingana | Tender | Active - Contracted | 2017-02-02 |  | 2026-06-30 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29226 | W/500440633/SDS | KwaZulu-Natal | PHUMELA PRIMARY SCHOOL | 500440633 | Msinga | Design | Active - Not Contracted | 2016-06-28 |  | 2025-06-28 |  |  | 2517840 | 11470161 | 13988001 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29228 | W/500249824/WS | KwaZulu-Natal | PHUMELELANI PRIMARY SCHOOL | 500249824 | Inkosi Langalibalele | Design | Active - Not Contracted | 2016-06-17 |  | 2024-05-31 |  |  | 742000 | 3380000 | 4122000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29229 | W/500179746/SDS | KwaZulu-Natal | KWAHLONGWA PRIMARY SCHOOL | 500179746 | Umzumbe | Project Initiation | Proposed | 2016-02-05 |  | 2024-01-26 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29230 | W/500179709/SDS | KwaZulu-Natal | KWAGWEGWE PRIMARY SCHOOL | 500179709 | eThekwini | Tender | Active - Contracted | 2017-03-12 |  | 2025-11-20 |  |  | 162000 | 934000 | 1096000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29232 | DB/500179635/SDS | KwaZulu-Natal | KWAGUMBI PRIMARY SCHOOL | 500179635 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2020-02-03 | 2023-10-31 | 2023-09-30 | 2027-10-29 | 1221996 | 5566871 | 6788867 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29233 | CDC/500165390/ECD | KwaZulu-Natal | INQANULA P | 500165390 | Umdoni | Practical Completion (100%) | Active - Contracted | 2015-12-11 | 2015-12-23 | 2023-12-01 | 2018-02-02 | 2024-06-13 | 529000 | 2414000 | 2943000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29237 | I/500171273/WS | KwaZulu-Natal | JIKAZA PRIMARY SCHOOL | 500171273 | Ulundi | Construction 76% - 99% | Active - Contracted | 2015-10-24 | 2016-06-27 | 2023-03-31 | 2018-03-11 | 2023-03-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29238 | DB/500177082/SDS | KwaZulu-Natal | KONFOOR HIGH SCHOOL | 500176120 | Ulundi | Project Initiation | Active - Not Contracted | 2015-01-06 |  | 2025-11-10 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29241 | W/500239390/WS | KwaZulu-Natal | NTANYANDLOVU PRIMARY SCHOOL | 500239390 | Msinga | Tender | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 3000000 | 1168000 | 4168000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29245 | W/500241573/WS | KwaZulu-Natal | NYANDA PRIMARY SCHOOL | 500241573 | The Msunduzi | Tender | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 863460 | 3933541 | 4797001 | Education Infrastructure Grant | Upgrading and Additions
|  | 29247 | W/500241869/WS | KwaZulu-Natal | NYONI PRIMARY SCHOOL | 500241869 | eThekwini | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2016-04-11 | 2023-09-11 | 2023-04-11 | 2023-04-11 | 500000 | 2661000 | 3161000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29248 | W/500241943/WS | KwaZulu-Natal | NYONIYEZWE SECONDARY SCHOOL | 500241943 | Msinga | Practical Completion (100%) | Active - Contracted | 2021-01-02 | 2021-11-01 | 2023-01-11 | 2023-02-04 | 2023-06-30 | 412000 | 1875000 | 2287000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29250 | W/500312169/SDS | KwaZulu-Natal | KWACUBELA INTERMIDIATE SCHOOL | 500312169 | Mpofana | Project Initiation | Proposed | 2015-11-20 |  | 2024-03-30 |  |  | 600000 | 2000000 | 2600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29251 | W/500242128/WS | KwaZulu-Natal | NZOBO PRIMARY SCHOOL | 500242128 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2017-01-02 |  | 2023-06-30 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29252 | W/500242387/WS | KwaZulu-Natal | OBIVANE COMBINED SCHOOL | 500242387 | Abaqulusi | Tender | Active - Contracted | 2017-11-20 |  | 2026-03-30 |  |  | 0 | 2450000 | 2450000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29253 | DB/500427350/WS | KwaZulu-Natal | NOKHWEZI SENIOR PRIMARY SCHOOL | 500427350 | Umzimkhulu | Design | Active - Contracted | 2015-04-01 |  | 2024-03-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29255 | C/500235443/ECD | KwaZulu-Natal | NOMANDLA PRIMARY SCHOOL | 500235443 | Ubuhlebezwe | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2022-03-31 | 2024-04-20 | 2023-07-31 | 2024-12-20 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29257 | C/500235579/LSEN | KwaZulu-Natal | NOMGOMA INTERMEDIATE | 500235579 | Nongoma | Design | Active - Not Contracted | 2014-04-01 |  | 2026-04-20 |  |  | 4166000 | 18981000 | 23147000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29259 | W/500242868/WS | KwaZulu-Natal | OGADE PRIMARY SCHOOL | 500242868 | Okhahlamba | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29260 | W/500243349/WS | KwaZulu-Natal | OKHALWENI PRIMARY SCHOOL | 500243312 | Newcastle | Design | Active - Not Contracted | 2015-11-20 |  | 2024-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29261 | W/500243460/WS | KwaZulu-Natal | OKHOMBE PRIMARY SCHOOL | 500243460 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 681000 | 3242000 | 3923000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29262 | W/500243534/WS | KwaZulu-Natal | OKHUKHO PRIMARY SCHOOL | 500243534 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2026-05-30 |  |  | 522000 | 3439643 | 3961643 | Education Infrastructure Grant | Upgrading and Additions
|  | 29264 | W/500243867/WS | KwaZulu-Natal | ONGOYE PRIMARY SCHOOL | 500243867 | Mthonjaneni | On Hold | Active - Contracted | 2016-04-01 | 2016-04-22 | 2023-03-30 | 2018-02-15 | 2023-02-23 | 2153200 | 9808840 | 11962040 | Education Infrastructure Grant | Upgrading and Additions
|  | 29265 | W/500243941/WS | KwaZulu-Natal | ONINGENI PRIMARY SCHOOL | 500243941 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-02-01 | 2018-02-28 | 2024-03-30 | 2023-06-30 | 2022-11-20 | 712216 | 3244540 | 3956756 | Education Infrastructure Grant | Upgrading and Additions
|  | 29266 | W/500244052/WS | KwaZulu-Natal | OPHATHE PRIMARY SCHOOL | 500244052 | Msinga | On Hold | Active - Not Contracted | 2017-03-06 |  | 2023-03-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29267 | W/500244348/WS | KwaZulu-Natal | OPHUZANE PRIMARY SCHOOL | 500244348 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29268 | W/500244422/WS | KwaZulu-Natal | OQAQENI PRIMARY SCHOOL | 500244422 | uMngeni | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 760000 | 3460000 | 4220000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29269 | W/500244829/WS | KwaZulu-Natal | OSINGISINGINI PRIMARY SCHOOL | 500244829 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 522000 | 2989272 | 3511272 | Education Infrastructure Grant | Upgrading and Additions
|  | 29270 | W/500244866/WS | KwaZulu-Natal | OSIZWENI PRIMARY SCHOOL | 50244866 | KwaDukuza | On Hold | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29274 | I/500239834/WS | KwaZulu-Natal | NTILINGWE HIGH SCHOOL | 500239834 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 |  | 2023-03-30 |  |  | 146000 | 664000 | 810000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29276 | DB/500182928/WS | KwaZulu-Natal | KWAPHAWENI PRIMARY SCHOOL | 500182928 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2010-11-12 | 2017-05-20 | 2023-01-30 | 2024-05-05 | 2025-06-20 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29277 | W/500312687/WS | KwaZulu-Natal | NTANDOYETHU PRIMARY SCHOOL | 500312687 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 0 | 2178000 | 2178000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29279 | W/500228845/SDS | KwaZulu-Natal | NGQOKWANE HIGH SCHOOL | 500228845 | Maphumulo | Design | Active - Not Contracted | 2017-09-15 |  | 2024-03-08 |  |  | 1300000 | 2700000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29280 | W/500239316/WS | KwaZulu-Natal | NTANDO PRIMARY SCHOOL | 500239316 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-02-23 | 2025-05-31 | 2025-02-28 | 2025-04-30 | 660992 | 3834008 | 4495000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29282 | DB/500230547/SDS | KwaZulu-Natal | NHLOYANA HIGH SCHOOL | 500230547 | Mthonjaneni | Final Completion | Approved | 2016-06-24 | 2018-01-15 | 2023-03-27 | 2023-06-30 | 2025-06-30 | 1009739 | 4599921 | 5609660 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29284 | W/500234876/WS | KwaZulu-Natal | NOMBUSO SECONDARY SCHOOL | 500234876 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-24 |  | 2023-05-31 |  |  | 508520 | 2316591 | 2825111 | Education Infrastructure Grant | Upgrading and Additions
|  | 29285 | W/500213897/WS | KwaZulu-Natal | NOMDUMO PRIMARY SCHOOL | 500213897 | uMlalazi | Design | Active - Contracted | 2015-11-20 |  | 2024-06-30 |  |  | 1000000 | 2549000 | 3549000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29287 | W/500235098/WS | KwaZulu-Natal | NOMTSHILO PRIMARY SCHOOL | 500235098 | Okhahlamba | Practical Completion (100%) | Approved | 2017-02-20 | 2018-04-27 | 2024-03-30 | 2023-06-30 | 2022-05-29 | 288807 | 2064193 | 2353000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29289 | W/500235135/SDS | KwaZulu-Natal | NOMUWA PRIMARY SCHOOL | 500235135 | Mfolozi | Final Completion | Active - Contracted | 2016-06-24 |  | 2023-03-30 |  |  | 466948 | 2127205 | 2594153 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29290 | W/500206904/WS | KwaZulu-Natal | MEADOWSWEET COMBINED SCHOOL | 500206904 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-24 | 2017-02-23 | 2023-03-31 | 2019-02-28 | 2023-03-31 | 285714 | 1664286 | 1950000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29291 | W/500235246/WS | KwaZulu-Natal | NOMZINTO HIGH SCHOOL | 500235246 | Nongoma | Tender | Active - Contracted | 2015-11-20 |  | 2025-03-30 |  |  | 801406 | 3650850 | 4452256 | Education Infrastructure Grant | Upgrading and Additions
|  | 29292 | I/500242979/WS | KwaZulu-Natal | OGEDLENI PRIMARY SCHOOL | 500242979 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-20 | 2023-03-31 | 2018-02-15 | 2023-03-31 | 234000 | 1067000 | 1301000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29294 | I/500235357/UA | KwaZulu-Natal | NONDUMISO SECONDARY SCHOOL | 500235357 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-23 | 2017-01-17 | 2023-10-27 | 2017-12-29 | 2023-03-30 | 840600 | 3829400 | 4670000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29295 | I/500286306/CU | KwaZulu-Natal | OHLANGE SECONDARY SCHOOL | 500286306 | eThekwini | Design | Active - Contracted | 2016-04-30 |  | 2023-03-31 |  |  | 3600000 | 45331000 | 48931000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29296 | W/500235505/SDS | KwaZulu-Natal | NONGAMLANA HIGH SCHOOL | 500235505 | Nkandla | Tender | Active - Not Contracted | 2016-06-23 |  | 2025-03-30 |  |  | 500000 | 1000000 | 1500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29297 | DB/500197284/SDS | KwaZulu-Natal | MANQAMU HIGH SCHOOL | 500197284 | Mfolozi | Feasibility | Active - Not Contracted | 2016-05-25 |  | 2024-06-25 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29298 | DB/500198172/SDS | KwaZulu-Natal | MANZIMHLOPHE HIGH SCHOOL | 500198172 | Mthonjaneni | Design | Active - Not Contracted | 2016-06-21 |  | 2024-03-30 |  |  | 476509 | 2170765 | 2647274 | Education Infrastructure Grant | Upgrading and Additions
|  | 29301 | I/500243793/WS | KwaZulu-Natal | OMBIMBINI PRIMARY SCHOOL | 500243793 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-05-01 | 2023-11-18 | 2019-06-15 | 2023-11-18 | 502000 | 2788000 | 3290000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29304 | I/500245828/WS | KwaZulu-Natal | PADDAFONTEIN C | I/500245828/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-04-30 | 2023-03-31 | 2018-05-30 | 2024-03-31 | 213000 | 972000 | 1185000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29305 | W/500126096/WS | KwaZulu-Natal | EBHETHANI PRIMARY SCHOOL | 500126096 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2017-03-01 | 2024-09-30 | 2022-01-30 | 2024-09-30 | 780000 | 3551000 | 4331000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29306 | W/500126207/WS | KwaZulu-Natal | EBOYENI PRIMARY SCHOOL | 500126207 | Okhahlamba | Tender | Active - Contracted | 2015-11-20 |  | 2024-09-01 |  |  | 772989 | 3521396 | 4294385 | Education Infrastructure Grant | Upgrading and Additions
|  | 29307 | DB/500440448/SDS | KwaZulu-Natal | NOMAQHULU PRIMARY SCHOOL | 500440448 | Msinga | Feasibility | Active - Contracted | 2015-05-25 |  | 2024-07-05 |  |  | 284940 | 1298000 | 1582940 | Education Infrastructure Grant | Upgrading and Additions
|  | 29308 | W/500126281/WS | KwaZulu-Natal | EBUHLEBEMFUNDO PRIMARY SCHOOL | 500126281 | Msinga | Tender | Active - Not Contracted | 2015-11-20 |  | 2028-03-30 |  |  | 0 | 2633000 | 2633000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29311 | DB/500126577/WS | KwaZulu-Natal | ECHAMENI PRIMARY SCHOOL | 500126577 | uMshwathi | Design | Active - Contracted | 2016-06-23 |  | 2025-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29312 | W/500126725/SDS | KwaZulu-Natal | EDAKENI PRIMARY SCHOOL | 500126725 | uMlalazi | Final Completion | Active - Contracted | 2016-06-21 | 2019-05-30 | 2023-04-30 | 2024-03-31 | 2024-05-31 | 583926 | 2660108 | 3244034 | Education Infrastructure Grant | Upgrading and Additions
|  | 29314 | W/500127095/SDS | KwaZulu-Natal | EFFINGHAM SECONDARY SCHOOL | 500127095 | eThekwini | Design | Active - Not Contracted | 2016-06-23 |  | 2023-10-31 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29316 | W/500127613/WS | KwaZulu-Natal | EHLANZENI INTERMEDIATE SCHOOL | 500127613 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2020-10-30 | 2023-06-30 | 2023-10-30 | 2024-10-30 | 688737 | 3137581 | 3826318 | Education Infrastructure Grant | Upgrading and Additions
|  | 29317 | W/500127798/WS | KwaZulu-Natal | EKHAMANZI PRIMARY SCHOOL | 500127798 | uMshwathi | Tender | Active - Contracted | 2016-06-21 |  | 2024-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29318 | DB/500133126/WS | KwaZulu-Natal | EKHOMBE PRIMARY SCHOOL | 500133126 | Nkandla | Tender | Active - Contracted | 2016-11-20 |  | 2025-03-25 |  |  | 0 | 3097000 | 3097000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29319 | DB/500239057/SDS | KwaZulu-Natal | NTABENDE SECONDARY SCHOOL | 500239057 | The Msunduzi | Feasibility | Active - Not Contracted | 2016-06-22 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29320 | W/500128020/WS | KwaZulu-Natal | EKHOMBELA PRIMARY SCHOOL | 500128020 | eDumbe | Construction 76% - 99% | Active - Contracted | 2016-11-20 | 2022-06-30 | 2023-06-30 | 2024-06-30 | 2025-06-30 | 0 | 902000 | 902000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29322 | W/500128612/WS | KwaZulu-Natal | EKUJULUKENI PRIMARY SCHOOL | 500128612 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2020-07-30 | 2022-06-30 | 2023-10-10 | 2024-10-10 | 987240 | 4497427 | 5484667 | Education Infrastructure Grant | Upgrading and Additions
|  | 29323 | W/500057393/SDS | KwaZulu-Natal | EKUNGOBENI PRIMRY SCHOOL | 500057393 | Maphumulo | Tender | Active - Not Contracted | 2016-06-24 |  | 2024-04-30 |  |  | 600000 | 2000000 | 2600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29325 | DB/500247012/SDS | KwaZulu-Natal | PENZANCE PRIMARY SCHOOL | 500247012 | eThekwini | Feasibility | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 300000 | 1662000 | 1962000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29326 | W/500238983/SDS | KwaZulu-Natal | NTABASUKA SECONDARY SCHOOL | 500238983 | Ulundi | Tender | Active - Not Contracted | 2017-06-13 |  | 2023-03-30 |  |  | 980000 | 4466000 | 5446000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29327 | W/500238872/SDS | KwaZulu-Natal | NTABANTUZUMA SECONDARY SCHOOL | 500238872 | Mthonjaneni | Design | Active - Not Contracted | 2016-06-13 |  | 2023-07-31 |  |  | 48600 | 532733 | 581333 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29328 | W/500238835/WS | KwaZulu-Natal | NTABAMHLOPHE PRIMARY SCHOOL | 500238835 | Inkosi Langalibalele | Design | Active - Not Contracted | 2016-06-13 |  | 2024-06-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29330 | IDT/500327746/WS | KwaZulu-Natal | NTABABUSUKU JUNIOR SECONDARY | 500327746 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-13 |  | 2024-02-11 |  |  | 245000 | 1817000 | 2062000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29331 | W/500238650/SDS | KwaZulu-Natal | NSUZE PRIMARY SCHOOL | 500238650 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-02-03 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 3872012 | 4721966 | 8593978 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29333 | W/500238317/WS | KwaZulu-Natal | NSONGANSONGA PRIMARY SCHOOL | 50023831 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 1165293 | 5308557 | 6473850 | Education Infrastructure Grant | Upgrading and Additions
|  | 29335 | W/500238095/WS | KwaZulu-Natal | NSIKAYEZWE SENIOR PRIMARY SCHOOL | 500238095 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 1024764 | 4879829 | 5904593 | Education Infrastructure Grant | Upgrading and Additions
|  | 29336 | W/500325637/WS | KwaZulu-Natal | NSIKAYEMPILO PRIMARY SCHOOL | 500325637 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29337 | W/500237873/WS | KwaZulu-Natal | NSETHENI INTERMEDIATE SCHOOL | 500237873 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-02-01 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 662000 | 3014000 | 3676000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29338 | W/500441595/WS | KwaZulu-Natal | NQUTSHINI PRIMARY SCHOOL | 500441595 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-05-01 | 2023-03-30 | 2024-03-31 | 2024-03-31 | 593270 | 2702673 | 3295943 | Education Infrastructure Grant | Upgrading and Additions
|  | 29339 | W/500237688/ECD | KwaZulu-Natal | NQUTSHINI PRIMARY SCHOOL | 500441595 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-09-18 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 242000 | 1105000 | 1347000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29340 | W/500237577/WS | KwaZulu-Natal | NQUNDU COMBINED SCHOOL | 500237577 | Nkandla | Construction 51% - 75% | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 389824 | 1856304 | 2246128 | Education Infrastructure Grant | Upgrading and Additions
|  | 29341 | W/500311244/WS | KwaZulu-Natal | NQOBIZITHA HIGH SCHOOL | 500311244 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2025-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29342 | W/500237392/WS | KwaZulu-Natal | NQOBANE PRIMARY SCHOOL | 500237392 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 |  | 2023-09-11 |  |  | 924909 | 4213473 | 5138382 | Education Infrastructure Grant | Upgrading and Additions
|  | 29343 | W/500237355/WS | KwaZulu-Natal | NQIWANENI PRIMARY SCHOOL | 500237355 | Mtubatuba | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29344 | W/500309468/WS | KwaZulu-Natal | W/NQAMANA JUNIOR SECONDARY SCHOOL | 500309468 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 537212 | 2447298 | 2984510 | Education Infrastructure Grant | Upgrading and Additions
|  | 29345 | W/500237244/UA | KwaZulu-Natal | NQAKATHELA SECONDARY SCHOOL | 500237244 | Ndwedwe | Design | Active - Not Contracted | 2016-06-13 |  | 2024-06-29 |  |  | 1125000 | 5123000 | 6248000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29347 | W/500236911/WS | KwaZulu-Natal | NOVIMBA PRIMARY SCHOOL | 500236911 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29349 | DB/500203648/SDS | KwaZulu-Natal | MBAMBANGWE HIGH SCHOOL | 500203648 | eThekwini | Final Completion | Approved | 2016-04-01 | 2018-04-04 | 2023-08-21 | 2023-06-30 | 2025-06-30 | 1221152 | 5563025 | 6784177 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29354 | W/500255226/WS | KwaZulu-Natal | RHEIBOKSPRUIT PRIMARY SCHOOL | 500255226 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-04-27 | 2023-03-30 | 2018-09-01 | 2023-05-31 | 645000 | 2941000 | 3586000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29355 | DB/500248862/SDS | KwaZulu-Natal | PHINDIZWE HIGH SCHOOL | 500248862 | Nkandla | Feasibility | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29356 | DB/500428275/SDS | KwaZulu-Natal | ST PATRICKS JUNIOR SECONDARY SCHO | 500428275 | Dr Nkosazana Dlamini Zuma | Feasibility | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29357 | W/500427831/WS | KwaZulu-Natal | RIETVLEI JUNIOR SECONDARY SCHOOL | 500427831 | Umzimkhulu | Tender | Active - Contracted | 2016-04-01 |  | 2026-06-30 |  |  | 1101024 | 5015775 | 6116799 | Education Infrastructure Grant | Upgrading and Additions
|  | 29358 | W/500255041/WS | KwaZulu-Natal | REICHENAU PRIMARY SCHOOL | 500255041 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 425000 | 2025000 | 2450000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29360 | W/500254819/SDS | KwaZulu-Natal | RANTJIESVLAKTE PRIMARY SCHOOL | 500254819 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2016-04-01 | 2021-02-26 | 2023-06-28 | 2022-02-28 | 2023-04-01 | 699291 | 3815737 | 4515028 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29361 | W/500255929/WS | KwaZulu-Natal | RIVERDALE PRIMARY SCHOOL | 500255929 | Inkosi Langalibalele | Design | Active - Not Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 54000 | 2089 | 56089 | Education Infrastructure Grant | Upgrading and Additions
|  | 29363 | W/500288748/RRR | KwaZulu-Natal | UMQHELE SECONDARY SCHOOL | 500288748 | eThekwini | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 2016000 | 9184000 | 11200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29365 | W/500129130/SDS | KwaZulu-Natal | EKUTHULENI PRIMARY SCHOOL | 500129130 | Mthonjaneni | Tender | Active - Not Contracted | 2016-06-22 |  | 2023-06-30 |  |  | 808200 | 3681800 | 4490000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29366 | W/500401191/SDS | KwaZulu-Natal | EKUTHUTHUKENI S | 500401191 | Nqutu | Tender | Active - Contracted | 2015-11-20 |  | 2023-08-26 |  |  | 362697 | 2174798 | 2537495 | Education Infrastructure Grant | Upgrading and Additions
|  | 29367 | W/500129352/WS | KwaZulu-Natal | EKWAKHENI PRIMARY SCHOOL | 500129352 | Mtubatuba | Tender | Active - Contracted | 2016-06-21 |  | 2023-03-30 |  |  | 712216 | 3244540 | 3956756 | Education Infrastructure Grant | Upgrading and Additions
|  | 29368 | I/500300144/WS | KwaZulu-Natal | ZILULWANE P | 500300144 | Ulundi | Design | Active - Contracted | 2016-06-22 |  | 2027-06-22 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29369 | W/500129389/WS | KwaZulu-Natal | EKWALUSENI HIGH SCHOOL | 500129389 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-02-05 | 2024-03-30 | 2023-06-30 | 2022-05-31 | 525000 | 2394000 | 2919000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29372 | I/500237392/UA | KwaZulu-Natal | NQOBANE PRIMARY SCHOOL | 500237392 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-20 | 2016-10-20 | 2023-04-30 | 2018-03-30 | 2023-04-30 | 10119060 | 46097940 | 56217000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29374 | DB/500256447/WS | KwaZulu-Natal | ROSETTENSTEIN PRIMARY SCHOOL | 500256447 | Richmond | Tender | Active - Contracted | 2016-04-01 |  | 2025-07-31 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29375 | I/500164539/WS | KwaZulu-Natal | INKANYEZI PRIMARY SCHOOL | 500164539 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-10-12 | 2023-03-30 | 2018-03-31 | 2023-03-30 | 307955 | 1710859 | 2018814 | Education Infrastructure Grant | Upgrading and Additions
|  | 29376 | W/500129870/WS | KwaZulu-Natal | ELUDIMBI PRIMARY SCHOOL | 500129870 | Alfred Duma | Tender | Active - Contracted | 2016-06-22 |  | 2024-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29377 | W/500158027/SDS | KwaZulu-Natal | HLWEMINI PRIMARY SCHOOL | 500158027 | uMshwathi | Final Completion | Active - Contracted | 2016-04-01 | 2022-03-30 | 2024-01-31 | 2024-03-30 | 2025-03-30 | 1402088 | 6387289 | 7789377 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29378 | DB/500427683/SDS | KwaZulu-Natal | PETROS JOZANA JUNIOR SECONDARY SC | 500427683 | Umzimkhulu | Feasibility | Active - Contracted | 2016-09-14 |  | 2024-04-19 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29381 | W/500130018/WS | KwaZulu-Natal | EMABHELENI PRIMARY SCHOOL | 500130018 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2016-09-19 | 2023-06-30 | 2023-06-30 | 2024-06-30 | 87000 | 3014816 | 3101816 | Education Infrastructure Grant | Upgrading and Additions
|  | 29382 | W/500130055/WS | KwaZulu-Natal | EMACABAZINI PRIMARY SCHOOL | 500130055 | Dr Nkosazana Dlamini Zuma | Tender | Active - Not Contracted | 2016-06-27 |  | 2026-03-31 |  |  | 1286758 | 5861896 | 7148654 | Education Infrastructure Grant | Upgrading and Additions
|  | 29383 | W/500130129/WS | KwaZulu-Natal | EMACHUNWINI PRIMARY SCHOOL | 500130129 | Msinga | Tender | Active - Contracted | 2015-11-20 |  | 2024-06-30 |  |  | 865000 | 2000000 | 2865000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29384 | W/500130240/WS | KwaZulu-Natal | EMADOLOBHENI PRIMARY SCHOOL | 500130240 | Inkosi Langalibalele | Construction 76% - 99% | Active - Contracted | 2015-11-20 | 2019-06-30 | 2024-06-30 | 2023-06-30 | 2024-06-30 | 690825 | 3147093 | 3837918 | Education Infrastructure Grant | Upgrading and Additions
|  | 29385 | W/500327561/WS | KwaZulu-Natal | EMADULWINI PRIMARY SCHOOL | 500327561 | Abaqulusi | Tender | Active - Contracted | 2016-11-20 |  | 2026-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29386 | W/500256780/WS | KwaZulu-Natal | W/RUTLAND INTERMEDIATE SCHOOL | 500256780 | Dannhauser | On Hold | Active - Not Contracted | 2016-06-13 | 2021-02-26 | 2023-03-30 | 2022-02-28 | 2023-04-01 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29387 | W/500256928/WS | KwaZulu-Natal | S E VAWDA PRIMARY SCHOOL | 500256928 | Newcastle | Design | Active - Contracted | 2016-06-13 | 2021-02-26 | 2023-03-30 | 2022-02-28 | 2023-04-01 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29389 | W/500100011/UA | KwaZulu-Natal | SABUYAZE HIGH SCHOOL | 500100011 | Maphumulo | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 1440000 | 6560000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29391 | W/500257483/WS | KwaZulu-Natal | SAKHESETHU COMBINED SCHOOL | 500257483 | Abaqulusi | Tender | Proposed | 2016-06-13 |  | 2026-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29392 | W/500257446/WS | KwaZulu-Natal | SAKHESETHU PRIMARY SCHOOL | 500257446 | Mandeni | On Hold | Active - Not Contracted | 2016-04-01 | 2021-02-26 | 2023-03-29 | 2022-02-28 | 2023-05-31 | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29393 | W/500257520/WS | KwaZulu-Natal | SAKHILE PRIMARY SCHOOL | 500257520 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2015-06-13 |  | 2023-06-30 |  |  | 1000000 | 3792000 | 4792000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29394 | W/500257557/SDS | KwaZulu-Natal | SAKHISENI HIGH SCHOOL | 500257557 | Msinga | Tender | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 49000 | 221000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29395 | W/500257594/WS | KwaZulu-Natal | SAKHISIZWE HIGH SCHOOL | 500257594 | Maphumulo | Tender | Active - Not Contracted | 2016-04-01 |  | 2026-06-26 |  |  | 1101024 | 5015775 | 6116799 | Education Infrastructure Grant | Upgrading and Additions
|  | 29397 | W/500257668/WS | KwaZulu-Natal | SALEM PRIMARY SCHOOL | 500257668 | uMuziwabantu | Design | Active - Contracted | 2016-04-01 |  | 2023-03-30 |  |  | 360000 | 1732576 | 2092576 | Education Infrastructure Grant | Upgrading and Additions
|  | 29399 | W/500257742/SDS | KwaZulu-Natal | SALPINE PRIMARY SCHOOL | 500257742 | Mfolozi | Final Completion | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 495662 | 2258018 | 2753680 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29400 | W/500257779/ECD | KwaZulu-Natal | SAMBANE COMPREHENSIVE PRIMARY SCHOOL | 500257779 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-13 | 2023-05-31 | 2018-03-30 | 2023-05-31 | 406000 | 1847000 | 2253000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29401 | W/500257816/WS | KwaZulu-Natal | SAMPOFU INTERMEDIATE SCHOOL | 500257816 | Msinga | Design | Active - Not Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29402 | W/500258223/WS | KwaZulu-Natal | SANELISIWE PRIMARY SCHOOL | 500258223 | The Msunduzi | Design | Active - Not Contracted | 2016-04-01 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-04-01 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29403 | W/500258408/SDS | KwaZulu-Natal | SANKONTSHE PRIMARY SCHOOL | 500258408 | eThekwini | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 1759354 | 8014834 | 9774188 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29404 | DB/OFFICE 1/SDS | KwaZulu-Natal | SAYIDI CMC OFFICE | DB/NOT APPLICABLE/SDS | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-04 | 2023-10-04 | 2020-07-31 | 2025-08-07 | 703964 | 3206946 | 3910910 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29405 | W/500259111/RRR | KwaZulu-Natal | SAWOTI PRIMARY SCHOOL | 500259111 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-13 | 2023-03-30 | 2023-03-30 | 2023-06-29 | 2230000 | 10159000 | 12389000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29406 | W/500259111/WS | KwaZulu-Natal | SAWOTI PRIMARY SCHOOL | 500259111 | Ulundi | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29407 | W/500259629/WS | KwaZulu-Natal | SCOTTSFONTEIN PRIMARY SCHOOL | 500259629 | Mpofana | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-02-01 | 2023-03-31 | 2020-03-31 | 2023-05-31 | 18000 | 500000 | 518000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29408 | W/500259999/WS | KwaZulu-Natal | SEBENZANI PRIMARY SCHOOL | 500259999 | Newcastle | On Hold | Active - Not Contracted | 2016-06-13 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29410 | W/500414437/SDS | KwaZulu-Natal | SEKUSILE PRIMARY SCHOOL | 500414437 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-13 | 2023-03-30 | 2018-03-30 | 2023-05-31 | 1006000 | 4582000 | 5588000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29412 | W/500254079/WS | KwaZulu-Natal | QUDENI COMBINED SCHOOL | 500254079 | Nkandla | On Hold | Active - Not Contracted | 2016-06-13 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-05-31 | 402000 | 1916000 | 2318000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29414 | W/500253783/WS | KwaZulu-Natal | QONQO PRIMARY SCHOOL | 5002537783 | Nongoma | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 487000 | 1413000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29415 | W/500321567/WS | KwaZulu-Natal | SENZOKUHLE JUNIOR SECONDARY SCHOOL | 500321567 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 854586 | 3893112 | 4747698 | Education Infrastructure Grant | Upgrading and Additions
|  | 29417 | W/500260369/WS | KwaZulu-Natal | SENZOKUHLE J PRIMARY SCHOOL | 500260369 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-02-01 | 2023-03-11 | 2020-03-31 | 2023-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29418 | W/500260406/SDS | KwaZulu-Natal | SENZOKWETHU PRIMARY SCHOOL (WINTERTON) | 500260406 | Okhahlamba | Design | Active - Not Contracted | 2016-04-01 |  | 2023-12-30 |  |  | 588300 | 2680034 | 3268334 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29422 | W/500253154/WS | KwaZulu-Natal | QHUBIMFUNDO PRIMARY SCHOOL | 500253154 | Newcastle | On Hold | Active - Contracted | 2016-06-13 | 2021-02-26 | 2023-03-30 | 2022-02-28 | 2023-04-01 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29423 | W/500249925/SDS | KwaZulu-Natal | PHUMLANI HIGH SCHOOL | 500249925 | Msinga | Tender | Active - Contracted | 2016-04-01 |  | 2025-05-31 |  |  | 756929 | 3960819 | 4717748 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29425 | W/500250046/WS | KwaZulu-Natal | PHUMZA PRIMARY SCHOOL | 500250046 | uMuziwabantu | Tender | Active - Contracted | 2016-04-01 |  | 2025-05-31 |  |  | 1139614 | 5191573 | 6331187 | Education Infrastructure Grant | Upgrading and Additions
|  | 29426 | W/500252969/WS | KwaZulu-Natal | QHUBAKAHLE PRIMARY SCHOOL | 500252969 | Ndwedwe | Construction 26% - 50% | Active - Contracted | 2016-04-01 |  | 2023-04-26 |  |  | 823810 | 3752912 | 4576722 | Education Infrastructure Grant | Upgrading and Additions
|  | 29427 | W/500343212/WS | KwaZulu-Natal | PHUZAMANZI PRIMARY SCHOOL | 500343212 | Abaqulusi | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29428 | W/500250231/WS | KwaZulu-Natal | PHUZEMTHONJENI PRIMARY SCHOOL | 500250231 | Umhlabuyalingana | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29429 | DB/500215081/SDS | KwaZulu-Natal | MORNING STAR PRIMARY SCHOOL | 500215081 | Okhahlamba | Feasibility | Active - Contracted | 2016-04-01 |  | 2024-02-06 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29430 | W/500250675/SDS | KwaZulu-Natal | PISGAH PRIMARY SCHOOL | 500250675 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2016-04-01 | 2021-02-26 | 2023-03-27 | 2023-02-28 | 2023-03-31 | 823072 | 4515915 | 5338987 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29431 | W/500250675/WS | KwaZulu-Natal | PISGAH PRIMARY SCHOOL | 500250675 | Inkosi Langalibalele | Construction 1% - 25% | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 118000 | 2394000 | 2512000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29432 | W/500252821/WS | KwaZulu-Natal | QHOQHOZA PRIMARY SCHOOL | 500252821 | Nongoma | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29433 | W/500250749/WS | KwaZulu-Natal | PIVAAN COMBINE SCHOOL | 500250749 | eDumbe | Tender | Active - Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 809004 | 3685464 | 4494468 | Education Infrastructure Grant | Upgrading and Additions
|  | 29436 | W/500250897/WS | KwaZulu-Natal | PONGOLA COMBINE SCHOOL | 500250897 | uPhongolo | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 952657 | 4536460 | 5489117 | Education Infrastructure Grant | Upgrading and Additions
|  | 29438 | I/500217671/WS | KwaZulu-Natal | MQAMATHI SECONDARY SCHOOL | 500217671 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-06-13 | 2024-10-23 | 2018-03-30 | 2024-10-23 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29439 | W/500251637/WS | KwaZulu-Natal | PRINCE MNYAYIZA SECONDARY SCHOOL | 500251637 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-28 | 2024-03-30 | 2023-06-30 | 2022-11-20 | 0 | 2683000 | 2683000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29440 | W/500251637/RRR | KwaZulu-Natal | PRINCE MNYAYIZA HIGH SCHOOL | 500251637 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-27 | 2024-03-30 | 2023-06-30 | 2022-03-29 | 1053000 | 4798000 | 5851000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29441 | DB/500302031/WS | KwaZulu-Natal | ZWELITHULE PRIMARY SCHOOL | 500302031 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2011-06-08 |  | 2024-09-26 |  |  | 351000 | 1600000 | 1951000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29443 | W/500252451/WS | KwaZulu-Natal | QEDIPHIKA PRIMARY SCHOOL | 500252451 | Msinga | Tender | Active - Contracted | 2016-01-01 |  | 2025-06-30 |  |  | 967957 | 4409581 | 5377538 | Education Infrastructure Grant | Upgrading and Additions
|  | 29445 | W/500446220/WS | KwaZulu-Natal | LUBHOKO COMP SECONDARY SCHOOL | 500446220 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-06-19 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29448 | W/500252414/WS | KwaZulu-Natal | QAPHELA JENIOR SCHOOL | 500252414 | Newcastle | On Hold | Active - Not Contracted | 2016-06-13 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 32000 | 144000 | 176000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29449 | W/500269582/WS | KwaZulu-Natal | SIYACOTHOZA PRIMARY SCHOOL | 500269582 | Maphumulo | Construction 26% - 50% | Active - Contracted | 2015-04-13 |  | 2023-06-30 |  |  | 825902 | 3762444 | 4588346 | Education Infrastructure Grant | Upgrading and Additions
|  | 29452 | W/500188108/WS | KwaZulu-Natal | LUCAS MEMORIAL PRIMARY SCHOOL | 500188108 | Umzumbe | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 125386 | 935453 | 1060839 | Education Infrastructure Grant | Upgrading and Additions
|  | 29453 | W/500441410/WS | KwaZulu-Natal | QAMBOKUHLE PRIMARY SCHOOL | 500441410 | Abaqulusi | Tender | Active - Contracted | 2016-06-13 |  | 2025-03-30 |  |  | 358000 | 1703000 | 2061000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29454 | I/500426462/NS | KwaZulu-Natal | MAHOBE JS | 500426462/NS | Umzimkhulu | Feasibility | Proposed | 2016-06-06 |  | 2023-10-01 |  |  | 507000 | 2311000 | 2818000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29455 | W/500440374/SDS | KwaZulu-Natal | MSAWENKOSI PRIMARY SCHOOL | 500440374 | eThekwini | Final Completion | Active - Contracted | 2017-12-11 | 2019-08-27 | 2023-01-01 | 2021-10-30 | 2023-04-01 | 404494 | 1842694 | 2247188 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29456 | W/500188219/WS | KwaZulu-Natal | LUDAKA PRIMARY SCHOOL | 500188219 | Jozini | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 770510 | 3510103 | 4280613 | Education Infrastructure Grant | Upgrading and Additions
|  | 29458 | DB/500188293/SDS | KwaZulu-Natal | LUFAFA PRIMARY SCHOOL | 500188256 | Ubuhlebezwe | Final Completion | Approved | 2015-06-13 | 2023-06-14 | 2023-02-13 | 2023-10-15 | 2024-04-18 | 960778 | 3614356 | 4575134 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29459 | DB/500180116/SDS | KwaZulu-Natal | KWALUHLAZA PRIMARY SCHOOL | 500180116 | Ray Nkonyeni | Project Initiation | Active - Contracted | 2016-05-11 |  | 2024-01-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29461 | W/500188330/WS | KwaZulu-Natal | LUGAJU JUNIOR SECONDARY SCHOOL | 500188330 | Impendle | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 894027 | 4072788 | 4966815 | Education Infrastructure Grant | Upgrading and Additions
|  | 29463 | I/500253635/WS | KwaZulu-Natal | QONDISANI PRIMARY SCHOOL | 500253635 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2021-02-03 | 2024-03-30 | 2024-08-15 | 2024-09-05 | 406980 | 1854020 | 2261000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29465 | W/500188515/WS | KwaZulu-Natal | LUJOJWANA PRIMARY SCHOOL | 500188515 | eDumbe | Tender | Active - Not Contracted | 2016-06-14 |  | 2025-06-14 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29466 | I/500308321/CU | KwaZulu-Natal | RAMAROBI | 500308321 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2017-04-30 |  | 2024-03-30 |  |  | 2828372 | 12884808 | 15713180 | Education Infrastructure Grant | Upgrading and Additions
|  | 29467 | W/500188552/WS | KwaZulu-Natal | LUKAZI PRIMARY SCHOOL | 500188552 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2016-06-06 |  | 2026-06-06 |  |  | 740000 | 2644000 | 3384000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29470 | W/500442076/WS | KwaZulu-Natal | SIYAKHULA SECONDARY SCHOOL | 500442076 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-01-21 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 492101 | 2241795 | 2733896 | Education Infrastructure Grant | Upgrading and Additions
|  | 29471 | W/500188626/WS | KwaZulu-Natal | LUNDINI PRIMARY SCHOOL | 500188626 | Jozini | Tender | Active - Contracted | 2016-06-06 |  | 2026-06-30 |  |  | 789156 | 3595045 | 4384201 | Education Infrastructure Grant | Upgrading and Additions
|  | 29472 | I/500281755/WS | KwaZulu-Natal | THEMBOKUHLE PRIMARY SCHOOL | 500281755 | uPhongolo | Practical Completion (100%) | Approved | 2016-06-06 | 2016-06-13 | 2023-06-20 | 2017-10-01 | 2023-10-05 | 310854 | 1726965 | 2037819 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29473 | I/500255559/CU | KwaZulu-Natal | RICHLEA PRIMARY SCHOOL | 500255559 | The Msunduzi | Project Initiation | Active - Contracted | 2017-04-30 |  | 2027-03-30 |  |  | 1649747 | 6206193 | 7855940 | Education Infrastructure Grant | Upgrading and Additions
|  | 29474 | I/500176342/WS | KwaZulu-Natal | KLEIN EDEN COMBINED SCHOOL | 500176342 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2021-02-06 | 2023-10-31 | 2022-01-05 | 2023-01-31 | 514000 | 2858000 | 3372000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29475 | W/500188848/WS | KwaZulu-Natal | LUPHAPHE SECONDARY SCHOOL | 500188848 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2018-12-01 | 2023-03-04 | 2022-03-04 | 2025-03-04 | 535000 | 2438000 | 2973000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29480 | I/500281903/WS | KwaZulu-Natal | THIBANE | 500281903 | Inkosi Langalibalele | Practical Completion (100%) | Approved | 2016-06-06 | 2016-06-13 | 2022-10-05 | 2018-10-01 | 2023-10-05 | 243383 | 1352129 | 1595512 | Education Infrastructure Grant | Upgrading and Additions
|  | 29481 | W/500189699/WS | KwaZulu-Natal | M.L SULTAN COLENSO PRIMARY SCHOOL | W/500189699/WS | Msinga | Tender | Active - Contracted | 2016-06-27 |  | 2026-11-20 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29482 | I/500257557/WS | KwaZulu-Natal | SAKHISENI H | 500257557 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-10-20 | 2024-02-20 | 2018-09-30 | 2024-02-20 | 392220 | 1786780 | 2179000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29484 | W/500170718/WS | KwaZulu-Natal | JABULANI PRIMARY SCHOOL | 500170718 | uMngeni | Tender | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29485 | W/500189884/UA | KwaZulu-Natal | MABAYANA SECONDARY SCHOOL | 500189884 | Ndwedwe | Design | Active - Not Contracted | 2016-06-28 |  | 2024-06-10 |  |  | 1440000 | 6560000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29486 | DB/500282902/WS | KwaZulu-Natal | THOLULWAZI PRIMARY SCHOOL | 500282902/WS | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-04-05 | 2025-08-31 | 2023-05-05 | 2025-08-31 | 515997 | 1289993 | 1805990 | Education Infrastructure Grant | Upgrading and Additions
|  | 29487 | W/500228068/WS | KwaZulu-Natal | NGILANDELA PRIMARY SCHOOL | 500228068 | uMlalazi | Tender | Active - Contracted | 2015-11-20 |  | 2026-03-31 |  |  | 1237606 | 5637984 | 6875590 | Education Infrastructure Grant | Upgrading and Additions
|  | 29489 | DB/500427905/WS | KwaZulu-Natal | SAMARIA JUNIOR SECONDARY SCHOOL | 500427905 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2017-04-20 | 2018-04-05 | 2023-03-30 | 2023-05-05 | 2025-08-31 | 792000 | 3610000 | 4402000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29490 | W/500189921/RRR | KwaZulu-Natal | MABEDLANA P (ULUNDI) | 500189921 | Msinga | Feasibility | Active - Not Contracted | 2016-06-27 |  | 2024-04-20 |  |  | 2250000 | 10250000 | 12500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29491 | W/500426980/WS | KwaZulu-Natal | MT HOREB JUNIOR SECONDARY SCHOOL | 500426980 | Umzimkhulu | Design | Approved | 2016-06-06 |  | 2023-01-26 |  |  | 68000 | 308000 | 376000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29492 | W/500170644/WS | KwaZulu-Natal | JABAVU PRIMARY SCHOOL | 500170644 | Msinga | Tender | Active - Contracted | 2015-11-20 |  | 2025-06-30 |  |  | 792000 | 2000000 | 2792000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29493 | W/500338069/WS | KwaZulu-Natal | MABEDLANA PRIMARY SCHOOL | 500338069 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-01-28 | 2018-02-01 | 2022-10-20 | 2022-10-20 | 2025-10-20 | 402000 | 1830000 | 2232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29494 | W/500228253/WS | KwaZulu-Natal | NGOLOTSHA PRIMARY SCHOOL | 500228253 | Nongoma | Tender | Active - Contracted | 2016-11-20 |  | 2026-03-31 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29495 | W/500274873/WS | KwaZulu-Natal | SPRINGVALE PRIMARY SCHOOL | 500274873 | Nkandla | Tender | Active - Not Contracted | 2015-11-19 |  | 2026-06-30 |  |  | 834255 | 3800496 | 4634751 | Education Infrastructure Grant | Upgrading and Additions
|  | 29496 | W/500423946/UA | KwaZulu-Natal | BUNGENDE JUNIOR SECONDARY SCHOOL | 500413845 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-03-30 | 2023-06-30 | 2022-01-30 | 2024-04-01 | 3635000 | 16560000 | 20195000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29497 | W/500190217/WS | KwaZulu-Natal | MABIZELA SECONDARY SCHOOL | 500190217 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-11-02 | 2017-03-30 | 2022-08-31 | 2022-08-31 | 2025-08-31 | 647000 | 2947000 | 3594000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29498 | C/500272986/ECD | KwaZulu-Natal | SOMBONGANGANI PRIMARY SCHOOL | 500272986 | The Msunduzi | Design | Approved | 2016-06-06 |  | 2025-04-05 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29499 | W/500413845/WS | KwaZulu-Natal | J G ZUMA HIGH SCHOOL | 500413845 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-09-01 | 2018-12-28 | 2023-01-31 | 2022-01-31 | 2022-07-31 | 940715 | 4285480 | 5226195 | Education Infrastructure Grant | Upgrading and Additions
|  | 29501 | W/500190291/WS | KwaZulu-Natal | MABUBULWANA PRIMARY SCHOOL | 500190291 | Msinga | Final Completion | Active - Contracted | 2016-06-01 | 2018-04-01 | 2022-10-31 | 2022-10-31 | 2025-10-31 | 677428 | 3086059 | 3763487 | Education Infrastructure Grant | Upgrading and Additions
|  | 29506 | W/500190328/RRR | KwaZulu-Natal | MABUTHELA HIGH SCHOOL | 500190328 | Umzumbe | Tender | Active - Not Contracted | 2016-06-03 |  | 2024-12-30 |  |  | 5209188 | 23730747 | 28939935 | Education Infrastructure Grant | Upgrading and Additions
|  | 29507 | DB/500303400/SDS | KwaZulu-Natal | ISIKHALISETHU PRIMARY SCHOOL | 500303400 | eDumbe | Feasibility | Active - Not Contracted | 2016-06-06 |  | 2024-06-17 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29510 | I/500401117/WS | KwaZulu-Natal | UGU PRIMARY SCHOOL | 500401117 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2017-06-13 | 2022-06-29 | 2018-10-01 | 2023-06-29 | 183908 | 1021688 | 1205596 | Education Infrastructure Grant | Upgrading and Additions
|  | 29511 | W/500190772/SDS | KwaZulu-Natal | MACHOTSHANENI PRIMARY SCHOOL | 500190772 | uMlalazi | Design | Active - Not Contracted | 2016-06-15 |  | 2024-09-28 |  |  | 195120 | 888880 | 1084000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29513 | DB/500162023/SDS | KwaZulu-Natal | INCHANGA PRIMARY SCHOOL | 500162023 | eThekwini | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29514 | I/500197728/WS | KwaZulu-Natal | MANYANDENI PRIMARY SCHOOL | 500197728 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-11-24 | 2024-03-31 | 2017-12-15 | 2024-03-31 | 208000 | 2350000 | 2558000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29515 | W/500190846/WS | KwaZulu-Natal | MACONGCO PRIMARY SCHOOL | 500190846 | Umvoti | Tender | Active - Not Contracted | 2015-11-27 |  | 2026-06-30 |  |  | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29518 | W/500410996/WS | KwaZulu-Natal | NGOME PRIMARY SCHOOL | 500410996 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-04-11 |  | 2025-03-06 |  |  | 54000 | 2406929 | 2460929 | Education Infrastructure Grant | Upgrading and Additions
|  | 29524 | W/500228346/WS | KwaZulu-Natal | NGONGOLO PRIMARY SCHOOL | 500228346 | Msinga | Design | Active - Contracted | 2016-02-20 |  | 2023-03-16 |  |  | 263000 | 1197000 | 1460000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29526 | W/500191401/WS | KwaZulu-Natal | MADUDULA SECONDARY SCHOOL | 500191401 | Msinga | Site Handed - Over to Contractor | Active - Contracted | 2016-06-22 |  | 2025-06-30 |  |  | 789160 | 3595060 | 4384220 | Education Infrastructure Grant | Upgrading and Additions
|  | 29528 | I/500164946/WS | KwaZulu-Natal | INKOSENTSHA PRIMARY SCHOOL | 500164946 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-01 | 2017-10-12 | 2022-10-05 | 2019-03-20 | 2023-10-05 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29529 | I/500159879/WS | KwaZulu-Natal | HLUSHWANA PRIMARY SCHOOL | 500159879 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2022-11-30 | 2022-10-01 | 2023-11-30 | 443000 | 2019000 | 2462000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29530 | I/500446368/WS | KwaZulu-Natal | GCINUXOLO PRIMARY SCHOOL | 500446368 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-12-18 | 2023-07-01 | 2023-09-01 | 2023-11-30 | 295000 | 1342000 | 1637000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29531 | W/500228401/WS | KwaZulu-Natal | NGONGOMA PRIMARY SCHOOL | 500228401 | Ulundi | Tender | Active - Contracted | 2017-01-02 |  | 2026-03-31 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29532 | I/500428793/NS | KwaZulu-Natal | UMGANO PS | 500428793/NS | Umzimkhulu | Feasibility | Active - Contracted | 2016-06-06 |  | 2023-10-01 |  |  | 1066000 | 4861000 | 5927000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29533 | W/500186813/RRR | KwaZulu-Natal | LINDIZWE PRIMARY SCHOOL | 500186813 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-01 | 2017-03-01 | 2022-05-24 | 2022-05-24 | 2023-05-24 | 3834000 | 17464000 | 21298000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29534 | I/500248085/UA | KwaZulu-Natal | Phelelani PS | 500248085 | eThekwini | Project Initiation | Active - Contracted | 2017-11-15 |  | 2026-03-31 |  |  | 1100400 | 4139600 | 5240000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29535 | I/500121175/WS | KwaZulu-Natal | DIKANA SECONDARY SCHOOL | 500121175 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-03-30 | 2023-03-30 | 2019-03-30 | 2023-03-30 | 468000 | 2130000 | 2598000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29536 | I/500287860/WS | KwaZulu-Natal | UMHLOLUTHINI H | 500287860/WS | Ulundi | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 0 | 656000 | 656000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29537 | I/500150553/WS | KwaZulu-Natal | GOJE PRIMARY SCHOOL | 500150553 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-01 | 2017-10-12 | 2023-04-16 | 2023-06-20 | 2023-09-30 | 521000 | 2372000 | 2893000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29538 | W/500223406/SDS | KwaZulu-Natal | NCANDU COMBINED SCHOOL | 500223406 | Newcastle | Design | Active - Contracted | 2016-04-01 |  | 2024-03-22 |  |  | 1092000 | 2372000 | 3464000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29539 | DB/500248788/WS | KwaZulu-Natal | PHINDAVELE HIGH SCHOOL | 500248788 | Ray Nkonyeni | Construction 1% - 25% | Active - Contracted | 2017-04-30 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 548781 | 2500001 | 3048782 | Education Infrastructure Grant | Upgrading and Additions
|  | 29540 | DB/500443926/WS | KwaZulu-Natal | UMVUZO SECONDARY SCHOOL | 500443926 | The Msunduzi | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2020-05-29 | 2025-06-03 | 2022-05-31 | 2027-06-03 | 377446 | 1719477 | 2096923 | Education Infrastructure Grant | Upgrading and Additions
|  | 29544 | W/500228623/WS | KwaZulu-Natal | NGOZA PRIMARY SCHOOL | 500228623 | Ulundi | Tender | Active - Contracted | 2017-01-02 |  | 2025-03-21 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29546 | W/500228697/WS | KwaZulu-Natal | NGQAMZANA PRIMARY SCHOOL | 500228697 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2015-11-24 | 2016-07-29 | 2023-03-13 | 2023-03-13 | 2023-03-13 | 728000 | 3315000 | 4043000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29548 | W/500300514/WS | KwaZulu-Natal | ZINQOBELE SECONDARY SCHOOL | 500300514 | uMlalazi | On Hold | Active - Not Contracted | 2016-06-06 |  | 2023-06-17 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29549 | W/500218707/SDS | KwaZulu-Natal | MSITHA PRIMARY SCHOOL | 500218707 | Msinga | Final Completion | Active - Contracted | 2016-06-13 | 2018-04-27 | 2023-04-26 | 2020-10-30 | 2023-03-20 | 510133 | 3678289 | 4188422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29550 | W/500320198/WS | KwaZulu-Natal | QALINDLELA PRIMARY SCHOOL | 500320198 | Msinga | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 522000 | 2732000 | 3254000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29552 | ET/500109483/WS | KwaZulu-Natal | BHIDAKHONA PRIMARY SCHOOL | 500109483 | Maphumulo | Final Completion | Active - Contracted | 2016-06-06 | 2019-09-10 | 2023-01-31 | 2021-01-31 | 2023-06-16 | 604737 | 4707052 | 5311789 | Education Infrastructure Grant | Upgrading and Additions
|  | 29554 | W/500227698/WS | KwaZulu-Natal | NGCOLOSI SECONDARY SCHOOL | 500227698 | Maphumulo | Tender | Active - Not Contracted | 2016-06-06 |  | 2026-03-14 |  |  | 360000 | 1761000 | 2121000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29556 | W/500170348/WS | KwaZulu-Natal | IZINHLENDLENI PRIMARY SCHOOL | W/500170348/WS | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2026-03-30 |  |  | 378800 | 1725644 | 2104444 | Education Infrastructure Grant | Upgrading and Additions
|  | 29559 | W/500490324/WS | KwaZulu-Natal | ITHUBALETHU PRIMARY SCHOOL | 500490324 | Msinga | Design | Active - Not Contracted | 2016-05-11 |  | 2024-01-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29560 | I/500291264/UA | KwaZulu-Natal | VELANGAYE HIGH SCHOOL | 500291264/UA | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2023-06-17 | 2017-10-01 | 2023-10-30 | 4716900 | 21488100 | 26205000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29562 | DB/500309616/SDS | KwaZulu-Natal | IZINGWELEVU PRIMARY SCHOOL | 500161098 | Mthonjaneni | Final Completion | Approved | 2016-04-01 | 2017-02-20 | 2025-04-20 | 2019-02-20 | 2025-04-20 | 37692 | 171710 | 209402 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29568 | I/500261146/UA | KwaZulu-Natal | SHAKASKRAAL S | 500261146 | KwaDukuza | Project Initiation | Active - Contracted | 2017-11-15 |  | 2026-03-31 |  |  | 4620000 | 17380000 | 22000000 | Equitable Share | Upgrading and Additions
|  | 29569 | W/500227254/SDS | KwaZulu-Natal | NGALI SECONDARY SCHOOL | 500227254 | Abaqulusi | Tender | Active - Contracted | 2017-04-01 |  | 2025-02-09 |  |  | 676789 | 3083148 | 3759937 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29570 | I/500444888/WS | KwaZulu-Natal | VEZUKUKHANYA PRIMARY SCHOOL | 500444888 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2022-05-31 | 2017-10-01 | 2023-05-31 | 349000 | 1940000 | 2289000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29571 | W/500251933/WS | KwaZulu-Natal | PROTES PRIMARY SCHOOL | 500251933 | eDumbe | Tender | Active - Contracted | 2016-06-13 |  | 2025-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29573 | W/500260628/WS | KwaZulu-Natal | SESIYABONGA SECONDARY SCHOOOL | 500260628 | Newcastle | Design | Active - Not Contracted | 2017-02-20 |  | 2023-06-30 |  |  | 708000 | 3225000 | 3933000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29574 | W/500288919/SDS | KwaZulu-Natal | NGUBEVU PRIMARY SCHOOL | 500288919 | Msinga | Design | Active - Contracted | 2014-10-22 |  | 2024-03-05 |  |  | 556181 | 2533713 | 3089894 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29575 | W/500237873/UA | KwaZulu-Natal | NSETHENI PRIMARY SCHOOL | 500237873 | Okhahlamba | Design | Active - Contracted | 2016-04-01 |  | 2024-03-31 |  |  | 0 | 363000 | 363000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29577 | W/500105598/WS | KwaZulu-Natal | ST LEWIS BERTRANDS SECONDARY SCHOOL | 500105598 | Newcastle | Design | Active - Not Contracted | 2012-09-03 |  | 2023-06-30 |  |  | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29578 | W/500275206/WS | KwaZulu-Natal | ST BERNARDS JOLWAYO PRIMARY SCHOOL | 500275206 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-06-30 | 2018-09-01 | 2023-05-31 | 424000 | 1932000 | 2356000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29579 | I/500343878/UA | KwaZulu-Natal | MYENDANE PRIMARY SCHOOL | 500343878 | Okhahlamba | Design | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29580 | I/500287231/WS | KwaZulu-Natal | UMFOLOZI PRIMARY SCHOOL | 500287231 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-01-29 | 2016-04-01 | 2023-04-29 | 2022-10-01 | 2024-03-31 | 104000 | 476000 | 580000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29581 | W/500218744/WS | KwaZulu-Natal | MSIYANE HIGH SCHOOL | 500218744 | Jozini | Tender | Active - Contracted | 2016-06-06 |  | 2026-04-23 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29584 | DB/500230880/SDS | KwaZulu-Natal | NINGIZIMU PRIMARY SCHOOL | 500230880 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2018-04-05 | 2023-10-05 | 2023-06-30 | 2025-06-30 | 1217554 | 5546633 | 6764187 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29585 | W/500218892/WS | KwaZulu-Natal | MTAKAYISE PRIMARY SCHOOL | 500218892 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-01 | 2021-02-04 | 2023-03-22 | 2023-01-10 | 2023-01-08 | 849000 | 3867000 | 4716000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29586 | W/500170126/WS | KwaZulu-Natal | IWETANE PRIMARY SCHOOL | 500170126 | KwaDukuza | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2017-09-18 | 2023-03-26 | 2023-03-26 | 2023-03-26 | 866786 | 3948694 | 4815480 | Education Infrastructure Grant | Upgrading and Additions
|  | 29587 | W/500289192/RRR | KwaZulu-Natal | MTHOQOTHO SECONDARY SCHOOL | 500289192 | uMngeni | Project Initiation | Active - Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29588 | W/500260665/WS | KwaZulu-Natal | SETHABE PRIMARY SCHOOL | 500260665 | Mkhambathini | Design | Proposed | 2016-06-27 |  | 2023-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29589 | W/500322233/WS | KwaZulu-Natal | MTHALENI JUNIOR SECONDARY SCHOOL | 500322233 | Msinga | Design | Active - Contracted | 2016-06-06 |  | 2024-02-15 |  |  | 54000 | 246000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29591 | W/500429126/NS | KwaZulu-Natal | VULINDLELA JUNIOR SECONDARY SCHOOL | 500429126 | Umzimkhulu | Feasibility | Active - Contracted | 2016-06-06 |  | 2023-10-01 |  |  | 873000 | 3978000 | 4851000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29592 | W/500170089/SDS | KwaZulu-Natal | IWANGU PRIMARY SCHOOL | 500170089 | Mthonjaneni | Tender | Active - Contracted | 2016-04-01 |  | 2025-03-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29593 | W/500251674/WS | KwaZulu-Natal | PRINCE SILWANE SECONDARY SCHOOL | 500251674 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29594 | W/500111518/RRR | KwaZulu-Natal | BONISANANI PRIMARY SCHOOL | 500111518 | eThekwini | Feasibility | Active - Not Contracted | 2016-06-06 |  | 2024-06-17 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29595 | W/500261331/WS | KwaZulu-Natal | SHALOM PRIMARY SCHOOL | W/500261331/WS | Greater Kokstad | On Hold | Active - Not Contracted | 2016-06-27 |  | 2022-12-31 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29596 | I/500442298/CU | KwaZulu-Natal | SHIYAMPAHLA PRIMARY SCHOOL | 500442298 | The Msunduzi | Design | Active - Contracted | 2017-04-30 |  | 2024-03-30 |  |  | 1639050 | 6165950 | 7805000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29597 | W/500170089/WS | KwaZulu-Natal | IWANGU PRIMARY SCHOOL | 500170089 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-03-20 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29598 | W/500261442/WS | KwaZulu-Natal | SHAYABANTU SECONDARY SCHOOL | 500261442 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-06-27 | 2019-02-01 | 2023-03-31 | 2020-03-31 | 2023-05-31 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29599 | I/500293743/WS | KwaZulu-Natal | VUMABAKUSHOYO PRIMARY SCHOOL | 500293743 | Ulundi | Design | Active - Contracted | 2016-06-06 |  | 2027-10-01 |  |  | 0 | 1542000 | 1542000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29600 | W/500441484/WS | KwaZulu-Natal | MTHAMBALALA SECONDARY SCHOOL | 500441484 | Jozini | Design | Active - Contracted | 2016-06-06 |  | 2025-05-22 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29602 | W/500414881/WS | KwaZulu-Natal | SHAYAMOYA PRIMARY SCHOOL | 500414881 | eThekwini | Design | Active - Not Contracted | 2015-11-20 |  | 2023-06-30 |  |  | 1000000 | 1409000 | 2409000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29603 | W/500270026/WS | KwaZulu-Natal | Siyangempumelelo High School | 500270026 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-04-06 | 2022-04-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 1000000 | 2786000 | 3786000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29604 | W/500224479/WS | KwaZulu-Natal | PRINCE NDABUKO HIGH SCHOOL | 500224479 | Nongoma | Construction 1% - 25% | Active - Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 432000 | 1421000 | 1853000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29606 | W/500187886/RRR | KwaZulu-Natal | LOWER TUGELA PRIMARY SCHOOL | 500187886 | Mandeni | Feasibility | Active - Not Contracted | 2016-04-03 |  | 2024-01-12 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29607 | W/500186258/RRR | KwaZulu-Natal | LETHUXOLO SECONDARY SCHOOL | 500186258 | Maphumulo | Feasibility | Active - Not Contracted | 2016-06-06 |  | 2024-06-17 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29612 | W/500261664/WS | KwaZulu-Natal | SHEKELELA PRIMARY SCHOOL | 500261664 | Nqutu | On Hold | Active - Not Contracted | 2016-02-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-04-01 | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29613 | W/500327598/WS | KwaZulu-Natal | MTHANTI COMMTECH SCHOOL | 500327598 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-06-10 | 2021-01-10 | 2023-03-30 | 2022-12-01 | 2023-02-21 | 862000 | 3926000 | 4788000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29615 | C/500262293/UA | KwaZulu-Natal | Shonkweni P School | IDT/262293/FEN | Umdoni | On Hold | Active - Not Contracted | 2016-04-01 |  | 2023-04-30 |  |  | 1997000 | 9098000 | 11095000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29616 | W/500261738/WS | KwaZulu-Natal | SHELEZA PRIMARY SCHOOL | 500261738 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-11-20 |  | 2023-06-30 |  |  | 518000 | 1562000 | 2080000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29617 | W/500294964/WS | KwaZulu-Natal | WEBBSTOWN PRIMARY SCHOOL | 500294964 | Ubuhlebezwe | Design | Active - Not Contracted | 2016-06-06 |  | 2027-04-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29618 | W/500124875/WS | KwaZulu-Natal | DUNDULUZI PRIMARY SCHOOL | 500124875 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-15 |  | 2023-06-30 |  |  | 617273 | 2812020 | 3429293 | Education Infrastructure Grant | Upgrading and Additions
|  | 29620 | W/500440929/NS | KwaZulu-Natal | FAITH MLABA PRIMARY SCHOOL | 500440929 | eThekwini | Design | Active - Contracted | 2016-06-06 |  | 2026-05-30 |  |  | 12350000 | 65000000 | 77350000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29622 | W/500219040/WS | KwaZulu-Natal | MTHENDE SECONDARY SCHOOL | 500219040 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-11-07 | 2018-04-27 | 2024-03-30 | 2023-06-30 | 2022-01-31 | 396000 | 1804000 | 2200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29623 | W/500270063/WS | KwaZulu-Natal | SIYAPHAKAMA SECONDARY SCHOOL | 500270063 | Nongoma | Construction 26% - 50% | Active - Contracted | 2015-01-14 | 2022-03-30 | 2022-06-30 | 2023-04-30 | 2025-03-30 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29624 | W/500308654/SDS | KwaZulu-Natal | MTHIMUDE SECONDARY SCHOOL | 500308654 | Greater Kokstad | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-12-01 | 2024-03-30 | 2023-06-30 | 2022-03-09 | 664000 | 3091000 | 3755000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29625 | W/50039734/WS | KwaZulu-Natal | Siyaphambili Primary School | 500339734 | Abaqulusi | Tender | Active - Contracted | 2015-01-05 |  | 2023-03-29 |  |  | 0 | 1824000 | 1824000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29626 | W/500308654/WS | KwaZulu-Natal | MTHIMUDE SECONDARY SCHOOL | 500308654 | Greater Kokstad | Practical Completion (100%) | Active - Contracted | 2016-06-05 | 2018-04-27 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29631 | W/500340289/SDS | KwaZulu-Natal | THEMBUMZAMO PRIMARY SCHOOL | 500340289 | Alfred Duma | Tender | Active - Contracted | 2016-04-01 |  | 2025-06-30 |  |  | 802606 | 4511618 | 5314224 | Education Infrastructure Grant | Upgrading and Additions
|  | 29632 | W/500323306/WS | KwaZulu-Natal | THEMBUNYAWO SECONDARY SCHOOL | 500323306 | Nqutu | Tender | Active - Contracted | 2015-11-19 |  | 2026-06-30 |  |  | 318000 | 1987530 | 2305530 | Education Infrastructure Grant | Upgrading and Additions
|  | 29633 | W/500441743/WS | KwaZulu-Natal | NGUNGUNYANE PRIMARY SCHOOL | 500441743 | Umhlabuyalingana | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2018-02-01 | 2023-03-31 | 2021-10-30 | 2023-03-31 | 616381 | 2807958 | 3424339 | Education Infrastructure Grant | Upgrading and Additions
|  | 29634 | DB/500427757/WS | KwaZulu-Natal | QONDOKUHLE JUNIOR PRIMARY SCHOOL | 500427757 | Umzimkhulu | Feasibility | Active - Contracted | 2016-06-06 |  | 2027-10-01 |  |  | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29636 | C/500294816/UA | KwaZulu-Natal | WATERLOO SECONDARY SCHOOL | 500294816 | eThekwini | Design | Active - Not Contracted | 2016-03-16 | 2016-03-17 | 2023-09-09 | 2027-03-31 | 2027-03-31 | 877000 | 3999000 | 8496069 | Education Infrastructure Grant | Upgrading and Additions
|  | 29637 | ET/500240389/WS | KwaZulu-Natal | THEO HLALANATHI SECONDARY SCHOOL | 500240389 | Maphumulo | Construction 51% - 75% | Active - Contracted | 2016-03-20 | 2016-03-29 | 2023-03-29 | 2025-03-29 | 2025-03-29 | 1116732 | 5087334 | 6204066 | Education Infrastructure Grant | Upgrading and Additions
|  | 29639 | W/500281829/WS | KwaZulu-Natal | THETHANDABA PRIMARY SCHOOL | 500281829 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-03-30 | 2019-02-01 | 2023-06-30 | 2020-03-31 | 2025-05-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29641 | W/500320901/WS | KwaZulu-Natal | SIYATHOKOZA PRIMARY SCHOOL | 500320901 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-03-19 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 1048247 | 4775348 | 5823595 | Education Infrastructure Grant | Upgrading and Additions
|  | 29644 | W/500282162/WS | KwaZulu-Natal | THOBISIZWE PRIMARY SCHOOL | 500282162 | Alfred Duma | On Hold | Active - Not Contracted | 2016-03-30 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29645 | W/500446516/WS | KwaZulu-Natal | SIYATHUTHUKA PRIMARY SCHOOL | 500343693 | Mtubatuba | Construction 1% - 25% | Active - Contracted | 2015-01-05 | 2018-03-30 | 2022-06-30 | 2024-03-30 | 2025-04-30 | 1089000 | 4961000 | 6050000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29646 | W/500282199/WS | KwaZulu-Natal | Thokazi Primary School | 500282199 | Nongoma | Tender | Active - Contracted | 2015-11-19 |  | 2025-06-30 |  |  | 0 | 1289000 | 1289000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29647 | W/500270618/WS | KwaZulu-Natal | SIYAZIZAMELA SECONDARY SCHOOL | 500270618 | eDumbe | On Hold | Active - Not Contracted | 2014-10-17 | 2021-02-26 | 2024-03-30 | 2023-06-30 | 2022-03-31 | 118000 | 562000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29648 | W/500219743/SDS | KwaZulu-Natal | MTHWANA PRIMARY SCHOOL | 500219743 | Mfolozi | Design | Active - Contracted | 2016-03-30 |  | 2024-03-30 |  |  | 1653000 | 2933000 | 4586000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29649 | W/500270692/WS | KwaZulu-Natal | SIYEPHU PRIMARY SCHOOL | 500270692 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2015-02-09 | 2018-07-20 | 2023-03-29 | 2018-09-01 | 2025-05-31 | 279000 | 1272000 | 1551000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29650 | W/500282384/WS | KwaZulu-Natal | THOLAKELE PRIMARY SCHOOL | 500282384 | eDumbe | Tender | Active - Contracted | 2015-11-19 |  | 2025-06-30 |  |  | 368167 | 1753176 | 2121343 | Education Infrastructure Grant | Upgrading and Additions
|  | 29651 | W/500267584/WS | KwaZulu-Natal | SIPHIWE SECONDARY SCHOOL | 500267584 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2017-03-12 |  | 2023-06-30 |  |  | 919507 | 4188865 | 5108372 | Education Infrastructure Grant | Upgrading and Additions
|  | 29652 | W/500342879/WS | KwaZulu-Natal | SIZABONKE SECONDARY SCHOOL | 500342879 | Abaqulusi | On Hold | Active - Not Contracted | 2016-04-11 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 218000 | 1037000 | 1255000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29654 | W/500270877/WS | KwaZulu-Natal | SIZAKALA PRIMARY SCHOOL | 500270877 | eDumbe | Practical Completion (100%) | Active - Contracted | 2014-08-20 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-04-30 | 500000 | 2535000 | 3035000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29657 | W/500270840/WS | KwaZulu-Natal | SIZAKAHLE PRIMARY SCHOOL | 500270840 | eDumbe | Design | Active - Not Contracted | 2014-10-13 |  | 2023-06-30 |  |  | 1279109 | 5827052 | 7106161 | Education Infrastructure Grant | Upgrading and Additions
|  | 29658 | W/500309024/WS | KwaZulu-Natal | SINQUMA PRIMARY SCHOOL | 500309024 | Ulundi | Tender | Active - Not Contracted | 2017-05-11 |  | 2026-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29659 | W/500271025/RRR | KwaZulu-Natal | SIZAMINQUBEKO COMBINE SCHOOL | 500271025 | Umhlabuyalingana | Project Initiation | Active - Not Contracted | 2015-08-09 |  | 2023-06-30 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29660 | W/500337403/WS | KwaZulu-Natal | MTHINGANA JUNIOR SECONDARY SCHOOL | 500337403 | eDumbe | Practical Completion (100%) | Active - Contracted | 2015-06-21 | 2017-05-26 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 920626 | 4193963 | 5114589 | Education Infrastructure Grant | Upgrading and Additions
|  | 29662 | W/500219225/WS | KwaZulu-Natal | MTHIYAQHWA SECONDARY SCHOOL | 500219225 | Nkandla | Tender | Active - Not Contracted | 2016-06-15 |  | 2026-03-22 |  |  | 70000 | 317000 | 387000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29664 | W/500220298/WS | KwaZulu-Natal | MTHWALUME PRIMARY SCHOOL | 500220298 | Umdoni | Construction 76% - 99% | Active - Contracted | 2016-06-15 | 2017-05-25 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 562445 | 2562252 | 3124697 | Education Infrastructure Grant | Upgrading and Additions
|  | 29665 | W/500427942/WS | KwaZulu-Natal | SINGISI COMP SECONDARY SCHOOL | 500427942 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2017-03-17 |  | 2023-06-30 |  |  | 680708 | 3101003 | 3781711 | Education Infrastructure Grant | Upgrading and Additions
|  | 29666 | W/500165464/WS | KwaZulu-Natal | INQOLOBANE JUNIOR SECONDARY SCHOOL | 500165464 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-01-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29667 | W/500219854/WS | KwaZulu-Natal | MTSHAKELA SECONDARY SCHOOL | 500219854 | Jozini | Construction 76% - 99% | Active - Contracted | 2016-06-14 | 2017-04-27 | 2023-03-22 | 2023-03-22 | 2023-03-22 | 862000 | 3925000 | 4787000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29668 | W/500227587/WS | KwaZulu-Natal | NGCEDOMHLOPHE HIGH SCHOOL | 500227587 | The Msunduzi | Design | Active - Not Contracted | 2017-06-13 |  | 2023-03-14 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29669 | W/500229030/WS | KwaZulu-Natal | NGUNJINI PRIMARY SCHOOL | 500229030 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-04-27 | 2023-03-30 | 2018-09-01 | 2023-03-31 | 327000 | 1492253 | 1819253 | Education Infrastructure Grant | Upgrading and Additions
|  | 29671 | W/500219891/WS | KwaZulu-Natal | MTSHEKULA HIGH SCHOOL | 500219891 | uPhongolo | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-31 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29672 | W/500325600/WS | KwaZulu-Natal | NGUQE PRIMARY SCHOOL | 500325600 | Ulundi | Tender | Active - Contracted | 2017-01-02 |  | 2026-03-16 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29673 | W/500227513/WS | KwaZulu-Natal | NGCAKA PRIMARY SCHOOL | 500227513 | Newcastle | On Hold | Active - Contracted | 2016-06-13 |  | 2023-02-07 |  |  | 109000 | 494000 | 603000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29675 | W/500227291/WS | KwaZulu-Natal | NGANGAYIPHI PRIMARY SCHOOL | 500227291 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2025-03-30 |  |  | 984560 | 4485219 | 5469779 | Education Infrastructure Grant | Upgrading and Additions
|  | 29676 | DB/NEWSCHOOL | KwaZulu-Natal | MAMANDOSI COMBINED SCHOOL | NEWSCHOOL | Ubuhlebezwe | Construction 76% - 99% | Active - Contracted | 2016-06-05 | 2017-04-13 | 2023-03-29 | 2023-03-29 | 2023-03-29 | 5372331 | 29846538 | 35218869 | Education Infrastructure Grant | Upgrading and Additions
|  | 29678 | W/500227180/WS | KwaZulu-Natal | NGADUMBILI PRIMARY SCHOOL | 500227180 | Nongoma | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-10 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29681 | W/500220927/SDS | KwaZulu-Natal | MUZIKAWUTHANDWA SECONDARY SCHOOL | 500220927 | uMshwathi | Tender | Active - Contracted | 2016-06-14 |  | 2023-03-31 |  |  | 1735515 | 7906237 | 9641752 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29682 | W/500213786/WS | KwaZulu-Natal | MUNTONOKUDLA SECONDARY SCHOOL | 500213786 | uMhlathuze | Tender | Active - Contracted | 2015-06-14 |  | 2026-03-31 |  |  | 801053 | 3649240 | 4450293 | Education Infrastructure Grant | Upgrading and Additions
|  | 29683 | W/500227106/WS | KwaZulu-Natal | NEWTONVILLE PRIMARY SCHOOL | 500227106 | Dr Nkosazana Dlamini Zuma | Construction 76% - 99% | Active - Contracted | 2016-06-13 | 2017-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 870242 | 3964436 | 4834678 | Education Infrastructure Grant | Upgrading and Additions
|  | 29684 | W/500220779/WS | KwaZulu-Natal | MUNYWANA PRIAMRY SCHOOL | 500220779 | Nqutu | Design | Active - Contracted | 2016-06-15 |  | 2023-01-20 |  |  | 8000 | 36000 | 44000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29685 | W/500220890/WS | KwaZulu-Natal | MUTHIDLWE PRIMARY SCHOOL | 500220890 | Jozini | Tender | Active - Contracted | 2016-06-16 |  | 2026-03-31 |  |  | 769559 | 3505770 | 4275329 | Education Infrastructure Grant | Upgrading and Additions
|  | 29688 | W/500143634/WS | KwaZulu-Natal | EZINQOLENI JUNIOR SECONDARY SCHOOL | 500143634 | Ray Nkonyeni | Tender | Active - Contracted | 2016-06-22 |  | 2026-06-30 |  |  | 1219117 | 5553756 | 6772873 | Education Infrastructure Grant | Upgrading and Additions
|  | 29689 | W/500144115/WS | KwaZulu-Natal | FAIRLEGH PRIMARY SCHOOL | 500144115 | Mkhambathini | Design | Active - Not Contracted | 2016-06-13 |  | 2024-05-30 |  |  | 536000 | 2441000 | 2977000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29690 | W/500249972/WS | KwaZulu-Natal | PHUMUZUZULU PRIMARY SCHOOL | 500249972 | eThekwini | On Hold | Active - Not Contracted | 2016-06-21 | 2021-02-26 | 2022-06-28 | 2022-02-28 | 2023-04-01 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29692 | W/500221112/WS | KwaZulu-Natal | MUZOKHANYAYO SECONDARY SCHOOL | 500221112 | Dannhauser | Design | Active - Contracted | 2016-06-22 |  | 2023-03-22 |  |  | 609000 | 2773000 | 3382000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29693 | W/500495874/WS | KwaZulu-Natal | NETHEZEKA PRIMARY SCHOOL | 500495874 | Umhlabuyalingana | Tender | Active - Contracted | 2016-06-13 |  | 2026-02-17 |  |  | 712628 | 3246417 | 3959045 | Education Infrastructure Grant | Upgrading and Additions
|  | 29694 | W/500303770/WS | KwaZulu-Natal | SIZAMOKUHLE PRIMARY SCHOOL | 500303770 | Newcastle | Design | Active - Not Contracted | 2015-01-07 |  | 2023-06-30 |  |  | 300000 | 700000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29695 | W/500221408/WS | KwaZulu-Natal | MVINI PRIMARY SCHOOL | 500221408 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2019-08-27 | 2023-03-31 | 2021-10-30 | 2022-03-31 | 702000 | 3197000 | 3899000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29696 | W/500266585/WS | KwaZulu-Natal | SINGANA PRIMARY SCHOOL | 500266585 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-03-12 |  | 2023-06-18 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29697 | W/500226070/WS | KwaZulu-Natal | NDUNGE PRIMARY SCHOOL | 500226070 | Ubuhlebezwe | Design | Active - Contracted | 2016-06-13 |  | 2023-03-24 |  |  | 47000 | 216000 | 263000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29698 | W/500221038/WS | KwaZulu-Natal | MUZIWENGQONDO SECONDARY SCHOOL | 500221038 | Ulundi | Construction 76% - 99% | Active - Contracted | 2016-06-22 | 2017-03-23 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 798572 | 3637938 | 4436510 | Education Infrastructure Grant | Upgrading and Additions
|  | 29699 | W/500225330/WS | KwaZulu-Natal | NDLOKOLO PRIMARY SCHOOL | 500225330 | Mkhambathini | On Hold | Active - Not Contracted | 2016-06-06 |  | 2023-02-24 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29700 | W/500271099/WS | KwaZulu-Natal | Sizana Primary School | 500271099 | Ulundi | Construction 76% - 99% | Active - Contracted | 2015-01-19 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 561356 | 2673125 | 3234481 | Education Infrastructure Grant | Upgrading and Additions
|  | 29702 | I/500295778/UA | KwaZulu-Natal | WESTON AGRICULTURAL | 500295778 | Mpofana | On Hold | Active - Not Contracted | 2016-06-06 | 2016-06-13 | 2023-10-01 | 2023-10-01 | 2027-03-31 | 4320000 | 19680000 | 24000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29703 | W/500413734/WS | KwaZulu-Natal | SINENZUZO PRIMARY SCHOOL | 500413734 | eThekwini | On Hold | Proposed | 2017-03-12 | 2021-02-26 | 2023-05-01 | 2023-06-30 | 2023-05-31 | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29705 | I/500296259/WS | KwaZulu-Natal | WILLIAM BOOTH PRIMARY SCHOOL | 500296259 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2020-03-20 | 2022-10-01 | 2023-07-02 | 2027-09-30 | 283000 | 1786000 | 2069000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29706 | W/500326599/WS | KwaZulu-Natal | NDUKENDE SECONDARY SCHOOL | 500326599 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 833141 | 3795420 | 4628561 | Education Infrastructure Grant | Upgrading and Additions
|  | 29710 | W/500271136/RRR | KwaZulu-Natal | SIZANANI SECONDARY SCHOOL | 500271136 | Newcastle | Final Completion | Active - Contracted | 2014-08-11 | 2018-02-01 | 2023-06-30 | 2024-03-30 | 2025-05-31 | 7231000 | 32942000 | 40173000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29711 | W/500225589/WS | KwaZulu-Natal | NDONDAKUSUKU SECONDARY SCHOOL | 500225589 | KwaDukuza | Tender | Active - Contracted | 2016-06-13 |  | 2026-02-17 |  |  | 823658 | 3752218 | 4575876 | Education Infrastructure Grant | Upgrading and Additions
|  | 29712 | W/500271617/WS | KwaZulu-Natal | SIZOPHUMELELA SECONDARY SCHOOL | 500271617 | Umdoni | Design | Active - Not Contracted | 2015-01-27 |  | 2023-06-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29714 | W/500225515/WS | KwaZulu-Natal | NDLUYESILO SECONDARY SCHOOL | 500225515 | uMlalazi | Tender | Active - Contracted | 2016-06-13 |  | 2025-03-24 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29715 | W/500271654/SDS | KwaZulu-Natal | SIZUZULU PRIMARY SCHOOL | 500271654 | eDumbe | Tender | Active - Contracted | 2015-01-12 |  | 2025-06-30 |  |  | 194282 | 969278 | 1163560 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29716 | W/500225441/SDS | KwaZulu-Natal | NDLONGOLWANE HIGH SCHOOL | 500225441 | uMlalazi | Design | Active - Contracted | 2016-06-13 |  | 2024-03-23 |  |  | 217440 | 990560 | 1208000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29717 | W/500229696/WS | KwaZulu-Natal | NHLALAKAHLE SECONDARY SCHOOL | 500229696 | Alfred Duma | Design | Active - Not Contracted | 2015-11-20 |  | 2025-02-12 |  |  | 409000 | 1865000 | 2274000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29718 | W/500271802/WS | KwaZulu-Natal | SIZWELABANTU PRIMARY SCHOOL | 500271802 | Nongoma | Tender | Active - Contracted | 2015-01-26 |  | 2026-06-30 |  |  | 0 | 2178000 | 2178000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29719 | W/500229807/WS | KwaZulu-Natal | NHLAMBANYATHI JUNIOR SECONDARY SCHOOL | 500229807 | Umhlabuyalingana | Tender | Active - Contracted | 2017-02-20 |  | 2025-03-31 |  |  | 785384 | 3577862 | 4363246 | Education Infrastructure Grant | Upgrading and Additions
|  | 29721 | W/500229844/WS | KwaZulu-Natal | NHLANGAKAZI PRIMARY SCHOOL | 500229844 | Ndwedwe | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2020-07-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 830468 | 3783243 | 4613711 | Education Infrastructure Grant | Upgrading and Additions
|  | 29723 | W/500271987/WS | KwaZulu-Natal | SKRAALHOEK PRIMARY SCHOOL | 500271987 | Okhahlamba | Design | Active - Not Contracted | 2016-03-24 |  | 2023-06-30 |  |  | 430000 | 1957000 | 2387000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29725 | W/500272468/UA | KwaZulu-Natal | SOBANTU SECONDARY SCHOOL | 500272468 | The Msunduzi | Design | Active - Contracted | 2015-01-26 |  | 2026-06-30 |  |  | 0 | 2426000 | 2426000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29726 | W/500272542/WS | KwaZulu-Natal | SOGADUZELA SECONDARY SCHOOL | 500272542 | eDumbe | Practical Completion (100%) | Active - Contracted | 2014-08-18 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-04-30 | 400000 | 1424000 | 1824000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29728 | W/500273837/WS | KwaZulu-Natal | SONTSHENGE PRIMARY SCHOOL | 500273837 | Ndwedwe | Construction 76% - 99% | Active - Contracted | 2014-07-14 | 2023-06-01 | 2023-06-30 | 2023-06-30 | 2024-03-30 | 823788 | 3752814 | 4576602 | Education Infrastructure Grant | Upgrading and Additions
|  | 29731 | DB/500274429/SDS | KwaZulu-Natal | SOZAMA HIGH SCHOOOL | 500274429 | uPhongolo | Final Completion | Approved | 2016-04-13 | 2017-06-20 | 2023-07-06 | 2019-04-20 | 2025-06-20 | 984367 | 4484340 | 5468707 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29732 | W/500343878/WS | KwaZulu-Natal | MYENDANE PRIMARY SCHOOL | 500343878 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-06-21 | 2018-04-27 | 2023-03-31 | 2018-09-01 | 2022-03-31 | 225000 | 1025000 | 1250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29733 | W/500274688/WS | KwaZulu-Natal | SPRINGLAKE SECONDARY SCHOOL | 500274688 | Nqutu | Final Completion | Active - Contracted | 2015-04-20 | 2021-02-26 | 2023-06-30 | 2023-04-20 | 2025-04-01 | 834255 | 3800496 | 4634751 | Education Infrastructure Grant | Upgrading and Additions
|  | 29735 | W/500222000/WS | KwaZulu-Natal | MZIKI PRIMARY SCHOOL | 500222000 | Jozini | Tender | Active - Contracted | 2016-06-22 |  | 2026-03-31 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29737 | W/500222481/WS | KwaZulu-Natal | MZOMUSHA INTERMEDIATE SCHOOL (TUGELA FERRY) | 500222481 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2017-04-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 301000 | 1371000 | 1672000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29738 | W/500222370/SDS | KwaZulu-Natal | MZIWENKOSI PRIMARY SCHOOL | 500222370 | Umvoti | Tender | Active - Contracted | 2016-06-22 |  | 2023-03-31 |  |  | 852857 | 4640952 | 5493809 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29739 | W/500291893/WS | KwaZulu-Natal | VEZAMAFA PRIMARY SCHOOL | 500291893 | eThekwini | On Hold | Active - Not Contracted | 2016-06-22 |  | 2023-06-28 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29741 | W/500207163/WS | KwaZulu-Natal | MEHLOMLUNGU SECONDARY SCHOOL | 500207163 | Maphumulo | Tender | Active - Contracted | 2016-06-06 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29744 | W/500282458/WS | KwaZulu-Natal | THOLATHEMBA PRIMARY SCHOOL | 500282458 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 405813 | 1848703 | 2254516 | Education Infrastructure Grant | Upgrading and Additions
|  | 29745 | ET/500266474/WS | KwaZulu-Natal | SINENHLANHLA (INANDA) PRIMARY SCHOOL | 500266474 | Alfred Duma | Final Completion | Proposed | 2019-03-17 | 2020-06-10 | 2024-12-18 | 2024-01-31 | 2024-06-30 | 500000 | 3180103 | 3680103 | Education Infrastructure Grant | Upgrading and Additions
|  | 29747 | W/500205794/SDS | KwaZulu-Natal | MCITSHENI PRIMARY SCHOOL | 500205794 | Alfred Duma | Final Completion | Active - Contracted | 2016-06-22 | 2018-04-27 | 2023-03-29 | 2023-01-31 | 2023-03-30 | 783923 | 3571204 | 4355127 | Education Infrastructure Grant | Upgrading and Additions
|  | 29748 | W/500261775/WS | KwaZulu-Natal | SHEMBE PRIMARY SCHOOL | 500261775 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-04-01 | 100000 | 3674000 | 3774000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29750 | W/500261849/WS | KwaZulu-Natal | SHENGEZA SECONDARY SCHOOL | 500261849 | Umhlabuyalingana | Tender | Active - Not Contracted | 2017-03-02 |  | 2026-06-30 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29751 | W/500185925/WS | KwaZulu-Natal | LENGOLA SECONDARY SCHOOL | 500185925 | Dannhauser | Design | Active - Not Contracted | 2016-01-29 |  | 2024-04-29 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29752 | W/500302512/WS | KwaZulu-Natal | NDLELENI PRIMARY SCHOOL | 500302512 | Maphumulo | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-03-10 |  |  | 804000 | 3662000 | 4466000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29753 | W/500128279/NS | KwaZulu-Natal | EKUCABANGENI SECONDARY SCHOOL | 500128279 | Nqutu | Construction 76% - 99% | Active - Contracted | 2016-02-15 | 2016-02-19 | 2023-06-30 | 2021-06-30 | 2022-06-30 | 12238435 | 55752872 | 67991307 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29755 | I/500444333/WS | KwaZulu-Natal | SIBONGINTUTHUKO P | 500444333 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2020-06-10 | 2023-03-30 | 2023-04-30 | 2024-03-30 | 347000 | 1925000 | 2272000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29756 | W/500225034/WS | KwaZulu-Natal | NDIMANDE SECONDARY SCHOOL | 500225034 | Mtubatuba | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-17 |  |  | 834181 | 3800158 | 4634339 | Education Infrastructure Grant | Upgrading and Additions
|  | 29757 | W/500261997/WS | KwaZulu-Natal | SHESHISAMSAMO PRIMARY SCHOOL | 500261997 | Umvoti | Tender | Active - Not Contracted | 2017-02-20 |  | 2023-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29759 | W/500324231/RRR | KwaZulu-Natal | COTTONLANDS PRIMARY SCHOOL | 500324231 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2016-06-20 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2049300 | 11007700 | 13057000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29763 | W/500205868/UA | KwaZulu-Natal | MCOPHELELI PRIMARY SCHOOL | 500205868 | eThekwini | Design | Active - Contracted | 2016-01-29 |  | 2023-06-30 |  |  | 1836000 | 3116000 | 4952000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29764 | W/500262182/WS | KwaZulu-Natal | SHIYANE PRIMARY SCHOOL | 500262182 | Msinga | Final Completion | Active - Contracted | 2017-11-20 |  | 2023-06-30 |  |  | 668492 | 3045352 | 3713844 | Education Infrastructure Grant | Upgrading and Additions
|  | 29765 | W/500273134/SDS | KwaZulu-Natal | SOMILE SECONDARY SCHOOL | 500273134 | uPhongolo | Design | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 1369800 | 6240200 | 7610000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29766 | W/500216820/SDS | KwaZulu-Natal | MPINDISO SECONDARY SCHOOL | 500216820 | uPhongolo | Design | Active - Contracted | 2014-02-20 |  | 2024-02-25 |  |  | 1364400 | 6215600 | 7580000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29767 | W/500224812/WS | KwaZulu-Natal | NDEMA PRIMARY SCHOOL | 500224812 | Nongoma | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-03-24 |  |  | 846440 | 3856007 | 4702447 | Education Infrastructure Grant | Upgrading and Additions
|  | 29768 | W/500139046/SDS | KwaZulu-Natal | ENYAWOSHANE PRIMARY SCHOOL | 500139046 | Nkandla | Design | Active - Not Contracted | 2016-06-06 |  | 2024-06-17 |  |  | 812520 | 3701480 | 4514000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29769 | W/500113183/WS | KwaZulu-Natal | BUHLEBENTUTHUKO PRIMARY SCHOOL | 500113183 | Newcastle | Design | Active - Not Contracted | 2016-06-06 |  | 2024-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29770 | W/500230066/SDS | KwaZulu-Natal | NHLAYENZA JUNIOR PRIMARY SCHOOL | 500230066 | Umzumbe | Design | Active - Contracted | 2017-09-28 |  | 2023-03-25 |  |  | 1933000 | 3333000 | 5266000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29772 | W/500224590/WS | KwaZulu-Natal | NDAMKANE HIGH SCHOOL | 500224590 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-06-13 | 2017-11-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 797000 | 3630000 | 4427000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29774 | W/500133607/WS | KwaZulu-Natal | EMOLWENI PRIMARY SCHOOL | 500133607 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-29 | 2017-01-31 | 2023-06-30 | 2021-06-30 | 2021-06-30 | 751118 | 3421762 | 4172880 | Education Infrastructure Grant | Upgrading and Additions
|  | 29776 | DB/500205646/WS | KwaZulu-Natal | MCEBO PRIMARY SCHOOL | 500205646 | Mtubatuba | Design | Active - Not Contracted | 2016-06-06 |  | 2025-06-17 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29778 | W/500265919/WS | KwaZulu-Natal | SILWENI COMBINED SCHOOL | 500265919 | Abaqulusi | Tender | Active - Not Contracted | 2017-03-12 |  | 2023-06-30 |  |  | 834181 | 3800158 | 4634339 | Education Infrastructure Grant | Upgrading and Additions
|  | 29779 | W/500208125/WS | KwaZulu-Natal | MEVAMHLOPHE HIGH SCHOOL | 500208125 | uMhlathuze | On Hold | Active - Not Contracted | 2016-06-06 |  | 2023-01-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29780 | W/500296999/WS | KwaZulu-Natal | MNTONJANI SS | 61008/FEN | Mkhambathini | Design | Active - Not Contracted | 2021-06-06 |  | 2027-03-31 |  |  | 863691 | 3934594 | 4798285 | Education Infrastructure Grant | Upgrading and Additions
|  | 29781 | I/500264735/WS | KwaZulu-Natal | SIHLENGENI COMBINED SCHOOL | 500264735 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-10-12 | 2024-03-30 | 2024-06-29 | 2024-07-14 | 300000 | 1665000 | 1965000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29782 | DB/500111888/WS | KwaZulu-Natal | BOTHA`S PASS FARM PRIMARY SCHOOL | 500111888 | Newcastle | Design | Active - Not Contracted | 2016-06-22 |  | 2024-03-22 |  |  | 1350000 | 4580000 | 5930000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29784 | W/500262626/WS | KwaZulu-Natal | SIBANISAKHE SECONDARY SCHOOL | 500262626 | Ulundi | Tender | Active - Not Contracted | 2017-02-01 |  | 2026-03-30 |  |  | 438000 | 2088000 | 2526000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29785 | I/500309320/WS | KwaZulu-Natal | Sikhalelumuzi P | I/500309320/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-05 | 2024-03-30 | 2024-03-30 | 2024-07-02 | 255000 | 1160000 | 1415000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29787 | W/500214193/WS | KwaZulu-Natal | MNYAYIZA PRIMARY SCHOOL | 500214193 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-02-05 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29788 | I/500327448/WS | KwaZulu-Natal | SIKHIYE SECONDARY SCHOOL | 500327448 | Emadlangeni | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2020-03-30 | 2024-03-30 | 2024-04-30 | 2026-03-31 | 188640 | 859360 | 1048000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29789 | W/500214341/WS | KwaZulu-Natal | MOMBENI PRIMARY SCHOOL | 500214341 | uMlalazi | Tender | Active - Not Contracted | 2016-06-06 |  | 2024-01-01 |  |  | 1277000 | 5820000 | 7097000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29790 | W/500205868/WS | KwaZulu-Natal | MCOPHELELI PRIMARY SCHOOL | 500205868 | eThekwini | Design | Active - Contracted | 2016-06-21 |  | 2023-03-15 |  |  | 961000 | 4379000 | 5340000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29791 | W/500229955/WS | KwaZulu-Natal | NHLANHLAYETHU SECONDARY SCHOOL | 500229955 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2017-11-19 | 2023-02-20 | 2023-03-31 | 2023-03-30 | 750000 | 3417000 | 4167000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29792 | W/500429015/WS | KwaZulu-Natal | VUKANI PRIMARY SCHOOL | 500429015 | Ubuhlebezwe | Project Initiation | Active - Contracted | 2016-01-29 |  | 2025-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29795 | I/500206127/WS | KwaZulu-Natal | MDLADLA SECONDARY SCHOOL | 500206127 | Jozini | Tender | Active - Not Contracted | 2016-06-22 |  | 2024-06-28 |  |  | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29796 | W/500229992/WS | KwaZulu-Natal | NHLANHLENI SENIOR PRIMARY SCHOOL | 500229992 | uMngeni | Design | Active - Contracted | 2016-04-01 |  | 2024-02-13 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29797 | W/500214378/SDS | KwaZulu-Natal | MOME PRIMARY SCHOOL | 500214378 | Mthonjaneni | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-03-11 |  |  | 455546 | 2269378 | 2724924 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29798 | DB/500223517/SDS | KwaZulu-Natal | MEHLATHATHANI PRIMARY SCHOOL | 500223517 | Mthonjaneni | Final Completion | Active - Contracted | 2016-06-22 | 2017-12-01 | 2022-06-28 | 2022-12-12 | 2023-05-31 | 297379 | 1354726 | 1652105 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29800 | W/500230140/WS | KwaZulu-Natal | NHLAZATSHE PRIMARY SCHOOL | 500230140 | Ulundi | Construction 76% - 99% | Active - Contracted | 2016-11-20 | 2018-02-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29801 | W/500287564/WS | KwaZulu-Natal | UMGODI PRIMARY SCHOOL | 500287564 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-06-01 | 2022-06-30 | 2024-06-30 | 2025-05-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29803 | W/5002243689/WS | KwaZulu-Natal | NDABEZITHA PRIMARY SCHOOL | 5002243689 | eDumbe | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2023-03-24 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29804 | W/500215044/WS | KwaZulu-Natal | MORESON PRIMARY SCHOOL | 500215044 | uPhongolo | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-04-01 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29808 | W/500215081/WS | KwaZulu-Natal | MORNING STAR PRIMARY SCHOOL | 500215081/WS | Okhahlamba | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2017-07-20 | 2023-01-30 | 2023-07-27 | 2023-04-01 | 655000 | 2983000 | 3638000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29810 | W/500215229/WS | KwaZulu-Natal | MOSES ZIKHALI SECONDARY SCHOOL | 500215229 | Umhlabuyalingana | Design | Active - Contracted | 2016-06-06 |  | 2024-01-10 |  |  | 1288000 | 5868000 | 7156000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29811 | DB/500206608/WS | KwaZulu-Natal | MDUMEZULU PRIMARY SCHOOL | 500206608 | eThekwini | Tender | Active - Contracted | 2016-06-22 |  | 2024-07-26 |  |  | 1055000 | 4809000 | 5864000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29816 | W/500215599/WS | KwaZulu-Natal | MOUNTAIN VIEW PRIMARY SCHOOL | 500215599 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-02-01 | 2024-10-31 | 2024-03-31 | 2024-03-15 | 250000 | 1139000 | 1389000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29818 | W/500428090/WS | KwaZulu-Natal | ST AUGUSTINE PRIMARY SCHOOL | 500428090 | Ubuhlebezwe | Design | Active - Not Contracted | 2016-06-13 |  | 2025-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29819 | W/500492544/SDS | KwaZulu-Natal | NHLOKWANE SECONDARY SCHOOL | 500492544 | Alfred Duma | Design | Active - Not Contracted | 2016-04-01 |  | 2025-02-15 |  |  | 2899000 | 4179000 | 7078000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29822 | W/500492544/WS | KwaZulu-Natal | NHLOKWANE SECONDARY SCHOOL | 500492544 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-03-20 | 2019-02-01 | 2023-03-30 | 2023-03-31 | 2023-02-21 | 245000 | 1115000 | 1360000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29823 | W/500427868/WS | KwaZulu-Natal | RIETVIEL SECONDARY SCHOOL | 500427868 | Ubuhlebezwe | Practical Completion (100%) | Approved | 2016-06-06 | 2020-11-01 | 2023-03-29 | 2022-02-03 | 2023-04-01 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29824 | W/500282754/WS | KwaZulu-Natal | THOLITHEMBA SECONDARY SCHOOL | 500282754 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-11-19 | 2020-03-20 | 2023-03-30 | 2022-03-19 | 2023-10-31 | 163000 | 775000 | 938000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29826 | W/500241055/WS | KwaZulu-Natal | NTWASAHLOBO HIGH SCHOOL | 500241055 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2016-06-06 |  | 2024-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29827 | W/500262663/WS | KwaZulu-Natal | SIBANISETHU PRIMARY SCHOOL | 500262663 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 975252 | 4442812 | 5418064 | Education Infrastructure Grant | Upgrading and Additions
|  | 29828 | W/500334702/WS | KwaZulu-Natal | THOLULWAZI PRIMARY SCHOOL | 500282902 | Alfred Duma | Design | Active - Not Contracted | 2015-11-19 |  | 2023-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29829 | W/500334332/WS | KwaZulu-Natal | SILOKOZA SECONDARY SCHOOL | 500334332 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-03-12 | 2023-06-01 | 2023-06-30 | 2023-06-30 | 2023-07-01 | 584000 | 2658000 | 3242000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29830 | W/500427239/WS | KwaZulu-Natal | NGQUMARENI JUNIOR SECONDARY SCHOOL | 500427239 | Umzimkhulu | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2016-07-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 981003 | 4469013 | 5450016 | Education Infrastructure Grant | Upgrading and Additions
|  | 29831 | DB/500426721/WS | KwaZulu-Natal | MFULAMHLE JUNIOR COMBINED SCHOOL | 500426721 | Umzimkhulu | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 568945 | 2591860 | 3160805 | Education Infrastructure Grant | Upgrading and Additions
|  | 29834 | W/500262996/WS | KwaZulu-Natal | SIBIYANGANKOMO PRIMARY SCHOOL | 500262996 | Abaqulusi | Construction 76% - 99% | Active - Contracted | 2017-02-01 | 2023-06-01 | 2023-06-30 | 2023-06-30 | 2024-05-31 | 834181 | 3800158 | 4634339 | Education Infrastructure Grant | Upgrading and Additions
|  | 29838 | DB/500414955/WS | KwaZulu-Natal | SIYAPHAMBILI PRIMARY SCHOOL | 500414955 | Abaqulusi | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 2776000 | 3096000 | 5872000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29841 | W/500231028/WS | KwaZulu-Natal | NJAKAZANA PRIMARY SCHOOL | 500231028 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-03-02 | 2022-05-31 | 2023-03-23 | 2023-03-31 | 2023-03-28 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29845 | W/500263588/WS | KwaZulu-Natal | SIBUMBA PRIMARY SCHOOL | 500263588 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2021-02-26 | 2022-06-30 | 2022-02-28 | 2023-04-01 | 665000 | 3030000 | 3695000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29846 | W/500216154/WS | KwaZulu-Natal | MPEMBENI PRIMARY SCHOOL | 500216154 | Abaqulusi | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-01-01 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29847 | W/500231213/WS | KwaZulu-Natal | NJOMELWANE PRIMARY SCHOOL | 500231213 | Ulundi | Tender | Active - Contracted | 2016-03-20 |  | 2025-03-31 |  |  | 881000 | 4013000 | 4894000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29848 | W/500263625/SDS | KwaZulu-Natal | SIBUMBENE SECONDARY SCHOOL | 500263625 | Abaqulusi | Final Completion | Approved | 2016-04-01 | 2023-06-01 | 2022-06-30 | 2023-06-30 | 2024-04-01 | 995836 | 4536586 | 5532422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29852 | W/500303215/WS | KwaZulu-Natal | UZWANO SECONDARY SCHOOL | 500303215 | eDumbe | Practical Completion (100%) | Active - Contracted | 2015-03-06 | 2020-01-01 | 2023-06-30 | 2022-06-10 | 2022-06-30 | 500000 | 1903000 | 2403000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29853 | W/500263773/WS | KwaZulu-Natal | SIBUYILE SECONDARY SCHOOL | 500263773 | Umzumbe | Construction 76% - 99% | Active - Contracted | 2016-04-01 |  | 2023-07-31 |  |  | 822577 | 3747295 | 4569872 | Education Infrastructure Grant | Upgrading and Additions
|  | 29856 | W/500263847/WS | KwaZulu-Natal | SICELOKUHLE HIGH SCHOOL | 500263847 | Alfred Duma | Tender | Active - Not Contracted | 2016-11-20 |  | 2023-06-30 |  |  | 0 | 2917000 | 2917000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29857 | W/500283605/RRR | KwaZulu-Natal | THULWANA HIGH SCHOOL | 500283605 | Nongoma | Design | Active - Not Contracted | 2016-03-30 |  | 2023-06-30 |  |  | 1257000 | 5727000 | 6984000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29858 | ET/500263995/WS | KwaZulu-Natal | SIDIYA PRIMARY SCHOOL | 500263995 | eThekwini | Design | Active - Not Contracted | 2016-04-01 | 2021-02-26 | 2023-04-26 | 2022-02-28 | 2023-05-31 | 100000 | 500000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29860 | W/500283716/WS | KwaZulu-Natal | THUSANE PRIMARY SCHOOL | 500283716 | Big Five Hlabisa | Tender | Active - Contracted | 2015-11-19 |  | 2025-06-30 |  |  | 343065 | 1633641 | 1976706 | Education Infrastructure Grant | Upgrading and Additions
|  | 29861 | W/500290968/WS | KwaZulu-Natal | VAVULE PRIMARY SCHOOL | 500290968 | Umvoti | Tender | Active - Contracted | 2015-11-11 |  | 2025-06-30 |  |  | 0 | 2587000 | 2587000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29862 | W/500264143/WS | KwaZulu-Natal | SIDUNGE PRIMARY SCHOOL | 500261143 | uMngeni | Construction 76% - 99% | Active - Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 544789 | 2481816 | 3026605 | Education Infrastructure Grant | Upgrading and Additions
|  | 29864 | W/500264476/WS | KwaZulu-Natal | SIGIDISABATHEMBU PRIMARY SCHOOL (SIGIDI PS) | 500264476 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2018-02-01 | 2023-07-31 | 2018-09-01 | 2023-05-31 | 476000 | 2167000 | 2643000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29866 | W/500264587/WS | KwaZulu-Natal | SIGUBUDU PRIMARY SCHOOL | 500264587 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-02-01 | 2023-06-01 | 2023-01-31 | 2023-06-30 | 2024-03-30 | 846032 | 3854148 | 4700180 | Education Infrastructure Grant | Upgrading and Additions
|  | 29868 | W/500152440/WS | KwaZulu-Natal | GUDLINTABA PRIMARY SCHOOL | 500152440 | Umzimkhulu | Design | Active - Not Contracted | 2016-04-01 |  | 2026-11-30 |  |  | 984725 | 4485970 | 5470695 | Education Infrastructure Grant | Upgrading and Additions
|  | 29869 | W/500216191/SDS | KwaZulu-Natal | MPEMVAANA PRIMARY SCHOOL | 500216191 | eDumbe | Tender | Active - Not Contracted | 2016-06-06 | 2019-08-27 | 2023-03-01 | 2022-10-30 | 2023-03-30 | 605463 | 2758221 | 3363684 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29872 | W/500170015/WS | KwaZulu-Natal | IVUNGU HIGH SCHOOL | 500170015 | Abaqulusi | Tender | Active - Contracted | 2015-11-20 |  | 2026-03-30 |  |  | 0 | 1853000 | 1853000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29887 | W/500264618/WS | KwaZulu-Natal | SIHLE SECONDARY SCHOOL | 500264772 | Umzumbe | Design | Active - Not Contracted | 2016-04-01 |  | 2023-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29888 | W/500216450/WS | KwaZulu-Natal | MPHAZIMA PRIMARY SCHOOL | 500216450 | Nqutu | Final Completion | Active - Contracted | 2016-06-06 | 2018-02-01 | 2023-05-01 | 2021-12-30 | 2023-03-31 | 826408 | 3764746 | 4591154 | Education Infrastructure Grant | Upgrading and Additions
|  | 29889 | W/500224072/WS | KwaZulu-Natal | NDABAMBI COMBINED SCHOOL | 500224072 | eThekwini | Tender | Active - Not Contracted | 2016-06-13 |  | 2026-02-17 |  |  | 819912 | 3735156 | 4555068 | Education Infrastructure Grant | Upgrading and Additions
|  | 29892 | W/500291338/WS | KwaZulu-Natal | VELANKOSI P | 500291338 | Abaqulusi | Tender | Active - Contracted | 2015-11-11 |  | 2025-03-11 |  |  | 513120 | 2443430 | 2956550 | Education Infrastructure Grant | Upgrading and Additions
|  | 29894 | W/500231472/WS | KwaZulu-Natal | NKAMBA PRIMARY SCHOOL | 500231472 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-11-22 | 2016-04-01 | 2024-10-30 | 2024-03-30 | 2024-03-31 | 0 | 2447000 | 2447000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29897 | W/500424686/WS | KwaZulu-Natal | EGUGWINI JUNIOR PRIMARY SCHOOL | 500424686 | Umzimkhulu | Design | Active - Not Contracted | 2016-04-01 |  | 2023-04-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29898 | W/500231805/WS | KwaZulu-Natal | THANDULWAZI SECONDARY SCHOOL (NKAWU S) | 500231805 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2017-07-20 | 2023-06-30 | 2023-07-15 | 2023-12-20 | 273000 | 1302000 | 1575000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29899 | W/500216635/WS | KwaZulu-Natal | MPHONDI PRIMARY SCHOOL | 500216635 | Nqutu | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-01-30 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29900 | DB/500307655/RRR | KwaZulu-Natal | VEZOBALA SECONDARY SCHOOL | 500307655 | Mtubatuba | Project Initiation | Active - Not Contracted | 2017-03-11 |  | 2027-06-30 |  |  | 2806167 | 12783648 | 15589815 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29901 | W/500264772/WS | KwaZulu-Natal | SIKANISWENI SECONDARY SCHOOL | 500264772 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2019-02-01 | 2023-03-30 | 2020-03-31 | 2023-05-31 | 285000 | 1298000 | 1583000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29903 | W/500207200/WS | KwaZulu-Natal | MEHLOMNYAMA PRIMARY SCHOOL | 500207200 | Ubuhlebezwe | Construction 51% - 75% | Active - Contracted | 2016-04-01 |  | 2023-03-30 |  |  | 1373503 | 6257070 | 7630573 | Education Infrastructure Grant | Upgrading and Additions
|  | 29904 | W/500231509/WS | KwaZulu-Natal | NKAMELWANE PRIMARY SCHOOL | 500231509 | Ulundi | Tender | Active - Contracted | 2016-06-22 |  | 2027-06-30 |  |  | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 29905 | W/500264846/WS | KwaZulu-Natal | SIKHANYISELENI COMBINED SCHOOL | 500264846 | Abaqulusi | Tender | Active - Not Contracted | 2017-02-01 |  | 2024-03-30 |  |  | 292000 | 1391000 | 1683000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29906 | W/500216746/WS | KwaZulu-Natal | MPIKAYIZEKANYE SECONDARY SCHOOL | 500216746 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2015-11-06 | 2019-02-01 | 2024-11-01 | 2024-03-31 | 2024-01-31 | 267000 | 1217000 | 1484000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29907 | W/500414474/UA | KwaZulu-Natal | MEHLWANE PRIMARY SCHOOL | 500414474 | uMlalazi | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 4546000 | 20709000 | 25255000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29908 | W/500231324/WS | KwaZulu-Natal | NKABANE PRIMARY SCHOOL | 500231324 | Nongoma | Tender | Active - Contracted | 2016-06-22 |  | 2025-03-31 |  |  | 834181 | 3800158 | 4634339 | Education Infrastructure Grant | Upgrading and Additions
|  | 29911 | W/500207385/WS | KwaZulu-Natal | MELOKUHLE SECONDARY SCHOOL | 500207385 | Nqutu | Final Completion | Active - Contracted | 2015-02-02 | 2019-08-27 | 2023-05-30 | 2022-01-31 | 2023-01-31 | 757252 | 3449703 | 4206955 | Education Infrastructure Grant | Upgrading and Additions
|  | 29913 | DB/500187812/WS | KwaZulu-Natal | LOUWSBURG PRIMARY SCHOOL | 500187812 | Abaqulusi | Practical Completion (100%) | Active - Not Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29914 | DB/500223998/WS | KwaZulu-Natal | NCWECWE SECONDARY SCHOOL | 5002223998 | Abaqulusi | Design | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 335000 | 1595000 | 1930000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29915 | W/500292189/WS | KwaZulu-Natal | VIKINDLALA INTERMEDIATE SCHOOL | 500292189 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-02-01 | 2018-04-27 | 2022-08-23 | 2022-08-23 | 2025-08-23 | 435273 | 4389539 | 4824812 | Education Infrastructure Grant | Upgrading and Additions
|  | 29916 | W/500265031/WS | KwaZulu-Natal | SIKHUKHUKHU PRIMARY SCHOOL | 500164132 | uMngeni | Final Completion | Active - Contracted | 2016-01-01 | 2023-06-01 | 2023-06-30 | 2023-06-30 | 2024-03-30 | 648101 | 2952462 | 3600563 | Education Infrastructure Grant | Upgrading and Additions
|  | 29917 | W/500216931/WS | KwaZulu-Natal | MPOFANA PRIMARY SCHOOL | 500216931 | Richmond | Tender | Active - Not Contracted | 2016-06-06 |  | 2026-01-30 |  |  | 390452 | 1778724 | 2169176 | Education Infrastructure Grant | Upgrading and Additions
|  | 29918 | W/500309394/WS | KwaZulu-Natal | INKOSI GODLUMKHONTO PRIMARY SCHOOL | 500309394 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2016-10-01 |  | 2025-06-30 |  |  | 871200 | 3968800 | 4840000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29919 | W/500207681/UA | KwaZulu-Natal | MENZI HIGH SCHOOL | 500207681 | eThekwini | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 4248000 | 19352000 | 23600000 | Equitable Share | Upgrading and Additions
|  | 29920 | DB/500216968/WS | KwaZulu-Natal | MPOFANYANA PRIMARY SCHOOL | 500216968/WS | Mpofana | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2019-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29921 | W/500304621/WS | KwaZulu-Natal | SIKHULILE COMBINED SCHOOL | 500304621 | Abaqulusi | Tender | Active - Not Contracted | 2017-03-01 |  | 2026-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29922 | W/500217190/WS | KwaZulu-Natal | MPOMPOLWANA PRIMARY SCHOOL | 500217190 | Msinga | Tender | Active - Not Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29924 | W/500292226/WS | KwaZulu-Natal | VIKINDUKU PRIMARY SCHOOL | 500292226 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-17 | 2016-03-23 | 2023-06-30 | 2022-06-30 | 2025-06-30 | 500000 | 1392000 | 1892000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29926 | W/500207718/WS | KwaZulu-Natal | MENZIWA PRIMARY SCHOOL | 500207718 | Richmond | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-27 | 2023-06-30 | 2022-01-31 | 2023-01-31 | 1313792 | 5985051 | 7298843 | Education Infrastructure Grant | Upgrading and Additions
|  | 29930 | W/500292892/WS | KwaZulu-Natal | VRYSTAAT PRIMARY SCHOOL | 500292892 | Mpofana | Practical Completion (100%) | Active - Contracted | 2016-03-14 | 2019-02-01 | 2023-10-12 | 2023-03-31 | 2025-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29932 | W/500207755/WS | KwaZulu-Natal | MEPHO PRIMARY SCHOOL | 500207755 | Ndwedwe | Construction 51% - 75% | Active - Contracted | 2016-04-01 |  | 2023-01-30 |  |  | 841415 | 3833114 | 4674529 | Education Infrastructure Grant | Upgrading and Additions
|  | 29935 | W/500292929/WS | KwaZulu-Natal | VUKA PRIMARY SCHOOL | 500292929 | uMshwathi | Design | Active - Not Contracted | 2017-03-11 |  | 2023-08-14 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29936 | I/500499389/NS | KwaZulu-Natal | SIPHUMELELE SECONDARY SCHOOL (MEER-EN-SEE) | I/500499389/NS | uMhlathuze | Construction 76% - 99% | Active - Contracted | 2015-06-24 | 2016-04-20 | 2023-02-21 | 2022-02-21 | 2026-03-31 | 22034520 | 100379480 | 122414000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29937 | W/500217782/WS | KwaZulu-Natal | MQEDANDABA SECONDARY SCHOOLSCHOOL | 500217782 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-04-27 | 2024-03-30 | 2024-09-01 | 2024-01-31 | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29938 | W/500208088/WS | KwaZulu-Natal | METZELFONTEIN COMBINED SCHOOL | 500208088 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2017-01-02 |  | 2023-01-30 |  |  | 712216 | 3244540 | 3956756 | Education Infrastructure Grant | Upgrading and Additions
|  | 29941 | W/500293040/WS | KwaZulu-Natal | VUKANIMAZULU SECONDARY SCHOOL | 500293040 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2017-05-11 | 2019-01-14 | 2023-06-30 | 2024-03-30 | 2025-05-30 | 812323 | 3700583 | 4512906 | Education Infrastructure Grant | Upgrading and Additions
|  | 29943 | W/500217819/WS | KwaZulu-Natal | MQEDI SENIOR PRIMARY SCHOOL | 500217819 | Ndwedwe | On Hold | Active - Not Contracted | 2016-06-06 |  | 2023-03-29 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29944 | W/500208162/RRR | KwaZulu-Natal | MEYAMA H | W/500208162/RRR | Nongoma | Tender | Active - Not Contracted | 2016-04-01 |  | 2025-01-30 |  |  | 3493800 | 15916200 | 19410000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29945 | I/500499315/NS | KwaZulu-Natal | SINOTHANDO PRIMARY SCHOOL | 500266770 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2022-03-30 | 2022-08-30 | 2022-09-20 | 2024-03-30 | 5782226 | 32123462 | 37905688 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 29946 | W/500217856/WS | KwaZulu-Natal | MQHAKAMA SECONDARY SCHOOL | 500217856 | Umzumbe | Design | Active - Not Contracted | 2016-06-06 |  | 2023-02-16 |  |  | 63000 | 287000 | 350000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29947 | W/500286861/WS | KwaZulu-Natal | UMBANGO SECONDARY SCHOOL | 500286861 | Alfred Duma | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29948 | W/500293262/WS | KwaZulu-Natal | VUKUZA HIGH SCHOOL | 500293262 | Ulundi | Tender | Active - Not Contracted | 2017-05-11 |  | 2025-06-30 |  |  | 872289 | 3973761 | 4846050 | Education Infrastructure Grant | Upgrading and Additions
|  | 29949 | DB/500217930/UA | KwaZulu-Natal | MQHAWE S | 500217930 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 2516000 | 11463000 | 13979000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29950 | W/500227365/SDS | KwaZulu-Natal | NGAWU JUNIOR PRIMARY SCHOOL | 500227365 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-02-22 | 2018-08-31 | 2025-03-31 | 2025-10-30 | 2025-03-31 | 1932000 | 3332000 | 5264000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29954 | W/500208162/WS | KwaZulu-Natal | MEYAMA SECONDARY SCHOOL | 500208162 | Nongoma | Tender | Active - Contracted | 2015-11-20 |  | 2025-02-14 |  |  | 522000 | 3005321 | 3527321 | Education Infrastructure Grant | Upgrading and Additions
|  | 29955 | W/500218004/WS | KwaZulu-Natal | MQINISENI SECONDARY SCHOOL | 500218004 | Ulundi | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2017-07-20 | 2023-01-10 | 2023-07-15 | 2023-11-30 | 734297 | 3345130 | 4079427 | Education Infrastructure Grant | Upgrading and Additions
|  | 29957 | DB/500253746/WS | KwaZulu-Natal | MQONGWANA PRIMARY SCHOOL | 500253746 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-06-06 |  | 2024-06-16 |  |  | 517000 | 2357000 | 2874000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29958 | DB/500208199/WS | KwaZulu-Natal | MEYERSHOEK PRIMARY SCHOOL | 500208199 | Richmond | Tender | Active - Contracted | 2016-04-01 |  | 2023-03-31 |  |  | 0 | 500 | 500 | Education Infrastructure Grant | Upgrading and Additions
|  | 29959 | W/500335109/WS | KwaZulu-Natal | VUKUZAME PRIMARY SCHOOL | 500335109 | eDumbe | Feasibility | Proposed | 2017-05-11 |  | 2025-11-14 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29960 | I/500266992/WS | KwaZulu-Natal | SIPHALAZA P | 500266992 | eDumbe | Practical Completion (100%) | Active - Contracted | 2015-10-20 | 2016-04-01 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 229000 | 1045000 | 1274000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29961 | W/500323824/WS | KwaZulu-Natal | MQUNGEBE SECONDARY SCHOOL | 500323824 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2021-02-26 | 2023-06-30 | 2021-04-30 | 2023-03-31 | 942000 | 4291000 | 5233000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29962 | W/500218078/WS | KwaZulu-Natal | MQWABE PRIMARY SCHOOL | 500218078 | eDumbe | Tender | Active - Not Contracted | 2015-06-06 |  | 2026-02-01 |  |  | 706202 | 3217142 | 3923344 | Education Infrastructure Grant | Upgrading and Additions
|  | 29963 | ET/500293336/WS | KwaZulu-Natal | VUKUZENZELE PRIMARY SCHOOL | 500293336 | Maphumulo | Design | Active - Contracted | 2017-05-11 |  | 2023-03-30 |  |  | 300000 | 1500000 | 1800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29965 | W/500238056/WS | KwaZulu-Natal | NSIKAYEZWE COMBINED SCHOOL | 500238056 | Alfred Duma | Design | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29968 | W/500310800/WS | KwaZulu-Natal | VULAKWENILE JUNIOR SECONDARY SCHOOL | 500310800 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2017-03-06 |  | 2025-06-30 |  |  | 790909 | 3603028 | 4393937 | Education Infrastructure Grant | Upgrading and Additions
|  | 29969 | W/500218300/WS | KwaZulu-Natal | MSENTELI PRIMARY SCHOOL | 500218300 | Nongoma | Tender | Active - Not Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 174600 | 795400 | 970000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29970 | W/500312650/WS | KwaZulu-Natal | NCULWANE PRIMARY SCHOOL | 500312650 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2019-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 500000 | 2000000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29972 | W/500218337/WS | KwaZulu-Natal | MSHANELOWESIZWE SECONDARY SCHOOL | 500218337/WS | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2021-01-10 | 2023-03-08 | 2023-02-01 | 2023-03-05 | 80460 | 366540 | 447000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29974 | W/500156547/WS | KwaZulu-Natal | HLATHIKHULU PRIMARY SCHOOL | 500156547 | uMshwathi | Design | Active - Contracted | 2016-06-06 |  | 2024-06-30 |  |  | 561285 | 2556964 | 3118249 | Education Infrastructure Grant | Upgrading and Additions
|  | 29975 | W/500293447/WS | KwaZulu-Natal | VULAMEHLO PRIMARY SCHOOL | 500293447 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-05-11 | 2018-05-14 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 661000 | 3012000 | 3673000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29977 | W/500208347/WS | KwaZulu-Natal | MFANAWENDLELA PRIMARY SCHOOL | 500208347 | Ulundi | Tender | Active - Not Contracted | 2015-11-20 |  | 2025-03-31 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29978 | W/500218411/WS | KwaZulu-Natal | MSHIYANE HIGH SCHOOL | 500218411 | Ndwedwe | On Hold | Active - Not Contracted | 2015-11-06 |  | 2023-01-31 |  |  | 500000 | 1700000 | 2200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29979 | W/500222814/SDS | KwaZulu-Natal | NADI PRIMARY SCHOOL | 500222814 | uMngeni | Project Initiation | Approved | 2017-09-06 |  | 2024-03-15 |  |  | 2109000 | 3509000 | 5618000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29980 | W/500169756/WS | KwaZulu-Natal | ITSHEHLOPHE PRIMARY SCHOOL | 500169756 | Umzumbe | Tender | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 1279757 | 5830006 | 7109763 | Education Infrastructure Grant | Upgrading and Additions
|  | 29981 | W/500208532/SDS | KwaZulu-Natal | Mfenebude Primary School | 500208532 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-04-27 | 2023-06-30 | 2023-03-30 | 2023-03-30 | 382432 | 3477800 | 3860232 | Education Infrastructure Grant | Maintenance and Repairs
|  | 29985 | I/500304991/WS | KwaZulu-Natal | SIQOPHUMLANDO S | 500304991 | Abaqulusi | Design | Active - Contracted | 2016-06-22 |  | 2023-10-25 |  |  | 106740 | 486260 | 593000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29987 | W/500208532/WS | KwaZulu-Natal | MFENEBUDE PRIMARY SCHOOL | 500208532 | Msinga | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2018-02-01 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 199000 | 906000 | 1105000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29988 | I/500269101/WS | KwaZulu-Natal | SIVANANDA HP | 500269101 | Ulundi | Design | Active - Contracted | 2016-06-22 |  | 2023-11-29 |  |  | 147600 | 672400 | 820000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29991 | W/500208569/WS | KwaZulu-Natal | MFENI PRIMARY SCHOOL | 500208569 | eDumbe | Tender | Active - Not Contracted | 2017-11-20 |  | 2025-01-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29992 | W/500284715/WS | KwaZulu-Natal | TROUTWATERS PRIMARY SCHOOL | 500284715 | Greater Kokstad | Design | Active - Not Contracted | 2016-03-30 |  | 2023-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29993 | W/500169719/UA | KwaZulu-Natal | ITHWELENYE PRIMARY SCHOOL | 500169719 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2016-09-18 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 1440000 | 6560000 | 8000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 29994 | I/500270100/CR | KwaZulu-Natal | SIYAPHAMBILI S | I/500270100/CR | uMuziwabantu | Feasibility | Active - Contracted | 2016-06-22 |  | 2024-05-31 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29995 | W/500223887/WS | KwaZulu-Natal | NCOTSHENI SENIOR PRIMARY SCHOOL | 500223887 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-11-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 712216 | 3244540 | 3956756 | Education Infrastructure Grant | Upgrading and Additions
|  | 29996 | W/500293854/WS | KwaZulu-Natal | VUMELANI PRIMARY SCHOOL | 500293854 | Newcastle | Design | Active - Contracted | 2017-03-06 |  | 2027-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 29999 | I/500427979/CU | KwaZulu-Natal | SIZAKANCANE PRIMARY SCHOOL | 500427979 | Umzimkhulu | Design | Active - Contracted | 2016-06-22 |  | 2023-06-28 |  |  | 84456000 | 20056000 | 104512000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30000 | W/500294039/WS | KwaZulu-Natal | VUMUTHANDO PRIMARY SCHOOL | 500294039 | uMshwathi | Design | Active - Not Contracted | 2017-03-12 |  | 2027-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30001 | DB/500341584/WS | KwaZulu-Natal | SIPHAKEME SECONDARY SCHOOL | 500341584 | Umvoti | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30002 | DB/500247345/WS | KwaZulu-Natal | PHAKATHWAYO SECONDARY SCHOOL | 500247345 | Nqutu | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30003 | DB/500220409/WS | KwaZulu-Natal | MUDEN COMBINED SCHOOL | 500220409 | Umvoti | Design | Active - Contracted | 2011-12-15 |  | 2025-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30004 | DB/500342805/WS | KwaZulu-Natal | SIZATHINA JUNIOR SECONDARY SCHOOL | 500342805 | Umdoni | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30005 | W/500223813/WS | KwaZulu-Natal | NCOMANI HIGH SCHOOL | 500223813 | Ubuhlebezwe | On Hold | Active - Contracted | 2016-06-13 |  | 2023-03-17 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30006 | W/500285048/WS | KwaZulu-Natal | TSHEKHULU PRIMARY SCHOOLl | 500285048 | Nongoma | Tender | Active - Contracted | 2015-11-19 |  | 2025-06-30 |  |  | 61000 | 800000 | 861000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30007 | W/500218596/WS | KwaZulu-Natal | MSIMBU SECONDARY SCHOOL | 500218596 | Nqutu | Design | Active - Contracted | 2016-06-06 |  | 2024-02-13 |  |  | 1106000 | 5037000 | 6143000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30012 | DB/500208014/WS | KwaZulu-Natal | MERTOUN PRIMARY SCHOOL | 500208014 | Msinga | Construction 26% - 50% | Active - Contracted | 2016-02-15 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2025-01-31 | 231015 | 1052402 | 1283417 | Education Infrastructure Grant | Upgrading and Additions
|  | 30013 | W/500294446/WS | KwaZulu-Natal | WANGU PRIMARY SCHOOL | 500294446 | Mandeni | Construction 76% - 99% | Active - Contracted | 2017-03-11 | 2023-05-30 | 2023-06-30 | 2023-07-30 | 2027-08-30 | 937200 | 4269465 | 5206665 | Education Infrastructure Grant | Upgrading and Additions
|  | 30016 | W/500285085/WS | KwaZulu-Natal | TSHELABANTU PRIMARY SCHOOL | 500285085 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-03-25 | 2022-06-01 | 2022-06-30 | 2024-03-30 | 2025-05-03 | 1012429 | 4612175 | 5624604 | Education Infrastructure Grant | Upgrading and Additions
|  | 30017 | I/500274429/WS | KwaZulu-Natal | SOZAMA HIGH SCHOOL | 500274429/WS | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2023-06-17 | 2023-06-20 | 2023-04-30 | 314000 | 1429000 | 1743000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30018 | W/500223628/WS | KwaZulu-Natal | NCIBIDWANE PRIMARY SCHOOL | 500223628 | Inkosi Langalibalele | Design | Active - Contracted | 2016-06-13 |  | 2024-03-08 |  |  | 646000 | 2941000 | 3587000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30019 | I/500339734/WS | KwaZulu-Natal | SIYAPHAMBILI P | I/500339734/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-06-22 | 2019-09-10 | 2022-08-30 | 2020-04-30 | 2023-04-30 | 376000 | 2091000 | 2467000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30022 | I/500275391/UA | KwaZulu-Natal | ST CHRISTOPHER P | 500275391/UA | KwaDukuza | Design | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 10800000 | 49200000 | 60000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30023 | DB/500270174/WS | KwaZulu-Natal | SIYAPHUMLA SCHOOL | 500270174 | KwaDukuza | Design | Active - Contracted | 2013-12-26 |  | 2024-03-30 |  |  | 295000 | 1343000 | 1638000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30024 | W/500342213/WS | KwaZulu-Natal | NCEKUYA PRIMARY SCHOOL | 500342213 | uMlalazi | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-31 |  |  | 1159000 | 5279000 | 6438000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30025 | DB/500186295/WS | KwaZulu-Natal | LEWIS COMBINED SCHOOL | 500186295 | Msinga | Construction 26% - 50% | Active - Contracted | 2014-02-24 | 2022-05-31 | 2023-01-31 | 2023-01-31 | 2027-01-31 | 609323 | 2775803 | 3385126 | Education Infrastructure Grant | Upgrading and Additions
|  | 30026 | I/500275428/LSEN | KwaZulu-Natal | ST CHRISTOPHER | 500275428/LSEN | KwaDukuza | Design | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 10804320 | 49219680 | 60024000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30027 | W/500294890/WS | KwaZulu-Natal | WATERSHED PRIMARY SCHOOL | 500294890 | Alfred Duma | Design | Active - Contracted | 2015-11-11 |  | 2024-05-21 |  |  | 500000 | 1675000 | 2175000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30029 | I/500270248/WS | KwaZulu-Natal | SIYAQHUBEKA LOWER PRIMARY SCHO | I/500270248/WS | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-08 | 2017-06-08 | 2024-06-08 | 2024-06-08 | 2024-03-31 | 106000 | 482000 | 588000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30031 | W/500154808/WS | KwaZulu-Natal | HERMANNBURG SECONDARY SCHOOL | 500154808 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-12-01 | 2023-03-30 | 2023-05-05 | 2025-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30036 | I/500428349/CU | KwaZulu-Natal | STRAALHOEK PRIMARY SCHOOL | 500428349 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 540000 | 18585000 | 19125000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30041 | W/500119547/WS | KwaZulu-Natal | DALTON PRIMARY SCHOOL | 500119547 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-01-03 | 2023-03-30 | 2023-01-03 | 2024-01-03 | 2205000 | 3485000 | 5690000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30042 | I/500279054/CU | KwaZulu-Natal | SUTTON PRIMARY SCHOOL | 500279054 | Umzumbe | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 540000 | 26738000 | 27278000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30045 | I/500280460/WS | KwaZulu-Natal | THANDOKWAKHE | 500280460/WS | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2019-09-10 | 2024-03-30 | 2024-09-10 | 2024-11-07 | 0 | 1934000 | 1934000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30047 | W/500223036/SDS | KwaZulu-Natal | NANI SECONDARY SCHOOL | 500223036 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2017-06-13 | 2018-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1373000 | 6253000 | 7626000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30049 | DB/500116624/WS | KwaZulu-Natal | COSH PRIMARY SCHOOL | 500116624 | Msinga | Design | Active - Contracted | 2016-02-15 |  | 2024-03-31 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30050 | I/500280645/CR | KwaZulu-Natal | THANDUXOLO P | 500280645/CR | Dr Nkosazana Dlamini Zuma | Feasibility | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30051 | W/500295112/WS | KwaZulu-Natal | WELA PRIMARY SCHOOL | 500295112 | Nongoma | Tender | Active - Not Contracted | 2015-11-12 |  | 2027-11-12 |  |  | 486541 | 2316864 | 2803405 | Education Infrastructure Grant | Upgrading and Additions
|  | 30052 | W/500222740/WS | KwaZulu-Natal | MZWENDABA PRIMARY SCHOOL | W/500222740/WS | Dr Nkosazana Dlamini Zuma | Final Completion | Active - Contracted | 2016-06-13 | 2018-04-27 | 2023-03-31 | 2021-11-30 | 2022-01-31 | 1164483 | 5304869 | 6469352 | Education Infrastructure Grant | Upgrading and Additions
|  | 30053 | I/500280756/WS | KwaZulu-Natal | THATHOKUHLE PRIMARY SCHOOL | 50032611 | eThekwini | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 0 | 696000 | 696000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30054 | W/500295297/WS | KwaZulu-Natal | WELENI PRIMARY SCHOOL | 500295297 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-06 | 2016-03-07 | 2025-06-30 | 2027-03-31 | 2027-03-31 | 500000 | 1402000 | 1902000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30056 | W/500222629/WS | KwaZulu-Natal | MZUKELA PRIMARY SCHOOL | 500222629 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2023-03-31 | 2018-09-01 | 2021-05-31 | 338000 | 1539000 | 1877000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30067 | W/500285973/WS | KwaZulu-Natal | UBUMBANO PRIMARY SCHOOL | 500285973 | Nongoma | Construction 51% - 75% | Active - Contracted | 2014-10-14 | 2022-06-01 | 2023-06-30 | 2024-03-30 | 2025-05-30 | 873799 | 3980642 | 4854441 | Education Infrastructure Grant | Upgrading and Additions
|  | 30069 | W/500285196/WS | KwaZulu-Natal | TSHENDLOVU PRIMARY SCHOOL | 500285196 | Ulundi | Practical Completion (100%) | Active - Contracted | 2017-05-17 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2025-03-31 | 513976 | 2341445 | 2855421 | Education Infrastructure Grant | Upgrading and Additions
|  | 30071 | W/500285233/WS | KwaZulu-Natal | TSHENILOKWAZI PRIMARY SCHOOL | 500285233 | Ulundi | Tender | Active - Contracted | 2017-05-17 |  | 2025-06-30 |  |  | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30072 | W/500285344/WS | KwaZulu-Natal | TSHUTSHUTSHU SECONDARY SCHOOL | 500285344 | Maphumulo | Construction 51% - 75% | Active - Contracted | 2017-03-11 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2025-03-31 | 840323 | 3828137 | 4668460 | Education Infrastructure Grant | Upgrading and Additions
|  | 30073 | W/500286232/WS | KwaZulu-Natal | UGEDLA PRIMARY SCHOOL | 500286232 | Nongoma | Tender | Active - Contracted | 2015-01-12 |  | 2025-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30074 | W/500285529/WS | KwaZulu-Natal | TWASANA PRIMARY SCHOOL | 500285529 | Ulundi | Tender | Active - Contracted | 2015-04-06 |  | 2025-06-30 |  |  | 674420 | 3072356 | 3746776 | Education Infrastructure Grant | Upgrading and Additions
|  | 30075 | W/500286343/WS | KwaZulu-Natal | UKHAHLAMBA SECONDARY SCHOOL | 500286343 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2014-05-05 | 2018-04-27 | 2023-06-30 | 2018-09-01 | 2025-05-31 | 590000 | 2686000 | 3276000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30076 | W/500285677/WS | KwaZulu-Natal | UBIZO PRIMARY SCHOOL | 500285677 | uMhlathuze | Tender | Active - Contracted | 2017-03-11 |  | 2025-06-30 |  |  | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30077 | W/500286639/WS | KwaZulu-Natal | UKUSA SECONDARY SCHOOL | 500286639 | eThekwini | Practical Completion (100%) | Active - Contracted | 2015-01-27 | 2019-02-01 | 2022-06-30 | 2020-03-31 | 2025-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30079 | W/500306323/WS | KwaZulu-Natal | UKUSAKWABASHA PRIMARY SCHOOL | 500306323 | Mkhambathini | Construction 76% - 99% | Active - Contracted | 2015-01-26 | 2022-06-01 | 2023-06-30 | 2024-03-30 | 2025-05-30 | 805341 | 3668775 | 4474116 | Education Infrastructure Grant | Upgrading and Additions
|  | 30080 | W/500321271/WS | KwaZulu-Natal | UBONGUMENZI SECONDARY SCHOOL | 500321271 | Nqutu | Design | Active - Not Contracted | 2016-11-19 |  | 2023-06-30 |  |  | 914000 | 4163000 | 5077000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30081 | W/500286750/WS | KwaZulu-Natal | ULUNDI PRIMARY SCHOOL | 500286750 | Ulundi | Tender | Active - Contracted | 2017-05-11 |  | 2025-06-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30083 | W/500287120/WS | KwaZulu-Natal | UMBONJE SECONDARY SCHOOL | 500287120 | Msinga | Final Completion | Active - Contracted | 2015-11-15 | 2019-03-01 | 2023-06-30 | 2024-03-30 | 2025-05-30 | 1000000 | 3086407 | 4086407 | Education Infrastructure Grant | Upgrading and Additions
|  | 30085 | W/500287231/WS | KwaZulu-Natal | UMFOLOZI PRIMARY SCHOOL | 500287231 | eThekwini | Construction 76% - 99% | Active - Contracted | 2017-03-11 | 2019-03-01 | 2022-05-31 | 2023-12-25 | 2025-05-30 | 700567 | 3191472 | 3892039 | Education Infrastructure Grant | Upgrading and Additions
|  | 30087 | W/500287527/WS | KwaZulu-Natal | UMGNAMA COMBINED SCHOOL | 500287527 | uPhongolo | On Hold | Active - Not Contracted | 2017-03-11 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 0 | 3423000 | 3423000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30088 | W/500287860/WS | KwaZulu-Natal | UMHLOLUTHINI HIGH SCHOOL | 500287860 | Ulundi | Design | Approved | 2017-03-02 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30089 | W/500227735/WS | KwaZulu-Natal | CONGCO SECONDARY SCHOOL | 500227735 | Richmond | Design | Active - Not Contracted | 2016-03-30 |  | 2023-06-30 |  |  | 675655 | 3077985 | 3753640 | Education Infrastructure Grant | Upgrading and Additions
|  | 30090 | W/500287934/WS | KwaZulu-Natal | UMKHATHINI PRIMARY SCHOOL | 500287934 | Umvoti | Design | Active - Not Contracted | 2016-02-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30092 | W/500288526/WS | KwaZulu-Natal | UMNINI MEMORIAL SP | 500288526 | eThekwini | Design | Active - Not Contracted | 2017-03-05 |  | 2025-06-30 |  |  | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30093 | W/500288785/WS | KwaZulu-Natal | UMQONGQOTHO PRIMARY SCHOOL | 500288785 | The Msunduzi | Tender | Active - Contracted | 2017-03-05 |  | 2025-06-30 |  |  | 839000 | 500000 | 1339000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30095 | W/500288859/WS | KwaZulu-Natal | UMSILINGA PRIMARY SCHOOL | 500288859 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2017-03-04 | 2019-02-01 | 2023-06-30 | 2020-03-31 | 2025-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30098 | W/500289081/WS | KwaZulu-Natal | UMTHENTE HIGH SCHOOL | 500289081 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-03-11 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2025-03-31 | 1171041 | 5334741 | 6505782 | Education Infrastructure Grant | Upgrading and Additions
|  | 30099 | W/500289229/WS | KwaZulu-Natal | UMTHUNZI PRIMARY SCHOOL | 500289229 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-03-04 | 2018-02-01 | 2023-06-30 | 2018-09-01 | 2025-05-31 | 870000 | 2413000 | 3283000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30100 | W/500289266/WS | KwaZulu-Natal | UMVOLOZI PRIMARY SCHOOL | 500289266 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2017-01-11 | 2019-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 354000 | 1615000 | 1969000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30101 | W/500289340/WS | KwaZulu-Natal | UMVOZANE PRIMARY SCHOOL | 500289340 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2017-03-02 | 2019-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 1438492 | 7621573 | 9060065 | Education Infrastructure Grant | Upgrading and Additions
|  | 30106 | W/500106449/WS | KwaZulu-Natal | BAYABONGA PRIMARY SCHOOL | 500106449 | Nqutu | Design | Active - Contracted | 2016-05-11 |  | 2024-07-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30107 | W/500186702/WS | KwaZulu-Natal | LINDELANI PRIMARY SCHOOL | 500186702 | eThekwini | Design | Active - Not Contracted | 2013-10-08 |  | 2024-07-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30108 | W/500208865/WS | KwaZulu-Natal | MFUNZI PRIMARY SCHOOL | 500208865 | Msinga | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2019-02-01 | 2023-03-30 | 2023-03-31 | 2023-03-31 | 263000 | 1074000 | 1337000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30109 | DB/500223369/ECD | KwaZulu-Natal | NCAKUBANA | I/500223369/ECD | Dr Nkosazana Dlamini Zuma | Tender | Active - Contracted | 2017-04-30 |  | 2025-03-30 |  |  | 268740 | 1448260 | 1717000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30111 | W/500440966/WS | KwaZulu-Natal | EMPUMELELWENI PRIMARY SCHOOL | 500440966 | Jozini | Tender | Active - Not Contracted | 2016-02-15 |  | 2023-06-30 |  |  | 594334 | 2707520 | 3301854 | Education Infrastructure Grant | Upgrading and Additions
|  | 30112 | W/500335183/WS | KwaZulu-Natal | MFUSHANE PRIMARY SCHOOL | 500335183 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2019-02-01 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30113 | W/500208939/WS | KwaZulu-Natal | MGABHANYONGO PRIMARY SCHOOL | 500208939 | Nongoma | Tender | Active - Not Contracted | 2016-11-20 |  | 2025-03-31 |  |  | 986000 | 4494000 | 5480000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30114 | DB/500232545/WS | KwaZulu-Natal | NKOSANA HIGH SCHOOL | 500232545 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-01-29 | 2021-01-01 | 2024-01-29 | 2024-07-14 | 2027-08-31 | 346852 | 1580102 | 1926954 | Education Infrastructure Grant | Upgrading and Additions
|  | 30115 | W/500208902/WS | KwaZulu-Natal | MGABADELI PRIMARY SCHOOL | 500208902 | Jozini | Tender | Active - Contracted | 2017-02-20 |  | 2025-01-30 |  |  | 970097 | 4419331 | 5389428 | Education Infrastructure Grant | Upgrading and Additions
|  | 30118 | I/500224331/WS | KwaZulu-Natal | NDABEZIPHEZULU SECONDARY SCHOOL | W/500224331/WS | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-12-18 | 2024-07-01 | 2024-12-01 | 2024-03-31 | 337000 | 3609633 | 3946633 | Education Infrastructure Grant | Upgrading and Additions
|  | 30119 | W/500290228/WS | KwaZulu-Natal | UPPER UMVOTI COMBINED SCHOOL | 500290228 | Umvoti | Practical Completion (100%) | Active - Contracted | 2015-11-11 | 2018-04-27 | 2023-07-05 | 2022-09-01 | 2022-05-31 | 701000 | 3193000 | 3894000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30121 | W/500209050/WS | KwaZulu-Natal | MGAMULE SECONDARY SCHOOL | 500209050 | Ubuhlebezwe | Construction 26% - 50% | Active - Contracted | 2016-04-01 |  | 2023-02-16 |  |  | 815187 | 3713629 | 4528816 | Education Infrastructure Grant | Upgrading and Additions
|  | 30122 | W/500231176/WS | KwaZulu-Natal | NJOJO PRIMARY SCHOOL | 500231176 | Mtubatuba | On Hold | Active - Not Contracted | 2016-01-29 |  | 2023-03-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30123 | W/500118067/RRR | KwaZulu-Natal | COPHELA PRIMARY SCHOOL | 500118067 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-02-15 | 2016-04-01 | 2023-04-21 | 2018-03-25 | 2023-04-21 | 346000 | 1576000 | 1922000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30124 | W/500290265/WS | KwaZulu-Natal | UQWEQWE SECONDARY SCHOOL | 500290265 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2017-04-03 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 54000 | 246000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30131 | W/500213453/UA | KwaZulu-Natal | MNGOMENI SECONDARY SCHOOL | 5002134453 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2017-02-01 | 2024-03-30 | 2024-03-30 | 2024-02-16 | 1728000 | 7871000 | 9599000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30132 | I/500225478/WS | KwaZulu-Natal | NDLOVANA SECONDARY SCHOOL | 500225478 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-12-18 | 2024-07-01 | 2024-12-01 | 2024-03-30 | 0 | 1503000 | 1503000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30137 | DB/500278980/SDS | KwaZulu-Natal | GREYVILLE PRIMARY SCHOOL | 500278980 | eThekwini | Final Completion | Approved | 2016-02-15 | 2016-10-20 | 2023-07-01 | 2022-12-01 | 2023-09-12 | 1026107 | 3860119 | 4886226 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30138 | DB/500149739/WS | KwaZulu-Natal | GLENPARK PRIMARY SCHOOL | 500149739 | Umhlabuyalingana | Construction 26% - 50% | Active - Contracted | 2016-04-01 | 2020-05-31 | 2024-01-31 | 2024-03-25 | 2027-03-30 | 463708 | 2112448 | 2576156 | Education Infrastructure Grant | Upgrading and Additions
|  | 30139 | W/500213268/WS | KwaZulu-Natal | MNDENI PRIMARY SCHOOL | 500213268 | Alfred Duma | Design | Active - Not Contracted | 2016-06-13 |  | 2023-02-10 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30140 | W/500209346/WS | KwaZulu-Natal | MGEBISA PRIMARY SCHOOL | 500209346 | uMlalazi | Tender | Active - Contracted | 2016-11-20 |  | 2025-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30141 | W/500324046/WS | KwaZulu-Natal | MNAWE PRIMARY SCHOOL | 500324046 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2021-02-26 | 2024-05-31 | 2024-04-30 | 2024-02-21 | 911000 | 4151000 | 5062000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30142 | W/500209494/WS | KwaZulu-Natal | MGIGIMBE PRIMARY SCHOOL | 500209494 | KwaDukuza | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2016-04-05 | 2023-02-20 | 2023-02-20 | 2023-02-20 | 680000 | 3098000 | 3778000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30143 | W/500212972/WS | KwaZulu-Natal | MLONYENI INTERMEDIATE SCHOOL | 500212972 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-04-27 | 2024-03-30 | 2024-09-01 | 2024-01-31 | 201000 | 1032170 | 1233170 | Education Infrastructure Grant | Upgrading and Additions
|  | 30144 | W/500123987/WS | KwaZulu-Natal | DUMA PRIMARY SCHOOL | 500123987 | Mtubatuba | Tender | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30145 | W/500131498/WS | KwaZulu-Natal | EMASAKENI PRIMARY SCHOOL | 500131498 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-04-01 |  | 2024-06-30 |  |  | 1196778 | 5451989 | 6648767 | Education Infrastructure Grant | Upgrading and Additions
|  | 30146 | W/500212602/WS | KwaZulu-Natal | MLANDOWETHU SECONDARY SCHOOL | 500212602 | Nqutu | Tender | Active - Not Contracted | 2016-06-13 |  | 2023-01-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30147 | W/500212528/WS | KwaZulu-Natal | MLAMLELI PRIMARY SCHOOL | 500212528 | Newcastle | Design | Active - Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 28000 | 128000 | 156000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30148 | W/500212306/WS | KwaZulu-Natal | MKHUPHANE PRIMARY SCHOOL | 500212306 | eDumbe | Tender | Active - Not Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30149 | W/500212121/WS | KwaZulu-Natal | MKHONJANE PRIMARY SCHOOL | 500212121 | Msinga | Tender | Active - Not Contracted | 2016-06-13 |  | 2023-03-10 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30150 | DB/500207274/WS | KwaZulu-Natal | MEHLWENKOSI PRIMARY SCHOOL | 500207274 | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 310929 | 1416455 | 1727384 | Education Infrastructure Grant | Upgrading and Additions
|  | 30151 | W/500211973/WS | KwaZulu-Natal | MKHOBOSA PRIMARY SCHOOL | 500211973 | Mthonjaneni | Tender | Active - Not Contracted | 2015-06-13 |  | 2023-01-18 |  |  | 1044388 | 4757770 | 5802158 | Education Infrastructure Grant | Upgrading and Additions
|  | 30152 | I/500441928/WS | KwaZulu-Natal | MDUMISA PRIMARY SCHOOL | 500441928 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2015-02-16 | 2016-04-01 | 2024-02-22 | 2024-03-30 | 2024-11-17 | 217000 | 2439467 | 2656467 | Education Infrastructure Grant | Upgrading and Additions
|  | 30153 | I/500205905/WS | KwaZulu-Natal | Mcoseleli P | 500205905 | uMngeni | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2021-03-20 | 2023-03-30 | 2023-05-25 | 2023-07-30 | 320400 | 3085215 | 3405615 | Education Infrastructure Grant | Upgrading and Additions
|  | 30154 | I/500208273/WS | KwaZulu-Natal | MFABENI PRIMARY SCHOOL | 500208273 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2024-06-20 | 2024-10-30 | 2024-04-30 | 0 | 1464000 | 1464000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30155 | DB/500226477/WS | KwaZulu-Natal | ST JOSEPHS SECONDARY SCHOOL | 500226477 | uMngeni | Design | Active - Contracted | 2016-06-06 |  | 2024-06-20 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30156 | W/500264217/WS | KwaZulu-Natal | SIFISESIHLE PRIMARY SCHOOL | 50020906 | uMngeni | Final Completion | Active - Contracted | 2013-04-09 | 2021-02-26 | 2023-10-29 | 2022-02-28 | 2023-05-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30157 | I/500204832/CR | KwaZulu-Natal | MBONWA S | 500204832 | Umzumbe | Feasibility | Proposed | 2016-03-31 |  | 2024-03-29 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30158 | I/500204795/UA | KwaZulu-Natal | MBONISWENI PS | 500204795 | eThekwini | Feasibility | Proposed | 2016-03-31 |  | 2026-03-31 |  |  | 3600000 | 16400000 | 20000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30162 | I/500210678/WS | KwaZulu-Natal | MHONGOZINI PRIMARY SCHOOL | 500210678/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-13 | 2024-06-20 | 2024-10-01 | 2024-02-19 | 246000 | 1870000 | 2116000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30163 | I/500211344/WS | KwaZulu-Natal | MJELE SS | 500211344/WS | uMshwathi | Practical Completion (100%) | Approved | 2016-06-06 | 2021-01-15 | 2023-11-26 | 2022-05-05 | 2023-02-05 | 402000 | 2231000 | 2633000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30164 | DB/500230029/WS | KwaZulu-Natal | NHLATHIMBE HIGH SCHOOL | 500230029 | Impendle | Construction 1% - 25% | Active - Not Contracted | 2016-10-05 | 2021-01-01 | 2024-01-29 | 2024-07-14 | 2027-08-31 | 361660 | 1647563 | 2009223 | Education Infrastructure Grant | Upgrading and Additions
|  | 30165 | W/500211936/WS | KwaZulu-Natal | MKHOBENI SECONDARY SCHOOL | 500211936 | Richmond | Design | Active - Contracted | 2016-06-13 |  | 2023-02-20 |  |  | 712110 | 3244058 | 3956168 | Education Infrastructure Grant | Upgrading and Additions
|  | 30168 | W/500211825/WS | KwaZulu-Natal | MKHIZE INTERMEDIATE SCHOOL | 500211825 | Inkosi Langalibalele | Design | Active - Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 1075000 | 4899000 | 5974000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30169 | I/500217597/WS | KwaZulu-Natal | Mpungamhlophe H | I/500217597/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-05 | 2024-03-30 | 2024-03-30 | 2024-11-20 | 129000 | 586000 | 715000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30170 | I/500212269/WS | KwaZulu-Natal | MKHUNJINI PRIMARY SCHOOL | 500212269 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-06-13 | 2022-06-20 | 2022-10-01 | 2023-04-30 | 141000 | 643000 | 784000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30171 | W/500228105/WS | KwaZulu-Natal | NGILANYONI PRIMARY SCHOOL | 500228105 | Mkhambathini | Design | Active - Contracted | 2016-06-06 |  | 2023-02-07 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30176 | W/500211788/UA | KwaZulu-Natal | MKHAZENI PRIMARY SCHOOL | 500211788 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 6440000 | 29339000 | 35779000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30177 | W/500152625/WS | KwaZulu-Natal | GULUBE PRIMARY SCHOOL | 500152625 | Mkhambathini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-01-20 | 2023-06-20 | 2024-05-05 | 2025-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30179 | W/500128464/WS | KwaZulu-Natal | EKUFUNDENI PRIMARY SCHOOL | 500128464 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2016-06-10 | 2024-06-10 | 2022-06-10 | 2024-06-10 | 637000 | 2903000 | 3540000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30180 | W/500211677/WS | KwaZulu-Natal | MKHANDI PRIMARY SCHOOL | 500211677 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2020-02-01 | 2023-03-30 | 2021-04-30 | 2023-02-01 | 257000 | 1173000 | 1430000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30181 | I/500218152/WS | KwaZulu-Natal | MSEBE PRIMARY SCHOOL | 500218152 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-04-08 | 2023-03-30 | 2023-03-30 | 2023-11-11 | 108000 | 1247000 | 1355000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30183 | W/500112887/WS | KwaZulu-Natal | BUCKLANDS PRIMARY SCHOOL | 500112887 | uMshwathi | Design | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30184 | I/500218263/WS | KwaZulu-Natal | MSENI P | I/500218263/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-04-08 | 2022-05-30 | 2022-06-30 | 2023-09-19 | 108162 | 492738 | 600900 | Education Infrastructure Grant | Upgrading and Additions
|  | 30185 | I/500215007/RRR | KwaZulu-Natal | MOPHELA PRIMARY SCHOOL | 500215007 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 7099056 | 32340144 | 39439200 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30188 | W/500442520/SDS | KwaZulu-Natal | MKANGALA PRIMARY SCHOOL | 500442520 | Greater Kokstad | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-09-10 | 2023-03-01 | 2022-01-31 | 2023-03-01 | 729000 | 3424000 | 4153000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30190 | W/500211529/WS | KwaZulu-Natal | INKOSI MJWAYELI PRIMARY SCHOOL | 500211529 | Inkosi Langalibalele | Construction 51% - 75% | Active - Contracted | 2015-06-13 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-03-30 | 956893 | 4359178 | 5316071 | Education Infrastructure Grant | Upgrading and Additions
|  | 30192 | W/500211455/SDS | KwaZulu-Natal | MJINDI SECONDARY SCHOOL | 500211455 | Jozini | Design | Active - Not Contracted | 2016-06-13 |  | 2025-01-01 |  |  | 1114743 | 5078275 | 6193018 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30194 | W/500178821/SDS | KwaZulu-Natal | KWABAZOTHINI HIGH SCHOOL | 500178821 | eThekwini | Design | Active - Contracted | 2017-06-14 |  | 2024-12-28 |  |  | 131719 | 600051 | 731770 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30195 | I/500219595/WS | KwaZulu-Natal | Mthukwana P | 500219595 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-04-08 | 2023-05-30 | 2023-06-05 | 2023-11-28 | 282000 | 1287000 | 1569000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30196 | W/500211381/WS | KwaZulu-Natal | MJIKA PRIMARY SCHOOL | 500211381 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2021-02-26 | 2023-03-30 | 2021-04-30 | 2023-03-01 | 305000 | 1390000 | 1695000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30197 | DB/500215525/WS | KwaZulu-Natal | MOUNTAIN HOME PRIMARY SCHOOL | 500215525 | uMngeni | Design | Active - Contracted | 2017-06-06 |  | 2024-10-01 |  |  | 1990000 | 2310000 | 4300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30198 | W/500211196/WS | KwaZulu-Natal | MINYA PRIMARY SCHOOL | W/500211196/WS | Nongoma | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30199 | DB/500219780/ECD | KwaZulu-Natal | MTIKINI PRIMARY SCHOOL | 500219780 | Umhlabuyalingana | Tender | Active - Contracted | 2017-04-30 |  | 2025-03-30 |  |  | 565740 | 2577260 | 3143000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30200 | DB/500210974/WS | KwaZulu-Natal | MIDDELRUS PRIMARY SCHOOL | 500210974 | uMngeni | Construction 26% - 50% | Active - Contracted | 2016-06-13 | 2019-09-12 | 2024-03-31 | 2024-05-05 | 2025-01-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30202 | W/500210715/SDS | KwaZulu-Natal | MHUBHENI SECONDARY SCHOOL | 500210715 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2016-06-13 |  | 2023-01-10 |  |  | 595455 | 2712628 | 3308083 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30203 | I/500448995/LSEN | KwaZulu-Natal | MUSA SCHOOL FOR DISABLED | 500448995 | Abaqulusi | Tender | Active - Contracted | 2017-11-15 |  | 2026-03-31 |  |  | 42835500 | 195139500 | 237975000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30205 | I/500303474/WS | KwaZulu-Natal | Muziwesizwe H | I/500303474/WS | eDumbe | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-04-08 | 2022-05-30 | 2022-08-30 | 2023-03-31 | 413000 | 1881000 | 2294000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30206 | W/500414770/WS | KwaZulu-Natal | MHLWAZINI SECONDARY SCHOOL | 500414770 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-02-01 | 2024-03-30 | 2024-09-01 | 2024-02-21 | 224000 | 1190000 | 1414000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30207 | I/500237133/WS | KwaZulu-Natal | NQABAYEMBUBE SECONDARY SCHOOL | 500237133 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-12-18 | 2023-03-30 | 2023-08-01 | 2023-09-17 | 282000 | 1564000 | 1846000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30208 | I/500236911/UA | KwaZulu-Natal | NOVIMBA P | 500236911 | KwaDukuza | Design | Active - Contracted | 2017-04-01 |  | 2026-03-31 |  |  | 549000 | 2502000 | 3051000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30210 | W/500210419/WS | KwaZulu-Natal | MHLWANGWANE PRIMARY SCHOOL | 500210419 | Msinga | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-01-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30211 | DB/500270803/SDS | KwaZulu-Natal | SIYOKOMANA PRIMARY SCHOOL | 500270803 | Mfolozi | Final Completion | Approved | 2016-11-26 | 2018-03-30 | 2023-12-31 | 2019-04-05 | 2025-04-15 | 219489 | 999897 | 1219386 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30212 | W/500210567/WS | KwaZulu-Natal | MHLAMBU PRIMARY SCHOOL | 500210567 | Msinga | Tender | Active - Not Contracted | 2015-06-13 |  | 2025-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30215 | W/500210530/WS | KwaZulu-Natal | MHLUMAYO PRIMARY SCHOOL | 500210530 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-04-27 | 2024-03-30 | 2024-09-01 | 2024-01-31 | 216000 | 982000 | 1198000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30217 | W/500210493/WS | KwaZulu-Natal | MHLATHUZE PRIMARY SCHOOL | W/500210493/WS | Ulundi | Construction 1% - 25% | Active - Contracted | 2016-06-13 |  | 2023-01-30 |  |  | 843242 | 3841437 | 4684679 | Education Infrastructure Grant | Upgrading and Additions
|  | 30219 | ET/500312391/WS | KwaZulu-Natal | THANDAYIPHI SECONDARY SCHOOL | 500312391 | KwaDukuza | Final Completion | Active - Contracted | 2011-12-05 | 2018-09-10 | 2023-02-23 | 2023-04-30 | 2023-04-30 | 703009 | 3202597 | 3905606 | Education Infrastructure Grant | Upgrading and Additions
|  | 30220 | W/500210382/WS | KwaZulu-Natal | MHLANGEZULU SECONDARY SCHOOL | 500210382 | Msinga | Final Completion | Active - Contracted | 2016-06-13 | 2018-04-27 | 2023-06-30 | 2021-01-31 | 2023-03-31 | 589343 | 2684786 | 3274129 | Education Infrastructure Grant | Upgrading and Additions
|  | 30221 | W/500275502/WS | KwaZulu-Natal | ST CYPRIANS INTERMEDIATE SCHOOL | 500275502 | KwaDukuza | On Hold | Active - Not Contracted | 2015-11-25 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30222 | C/500424390/UA | KwaZulu-Natal | DRC JUNIOR SECONDARY SCHOOL (RETENDER) | 500424390 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2013-06-30 | 2016-04-01 | 2023-04-28 | 2023-02-23 | 2023-08-23 | 2691596 | 5758961 | 8450557 | Education Infrastructure Grant | Upgrading and Additions
|  | 30223 | ET/500266178/WS | KwaZulu-Natal | SIMUNYE SECONDARY SCHOOL | 500266178 | Ndwedwe | Final Completion | Active - Contracted | 2016-08-09 | 2018-09-10 | 2024-02-15 | 2024-04-30 | 2024-04-30 | 550303 | 3572697 | 4123000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30227 | DB/500204129/UA | KwaZulu-Natal | MBHEKWA HIGH SCHOOL | 500204129 | Nkandla | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2018-12-01 | 2024-03-30 | 2024-10-20 | 2027-03-04 | 6741144 | 30709656 | 37450800 | Education Infrastructure Grant | Upgrading and Additions
|  | 30229 | W/500252081/WS | KwaZulu-Natal | QALAKAHLE HIGH SCHOOL | 500252081 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2015-11-17 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-04-01 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30231 | W/500209679/WS | KwaZulu-Natal | MGQWABAGQWABA PRIMARY SCHOOL | 500209679 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-01-27 | 2023-02-20 | 2023-02-02 | 2023-02-02 | 1023240 | 4661425 | 5684665 | Education Infrastructure Grant | Upgrading and Additions
|  | 30239 | W/500209716/WS | KwaZulu-Natal | MGUDLWA SECONDARY SCHOOL | 500209716 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2017-11-20 | 2023-01-10 | 2023-01-10 | 2023-01-10 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30242 | W/500209864/WS | KwaZulu-Natal | MGWAZENI SECONDARY SCHOOL | 500209864 | Mtubatuba | Tender | Active - Contracted | 2016-06-13 |  | 2025-01-30 |  |  | 1230421 | 5605251 | 6835672 | Education Infrastructure Grant | Upgrading and Additions
|  | 30243 | W/500209901/WS | KwaZulu-Natal | MGWEMPISI-FABASE COMBINED SCHOOL | 500209901 | Msinga | On Hold | Active - Not Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 10000 | 43000 | 53000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30246 | I/500321641/WS | KwaZulu-Natal | NKALALENI PRIMARY SCHOOL | I/500321641/WS | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-10-20 | 2022-07-01 | 2022-03-20 | 2023-03-30 | 595000 | 2874000 | 3469000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30254 | W/500221519/WS | KwaZulu-Natal | MVUMASE INTERMEDIATE SCHOOL | 500221519 | Maphumulo | Construction 51% - 75% | Active - Contracted | 2016-06-06 |  | 2023-03-31 |  |  | 1052082 | 4792818 | 5844900 | Education Infrastructure Grant | Upgrading and Additions
|  | 30255 | W/500323750/WS | KwaZulu-Natal | MLAMULANKUNZI PRIMARY SCHOOL | 500323750 | Ndwedwe | Final Completion | Active - Contracted | 2016-06-06 | 2016-06-13 | 2023-06-27 | 2023-10-30 | 2023-05-31 | 298347 | 1359138 | 1657485 | Education Infrastructure Grant | Upgrading and Additions
|  | 30257 | ET/500203056/WS | KwaZulu-Natal | MAYELESWENI PRIMARY SCHOOL | 500203056 | Ndwedwe | Practical Completion (100%) | Approved | 2015-06-10 | 2015-08-10 | 2022-08-10 | 2022-08-10 | 2023-05-30 | 705767 | 3215160 | 3920927 | Education Infrastructure Grant | Upgrading and Additions
|  | 30258 | DB/500177933/SDS | KwaZulu-Natal | KUSAKUSA PRIMARY SCHOOL | 500177933 | eThekwini | Final Completion | Approved | 2015-11-20 | 2018-01-12 | 2023-06-19 | 2023-06-19 | 2025-06-19 | 1849179 | 8424039 | 10273218 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30260 | W/500426758/WS | KwaZulu-Natal | MHLABA JUNIOR SECONDARY SCHOOL | 500426758 | Umzimkhulu | Tender | Active - Contracted | 2016-06-13 |  | 2025-02-21 |  |  | 1283457 | 5846858 | 7130315 | Education Infrastructure Grant | Upgrading and Additions
|  | 30261 | W/500322122/WS | KwaZulu-Natal | MHLABUHLANGNE JUNIOR SECONDARY SCHOOL | 500322122 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2016-06-13 |  | 2023-01-30 |  |  | 998470 | 4548586 | 5547056 | Education Infrastructure Grant | Upgrading and Additions
|  | 30263 | W/500210271/WS | KwaZulu-Natal | MHLAMBANSILA HIGH SCHOOL | 500210271 | Ulundi | Construction 26% - 50% | Active - Contracted | 2016-06-13 |  | 2024-02-10 |  |  | 851000 | 3877000 | 4728000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30266 | W/500210345/WS | KwaZulu-Natal | MHLANGAMKHULU PRIMARY SCHOOL | 50021035 | Umzumbe | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-02-11 |  |  | 985000 | 4486000 | 5471000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30268 | ET/500202057/WS | KwaZulu-Natal | MAQUMBI PRIMARY SCHOOL | 500202057 | Maphumulo | Practical Completion (100%) | Approved | 2014-03-28 | 2018-09-10 | 2023-11-20 | 2023-03-30 | 2023-06-30 | 638159 | 3284841 | 3923000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30270 | W/500324194/WS | KwaZulu-Natal | MHLANGANYELWA COMBINED SCHOOL | 500324194 | Alfred Duma | Design | Active - Contracted | 2016-06-13 |  | 2023-03-15 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30274 | I/500441891/WS | KwaZulu-Natal | MZIBULI S | 500441891/S | Umhlabuyalingana | Practical Completion (100%) | Approved | 2012-06-06 | 2014-04-05 | 2023-03-30 | 2023-03-31 | 2023-09-30 | 396000 | 2199000 | 2595000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30280 | W/500171125/WS | KwaZulu-Natal | IGUGULAMANYONI PRIMARY SCHOOL | 500171125 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2016-01-29 | 2016-06-13 | 2022-06-30 | 2022-06-30 | 2025-06-30 | 744384 | 3391083 | 4135467 | Education Infrastructure Grant | Upgrading and Additions
|  | 30286 | DB/500118474/WS | KwaZulu-Natal | CRANBURN PRIMARY SCHOOL | 500118474 | Mandeni | Design | Active - Contracted | 2015-11-25 |  | 2024-02-25 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30289 | I/500303659/WS | KwaZulu-Natal | NKONZA S | I/500303659/WS | Msinga | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2021-06-03 | 2022-06-25 | 2022-11-05 | 2023-01-10 | 444600 | 2127400 | 2572000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30290 | I/500232360/CU | KwaZulu-Natal | NKONKA SECONDARY SCHOOL | 500232360 | Umzumbe | Design | Active - Contracted | 2017-04-30 |  | 2024-03-30 |  |  | 540000 | 18519000 | 19059000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30291 | W/500140193/WS | KwaZulu-Natal | ESIDIDINI PRIMARY SCHOOL | 500140193 | Newcastle | Design | Active - Not Contracted | 2016-05-11 |  | 2024-07-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30292 | DB/500293225/WS | KwaZulu-Natal | VUKUFUNDE PRIMARY SCHOOL | 500293225 | Alfred Duma | Design | Active - Contracted | 2017-06-06 |  | 2024-04-26 |  |  | 2790000 | 3110000 | 5900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30294 | W/500143819/WS | KwaZulu-Natal | EZWELETHU PRIMARY SCHOOL | 500143819 | Okhahlamba | On Hold | Active - Not Contracted | 2016-03-30 |  | 2024-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30295 | W/500156325/WS | KwaZulu-Natal | HLANGANAKAHLE PRIMARY SCHOOL | 500156325 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-03-12 | 2022-03-30 | 2023-06-21 | 2024-04-30 | 2025-04-30 | 1082118 | 4929648 | 6011766 | Education Infrastructure Grant | Upgrading and Additions
|  | 30296 | W/500143930/WS | KwaZulu-Natal | FABENI PRIMARY SCHOOL | 500143930 | Msinga | Final Completion | Active - Contracted | 2015-11-19 | 2016-08-30 | 2023-03-30 | 2023-07-27 | 2024-03-30 | 635708 | 2896004 | 3531712 | Education Infrastructure Grant | Upgrading and Additions
|  | 30299 | W/500145040/WS | KwaZulu-Natal | FLORATON PRIMARY SCHOOL | 500145040 | uMhlathuze | Tender | Active - Contracted | 2016-11-19 |  | 2025-06-30 |  |  | 764143 | 3638778 | 4402921 | Education Infrastructure Grant | Upgrading and Additions
|  | 30300 | DB/500156510/WS | KwaZulu-Natal | HLANZENI PRIMARY SCHOOL | 500156510 | Mpofana | Design | Proposed | 2017-03-02 |  | 2025-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30301 | W/500145077/WS | KwaZulu-Natal | florence booth p | 500145077 | Inkosi Langalibalele | Tender | Active - Contracted | 2017-11-19 |  | 2025-05-30 |  |  | 433288 | 1973869 | 2407157 | Education Infrastructure Grant | Upgrading and Additions
|  | 30303 | W/500156880/WS | KwaZulu-Natal | HLENGINGQONDO PRIMARY SCHOOL | 500156880 | Abaqulusi | Tender | Active - Contracted | 2016-03-06 |  | 2026-06-30 |  |  | 901692 | 4107708 | 5009400 | Education Infrastructure Grant | Upgrading and Additions
|  | 30305 | W/500145410/WS | KwaZulu-Natal | FORTMANNSPRUIT PRIMARY SCHOOL | 500145410 | uMshwathi | Final Completion | Active - Contracted | 2016-03-30 | 2017-03-30 | 2024-03-31 | 2024-08-30 | 2025-03-30 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30309 | W/500145521/WS | KwaZulu-Natal | FREDVILLE SENIOR PRIMARY SCHOOL | 500145521 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-03-30 | 2018-04-27 | 2023-05-31 | 20224-09-01 | 2025-03-29 | 550000 | 2505000 | 3055000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30312 | W/500145558/WS | KwaZulu-Natal | FREIBURG PRIMARY SCHOOL | 500145558 | eDumbe | Construction 76% - 99% | Active - Contracted | 2016-11-19 | 2018-01-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 562500 | 2562500 | 3125000 | Equitable Share | Upgrading and Additions
|  | 30313 | W/500157361/WS | KwaZulu-Natal | HLONGOMIYA PRIMARY SCHOOL | 500157361 | eDumbe | Tender | Active - Contracted | 2016-03-05 |  | 2026-03-11 |  |  | 0 | 831000 | 831000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30315 | W/500145595/WS | KwaZulu-Natal | FUKULA PRIMARY SCHOOL | 500145595 | Mtubatuba | Tender | Active - Contracted | 2016-03-30 |  | 2026-06-30 |  |  | 798879 | 3639336 | 4438215 | Education Infrastructure Grant | Upgrading and Additions
|  | 30317 | W/500145743/WS | KwaZulu-Natal | FUNDANI PRIMARY PRIMARY (WEENEN) | 500145743 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-19 | 2017-03-01 | 2023-03-30 | 2022-01-30 | 2025-04-30 | 732000 | 3334000 | 4066000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30318 | W/500158249/WS | KwaZulu-Natal | HOLWANE PRIMARY SCHOOL | 500158249 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-04-30 | 2022-03-01 | 2022-12-11 | 2022-12-28 | 2025-12-28 | 432000 | 4186840 | 4618840 | Education Infrastructure Grant | Upgrading and Additions
|  | 30319 | W/500145780/WS | KwaZulu-Natal | FUNDEDUZE PRIMARY SCHOOL | 500145780 | Umzumbe | Tender | Active - Contracted | 2016-03-30 |  | 2025-05-31 |  |  | 697000 | 3173000 | 3870000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30320 | W/500158582/WS | KwaZulu-Natal | HORSESHOE PRIMARY SCHOOL | 500158582 | Inkosi Langalibalele | Tender | Active - Contracted | 2017-03-04 |  | 2025-06-30 |  |  | 770211 | 3508739 | 4278950 | Education Infrastructure Grant | Upgrading and Additions
|  | 30322 | W/500159100/WS | KwaZulu-Natal | HURSLEY PRIMARY SCHOOL | 500159100 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2015-11-12 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 990000 | 1000000 | 1990000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30324 | W/500159248/WS | KwaZulu-Natal | HYMAN PRIMARY SCHOOL | 500159248 | Umzumbe | Tender | Active - Contracted | 2016-03-05 |  | 2026-06-30 |  |  | 96813 | 951542 | 1048355 | Education Infrastructure Grant | Upgrading and Additions
|  | 30325 | I/500230584/WS | KwaZulu-Natal | NHLUNGWANE HIGH SCHOOL | 500230584 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-10-20 | 2023-07-01 | 2017-12-01 | 2023-09-11 | 147000 | 668000 | 815000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30326 | W/500490509/SDS | KwaZulu-Natal | VEZULWAZI PRIMARY SCHOOL | 500490509 | Msinga | Design | Active - Not Contracted | 2016-04-11 |  | 2024-05-10 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30330 | W/500306730/WS | KwaZulu-Natal | IFALETHU PRIMARY SCHOOL | 500306730 | Mandeni | Practical Completion (100%) | Active - Contracted | 2017-03-05 | 2022-03-30 | 2023-03-11 | 2024-03-30 | 2025-04-30 | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30332 | W/500244496/SDS | KwaZulu-Natal | OQUNGWENI PRIMARY SCHOOL | 500244496 | Okhahlamba | Design | Active - Not Contracted | 2016-06-13 |  | 2024-03-30 |  |  | 2900000 | 4180000 | 7080000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30333 | I/500444444/WS | KwaZulu-Natal | NHLOLAMVULA P | 500444444 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2022-08-01 | 2022-06-17 | 2022-11-15 | 2023-02-05 | 415000 | 2305000 | 2720000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30334 | W/500159655/WS | KwaZulu-Natal | IHAWULETHU SECONDARY SCHOOL | 500159655 | Mthonjaneni | Design | Proposed | 2017-03-04 |  | 2023-03-29 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30336 | W/500327487/WS | KwaZulu-Natal | NGWANYA SECONDARY SCHOOL | 500327487 | Abaqulusi | Tender | Active - Contracted | 2016-05-11 |  | 2025-03-31 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30337 | W/500280978/WS | KwaZulu-Natal | THE GROVE COMBINED SCHOOL | 500280978 | uMngeni | Practical Completion (100%) | Active - Contracted | 2016-05-11 | 2020-11-01 | 2024-07-01 | 2024-02-03 | 2024-11-20 | 87000 | 413000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30338 | I/500113442/UA | KwaZulu-Natal | BUHLEBUZILE LOWER PRIMARY SCHOOL | 500113442 | uPhongolo | Construction 1% - 25% | Active - Contracted | 2016-01-29 | 2021-10-14 | 2024-09-25 | 2025-03-11 | 2025-04-16 | 13233343 | 73518574 | 86751917 | Education Infrastructure Grant | Upgrading and Additions
|  | 30340 | I/500401376/WS | KwaZulu-Natal | NHLAKANIPHO PRIMARY SCHOOL | 500401376 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2016-10-20 | 2022-07-01 | 2022-12-01 | 2023-11-10 | 422000 | 1924000 | 2346000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30341 | I/500121582/UA | KwaZulu-Natal | DINGUKWAZI SECONDARY SCHOOL | 500121582 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2017-04-30 | 2022-09-18 | 2022-09-30 | 2022-09-30 | 2023-03-30 | 15316577 | 83938446 | 99255023 | Equitable Share | Upgrading and Additions
|  | 30343 | W/500159951/WS | KwaZulu-Natal | IKHUSANA COMBINED SCHOOL | 500159951 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2017-03-04 | 2022-03-30 | 2023-03-11 | 2024-03-30 | 2025-04-30 | 1231972 | 5612319 | 6844291 | Education Infrastructure Grant | Upgrading and Additions
|  | 30344 | I/500442816/CU | KwaZulu-Natal | NGWEYONKE SECONDARY SCHOOL | 500442816 | Umzumbe | Design | Active - Contracted | 2017-04-30 |  | 2024-03-30 |  |  | 4071270 | 15315730 | 19387000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30346 | I/500194657/WS | KwaZulu-Natal | MAKHOSINI PRIMARY SCHOOL | I/500194657/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-02-26 | 2022-03-31 | 2023-09-30 | 2023-10-01 | 2023-10-30 | 221486 | 1230480 | 1451966 | Education Infrastructure Grant | Upgrading and Additions
|  | 30347 | W/500441817/WS | KwaZulu-Natal | IKHWEZI PRIMARY SCHOOL | 500441817 | Umhlabuyalingana | Construction 1% - 25% | Active - Contracted | 2017-03-02 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 777272 | 3540908 | 4318180 | Education Infrastructure Grant | Upgrading and Additions
|  | 30348 | I/500282902/UA | KwaZulu-Natal | THOLULWAZI SENIOR PRIMARY SCHOOL | 500327487 | uPhongolo | Tender | Active - Contracted | 2012-02-29 |  | 2026-03-31 |  |  | 16732017 | 10475000 | 27207017 | Education Infrastructure Grant | Upgrading and Additions
|  | 30350 | W/500145928/UA | KwaZulu-Natal | FUNDUKHALIPHE PRIMARY SCHOOL | 500145928 | Nongoma | Design | Active - Not Contracted | 2016-03-31 |  | 2024-06-30 |  |  | 4320000 | 19680000 | 24000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30353 | W/500159988/WS | KwaZulu-Natal | IKHWEZILAMACHI PRIMARY SCHOOL | 500159988 | uMuziwabantu | Tender | Active - Contracted | 2017-03-04 |  | 2025-06-30 |  |  | 1508616 | 6872586 | 8381202 | Education Infrastructure Grant | Upgrading and Additions
|  | 30354 | I/500427239/NS | KwaZulu-Natal | NGQUMARENI JS | 500427239 | Dr Nkosazana Dlamini Zuma | Feasibility | Active - Contracted | 2017-04-20 |  | 2026-03-31 |  |  | 507000 | 2311000 | 2818000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 30356 | W/500160025/WS | KwaZulu-Natal | IKHWEZILOKUSA PRIMARY SCHOOL | 500160025 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2016-03-05 | 2022-03-30 | 2023-05-11 | 2024-04-30 | 2025-04-30 | 1300274 | 5923471 | 7223745 | Education Infrastructure Grant | Upgrading and Additions
|  | 30357 | W/500145965/WS | KwaZulu-Natal | FUNDUKHUPHUKE PRIMARY SCHOOL | 500145965 | Nongoma | Tender | Active - Contracted | 2016-11-19 |  | 2026-06-30 |  |  | 696306 | 3172062 | 3868368 | Education Infrastructure Grant | Upgrading and Additions
|  | 30359 | DB/500160247/WS | KwaZulu-Natal | ILANGA PRIMARY SCHOOL | 500160247 | Mpofana | Design | Proposed | 2017-03-06 |  | 2024-03-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30362 | I/500196581/WS | KwaZulu-Natal | MANDULUZA PRIMARY SCHOOL | 500196581 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2014-11-27 | 2021-08-25 | 2023-03-30 | 2022-03-30 | 2023-03-31 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30363 | W/500146113/WS | KwaZulu-Natal | FUNULWAZI SECONDARY SCHOOL | 500146113 | Msinga | Final Completion | Active - Contracted | 2015-11-19 | 2017-03-30 | 2023-03-30 | 2023-04-30 | 2024-03-30 | 665404 | 3031283 | 3696687 | Education Infrastructure Grant | Upgrading and Additions
|  | 30364 | I/500197802/WS | KwaZulu-Natal | MANYONI PRIMARY SCHOOL | 500197802 | Nongoma | Practical Completion (100%) | Active - Contracted | 2014-12-31 | 2016-04-01 | 2023-03-30 | 2022-03-30 | 2023-03-31 | 385000 | 2137000 | 2522000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30365 | W/500146483/WS | KwaZulu-Natal | GABANGEZWA SECONDARY SCHOOL | 500146483 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-05-19 | 2016-09-04 | 2023-03-30 | 2019-03-30 | 2025-03-30 | 349000 | 1589000 | 1938000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30366 | W/500141636/WS | KwaZulu-Natal | ESOKHENI SECONDARY SCHOOL | 500141636 | Umvoti | Tender | Active - Contracted | 2016-01-29 |  | 2025-02-28 |  |  | 394000 | 1796000 | 2190000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30368 | W/500446257/WS | KwaZulu-Natal | GADOKUWAYO PRIMARY SCHOOL | 500446257 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-03-30 | 2017-03-30 | 2022-06-30 | 2023-03-30 | 2024-04-30 | 849420 | 3869580 | 4719000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30373 | W/500161394/WS | KwaZulu-Natal | IMPUPHUSI PRIMARY SCHOOL | 500161394 | Nongoma | Tender | Active - Contracted | 2016-03-11 |  | 2026-04-11 |  |  | 0 | 1234000 | 1234000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30374 | W/500147038/WS | KwaZulu-Natal | GANGEYANA PRIMARY SCHOOL | 500147038 | Msinga | Tender | Active - Contracted | 2015-11-19 |  | 2026-06-30 |  |  | 680635 | 3100671 | 3781306 | Education Infrastructure Grant | Upgrading and Additions
|  | 30375 | W/500326377/WS | KwaZulu-Natal | IMVELOYAMASWAZI PRIMARY SCHOOL | 500326377 | Ulundi | Practical Completion (100%) | Active - Contracted | 2017-03-04 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-04-30 | 1088051 | 4956676 | 6044727 | Education Infrastructure Grant | Upgrading and Additions
|  | 30376 | DB/500147149/WS | KwaZulu-Natal | GARTMORE PRIMARY SCHOOL | 500147149 | uMngeni | Design | Active - Not Contracted | 2016-03-30 |  | 2024-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30377 | I/500200540/WS | KwaZulu-Natal | MASHIYANE PRIMARY SCHOOL | 500200540 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-03-27 | 2016-04-01 | 2023-03-30 | 2022-03-30 | 2023-03-31 | 189540 | 1053000 | 1242540 | Education Infrastructure Grant | Upgrading and Additions
|  | 30378 | W/500161542/RRR | KwaZulu-Natal | INALA PRIMARY SCHOOL | 500161542 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2015-01-15 | 2015-01-20 | 2023-09-16 | 2016-09-16 | 2025-03-29 | 1891000 | 8617000 | 10508000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30380 | I/500326118/WS | KwaZulu-Natal | MASIPHULA JS | 500326118 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2016-05-29 | 2022-03-26 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 180000 | 2047000 | 2227000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30382 | I/500315388UA | KwaZulu-Natal | INGULULE PRIMARY SCHOOL | 500315388 | Mandeni | Design | Active - Contracted | 2016-06-13 |  | 2026-03-31 |  |  | 198000 | 7698000 | 7896000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30383 | I/500201798/WS | KwaZulu-Natal | MATHOLE HIGH SCHOOL | 500201798 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-03-25 | 2022-04-01 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 228000 | 1568000 | 1796000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30384 | I/500202020/WS | KwaZulu-Natal | MATIMATOLO PRIMARY SCHOOL | 500202020 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-06-28 | 2017-03-30 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 430560 | 1961440 | 2392000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30385 | I/500202538/WS | KwaZulu-Natal | MAVUMBUKA SECONDARY SCHOOL | 500202538 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-02-01 | 2017-03-30 | 2023-03-30 | 2022-03-30 | 2023-08-28 | 325099 | 1806107 | 2131206 | Education Infrastructure Grant | Upgrading and Additions
|  | 30386 | C/500113664/UA | KwaZulu-Natal | BULWER PRIMARY SCHOOL | 500113664 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2016-06-06 |  | 2026-12-31 |  |  | 6250000 | 18952000 | 25202000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30388 | W/500147334/WS | KwaZulu-Natal | GAYISANI PRIMARY SCHOOL | 500147334 | Msinga | Practical Completion (100%) | Active - Contracted | 2015-11-19 | 2018-04-27 | 2023-03-30 | 2023-03-29 | 2024-09-30 | 342308 | 1769884 | 2112192 | Education Infrastructure Grant | Upgrading and Additions
|  | 30389 | W/500200392/WS | KwaZulu-Natal | MASHINGA SECONDARY SCHOOL | 500147556 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-01-05 | 2017-02-15 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30392 | W/500148407/WS | KwaZulu-Natal | GEZAHLALE PRIMARY SCHOOL | 500148407 | Nqutu | Tender | Active - Contracted | 2016-03-31 |  | 2026-03-31 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30394 | I/500203278/WS | KwaZulu-Natal | Mayizekanye P | I/500203278/WS | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-06-28 | 2021-10-15 | 2022-10-22 | 2022-10-01 | 2023-01-03 | 250000 | 1388000 | 1638000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30395 | DB/500133718/SDS | KwaZulu-Natal | EMOYENI PRIMARY SCHOOL | 500133718 | uMlalazi | Practical Completion (100%) | Approved | 2016-03-31 | 2016-08-01 | 2024-03-30 | 2019-12-10 | 2024-03-30 | 584064 | 2660735 | 3244799 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30397 | I/500194583/WS | KwaZulu-Natal | MAKHAME P | I/500194583/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2022-03-03 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 511000 | 2841000 | 3352000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30398 | I/500309172/WS | KwaZulu-Natal | Mazonke H | I/500309172/WS | Ulundi | Practical Completion (100%) | Active - Contracted | 2014-12-31 | 2016-04-01 | 2022-04-27 | 2022-04-27 | 2023-04-27 | 264000 | 1468000 | 1732000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30400 | W/500134421/WS | KwaZulu-Natal | EMPUCUKWENI PRIMARY SCHOOL | 500134421 | Ulundi | Tender | Active - Not Contracted | 2015-11-04 |  | 2026-07-19 |  |  | 630000 | 2000000 | 2630000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30403 | W/500312317/WS | KwaZulu-Natal | GENGESHE PRIMARY SCHOOL | 500312317 | Richmond | Practical Completion (100%) | Active - Contracted | 2016-03-31 | 2022-03-15 | 2023-09-30 | 2024-09-30 | 2025-09-30 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30405 | W/500175639/SDS | KwaZulu-Natal | KHUTHALANI PRIMARY SCHOOL | 500175639 | Okhahlamba | Final Completion | Active - Contracted | 2017-06-06 | 2018-06-10 | 2023-03-29 | 2022-03-29 | 2022-03-29 | 184397 | 840029 | 1024426 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30406 | W/500134199/WS | KwaZulu-Natal | EMPILWENI JS | 500134199 | Nongoma | Tender | Active - Not Contracted | 2015-11-05 |  | 2024-06-30 |  |  | 1007345 | 4589016 | 5596361 | Education Infrastructure Grant | Upgrading and Additions
|  | 30407 | I/500326303/WS | KwaZulu-Natal | QALOKUSHA PRIMARY SCHOOL | 500326303 | Nongoma | Construction 51% - 75% | Active - Contracted | 2016-06-13 | 2016-08-04 | 2023-03-30 | 2022-03-30 | 2023-02-20 | 287640 | 1310360 | 1598000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30408 | W/500148111/WS | KwaZulu-Natal | GEM PRIMARY SCHOOL | 500148111 | Ndwedwe | Tender | Active - Contracted | 2016-03-31 |  | 2028-05-28 |  |  | 808359 | 3682525 | 4490884 | Education Infrastructure Grant | Upgrading and Additions
|  | 30412 | W/500206793/WS | KwaZulu-Natal | MDUTSHULWA PRIMARY SCHOOL | 500206793 | Dannhauser | Design | Active - Not Contracted | 2015-04-01 |  | 2023-01-30 |  |  | 68000 | 308000 | 376000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30415 | DB/500303696/SDS | KwaZulu-Natal | OKHULANA PRIMARY SCHOOL | 500327154 | Msinga | Final Completion | Approved | 2016-06-06 | 2017-05-20 | 2025-08-20 | 2019-05-20 | 2025-08-20 | 308000 | 1403000 | 1711000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30424 | W/500135198/WS | KwaZulu-Natal | EMTULWA PRIMARY SCHOOL | 500135198 | uMshwathi | Practical Completion (100%) | Approved | 2015-03-05 | 2016-03-09 | 2023-06-30 | 2021-06-30 | 2024-06-30 | 0 | 734397 | 734397 | Education Infrastructure Grant | Upgrading and Additions
|  | 30426 | W/500135346/WS | KwaZulu-Natal | EMWANENI PRIMARY SCHOOL | 500135346 | Impendle | Final Completion | Active - Contracted | 2017-03-06 | 2018-03-08 | 2023-06-30 | 2021-06-30 | 2024-06-30 | 1255640 | 5720136 | 6975776 | Education Infrastructure Grant | Upgrading and Additions
|  | 30427 | W/500135272/WS | KwaZulu-Natal | EMVUNYANE SECONDARY SCHOOL | 500135272 | Abaqulusi | Tender | Active - Not Contracted | 2016-03-03 |  | 2028-12-05 |  |  | 0 | 980000 | 980000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30430 | W/500325452/SDS | KwaZulu-Natal | TONGAAT SPECIAL SCHOOL LSEN | 500325452 | eThekwini | Tender | Active - Contracted | 2016-06-29 |  | 2025-06-30 |  |  | 0 | 270000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30434 | W/500284345/WS | KwaZulu-Natal | TONYELANA PRIMARY SCHOOL | 500284345 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2016-06-29 | 2018-04-27 | 2023-06-30 | 2018-09-01 | 2025-05-31 | 371540 | 3765210 | 4136750 | Education Infrastructure Grant | Upgrading and Additions
|  | 30436 | W/500284863/UA | KwaZulu-Natal | TRUSTFEED COMBINED SCHOOL | 500284863 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2014-09-12 | 2015-03-01 | 2022-06-30 | 2018-03-28 | 2025-05-31 | 3524000 | 16052000 | 19576000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30437 | W/500135642/WS | KwaZulu-Natal | ENCUTSHE PRIMARY SCHOOL | 500135642 | Abaqulusi | Practical Completion (100%) | Approved | 2015-11-14 | 2022-05-28 | 2023-05-05 | 2023-07-31 | 2024-04-19 | 666004 | 3034018 | 3700022 | Education Infrastructure Grant | Upgrading and Additions
|  | 30440 | W/500135716/WS | KwaZulu-Natal | ENDABENHLE PRIMARY SCHOOL | 500135716 | Mthonjaneni | Tender | Active - Contracted | 2016-03-04 |  | 2023-05-11 |  |  | 667945 | 3042863 | 3710808 | Education Infrastructure Grant | Upgrading and Additions
|  | 30442 | W/500135827/WS | KwaZulu-Natal | ENDAKANE SECONDARY SCHOOL | 500135827 | Alfred Duma | Practical Completion (100%) | Approved | 2017-03-04 | 2018-02-28 | 2022-04-06 | 2022-02-03 | 2022-11-20 | 0 | 994000 | 994000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30446 | W/500135975/WS | KwaZulu-Natal | ENDLOVUKAZI SECONDARY SCHOOL | 500135975 | Ulundi | Tender | Active - Contracted | 2015-03-04 |  | 2026-06-30 |  |  | 0 | 1761000 | 1761000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30448 | W/500285899/WS | KwaZulu-Natal | UBUHLEBESIZWE JUNIOR SECONDARY | 500285899 | eThekwini | On Hold | Active - Not Contracted | 2016-06-29 | 2021-02-26 | 2023-06-30 | 2025-02-28 | 2025-03-31 | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30452 | W/500136012/WS | KwaZulu-Natal | ENDLOZANA PRIMARY SCHOOL | 500136012 | Nongoma | Final Completion | Active - Contracted | 2017-03-14 | 2017-03-16 | 2023-06-30 | 2022-05-20 | 2022-06-30 | 986919 | 4495964 | 5482883 | Education Infrastructure Grant | Upgrading and Additions
|  | 30458 | ET/500225996/WS | KwaZulu-Natal | NDUNAKAZI COMBINED PRIMARY SCHOOL | 500225996 | eThekwini | Practical Completion (100%) | Active - Contracted | 2018-03-12 | 2022-06-29 | 2023-06-29 | 2024-06-29 | 2025-06-29 | 670698 | 3055400 | 3726098 | Education Infrastructure Grant | Upgrading and Additions
|  | 30460 | W/500124801/UA | KwaZulu-Natal | DUNDEE SECONDARY SCHOOL | 500124801 | Endumeni | Construction 76% - 99% | Active - Contracted | 2016-06-29 | 2017-01-26 | 2023-04-30 | 2022-04-30 | 2022-04-30 | 11326612 | 51599009 | 62925621 | Education Infrastructure Grant | Upgrading and Additions
|  | 30462 | DB/500109927/WS | KwaZulu-Natal | BHUNGANE HIGH SCHOOL | 500109927 | Inkosi Langalibalele | Design | Active - Not Contracted | 2018-04-11 |  | 2024-03-25 |  |  | 2000385 | 7525259 | 9525644 | Education Infrastructure Grant | Upgrading and Additions
|  | 30467 | W/500136937/WS | KwaZulu-Natal | ENHLANGANISWENI PRIMARY SCHOOL | 500136937 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2016-03-02 |  | 2026-06-30 |  |  | 736502 | 3355174 | 4091676 | Education Infrastructure Grant | Upgrading and Additions
|  | 30469 | W/500137603/WS | KwaZulu-Natal | ENKEMBENI PRIMARY SCHOOL | 500137603 | eDumbe | Tender | Active - Not Contracted | 2021-06-09 |  | 2023-03-20 |  |  | 0 | 1799000 | 1799000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30471 | W/500138010/WS | KwaZulu-Natal | ENKUNGWINI PRIMARY SCHOOL | 500138010 | Umzumbe | Tender | Active - Not Contracted | 2017-03-05 |  | 2026-05-14 |  |  | 621000 | 2830000 | 3451000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30475 | W/500137122/WS | KwaZulu-Natal | ENHLISA PRIMARY SCHOOL | 500137122 | uMlalazi | Tender | Active - Contracted | 2019-03-05 |  | 2026-06-30 |  |  | 785792 | 3579721 | 4365513 | Education Infrastructure Grant | Upgrading and Additions
|  | 30477 | W/500137085/WS | KwaZulu-Natal | ENHLANZINI PRIMARY SCHOOL | 500137085 | Mfolozi | Practical Completion (100%) | Approved | 2016-03-05 | 2020-11-20 | 2023-06-30 | 2023-03-31 | 2024-04-19 | 785792 | 3579721 | 4365513 | Education Infrastructure Grant | Upgrading and Additions
|  | 30478 | W/500425056/WS | KwaZulu-Natal | ENGWAQA SECONDARY SCHOOL | 500425056 | Umzimkhulu | Tender | Active - Not Contracted | 2017-03-04 |  | 2026-05-30 |  |  | 1192397 | 5432029 | 6624426 | Education Infrastructure Grant | Upgrading and Additions
|  | 30486 | W/500165494/WS | KwaZulu-Natal | EMZWENI PRIMARY SCHOOL | 500165494 | Msinga | Tender | Active - Not Contracted | 2015-11-09 |  | 2026-06-30 |  |  | 1000000 | 2349000 | 3349000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30488 | W/500134902/WS | KwaZulu-Natal | EMTHONJENI PRIMARY SCHOOL | 500134902 | Jozini | Tender | Active - Not Contracted | 2017-03-04 |  | 2026-04-21 |  |  | 0 | 680000 | 680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30490 | W/500134162/WS | KwaZulu-Natal | EMPHISE PRIMARY SCHOOL | 500134162 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2017-03-05 | 2019-02-01 | 2022-09-11 | 2022-03-31 | 2022-05-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30494 | W/500143042/WS | KwaZulu-Natal | EZAKHENI SECONDARY SCHOOL | 500143042 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2016-09-20 | 2017-11-30 | 2023-03-30 | 2022-01-30 | 2025-08-31 | 0 | 656000 | 656000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30496 | W/500142894/WS | KwaZulu-Natal | EWUBWINI PRIMARY SCHOOL | 500142894 | eThekwini | Final Completion | Active - Contracted | 2016-04-01 | 2022-03-02 | 2023-06-30 | 2024-08-02 | 2025-09-30 | 1245995 | 5676199 | 6922194 | Education Infrastructure Grant | Upgrading and Additions
|  | 30497 | W/500142339/WS | KwaZulu-Natal | ETHULENI PRIMARY SCHOOL | 500142339 | Alfred Duma | Tender | Active - Contracted | 2016-11-20 |  | 2025-05-30 |  |  | 624591 | 2845357 | 3469948 | Education Infrastructure Grant | Upgrading and Additions
|  | 30498 | W/500142006/WS | KwaZulu-Natal | ESWENI PRIMARY SCHOOL | 500142006 | Msinga | Tender | Active - Contracted | 2015-11-20 |  | 2026-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30504 | W/500141969/WS | KwaZulu-Natal | ESUSWENI PRIMARY SCHOOL | 500141969 | Nongoma | Construction 76% - 99% | Active - Contracted | 2016-11-20 | 2022-03-02 | 2023-05-20 | 2024-08-02 | 2025-09-30 | 539055 | 2455695 | 2994750 | Education Infrastructure Grant | Upgrading and Additions
|  | 30505 | W/500141784/WS | KwaZulu-Natal | ESTCOURT PRIMARY SCHOOL | 500141784 | Inkosi Langalibalele | Design | Active - Not Contracted | 2015-11-20 |  | 2023-11-30 |  |  | 994031 | 4528365 | 5522396 | Education Infrastructure Grant | Upgrading and Additions
|  | 30509 | W/500141081/WS | KwaZulu-Natal | ESIPHIVA PRIMARY SCHOOL | 500141081 | Ulundi | Tender | Approved | 2016-11-20 |  | 2026-05-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30514 | C/500171273/ECD | KwaZulu-Natal | JIKAZA PRIMARY SCHOOL | 500171273 | Ulundi | Practical Completion (100%) | Active - Contracted | 2014-04-25 | 2015-03-25 | 2023-11-24 | 2017-10-27 | 2025-10-27 | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30515 | W/500169349/WS | KwaZulu-Natal | ISUBALASHA PRIMARY SCHOOL | 500169349 | Umdoni | Practical Completion (100%) | Active - Contracted | 2013-08-27 | 2014-01-27 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1438009 | 6550928 | 7988937 | Education Infrastructure Grant | Upgrading and Additions
|  | 30516 | W/School Maintenance/AMAJ | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 |  | 2024-06-30 |  |  | 0 | 27089000 | 27089000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30517 | W/500188293/WS | KwaZulu-Natal | LUFAFA PRIMARY SCHOOL | 500188293 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2016-09-13 | 2023-06-30 | 2024-07-30 | 2025-08-30 | 868854 | 3958114 | 4826968 | Education Infrastructure Grant | Upgrading and Additions
|  | 30518 | W/School Maintenance/ILE | KwaZulu-Natal | MAINTENANCE DISTRICTS ILEMBE | 50000000 | KwaDukuza | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 |  | 2023-06-30 |  |  | 0 | 50481000 | 50481000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30519 | W/School Maintenance/PTWN | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2018-04-01 |  | 2024-06-30 |  |  | 1982000 | 53096000 | 55078000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30520 | W/School Maintenance/UMLZ | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2018-04-01 |  | 2024-06-30 |  |  | 1892000 | 8620000 | 10512000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30522 | W/School Maintenance/UGU | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 |  | 2024-06-30 |  |  | 1574000 | 24342000 | 25916000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30525 | W/School Maintenance/HG | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2015-06-14 |  | 2024-06-30 |  |  | 0 | 760000000 | 760000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30526 | W/School Maintenance/UMGU | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 |  | 2024-06-30 |  |  | 1391000 | 36317000 | 37708000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30527 | W/School Maintenance/UMKH | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 |  | 2024-06-30 |  |  | 1733000 | 29854000 | 31587000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30529 | C/500427905/ECD | KwaZulu-Natal | SAMARIA PS | C/500427905/ECD | Umzimkhulu | Construction 76% - 99% | Active - Contracted | 2016-06-30 | 2017-07-20 | 2023-05-25 | 2023-07-15 | 2023-11-30 | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30530 | DB/500259000/WS | KwaZulu-Natal | SAVELA PRIMARY SCHOOL | 500259000 | Ubuhlebezwe | Construction 26% - 50% | Active - Contracted | 2016-06-30 |  | 2024-05-31 |  |  | 395000 | 1799000 | 2194000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30531 | W/500206534/WS | KwaZulu-Natal | MDULASHI JUNIOR SECONDARY SCHOOL | 500206534 | uMuziwabantu | Design | Active - Contracted | 2016-06-22 |  | 2023-03-30 |  |  | 463310 | 2110636 | 2573946 | Education Infrastructure Grant | Upgrading and Additions
|  | 30541 | W/500257298/WS | KwaZulu-Natal | SAHLUMBE HIGH SCHOOL | 500257298 | Alfred Duma | Design | Active - Not Contracted | 2016-04-13 |  | 2023-06-30 |  |  | 287000 | 1413000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30551 | W/500140600/WS | KwaZulu-Natal | ESIKHOTHO PRIMARY SCHOOL | 500140600 | uMshwathi | Feasibility | Proposed | 2016-04-01 |  | 2022-09-30 |  |  | 90000 | 410000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30552 | W/500139749/WS | KwaZulu-Natal | ESETHU SECONDARY SCHOOL | 500139749 | Msinga | Tender | Active - Not Contracted | 2015-11-20 |  | 2026-03-30 |  |  | 0 | 2075000 | 2075000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30553 | W/500139009/WS | KwaZulu-Natal | ENYATHI INTERMEDIATE SCHOOL | 500139009 | Abaqulusi | Tender | Active - Not Contracted | 2015-11-20 |  | 2023-06-30 |  |  | 928307 | 4228956 | 5157263 | Education Infrastructure Grant | Upgrading and Additions
|  | 30554 | C/500280016/FSS | KwaZulu-Natal | THAKAZELA PRIMARY SCHOOL | 500280016 | Abaqulusi | On Hold | Active - Contracted | 2015-07-04 |  | 2023-10-27 |  |  | 771000 | 7000000 | 7771000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30557 | W/500276797/WS | KwaZulu-Natal | ST THERESA PRIMARY SCHOOL | 500276797 | Umzumbe | Tender | Active - Not Contracted | 2016-07-01 |  | 2026-06-30 |  |  | 1067950 | 4865107 | 5933057 | Education Infrastructure Grant | Upgrading and Additions
|  | 30558 | W/500138898/WS | KwaZulu-Natal | ENYANDENI PRIMARY | 500138898 | uMuziwabantu | Practical Completion (100%) | Active - Contracted | 2016-11-20 | 2018-12-01 | 2023-03-30 | 2022-06-20 | 2023-04-04 | 302000 | 1375000 | 1677000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30565 | DB/500216413/SDS | KwaZulu-Natal | MPHATHISWANA P | DB/500216191/SDS | Mfolozi | Feasibility | Active - Not Contracted | 2016-05-20 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30566 | W/500143560/WS | KwaZulu-Natal | EZINDLOVINI PRIMARY SCHOOL | 500143560 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2021-03-02 | 2023-10-31 | 2024-02-02 | 2024-08-30 | 1191208 | 5426616 | 6617824 | Education Infrastructure Grant | Upgrading and Additions
|  | 30568 | W/500425278/WS | KwaZulu-Natal | EZIMPUNGENI JUNIOR SECONDARY SCHOOL | 500425278 | Umzimkhulu | Tender | Active - Contracted | 2016-04-01 |  | 2026-10-30 |  |  | 1352600 | 6161843 | 7514443 | Education Infrastructure Grant | Upgrading and Additions
|  | 30570 | DB/500152847/SDS | KwaZulu-Natal | GWEGWEDE PRIMARY SCHOOL | 500152847 | Big Five Hlabisa | Design | Active - Contracted | 2015-09-10 |  | 2024-03-30 |  |  | 252439 | 1150001 | 1402440 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30571 | W/500143338/WS | KwaZulu-Natal | EZILOZINI PRIMARY SCHOOL | 500143338 | Nkandla | Tender | Active - Contracted | 2016-04-01 |  | 2025-05-05 |  |  | 452526 | 2061509 | 2514035 | Education Infrastructure Grant | Upgrading and Additions
|  | 30574 | DB/500173160/SDS | KwaZulu-Natal | KHANDALESIZWE JUNIOR SECONDARY SCHOOL | 500173160 | Ray Nkonyeni | Final Completion | Approved | 2016-01-06 | 2016-07-07 | 2023-09-01 | 2019-02-06 | 2024-03-08 | 329193 | 1238394 | 1567587 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30577 | DB/500203463/SDS | KwaZulu-Natal | MBALANE PRIMARY SCHOOL | 500203463 | Umvoti | Feasibility | Active - Contracted | 2016-09-20 |  | 2023-02-21 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30578 | I/500138269/WS | KwaZulu-Natal | ENSUKANGIHLALE PRIMARY SCHOOL | 500138269 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-02 | 2016-10-20 | 2023-03-30 | 2022-03-31 | 2024-03-30 | 391000 | 1782000 | 2173000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30580 | W/500141155/WS | KwaZulu-Natal | ESIPHUKWINI PRIMARY SCHOOL | 500141155 | eThekwini | Construction 1% - 25% | Active - Contracted | 2016-04-01 | 2022-05-28 | 2022-05-28 | 2022-06-28 | 2023-02-28 | 771725 | 3515636 | 4287361 | Education Infrastructure Grant | Upgrading and Additions
|  | 30581 | W/500139120/WS | KwaZulu-Natal | ENYOKENI PRIMARY SCHOOL | 500139120 | Maphumulo | Tender | Active - Contracted | 2016-04-01 |  | 2024-06-30 |  |  | 686574 | 3127724 | 3814298 | Education Infrastructure Grant | Upgrading and Additions
|  | 30583 | DB/500132978/SDS | KwaZulu-Natal | EMKHAMO COMBINED SCHOOL | 500132978 | Msinga | Final Completion | Approved | 2016-01-03 | 2016-07-27 | 2023-04-26 | 2023-04-26 | 2024-03-26 | 45383 | 206745 | 252128 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30584 | DB/500133015/SDS | KwaZulu-Natal | EMKHANDLWINI PRIMARY SCHOOL | 500133015 | Mthonjaneni | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 360000 | 1945044 | 2305044 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30604 | W/500326932/WS | KwaZulu-Natal | NGWENYABEYIGWINYA PRIMARY SCHOOL | 500326932 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-05-02 | 2016-07-11 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 700567 | 3191472 | 3892039 | Education Infrastructure Grant | Upgrading and Additions
|  | 30605 | W/500229104/WS | KwaZulu-Natal | NGWABI PRIMARY SCHOOL | 500229104 | Nongoma | Construction 26% - 50% | Active - Contracted | 2016-11-20 | 2016-11-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 834181 | 3800158 | 4634339 | Education Infrastructure Grant | Upgrading and Additions
|  | 30609 | W/500246642/WS | KwaZulu-Natal | PAULPIETERSBURG PRIMARY SCHOOL (MAARSCHALK ST) | 500246642 | Abaqulusi | Tender | Active - Contracted | 2016-06-06 |  | 2026-02-28 |  |  | 691000 | 3290000 | 3981000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30610 | I/500490509/WS | KwaZulu-Natal | VEZULWAZI PRIMARY SCHOOL | 500490509 | Msinga | Practical Completion (100%) | Active - Contracted | 2017-06-10 | 2018-11-30 | 2023-02-10 | 2023-02-10 | 2023-02-10 | 211000 | 960000 | 1171000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30611 | I/500164169/CU | KwaZulu-Natal | INHLAZUKA PRIMARY SCHOOL | 500164169 | Richmond | Design | Active - Not Contracted | 2012-03-15 |  | 2024-06-03 |  |  | 123691 | 1591570 | 1715261 | Education Infrastructure Grant | Upgrading and Additions
|  | 30612 | I/500124267/UA | KwaZulu-Natal | MOFU JUNIOR PRIMARY SCHOOL | 500214267 | eThekwini | Construction 76% - 99% | Active - Contracted | 2012-05-10 | 2022-03-30 | 2022-09-10 | 2022-09-30 | 2023-09-30 | 1841000 | 8388000 | 10229000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30660 | I/500204277/UA | KwaZulu-Natal | Mbhanana Zenex Primary School | 500204277 | eThekwini | Design | Active - Contracted | 2012-03-10 |  | 2026-03-31 |  |  | 320441 | 1348667 | 1669108 | Education Infrastructure Grant | Upgrading and Additions
|  | 30671 | ET/500232730/WS | KwaZulu-Natal | NKOSINATHI SECONDARY SCHOOL | 500232730 | eThekwini | Practical Completion (100%) | Active - Contracted | 2018-02-03 | 2023-04-06 | 2023-04-06 | 2024-04-06 | 2025-04-06 | 874103 | 3982026 | 4856129 | Education Infrastructure Grant | Upgrading and Additions
|  | 30672 | W/500136789/RRR | KwaZulu-Natal | ENGWENI PRIMARY SCHOOL | 500136789 | Mtubatuba | Design | Active - Contracted | 2018-01-01 |  | 2024-05-30 |  |  | 1375272 | 6265128 | 7640400 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30673 | ET/500234950/WS | KwaZulu-Natal | NOMFIHLELA PRIMARY SCHOOL | 500234950 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-03-12 | 2023-06-24 | 2023-06-24 | 2024-06-24 | 2025-06-24 | 887304 | 4042165 | 4929469 | Education Infrastructure Grant | Upgrading and Additions
|  | 30674 | W/500223480/RRR | KwaZulu-Natal | NCECENI PRIMARY SCHOOL | 500223480 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-02-12 | 2018-04-27 | 2023-03-31 | 2020-10-30 | 2021-11-11 | 2362099 | 10760673 | 13122772 | Education Infrastructure Grant | Upgrading and Additions
|  | 30675 | ET/500302697/WS | KwaZulu-Natal | EMBONQENI PRIMARY SCHOOL | 500302697 | Maphumulo | Final Completion | Active - Contracted | 2018-03-12 | 2022-03-10 | 2023-09-24 | 2022-09-30 | 2023-04-30 | 833560 | 3797327 | 4630887 | Education Infrastructure Grant | Upgrading and Additions
|  | 30679 | W/500248862/WS | KwaZulu-Natal | PHINDIZWE HIGH SCHOOL | 500248862 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-01-20 | 2021-02-26 | 2023-03-29 | 2021-04-30 | 2022-05-31 | 762000 | 3473000 | 4235000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30680 | W/500180412/SDS | KwaZulu-Natal | KWAMAKHUTHA COMPREHENSIVE HIGH SCHOOL | 500180412 | eThekwini | Feasibility | Active - Not Contracted | 2016-06-13 |  | 2023-03-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30681 | W/500264402/RRR | KwaZulu-Natal | SIGANANDA PRIMARY SCHOOL | 500264402 | Nkandla | Final Completion | Active - Contracted | 2015-03-05 | 2017-03-30 | 2023-02-28 | 2018-01-30 | 2023-05-31 | 1386000 | 6316000 | 7702000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30682 | W/500428423/WS | KwaZulu-Natal | SUMMERFIELD JUNIOR SECONDARY SCHOOL | 500428423 | Dr Nkosazana Dlamini Zuma | Tender | Active - Not Contracted | 2016-06-13 |  | 2023-06-30 |  |  | 1177663 | 5364908 | 6542571 | Education Infrastructure Grant | Upgrading and Additions
|  | 30683 | W/500269841/UA | KwaZulu-Natal | SIYALUNGELWA S | 500269841 | Newcastle | Design | Active - Not Contracted | 2012-02-11 |  | 2023-06-30 |  |  | 500000 | 1018000 | 1518000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30688 | TBD: REPLACEMENT SCHOOL | Northern Cape | ANDERSON PRIMARY SCHOOL | 300016202 | Siyancuma | Feasibility | Approved | 2020-04-01 |  | 2025-03-28 |  |  | 15000000 | 69259714 | 84259714 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 30695 | W/500109298/WS | KwaZulu-Natal | BHEKUZULU PRIMARY SCHOOL | 500304695 | Abaqulusi | Design | Active - Not Contracted | 2016-06-13 |  | 2024-06-30 |  |  | 491443 | 2238797 | 2730240 | Education Infrastructure Grant | Upgrading and Additions
|  | 30698 | W/500212158/SDS | KwaZulu-Natal | MKHONJENI PRIMARY SCHOOL | 500212158 | Jozini | Final Completion | Active - Contracted | 2016-06-13 | 2019-08-27 | 2022-10-30 | 2022-12-15 | 2023-03-30 | 373992 | 1703739 | 2077731 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30701 | W/500229363/WS | KwaZulu-Natal | NGWEMNYAMA PRIMARY SCHOOL | 500229363 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-02-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30712 | W/500227735/SDS | KwaZulu-Natal | CONGCO SECONDARY SCHOOL | 500227735 | Richmond | Design | Active - Not Contracted | 2016-06-13 |  | 2024-06-01 |  |  | 1086000 | 4952000 | 6038000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30714 | DOE03NCAR037 | Northern Cape | BORESETSE SECONDARY SCHOOL | 300013401 | Dikgatlong | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-08-17 | 2025-03-31 | 2025-03-30 | 2025-03-31 | 5283349 | 18411194 | 24191290 | Education Infrastructure Grant | Upgrading and Additions
|  | 30715 | W/500266622/SDS | KwaZulu-Natal | SINGELE HIGH SCHOOL | 500266622 | eThekwini | Project Initiation | Proposed | 2016-06-13 |  | 2023-06-30 |  |  | 2143000 | 9764000 | 11907000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30723 | BBB010/2017_ OR-027067 | Northern Cape | KIMBERLEY BOYS HIGH SCHOOL | 300015403 | Sol Plaatjie | Construction 26% - 50% | Active - Contracted | 2016-07-01 | 2018-11-01 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 1459658 | 6362966 | 8096620 | Education Infrastructure Grant | Upgrading and Additions
|  | 30726 | V3007/2017 | Northern Cape | VAALHARTS GEKOMBINEERDE SKOOL | 300017304 | Phokwane | Construction 26% - 50% | Active - Contracted | 2017-08-24 | 2021-03-10 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2120956 | 9098909 | 11219865 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30727 | DOE03NCAR026 | Northern Cape | KUDUMANE PRIMARY SCHOOL | 300100778 | Ga-Segonyana | Practical Completion (100%) | Approved | 2016-08-01 | 2017-04-01 | 2025-03-31 | 2025-03-30 | 2025-03-31 | 2378208 | 8013661 | 10391869 | Education Infrastructure Grant | Upgrading and Additions
|  | 30734 | TBD_ KHEIS | Northern Cape | KHEIS MET PRIMERE SKOOL | 300032202 | Kamiesberg | Design | Approved | 2022-10-13 |  | 2023-01-31 |  |  | 0 | 150000 | 150000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30755 | DOE03NCAR043 | Northern Cape | JAN KEMPDORP PRIMARY SCHOOL | 300017224 | Phokwane | Practical Completion (100%) | Active - Contracted | 2016-08-01 | 2016-08-03 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1254011 | 6966726 | 8220737 | Education Infrastructure Grant | Upgrading and Additions
|  | 30760 | DOE03NCAR036 | Northern Cape | INEELENG PRIMARY SCHOOL | 3000100542 | Ga-Segonyana | Construction 51% - 75% | Approved | 2016-08-01 | 2016-09-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2961465 | 2808330 | 5769795 | Education Infrastructure Grant | Upgrading and Additions
|  | 30764 | DB/500243682/SDS | KwaZulu-Natal | OLWANDLE HIGH SCHOOL | 500303696 | Ray Nkonyeni | Project Initiation | Active - Not Contracted | 2015-11-20 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30765 | DB/500188256/SDS | KwaZulu-Natal | LUDLIKI PRIMARY SCHOOL | 500188258 | Ubuhlebezwe | Final Completion | Approved | 2015-10-24 | 2016-12-20 | 2023-04-30 | 2023-09-20 | 2023-12-20 | 400951 | 1508341 | 1909292 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30767 | V3002/2017 | Northern Cape | WARRENTON PUBLIC PRIMARY SCHOOL | 300017215 | Magareng | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2019-08-22 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 1777886 | 6925933 | 8703819 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30769 | BBB/2016/001/03/10_ OR-025880 | Northern Cape | WEST END PRIMARY SCHOOL | 300016218 | Sol Plaatjie | Construction 51% - 75% | Approved | 2016-04-01 | 2017-03-04 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 13786998 | 53708601 | 69614818 | Education Infrastructure Grant | Upgrading and Additions
|  | 30772 | DOE03NCAR024 | Northern Cape | OMANG PRIMARY SCHOOL | 300101568 | Joe Morolong | Practical Completion (100%) | Approved | 2016-04-01 | 2018-05-10 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 4011016 | 7273563 | 11284579 | Education Infrastructure Grant | Upgrading and Additions
|  | 30778 | DOE03NCAR042 | Northern Cape | HOERSKOOL HARTSWATER | 300017401 | Phokwane | Construction 51% - 75% | Approved | 2016-08-01 | 2019-05-21 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 11091140 | 28092558 | 39183698 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 30795 | DB/500205202/SDS | KwaZulu-Natal | MBUSOWABATHETHWA HIGH SCHOOL | 500204536 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2015-10-23 | 2019-09-30 | 2023-04-29 | 2023-05-31 | 2023-06-30 | 985158 | 4487942 | 5473100 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30797 | DB/500140008/SDS | KwaZulu-Natal | ESIBHOWENI HIGH SCHOOL | 500139046 | Umhlabuyalingana | Final Completion | Approved | 2015-04-30 | 2018-03-09 | 2023-04-30 | 2023-09-10 | 2023-08-16 | 771595 | 2902669 | 3674264 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30798 | DB/500153291/SDS | KwaZulu-Natal | HALAMBU PRIMARY SCHOOL | 500153291 | Nkandla | Final Completion | Approved | 2016-02-01 | 2017-05-20 | 2023-02-05 | 2023-10-20 | 2025-03-30 | 178175 | 811685 | 989860 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30799 | DB/500191697/SDS | KwaZulu-Natal | MAFAHLENI HIGH SCHOOL | 500191364 | Impendle | Final Completion | Approved | 2015-09-06 | 2018-04-19 | 2023-04-06 | 2023-10-23 | 2023-04-29 | 1090695 | 4103092 | 5193787 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30803 | DB/500304436/SDS | KwaZulu-Natal | MTHANDI PRIMARY SCHOOL | 500218707 | Alfred Duma | Final Completion | Approved | 2015-09-10 | 2018-04-11 | 2023-04-30 | 2023-12-12 | 2023-03-27 | 738836 | 2779432 | 3518268 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30806 | DB/500240685/SDS | KwaZulu-Natal | NTSHOSHO PRIMARY SCHOOL | 500240685 | Alfred Duma | Final Completion | Approved | 2015-09-12 | 2016-05-20 | 2023-04-30 | 2019-06-20 | 2025-10-20 | 504369 | 1897388 | 2401757 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30809 | DB/500263884/SDS | KwaZulu-Natal | SICELUKUKHANYA HIGH SCHOOL | 500429829 | Endumeni | Construction 76% - 99% | Active - Contracted | 2015-09-12 | 2019-04-29 | 2023-04-29 | 2023-04-29 | 2025-04-29 | 1078377 | 4912606 | 5990983 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30812 | DB/500290561/SDS | KwaZulu-Natal | UTRECHT HIGH SCHOOL | 500287305 | Emadlangeni | Final Completion | Approved | 2015-11-03 | 2016-12-20 | 2023-04-30 | 2023-09-20 | 2023-10-20 | 1213909 | 4566612 | 5780521 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30815 | DB/500424094/WS | KwaZulu-Natal | CLYDESDALE SECONDARY SCHOOL | 500424094 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30816 | DB/500131868/SDS | KwaZulu-Natal | EMBADLENI PRIMARY SCHOOL | 500131868 | Jozini | Final Completion | Approved | 2015-09-10 | 2016-02-10 | 2023-04-30 | 2023-09-07 | 2023-09-12 | 852535 | 3207156 | 4059691 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30818 | DB/500310615/SDS | KwaZulu-Natal | INTONGA HIGH SCHOOL | 500310615 | uPhongolo | Feasibility | Active - Contracted | 2016-01-06 |  | 2024-03-12 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 30821 | DB/500447589/SDS | KwaZulu-Natal | KHANYAKUFIKILE PRIMARY SCHOOL | 500447589 | uMlalazi | Design | Active - Not Contracted | 2016-02-01 |  | 2024-02-03 |  |  | 878615 | 4002581 | 4881196 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30822 | DB/500171088/SDS | KwaZulu-Natal | IGUGU LESIZWE SECONDARY SCHOOL | 50015784 | Jozini | Final Completion | Approved | 2015-09-12 | 2016-06-20 | 2023-09-20 | 2023-12-20 | 2023-12-20 | 272734 | 1242454 | 1515188 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30824 | DB/500178451/SDS | KwaZulu-Natal | Kwa-Phaweni Ps | 500178451 | Jozini | Feasibility | Active - Not Contracted | 2015-09-10 |  | 2024-04-30 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30826 | DB/500180893/SDS | KwaZulu-Natal | KWAMBOMA PRIMARY SCHOOL | 500180893 | Umhlabuyalingana | Feasibility | Active - Contracted | 2016-02-12 |  | 2024-03-01 |  |  | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30829 | DB/500191845/SDS | KwaZulu-Natal | MAFUMBUKA SECONDARY SCHOOL | 500191845 | eThekwini | Final Completion | Approved | 2015-04-30 | 2018-04-05 | 2023-07-26 | 2023-12-06 | 2023-03-19 | 667000 | 3036000 | 3703000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30832 | DB/500338809/SDS | KwaZulu-Natal | MANGWAZANE HIGH SCHOOL | 500338809 | Jozini | Final Completion | Approved | 2015-11-19 | 2018-12-01 | 2023-04-30 | 2023-09-05 | 2023-03-04 | 360000 | 1640000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30836 | DB/500327004/SDS | KwaZulu-Natal | MACEBA HIGH SCHOOL | 500190217 | Nqutu | Final Completion | Approved | 2015-09-20 | 2017-08-20 | 2022-04-30 | 2022-08-20 | 2025-10-20 | 1070000 | 4875000 | 5945000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30839 | DB/500220224/SDS | KwaZulu-Natal | Inqabayamazimela S | 500220224 | uMlalazi | Design | Active - Not Contracted | 2016-02-01 |  | 2024-02-05 |  |  | 1252530 | 2705970 | 3958500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30841 | DB/500274910/SDS | KwaZulu-Natal | ST ALEXIS PRIMARY SCHOOL | 50027491 | Jozini | Final Completion | Approved | 2015-11-25 | 2016-12-20 | 2023-04-30 | 2019-05-20 | 2025-07-20 | 628663 | 2364971 | 2993634 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30842 | DB/500277685/SDS | KwaZulu-Natal | STAR OF THE SEA PRIMARY SCHOOL | 500277685 | Umhlabuyalingana | Final Completion | Approved | 2015-09-11 | 2018-04-12 | 2023-04-29 | 2023-09-20 | 2023-06-16 | 812845 | 3057845 | 3870690 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30848 | DRPW019/2018 | Northern Cape | NEW CILLIE PRIMARY SCHOOL | NEW | Kai !Garib | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2016-04-11 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 6930000 | 31570000 | 50783911 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 30849 | DB/500217190/SDS | KwaZulu-Natal | MPOMPOLWANA PRIMARY SCHOOL | 500217190 | Msinga | Design | Active - Contracted | 2015-11-20 |  | 2024-03-01 |  |  | 7370 | 33572 | 40942 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30850 | ISJX026/2019 | Northern Cape | NEW MAGOJANENG PRIMARY SCHOOL | NEW | Ga-Segonyana | Feasibility | Approved | 2018-04-01 |  | 2025-03-31 |  |  | 15654069 | 70000000 | 85654069 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 30852 | DB/500153513/SDS | KwaZulu-Natal | HAMILTON MAKHANYA | DB/500306175/SDS | eThekwini | Final Completion | Approved | 2015-11-19 | 2015-12-20 | 2023-07-19 | 2023-10-20 | 2023-12-20 | 747309 | 2811306 | 3558615 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30853 | DB/500203500/SDS | KwaZulu-Natal | MBALASI PRIMARY SCHOOL | DBSA/500203500 - SDS | eThekwini | Final Completion | Approved | 2015-09-12 | 2018-04-11 | 2023-04-30 | 2023-10-19 | 2023-02-22 | 519940 | 1955963 | 2475903 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30855 | W/500192585/SDS | KwaZulu-Natal | MAGUBULUNDU SECONDARY SCHOOL | 500192585 | eDumbe | Design | Active - Not Contracted | 2015-11-20 |  | 2024-09-11 |  |  | 1296060 | 5904272 | 7200332 | Education Infrastructure Grant | Maintenance and Repairs
|  | 30857 | DB/500219336/SDS | KwaZulu-Natal | MTHOMBENI PRIMARY SCHOOL | DBSA/500219336 - SDS | eThekwini | Final Completion | Approved | 2015-11-19 | 2016-02-20 | 2023-04-30 | 2023-10-20 | 2023-10-20 | 812150 | 3055229 | 3867379 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 30859 | DB/500292263/SDS | KwaZulu-Natal | VIKINGOZI SECONDARY SCHOOL | 500292263 | eThekwini | Final Completion | Approved | 2015-11-25 | 2018-04-19 | 2023-04-30 | 2023-10-20 | 2023-03-22 | 272451 | 1024936 | 1297387 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31229 | W/500137344/SDS | KwaZulu-Natal | ENHLUBE P | 500137344 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2015-02-02 | 2020-03-03 | 2023-03-30 | 2023-07-31 | 2022-04-04 | 1296054 | 5904248 | 7200302 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31354 | P9010685_ | Eastern Cape | DUMALISILE COMPREHENSIVE HIGH SCHOOL | 200300875 | Buffalo City | Project Initiation | Active - Not Contracted | 2016-04-19 | 2016-08-20 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 5045000 | 5045000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 31361 | GDE00036 | Gauteng | COSMO CITY JUNIOR PRIMARY SCHOOL | 700400179 | City of Johannesburg | Feasibility | Approved | 2016-04-01 |  | 2025-08-08 |  |  | 11292000 | 56661000 | 67953000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31367 | GDE00269 | Gauteng | Panorama Primary School | 700250878 | City of Johannesburg | Design | Approved | 2020-02-14 |  | 2026-03-13 |  |  | 276160 | 1449840 | 1726000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31369 | GDE00223 | Gauteng | Mayfield Primary School | MayfieldPS | City of Ekurhuleni | Practical Completion (100%) | Approved | 2016-04-24 | 2016-07-20 | 2025-03-13 | 2025-03-18 | 2025-03-12 | 3360000 | 17640000 | 21000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31383 | Dtpw064/2014 | Western Cape | Aurecon PSP | TBC | Prince Albert | Other - Packaged Ongoing Project | Active - Contracted | 2016-04-01 | 2016-11-06 | 2027-03-28 | 2025-03-29 | 2026-03-31 | 53244000 | 0 | 53244000 | Equitable Share | Maintenance and Repairs
|  | 31392 | GDE00279 | Gauteng | PHOMOLONG SECONDARY SCHOOL | 700400138 | City of Ekurhuleni | Feasibility | Approved | 2019-01-24 |  | 2026-03-13 |  |  | 7156000 | 37569000 | 44725000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31398 | GDE00316 | Gauteng | Roodekop Primary School (Settlement) | RoodekopNew | City of Ekurhuleni | Design | Approved | 2019-08-15 |  | 2025-03-30 |  |  | 1376000 | 7224000 | 8600000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31408 | GDE00388 | Gauteng | TSHEPISONG PRIMARY SCHOOL | 700252825 | City of Johannesburg | Tender | Active - Not Contracted | 2016-04-01 |  | 2026-03-13 |  |  | 14746720 | 77420280 | 92167000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31415 | Dtpw03 1/2012 | Western Cape | To be confirmed | TBC | City of Cape Town | Other - Compensation of Employees | Active - Contracted | 2015-04-01 | 2016-04-01 | 2027-03-29 | 2025-03-29 | 2025-03-29 | 53384000 | 0 | 53384000 | Equitable Share | Non-Infrastructure
|  | 31418 | GDE00412 | Gauteng | Mobile Relocation | Mobile Relocation | City of Ekurhuleni | Tender | Approved | 2021-11-01 |  | 2026-03-08 |  |  | 10000000 | 160000000 | 170000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 31661 | GDE00213 | Gauteng | MAMELODI EAST PRE-VOCATIONAL SCHOOL FOR LEARNERS WITH SPECIAL EDUCATION NEEDS | 700400896 | City of Tshwane | Construction 1% - 25% | Approved | 2019-04-01 | 2019-07-20 | 2024-01-31 | 2021-02-14 | 2024-03-19 | 576280 | 4543720 | 5120000 | Education Infrastructure Grant | Upgrading and Additions
|  | 31666 | DOE/05/16/17 | Free State | PARYS NEW PRIMARY | 2 | Ngwathe | Design | Active - Contracted | 2016-11-01 |  | 2026-03-31 |  |  | 12500000 | 60000000 | 72500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31668 | DOE/07/16/17 | Free State | BOTHAVILLE TSHEHETSO | 5 | Nala | Construction 1% - 25% | Active - Contracted | 2016-11-01 | 2016-12-01 | 2025-03-31 | 2021-03-31 | 2025-01-31 | 14332930 | 60000000 | 74332930 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31669 | DOE/08/16/17 | Free State | SASOLBURG KATLEGO MPUMELLELO | 4 | Metsimaholo | Construction 1% - 25% | Active - Contracted | 2016-11-01 | 2016-12-01 | 2025-03-31 | 2021-03-31 | 2024-03-20 | 10000000 | 64264835 | 74264835 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31671 | DOE/10/16/17 | Free State | FRANKFORT TSEBO ULWAZI | 1 | Maluti a Phofung | Design | Active - Contracted | 2016-11-01 |  | 2025-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 31714 | GDE00186 | Gauteng | Laerskool Wierdapark | 700210856 | City of Tshwane | Feasibility | Proposed | 2022-04-01 |  | 2024-07-09 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31716 | GDE00103 | Gauteng | Hoerskool Die Wilgers | 700210153 | Emfuleni | Feasibility | Proposed | 2021-04-01 |  | 2026-03-13 |  |  | 50000 | 200000 | 250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31718 | TBD: BBB | Northern Cape | LAERSKOOL KLEINZEE | 300033221 | Nama Khoi | Feasibility | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 4261358 | 4261358 | Education Infrastructure Grant | Upgrading and Additions
|  | 31720 | GDE00108 | Gauteng | Hoerskool Pretoria-Wes | 700230367 | City of Tshwane | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 3296000 | 17304000 | 20600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31722 | GDE00117 | Gauteng | INKULULEKO YESIZWE PRIMARY SCHOOL | 700400084 | City of Johannesburg | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-03-20 |  |  | 2400000 | 59600000 | 62000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31724 | GDE00120 | Gauteng | ISIZWE-SETJHABA SECONDARY SCHOOL | 700330860 | Emfuleni | Project Initiation | Approved | 2022-04-01 |  | 2025-03-09 |  |  | 50000 | 150000 | 200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 31798 | GDE00379 | Gauteng | Transoranje LSEN | 700231456 | City of Tshwane | Tender | Approved | 2019-04-01 |  | 2025-03-21 |  |  | 3317600 | 20473400 | 23791000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51092 | PWRT/2267/17/MP (MDOE/P/EHL/EIG/NEW/17-18/379) | Mpumalanga | MSOGWABA PRIMARY | new | Mbombela | Construction 1% - 25% | Active - Contracted | 2018-05-04 | 2018-05-05 | 2023-03-31 | 2022-03-29 | 2022-03-29 | 7337722 | 48450587 | 55788309 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51093 | MDOE/SP/EHL/EIG/NEW/17-18/378 | Mpumalanga | School for the Deaf | New | Emalahleni | Design | Active - Not Contracted | 2017-04-03 |  | 2025-04-30 |  |  | 59924340 | 428031000 | 487955340 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51096 | MDOE/UPG/176/19-20(DPWRT/200/19) | Mpumalanga | Nokuthula primary school | 800017194 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2017-09-01 | 2020-07-03 | 2023-12-30 | 2023-10-03 | 2023-03-31 | 471483 | 2932655 | 3404138 | Education Infrastructure Grant | Upgrading and Additions
|  | 51105 | MDOE/S/BOH/EIG/NEW/18-19/001(DPWRT/081/18/MP) | Mpumalanga | SILULU SECONDARY | 800035304 | Bushbuckridge | Tender | Active - Contracted | 2018-05-01 |  | 2025-11-15 |  |  | 8388220 | 59915856 | 68304076 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51112 | GDE00328 | Gauteng | Savanna City Primary School No. 1 | Savanna CityPS1 | Midvaal | Feasibility | Approved | 2019-09-15 |  | 2026-03-13 |  |  | 4413600 | 23171400 | 27585000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51157 | MDOE/P/EHL/EIG/MAIN/17-18/031 (PWRT/009/17/MP) | Mpumalanga | LUNDANDA PRIMARY | 800010835 | Mbombela | Project Initiation | Proposed | 2022-08-01 |  | 2024-11-01 |  |  | 254389 | 2543888 | 2798277 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51230 | GDE00308 | Gauteng | RIBANE-LAKA SECONDARY SCHOOL | 700221044 | City of Tshwane | Tender | Approved | 2019-10-04 |  | 2025-04-11 |  |  | 4828480 | 25349520 | 30178000 | Education Infrastructure Grant | Upgrading and Additions
|  | 51419 | P9005797 | Eastern Cape | EMFUNDWENI PRIMARY SCHOOL | 200100202 | Nelson Mandela Bay | Tender | Active - Not Contracted | 2016-01-04 |  | 2026-03-31 |  |  | 0 | 93714 | 93714 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51430 | P9008752_ | Eastern Cape | GREENVILLE PRIMARY SCHOOL | 200100275 | Nelson Mandela Bay | Project Initiation | Proposed | 2022-01-04 |  | 2023-03-31 |  |  | 0 | 1 | 1 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51476 | P9013237 | Eastern Cape | MTHETHO SENIOR PRIMARY SCHOOL | 200300384 | Mbhashe | Tender | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51492 | P9013325 | Eastern Cape | TOISEKRAAL PUBLIC SCHOOL | 200600850 | Enoch Mgijima | Project Initiation | Proposed | 2017-04-01 |  | 2026-03-31 |  |  | 0 | 1321327 | 1321327 | Education Infrastructure Grant | Upgrading and Additions
|  | 51531 | P9008402_ | Eastern Cape | PANGINDLELA JUNIOR SECONDARY SCHOOL | 200400909 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2015-04-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 884298 | 884298 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51534 | DOE03NCAR040 | Northern Cape | BEACON PRIMARY SCHOOL | 300015201 | Sol Plaatjie | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-10-26 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 754740 | 3773700 | 4528440 | Education Infrastructure Grant | Upgrading and Additions
|  | 51545 | TBD_DR EP LEKHELA | Northern Cape | DR EP LEKHELA HIGH SCHOOL | 300015406 | Sol Plaatjie | Project Initiation | Proposed | 2022-06-16 |  | 2022-11-30 |  |  | 0 | 800000 | 800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51561 | TBD_KGOMOTSO | Northern Cape | KGOMOTSO SECONDARY SCHOOL: ELECTRICITY | 300100690 | Phokwane | Project Initiation | Proposed | 2022-06-14 |  | 2022-12-29 |  |  | 0 | 600000 | 600000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51565 | ISJX006/2017 | Northern Cape | HOMEVALE PRIMARY SCHOOL | 300014202 | Sol Plaatjie | Construction 1% - 25% | Active - Contracted | 2017-04-01 | 2020-04-01 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 0 | 80541859 | 80541859 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51569 | P9013263 | Eastern Cape | ABRAHAM VANQA PRIMARY SCHOOL | 200600006 | Emalahleni | Feasibility | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 775000 | 775000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51580 | P9009665_ | Eastern Cape | MHALA JUNIOR SECONDARY SCHOOL | 200300334 | Makana | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2015-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 418823 | 1000 | 419823 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51604 | P9006503_ | Eastern Cape | SAPPHIRE ROAD PRIMARY SCHOOL | 200100682 | Nelson Mandela Bay | Feasibility | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 0 | 5266274 | 5266274 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51618 | P0004341_ | Eastern Cape | ENDULINI JUNIOR SECONDARY SCHOOL | 200200782 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2014-07-21 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 23661828 | 23661828 | Education Infrastructure Grant | Maintenance and Repairs
|  | 51629 | ST410/2021 | Northern Cape | ST PETERS PRIMARY SCHOOL | 300016216 | Sol Plaatjie | Practical Completion (100%) | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 6500000 | 6500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 51661 | V3006/2017 | Northern Cape | OLYMPIC PRIMARY SCHOOL | 300013215 | Sol Plaatjie | Construction 76% - 99% | Active - Contracted | 2017-04-01 | 2020-04-01 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2639442 | 10282208 | 12921650 | Education Infrastructure Grant | Upgrading and Additions
|  | 51662 | V3009/2017 | Northern Cape | REAIPELA INTERMEDIATE SCHOOL | 300017220 | Phokwane | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2020-04-01 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 3815622 | 16755343 | 20570965 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51665 | ISJX007/2017 | Northern Cape | VENUS PRIMERE SKOOL | 300016217 | Sol Plaatjie | Construction 1% - 25% | Active - Contracted | 2017-04-01 | 2020-04-01 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 5069433 | 28163519 | 33232952 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 51666 | VOORSPOED: DRPW | Northern Cape | VOORSPOED PRIMARY SCHOOL | 300012208 | Phokwane | Feasibility | Active - Not Contracted | 2020-07-01 |  | 2023-10-27 |  |  | 0 | 11395389 | 11395389 | Education Infrastructure Grant | Upgrading and Additions
|  | 51687 | V3008/2017 | Northern Cape | HOERSKOOL VAALHARTS | 300017402 | Phokwane | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2020-05-07 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 1725287 | 6533180 | 8258467 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51688 | V3005/2017 | Northern Cape | FLOORS NORTH INTERMEDIATE SCHOOL | 300012203 | Sol Plaatjie | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2020-04-13 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2174321 | 8470280 | 10644601 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 51737 | V3010/2017 | Northern Cape | REDIRILE PRIMARY SCHOOL- STATE OF THE ART SCHOOL | 300071100 | Sol Plaatjie | Construction 51% - 75% | Active - Contracted | 2017-04-01 | 2019-05-23 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 50312671 | 187663823 | 237976494 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52113 | LEKALAKE | North West | CN LEKALAKE PRIMARY | LEKAKE | Mafikeng | Feasibility | Active - Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 0 | 8000000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 52116 | DP KGOTLENG | North West | DP KGOTLENG PRIMARY | DP KGOTLENG | Mafikeng | Construction 1% - 25% | Active - Contracted | 2014-12-29 | 2022-07-19 | 2023-10-19 | 2023-07-19 | 2023-07-19 | 0 | 30000000 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 52127 | WE/000502/2017 | Western Cape | Saldanha Middelpos (Replacing Buhrein Estate) | 134309337 | Saldanha Bay | Construction 26% - 50% | Active - Contracted | 2017-04-03 | 2021-09-01 | 2025-03-31 | 2023-06-30 | 2023-08-31 | 18238000 | 73000000 | 91238000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52128 | WE/000416/2017 | Western Cape | Roodewal PS | 130330108 | Breede Valley | Feasibility | Proposed | 2017-04-03 |  | 2026-03-31 |  |  | 14483000 | 64000000 | 78483000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52129 | WE/000867/2020 | Western Cape | De Waalville PS | 116330388 | Hessequa | Construction 26% - 50% | Active - Contracted | 2017-05-01 | 2021-10-11 | 2024-03-29 | 2023-07-03 | 2023-05-31 | 10149000 | 54000000 | 64149000 | Equitable Share | New or Replaced Infrastructure
|  | 52130 | WE 000427/2017 | Western Cape | Mvula PS | 106005100 | City of Cape Town | Design | Active - Not Contracted | 2017-05-10 |  | 2025-03-31 |  |  | 14566000 | 61000000 | 75566000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52131 | WE/000725/2018 | Western Cape | Perivale PS | 105310689 | City of Cape Town | Practical Completion (100%) | Active - Contracted | 2017-05-03 | 2020-06-04 | 2024-03-29 | 2022-03-31 | 2022-09-09 | 13860000 | 54554000 | 68414000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52134 | WE/000168/2017 | Western Cape | Chatsworth PS | 132476161 | Swartland | Construction 51% - 75% | Active - Contracted | 2017-05-24 | 2021-06-24 | 2024-03-29 | 2022-12-01 | 2023-01-31 | 11909000 | 45000000 | 56909000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 52157 | 31658051 | Western Cape | Incentive Grant Projects (Ablutions) | TBC | City of Cape Town | Other - Packaged Ongoing Project | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 56634000 | 244837000 | 301471000 | Education Infrastructure Grant | Upgrading and Additions
|  | 52444 | ST057/2017 | Northern Cape | VICTORIA-WES GEKOMBINEERDE SKOOL | 300024304 | Ubuntu | Construction 76% - 99% | Active - Contracted | 2017-03-01 | 2018-04-23 | 2023-03-31 | 2023-04-15 | 2024-03-31 | 0 | 1200000 | 1200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 52831 | DB/500105857/SDS | KwaZulu-Natal | Baqoqe Primary School | 500105857 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-12-20 | 2023-02-20 | 2023-04-20 | 2025-05-20 | 531031 | 2419139 | 2950170 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 52860 | DB/500186591/SDS | KwaZulu-Natal | LINCOLN HEIGHTS SECONDARY SCHOOL | 500186591 | The Msunduzi | Final Completion | Approved | 2016-02-20 | 2017-01-20 | 2023-02-20 | 2023-04-20 | 2023-05-20 | 263618 | 991704 | 1255322 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 53030 | LE19TMT17100 | Limpopo | Kgobuki Primary School | 921111719 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2017-06-30 |  | 2024-03-30 |  |  | 606489 | 3750700 | 4357189 | Education Infrastructure Grant | Upgrading and Additions
|  | 60662 | EDDP184/428 | Limpopo | MakgalaePhasha Sec School | 992203501 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2015-09-30 | 2016-04-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 5223000 | 20892000 | 26115000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 60663 | EDDP184/275 | Limpopo | Kgakgala Primary School | 921140229 | Mogalakwena | Terminated | Active - Contracted | 2015-09-30 | 2016-06-30 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 2764000 | 11056000 | 13820000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 60678 | EDDP184/57B | Limpopo | LEBOENG PRIMARY SCHOOL | 925620237 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2016-10-11 | 2016-12-15 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 16000 | 66000 | 82000 | Education Infrastructure Grant | Upgrading and Additions
|  | 60717 | EDDP184/326 | Limpopo | Nkuri P.School | 911410850 | Greater Giyani | Construction 76% - 99% | Active - Contracted | 2015-09-30 | 2016-12-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2256200 | 9024800 | 11281000 | Education Infrastructure Grant | Upgrading and Additions
|  | 61682 | EDDP184/314 | Limpopo | Modishane Primary School | EDDP184/314 | Makhuduthamaga | Construction 26% - 50% | Active - Contracted | 2016-06-01 | 2016-12-31 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 1918000 | 7673000 | 9591000 | Education Infrastructure Grant | Upgrading and Additions
|  | 61691 | MDOE/P/GSD/Education/Infrastructure Grant(EIG)MAIN/17-18/109(PWRT/089/18/MP) | Mpumalanga | NEW ERMELO PRIMARY | 800030486 | Msukaligwa | Construction 1% - 25% | Active - Contracted | 2019-05-01 | 2021-03-09 | 2023-04-15 | 2023-04-10 | 2022-04-29 | 6852424 | 43624576 | 50477000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 61694 | EDDP184/360 | Limpopo | Krause Primary | 909130475 | Thabazimbi | Final Completion | Active - Contracted | 2015-04-01 | 2016-12-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 4263600 | 17054400 | 21318000 | Education Infrastructure Grant | Upgrading and Additions
|  | 62150 | DOE11/13/14 | Free State | MOBILE CLASSES | BLOEMFONTEIN | Mangaung | Other - Packaged Ongoing Project | Active - Contracted | 2015-04-01 | 2015-05-30 | 2025-04-01 | 2017-03-31 | 2017-11-29 | 0 | 88632000 | 88632000 | Education Infrastructure Grant | Upgrading and Additions
|  | 62196 | DOE19/13/14 | Free State | STORM DAMAGES | VARIOUS | Masilonyana | Design | Active - Not Contracted | 2015-04-01 |  | 2026-03-31 |  |  | 0 | 47242000 | 47242000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 62364 | DPWRT/082/16/MP | Mpumalanga | LEHUKWE CIRCUIT OFFICE | 800035593 | Bushbuckridge | Feasibility | Active - Not Contracted | 2017-04-03 |  | 2024-03-31 |  |  | 990000 | 5500000 | 6490000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 62384 | DPWRT/2291/18/MP8/154( MDOE/OFFICES/EHL/EIG/NEW/17-18/154)) | Mpumalanga | Lubombo Circuit Offices | 800035586 | Nkomazi | Construction 1% - 25% | Active - Contracted | 2017-05-01 | 2018-11-16 | 2023-03-31 | 2022-03-16 | 2022-03-16 | 1594649 | 8859162 | 10453811 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 62406 | PWRT/2300/17/MP | Mpumalanga | THABA CHWEU BOARDING SCHOOL | 0 | Thaba Chweu | Practical Completion (100%) | Active - Contracted | 2017-07-03 | 2018-05-30 | 2023-03-31 | 2020-06-30 | 2020-11-24 | 45313159 | 381385753 | 426698912 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 63374 | DPWRT/109/18/MP LTS | Mpumalanga | LONG TOM SECONDARY | 0 | Thaba Chweu | Design | Active - Not Contracted | 2019-11-04 |  | 2024-03-31 |  |  | 7209352 | 31166956 | 38376308 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 63397 | DPWRT/088/16MP(SHANKE SEC)--------------- | Mpumalanga | Shanke Senior Secondary School | 800035017 | Bushbuckridge | Design | Approved | 2018-04-01 |  | 2025-03-31 |  |  | 6848730 | 38048500 | 44897230 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 63420 | MDOE/NEW/19-20/013 | Mpumalanga | Tidimalo Primary School | 800035682 | Thembisile | Final Completion | Active - Contracted | 2021-05-01 | 2022-11-01 | 2024-05-30 | 2024-08-30 | 2024-08-30 | 3153501 | 22525005 | 25678506 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 63425 | PWRT/2285/17/MP | Mpumalanga | Manyano Primary School | 800012385 | Steve Tshwete | Design | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 411257 | 4112573 | 4523830 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65099 | GDE00082 | Gauteng | FRED MAGARDIE PRIMARY SCHOOL | 700220038 | City of Tshwane | Project Initiation | Approved | 2019-11-01 |  | 2026-01-09 |  |  | 10438840 | 54809160 | 65248000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65100 | GDE00089 | Gauteng | Golden Gardens Primary School | Golden Gardens | Midvaal | Practical Completion (100%) | Proposed | 2017-09-01 | 2017-11-01 | 2022-07-12 | 2023-08-27 | 2024-04-11 | 10053922 | 52783092 | 62837014 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65101 | GDE00093 | Gauteng | Hammanskraal West Primary School | 700400207 | City of Tshwane | Tender | Approved | 2019-06-14 |  | 2026-01-09 |  |  | 4960000 | 26040000 | 31000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65111 | GDE00121 | Gauteng | ITIRELENG SCHOOL FOR SEVERLY MENTALLY HANDICAPPED | 700251470 | Mogale City | Project Initiation | Approved | 2019-09-15 |  | 2026-01-09 |  |  | 5363840 | 28160160 | 33524000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65117 | GDE00132 | Gauteng | Kaalfontein Primary No 2 | Kaalfontein PS-No2 | City of Johannesburg | Feasibility | Approved | 2019-09-15 |  | 2026-01-09 |  |  | 6161440 | 32347560 | 38509000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65200 | GDE00271 | Gauteng | Parktown Girls High School | 700131136 | City of Johannesburg | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 2324960 | 10631040 | 12956000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65206 | GDE00380 | Gauteng | Transvaliaskool School | 700221333 | City of Tshwane | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 2240000 | 11760000 | 14000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65208 | GDE00418 | Gauteng | Vereeniging Gymnasium | 700330209 | Emfuleni | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 13300000 | 65000000 | 78300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65341 | GDE00039 | Gauteng | Cultura High School | 700210062 | City of Tshwane | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 1649140 | 21454860 | 23104000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65344 | PWRT/2406/19/MP | Mpumalanga | New Doornkop School (Phase 1) | New | Steve Tshwete | Practical Completion (100%) | Active - Contracted | 2019-04-03 | 2020-01-21 | 2023-03-31 | 2022-02-28 | 2022-02-28 | 4234428 | 31285829 | 35520257 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 65346 | GDE00077 | Gauteng | FELICITASSKOOL - SCHOOL | 700311746 | City of Ekurhuleni | Feasibility | Approved | 2019-04-01 |  | 2024-09-16 |  |  | 1300000 | 10700000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65363 | GDE00163 | Gauteng | LAERSKOOL FRIKKIE MEYER | 700320093 | Emfuleni | Tender | Proposed | 2019-08-05 |  | 2026-03-13 |  |  | 5478240 | 37510760 | 42989000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65384 | GDE00324 | Gauteng | RUST-TER-VAAL PRIMARY SCHOOL | 700330019 | Emfuleni | Feasibility | Approved | 2019-04-30 |  | 2025-07-11 |  |  | 4041280 | 28216720 | 32258000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65390 | GDE00370 | Gauteng | Thulasizwe Special School | 700133165 | City of Johannesburg | Feasibility | Approved | 2019-10-01 |  | 2026-03-13 |  |  | 7000000 | 27000000 | 34000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65401 | GDE00259 | Gauteng | Northcliff Primary School | 700140293 | City of Johannesburg | Feasibility | Approved | 2019-04-01 |  | 2023-05-12 |  |  | 546000 | 2289000 | 2835000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65426 | DB/500112295/SDS | KwaZulu-Natal | BRETTONWOOD SECONDARY SCHOOL | 500112295 | eThekwini | Design | Active - Not Contracted | 2016-12-20 |  | 2024-03-22 |  |  | 3066683 | 13970444 | 17037127 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65433 | DB/500340807/SDS | KwaZulu-Natal | MAYVILLE SECONDARY SCHOOL | 500340807 | eThekwini | Final Completion | Active - Contracted | 2017-03-01 | 2018-04-05 | 2023-10-05 | 2023-09-06 | 2025-09-06 | 576659 | 2627003 | 3203662 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65459 | W/500202427/SDS | KwaZulu-Natal | MAVANA PRIMARY SCHOOL | 500202427 | Mtubatuba | Final Completion | Active - Contracted | 2017-02-20 | 2019-02-01 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 248482 | 1131974 | 1380456 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65461 | DB/500113849/SDS | KwaZulu-Natal | BUSHLANDS PRIMARY SCHOOL | 500113960 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-01-15 | 2022-09-25 | 2022-10-11 | 2025-10-11 | 739421 | 4511579 | 5251000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65462 | DB/500114367/SDS | KwaZulu-Natal | CANAAN PRIMARY SCHOOL | 500114367 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2019-01-14 | 2023-06-30 | 2023-07-14 | 2027-03-20 | 526883 | 2400246 | 2927129 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65463 | DB/500302549/SDS | KwaZulu-Natal | CARRINGTON PRIMARY SCHOOL | 500302549 | eThekwini | Practical Completion (100%) | Approved | 2016-02-20 | 2018-01-15 | 2022-07-09 | 2022-07-09 | 2024-07-30 | 577083 | 3963537 | 4540620 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65464 | DB/500340177/SDS | KwaZulu-Natal | CATO CREST P | 500340177 | eThekwini | Design | Active - Not Contracted | 2016-02-20 |  | 2024-03-25 |  |  | 1082506 | 4931418 | 6013924 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65474 | DB/500311688/SDS | KwaZulu-Natal | MATHEKU SECONDARY SCHOOL | 500311688 | uMlalazi | Design | Active - Contracted | 2015-11-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65477 | DB/500124283/SDS | KwaZulu-Natal | MATAMZANA DUBE SECONDARY SCHOOL | 500124283 | uMhlathuze | Design | Active - Not Contracted | 2016-02-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65478 | W/500200466/SDS | KwaZulu-Natal | MASHIWANE PRIMARY SCHOOL | 500200466 | Umzumbe | Project Initiation | Proposed | 2017-02-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65481 | DB/500200207/SDS | KwaZulu-Natal | MASHANANANDANE SECONDARY SCHOOL | 500200207 | uMlalazi | Design | Proposed | 2016-02-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65482 | W/500443408/SDS | KwaZulu-Natal | UKUKHANYA KWEAFRIKA PRIMARY SCHOOL | 500443408 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-06-01 | 2022-10-01 | 2024-03-30 | 2025-03-30 | 89932 | 409690 | 499622 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65483 | DB/500124283/WS | KwaZulu-Natal | MATAMZANA DUBE SECONDARY SCHOOL | 500124283 | uMhlathuze | Construction 51% - 75% | Active - Contracted | 2017-02-20 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 359049 | 1635670 | 1994719 | Education Infrastructure Grant | Upgrading and Additions
|  | 65484 | DB/500286898/SDS | KwaZulu-Natal | UMBELEBELE HIGH SCHOOL | 500286898 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2024-10-10 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65485 | DB/500286972/SDS | KwaZulu-Natal | UMBILO SECONDARY SCHOOL | 500286972 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-06-06 | 2019-10-20 | 2023-02-03 | 2022-10-18 | 2024-04-14 | 842212 | 3836743 | 4678955 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65486 | DB/500199652/SDS | KwaZulu-Natal | MARIS STELLA COMBINED PRIMARY SCHOOL | 500199652 | Ray Nkonyeni | Final Completion | Approved | 2016-02-20 | 2018-01-11 | 2023-03-28 | 2023-03-28 | 2025-06-28 | 455618 | 2075594 | 2531212 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65487 | DB/500287157/SDS | KwaZulu-Natal | UMDLAMFE SECONDARY SCHOOL | 500287157 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-12-11 | 2022-06-08 | 2022-10-12 | 2024-08-17 | 1297545 | 5911039 | 7208584 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65490 | DB/500287490/SDS | KwaZulu-Natal | UMGIJIMI PRIMARY SCHOOL | 500287490 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-06-06 | 2019-10-17 | 2023-01-10 | 2022-10-02 | 2024-03-30 | 901061 | 4104833 | 5005894 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65494 | DB/500199060/SDS | KwaZulu-Natal | MAQHWAKAZI PRIMARY SCHOOL | 500199060 | eThekwini | Design | Proposed | 2016-02-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65497 | DB/500288341/SDS | KwaZulu-Natal | UMLAZI SECONDARY SCHOOL | 500288341 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-01-17 | 2023-07-17 | 2023-07-17 | 2023-07-17 | 854949 | 3894768 | 4749717 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65500 | W/500289303/SDS | KwaZulu-Natal | UMVOTI HIGH SCHOOL | 500289303 | Umvoti | Design | Active - Not Contracted | 2017-06-19 |  | 2027-03-27 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65501 | DB/500289525/SDS | KwaZulu-Natal | UMZINTO PRIMARY SCHOOL | 500289525 | Umdoni | Practical Completion (100%) | Active - Contracted | 2020-06-06 | 2020-12-04 | 2023-01-04 | 2023-02-07 | 2027-03-27 | 704916 | 3211285 | 3916201 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65503 | DB/500291042/SDS | KwaZulu-Natal | VELA PRIMARY SCHOOL | 500291042 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-01-17 | 2022-07-18 | 2022-07-22 | 2027-03-08 | 1174108 | 5348715 | 6522823 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65508 | DB/500275021/SDS | KwaZulu-Natal | ST ANTHONYS PRIMARY SCHOOL | 500275021 | eThekwini | Design | Active - Not Contracted | 2016-02-20 |  | 2024-09-26 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65509 | DB/500291745/SDS | KwaZulu-Natal | VERULAM PRIMARY SCHOOL | 500291745 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-01-17 | 2022-07-18 | 2022-10-25 | 2027-08-08 | 1091567 | 4972696 | 6064263 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65510 | W/500274392/SDS | KwaZulu-Natal | SOZABE HIGH SCHOOL | 500274392 | Ray Nkonyeni | Project Initiation | Proposed | 2016-02-20 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65511 | DB/500266511/SDS | KwaZulu-Natal | SINENHLANHLA PRIMARY SCHOOL | 500266511 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2020-01-05 | 2020-03-01 | 2023-02-10 | 2023-04-03 | 2025-06-30 | 1249136 | 5690510 | 6939646 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65512 | DB/500274244/SDS | KwaZulu-Natal | SOUTHLANDS SECONDARY SCHOOL | 500274244 | eThekwini | Design | Proposed | 2017-02-20 |  | 2024-09-26 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65513 | W/500274022/SDS | KwaZulu-Natal | SOSUKWANA PRIMARY SCHOOL | 500274022 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65516 | DB/500295445/SDS | KwaZulu-Natal | WENTWORTH PRIMARY SCHOOL | 500295445 | eThekwini | Practical Completion (100%) | Active - Contracted | 2020-01-05 | 2020-06-21 | 2022-10-01 | 2022-07-11 | 2027-08-15 | 548199 | 2497349 | 3045548 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65518 | W/500273356/SDS | KwaZulu-Natal | SOMSHOKO SECONDARY SCHOOL | 500273356 | Mandeni | Final Completion | Active - Contracted | 2015-11-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 148494 | 817012 | 965506 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65520 | W/500296111/SDS | KwaZulu-Natal | WHEBEDE PRIMARY SCHOOL | 500296111 | Mandeni | Tender | Proposed | 2016-06-06 |  | 2025-03-01 |  |  | 93480 | 965420 | 1058900 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65525 | DB/500115625/SDS | KwaZulu-Natal | CENTENARY SECONDARY SCHOOL | 500115625 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2019-01-17 | 2023-07-17 | 2023-07-17 | 2027-03-17 | 897346 | 4087909 | 4985255 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65526 | DB/500296481/SDS | KwaZulu-Natal | WINDY HEIGHTS PRIMARY SCHOOL | 500296481 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-06-30 | 2022-07-01 | 2022-10-08 | 2027-08-05 | 1250658 | 6499441 | 7750099 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65529 | W/500298553/SDS | KwaZulu-Natal | ZAMAFUTHI PRIMARY SCHOOL | 500298553 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-06-08 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65530 | DB/500116143/SDS | KwaZulu-Natal | CHATSWORTH SECONDARY SCHOOL | 500116143 | eThekwini | Final Completion | Approved | 2016-02-20 | 2018-04-04 | 2022-10-04 | 2022-01-25 | 2024-04-25 | 649027 | 3934973 | 4584000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65531 | W/500272949/SDS | KwaZulu-Natal | SOMASHI PRIMARY SCHOOL | 500272949 | Umvoti | Design | Active - Contracted | 2016-02-20 |  | 2024-03-30 |  |  | 351162 | 1961838 | 2313000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65533 | DB/500307729/SDS | KwaZulu-Natal | ZENZELENI MASHAMASE SECONDARY SECONDARY | 500307729 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-12-11 | 2022-06-01 | 2022-06-13 | 2025-06-29 | 734832 | 3347568 | 4082400 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65534 | DB/500271617/SDS | KwaZulu-Natal | SIZOPHUMELELE HIGH SCHOOL | 500271617 | Umdoni | Construction 76% - 99% | Active - Contracted | 2019-10-30 | 2020-02-10 | 2023-07-14 | 2023-10-30 | 2025-02-20 | 1285316 | 6525478 | 7810794 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65536 | DB/500319791/WS | KwaZulu-Natal | ZICABANGELE PRIMARY SCHOOL | 500319791 | uMhlathuze | Design | Active - Not Contracted | 2016-06-06 |  | 2027-10-10 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65538 | W/500300181/SDS | KwaZulu-Natal | ZILUNGISELE PRIMARY SCHOOL | 500300181 | KwaDukuza | Design | Active - Not Contracted | 2016-06-06 |  | 2027-05-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65539 | DB/500300329/SDS | KwaZulu-Natal | ZIMEME SECONDARY SCHOOL | 500300329 | Nkandla | Design | Active - Not Contracted | 2016-06-06 |  | 2027-06-20 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65540 | DB/500307507/SDS | KwaZulu-Natal | SIZAKAHLE HIGH SCHOOL | 500307507 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65541 | DB/500300403/SDS | KwaZulu-Natal | ZIMISELE PRIMARY SCHOOL | 500300403 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2027-10-16 |  |  | 1966500 | 8958500 | 10925000 | Equitable Share | Maintenance and Repairs
|  | 65546 | DB/500300699/SDS | KwaZulu-Natal | ZIPHOZONKE PRIMARY SCHOOL | 500300699 | uMhlathuze | Design | Active - Not Contracted | 2016-06-06 |  | 2027-09-26 |  |  | 1396823 | 6363305 | 7760128 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65547 | W/500302956/SDS | KwaZulu-Natal | ZUBANE PRIMARY SCHOOL | 500302956 | Ndwedwe | Final Completion | Active - Not Contracted | 2016-06-06 | 2018-04-27 | 2023-10-01 | 2024-03-30 | 2024-03-30 | 292668 | 1542832 | 1835500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65548 | W/500301476/SDS | KwaZulu-Natal | ZUZIOCEBO HIGH SCHOOL | 500301476 | uMuziwabantu | Design | Active - Not Contracted | 2016-06-06 |  | 2024-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65551 | DB/500338402/SDS | KwaZulu-Natal | ZWANANI PRIMARY SCHOOL | 500338402 | Nkandla | Construction 76% - 99% | Active - Contracted | 2020-03-06 | 2020-06-20 | 2023-10-03 | 2023-11-08 | 2027-12-04 | 768681 | 6455712 | 7224393 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65552 | DB/500301772/SDS | KwaZulu-Natal | ZWELETHU SECONDARY SCHOOL | 500301772 | eThekwini | Practical Completion (100%) | Active - Contracted | 2020-01-05 | 2020-08-10 | 2022-10-04 | 2022-11-09 | 2027-12-08 | 1012314 | 4611654 | 5623968 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65555 | DB/500301883/SDS | KwaZulu-Natal | ZWELIHLE SENIOR SECONDARY SCHOOL | 500301883 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-01-15 | 2022-07-04 | 2022-10-12 | 2027-09-13 | 782724 | 3565742 | 4348466 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65556 | DB/500161505/SDS | KwaZulu-Natal | IMVUNULO SECONDARY SCHOOL | 500161505 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-04-10 | 2023-10-10 | 2023-03-30 | 2023-03-30 | 772149 | 3517568 | 4289717 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65560 | DB/500116772/SDS | KwaZulu-Natal | CLAIRWOOD BOYS PRIMARY SCHOOL | 500116772 | eThekwini | Final Completion | Approved | 2016-04-20 | 2018-01-15 | 2022-07-09 | 2022-07-09 | 2024-07-09 | 408912 | 1906088 | 2315000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65562 | DB/500268546/SDS | KwaZulu-Natal | SITHANDIWE PRIMARY SCHOOL | 500268546 | eThekwini | Final Completion | Approved | 2015-11-20 | 2018-05-04 | 2024-03-30 | 2024-03-30 | 2025-04-30 | 464114 | 2114297 | 2578411 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65564 | DB/500116846/SDS | KwaZulu-Natal | CLAIRWOOD SECONDARY SCHOOL | 50016846 | eThekwini | Final Completion | Approved | 2016-02-20 | 2018-04-04 | 2022-10-04 | 2022-03-26 | 2024-04-26 | 3367949 | 15342878 | 18710827 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65565 | W/500268028/SDS | KwaZulu-Natal | SIQHAKAZILE PRIMARY SCHOOL | 500268028 | Umzumbe | Final Completion | Active - Contracted | 2016-02-20 | 2018-02-28 | 2022-06-30 | 2022-10-16 | 2023-04-01 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65566 | DB/500117031/SDS | KwaZulu-Natal | CLAREVILLE PRIMARY SCHOOL | 500117031 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2017-07-01 | 2023-02-20 | 2023-12-11 | 2027-03-25 | 107606 | 521394 | 629000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65567 | DB/500267843/SDS | KwaZulu-Natal | SIPHOSO SECONDARY SCHOOL | 500267843 | uMlalazi | Design | Active - Contracted | 2015-11-20 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65568 | DB/500117697/SDS | KwaZulu-Natal | COLLEGEVALE PRIMARY SCHOOL | 500117697 | eThekwini | Design | Active - Not Contracted | 2016-02-20 |  | 2024-03-20 |  |  | 2818994 | 12842082 | 15661076 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65570 | W/500118474/SDS | KwaZulu-Natal | CRANBURN PRIMARY SCHOOL | 500118474 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-08-20 | 2023-02-20 | 2022-02-20 | 2023-02-20 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65572 | DB/500118992/SDS | KwaZulu-Natal | CWAKA PRIMARY SCHOOL | 500118992 | Mfolozi | Design | Active - Not Contracted | 2016-06-06 |  | 2024-03-31 |  |  | 981774 | 4472526 | 5454300 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65620 | W/500266437/SDS | KwaZulu-Natal | SINEKE PRIMARY SCHOOL | 500266437 | Ray Nkonyeni | Project Initiation | Proposed | 2016-02-20 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65621 | DB/500265808/SDS | KwaZulu-Natal | SILVERTOWN PRIMARY SCHOOL | 500265808 | eThekwini | Final Completion | Approved | 2020-01-05 | 2020-06-21 | 2023-10-01 | 2023-01-05 | 2025-04-03 | 834078 | 3799690 | 4633768 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65622 | W/500119436/SDS | KwaZulu-Natal | DALEVIEW SECONDARY SCHOOL | 500119436 | eThekwini | Project Initiation | Active - Not Contracted | 2016-02-20 |  | 2024-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65623 | DB/500264513/SDS | KwaZulu-Natal | SIGISI PRIMARY SCHOOL | 500264513 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-12-11 | 2023-06-10 | 2023-06-10 | 2025-06-10 | 1086840 | 4088590 | 5175430 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65628 | W/500249010/SDS | KwaZulu-Natal | PHOENIX HEIGHTS PRIMARY SCHOOL | 500249010 | eThekwini | Final Completion | Active - Contracted | 2017-06-06 | 2021-02-26 | 2023-10-01 | 2021-04-30 | 2022-03-31 | 144396 | 810249 | 954645 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65629 | W/500263255/SDS | KwaZulu-Natal | SIBONGUMFEKA SECONDARY SCHOOL | 500263255 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2021-02-26 | 2023-06-30 | 2023-07-30 | 2023-05-31 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65630 | W/500251304/SDS | KwaZulu-Natal | PORT SHEPSTONE SENIOR PRIMARY SCHOOL | 500251304 | Ray Nkonyeni | Project Initiation | Active - Not Contracted | 2016-06-06 |  | 2023-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65631 | DB/500262441/SDS | KwaZulu-Natal | SHUMAYELA SECONDARY SCHOOL | 500262441 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2018-04-03 | 2023-10-03 | 2023-03-12 | 2025-06-30 | 1199300 | 5463479 | 6662779 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65632 | DB/500245791/SDS | KwaZulu-Natal | PR PATHER SECONDARY SCHOOL | 500245791 | eThekwini | Final Completion | Approved | 2016-06-06 | 2018-04-05 | 2023-10-05 | 2023-11-16 | 2025-11-16 | 1049931 | 4783018 | 5832949 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65633 | W/500305065/SDS | KwaZulu-Natal | PRO NOBIS SPECIAL SCHOOL | 500305065 | Endumeni | Final Completion | Active - Contracted | 2016-06-06 | 2021-02-26 | 2023-03-01 | 2022-02-28 | 2022-04-01 | 100000 | 2000000 | 2100000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65634 | DB/500262034/SDS | KwaZulu-Natal | SHIBASE PRIMARY SCHOOL | 500262034 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2018-01-12 | 2023-09-28 | 2023-06-30 | 2025-07-10 | 488291 | 2224436 | 2712727 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65640 | W/500119473/SDS | KwaZulu-Natal | DALIBO PRIMARY SCHOOL | 500119473 | KwaDukuza | Design | Active - Not Contracted | 2016-04-20 |  | 2024-04-20 |  |  | 1252000 | 2652000 | 3904000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 65642 | W/500119584/SDS | KwaZulu-Natal | DALUSIZO HIGH SCHOOL | 500119584 | Umdoni | Project Initiation | Active - Not Contracted | 2016-04-20 |  | 2024-02-20 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65644 | W/500494801/SDS | KwaZulu-Natal | DANIEL MZAMO SPECIAL SCHOOL | 500494801 | The Msunduzi | Project Initiation | Active - Not Contracted | 2016-02-20 |  | 2024-04-20 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65646 | W/500120028/SDS | KwaZulu-Natal | DARNALL SECONDARY SCHOOL | 500120028 | KwaDukuza | Tender | Active - Not Contracted | 2016-05-20 |  | 2025-06-30 |  |  | 270000 | 6595000 | 6865000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65648 | W/500121471/SDS | KwaZulu-Natal | DINGEZWENI PRIMARY SCHOOL | 500121471 | KwaDukuza | Project Initiation | Active - Not Contracted | 2016-02-20 |  | 2024-05-20 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65650 | DB/500121952/SDS | KwaZulu-Natal | DLAMVUZO HIGH SCHOOL | 500121952 | uMhlathuze | Design | Active - Not Contracted | 2016-02-20 |  | 2024-03-25 |  |  | 1594959 | 7265926 | 8860885 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65651 | DB/500121989/SDS | KwaZulu-Natal | DLANGEZWA SECONDARY SCHOOL | 500121989 | uMhlathuze | Design | Active - Not Contracted | 2016-06-20 |  | 2024-03-25 |  |  | 3818659 | 17396114 | 21214773 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65652 | DB/500123099/SDS | KwaZulu-Natal | DOVER COMBINED SCHOOL | 500123099 | uMhlathuze | Design | Active - Not Contracted | 2016-02-20 |  | 2024-03-25 |  |  | 805450 | 3669274 | 4474724 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65654 | DB/500125060/SDS | KwaZulu-Natal | DUNYWA PRIMARY SCHOOL | 500125060 | Ray Nkonyeni | Construction 51% - 75% | Active - Contracted | 2016-04-20 | 2020-01-30 | 2024-03-30 | 2020-08-30 | 2024-03-30 | 1068651 | 4868301 | 5936952 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65656 | DB/500252377/SDS | KwaZulu-Natal | QANTAYI SECONDARY SCHOOL | 500252377 | uMhlathuze | Design | Active - Not Contracted | 2016-06-06 |  | 2024-10-01 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65658 | W/500254486/SDS | KwaZulu-Natal | RA ENGAR PRIMARY SCHOOL | 500254486 | Ray Nkonyeni | Project Initiation | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65664 | DB/500281089/SDS | KwaZulu-Natal | REUNION SPECIAL SCHOOL | 500281089 | eThekwini | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2019-01-17 | 2022-07-01 | 2022-10-28 | 2027-08-19 | 752147 | 3694853 | 4447000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65665 | W/500325008/SDS | KwaZulu-Natal | ROBERT HLONGWA SECONDARY SCHOOL | 500325008 | eThekwini | Design | Active - Not Contracted | 2016-06-06 |  | 2023-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65666 | W/500256410/SDS | KwaZulu-Natal | ROSELAND PRIMARY SCHOOL | 500256410 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2021-02-26 | 2023-02-01 | 2022-02-28 | 2022-05-31 | 157222 | 831410 | 988632 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65667 | DB/500256521/SDS | KwaZulu-Natal | ROSEVILLE SECONDARY SCHOOL | 500256521 | Umdoni | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-06-02 | 2023-07-15 | 2023-02-25 | 2025-03-24 | 1588595 | 7467387 | 9055982 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65668 | W/500256632/SDS | KwaZulu-Natal | RUSSEL HIGH SCHOOL | 500256632 | The Msunduzi | Design | Active - Not Contracted | 2016-06-06 |  | 2025-10-01 |  |  | 300000 | 5117000 | 5417000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65670 | W/500258519/SDS | KwaZulu-Natal | SANZWILI PRIMARY SCHOOL | 500258519 | The Msunduzi | Project Initiation | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65671 | DB/500258593/SDS | KwaZulu-Natal | SAPHINDA PRIMARY SCHOOL | 500258593 | eThekwini | Final Completion | Approved | 2016-06-06 | 2020-05-28 | 2023-12-11 | 2023-02-26 | 2025-03-11 | 1588913 | 7238382 | 8827295 | Education Infrastructure Grant | Upgrading and Additions
|  | 65673 | W/500259518/SDS | KwaZulu-Natal | SCOTTBURGH HIGH SCHOOL | 500259518 | Umdoni | Project Initiation | Active - Not Contracted | 2016-06-06 |  | 2023-10-01 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65674 | DB/500260813/SDS | KwaZulu-Natal | SETTLERS PRIMARY SCHOOL | 500260813 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-01-16 | 2023-07-16 | 2023-07-16 | 2025-07-16 | 945584 | 4307658 | 5253242 | Education Infrastructure Grant | Upgrading and Additions
|  | 65675 | DB/500261035/SDS | KwaZulu-Natal | SEZELA PRIMARY SCHOOL | 500261035 | Umdoni | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-06-01 | 2023-10-30 | 2023-02-25 | 2025-03-10 | 1153419 | 7853058 | 9006477 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65677 | DB/500125134/SDS | KwaZulu-Natal | DURBAN EAST PRIMARY SCHOOL | 500125134 | eThekwini | Practical Completion (100%) | Approved | 2016-04-20 | 2018-12-01 | 2022-04-20 | 2022-05-05 | 2024-06-29 | 1325056 | 6036368 | 7361424 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65679 | DB/500277796/SDS | KwaZulu-Natal | DURBAN PRIMARY SCHOOL | 500277796 | eThekwini | Design | Active - Not Contracted | 2016-04-20 |  | 2024-03-30 |  |  | 2619310 | 11932411 | 14551721 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65682 | DB/500125504/SDS | KwaZulu-Natal | DURBAN SOUTH PRIMARY SCHOOL | 500125504 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2019-07-31 | 2023-02-26 | 2023-02-26 | 2027-03-30 | 1093033 | 4979373 | 6072406 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65688 | W/500126873/SDS | KwaZulu-Natal | EDENDALE TECHNICAL HIGH SCHOOL | 500126873 | uMngeni | Project Initiation | Active - Not Contracted | 2016-04-20 |  | 2024-03-20 |  |  | 800000 | 2700000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65689 | DB/500127317/SDS | KwaZulu-Natal | EGOLI PRIMARY SCHOOL | 500127317 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-08-20 | 2020-05-31 | 2024-03-20 | 2020-11-30 | 2024-03-20 | 1122000 | 5110000 | 6232000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65908 | DB/500128390/SDS | KwaZulu-Natal | EKUDONSENI PRIMARY SCHOOL | 500128390 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-05-20 | 2019-07-31 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 678977 | 4451000 | 5129977 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65910 | DB/500289488/SDS | KwaZulu-Natal | ST PATRICKS PRIMARY SCHOOL | 500289488 | Ray Nkonyeni | Final Completion | Active - Not Contracted | 2020-01-05 | 2020-06-12 | 2023-01-06 | 2022-10-03 | 2025-03-21 | 1469837 | 6695924 | 8165761 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65922 | DB/500276760/SDS | KwaZulu-Natal | ST RAPHAEL SECONDAQRY SCHOOL | 500276760 | eThekwini | Final Completion | Approved | 2020-02-05 | 2020-08-25 | 2022-09-25 | 2022-10-21 | 2022-11-15 | 241214 | 2121786 | 2363000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65926 | DB/500278536/SDS | KwaZulu-Natal | SUMMERFIELD PRIMARY SCHOOL | 500278536 | eThekwini | Construction 1% - 25% | Active - Contracted | 2019-10-30 | 2020-06-12 | 2022-07-14 | 2022-07-28 | 2025-08-31 | 1036810 | 4723246 | 5760056 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65927 | DB/500278869/SDS | KwaZulu-Natal | SUNNYDALE SECONDARY SCHOOL | 500278869 | uMhlathuze | Design | Active - Not Contracted | 2016-08-20 |  | 2024-05-20 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65928 | DB/500279239/SDS | KwaZulu-Natal | SWELIHLE HIGH SCHOOL | 500279239 | eThekwini | Final Completion | Approved | 2016-04-20 | 2018-01-15 | 2022-06-01 | 2022-10-30 | 2025-07-15 | 946718 | 4312824 | 5259542 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65930 | W/500334591/SDS | KwaZulu-Natal | TATAZELA SECONDARY SCHOOL | 500334591 | Inkosi Langalibalele | Project Initiation | Active - Not Contracted | 2016-02-20 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65931 | W/500279572/SDS | KwaZulu-Natal | Tauricus Intermediate School | 500279572 | The Msunduzi | Design | Active - Not Contracted | 2016-05-20 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 65932 | DB/500285418/SDS | KwaZulu-Natal | THAMBOLINI SECONDARY SCHOOL | 500285418 | uMhlathuze | Design | Active - Not Contracted | 2016-04-20 |  | 2024-05-20 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65933 | W/500340474/SDS | KwaZulu-Natal | THANDANANI PRIMARY SCHOOL | 500340474 | Ubuhlebezwe | Final Completion | Active - Contracted | 2016-05-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 192971 | 2814287 | 3007258 | Education Infrastructure Grant | Upgrading and Additions
|  | 65934 | DB/500280682/SDS | KwaZulu-Natal | THANDUYISE SECONDARY SCHOOL | 500280682 | uMhlathuze | Design | Active - Not Contracted | 2016-08-20 |  | 2024-08-28 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65935 | W/500280275/SDS | KwaZulu-Natal | THANDIMFUNDO PRIMARY SCHOOL | 500280275 | eThekwini | Final Completion | Active - Contracted | 2016-08-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 153501 | 699281 | 852782 | Education Infrastructure Grant | Upgrading and Additions
|  | 65937 | DB/500243904/SDS | KwaZulu-Natal | ONGOYE SECONDARY SCHOOL | 500243904 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65945 | DB/500285603/SDS | KwaZulu-Natal | UBAMBISWANO SECONDARY SCHOOL | DB/500285603/SDS | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2024-03-01 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65946 | W/500285344/SDS | KwaZulu-Natal | TSHUTSHUTSHU HIGH SCHOOL | 500285344 | uMhlathuze | Final Completion | Active - Contracted | 2017-09-12 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2022-03-31 | 199889 | 1342955 | 1542844 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65950 | W/500285085/SDS | KwaZulu-Natal | TSHELABANTU PRIMARY SCHOOL | 500285085 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2017-09-12 | 2019-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 446901 | 2035884 | 2482785 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65953 | W/500283383/SDS | KwaZulu-Natal | THUKELA SECONDARY SCHOOL | 500283383 | KwaDukuza | Tender | Active - Contracted | 2017-09-12 |  | 2025-06-30 |  |  | 746491 | 3400680 | 4147171 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65955 | DB/500328188/SDS | KwaZulu-Natal | THOLISU HIGH SCHOOL | 500328188 | Umdoni | Practical Completion (100%) | Active - Contracted | 2019-09-12 | 2020-01-03 | 2023-03-10 | 2022-04-06 | 2025-05-25 | 599836 | 2732586 | 3332422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65958 | DB/500282606/SDS | KwaZulu-Natal | THOLIMFUNDO HIGH SCHOOL | 500282606 | Umdoni | Construction 51% - 75% | Active - Contracted | 2020-01-06 | 2020-03-01 | 2023-05-12 | 2023-06-06 | 2025-09-28 | 1923963 | 8764719 | 10688682 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65959 | DB/500242646/SDS | KwaZulu-Natal | THEMBELIHLE PRIMARY SCHOOL | 500281533 | Ulundi | Design | Active - Not Contracted | 2017-09-12 |  | 2024-03-26 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65962 | DB/500214563/SDS | KwaZulu-Natal | MONTCLAIR PRIMARY SCHOOL | 5000307174 | eThekwini | On Hold | Active - Not Contracted | 2017-09-12 | 2018-04-06 | 2023-10-04 | 2023-10-04 | 2023-06-19 | 10001 | 37621 | 47622 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65963 | DB/500214600/SDS | KwaZulu-Natal | MONTCLAIR SENIOR PRIMARY SCHOOL | 500214600 | eThekwini | On Hold | Active - Not Contracted | 2017-09-12 | 2018-04-06 | 2023-10-04 | 2023-05-05 | 2023-03-04 | 18503 | 69608 | 88111 | Education Infrastructure Grant | Maintenance and Repairs
|  | 65966 | DB/500213342/SDS | KwaZulu-Natal | MNGANIWAKHE PRIMARY SCHOOL | 500213342 | eThekwini | Design | Active - Not Contracted | 2017-09-12 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65968 | DB/500307211/ECD | KwaZulu-Natal | MUNTUNOKUDLAI HIGH SCHOOL | 500213786 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2023-03-20 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 65969 | DB/500222148/SDS | KwaZulu-Natal | MZINGAZI PRIMARY SCHOOL | 500222148 | uMhlathuze | Design | Active - Not Contracted | 2017-09-12 |  | 2023-03-30 |  |  | 300000 | 1700000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 65972 | V3004/2017 | Northern Cape | E R MOTSWALEDI PRIMARY SCHOOL | 300017201 | Phokwane | Practical Completion (100%) | Active - Contracted | 2017-11-27 | 2019-08-22 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 1804992 | 5853753 | 7658745 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66007 | LE19TMT17038 | Limpopo | MATSAMBU SECONDARY | EDDP184/0030 | Greater Giyani | Tender | Active - Contracted | 2014-04-30 |  | 2025-03-31 |  |  | 591521 | 7599375 | 8190896 | Education Infrastructure Grant | Upgrading and Additions
|  | 66116 | W/500327561/SDS | KwaZulu-Natal | EMADULWINI PRIMARY SCHOOL | 500327561 | Nkandla | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 477969 | 2177412 | 2655381 | Education Infrastructure Grant | Upgrading and Additions
|  | 66117 | W/500106634/SDS | KwaZulu-Natal | BAZINI PRIMARY SCHOOL | 500106634 | Nongoma | Practical Completion (100%) | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 1191451 | 5427722 | 6619173 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66118 | W/500140711/SDS | KwaZulu-Natal | ESIKHWEBEZANE PRIMARY SCHOOL | 500140711 | Ulundi | Final Completion | Active - Not Contracted | 2016-06-06 | 2020-03-03 | 2023-06-30 | 2022-06-28 | 2022-06-28 | 448549 | 2043392 | 2491941 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66120 | W/500209309/SDS | KwaZulu-Natal | MGAZINI PRIMARY SCHOOL | 500209309 | Mfolozi | Tender | Active - Contracted | 2016-06-06 |  | 2025-01-30 |  |  | 563296 | 2566126 | 3129422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66122 | W/500298627/SDS | KwaZulu-Natal | ZAMANGOTHANDO SECONDARY SCHOOL | 500298627 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2020-11-01 | 2022-06-30 | 2021-07-01 | 2023-06-30 | 796197 | 3627118 | 4423315 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66123 | W/500495948/SDS | KwaZulu-Natal | THOLIMFUNDO SECONDARY SCHOOL | 500495948 | Ray Nkonyeni | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 222643 | 1014264 | 1236907 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66124 | W/500181004/SDS | KwaZulu-Natal | KWAMDOLO JUNIOR PRIMARY SCHOOL | 500181004 | Nongoma | Feasibility | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 100000 | 170000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66125 | W/500135087/SDS | KwaZulu-Natal | EMTHUNZINI PRIMARY SCHOOL | 500135087 | Newcastle | Tender | Active - Not Contracted | 2016-06-06 |  | 2024-06-30 |  |  | 471366 | 2147333 | 2618699 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66126 | W/500324786/SDS | KwaZulu-Natal | SIBONILE PRIMARY SCHOOL | 500324786 | uPhongolo | Final Completion | Active - Contracted | 2016-06-06 | 2021-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 680932 | 3102026 | 3782958 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66127 | W/500444888/SDS | KwaZulu-Natal | VEZUKUKHANYA PRIMARY SCHOOL | 500444888 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 341716 | 1556705 | 1898421 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66128 | W/500311392/SDS | KwaZulu-Natal | BHANGANOMO PRIMARY SCHOOL | 500311392 | Nongoma | Construction 76% - 99% | Active - Contracted | 2017-06-06 |  | 2023-04-03 |  |  | 317765 | 1876235 | 2194000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 66130 | W/500309838/SDS | KwaZulu-Natal | SIHOLWA PRIMARY SCHOOL | 500309838 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 702485 | 3200210 | 3902695 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66137 | W/500201058/SDS | KwaZulu-Natal | MASITHOKOZE PRIMARY SCHOOL | 500201058 | uPhongolo | Practical Completion (100%) | Active - Not Contracted | 2016-06-06 | 2018-04-27 | 2023-06-30 | 2023-10-30 | 2023-11-11 | 530164 | 3399104 | 3929268 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66138 | W/500290265/SDS | KwaZulu-Natal | UQWEQWE SECONDARY SCHOOL | 500290265 | Abaqulusi | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 1554740 | 7082704 | 8637444 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66140 | W/500182558/SDS | KwaZulu-Natal | KWANOTSHELWA SECONDARY SCHOOL | 500182558 | Abaqulusi | Final Completion | Active - Contracted | 2016-06-06 | 2022-03-30 | 2023-06-30 | 2024-04-30 | 2025-04-30 | 1244727 | 5670424 | 6915151 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66141 | W/500180728/SDS | KwaZulu-Natal | IMBUTHUMA PRIMARY SCHOOL | 500180728 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 432205 | 2722966 | 3155171 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66142 | W/500266770/SDS | KwaZulu-Natal | SINOTHANDO PRIMARY SCHOOL | 500266770 | uPhongolo | Tender | Active - Not Contracted | 2016-06-06 |  | 2023-06-30 |  |  | 462017 | 2104745 | 2566762 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66144 | W/500303104/SDS | KwaZulu-Natal | ONGANE PRIMARY SCHOOL | 500303104 | eDumbe | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 812522 | 3701490 | 4514012 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66145 | W/500273393/SDS | KwaZulu-Natal | SONDABA PRIMARY SCHOOL | 500273393 | uPhongolo | Tender | Active - Contracted | 2016-06-06 |  | 2025-06-30 |  |  | 963576 | 4389625 | 5353201 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66155 | W/500124912/UA | KwaZulu-Natal | DUNGA JUNIOR PRIMARY SCHOOL | 500124912 | Mandeni | Practical Completion (100%) | Proposed | 2016-02-20 | 2020-06-15 | 2023-03-30 | 2022-05-30 | 2024-06-15 | 200000 | 300000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66168 | W/500106153/SDS | KwaZulu-Natal | BATHEMBU SECONDARY SCHOOL | 500106153 | Msinga | Final Completion | Active - Contracted | 2016-05-09 | 2018-10-30 | 2023-06-30 | 2021-06-30 | 2022-06-30 | 581767 | 3438844 | 4020611 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66170 | W/500440633/WS | KwaZulu-Natal | PHUMELA PRIMARY SCHOOL | 500440633 | Msinga | Design | Active - Not Contracted | 2016-02-20 |  | 2025-06-30 |  |  | 165000 | 753000 | 918000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66171 | W/500313945/WS | KwaZulu-Natal | SUKASAMBE JUNIOR SECONDARY SCHOOL | 500313945 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-03-31 | 200000 | 300000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66497 | W/500271654/WS | KwaZulu-Natal | SIZUZULU PRIMARY SCHOOL | 500271654 | eDumbe | Tender | Active - Contracted | 2016-02-20 |  | 2026-06-30 |  |  | 90000 | 410000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66498 | W/500208310/WS | KwaZulu-Natal | MFAKUBHEKA PRIMARY SCHOOL | 500208310 | Umhlabuyalingana | Tender | Active - Not Contracted | 2016-02-20 |  | 2025-03-31 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66500 | I/500188441/WS | KwaZulu-Natal | LUHLANGA PRIMARY SCHOOL | 500188441 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-10-24 | 2023-03-30 | 2022-11-20 | 2023-01-31 | 220000 | 1300000 | 1520000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66501 | W/500307655/WS | KwaZulu-Natal | VEZOBALA JUNIOR SECONDARY SCHOOL | 500307655 | Mtubatuba | Construction 51% - 75% | Active - Contracted | 2016-02-20 |  | 2025-06-30 |  |  | 901885 | 4108588 | 5010473 | Education Infrastructure Grant | Upgrading and Additions
|  | 66503 | W/500309801/WS | KwaZulu-Natal | NHLAMVU PRIMARY SCHOOL | 500309801 | Umhlabuyalingana | Tender | Active - Contracted | 2016-02-20 |  | 2025-03-31 |  |  | 829290 | 3777875 | 4607165 | Education Infrastructure Grant | Upgrading and Additions
|  | 66530 | P9005811 | Eastern Cape | BETHANIA JUNIOR SECONDARY SCHOOL | 200500026 | Elundini | Practical Completion (100%) | Active - Contracted | 2017-11-17 | 2017-11-27 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 1626565 | 11200800 | 12827365 | Education Infrastructure Grant | Upgrading and Additions
|  | 66544 | P9005747 | Eastern Cape | ARTHUR NGUNGA SENIOR SECONDARY SCHOOL | 200500005 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2017-06-29 | 2017-08-24 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 8497463 | 45634415 | 54131878 | Education Infrastructure Grant | Upgrading and Additions
|  | 66549 | P9008749_ | Eastern Cape | GOBIZIZWE SENIOR PRIMARY SCHOOL | 200400214 | King Sabata Dalindyebo | Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 5154737 | 5154737 | Education Infrastructure Grant | Upgrading and Additions
|  | 66558 | P9008283 | Eastern Cape | KING NDLOVUYEZWE NDAMASE SPECIAL SCHOOL | 200404036 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-07-09 | 2020-02-28 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 9997532 | 9997532 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66569 | P9005874_ | Eastern Cape | CABAZI PRIMARY SCHOOL | 200500077 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2017-10-21 | 2017-12-21 | 2024-03-31 | 2024-03-31 | 2025-03-31 | 3048508 | 1388627895 | 1391676403 | Education Infrastructure Grant | Upgrading and Additions
|  | 66573 | P9003558 | Eastern Cape | MBANANGA SENIOR PRIMARY SCHOOL | 200400525 | Nyandeni | Construction 76% - 99% | Active - Contracted | 2017-04-20 | 2017-06-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 16099369 | 16099369 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 66574 | P9005814_ | Eastern Cape | CABANE JUNIOR SECONDARY SCHOOL | 200500075 | Umzimvubu | Construction 1% - 25% | Active - Not Contracted | 2018-10-08 | 2018-11-08 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 2790271 | 11096008 | 13886279 | Education Infrastructure Grant | Upgrading and Additions
|  | 66577 | P9006994_ | Eastern Cape | BIKIZANA JUNIOR SECONDARY SCHOOL | 200600046 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2023-03-31 | 2024-03-31 | 2025-03-31 | 758031 | 3295790 | 4053821 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66591 | P0002049 | Eastern Cape | CUNNINGHAM SENIOR SECONDARY SCHOOL | 200300053 | Mnquma | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 5182119 | 50159799 | 55341918 | Education Infrastructure Grant | Upgrading and Additions
|  | 66596 | P9006647 | Eastern Cape | BUFFALO FLATS PRIMARY SCHOOL | 200200061 | Buffalo City | Design | Active - Contracted | 2016-04-01 |  | 2025-03-31 |  |  | 0 | 9411066 | 9411066 | Education Infrastructure Grant | Upgrading and Additions
|  | 66606 | P9006098 | Eastern Cape | HLANKOMO JUNIOR SECONDARY SCHOOL | 200500303 | Ntabankulu | Construction 51% - 75% | Active - Contracted | 2018-09-01 | 2022-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3361800 | 3361800 | Education Infrastructure Grant | Upgrading and Additions
|  | 66628 | P9006102 | Eastern Cape | ILINGELETHU JUNIOR SECONDARY SCHOOL | 200500318 | Elundini | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2017-07-31 | 2026-03-31 | 2024-03-31 | 2026-03-31 | 4218992 | 12455651 | 16674643 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 66636 | P9007874_ | Eastern Cape | BATHURST PRIMARY SCHOOL | 200100049 | Ndlambe | Tender | Active - Not Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 0 | 625275 | 625275 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66649 | P9005340_ | Eastern Cape | J J NJEZA HIGH SCHOOL | 200300723 | Mnquma | Final Completion | Approved | 2014-07-21 | 2014-09-21 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 258147 | 1406793 | 1664940 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66652 | P9013426 | Eastern Cape | JAMES NGUZA JUNIOR SECONDARY SCHOOL | 200300155 | Mnquma | Design | Active - Contracted | 2015-02-02 |  | 2026-03-31 |  |  | 0 | 1582039 | 1582039 | Education Infrastructure Grant | Upgrading and Additions
|  | 66657 | W/500107966/SDS | KwaZulu-Natal | BHANDE HIGH SCHOOL | 500107966 | Alfred Duma | Design | Active - Not Contracted | 2017-02-20 |  | 2024-03-31 |  |  | 90000 | 631000 | 721000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66663 | P9005335_ | Eastern Cape | MENTE JUNIOR SECONDARY SCHOOL | 200300848 | Mbhashe | Final Completion | Active - Contracted | 2014-08-04 | 2014-08-12 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 0 | 10868 | 10868 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66673 | P0001142_ | Eastern Cape | DALUXOLO SENIOR PRIMARY SCHOOL | 200400113 | Engcobo | Final Completion | Approved | 2007-10-02 | 2007-11-02 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 200300 | 1146484 | 1346784 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66687 | P9006478 | Eastern Cape | MAMPELAZWE JUNIOR SECONDARY SCHOOL | 200501376 | Ingquza Hill | Construction 1% - 25% | Active - Contracted | 2017-11-17 | 2017-12-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 966199 | 1786758699 | 1787724898 | Education Infrastructure Grant | Upgrading and Additions
|  | 66689 | P9011588_ | Eastern Cape | ENDUKU PRIMARY JUNIOR SCHOOL | 200400166 | Engcobo | Tender | Active - Not Contracted | 2017-04-03 |  | 2026-03-31 |  |  | 0 | 12509970 | 12509970 | Education Infrastructure Grant | Upgrading and Additions
|  | 66692 | P0003555_ | Eastern Cape | MAQULU JUNIOR SECONDARY SCHOOL | 200500578 | Ingquza Hill | Practical Completion (100%) | Potential | 2012-07-03 | 2014-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 1409604 | 1409604 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66693 | W/500140230/SDS | KwaZulu-Natal | ESIDINSI PRIMARY SCHOOL | 500140230 | Nongoma | Construction 26% - 50% | Active - Contracted | 2017-02-20 | 2017-03-30 | 2023-05-31 | 2023-05-31 | 2023-05-31 | 1324030 | 6031694 | 7355724 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66701 | P9006484 | Eastern Cape | TSOLOBENG JUNIOR SECONDARY SCHOOL | 200501240 | Elundini | Construction 76% - 99% | Active - Contracted | 2017-11-08 | 2017-12-31 | 2026-03-31 | 2023-03-31 | 2026-03-31 | 0 | 2891289 | 2891289 | Education Infrastructure Grant | Upgrading and Additions
|  | 66712 | W/500209827/SDS | KwaZulu-Natal | MGWAYINI PRIMARY SCHOOL | 500209827 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-02-20 |  | 2025-01-30 |  |  | 128250 | 584250 | 712500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66716 | W/500211529/SDS | KwaZulu-Natal | MJWAYELI PRIMARY SCHOOL | 500211529 | Inkosi Langalibalele | Construction 26% - 50% | Active - Contracted | 2017-02-20 | 2020-01-01 | 2023-03-30 | 2023-03-30 | 2025-03-30 | 631218 | 2875548 | 3506766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66720 | W/500226292/SDS | KwaZulu-Natal | NETHEZEKA HIGH SCHOOL | 500226292 | Alfred Duma | Design | Active - Contracted | 2017-02-20 |  | 2024-03-30 |  |  | 49000 | 221000 | 270000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66731 | W/500280164/SDS | KwaZulu-Natal | THAMSANQA PRIMARY SCHOOL | 500280164 | Abaqulusi | Final Completion | Active - Contracted | 2017-02-20 | 2017-03-30 | 2023-06-30 | 2018-01-30 | 2022-05-31 | 413257 | 1882614 | 2295871 | Education Infrastructure Grant | Upgrading and Additions
|  | 66736 | W/500440152/SDS | KwaZulu-Natal | UKUKHANYA KOMSINGA SPECIAL SCHOOL(LSEN) | 500440152 | Msinga | Design | Active - Not Contracted | 2017-02-20 |  | 2023-06-30 |  |  | 200000 | 300000 | 500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 66738 | P9004718_ | Eastern Cape | KANYISA SPECIAL SCHOOL | 200600319 | Engcobo | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2017-10-19 | 2024-12-31 | 2025-12-31 | 2026-12-31 | 20771505 | 144028164 | 164799669 | Education Infrastructure Grant | Upgrading and Additions
|  | 66758 | P9008409 | Eastern Cape | AMATOLAVILLE PRIMARY SCHOOL | 200200825 | Amahlathi | Practical Completion (100%) | Active - Contracted | 2017-11-01 |  | 2024-03-31 |  |  | 0 | 8651813 | 8651813 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66760 | P9009669_ | Eastern Cape | NGUBEZULU JUNIOR PRIMARY SCHOOL | 200400774 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-08-06 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 681881 | 4870576 | 5552457 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66762 | P9005270 | Eastern Cape | DUMSI SENIOR SECONDARY SCHOOL | 200500151 | Ntabankulu | Project Initiation | Proposed | 2017-04-01 |  | 2024-03-31 |  |  | 800000 | 5882570 | 6682570 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66771 | P9007271 | Eastern Cape | AMATOLAVILLE JUNIOR SECONDARY SCHOOL | 200200825 | Amahlathi | Tender | Active - Contracted | 2016-04-01 |  | 2026-03-31 |  |  | 2284143 | 0 | 2284143 | Education Infrastructure Grant | Upgrading and Additions
|  | 66803 | P9008284_ | Eastern Cape | MOUNT FLETCHER SPECIAL SCHOOL | 200501604 | Elundini | Practical Completion (100%) | Active - Contracted | 2018-06-25 | 2020-02-28 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 6962865 | 6962865 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66834 | P9008410 | Eastern Cape | MDIZENI PRIMARY SCHOOL | 200200459 | Raymond Mhlaba | Construction 76% - 99% | Active - Contracted | 2017-03-13 | 2017-05-13 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8237401 | 8237401 | Education Infrastructure Grant | Maintenance and Repairs
|  | 66835 | P0002778_ | Eastern Cape | KHAYALETHU SPECIAL SCHOOL | 200201019 | Buffalo City | Construction 76% - 99% | Active - Not Contracted | 2017-04-03 | 2017-07-03 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 3984429 | 171390418 | 175374847 | Education Infrastructure Grant | Upgrading and Additions
|  | 66849 | 25/17/8 | Free State | PM FEES: MPHATI CONSULTING | 25/17/8 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 30000000 | 0 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66852 | 26/17/8 | Free State | PM FEES: MK&ASSOC CONSULTING | 26/17/8 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 30000000 | 0 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66854 | 27/17/18 | Free State | PM FEES: NALA CONSULTING | 27/17/18 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2024-03-31 | 30000000 | 0 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66856 | 28/17/18 | Free State | PM FEES: PHETOGO CONSULTING | 28/17/18 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2022-03-31 | 30000000 | 0 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66864 | 29/17/8 | Free State | PMFEES:`ETSHO CONSULTING | 29/17/8 | Mangaung | Not Applicable | Active - Contracted | 2015-11-01 | 2015-11-30 | 2024-03-31 | 2022-03-31 | 2022-03-31 | 30000000 | 0 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 66869 | 32/17/18 | Free State | INVENTORY: IT EQUIPMENT | 32/17/18 | Mangaung | Project Initiation | Active - Contracted | 2017-12-31 |  | 2026-03-31 |  |  | 6000000 | 0 | 6000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 66874 | 34/17/18 | Free State | MOBILE RELOCATION | 34/17/18 | Mangaung | Construction 1% - 25% | Active - Contracted | 2017-12-31 | 2018-01-31 | 2025-04-01 | 2020-04-01 | 2024-04-01 | 0 | 13000000 | 13000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 67032 | 31/17/18 | Free State | INVENTORY DISTRIBUTION TO SCHOOLS | 31/17/18 | Masilonyana | Construction 1% - 25% | Active - Contracted | 2017-12-31 | 2018-01-31 | 2026-03-31 | 2021-03-31 | 2024-03-31 | 145153000 | 0 | 145153000 | Education Infrastructure Grant | Non-Infrastructure
|  | 67052 | (24/17/18) | Free State | MOBILE KITCHEN | (24/17/18) | Mangaung | Construction 1% - 25% | Active - Contracted | 2017-12-31 | 2018-01-31 | 2025-04-01 | 2019-03-31 | 2022-03-31 | 0 | 9000000 | 9000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 68162 | ST053/2017 | Northern Cape | STRYDENBURG COMBINED SCHOOL | 300022307 | Thembelihle | Construction 76% - 99% | Active - Contracted | 2020-11-27 | 2021-11-25 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70667 | P9010447 | Eastern Cape | Programme Support Unit (PSU) | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2018-01-02 | 2018-01-04 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 355187304 | 0 | 355187304 | Education Infrastructure Grant | Non-Infrastructure
|  | 70801 | P9004821_ | Eastern Cape | NTSONKOTHA SENIOR SECONDARY SCHOOL | 200600642 | Enoch Mgijima | Construction 1% - 25% | Active - Contracted | 2018-09-01 | 2018-09-27 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 24878041 | 171021468 | 195899509 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 70811 | P0002992_ | Eastern Cape | ULWAZI SECONDARY SCHOOL | 200200872 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2011-05-04 | 2016-04-02 | 2024-03-31 | 2022-03-31 | 2022-03-31 | 0 | 1193902 | 1193902 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70815 | P9008740 | Eastern Cape | SIVE SPECIAL SCHOOL (PHASE III) | 200501449 | Matatiele | Practical Completion (100%) | Active - Contracted | 2013-12-12 | 2017-05-31 | 2024-03-31 | 2025-03-01 | 2025-03-01 | 0 | 118946211 | 118946211 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70829 | P9008285 | Eastern Cape | SAM XHALLIE SENIOR PRIMARY SCHOOL | 200600727 | Inxuba Yethemba | Construction 76% - 99% | Active - Contracted | 2018-02-09 | 2019-05-31 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 3621770 | 3621770 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70833 | P0004097 | Eastern Cape | NQABISILE HIGH SCHOOL | 200300832 | Amahlathi | Design | Active - Not Contracted | 2017-10-02 |  | 2026-03-31 |  |  | 6556025 | 59600231 | 66156256 | Education Infrastructure Grant | Upgrading and Additions
|  | 70850 | P9006476 | Eastern Cape | MPUTEKANE PRIMARY SCHOOL | 200500770 | Matatiele | Construction 76% - 99% | Active - Contracted | 2018-02-07 | 2018-06-27 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 1909018 | 6028395 | 7937413 | Education Infrastructure Grant | Upgrading and Additions
|  | 70860 | P9005227 | Eastern Cape | HUKU SENIOR SECONDARY SCHOOL | 200500313 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2014-04-30 | 2014-09-02 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 637144 | 637144 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70861 | P0000073 | Eastern Cape | J A NCACA PUBLIC PRIMARY SCHOOL | 200600303 | Inxuba Yethemba | Construction 51% - 75% | Active - Contracted | 2015-03-20 | 2017-06-29 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 22422246 | 22422246 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 70866 | P9005898 | Eastern Cape | KWABO JUNIOR SECONDARY SCHOOL | 200600355 | Senqu | Final Completion | Active - Contracted | 2008-07-01 | 2008-11-18 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70869 | P9004563 | Eastern Cape | MACLEAR PUBLIC SCHOOL | 200401317 | Elundini | Final Completion | Active - Contracted | 2015-02-05 | 2015-02-06 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 0 | 9532071 | 9532071 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 70872 | P0003550. | Eastern Cape | LUFAFA PRIMARY SCHOOL | 200500451 | Umzimvubu | Construction 51% - 75% | Active - Contracted | 2016-04-01 | 2016-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 194000 | 1200744 | 1394744 | Education Infrastructure Grant | Maintenance and Repairs
|  | 70989 | NEW HUHUDI | North West | HUHUDI EXT 25 | NEW HUHUDI | Naledi | Construction 51% - 75% | Active - Contracted | 2017-08-01 | 2026-01-10 | 2026-03-15 | 2026-02-09 | 2026-03-31 | 14537345 | 80763027 | 95300372 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 71003 | WAGPOS | North West | WAGPOS TECHNICAL | WAGPOS | Local Municipality of Madibeng | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2021-12-10 | 2026-03-01 | 2023-04-30 | 2026-03-31 | 0 | 6000000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 71005 | NIET | North West | NIETVERDIENT PRIMARY | NIET | Ramotshere Moiloa | Site Handed - Over to Contractor | Active - Contracted | 2017-04-01 | 2017-04-12 | 2025-03-31 | 2019-09-30 | 2025-03-31 | 0 | 31676000 | 31676000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 71016 | THABO S | North West | THABO SEMPEMPE | THABOS | Ditsobotla | Project Initiation | Active - Not Contracted | 2017-04-01 |  | 2025-03-28 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 71260 | P9007261 | Eastern Cape | VUKAYIBAMBE SENIOR SECONDARY SCHOOL | 200501278 | Mbizana | Construction 76% - 99% | Active - Contracted | 2017-03-21 | 2022-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 4960703 | 17445789 | 22406492 | Education Infrastructure Grant | Maintenance and Repairs
|  | 71270 | P9006424_ | Eastern Cape | MASIPHATHISANE SECONDARY SCHOOL | 200100498 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2016-01-28 | 2017-08-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 14163516 | 14163516 | Education Infrastructure Grant | Upgrading and Additions
|  | 71303 | P9007201 | Eastern Cape | SITOZA SENIOR SECONDARY SCHOOL | 200401009 | Engcobo | Construction 76% - 99% | Active - Contracted | 2017-11-01 | 2017-12-31 | 2026-03-31 | 2025-05-10 | 2025-05-10 | 0 | 29393433 | 29393433 | Education Infrastructure Grant | Upgrading and Additions
|  | 71328 | P9008562_ | Eastern Cape | MOSA SIBI SENIOR SECONDARY SCHOOL | 200500741 | Matatiele | Construction 51% - 75% | Active - Contracted | 2016-09-13 | 2019-05-23 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6552738 | 6552738 | Education Infrastructure Grant | Maintenance and Repairs
|  | 72051 | EDDP184/341 | Limpopo | Shorwane Secondary School | 925361276 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2016-04-01 | 2017-06-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 2547800 | 10191200 | 12739000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96403 | W/500147556/WS | KwaZulu-Natal | GCINIMFUNDO SECONDARY SCHOOL | 500147556 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2017-04-07 | 2022-03-01 | 2023-09-30 | 2024-09-30 | 2025-09-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96406 | W/500201539/WS | KwaZulu-Natal | MATHAMO PRIMARY SCHOOL | 500201539 | Inkosi Langalibalele | Tender | Active - Not Contracted | 2017-01-01 |  | 2023-06-30 |  |  | 856936 | 3903820 | 4760756 | Education Infrastructure Grant | Upgrading and Additions
|  | 96407 | W/500222370/WS | KwaZulu-Natal | MZIWENKOSI PRIMARY SCHOOL | 500222370 | Umvoti | On Hold | Active - Contracted | 2017-01-01 |  | 2023-01-01 |  |  | 12000 | 55000 | 67000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96408 | W/500446627/WS. | KwaZulu-Natal | NTABENDE PRIMARY SCHOOL | 500446627 | The Msunduzi | Construction 1% - 25% | Active - Contracted | 2017-01-01 | 2017-12-01 | 2023-01-01 | 2022-03-02 | 2022-05-31 | 684604 | 3118753 | 3803357 | Education Infrastructure Grant | Upgrading and Additions
|  | 96409 | W500337070/WS | KwaZulu-Natal | MGEZENGWANE PRIMARY SCHOOL | 500337070 | Ndwedwe | Feasibility | Active - Contracted | 2016-01-01 |  | 2023-01-01 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96410 | W500293188/WS | KwaZulu-Natal | VUKILE HIGH SCHOOL | 500293188 | Maphumulo | Construction 51% - 75% | Active - Contracted | 2016-06-14 | 2017-07-01 | 2023-01-01 | 2023-03-01 | 2023-04-30 | 1 | 1 | 2 | Education Infrastructure Grant | Upgrading and Additions
|  | 96411 | W/500279979/WS | KwaZulu-Natal | THAFAMASI PRIMARY SCHOOL | 500279979 | Ndwedwe | Construction 76% - 99% | Active - Contracted | 2016-01-01 | 2017-07-20 | 2023-06-30 | 2023-07-15 | 2023-11-30 | 829580 | 3779196 | 4608776 | Education Infrastructure Grant | Upgrading and Additions
|  | 96412 | W/500262293/WS | KwaZulu-Natal | SHONKWENI JUNIOR PRIMARY SCHOOL | 500262293 | Umdoni | Design | Active - Not Contracted | 2016-06-06 | 2017-12-01 | 2023-01-01 | 2018-03-02 | 2019-04-30 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96413 | W/500238946/WS | KwaZulu-Natal | NTABASKOP PRIMARY SCHOOL | 500238946 | Ndwedwe | On Hold | Active - Contracted | 2016-06-06 | 2022-03-10 | 2022-09-30 | 2022-09-30 | 2022-09-30 | 1 | 1 | 2 | Education Infrastructure Grant | Upgrading and Additions
|  | 96414 | W/500200503/WS | KwaZulu-Natal | MASHIYAMAHLE SECONDARY SCHOOL | 500200503 | Ndwedwe | On Hold | Active - Contracted | 2016-01-01 | 2017-12-01 | 2023-01-01 | 2023-12-12 | 2023-04-30 | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96416 | IDT/ELECTRIFICATION/ALL DISTRICTS | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2016-06-22 |  | 2024-03-20 |  |  | 3000000 | 23000000 | 26000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96598 | GDE00017 | Gauteng | BIRCH ACRES PRIMARY SCHOOL | N/A | City of Ekurhuleni | Design | Approved | 2016-10-24 |  | 2026-02-13 |  |  | 5288600 | 28263400 | 33552000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 96618 | GDE00011 | Gauteng | Bafiti Special School | Bafiti Special School | City of Johannesburg | Project Initiation | Approved | 2018-04-01 |  | 2026-04-16 |  |  | 12800000 | 67200000 | 80000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96627 | WE/001068/2018 | Western Cape | Manenberg SOS | 56723?? | City of Cape Town | Construction 1% - 25% | Active - Contracted | 2018-04-30 | 2022-07-05 | 2025-03-31 | 2024-06-14 | 2024-06-14 | 19053000 | 97000000 | 116053000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 96630 | WE/000592/2016 | Western Cape | Napakade PS | 132470805 | Swartland | Construction 1% - 25% | Active - Contracted | 2018-03-30 | 2022-06-30 | 2025-03-31 | 2023-08-31 | 2023-08-31 | 7413000 | 38000000 | 45413000 | Education Infrastructure Grant | Upgrading and Additions
|  | 96651 | GDE00306 | Gauteng | REV. A. MAPHETO PRIMARY SCHOOLRev. A Mapheto Primary School | 700400800 | City of Ekurhuleni | Terminated | Active - Not Contracted | 2018-03-02 | 2020-09-30 | 2024-06-29 | 2024-09-29 | 2025-10-17 | 4000000 | 21000000 | 25000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 102889 | GDE00069 | Gauteng | EMMANGWENI PRIMARY SCHOOL | 700260729 | City of Ekurhuleni | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2025-05-09 |  |  | 490250 | 2853750 | 3344000 | Education Infrastructure Grant | Upgrading and Additions
|  | 103611 | ONTLAMETSE PHAL | North West | ONTLAMETSE PHALATSE PRIMARY | OTLAMETSE PHAL | Local Municipality of Madibeng | Project Initiation | Active - Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 0 | 30000000 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 103916 | DB/500263995/SDS | KwaZulu-Natal | SIDIYA PRIMARY SCHOOL | 500263995 | eThekwini | Final Completion | Approved | 2016-01-01 | 2018-01-12 | 2023-06-05 | 2023-06-04 | 2025-06-04 | 776562 | 3537670 | 4314232 | Education Infrastructure Grant | Maintenance and Repairs
|  | 103978 | DB/500276982/SDS | KwaZulu-Natal | BAHLEBONKE PRIMARY SCHOOL | 500276982 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2018-04-05 | 2023-10-05 | 2018-10-05 | 2027-10-05 | 452177 | 2059918 | 2512095 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 103989 | DB/500109113/SDS | KwaZulu-Natal | BHEKULWANDLE PRIMARY SCHOOL | 500109113 | eThekwini | Final Completion | Approved | 2017-01-01 | 2018-01-15 | 2025-07-10 | 2022-07-10 | 2025-07-10 | 491688 | 2239910 | 2731598 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 103993 | DB/500113960/SDS | KwaZulu-Natal | BUYANI PRIMARY SCHOOL | 500113960 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-12-11 | 2023-03-31 | 2022-10-10 | 2027-03-25 | 596995 | 2719645 | 3316640 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104010 | DB/uTng.New12/003/SDS | KwaZulu-Natal | EHAWINI SECONDARY SCHOOL | uTng.New12/003 | Nkandla | Design | Active - Contracted | 2016-01-01 |  | 2024-03-20 |  |  | 300000 | 1500000 | 1800000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104016 | DB/500143264/SDS | KwaZulu-Natal | EZIGQIZWENI HIGH SCHOOL | 500143264 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2017-01-01 | 2019-02-01 | 2023-12-01 | 2023-01-31 | 2027-03-30 | 798427 | 3637279 | 4435706 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104028 | DB/500150886/SDS | KwaZulu-Natal | GOLOKODO PRIMARY SCHOOL | 500150886 | eThekwini | Final Completion | Approved | 2016-01-01 | 2018-01-12 | 2023-06-18 | 2023-06-18 | 2025-03-30 | 414290 | 2462710 | 2877000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104069 | DB/500220224/SDS. | KwaZulu-Natal | INQABAYAMAZIMELA (MTHUNZINI) HIGH | 500220224 | Nkandla | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104075 | DB/500167647/SDS | KwaZulu-Natal | ISIBUKOSEZWE HIGH SCHOOL | 500167647 | eThekwini | Final Completion | Approved | 2016-01-01 | 2018-01-12 | 2023-08-29 | 2023-05-29 | 2025-05-29 | 744518 | 3391694 | 4136212 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104081 | DB/500168128/SDS | KwaZulu-Natal | ISIKHUMBUZO PRIMARY SCHOOL | 500168128 | eThekwini | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 275000 | 1254000 | 1529000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104091 | DB/500182077/SDS | KwaZulu-Natal | KWANDABENZINHLE PRIMARY SCHOOL | 500182077 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-01-16 | 2023-07-16 | 2023-05-05 | 2025-05-29 | 522017 | 5610983 | 6133000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104100 | DB/500185074/SDS | KwaZulu-Natal | LAMONTVILLE HIGH SCHOOL | 500185074 | eThekwini | Final Completion | Approved | 2016-01-01 | 2018-01-12 | 2023-09-14 | 2023-09-19 | 2025-09-19 | 1426796 | 6499850 | 7926646 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104102 | DB/500187146/SDS | KwaZulu-Natal | LITTLE FLOWER PRIMARY SCHOOL | 500187146 | uMlalazi | Design | Active - Not Contracted | 2016-01-01 |  | 2024-01-12 |  |  | 1 | 1 | 2 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 104109 | DB/500189736/SDS | KwaZulu-Natal | M L SULTAN ST. MARYS PRIMARY SCHOOL | 500189736 | eThekwini | Design | Active - Not Contracted | 2016-01-01 | 2017-02-12 | 2023-12-01 | 2018-03-01 | 2024-12-01 | 1 | 1 | 2 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 104116 | DB/500319606/SDS | KwaZulu-Natal | MADLANKALA PRIMARY SCHOOL | 500319606 | uMhlathuze | Design | Active - Not Contracted | 2016-01-01 |  | 2027-12-01 |  |  | 200000 | 1700000 | 1900000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 104121 | DB/500201169/SDS | KwaZulu-Natal | MASON LINCOLN PRIMARY SCHOOL | 500201169 | eThekwini | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-04-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 502635 | 5131365 | 5634000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104128 | DB/500201761/SDS | KwaZulu-Natal | MATHOLAMNYAMA SECONDARY SCHOOL | 500201761 | Nkandla | Design | Proposed | 2016-01-01 |  | 2024-12-01 |  |  | 500000 | 2499000 | 2999000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104131 | DB/500202205/SDS | KwaZulu-Natal | MATSHANGULE PRIMARY SCHOOL | 500202205 | uMhlathuze | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 500000 | 1500000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 104136 | DB/500307174/SDS | KwaZulu-Natal | MNTOKHONA PRIMARY SCHOOL | 500307174 | uMhlathuze | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 500000 | 2800000 | 3300000 | Equitable Share | Maintenance and Repairs
|  | 104137 | DB/500213786/SDS | KwaZulu-Natal | MUNTONOKUDLA SECONDARY SCHOOL | 500213786 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-12-11 | 2023-06-10 | 2023-06-10 | 2023-08-28 | 1109754 | 5055545 | 6165299 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104141 | DB/500341103/SDS | KwaZulu-Natal | MZIMELA PRIMARY SCHOOL | 500341103 | Endumeni | Design | Active - Not Contracted | 2016-01-01 |  | 2023-12-01 |  |  | 747000 | 3404000 | 4151000 | Equitable Share | Maintenance and Repairs
|  | 104145 | DB/500228697/SDS | KwaZulu-Natal | NGQAMZANA PRIMARY SCHOOL | 500228697 | uMlalazi | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 500000 | 2500000 | 3000000 | Equitable Share | Maintenance and Repairs
|  | 104150 | DB/500235616/SDS | KwaZulu-Natal | NONGWELEZA HIGH SCHOOL | 500235616 | uMhlathuze | Design | Active - Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 300000 | 1311000 | 1611000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104154 | DB/500242276/SDS. | KwaZulu-Natal | OBANJENI PRIMARY SCHOOL | 500242276 | uMlalazi | Design | Active - Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 300000 | 700000 | 1000000 | Equitable Share | Maintenance and Repairs
|  | 104158 | DB/500253006/SDS | KwaZulu-Natal | QHUBANDABA PRIMARY SCHOOL | 500253006 | Ndwedwe | Design | Active - Not Contracted | 2016-01-01 |  | 2024-02-26 |  |  | 2186474 | 8225308 | 10411782 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104164 | DB/500257150/SDS | KwaZulu-Natal | SABOKWE PRIMARY SCHOOL | 500257150 | uMhlathuze | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 300000 | 700000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 104165 | DB/500269434/SDS | KwaZulu-Natal | SIYABONGA HIGH SCHOOL | 500269434 | eThekwini | Design | Active - Not Contracted | 2016-01-01 |  | 2024-12-01 |  |  | 513142 | 2337648 | 2850790 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104167 | DB/500273208/SDS | KwaZulu-Natal | SOMOPHO PRIMARY SCHOOL | 500273208 | uMhlathuze | Design | Active - Contracted | 2016-01-01 |  | 2024-12-02 |  |  | 300000 | 700000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104169 | DB/500273282/SDS | KwaZulu-Natal | SOMPUKWANE SECONDARY SCHOOL | 500273282 | eThekwini | Final Completion | Approved | 2020-01-05 | 2020-06-21 | 2022-08-05 | 2022-10-08 | 2022-10-06 | 1630585 | 7428222 | 9058807 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104171 | DB/500293114/SDS | KwaZulu-Natal | VUKAPHI PRIMARY SCHOOL | 500293114 | Umdoni | Practical Completion (100%) | Active - Contracted | 2019-01-01 | 2020-04-03 | 2022-07-04 | 2022-07-11 | 2027-09-09 | 712117 | 3244087 | 3956204 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104174 | DB/500296851/SDS | KwaZulu-Natal | WOOD AND RAW PRIMARY SCHOOL | 500296851 | uMhlathuze | Project Initiation | Active - Not Contracted | 2016-01-01 |  | 2027-12-03 |  |  | 1262035 | 5749270 | 7011305 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104179 | DB/500297036/SDS | KwaZulu-Natal | WOODHURST SECONDARY SCHOOL | 500297036 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-08-19 | 2020-02-11 | 2022-07-07 | 2022-08-11 | 2027-08-25 | 2581738 | 11761253 | 14342991 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104187 | DB/500320346/SDS | KwaZulu-Natal | MANDAWE PRIMARY SCHOOL | 500320346 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2019-01-16 | 2025-07-16 | 2023-07-16 | 2023-07-16 | 786455 | 3582741 | 4369196 | Education Infrastructure Grant | Maintenance and Repairs
|  | 104191 | DB/500166833/SDS | KwaZulu-Natal | INYATHI PRIMARY SCHOOL | 500166833 | uMlalazi | Practical Completion (100%) | Approved | 2015-01-01 | 2017-01-31 | 2023-12-01 | 2019-01-31 | 2025-05-31 | 730219 | 3326555 | 4056774 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104194 | w/500334295/ws | KwaZulu-Natal | MBELEBELE PRIMARY SCHOOL - ERF 3232 EKUVUKENI | 500334295 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2018-02-01 | 2023-03-30 | 2022-04-01 | 2023-04-26 | 850000 | 1300000 | 2150000 | Education Infrastructure Grant | Upgrading and Additions
|  | 104195 | DB/500138602/SDS | KwaZulu-Natal | ENTUMENI PRIMARY SCHOOL | 500138602 | uMlalazi | Design | Active - Not Contracted | 2016-01-01 |  | 2027-03-30 |  |  | 970259 | 4420068 | 5390327 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104196 | DB/500138232/SDS | KwaZulu-Natal | ENSINGWENI PRIMARY SCHOOL | 500138232 | uMlalazi | Design | Active - Not Contracted | 2016-01-01 |  | 2027-03-30 |  |  | 882517 | 4020355 | 4902872 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 104202 | DB/500190550/SDS | KwaZulu-Natal | MACEKANE PRIMARY SCHOOL | 500190550 | uMhlathuze | Design | Active - Not Contracted | 2016-01-01 | 2017-02-12 | 2023-12-01 | 2018-03-01 | 2024-12-01 | 500000 | 1500000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 104290 | W/500303955/WS | KwaZulu-Natal | HLABANE SECONDARY SCHOOL - LOSKOP | 500303955 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2017-03-01 | 2022-03-30 | 2023-06-30 | 2024-03-30 | 2025-03-30 | 674634 | 3073333 | 3747967 | Education Infrastructure Grant | Upgrading and Additions
|  | 104302 | W/500179154/UA. | KwaZulu-Natal | KWADINDA PRIMARY SCHOOL - GREYTOWN | 500179154 | Umvoti | Design | Active - Not Contracted | 2017-02-20 |  | 2024-03-30 |  |  | 200000 | 200000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 105313 | P9009570 | Eastern Cape | BETHANIA SENIOR SECONDARY SCHOOL | 200500027 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 284081 | 1841169 | 2125250 | Education Infrastructure Grant | Maintenance and Repairs
|  | 105341 | P9006619 | Eastern Cape | CILO SENIOR PRIMARY SCHOOL | 200300048 | Mnquma | Design | Approved | 2016-04-01 |  | 2024-03-31 |  |  | 2017717 | 12670545 | 14688262 | Education Infrastructure Grant | Upgrading and Additions
|  | 105435 | P9006099 | Eastern Cape | DOCUMENT MANAGEMENT CENTRE (Hanker) | 200999925 | Amahlathi | Construction 1% - 25% | Active - Not Contracted | 2015-04-01 | 2015-06-01 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 13723390 | 106983093 | 120706483 | Education Infrastructure Grant | Upgrading and Additions
|  | 105491 | GDE00003 | Gauteng | Adelaide Tambo School | 700133652 | City of Johannesburg | Project Initiation | Approved | 2019-09-01 |  | 2025-08-12 |  |  | 1002000 | 5262000 | 6264000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 105565 | P9006045 | Eastern Cape | SIDINANE SENIOR SECONDARY SCHOOL | 200501098 | Elundini | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 105580 | P9008610_ | Eastern Cape | XUGXWALA PRIMARY SCHOOL | 200401155 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2017-06-01 | 2023-03-31 | 2025-03-31 | 2025-03-31 | 508914 | 2993716 | 3502630 | Education Infrastructure Grant | Maintenance and Repairs
|  | 105786 | 09/18/19 | Free State | STIPEND EPWP WORKERS | 09/18/19 | Mangaung | Not Applicable | Active - Contracted | 2018-04-01 | 2018-04-30 | 2023-03-31 | 2023-03-31 | 2024-03-31 | 5800000 | 0 | 5800000 | Expanded Public Works Programme Intergrated Grant for Provinces | Non-Infrastructure
|  | 105789 | P9008407 | Eastern Cape | HOLY CROSS SENIOR SECONDARY SCHOOL | 200400272 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2017-03-23 | 2017-05-23 | 2023-06-30 | 2023-05-31 | 2023-05-31 | 0 | 7791273 | 7791273 | Education Infrastructure Grant | Maintenance and Repairs
|  | 105941 | P0004530 | Eastern Cape | LEADERSHIP INSTITUTE EAST LONDON (Mandla Makapula) | 200999925 | Buffalo City | Pre - Feasibility | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 0 | 15825000 | 15825000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 106355 | P9008412 | Eastern Cape | JOSI MARELA SENIOR SECONDARY SCHOOL | 200200297 | Amahlathi | Practical Completion (100%) | Active - Contracted | 2017-03-13 | 2017-05-30 | 2025-05-13 | 2022-05-13 | 2022-05-13 | 0 | 5994306 | 5994306 | Education Infrastructure Grant | Maintenance and Repairs
|  | 106463 | P9008411 | Eastern Cape | KHWEZILESIZWE PRIMARY SCHOOL | 200100385 | Raymond Mhlaba | Construction 76% - 99% | Active - Contracted | 2017-03-13 | 2017-06-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2377269 | 11759743 | 14137012 | Education Infrastructure Grant | Maintenance and Repairs
|  | 106498 | P9006483 | Eastern Cape | kwaMATAMBO SENIOR PRIMARY SCHOOL | 200500373 | Ingquza Hill | Tender | Active - Contracted | 2019-02-04 |  | 2025-03-31 |  |  | 3146456 | 14447323 | 17593779 | Education Infrastructure Grant | Upgrading and Additions
|  | 106650 | P0002093 | Eastern Cape | MPAKO JUNIOR SECONDARY SCHOOL | 200400636 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2018-10-01 | 2019-05-22 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 276644 | 1844294 | 2120938 | Education Infrastructure Grant | Maintenance and Repairs
|  | 106691 | 13/18/19 | Free State | MOBILE ABLUTION BLOCKS 13/18/19 | 13/18/19 | Mangaung | Construction 1% - 25% | Active - Contracted | 2018-04-01 | 2018-04-30 | 2025-04-01 | 2019-03-31 | 2022-03-31 | 0 | 22835000 | 22835000 | Education Infrastructure Grant | Upgrading and Additions
|  | 106787 | P9005932 | Eastern Cape | MALUTI SENIOR SECONDARY SCHOOL | 200500551 | Umzimvubu | Construction 51% - 75% | Approved | 2014-05-12 | 2018-01-30 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 7530467 | 54174004 | 61704471 | Education Infrastructure Grant | Upgrading and Additions
|  | 106817 | P0002080 | Eastern Cape | ISILINDINI JUNIOR SECONDARY SCHOOL | 200500324 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-11-05 | 2019-04-10 | 2023-03-31 | 2021-11-17 | 2020-06-30 | 243984 | 2012816 | 2256800 | Education Infrastructure Grant | Maintenance and Repairs
|  | 106822 | 16/18/19 | Free State | Unity Primary School | Mobiles | Mangaung | Other - Packaged Ongoing Project | Active - Contracted | 2017-04-01 | 2019-02-18 | 2025-04-01 | 2024-10-25 | 2024-01-31 | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 106838 | 14/18/19 | Free State | lepanya primary school | PITTOILET | Maluti a Phofung | Other - Packaged Ongoing Project | Active - Contracted | 2018-04-01 | 2019-02-18 | 2023-03-31 | 2023-01-31 | 2023-03-31 | 0 | 60000000 | 60000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 107863 | P9010205 | Eastern Cape | OPERATIONS & MAINTENANCE (AW) | 200999925 | Amahlathi | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 62000000 | 62000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 115186 | LE19DPW00090 | Limpopo | Chameti Secondary School | 916410072 | Greater Giyani | Design | Active - Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8227061 | 32908243 | 41135304 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115193 | LE19DPW00072 | Limpopo | DIKGALAOPENG Secondary | 924650023 | Elias Motsoaledi | Design | Active - Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 7128361 | 28513442 | 35641803 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115201 | LE19DPW00019 | Limpopo | CHITA KEKANA Secondary | 921230023 | Lepele-Nkumpi | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 9825806 | 39303222 | 49129028 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115209 | LE19DPW00037 | Limpopo | DIKOLOI SECONDARY | 920210128 | Blouberg | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 5554391 | 22217556 | 27771947 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115211 | LE19DPW00001 | Limpopo | Diphuti Primary | 926540522 | Maruleng | Tender | Active - Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8104593 | 32418372 | 40522965 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115213 | LE19DPW00073 | Limpopo | George Clifford Mosely Primary | 924640217 | Makhuduthamaga | Design | Active - Contracted | 2018-04-01 |  | 2023-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115214 | LE19DPW00038 | Limpopo | GIVEN MANGOLO PRIMARY | 921142300 | Mogalakwena | Design | Active - Not Contracted | 2018-04-01 |  | 2024-06-30 |  |  | 1802000 | 7208000 | 9010000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115218 | LE19DPW00091 | Limpopo | Hanyanyani Primary | 921410195 | Collins Chabane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115220 | LE19DPW00092 | Limpopo | Hawuka Senior Secondary | 902971823 | Greater Giyani | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2780000 | 11120000 | 13900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115225 | LE19DPW00039 | Limpopo | Hututu Secondary | 924651910 | Ephraim Mogale | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8824550 | 35298201 | 44122751 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115227 | LE19DPW00002 | Limpopo | Joel Sibasa Secondary | 922220286 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 6000000 | 7200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115230 | LE19DPW00054 | Limpopo | kgalushi High School | 922010258 | Blouberg | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8800000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115233 | LE19DPW00003 | Limpopo | Kgarahara Secondary | 919340678 | Molemole | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 8133974 | 15003551 | 23137525 | Education Infrastructure Grant | Upgrading and Additions
|  | 115234 | LE19DPW00040 | Limpopo | KGOMOTLOU PRIMARY | 996606809 | Ephraim Mogale | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115235 | LE19DPW00108 | Limpopo | Khekhutini Primary | 918510123 | Greater Letaba | Tender | Active - Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115236 | LE19DPW00093 | Limpopo | Kheodi Secondary | 918520108 | Greater Letaba | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 4000000 | 16000000 | 20000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115238 | LE19DPW00075 | Limpopo | Kopa Secondary School | 924650184 | Elias Motsoaledi | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 15302774 | 61211095 | 76513869 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115239 | LE19DPW00076 | Limpopo | KOPANONG PRIMARY | 924640491 | Makhuduthamaga | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 13942750 | 55771000 | 69713750 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115242 | LE19DPW00004 | Limpopo | Lepono Primary | 926540102 | Maruleng | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1846000 | 7384000 | 9230000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115243 | LE19DPW00005 | Limpopo | Letheba Secondary | 919340685 | Molemole | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-05-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115244 | LE19DPW00006 | Limpopo | Maahlamele Secondary | 926540119 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115245 | LE19DPW00020 | Limpopo | MADITSI SECONDARY | 923260475 | Lepele-Nkumpi | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 650000 | 2600000 | 3250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115246 | LE19DPW00077 | Limpopo | Magukubyane Secondary | 924650672 | Elias Motsoaledi | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115247 | LE19DPW00007 | Limpopo | Mahlabezulu Primary | 915530662 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115257 | LE19DPW00078 | Limpopo | Mahlakanaseleng Primary | 924640842 | Makhuduthamaga | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115259 | LE19DPW00109 | Limpopo | Makgope Primary | 918510293 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 8000000 | 9200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115263 | LE19DPW00110 | Limpopo | Makgopele Secondary | 918521309 | Greater Giyani | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 4333683 | 17334730 | 21668413 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115264 | LE19DPW00021 | Limpopo | Makhwese Secondary | 925620480 | Greater Tubatse/Fetakgomo | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 4720801 | 18883203 | 23604004 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115266 | LE19DPW00041 | Limpopo | JAMELA PRIMARY SCHOOL | 918520450 | Greater Letaba | Design | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115268 | LE19DPW00042 | Limpopo | MAMANENG PRIMARY | 996606829 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115293 | TBD - ABLUTION BLOCK | Northern Cape | VICTORIA-WES GEKOMBINEERDE SKOOL | 300024304 | Ubuntu | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 0 | 5171078 | 5171078 | Education Infrastructure Grant | Upgrading and Additions
|  | 115297 | ISJX025/2019 | Northern Cape | MAGOJANENG (NEW) | NEW | Joe Morolong | Design | Approved | 2019-03-29 |  | 2025-03-31 |  |  | 1676838 | 120200166 | 121877004 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 115298 | LE19DPW00055 | Limpopo | Mamoduane Secondary | 920210175 | Blouberg | Design | Active - Not Contracted | 2018-04-01 |  | 2025-05-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115301 | LE19DPW00057 | Limpopo | MANKOPANE PRIMARY | 918610360 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2023-03-31 |  |  | 2060000 | 8240000 | 10300000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115302 | ISJX029/2019 | Northern Cape | NEW SCHOOL - SECONDARY ENGLISH MEDIUM KIMBERLEY | NEW | Sol Plaatjie | Design | Approved | 2019-03-30 |  | 2025-03-28 |  |  | 19751102 | 60000000 | 79751102 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 115303 | LE19DPW00111 | Limpopo | Manokwe Secondary | 918510408 | Greater Letaba | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115304 | LE19DPW00112 | Limpopo | Manorvlei Primary | 901530716 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 4000000 | 16000000 | 20000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115305 | LE19DPW00022 | Limpopo | Maragane Primary | 921230279 | Polokwane | Design | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115306 | LE19DPW00113 | Limpopo | MARIPHU PRIMARY | 922220668 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115307 | LE19DPW00114 | Limpopo | Mark Shope Secondary | 915530242 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115308 | LE19DPW00008 | Limpopo | Masedi Primary | 919340388 | Molemole | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115311 | ST055/2022-23 | Northern Cape | TT LEKALAKE PRIMARY SCHOOL | 300102050 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 1901889 | 1901889 | Education Infrastructure Grant | Maintenance and Repairs
|  | 115312 | LE19DPW00043 | Limpopo | Mashile Primary | 924141401 | Makhuduthamaga | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6560000 | 7760000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 115313 | LE19DPW00044 | Limpopo | MASHOBELA HIGH | 92142027 | Mogalakwena | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115315 | LE19DPW00009 | Limpopo | MASIKHWA PRIMARY | 930350231 | Thulamela | Tender | Active - Not Contracted | 2018-04-01 |  | 2024-04-30 |  |  | 7176668 | 9685182 | 16861850 | Education Infrastructure Grant | Upgrading and Additions
|  | 115316 | LE19DPW00115 | Limpopo | MATIMU SECONDARY SCHOOL | 915540218 | Greater Tzaneen | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 7831509 | 31326037 | 39157546 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115318 | LE19DPW00058 | Limpopo | Matleu Primary | 925610599 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 6000000 | 7200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115319 | LE19DPW00046 | Limpopo | Matsibe Secondary | 921120935 | Mogalakwena | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 5547681 | 22190726 | 27738407 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115320 | LE19DPW00059 | Limpopo | Matsuokwane Secondary | 920210951 | Polokwane | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6343514 | 25374055 | 31717569 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115325 | LE19DPW00060 | Limpopo | MATUMA PRIMARY | 922220781 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 115330 | ST330/2021 | Northern Cape | TSOE PRIMARY SCHOOL | 300104019 | Joe Morolong | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 6000000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 115335 | UMSO - BBB | Northern Cape | UMSO HIGH SCHOOL | 300023403 | Umsobomvu | Feasibility | Proposed | 2020-04-30 |  | 2024-03-31 |  |  | 0 | 9100703 | 9100703 | Education Infrastructure Grant | Upgrading and Additions
|  | 115353 | ST031/2022-23 | Northern Cape | HOERSKOOL CALTON VAN HEERDEN | 300043401 | Dawid Kruiper | Construction 51% - 75% | Approved | 2022-05-05 |  | 2022-08-04 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 117364 | ELECTRICITY1 | Northern Cape | ITSHOKENG PRIMARY SCHOOL | 300100575 | Joe Morolong | Feasibility | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 198840 | 198840 | Education Infrastructure Grant | Upgrading and Additions
|  | 117369 | LE19DPW00094 | Limpopo | Mayeke Primary | 911360269 | Collins Chabane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 9260592 | 37042369 | 46302961 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117371 | LE19DPW00116 | Limpopo | Mbangwa Primary | 930351074 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117372 | LE19DPW00117 | Limpopo | Mbetana Primary | 915531337 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 4000000 | 16000000 | 20000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117374 | LE19DPW00079 | Limpopo | MMAMARAMA SECONDARY | 922220866 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 8000000 | 9200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117375 | LE19DPW00023 | Limpopo | Mmaphuti Manamela Secondary | 991104202 | Polokwane | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 9216574 | 36866295 | 46082869 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117376 | LE19DPW00061 | Limpopo | Modimolle 2 Primary | 906610780 | Modimolle/Mookgophong | Site Handed - Over to Contractor | Active - Contracted | 2018-04-01 | 2020-08-20 | 2025-03-31 | 2022-09-01 | 2023-03-31 | 1200000 | 4800000 | 6000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117378 | LE19DPW00024 | Limpopo | David Scara Kutumela Primary | 991104204 | Greater Tubatse/Fetakgomo | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 10954800 | 43819200 | 54774000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117380 | LE19DPW00062 | Limpopo | Moisele Primary | 925620756 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117389 | LE19DPW00025 | Limpopo | MOKHARI COMBINED PRIMARY | 906121051 | Modimolle/Mookgophong | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 7794388 | 31177551 | 38971939 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117391 | LE19DPW00081 | Limpopo | Mokone A Mabula Secondary | 924651927 | Ephraim Mogale | Design | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1400000 | 6000000 | 7400000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117392 | LE19DPW00047 | Limpopo | MOLESHATLOU SECONDARY | 925660853 | Makhuduthamaga | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6848872 | 27395490 | 34244362 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 117394 | LE19DPW00063 | Limpopo | Mookotsi Primary | 925620800 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Not Contracted | 2018-04-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 117395 | LE19DPW00026 | Limpopo | Moosrivier Primary | 996606522 | Ephraim Mogale | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2020000 | 8080000 | 10100000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118315 | LE19DPW00064 | Limpopo | MORETHUSHE PRIMARY | 925620824 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 5416000 | 6616000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118320 | BBB011/2018 | Northern Cape | EUREKA INTERMEDIERE SKOOL | 300023301 | Sol Plaatjie | On Hold | Active - Not Contracted | 2018-05-17 | 2018-08-15 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 16122368 | 60000000 | 76122368 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 118331 | P0001678 | Eastern Cape | HECTOR PETERSEN HIGH SCHOOL | 200200240 | Buffalo City | Project Initiation | Active - Not Contracted | 2015-03-20 |  | 2025-03-31 |  |  | 11489932 | 88888792 | 100378724 | Education Infrastructure Grant | Upgrading and Additions
|  | 118332 | P0001679 | Eastern Cape | MICHAUSDAL PRIMARY SCHOOL | 200600481 | Inxuba Yethemba | Feasibility | Proposed | 2015-03-20 |  | 2026-03-31 |  |  | 14809664 | 98731094 | 113540758 | Education Infrastructure Grant | Upgrading and Additions
|  | 118333 | P9005960 | Eastern Cape | LINGCOM PRIMARY SCHOOL | 200100457 | Dr Beyers Naude | Construction 26% - 50% | Active - Contracted | 2018-03-07 | 2018-05-20 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 3701127 | 79273598 | 82974725 | Education Infrastructure Grant | Upgrading and Additions
|  | 118334 | P0000319 | Eastern Cape | RUFANE DONKIN PRIMARY SCHOOL | 200100667 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2011-12-11 | 2019-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 51832672 | 51832672 | Education Infrastructure Grant | Upgrading and Additions
|  | 118340 | P9004958 | Eastern Cape | J F MATI SENIOR SECONDARY SCHOOL | 200200455 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2015-03-20 | 2017-03-19 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1843103 | 7254218 | 9097321 | Education Infrastructure Grant | Upgrading and Additions
|  | 118342 | P9006089_ | Eastern Cape | CLARKEBURY AGRICULTURAL SCHOOL (Durapi) | 200400084 | Engcobo | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2019-06-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 363525 | 363525 | Education Infrastructure Grant | Upgrading and Additions
|  | 118344 | P9006479 | Eastern Cape | MAQEBEVU PRIMARY SCHOOL | 200400499 | Port St Johns | Construction 1% - 25% | Active - Contracted | 2018-01-08 | 2018-08-30 | 2024-03-31 | 2025-03-31 | 2026-03-31 | 3674720 | 1441350516 | 1445025236 | Education Infrastructure Grant | Upgrading and Additions
|  | 118351 | OR-032789 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 300010101 | Sol Plaatjie | Construction 76% - 99% | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 118365 | DPWRT/SAN/276/20MP RAMAKGELETSAN--------- | Mpumalanga | Isu Elihle Primary School | 800006791 | Dr Pixley Ka Isaka Seme | Design | Active - Not Contracted | 2021-05-01 |  | 2024-10-01 |  |  | 923302 | 9233022 | 10156324 | Education Infrastructure Grant | Upgrading and Additions
|  | 118369 | PWRT/MAIN/031/19/MP | Mpumalanga | Jeugkrag Primary School | 800009233 | Lekwa | Practical Completion (100%) | Active - Contracted | 2018-05-15 | 2020-07-14 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 200000 | 2000000 | 2200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 118374 | OR-025891 | Northern Cape | ISAGONTLE PRIMARY SCHOOL | 300100555 | Ga-Segonyana | Construction 51% - 75% | Active - Contracted | 2019-04-01 | 2019-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 1435530 | 1435530 | Education Infrastructure Grant | Upgrading and Additions
|  | 118400 | P9011581 | Eastern Cape | EXTENDED PUBLIC WORKS PROGRAMME | 200999925 | Buffalo City | Construction 76% - 99% | Active - Contracted | 2014-08-12 | 2014-08-14 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 16000000 | 0 | 16000000 | Expanded Public Works Programme Intergrated Grant for Provinces | Non-Infrastructure
|  | 118402 | LE19DPW00027 | Limpopo | Morokadieta Primary | 925630531 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118403 | LE19DPW00010 | Limpopo | Mosehleng Primary(Merging with Lekiting Primary) | 922250737 | Blouberg | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118404 | LE19DPW00065 | Limpopo | Motsatsi Primary | 924643414 | Makhuduthamaga | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118405 | LE19DPW00066 | Limpopo | Mphaaneng Primary | 925610704 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118406 | LE19DPW00095 | Limpopo | Mphakani(Mphagane) Primary | 994402104 | Collins Chabane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8588069 | 34352278 | 42940347 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118409 | LE19DPW00011 | Limpopo | Napsadi Secondary | 926540294 | Maruleng | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 5715645 | 22862578 | 28578223 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118411 | LE19DPW00096 | Limpopo | Ndzhovela Primary | 916420468 | Greater Giyani | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118415 | LE19DPW00012 | Limpopo | Ngwanamakhutswe Secondary | 926540331 | Maruleng | Tender | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 7578576 | 11918004 | 19496580 | Education Infrastructure Grant | Upgrading and Additions
|  | 118416 | LE19DPW00097 | Limpopo | Nkatini Secondary | 911360863 | Collins Chabane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 5769124 | 23076498 | 28845622 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118422 | LE19DPW00067 | Limpopo | Nkgonyeletse Secondary | 924642329 | Makhuduthamaga | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8920248 | 35680993 | 44601241 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118424 | LE19DPW00068 | Limpopo | Nkota Secondary | 925621315 | Greater Tubatse/Fetakgomo | Design | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118427 | LE19DPW00069 | Limpopo | Lekoko Secondary School | 924640590 | Makhuduthamaga | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8073489 | 32293956 | 40367445 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118428 | LE19DPW00098 | Limpopo | Nyiko Primary | 916420512 | Greater Giyani | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1600000 | 6400000 | 8000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118429 | LE19DPW00099 | Limpopo | Nyumbani Secondary | 916420529 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 10160000 | 11360000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118430 | LE19DPW00028 | Limpopo | Pfumbada Primary | 928330015 | Thulamela | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 4724647 | 18898587 | 23623234 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118431 | LE19DPW00118 | Limpopo | OOGHOEK PRIMARY | 925630593 | Greater Tzaneen | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6027382 | 24109528 | 30136910 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118432 | LE19DPW00048 | Limpopo | Pezunga Secondary | 996606801 | Ephraim Mogale | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 6000000 | 7200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118433 | LE19DPW00082 | Limpopo | PHAPHAMANI PRIMARY | 924650535 | Elias Motsoaledi | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6894685 | 27578738 | 34473423 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118434 | LE19DPW00029 | Limpopo | Phasoane Primary | 923261041 | Lepele-Nkumpi | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1650000 | 6600000 | 8250000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118435 | LE19DPW00119 | Limpopo | Phetole Primary | 919340241 | Greater Letaba | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1720000 | 6880000 | 8600000 | Equitable Share | Upgrading and Additions
|  | 118436 | LE19DPW00030 | Limpopo | MATSOBANE PRIMARY | 923260772 | Elias Motsoaledi | Tender | Active - Not Contracted | 2018-12-01 |  | 2025-03-31 |  |  | 8771221 | 35084885 | 43856106 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118437 | LE19DPW00031 | Limpopo | Phutakwe Secondary | 925610223 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1760000 | 7040000 | 8800000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118438 | LE19DPW00083 | Limpopo | Photokela Primary | 920211404 | Blouberg | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 10777531 | 43110124 | 53887655 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118439 | LE19DPW00120 | Limpopo | Professor Muhlava Shiluvana Secondary | 915530273 | Greater Tzaneen | Site Handed - Over to Contractor | Active - Contracted | 2018-04-01 | 2020-08-20 | 2028-06-30 | 2028-06-30 | 2028-06-30 | 980000 | 3920000 | 4900000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118444 | LE19DPW00121 | Limpopo | R.S.B Mutsinoni Secondary | 918510842 | Greater Letaba | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118445 | LE19DPW00032 | Limpopo | Rakgoatha Primary | 921230573 | Lepele-Nkumpi | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 8163660 | 32654639 | 40818299 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118446 | LE19DPW00100 | Limpopo | Ramatimana Primary | 918520917 | Greater Letaba | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6708228 | 26832914 | 33541142 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118447 | LE19DPW00101 | Limpopo | Ramollo Primary | 918520924 | Greater Letaba | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118448 | LE19DPW00013 | Limpopo | Rasema Secondary | 919341152 | Molemole | Tender | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 8148573 | 15084655 | 23233228 | Education Infrastructure Grant | Upgrading and Additions
|  | 118449 | LE19DPW00070 | Limpopo | Rebone Secondary | 924642589 | Makhuduthamaga | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 11995028 | 47980113 | 59975141 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118450 | LE19DPW00049 | Limpopo | REKHUDITSE SECONDARY | 996606815 | Mogalakwena | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 7200000 | 8400000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118455 | LE19DPW00014 | Limpopo | Rethuseng Special School | 992202502 | Blouberg | On Hold | Active - Not Contracted | 2018-04-01 | 2020-04-02 | 2025-03-31 | 2024-07-30 | 2024-09-30 | 1877600 | 7510400 | 9388000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118456 | LE19DPW00102 | Limpopo | Rhida Primary | 916410942 | Greater Giyani | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 4000000 | 16000000 | 20000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 118457 | LE19DPW00122 | Limpopo | Runnymede Primary | 915531078 | Polokwane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6771157 | 27084628 | 33855785 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 118467 | P9013183 | Eastern Cape | NQWEBA SECONDARY SCHOOL | 200100592 | Dr Beyers Naude | Design | Proposed | 2017-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 118469 | P9011623 | Eastern Cape | HEALDTOWN COMPREHENSIVE SCHOOL | 200100296 | Raymond Mhlaba | Construction 26% - 50% | Active - Contracted | 2017-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3974134 | 3974134 | Education Infrastructure Grant | Maintenance and Repairs
|  | 120537 | LE19DPW00015 | Limpopo | SEALE SECONDARY | 919340357 | Molemole | Tender | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 7945838 | 13958349 | 21904187 | Education Infrastructure Grant | Upgrading and Additions
|  | 120538 | LE19DPW00050 | Limpopo | Sebase High | 925661160 | Makhuduthamaga | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1400000 | 6000000 | 7400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120539 | LE19DPW00074 | Limpopo | Seboeng Primary | 925661177 | Makhuduthamaga | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 8000000 | 9200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120541 | LE19DPW00085 | Limpopo | SEFOTWANE PRIMARY | 920211657 | Blouberg | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1020000 | 6000000 | 7020000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120542 | LE19DPW00103 | Limpopo | Sehonwe Primary | 918520979 | Greater Letaba | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 7804898 | 31219591 | 39024489 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120545 | LE19DPW00051 | Limpopo | Sekete Secondary | 992201202 | Polokwane | Tender | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 8259231 | 15699421 | 23958652 | Education Infrastructure Grant | Upgrading and Additions
|  | 120546 | LE19DPW00052 | Limpopo | Semetse Primary | 920211749 | Blouberg | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120548 | LE19DPW00016 | Limpopo | SERIPA SECONDARY | 922211794 | Molemole | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1100000 | 6000000 | 7100000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120549 | LE19DPW00071 | Limpopo | Seroletshidi Secondary | 922250171 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120550 | LE19DPW00123 | Limpopo | Serurubele Secondary | 926540447 | Greater Tzaneen | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2180000 | 8720000 | 10900000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120551 | LE19DPW00033 | Limpopo | Sethwethwa Secondary | 921230740 | Lepele-Nkumpi | Design | Active - Not Contracted | 2018-04-01 |  | 2023-05-31 |  |  | 2400000 | 9600000 | 12000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120569 | LE19DPW00017 | Limpopo | S.T Scholastica Primary | 931340098 | Polokwane | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120589 | LE19DPW00053 | Limpopo | suswe primary | 991104402 | Mogalakwena | Tender | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6826010 | 27304040 | 34130050 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120594 | LE19DPW00087 | Limpopo | Thabakgone Primary | 923241443 | Polokwane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 5295054 | 21180214 | 26475268 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120599 | LE19DPW00088 | Limpopo | Thabakhubedu Primary | 996606707 | Elias Motsoaledi | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 3400000 | 13600000 | 17000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120603 | LE19DPW00034 | Limpopo | Thabane Primary | 925621162 | Greater Tubatse/Fetakgomo | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6830726 | 27322905 | 34153631 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120614 | LE19DPW00089 | Limpopo | Tlhona Sedimong Secondary | 920211886 | Blouberg | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 2000000 | 8000000 | 10000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120620 | LE19DPW00035 | Limpopo | Tloukwena Primary | 996606724 | Elias Motsoaledi | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1380000 | 5520000 | 6900000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120626 | LE19DPW00036 | Limpopo | Tseke Primary | 925610421 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1080000 | 4320000 | 5400000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120697 | LE19DPW00106 | Limpopo | Ukuthula Primary | 924320468 | Greater Giyani | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 11218510 | 44874040 | 56092550 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120700 | LE19DPW00124 | Limpopo | VALLAMBROSA PRIMARY | 918511500 | Greater Tzaneen | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 7571469 | 30285875 | 37857344 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120702 | LE19DPW00018 | Limpopo | Vhulaudzi Secondary | 928330930 | Makhado | Design | Active - Not Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 120704 | LE19DPW00107 | Limpopo | Vutivi Primary | 993303101 | Polokwane | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 6964282 | 27857128 | 34821410 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120769 | LE19DPW00105 | Limpopo | Mbangazeki Secondary | 916410614 | Greater Giyani | Design | Active - Not Contracted | 2018-04-01 |  | 2025-03-31 |  |  | 2720000 | 10880000 | 13600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120900 | DB/500289969/WS | KwaZulu-Natal | UNOBHALA SECONDARY SCHOOL | 500289969 | Mkhambathini | Design | Active - Not Contracted | 2017-02-20 |  | 2024-03-28 |  |  | 815000 | 3715000 | 4530000 | Education Infrastructure Grant | Upgrading and Additions
|  | 120902 | W/500277648/RRR | KwaZulu-Natal | STANMORE SECONDARY SCHOOL | 500277648 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2018-04-27 | 2023-06-30 | 2018-09-01 | 2019-03-29 | 3122000 | 14221000 | 17343000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120903 | W/500286676/RRR | KwaZulu-Natal | UKUTHULA SECONDARY SCHOOL | 500286676 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-04-27 | 2023-03-30 | 2018-09-01 | 2025-03-29 | 1082000 | 4928000 | 6010000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120904 | W/500298368/RRR | KwaZulu-Natal | ZAKHEKAHLE SECONDARY SCHOOL | 500298368 | Mfolozi | Project Initiation | Active - Not Contracted | 2017-02-20 | 2017-03-30 | 2023-03-30 | 2018-03-30 | 2024-05-29 | 280000 | 1277000 | 1557000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 120905 | W/500303511/SDS | KwaZulu-Natal | MNYANDA PRIMARY SCHOOL | 500303511 | Alfred Duma | Terminated | Active - Contracted | 2017-05-09 | 2021-04-06 | 2023-08-09 | 2023-07-15 | 2023-12-20 | 300000 | 2300000 | 2600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 131072 | MDOE/UPG/049/19-20(PWRT/211/19/MP) | Mpumalanga | Mbongeni Primary School | 800002907 | Mbombela | Final Completion | Active - Contracted | 2018-05-01 | 2021-10-31 | 2022-05-31 | 2022-05-31 | 2022-05-31 | 1165504 | 6454560 | 7620064 | Education Infrastructure Grant | Upgrading and Additions
|  | 143072 | MDOE/UPG/1002/19-20 | Mpumalanga | Silindokuhle Primary School | 800021121 | Nkomazi | Design | Proposed | 2018-04-01 |  | 2024-03-31 |  |  | 465000 | 2325000 | 2790000 | Education Infrastructure Grant | Upgrading and Additions
|  | 143077 | PWRT/148/19/MP (MDOE/NEW/19-20/003) | Mpumalanga | MPUMELELO PRIMARY School | 800015719 | Nkomazi | Construction 76% - 99% | Active - Contracted | 2018-04-02 | 2019-11-15 | 2023-03-31 | 2022-03-30 | 2022-03-29 | 3915332 | 27966658 | 31881990 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 143078 | DPWRT/2405/19/MP | Mpumalanga | Yinhle Lentfo (Dingindoda Primary ) Primary School | new | Mbombela | Construction 76% - 99% | Active - Contracted | 2018-04-02 | 2019-08-01 | 2023-12-31 | 2023-02-22 | 2023-02-22 | 5242256 | 46227482 | 51469738 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 143122 | MDOE/MAIN/014/19-20 | Mpumalanga | Tikhontele Secondary School | 800023507 | Mbombela | Design | Proposed | 2018-04-01 |  | 2023-03-31 |  |  | 497331 | 4521189 | 5018520 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 143152 | I/500343286/UA | KwaZulu-Natal | MYEKENI SECONNDARY SCHOOL | 500343286 | Ulundi | Design | Active - Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 6990488 | 35000000 | 41990488 | Education Infrastructure Grant | Upgrading and Additions
|  | 143166 | DB/500114145/UA | KwaZulu-Natal | CACA PRIMARY SCHOOL | 500114145 | Dannhauser | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-06-01 | 2023-03-11 | 2022-03-11 | 2024-03-25 | 5068477 | 23089728 | 28158205 | Equitable Share | Upgrading and Additions
|  | 143168 | I/500341399/WS | KwaZulu-Natal | FELIFA SECONDARY SCHOOL | 500341399 | Ulundi | Practical Completion (100%) | Active - Contracted | 2015-11-20 | 2018-12-01 | 2023-03-30 | 2022-05-05 | 2023-03-03 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 143170 | I/500211270/WS | KwaZulu-Natal | MISTY RIDGE PRIMARY SCHOOL | 500211270 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2020-10-20 | 2023-03-19 | 2023-04-13 | 2023-05-10 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 143171 | DB/500137233/WS | KwaZulu-Natal | ENHLOPHENI COMBINED SCHOOL | 500137233 | Nqutu | Construction 1% - 25% | Active - Contracted | 2017-02-20 | 2020-05-31 | 2023-01-31 | 2022-03-22 | 2027-03-30 | 344483 | 1569313 | 1913796 | Education Infrastructure Grant | Upgrading and Additions
|  | 143222 | DB/500199282/RRR | KwaZulu-Natal | MARIA MEMORIAL PRIMARY SCHOOL | 500199282 | The Msunduzi | Project Initiation | Proposed | 2018-04-01 |  | 2024-02-28 |  |  | 1858000 | 2178000 | 4036000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 143227 | W/500327598/RRR | KwaZulu-Natal | MTHANTI COM TECH SCHOOL | 500327598 | Jozini | Project Initiation | Proposed | 2017-02-20 |  | 2024-03-25 |  |  | 1300000 | 2700000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 143229 | MDOE/B/ALL.EIG/UPG/17-18/387 | Mpumalanga | Security Light | 0 | Emakhazeni | Tender | Active - Contracted | 2018-04-01 |  | 2024-03-31 |  |  | 0 | 5000000 | 5000000 | Equitable Share | Maintenance and Repairs
|  | 143233 | W/500227180/RRR | KwaZulu-Natal | NGADUMBILI PRIMARY SCHOOL | 500227180 | Nongoma | Feasibility | Approved | 2017-02-20 |  | 2024-02-28 |  |  | 2000000 | 3000000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 143303 | N/A(PWRT/2394/18/MP) | Mpumalanga | Mpisi Primary School | 800034924 | Bushbuckridge | Construction 76% - 99% | Active - Contracted | 2018-05-01 | 2019-05-23 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 8448045 | 50648991 | 59097036 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 143307 | I/500145891/UA | KwaZulu-Natal | FUNDOKUHLE PRIMARY SCHOOL | 500145891 | Msinga | Construction 51% - 75% | Active - Contracted | 2019-06-22 | 2023-03-05 | 2023-04-05 | 2023-09-30 | 2023-10-30 | 10176542 | 56536344 | 66712886 | Education Infrastructure Grant | Upgrading and Additions
|  | 143360 | DPWRT/042/19/MP | Mpumalanga | Green Valley Lower & Higher Primary School | 800034855 | Bushbuckridge | Design | Active - Contracted | 2019-01-04 |  | 2025-03-15 |  |  | 311234 | 3512345 | 3823579 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 143364 | MDOE/MAIN/020/19-20 | Mpumalanga | Mapulaneng Teacher Development Centre | OFFICES | Bushbuckridge | Tender | Active - Contracted | 2018-05-15 |  | 2024-03-15 |  |  | 772333 | 5516666 | 6288999 | Education Infrastructure Grant | Maintenance and Repairs
|  | 143374 | MDOE/MAIN/64/21-22 | Mpumalanga | Skhila Secondary School | 800001164 | Thaba Chweu | Design | Proposed | 2019-04-01 |  | 2024-03-31 |  |  | 75290 | 501930 | 577220 | Education Infrastructure Grant | Maintenance and Repairs
|  | 143378 | MDOE/GS/ALL/EQS/G&S/17-18/386 | Mpumalanga | DoRA computers and softwares | 0 | Mbombela | Project Initiation | Active - Contracted | 2018-03-01 |  | 2025-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Non-Infrastructure
|  | 143388 | MDOE//MAIN/118 | Mpumalanga | Hoxani ( Teachers centre) | OFFICES | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 447400 | 2373851 | 2821251 | Education Infrastructure Grant | Maintenance and Repairs
|  | 143420 | PWRT/SAN/012/18/MP | Mpumalanga | Mayisha Secondary School | 800013573 | Dr JS Moroka | Site Handed - Over to Contractor | Active - Contracted | 2018-03-31 | 2020-06-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 238693 | 1704950 | 1943643 | Education Infrastructure Grant | Maintenance and Repairs
|  | 143447 | DPWRT/033/19/MP | Mpumalanga | Somtshongweni Primary School | 800022095 | Thembisile | Practical Completion (100%) | Active - Contracted | 2019-09-02 | 2020-06-02 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 328202 | 3282021 | 3610223 | Education Infrastructure Grant | Maintenance and Repairs
|  | 143450 | DPWRT/036/19/MP | Mpumalanga | Thandulwazi Primary School | 800022970 | Thembisile | Design | Proposed | 2019-09-02 |  | 2024-03-31 |  |  | 248408 | 2484077 | 2732485 | Education Infrastructure Grant | Maintenance and Repairs
|  | 178781 | 4537tbc | Western Cape | Darling HS New | TBC | Swartland | Project Initiation | Potential | 2020-07-31 |  | 2027-03-30 |  |  | 13500000 | 63000000 | 76500000 | Equitable Share | New or Replaced Infrastructure
|  | 178788 | 32002051 | Western Cape | St Helenabaai HS | TBC | Saldanha Bay | Feasibility | Active - Not Contracted | 2020-10-01 |  | 2026-03-31 |  |  | 11500000 | 50500000 | 62000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 178790 | 30177051 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2014-08-01 |  | 2028-03-31 |  |  | 150507000 | 605696000 | 756203000 | Equitable Share | Upgrading and Additions
|  | 178826 | DB/500106116/WS | KwaZulu-Natal | BATHATHE JUNIOR PRIMARY SCHOOL | 500106116 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2018-12-20 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2025-09-30 | 217717 | 991821 | 1209538 | Education Infrastructure Grant | Upgrading and Additions
|  | 178829 | DB/500106338/WS | KwaZulu-Natal | BATTERSEA PARK PRIMARY SCHOOL | 500106338 | Endumeni | Practical Completion (100%) | Active - Contracted | 2018-08-20 | 2024-03-11 | 2024-08-20 | 2024-06-11 | 2025-05-11 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178831 | W/500118770/WS | KwaZulu-Natal | CROWFIELD PRIMARY SCHOOL | 500118770 | Okhahlamba | Design | Active - Not Contracted | 2018-09-20 |  | 2024-03-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178837 | W/500125726/WS | KwaZulu-Natal | DWENGU SECONDARY SCHOOL | 500125726 | Mkhambathini | Design | Active - Not Contracted | 2018-12-20 |  | 2024-08-20 |  |  | 2208000 | 3488000 | 5696000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178848 | W/500129648/WS | KwaZulu-Natal | ELANGENI SECONDARY SCHOOL | 500129648 | Mfolozi | Tender | Active - Contracted | 2018-12-20 |  | 2026-06-30 |  |  | 1439000 | 1759000 | 3198000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178849 | DB/500107966/RRR | KwaZulu-Natal | BHANDE HIGH SCHOOL | 500107966 | Alfred Duma | Design | Active - Not Contracted | 2018-12-20 |  | 2026-09-20 |  |  | 4078589 | 18580237 | 22658826 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 178850 | W/500445887/WS | KwaZulu-Natal | GOODHOME SECONDARY SCHOOL | 500445887 | Okhahlamba | Design | Active - Not Contracted | 2017-06-13 |  | 2024-05-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178859 | ST350/2021 | Northern Cape | STEYNSVILLE (NEW SCHOOL) | 300022305 | Thembelihle | Construction 1% - 25% | Active - Contracted | 2024-04-01 |  | 2025-03-31 |  |  | 0 | 6000000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178880 | ET/500263366/WS | KwaZulu-Natal | SIBONISE PRIMARY SCHOOL | 500263366 | eThekwini | Final Completion | Active - Contracted | 2016-01-20 | 2017-05-04 | 2022-09-19 | 2022-04-30 | 2023-04-30 | 625163 | 3156486 | 3781649 | Education Infrastructure Grant | Upgrading and Additions
|  | 178883 | DB/500108669/WS | KwaZulu-Natal | BHEKIMPILO PRIMARY SCHOOL | 500108669 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2018-05-20 | 2024-03-11 | 2024-03-20 | 2024-06-11 | 2025-03-26 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178884 | W/500304029/WS | KwaZulu-Natal | INJESUTHI HIGH SCHOOL | 500304029 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2018-02-20 | 2018-12-01 | 2023-06-30 | 2020-05-05 | 2025-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178885 | W/500443149/WS | KwaZulu-Natal | INKOSI ALBERT SECONDARY SCHOOL | 500443149 | KwaDukuza | Design | Active - Not Contracted | 2018-02-20 |  | 2024-05-20 |  |  | 788367 | 3591450 | 4379817 | Education Infrastructure Grant | Upgrading and Additions
|  | 178886 | W/500499093/WS | KwaZulu-Natal | ISIFISOSIKAYISE HIGH SCHOOL | 500499093 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2018-05-20 | 2022-03-01 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178887 | DB/500440004/WS | KwaZulu-Natal | IZAZI HIGH SCHOOL | 500440004 | Newcastle | Design | Active - Not Contracted | 2018-02-20 |  | 2024-08-20 |  |  | 859000 | 1179000 | 2038000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178888 | ET/500441003/WS | KwaZulu-Natal | PHEMBISIZWE PRIMARY SCHOOL | 500441003 | eThekwini | Final Completion | Active - Contracted | 2016-01-20 | 2018-05-04 | 2022-09-19 | 2022-04-30 | 2023-04-30 | 614572 | 3453262 | 4067834 | Education Infrastructure Grant | Upgrading and Additions
|  | 178890 | DB/500172346/WS | KwaZulu-Natal | KANGIKHO PRIMARY SCHOOL | 500172346 | uMhlathuze | Design | Active - Not Contracted | 2018-04-20 |  | 2022-09-30 |  |  | 1458000 | 5268421 | 6726421 | Education Infrastructure Grant | Upgrading and Additions
|  | 178891 | ET/500315388/WS | KwaZulu-Natal | INGULULE PRIMARY SCHOOL | 500315388 | Mandeni | Practical Completion (100%) | Active - Contracted | 2016-01-20 | 2022-03-04 | 2022-09-30 | 2025-09-30 | 2025-04-30 | 648700 | 4626660 | 5275360 | Education Infrastructure Grant | Upgrading and Additions
|  | 178892 | DB/500177415/WS | KwaZulu-Natal | KRANSKOP PRIMARY SCHOOL | 500177415 | Umvoti | Construction 26% - 50% | Active - Contracted | 2018-02-20 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 483874 | 2204314 | 2688188 | Education Infrastructure Grant | Upgrading and Additions
|  | 178894 | DB/500187035/WS | KwaZulu-Natal | LINWOOD PRIMARY SCHOOL | 500187035 | Richmond | Design | Active - Contracted | 2018-02-20 |  | 2024-08-20 |  |  | 2240000 | 3520000 | 5760000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178896 | DB/500190920/WS | KwaZulu-Natal | MADAKA PRIMARY SCHOOL | 500190920 | Ulundi | Construction 76% - 99% | Active - Contracted | 2018-03-20 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 351722 | 1602290 | 1954012 | Education Infrastructure Grant | Upgrading and Additions
|  | 178897 | ET/500495800/WS | KwaZulu-Natal | IKUSASALENTSHA PRIMARY SCHOOL | 500495800 | eThekwini | Final Completion | Active - Contracted | 2019-12-20 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-04-30 | 580633 | 2645108 | 3225741 | Education Infrastructure Grant | Upgrading and Additions
|  | 178898 | DB/500191253/WS | KwaZulu-Natal | MADLANYOKA PRIMARY SCHOOL | 500191253 | Richmond | Design | Active - Contracted | 2018-05-20 |  | 2027-12-20 |  |  | 2244000 | 3524000 | 5768000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178899 | DB/500415066/WS | KwaZulu-Natal | MAHLOKOHLOKO PRIMARY SCHOOL | 500415066 | Msinga | Design | Active - Contracted | 2018-01-20 |  | 2024-08-20 |  |  | 464000 | 2116000 | 2580000 | Education Infrastructure Grant | Upgrading and Additions
|  | 178901 | WE001118\2018 | Western Cape | New Hout Bay PS | TBC | City of Cape Town | Design | Proposed | 2018-11-30 |  | 2026-03-31 |  |  | 17513000 | 84000000 | 101513000 | Equitable Share | New or Replaced Infrastructure
|  | 178926 | LE20TMT17049 | Limpopo | Seipone Secondary | 922221470 | Polokwane | Tender | Active - Not Contracted | 2017-04-01 |  | 2025-03-31 |  |  | 89733 | 358931 | 448664 | Education Infrastructure Grant | Upgrading and Additions
|  | 178955 | GDE00266 | Gauteng | Orchards Primary School | 700130799 | City of Johannesburg | Feasibility | Active - Contracted | 2018-11-02 |  | 2026-03-13 |  |  | 19200000 | 100800000 | 120000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 178963 | GDE00362 | Gauteng | Thabotuna Primary Schooo | 700341321 | City of Ekurhuleni | Project Initiation | Approved | 2019-10-15 |  | 2026-03-13 |  |  | 13600000 | 71400000 | 85000000 | Equitable Share | New or Replaced Infrastructure
|  | 178964 | DPWRT/081/18MP(THANDA PRIM)-------------- | Mpumalanga | Thanda Primary School | 800022897 | Nkomazi | Tender | Active - Contracted | 2018-05-01 |  | 2022-11-30 |  |  | 223200 | 1116000 | 1339200 | Education Infrastructure Grant | Upgrading and Additions
|  | 178971 | GDE00374 | Gauteng | Tinasonke Primary School | No EMIS number | City of Ekurhuleni | Design | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 11200000 | 58800000 | 70000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 179097 | GDE00031 | Gauteng | Chokoe Primary School | 700212192 | City of Tshwane | Practical Completion (100%) | Approved | 2019-03-01 |  | 2025-04-18 |  |  | 1596250 | 14186750 | 15783000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179121 | MDOE/UPG/110/22-23 | Mpumalanga | Nj Mahlangu High School | 800030478 | Nkomazi | Design | Proposed | 2018-10-02 |  | 2025-11-18 |  |  | 518000 | 3700000 | 4218000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179218 | DOE 2018/19 Septic tanks | Free State | Septic Tanks-Maintenance | 2018/19 | Masilonyana | Project Initiation | Active - Contracted | 2018-04-02 |  | 2026-03-31 |  |  | 0 | 5000000 | 5000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 179248 | FSDOE 2018/19 HALLS | Free State | Halls | 2018/19 | Letsemeng | Construction 26% - 50% | Active - Contracted | 2016-07-01 | 2017-11-01 | 2025-04-01 | 2019-04-05 | 2022-03-31 | 0 | 35000000 | 35000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179366 | 200401058/ | Eastern Cape | TIPINI JUNIOR SECONDARY SCHOOL | 200401058 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2015-10-16 | 2018-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 180000 | 180000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 179562 | FSDOE 2018/19 Service Connection | Free State | Service Connection | DOE2018/19 | Masilonyana | Project Initiation | Approved | 2019-01-09 |  | 2025-04-01 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179574 | FSDOE 2018/19PM FEES | Free State | PM FEES: Qs online 2018/19 | FSDOE18/19 PM FEES | Kopanong | Construction 26% - 50% | Active - Contracted | 2018-04-02 | 2018-06-14 | 2024-03-31 | 2019-07-31 | 2022-03-31 | 5100000 | 0 | 5100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179581 | FSDOE 2018/19: Security Upgrades | Free State | FSDOE18/19 Security Upgrades | FSDOE18/19 Security Upgrades | Metsimaholo | Construction 51% - 75% | Active - Contracted | 2017-08-01 | 2017-11-01 | 2025-04-01 | 2019-04-05 | 2024-03-31 | 0 | 35000000 | 35000000 | Infrastructure Enhancement Allocation | Upgrading and Additions
|  | 179584 | FSDOE18/19: Sewer Treatment Plant | Free State | SEDITI & UNICOM | FSDOE 2018/19 BUSINESS CONSULTANTS | Mangaung | Other - Packaged Ongoing Project | Active - Contracted | 2018-12-03 | 2020-07-02 | 2025-04-01 | 20204-07-02 | 2024-07-02 | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 179603 | FSDoE Service Connection Current | Free State | Service Connection (Current) | FSDOE18/19 Current | Masilonyana | Site Handed - Over to Contractor | Approved | 2018-12-03 | 2019-01-07 | 2026-04-30 | 2019-04-05 | 2024-03-31 | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 179778 | P9013277 | Eastern Cape | SIMPHIWE KHETHWA SECONDARY SCHOOL | 200601001 | Walter Sisulu | Construction 1% - 25% | Active - Contracted | 2021-12-01 | 2021-12-02 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 180005 | P9009925_ | Eastern Cape | LUKHANYO HIGH SCHOOL | 200600394 | Enoch Mgijima | Feasibility | Active - Not Contracted | 2016-09-13 |  | 2026-03-31 |  |  | 0 | 262302 | 262302 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180006 | P9009682_ | Eastern Cape | MAKI JUNIOR SECONDARY SCHOOL | 200300272 | Amahlathi | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 104173 | 104173 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180055 | C/500448921/LSEN Completion Contract | KwaZulu-Natal | PHOLELA SPECIAL SCHOOL | 500448921 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2018-06-15 | 2018-10-16 | 2022-04-16 | 2022-04-16 | 2023-04-16 | 11906000 | 54236000 | 66142000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180067 | P9009666_ | Eastern Cape | MHLOPHEKAZI JUNIOR SECONDARY SCHOOL | 200400597 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-28 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2290058 | 319316 | 2609374 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180089 | P9009689_ | Eastern Cape | STONY CROFT JUNIOR SECONDARY SCHOOL | 200600805 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-11-29 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 619119 | 4422494 | 5041613 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180094 | P9009672_ | Eastern Cape | PAKAMISA SENIOR PRIMARY SCHOOL | 200400906 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2018-11-29 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 526575 | 3761252 | 4287827 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180095 | P9006443_ | Eastern Cape | PHAKAMISA HIGH SCHOOL | 200100626 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2016-01-28 | 2017-06-01 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 1165540 | 11226203 | 12391743 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180119 | P9011624 | Eastern Cape | IKWEZI LOKUSA SPECIAL SCHOOL - Sanitation | 200400275 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2016-06-24 | 2017-06-05 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 10560304 | 10560304 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180154 | P9009674_ | Eastern Cape | ZAMIWONGA SENIOR PRIMARY SCHOOL | 200401162 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-02-05 | 2023-03-31 | 2025-03-31 | 2025-03-31 | 395780 | 2827001 | 3222781 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180155 | P9006638 | Eastern Cape | NONESI SENIOR PRIMARY SCHOOL | 200600612 | Nyandeni | Construction 1% - 25% | Active - Contracted | 2018-04-10 | 2022-04-30 | 2026-03-31 | 2023-06-30 | 2024-12-31 | 0 | 272612 | 272612 | Education Infrastructure Grant | Upgrading and Additions
|  | 180157 | P9009679_ | Eastern Cape | NQUQU JUNIOR SECONDARY SCHOOL | 200600634 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-03-29 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 597963 | 4271246 | 4869209 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180160 | P9008595_ | Eastern Cape | JEKEZI JUNIOR SECONDARY SCHOOL | 200300157 | Mnquma | Practical Completion (100%) | Active - Contracted | 2017-08-01 | 2018-02-05 | 2023-03-30 | 2024-03-30 | 2025-03-31 | 0 | 2746348 | 2746348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180167 | P9009803_ | Eastern Cape | MTYAMDE JUNIOR SECONDARY SCHOOL | 200300394 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 640390 | 4574214 | 5214604 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180169 | P9006932_ | Eastern Cape | TOLOFIYENI PRIMARY SCHOOL | 200200849 | Buffalo City | Final Completion | Active - Contracted | 2018-04-01 | 2019-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2954592 | 2954592 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180172 | P9008578_ | Eastern Cape | SIYAZAKHA HIGH SCHOOL | 200201002 | Great Kei | Practical Completion (100%) | Active - Contracted | 2018-04-10 | 2019-04-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 1691000 | 1691000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180173 | P9008582_ | Eastern Cape | FANTI GAQA SENIOR PRIMARY SCHOOL | 200200173 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-30 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 374258 | 2200293 | 2574551 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180174 | P9009673_ | Eastern Cape | BEKILENI JUNIOR SECONDARY SCHOOL | 200400030 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2018-06-29 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 232184 | 1658455 | 1890639 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180176 | P9009659_ | Eastern Cape | TLOKWENG SENIOR SECONDARY SCHOOL | 200600849 | Senqu | Construction 76% - 99% | Active - Contracted | 2022-02-22 | 2024-04-30 | 2025-03-30 | 2025-03-31 | 2026-03-31 | 0 | 6146110 | 6146110 | Education Infrastructure Grant | Upgrading and Additions
|  | 180177 | P9008619_ | Eastern Cape | IMVISISWANO PRIMARY SCHOOL | 200100336 | Raymond Mhlaba | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 39115203 | 39115203 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180180 | P9008620_ | Eastern Cape | NOSIMO TECHNICAL HIGH SCHOOL | 200100336 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-30 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 105693 | 742846 | 848539 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180185 | P9005215_ | Eastern Cape | KHWAZA SENIOR SECONDARY SCHOOL | 200600335 | Intsika Yethu | Construction 76% - 99% | Approved | 2014-09-01 | 2017-09-15 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 115000 | 1158229 | 1273229 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180193 | P9011734_ | Eastern Cape | ENKWENKWEZINI SECONDARY SCHOOL | 200200164 | Raymond Mhlaba | Practical Completion (100%) | Active - Contracted | 2018-07-16 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 548987 | 548987 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180207 | P9003556_ | Eastern Cape | LUTSHAYA JUNIOR SECONDARY SCHOOL | 200500481 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2014-07-26 | 2018-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 5650000 | 30994911 | 36644911 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180284 | I/500240204/WS | KwaZulu-Natal | NTOLWANE PRIMARY SCHOOL | 500240204 | Nkandla | Construction 1% - 25% | Active - Contracted | 2019-02-13 | 2021-03-20 | 2022-09-24 | 2022-10-27 | 2023-02-15 | 128000 | 845000 | 973000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180294 | 23 | North West |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 0218-01-15 |  | 2024-03-31 |  |  | 0 | 18725000 | 18725000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180298 | IKA | North West | Ikalafeng Special | ika | Ventersdorp/Tlokwe | Project Initiation | Active - Not Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 0 | 30000000 | 30000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180418 | IJSX027/2019 | Northern Cape | NEW BANKHARA SCHOOL | NEW | Ga-Segonyana | Design | Approved | 2019-04-01 |  | 2025-03-28 |  |  | 25000000 | 100070376 | 125070376 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180419 | CO-FUNDING WITH AFBOB | Northern Cape | FRANCISCUS INTERMEDIATE SCHOOL | 300041202 | Dawid Kruiper | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2025-03-28 |  |  | 21382421 | 118791230 | 140173651 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180420 | ISJX0021/2019 | Northern Cape | ORANJE-OEWER INTERMAEDIATE SCHOOL | 300041213 | Dawid Kruiper | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-28 |  |  | 31238966 | 127558051 | 158797017 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180422 | ISJX028/2019 | Northern Cape | KURUMAN NEW MEDIUM PRIMARY SCHOOL (WRENCHVILLE/KALAHARI | TBD | Ga-Segonyana | Design | Approved | 2019-04-01 |  | 2025-03-28 |  |  | 28398802 | 70000000 | 98398802 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180498 | DB/500107707/SDS | KwaZulu-Natal | BESTERSPRUIT PRIMARY SCHOOL | 500107707 | Abaqulusi | Practical Completion (100%) | Approved | 2018-01-01 | 2019-01-08 | 2025-07-07 | 2023-07-07 | 2025-07-07 | 945537 | 4307444 | 5252981 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180501 | DB/500225478/SDS | KwaZulu-Natal | NDLOVANA SECONDARY SCHOOL | 500225478 | Ulundi | Final Completion | Approved | 2018-01-02 | 2019-01-08 | 2025-07-30 | 2022-07-30 | 2025-07-30 | 1809187 | 8241850 | 10051037 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180503 | DB/500269212/SDS | KwaZulu-Natal | SIVUKILE SECONDARY SCHOOL | 500269212 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2018-01-02 | 2019-01-08 | 2025-07-07 | 2019-07-07 | 2025-07-07 | 787858 | 3589129 | 4376987 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180504 | DB/500111333/SDS | KwaZulu-Natal | BONGUDUNGA PRIMARY SCHOOL | 500111333 | The Msunduzi | Final Completion | Approved | 2018-01-02 | 2019-01-11 | 2023-03-31 | 2022-10-10 | 2025-03-22 | 1345777 | 6130761 | 7476538 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180505 | DB/500164280/SDS | KwaZulu-Natal | INHLWATHI PRIMARY SCHOOL | 500164280 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-01-09 | 2023-07-08 | 2019-07-08 | 2024-07-08 | 1778159 | 8100502 | 9878661 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180506 | DB/500441632/SDS | KwaZulu-Natal | ZIPHOSHENI PRIMARY SCHOOL | 500441632 | Jozini | Practical Completion (100%) | Active - Not Contracted | 2018-01-25 | 2019-01-10 | 2023-07-03 | 2023-07-19 | 2027-08-30 | 556970 | 2537307 | 3094277 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180508 | DB/500239205/SD | KwaZulu-Natal | NTAMINEMIDWA HIGH SCHOOL | 500239205 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-01-09 | 2023-07-08 | 2020-07-08 | 2027-07-08 | 1001965 | 4564507 | 5566472 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180509 | DB/500192215/SD | KwaZulu-Natal | MAGENQEZA PRIMARY SCHOOL | 500192215 | Nongoma | Practical Completion (100%) | Active - Contracted | 2018-04-27 | 2019-01-08 | 2022-07-07 | 2022-10-07 | 2025-07-07 | 1818235 | 8283069 | 10101304 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180521 | WE001255/2019 | Western Cape | Happy Valley No.2 | TBC | City of Cape Town | Tender | Active - Not Contracted | 2019-05-03 |  | 2026-03-31 |  |  | 15028000 | 68000000 | 83028000 | Equitable Share | New or Replaced Infrastructure
|  | 180535 | GDE00225 | Gauteng | Mcbain Charles Primary | 700120220 | City of Johannesburg | Construction 26% - 50% | Approved | 2016-04-01 | 2016-08-15 | 2025-03-12 | 2025-04-01 | 2026-02-13 | 1440000 | 7560000 | 9000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180538 | ET/500186258/WS | KwaZulu-Natal | LETHUXOLO SECONDARY SCHOOL | 500186258 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2018-01-16 | 2018-05-04 | 2023-12-14 | 2024-11-05 | 2025-03-31 | 649064 | 2956845 | 3605909 | Education Infrastructure Grant | Upgrading and Additions
|  | 180540 | GDE00233 | Gauteng | Mohlakeng Secondary Secondary | No EMIS number | Rand West City | Tender | Approved | 2019-04-01 |  | 2026-03-01 |  |  | 2880000 | 15120000 | 18000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180550 | GDE00304 | Gauteng | Reiger Primary School | 700160077 | City of Ekurhuleni | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-13 |  |  | 7520000 | 39480000 | 47000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180555 | TBC 03 | Western Cape | Dagbreek LS | TBC | Langeberg | Design | Active - Not Contracted | 2021-04-01 |  | 2027-03-31 |  |  | 18000000 | 79000000 | 97000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180569 | DRPW022/2018 | Northern Cape | WRENCHVILLE HIGH SCHOOL | 300045218 | Ga-Segonyana | Construction 1% - 25% | Active - Contracted | 2019-06-03 | 2020-05-24 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 19877633 | 22107645 | Education Infrastructure Grant | Upgrading and Additions
|  | 180570 | MDOE/MAIN-OHS/001/19-20 | Mpumalanga | Nelspruit | F007940 | Mbombela | Project Initiation | Proposed | 2020-07-15 |  | 2023-03-31 |  |  | 498765 | 4987654 | 5486419 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180572 | DRPW024/2018 | Northern Cape | LARENG PRIMARY SCHOOL | 300100817 | Ga-Segonyana | Tender | Active - Contracted | 2019-06-01 |  | 2024-03-26 |  |  | 182045 | 14000000 | 14182045 | Education Infrastructure Grant | Upgrading and Additions
|  | 180574 | DRPW025/2018 | Northern Cape | OLEHILE MANCHWE INTERMEDIATE SCHOOL | 300101564 | Phokwane | Construction 1% - 25% | Active - Contracted | 2019-04-26 | 2020-06-01 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 0 | 6611859 | 6611859 | Education Infrastructure Grant | Upgrading and Additions
|  | 180575 | DRPW026/2018 | Northern Cape | SISHEN INTERMEDIATE MINE SCHOOL | N/A | Gamagara | Construction 51% - 75% | Active - Contracted | 2019-05-24 | 2019-06-03 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2186644 | 10000000 | 12186644 | Education Infrastructure Grant | Upgrading and Additions
|  | 180609 | ST368/2021 | Northern Cape | LEHIKENG INTERMEDIATE SCHOOL | 300100840 | Joe Morolong | Design | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 349453 | 349453 | Education Infrastructure Grant | Upgrading and Additions
|  | 180623 | BBB 2020/06 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2021-04-01 | 2021-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 983297 | 983297 | Education Infrastructure Grant | Upgrading and Additions
|  | 180628 | ISJX020/2019 | Northern Cape | RIETRIVIER PRIMARY SCHOOL | 300014208 | Sol Plaatjie | Design | Proposed | 2019-07-26 |  | 2025-03-31 |  |  | 29811793 | 121730472 | 151542265 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180642 | 10/19/20 | Free State | PROJECT MANAGEMENT FEES: OTHER | 10/19/20 | Mangaung | Site Handed - Over to Contractor | Active - Contracted | 2017-04-01 | 2017-04-02 | 2025-04-01 | 2022-03-31 | 2020-03-31 | 3000000 | 0 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180650 | .11/19/20 | Free State | SENEKAL LINDLEY | SL/1 | Nketoana | Other - Packaged Ongoing Project | Active - Contracted | 2015-11-01 | 2019-02-18 | 2026-03-31 | 2024-10-25 | 2024-01-31 | 0 | 737216000 | 737216000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 180652 | 13/19/20 | Free State | CONDITION ASSESSMENT & EFMS | 13/19/20 | Mangaung | Construction 1% - 25% | Active - Contracted | 2018-04-01 | 2018-04-02 | 2026-03-31 | 2022-03-31 | 2024-03-31 | 5000000 | 0 | 5000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 180704 | PWRT/2402/19/MP | Mpumalanga | Boschrand Primary School (Msholozi) | 800001545 | Mbombela | Construction 76% - 99% | Active - Contracted | 2018-11-01 | 2019-02-05 | 2023-03-31 | 2022-03-22 | 2022-03-22 | 5829047 | 51747409 | 57576456 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180713 | ( PWRT/151/17/MP) | Mpumalanga | Magogeni Primary School | 800011536 | Nkomazi | Final Completion | Active - Contracted | 2018-10-15 | 2019-02-04 | 2023-03-31 | 2019-11-27 | 2021-02-26 | 2705845 | 22863230 | 25569075 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180765 | DOE11/17/20 | Free State | stenysrus hostel | renovations | Moqhaka | Other - Packaged Ongoing Project | Active - Contracted | 2015-11-01 | 2020-07-02 | 2026-03-31 | 2027-03-31 | 2026-03-31 | 0 | 298369000 | 298369000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 180846 | DB/500154623/WS | KwaZulu-Natal | HEMFANE PRIMARY SCHOOL | 500154623 | uMlalazi | Design | Active - Contracted | 2017-06-20 |  | 2024-03-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180851 | DB/500160839/WS | KwaZulu-Natal | IMFULE PRIMARY SCHOOL | 500160839 | Mthonjaneni | Design | Active - Contracted | 2018-01-16 |  | 2024-03-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180860 | DB/500162356/WS | KwaZulu-Natal | INDATSHE COMBINED PRIMARY SCHOOL | 500162356 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-16 | 2022-06-01 | 2024-03-30 | 2024-03-30 | 2025-05-30 | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180862 | DB/500164132/WS | KwaZulu-Natal | INHLASANA PRIMARY SCHOOL | 500164132 | Umzumbe | Design | Active - Contracted | 2018-01-16 |  | 2024-03-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180866 | DB/500165353/WS | KwaZulu-Natal | INQABA PRIMARY SCHOOL | 500165353 | Mthonjaneni | Construction 76% - 99% | Active - Contracted | 2017-01-16 | 2019-09-12 | 2023-01-31 | 2022-06-25 | 2027-11-13 | 372843 | 1698506 | 2071349 | Education Infrastructure Grant | Upgrading and Additions
|  | 180875 | DB/500166722/WS | KwaZulu-Natal | INYANDEZULU PRIMARY SCHOOL | 500166722 | Ray Nkonyeni | Construction 1% - 25% | Active - Not Contracted | 2016-01-16 | 2018-06-12 | 2023-01-31 | 2022-06-15 | 2027-07-18 | 685449 | 3122599 | 3808048 | Education Infrastructure Grant | Upgrading and Additions
|  | 180878 | DB/500166907/WS | KwaZulu-Natal | INYONEMHLOPHE SECONDARY SCHOOL | 500166907 | eThekwini | Design | Active - Contracted | 2018-01-16 |  | 2024-04-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180884 | DB/500168165/WS | KwaZulu-Natal | ISIKHUTHALI PRIMARY SCHOOL | 500168165 | Ray Nkonyeni | Design | Active - Not Contracted | 2018-01-16 |  | 2024-04-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180905 | DB/500171051/WS | KwaZulu-Natal | JANGENI PRIMARY SCHOOL | 500171051 | Msinga | Design | Active - Contracted | 2018-01-16 | 2021-01-31 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 100000 | 300000 | 400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 180949 | GDE00430 | Gauteng | Zakhele Primary School | 700221200 | City of Tshwane | Design | Approved | 2019-11-05 |  | 2026-03-13 |  |  | 6400000 | 33600000 | 40000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 180963 | GDE00293 | Gauteng | 0 | 700270025 | Merafong City | Project Initiation | Approved | 2019-04-01 |  | 2026-03-15 |  |  | 2720000 | 14280000 | 17000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181040 | 11/19/20 | Free State | AJC Jooste | rehabilitation | Letsemeng | Other - Packaged Ongoing Project | Active - Contracted | 2019-04-23 | 2020-07-02 | 2025-10-31 | 2025-10-25 | 2024-01-31 | 0 | 5000000 | 5000000 | Infrastructure Enhancement Allocation | Rehabilitation, Renovations & Refurbishment
|  | 181087 | DRPW020/2018 | Northern Cape | PRIESKA COMBINED SCHOOL | 300022302 | Siyathemba | Practical Completion (100%) | Active - Contracted | 2019-05-17 | 2019-06-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 4786381 | 4786381 | Education Infrastructure Grant | Upgrading and Additions
|  | 181139 | DPWRT/105//19/MP(MDOE/NEW/19/20/012 | Mpumalanga | Ndindindi Primary School | 800016428 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2019-05-01 | 2019-10-16 | 2025-03-31 | 2022-03-30 | 2022-03-30 | 2663510 | 12236354 | 14899864 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181141 | MDOE/NEW/19-20/016(DPWRT/025/19/MP) | Mpumalanga | Mgobodi Primary School | 800014084 | Nkomazi | Design | Active - Not Contracted | 2019-05-01 |  | 2025-10-31 |  |  | 4651693 | 38764112 | 43415805 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181142 | MDOE/NEW/20-21/023 | Mpumalanga | Langa Secondary School | 80005311 | Nkomazi | Tender | Active - Not Contracted | 2022-02-01 |  | 2024-11-25 |  |  | 5424741 | 30137452 | 35562193 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181167 | Rys | North West | Rsymierbult Mega Farm | Rsy | Ventersdorp/Tlokwe | Project Initiation | Active - Contracted | 2019-04-01 |  | 2026-03-30 |  |  | 0 | 150000000 | 150000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181240 | GDE00280 | Gauteng | Phororong Primary School | 700271015 | Merafong City | Feasibility | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 6400000 | 33600000 | 40000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 181344 | DPWRT/110/18/MP (ROCKDALE P)------------- | Mpumalanga | Rockdale Primary School Middelburg X24 | New | Steve Tshwete | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2021-10-15 | 2025-03-31 | 2023-11-15 | 2023-11-15 | 6443202 | 35795568 | 42238770 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181360 | MDOE/MAIN/058/19-20(PWRT/MAIN/071/19/MP) | Mpumalanga | Klipspringer Primary School | 800008177 | Mbombela | Construction 76% - 99% | Active - Contracted | 2019-03-01 | 2019-04-24 | 2023-03-31 | 2022-03-30 | 2022-03-30 | 1460141 | 10429579 | 11889720 | Education Infrastructure Grant | Upgrading and Additions
|  | 181366 | Conditional Ass | North West | Conditonal Assessment | Conditonal Ass | Ditsobotla | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-07-31 | 2024-03-31 | 2025-03-01 | 2025-03-31 | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 181372 | PWRT/MAIN/016/19/MP (MDOE/UPG/102/19-20) | Mpumalanga | Schoemansdal Combined School | 800019968 | Nkomazi | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2019-07-10 | 2024-04-26 | 2022-03-28 | 2022-03-26 | 3293905 | 13175619 | 16469524 | Education Infrastructure Grant | Upgrading and Additions
|  | 181376 | MDOE/UPG/007/20-21(DPWRT/053/19/MP) | Mpumalanga | Mhlume Secondary School | 800034165 | Mbombela | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2020-10-12 | 2023-03-31 | 2021-09-23 | 2021-04-30 | 548702 | 4572520 | 5121222 | Education Infrastructure Grant | Upgrading and Additions
|  | 181391 | GDE/700270041/R&R/2019/ | Gauteng | Carleton Jones High School | 700270041 | Merafong City | Feasibility | Approved | 2019-11-05 |  | 2025-03-14 |  |  | 3200000 | 16800000 | 20000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 181396 | GDE00177 | Gauteng | Laerskool Queenswood | 700220418 | City of Tshwane | Project Initiation | Approved | 2020-08-14 |  | 2023-06-09 |  |  | 3164000 | 16086000 | 19250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 181424 | P9004830_ | Eastern Cape | UMTATA TECHNICAL HIGH SCHOOL | 200401340 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2017-03-03 | 2017-09-09 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1202632 | 9907608 | 11110240 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181444 | MDOE/NEW/19-20/007 | Mpumalanga | New Mbombela City Secondary School | 0 | Bushbuckridge | Feasibility | Active - Not Contracted | 2019-04-30 |  | 2027-03-31 |  |  | 8526238 | 47367988 | 55894226 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 181478 | P9010460_ | Eastern Cape | QUNU JUNIOR SECONDARY SCHOOL | 200400959 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2017-11-01 | 2018-01-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 568633 | 3243330 | 3811963 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181734 | P9011737 | Eastern Cape | KUBUSIE COMBINED SCHOOL | 200200328 | Amahlathi | Project Initiation | Approved | 2017-04-03 |  | 2026-03-31 |  |  | 0 | 548978 | 548978 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181740 | P0003283 | Eastern Cape | MANZIMAHLE SENIOR PRIMARY SCHOOL | 200400418 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2013-03-29 | 2015-09-16 | 2026-03-31 | 2023-03-31 | 2023-03-31 | 3940117 | 22676971 | 26617088 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181761 | P0003284_ | Eastern Cape | MASIBAMBISANE SENIOR PRIMARY SCHOOL | 200400503 | Mhlontlo | Final Completion | Active - Contracted | 2013-04-11 | 2016-08-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2774300 | 15398377 | 18172677 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181774 | P9010913_ | Eastern Cape | NDZULUKA PRIMARY SCHOOL | 200400730 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-09-03 | 2019-04-25 | 2023-03-31 | 2024-03-31 | 2024-03-31 | 0 | 842005 | 842005 | Education Infrastructure Grant | Maintenance and Repairs
|  | 181999 | DoE/Boh/MAIN/126 | Mpumalanga | Magwagwaza Secondary School | 800034971 | Bushbuckridge | Tender | Active - Contracted | 2021-01-05 |  | 2024-03-31 |  |  | 500747 | 3576767 | 4077514 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182017 | DPWRT/052/19/MP | Mpumalanga | Farel Primary School | 800035123 | Bushbuckridge | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-22 | 2023-04-29 | 2021-01-13 | 2021-03-31 | 250379 | 2180861 | 2431240 | Education Infrastructure Grant | Upgrading and Additions
|  | 182119 | MDOE/UPG/100/19-20 | Mpumalanga | Estralita Special School | Estralita Special School | Bushbuckridge | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 2522968 | 15768552 | 18291520 | Education Infrastructure Grant | Upgrading and Additions
|  | 182122 | TBD_ BATLHARO TLHAPING | Northern Cape | BATLHARO TLHAPING SECONDARY SCHOOL | 300100095 | Ga-Segonyana | Project Initiation | Active - Not Contracted | 2022-08-05 |  | 2022-12-02 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182125 | TBD:HOSTEL:R&R | Northern Cape | KGOTATSANO PRIMARY SCHOOL | 300045206 | Ga-Segonyana | Design | Active - Not Contracted | 2022-09-02 |  | 2025-03-31 |  |  | 0 | 2161387 | 2161387 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 182152 | RR BURNT HOSTEL | Northern Cape | VICTORIA-WES GEKOMBINEERDE SKOOL | 300024304 | Ubuntu | Feasibility | Active - Not Contracted | 2022-04-07 |  | 2024-03-31 |  |  | 0 | 2143801 | 2143801 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182159 | DISTRICT OFFICE | Northern Cape | FRANCES BAARD DISTRICT OFFICE - HADISON PARK | 300010201 | Gamagara | Feasibility | Active - Contracted | 2022-03-27 |  | 2023-03-31 |  |  | 0 | 1750000 | 1750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182172 | P0001948_ | Eastern Cape | MALUTI JUNIOR SECONDARY SCHOOL | 200500552 | Elundini | Construction 76% - 99% | Active - Contracted | 2014-05-12 | 2014-09-21 | 2023-03-31 | 2024-03-31 | 2025-03-31 | 0 | 27223 | 27223 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182175 | P9005333_ | Eastern Cape | JONGILIZWE SENIOR SECONDARY SCHOOL | 200400293 | Mhlontlo | Construction 76% - 99% | Active - Contracted | 2012-11-01 | 2014-01-23 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 141000 | 955537 | 1096537 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182176 | DPWRT/080/19/MP | Mpumalanga | Lugebhuta Secondary School | 800010785 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-01-02 | 2024-06-26 | 2020-11-24 | 2024-10-25 | 368148 | 3067896 | 3436044 | Education Infrastructure Grant | Upgrading and Additions
|  | 182188 | LE20TMT17003 | Limpopo | Madipoane Primary | 904242569 | Greater Tzaneen | Construction 1% - 25% | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 3614404 | 3614404 | Education Infrastructure Grant | Upgrading and Additions
|  | 182239 | P9006733_ | Eastern Cape | GOBINTSASA JUNIOR PRIMARY SCHOOL | 200100036 | Ntabankulu | Tender | Active - Not Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 0 | 178362 | 178362 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182251 | P9006738_ | Eastern Cape | INDWE HIGH SCHOOL | 200600296 | Emalahleni | Construction 51% - 75% | Active - Contracted | 2017-06-19 | 2019-04-01 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 2398274 | 2398274 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182255 | DPWRT/158/19/MP(LAMBALATI SEC) --------- | Mpumalanga | Lambalati Secondary School | 800009795 | Nkomazi | Tender | Proposed | 2019-05-01 |  | 2024-10-31 |  |  | 1508383 | 10774165 | 12282548 | Education Infrastructure Grant | Upgrading and Additions
|  | 182259 | P9011609 | Eastern Cape | ENKULULEKWENI PRIMARY SCHOOL | 200100317 | Nelson Mandela Bay | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 18000000 | 18000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182264 | P9006755_ | Eastern Cape | LADY GREY ARTS ACADEMY - Water | 200600985 | Senqu | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2018-05-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2874751 | 2874751 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182265 | P9005219_ | Eastern Cape | HALA SENIOR SECONDARY SCHOOL | 200100163 | Enoch Mgijima | Practical Completion (100%) | Approved | 2015-05-05 | 2018-06-04 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 295305 | 3374173 | 3669478 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182282 | P9011636 | Eastern Cape | NDAMASE SENIOR SECONDARY SCHOOL - Sanitation | 200400716 | Nyandeni | Construction 51% - 75% | Active - Contracted | 2017-06-19 | 2018-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4310889 | 4310889 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182283 | P9006438_ | Eastern Cape | NTLEMEZA PRIMARY SCHOOL | 200100596 | Nelson Mandela Bay | Construction 76% - 99% | Active - Contracted | 2016-01-28 | 2016-03-01 | 2026-03-31 | 2024-03-31 | 2026-03-31 | 277515 | 2672954 | 2950469 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 182284 | P9006783_ | Eastern Cape | NGANGELIZWE SENIOR SECONDARY SCHOOL | 200401343 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2016-06-24 | 2020-06-06 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 589840 | 2111925 | 2701765 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182291 | MDOE/MAIN/SP/001/20-21 | Mpumalanga | Silindokuhle Special School | 800021121 | Nkomazi | Design | Proposed | 2021-04-01 |  | 2024-03-31 |  |  | 1704699 | 1799762 | 3504461 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182319 | P9006787_ | Eastern Cape | NOLITHA SPECIAL SCHOOL - Water | 200501451 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2018-11-01 | 2019-04-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 971794 | 3931293 | 4903087 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182321 | P9006497_ | Eastern Cape | THEMBELIHLE JUNIOR PRIMARY SCHOOL | 200401051 | Enoch Mgijima | Construction 76% - 99% | Active - Not Contracted | 2015-03-31 | 2018-03-20 | 2024-03-31 | 2024-03-31 | 2023-03-31 | 3930457 | 12551820 | 16482277 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 182322 | P9007297_ | Eastern Cape | MOUNT ARTHUR GIRLS HIGH SCHOOL - Sanitation | 200601142 | Enoch Mgijima | Construction 51% - 75% | Active - Contracted | 2018-10-26 | 2018-11-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5807858 | 5807858 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182343 | P9006794_ | Eastern Cape | SHAWBURY SENIOR SECONDARY SCHOOL | 200400989 | Mhlontlo | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2019-04-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4054025 | 4054025 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182348 | P9006813_ | Eastern Cape | ZAMOKUHLE SPECIAL SCHOOL - Water | 200501311 | Mbizana | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2019-04-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1038948 | 2697270 | 3736218 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182375 | ET/500207644/WS | KwaZulu-Natal | MENYEZWAYO SECONDARY SCHOOL | 500207644 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2023-03-30 | 2023-03-30 | 2025-03-30 | 2025-03-30 | 1097683 | 5000557 | 6098240 | Education Infrastructure Grant | Upgrading and Additions
|  | 182377 | DB/500101898/WS | KwaZulu-Natal | AMANDLESIZWE HIGHER PRIMARY SCHOOL | 500101898 | Mtubatuba | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2019-03-01 | 2024-03-30 | 2024-03-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182378 | DB/500310874/WS | KwaZulu-Natal | AMANDLETHU JUNIOR SECONDARY SCHOOL (JOZINI) | 500310874 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2020-05-31 | 2023-01-31 | 2023-12-25 | 2025-05-30 | 284900 | 1297876 | 1582776 | Education Infrastructure Grant | Upgrading and Additions
|  | 182385 | DB/SAFE/500105746/WS | KwaZulu-Natal | BAPAUME PRIMARY SCHOOL | 500105746 | Endumeni | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2024-03-11 | 2024-06-30 | 2024-07-30 | 2025-05-11 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182386 | DB/SAFE/500105968/WS | KwaZulu-Natal | BARNHILL PRIMARY SCHOOL | 500105968 | Msinga | Practical Completion (100%) | Active - Not Contracted | 2016-06-06 | 2024-03-11 | 2024-12-01 | 2024-07-30 | 2025-05-11 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182387 | DB/500423724/WS | KwaZulu-Natal | BOMBASI PRIMARY SCHOOL | 500423724 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-06-08 | 2023-03-30 | 2022-03-21 | 2025-03-25 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182388 | DB/500112147/WS | KwaZulu-Natal | BRAKWAL PRIMARY SCHOOL | 500112147 | Alfred Duma | Design | Active - Contracted | 2016-06-06 |  | 2025-03-25 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182389 | DB/500122914/WS | KwaZulu-Natal | DOORNKLOOF INTERMIDIATE SCHOOL | 500122914 | Mpofana | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 277020 | 1261980 | 1539000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182390 | DB/500324860/WS | KwaZulu-Natal | DUMAZINKANI JUNIOR PRIMARY SCHOOL | 500324860 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182391 | DB/500130314/WS | KwaZulu-Natal | EMADUNDUBE PRIMARY SCHOOL | 500130314 | eThekwini | Tender | Active - Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182392 | DB/500137529/WS | KwaZulu-Natal | ENKATHWENI PRIMARY SCHOOL | 500137529 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 360777 | 1643540 | 2004317 | Education Infrastructure Grant | Upgrading and Additions
|  | 182393 | DB/uMg.New12/008/WS | KwaZulu-Natal | ESITEBHISINI PRIMARY SCHOOL | uMg.New12/008 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182394 | DB/500147223/WS | KwaZulu-Natal | GAWOZI SECONDARY SCHOOL | 500147223 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-03-01 | 2024-03-30 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182395 | DB/500147704/WS | KwaZulu-Natal | GCIZELA PRIMARY SCHOOL | 500147704 | Alfred Duma | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 292733 | 1333559 | 1626292 | Education Infrastructure Grant | Upgrading and Additions
|  | 182396 | DB/500147778/WS | KwaZulu-Natal | GCOTSHENI PRIMARY SCHOOL | 500147778 | uMlalazi | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 463901 | 2113325 | 2577226 | Education Infrastructure Grant | Upgrading and Additions
|  | 182397 | DB/500147889/WS | KwaZulu-Natal | GEDE JUNIOR PRIMARY SCHOOL | 500147889 | Msinga | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2019-03-01 | 2024-03-30 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182398 | DB/500148592/WS | KwaZulu-Natal | GIBINDLALA COMBINED PRIMARY SCHOOL | 500148592 | Nongoma | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 307166 | 1399314 | 1706480 | Education Infrastructure Grant | Upgrading and Additions
|  | 182399 | DB/500320124/WS | KwaZulu-Natal | GILONKI SECONDARY SCHOOL | 500320124 | Mtubatuba | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182400 | DB/500150072/WS | KwaZulu-Natal | GOBAMAHLAMVU PRIMARY SCHOOL | 500150072 | uMlalazi | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 274304 | 1249606 | 1523910 | Education Infrastructure Grant | Upgrading and Additions
|  | 182401 | DB/500150442/WS | KwaZulu-Natal | GODIDE HIGH SCHOOL | 500150442 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182402 | DB/500152292/WS | KwaZulu-Natal | GUBAZI PRIMARY SCHOOL | 500152292 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182403 | DB/500327931/WS | KwaZulu-Natal | HAMBANGOMTHETHO JUNIOR PRIMARY SCHOOL | 500327931 | Mtubatuba | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182404 | DB/500153439/WS | KwaZulu-Natal | HAMBISANANI HIGH SCHOOL | 500153439 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 530543 | 2416917 | 2947460 | Education Infrastructure Grant | Upgrading and Additions
|  | 182405 | DB/500425611/WS | KwaZulu-Natal | HIGHLANDS JUNIOR SECONDARY SCHOOL SCHOOL | 500425611 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182406 | DB/500156954/WS | KwaZulu-Natal | HLENGIWE SECONDARY SCHOOL | 500156954 | eThekwini | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182407 | DB/500157028/WS | KwaZulu-Natal | HLINZEKA COMBINED PRIMARY SCHOOL | 500157028 | Nqutu | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182408 | DB/500157657/WS | KwaZulu-Natal | HLULABANTU PRIMARY SCHOOL | 500157657 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 282270 | 1285897 | 1568167 | Education Infrastructure Grant | Upgrading and Additions
|  | 182409 | DB/500327078/WS | KwaZulu-Natal | IMBALIKHONA LOWER PRIMARY SCHOOL | 500327078 | Big Five Hlabisa | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2019-03-01 | 2024-03-30 | 2024-06-30 | 2025-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182410 | DB/500147926/WS | KwaZulu-Natal | INJULA (GEDLEZA) INTERMIDIATE SCHOOL | 500147926 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-08-12 | 2023-01-31 | 2023-09-06 | 2027-05-19 | 507005 | 2309692 | 2816697 | Education Infrastructure Grant | Upgrading and Additions
|  | 182411 | DB/500167388/WS | KwaZulu-Natal | ISIBANI SENIOR PRIMARY SCHOOL | 500167388 | Big Five Hlabisa | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182412 | DB/500167684/WS | KwaZulu-Natal | ISICELOSETHU HIGH SCHOOL | 500167684 | Jozini | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 467005 | 2127469 | 2594474 | Education Infrastructure Grant | Upgrading and Additions
|  | 182413 | DB/500168017/WS | KwaZulu-Natal | ISIHLANGWINI PRIMARY SCHOOL | 500168017 | Jozini | Design | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182414 | DB/500310467/WS | KwaZulu-Natal | ISIVUNGUVUNGU HIGH SCHOOL | 500310467 | Jozini | Design | Active - Not Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 432000 | 432000 | 864000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182415 | DB/500169423/WS | KwaZulu-Natal | ISULOMNDENI PRIMARY SCHOOL | 500169423 | Mtubatuba | Construction 26% - 50% | Active - Not Contracted | 2016-06-06 | 2021-07-26 | 2024-03-30 | 2024-03-09 | 2025-06-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182416 | DB/500314611/WS | KwaZulu-Natal | JULUKANI JUNIOR PRIMARY SCHOOL | 500314611 | Umhlabuyalingana | Design | Active - Not Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182417 | DB/500174825/WS | KwaZulu-Natal | KHONYA JUNIOR PRIMARY SCHOOL | 500174825 | Jozini | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2018-09-12 | 2023-03-30 | 2024-05-05 | 2025-04-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182419 | P9006528_ | Eastern Cape | NOMSA FRANS PRIMARY SCHOOL (hostel) | 200200825 | Inxuba Yethemba | Feasibility | Active - Not Contracted | 2019-03-01 |  | 2026-03-31 |  |  | 11845435 | 149180400 | 161025835 | Education Infrastructure Grant | Upgrading and Additions
|  | 182422 | P9007301_ | Eastern Cape | TSOLO SPECIAL SCHOOL - Water | 200401385 | Mhlontlo | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2018-09-06 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1751834 | 4075009 | 5826843 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182442 | MDOE/UPG/154/19-20(DPWRT/178/19/MP) | Mpumalanga | Hlabangemehlo Primary School | 800005173 | Chief Albert Luthuli | Site Handed - Over to Contractor | Active - Contracted | 2019-07-01 | 2021-03-09 | 2023-03-31 | 2023-11-29 | 2023-09-29 | 439638 | 3140271 | 3579909 | Education Infrastructure Grant | Upgrading and Additions
|  | 182444 | MDOE/UPG/155/19-20(DPWRT/179/19) | Mpumalanga | Siyabonga Primary School | 800021451 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2019-07-01 | 2020-01-28 | 2023-06-30 | 2020-06-30 | 2023-03-31 | 551781 | 3941290 | 4493071 | Education Infrastructure Grant | Upgrading and Additions
|  | 182448 | MDOE/UPG/156/19-20(DPWRT/180/19/MP ) | Mpumalanga | Siphumelele Secondary School | 800021287 | Msukaligwa | Terminated | Active - Contracted | 2019-07-01 | 2019-10-28 | 2023-05-31 | 2023-04-30 | 2023-01-31 | 506733 | 3378218 | 3884951 | Education Infrastructure Grant | Upgrading and Additions
|  | 182449 | P9006934_ | Eastern Cape | ZANDISE JUNIOR PRIMARY SCHOOL | 200401168 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3731057 | 3731057 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182451 | P9007304_ | Eastern Cape | HEALDTOWN COMPREHENSIVE SCHOOL - Water | 200100296 | Raymond Mhlaba | Construction 76% - 99% | Active - Not Contracted | 2017-06-19 | 2017-08-07 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8615992 | 8615992 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182452 | P9006935_ | Eastern Cape | GQIRA JUNIOR SECONDARY SCHOOL | 200401250 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4971331 | 4971331 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182486 | P9006936_ | Eastern Cape | HLAMVANA JUNIOR SECONDARY SCHOOL | 200400265 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2026-03-31 | 2020-03-31 | 2025-03-31 | 0 | 9025072 | 9025072 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182489 | P9006937_ | Eastern Cape | JOKWANA JUNIOR SECONDARY SCHOOL | 200400289 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8174236 | 8174236 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182576 | P9006941_ | Eastern Cape | MAGILA SENIOR PRIMARY SCHOOL | 200400450 | Nyandeni | Construction 26% - 50% | Active - Contracted | 2018-04-01 | 2019-04-10 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 4761259 | 4761259 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182579 | P9007268_ | Eastern Cape | SMUTS NDAMASE SENIOR SECONDARY SCHOOL (Hostel) | 200500076 | King Sabata Dalindyebo | Feasibility | Active - Not Contracted | 2018-11-01 |  | 2026-03-31 |  |  | 23499607 | 231671859 | 255171466 | Education Infrastructure Grant | Upgrading and Additions
|  | 182643 | P9007252_ | Eastern Cape | NYANDENI JUNIOR SECONDARY SCHOOL | 200404017 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 751181 | 3926753 | 4677934 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182644 | MDOE/UPG/163/19-20(DPWRT/187/19/MP) | Mpumalanga | Mp Magagula Primary School | 800026708 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-07-01 | 2020-02-20 | 2023-08-31 | 2023-10-27 | 2023-10-27 | 455592 | 3037277 | 3492869 | Education Infrastructure Grant | Upgrading and Additions
|  | 182647 | P9007055_ | Eastern Cape | NGONYAMENI SENIOR PRIMARY SCHOOL | 200400230 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3813614 | 3813614 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182649 | P9006995_ | Eastern Cape | NDOFELA JUNIOR SECONDARY SCHOOL | 200600557 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 823962 | 4939238 | 5763200 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182650 | MDOE/UPG/164/19-20(DPWRT/188/19/MP) | Mpumalanga | Inkaba Primary School (farm school) | 800006361 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-10-01 | 2019-12-02 | 2023-03-31 | 2020-06-30 | 2023-06-30 | 305715 | 2038099 | 2343814 | Education Infrastructure Grant | Upgrading and Additions
|  | 182653 | P9006947_ | Eastern Cape | NOWALALA JUNIOR SECONDARY SCHOOL | 200500943 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-10 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1830064 | 1830064 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182711 | P9006980_ | Eastern Cape | EKUZOLENI SENIOR PRIMARY SCHOOL | 200600164 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3433716 | 3433716 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182712 | P9006948_ | Eastern Cape | SILASVILLE SENIOR PRIMARY SCHOOL | 200501109 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2998210 | 2998210 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182713 | P9006949_ | Eastern Cape | RWANTSANA JUNIOR SECONDARY SCHOOL | 200501071 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1784912 | 1784912 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182714 | W/500325119/SDS | KwaZulu-Natal | KWAQONDILE JUNIOR PRIMARY SCHOOL | 500325119 | Jozini | Design | Active - Contracted | 2018-05-02 |  | 2024-11-30 |  |  | 1087200 | 4952800 | 6040000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182717 | MDOE/UPG/166/19-20(DPWRT/190/19/MP) | Mpumalanga | Lamagadlela Primary School | 800009787 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-06-03 | 2019-10-23 | 2023-05-31 | 2020-06-30 | 2023-02-23 | 550013 | 3356222 | 3906235 | Education Infrastructure Grant | Upgrading and Additions
|  | 182718 | MDOE/UPG/166/19-20(DPWRT/191/19/MP). | Mpumalanga | Letsakuthula Primary School | 500186221 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2020-02-03 | 2020-02-04 | 2023-04-05 | 2023-04-05 | 2023-04-05 | 346210 | 2019385 | 2365595 | Education Infrastructure Grant | Upgrading and Additions
|  | 182719 | MDOE/UPG/168/19-20(DPWRT/192/19/MP) | Mpumalanga | Soko Primary School | 800021980 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-06-05 | 2019-10-24 | 2023-05-31 | 2023-02-24 | 2023-06-24 | 358320 | 2098817 | 2457137 | Education Infrastructure Grant | Upgrading and Additions
|  | 182721 | MDOE/UPG/170/19-20(DPWRT/194/19/MP) | Mpumalanga | Warburton Primary School | 800025213 | Msukaligwa | Construction 1% - 25% | Active - Contracted | 2019-04-17 | 2019-04-24 | 2023-06-30 | 2020-10-24 | 2023-06-30 | 560781 | 3426856 | 3987637 | Education Infrastructure Grant | Upgrading and Additions
|  | 182723 | MDOE/UPG/172/19-20(DPWRT/196/19/MP) | Mpumalanga | Ziwelile Primary School (farm school) | 800034782 | Mkhondo | Practical Completion (100%) | Active - Contracted | 2019-12-10 | 2020-07-10 | 2023-03-31 | 2020-10-10 | 2023-03-31 | 464260 | 1077356 | 1541616 | Education Infrastructure Grant | Upgrading and Additions
|  | 182724 | MDOE/UPG/173/19-20(DPWRT/197/19/MP) | Mpumalanga | Vuka Primary School | 800024760 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2019-07-07 | 2020-02-15 | 2023-09-30 | 2020-09-15 | 2023-06-30 | 258912 | 2157600 | 2416512 | Education Infrastructure Grant | Upgrading and Additions
|  | 182726 | MDOE/UPG/175/19-20( DPWRT/199/19/MP ) | Mpumalanga | Madzanga Primary School | 800011403 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2019-10-24 | 2023-03-31 | 2020-04-30 | 2023-05-29 | 219781 | 1831506 | 2051287 | Education Infrastructure Grant | Upgrading and Additions
|  | 182733 | MDOE/UPG/1001/22-23(TBC) | Mpumalanga | George Hofmeyer Special School | 80000000000 | Govan Mbeki | Design | Active - Not Contracted | 2021-11-01 |  | 2024-08-31 |  |  | 684000 | 3800000 | 4484000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182737 | MDOE/UPG/1004/19-20(TBC) | Mpumalanga | Vaalrivier Special School | 800005983 | Lekwa | Design | Active - Not Contracted | 2021-05-01 |  | 2024-05-16 |  |  | 1769057 | 9828092 | 11597149 | Education Infrastructure Grant | Upgrading and Additions
|  | 182744 | MDOE/SAN/158/2020 (DPWRT/SAN/327/20/MP) | Mpumalanga | Blesbokspruit Primary School | 800001149 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2021-09-02 | 2021-09-10 | 2022-09-15 | 2022-09-15 | 2022-09-15 | 225000 | 1080000 | 1305000 | Education Infrastructure Grant | Upgrading and Additions
|  | 182755 | P9006950_ | Eastern Cape | ELUNCEDWENI JUNIOR PRIMARY SCHOOL | 200500172 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1589276 | 1589276 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182783 | P9013238 | Eastern Cape | LINDUBUHLE JUNIOR SECONDARY SCHOOL | 200400360 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2016-09-13 | 2017-05-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 10934 | 546724 | 557658 | Education Infrastructure Grant | Upgrading and Additions
|  | 182798 | P9006955_ | Eastern Cape | COLA JUNIOR SECONDARY SCHOOL | 200500096 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 515602 | 2597830 | 3113432 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182801 | P9006958/ | Eastern Cape | NOLUTHANDO SENIOR PRIMARY SCHOOL | 200500925 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 478233 | 2390227 | 2868460 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182808 | P9006962_ | Eastern Cape | MCUTU PRIMARY JUNIOR SCHOOL | 200400555 | Engcobo | Construction 51% - 75% | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3800554 | 3800554 | Education Infrastructure Grant | Maintenance and Repairs
|  | 182822 | P9011005 | Eastern Cape | RUBUSANA DISTRICT OFFICE | 200999925 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2017-04-03 | 2019-09-19 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 19970 | 19970 | Education Infrastructure Grant | Upgrading and Additions
|  | 183137 | LE20IDT00161 | Limpopo | MAPHADIME SECONDARY | 924641258 | Makhuduthamaga | Feasibility | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 59000 | 238000 | 297000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183139 | LE21DPW00005 | Limpopo | Piet Hugo Primary School | 904220439 | Polokwane | Feasibility | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 5916257 | 23665028 | 29581285 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183140 | EDDP184/323 | Limpopo | Ndzalama Primary School | 916410751 | Greater Giyani | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2000000 | 8000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183146 | LE19DPW00086 | Limpopo | St. Paul Secondary School | 924650740 | Elias Motsoaledi | Design | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 11018857 | 44075428 | 55094285 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183148 | LE19DPW00104 | Limpopo | Tlharihani Primary | 916411129 | Greater Giyani | Feasibility | Active - Not Contracted | 2020-01-04 |  | 2026-03-31 |  |  | 4000000 | 16000000 | 20000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 183155 | LE20IDT09019 | Limpopo | Mashwele Primary School | 996605100 | Greater Tubatse/Fetakgomo | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2948000 | 14740000 | 17688000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183230 | P9008280_ | Eastern Cape | LINGOMSO LETHU SPECIAL SCHOOL | 200300144 | Mnquma | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8287150 | 8287150 | Education Infrastructure Grant | Upgrading and Additions
|  | 183342 | MDOE/NEW/19-20/006 | Mpumalanga | New Mbombela City Primary School | New | Mbombela | Feasibility | Active - Not Contracted | 2019-03-02 |  | 2026-03-15 |  |  | 7852424 | 43624576 | 51477000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 183350 | EDDP184/309 | Limpopo | Mathede Secondary | 928331469 | Makhado | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2019-04-06 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2400000 | 9600000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183356 | EDDP184/350 | Limpopo | TSHAMISEKA PRIMARY | 911360795 | Collins Chabane | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 1580200 | 6320800 | 7901000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183361 | EDDP184/351 | Limpopo | tshehlwaneng secondary | 925661351 | Makhuduthamaga | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2016-12-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 6065400 | 24261600 | 30327000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183363 | LE20IDT09021 | Limpopo | MMAKGOTLO PRIMARY SCHOOL | 926540812 | Greater Tzaneen | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2470000 | 9880000 | 12350000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183375 | LE20IDT09022 | Limpopo | MOHLOPING PRIMARY | 925630876 | Greater Tubatse/Fetakgomo | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1700000 | 6800000 | 8500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183416 | MDOE/SAN/270/2020 | Mpumalanga | Ezenzeleni Primary School | 800004135 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-31 |  |  | 330000 | 1980000 | 2310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183417 | DPWRT/SAN/321/20MP GOEBRAM--------------- | Mpumalanga | Goebram Primary School | 800004580 | Chief Albert Luthuli | Design | Active - Not Contracted | 2021-05-01 |  | 2022-09-15 |  |  | 225000 | 1350000 | 1575000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183420 | MDOE/SAN/272/2020 | Mpumalanga | Ithafa Comprehensive School | 800006809 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-31 |  |  | 495000 | 2970000 | 3465000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183423 | MDOE/SAN/276/2020 | Mpumalanga | Langelihle Primary School | 800009894 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-31 |  |  | 330000 | 1980000 | 2310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183424 | MDOE/SAN/278/2020 | Mpumalanga | Madola Primary School | 800011361 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-28 |  |  | 225000 | 1350000 | 1575000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183425 | DPWRT/SAN/006/22MP(MLAMBONGWANE --------- | Mpumalanga | Mlambongwane Primary School | 800014498 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-10-01 |  |  | 225000 | 1350000 | 1575000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183426 | MDOE/SAN/279/2020 | Mpumalanga | Nalithuba Secondary School | 800016238 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-31 |  |  | 360000 | 2160000 | 2520000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183428 | MDOE/SAN/280/2020 | Mpumalanga | Phembindlela Primary School | 800018242 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2022-05-31 |  |  | 330000 | 1980000 | 2310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183429 | MDOE/SAN/135/2020( DPWRT/SAN/195/20/MP ) | Mpumalanga | Phumulani Primary School | 800018432 | Msukaligwa | Tender | Active - Contracted | 2019-05-01 |  | 2022-06-16 |  |  | 1470000 | 2488635 | 3958635 | Education Infrastructure Grant | Upgrading and Additions
|  | 183430 | EDDP184/38 | Limpopo | GEORGE MORAGULA SECONDARY | 922220187 | Polokwane | Construction 76% - 99% | Active - Contracted | 2017-04-01 | 2017-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 3255200 | 13020800 | 16276000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183433 | MDOE/SAN/248/2020(DPWRT/SAN/220/20MP) | Mpumalanga | Sakhisizwe Primary School | 800019737 | Govan Mbeki | Construction 76% - 99% | Active - Contracted | 2021-05-01 |  | 2022-09-15 |  |  | 315000 | 2250000 | 2565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183436 | MDOE/NEW/19-20/005(TBC) | Mpumalanga | Shapeve Primary School | 800020461 | Msukaligwa | Design | Active - Not Contracted | 2019-05-01 |  | 2025-04-30 |  |  | 7852424 | 44807576 | 52660000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 183438 | MDOE/SAN/256/2020(DPWRT/SAN/218/20/MP) | Mpumalanga | Camden Combined School | 800001883 | Msukaligwa | Site Handed - Over to Contractor | Active - Contracted | 2021-05-01 |  | 2023-10-01 |  |  | 226800 | 1620000 | 1846800 | Education Infrastructure Grant | Upgrading and Additions
|  | 183439 | MDOE/UPG/1016/20-21( DPWRT/SAN/200/20/MP ) | Mpumalanga | Thandeka Primary School | 800022947 | Msukaligwa | Tender | Active - Contracted | 2019-05-01 |  | 2022-11-30 |  |  | 289942 | 1535887 | 1825829 | Education Infrastructure Grant | Upgrading and Additions
|  | 183444 | DPWRT/SAN/180/20MP(UMLAMBO PRIM)--------- | Mpumalanga | Umlambo Combined School | 800024323 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2021-04-01 | 2021-04-02 | 2023-05-17 | 2023-05-17 | 2023-05-17 | 352000 | 2160000 | 2512000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183446 | LE20IDT00162 | Limpopo | RIVONI SCHOOL FOR THE BLIND | 929332041 | Makhado | Construction 1% - 25% | Active - Not Contracted | 2019-03-01 |  | 2024-03-31 |  |  | 4800000 | 19200000 | 24000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183447 | MDOE/SAN/289/2020 | Mpumalanga | Uthaka Secondary School | 800029926 | Msukaligwa | Project Initiation | Active - Not Contracted | 2019-05-01 |  | 2024-03-31 |  |  | 38980 | 378425 | 417405 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183449 | MDOE/SAN/160/2020(DPWRT/SAN/326/20/MP) | Mpumalanga | Vulingcondvo Primary School | 800025015 | Msukaligwa | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 285000 | 1710000 | 1995000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183450 | LE20IDT09023 | Limpopo | Ndlhavheya Primary (Project relocated from Mutsetweni) | 912520771 | Collins Chabane | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1600000 | 6400000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183456 | MDOE/SAN/295/2020 | Mpumalanga | Buhlebuyeza Primary School | 800034454 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2023-04-30 |  |  | 213921 | 2070000 | 2283921 | Education Infrastructure Grant | Upgrading and Additions
|  | 183458 | LE20IDT09024 | Limpopo | Nhombelani Primary | 911360740 | Collins Chabane | Feasibility | Active - Not Contracted | 2019-06-30 |  | 2024-03-31 |  |  | 1800000 | 7200000 | 9000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183460 | MDOE/SAN/297/2020 | Mpumalanga | Lusushwana Secondary School | 800010884 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2019-05-01 |  | 2024-03-31 |  |  | 168885 | 1350000 | 1518885 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183461 | LE20IDT09010 | Limpopo | LORRAINE BANARENG PRIMARY SCHOOL | 926540683 | Maruleng | Final Completion | Active - Contracted | 2019-06-30 | 2020-04-01 | 2024-03-24 | 2024-03-24 | 2024-03-24 | 800000 | 3200000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183478 | LE20IDT09025 | Limpopo | Ramatsetse Primary | 996606624 | Elias Motsoaledi | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1700000 | 6800000 | 8500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183486 | LE20IDT09026 | Limpopo | Reahlahlwa Combined School | 907111832 | Modimolle/Mookgophong | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 510000 | 2040000 | 2550000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183505 | LE20IDT09028 | Limpopo | Sigonde primary | 929310264 | Musina | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1500000 | 6000000 | 7500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183518 | LE20IDT09029 | Limpopo | St. Josefs Technical Secondary School | 996606608 | Elias Motsoaledi | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2400000 | 9600000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183520 | LE20TMT17047 | Limpopo | Muhuvhini Primary | 993306400 | Collins Chabane | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 3860000 | 15440000 | 19300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183525 | LE20IDT09032 | Limpopo | Tibanefontein Primary | 922251679 | Polokwane | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2240000 | 8960000 | 11200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183532 | LE20IDT09003 | Limpopo | Florapark Comprehensive Primary School | 922223292 | Makhado | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1080000 | 4320000 | 5400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183535 | LE20IDT09004 | Limpopo | Frederick Langa Secondary School | 991101102 | Modimolle/Mookgophong | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2400000 | 9600000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183537 | LE20IDT09013 | Limpopo | Madzikuse Primary School | 911360405 | Collins Chabane | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2116000 | 8464000 | 10580000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183539 | LE20IDT09015 | Limpopo | MAILA -2 Primary School | 931340203 | Makhado | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1900000 | 7600000 | 9500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183541 | LE20IDT09016 | Limpopo | MAKGOATHANE PRIMARY | 923260574 | Lepele-Nkumpi | Feasibility | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2768000 | 11072000 | 13840000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183542 | LE20IDT09006 | Limpopo | Hatlani Muyexe Secondary School | 916410218 | Makhado | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 1690000 | 6760000 | 8450000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183544 | LE20IDT09017 | Limpopo | MALEMATI SCHOOL | 923260604 | Lepele-Nkumpi | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 4168000 | 16672000 | 20840000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183568 | W/500101972/WS | KwaZulu-Natal | AMANDOSI PRIMARY SCHOOL | 500101972 | uMhlathuze | Tender | Active - Contracted | 2016-06-13 |  | 2026-06-30 |  |  | 1462500 | 6662500 | 8125000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183583 | W/500102527/WS | KwaZulu-Natal | AMAQHAWE PRIMARY SCHOOL | 500102527 | Jozini | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2019-02-01 | 2023-06-30 | 2023-03-31 | 2024-05-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183590 | LE20IDT09033 | Limpopo | Tshapinda Primary | 929310073 | Musina | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2020000 | 8080000 | 10100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183603 | LE20IDT09034 | Limpopo | Unity Primary | 995503401 | Greater Tzaneen | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2400000 | 9600000 | 12000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183611 | P9008605_ | Eastern Cape | HOLOMISA SENIOR SECONDARY SCHOOL | 200100367 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-09 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 168044 | 864970 | 1033014 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183628 | P9008607_ | Eastern Cape | ZIBUZELE JUNIOR SECONDARY SCHOOL | 200401307 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-09 | 2023-03-31 | 2025-03-31 | 2025-03-31 | 527697 | 3107424 | 3635121 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183634 | P9008609_ | Eastern Cape | SITETO PRIMARY SCHOOL | 200401356 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 101511 | 597123 | 698634 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183641 | P9008611_ | Eastern Cape | KUYASA PRIMARY SCHOOL | 200400337 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-09 | 2025-03-31 | 2018-08-09 | 2025-03-01 | 541386 | 2901044 | 3442430 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183648 | P9008615_ | Eastern Cape | JUMBA SENIOR SCONDARY SCHOOL | 200401269 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2026-03-31 | 2026-03-01 | 410947 | 2417335 | 2828282 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183649 | DB/SAFE/500104636/WS | KwaZulu-Natal | BABAZANI PRIMARY SCHOOL | 500104636 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-03-01 | 2024-03-30 | 2024-03-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183655 | P9008616_ | Eastern Cape | LYNDALE PRIMARY SCHOOL | 200400427 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 117958 | 693872 | 811830 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183656 | DB/500173419/WS | KwaZulu-Natal | KHANYA HIGH SCHOOL | 500173419 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2022-01-01 | 2022-09-12 | 2024-12-01 | 2024-05-05 | 2025-04-20 | 127080 | 578920 | 706000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183659 | P9008617_ | Eastern Cape | LUTHUTHU PRIMARY SCHOOL | 200400420 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-09 | 2025-03-31 | 2025-03-31 | 2026-03-01 | 187702 | 1104132 | 1291834 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183675 | P9009655_ | Eastern Cape | LONWABO SENIOR SECONDARY SCHOOL | 200100462 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2018-04-02 | 2019-05-08 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 2117901 | 2117901 | Education Infrastructure Grant | Upgrading and Additions
|  | 183679 | P9008622_ | Eastern Cape | NKANTSINI JUNIOIR SECONDARY SCHOOL | 200500522 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 511962 | 3011711 | 3523673 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183683 | P9008623. | Eastern Cape | MIRRLEES JUNIOR SECONDARY SCHOOL | 200200539 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 419076 | 2465157 | 2884233 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183689 | P9008624. | Eastern Cape | QENGQELEKA PRIMARY JUNIOR SCHOOL | 200400942 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 554472 | 3261604 | 3816076 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183702 | P9008626_ | Eastern Cape | SIPETU JUNIOR SECONDARY SCHOOL | 200200706 | Ntabankulu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2023-03-01 | 2024-03-01 | 2025-03-31 | 237932 | 1468720 | 1706652 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183704 | W/500107966/WS | KwaZulu-Natal | BHANDE HIGH SCHOOL | 500107966 | Alfred Duma | Design | Active - Not Contracted | 2016-06-14 |  | 2024-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183708 | LE19TMT17003 | Limpopo | Benson Shiviti Primary | 916410041 | Greater Giyani | Construction 1% - 25% | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 307000 | 1228000 | 1535000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183710 | W/500115329/WS | KwaZulu-Natal | CELIMFUNDO PRIMARY SCHOOL (WINTERTON) | 500115366 | Inkosi Langalibalele | Tender | Proposed | 2016-06-06 |  | 2023-06-30 |  |  | 432000 | 2655000 | 3087000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183711 | P9009663_ | Eastern Cape | TALENI JUNIOR SECONDARY SCHOOL | 200300584 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 293014 | 2092056 | 2385070 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183715 | P9008560_ | Eastern Cape | SIGCAU SPECIAL SCHOOL | 200501591 | Ingquza Hill | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2019-04-11 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1853905 | 1084269 | 2938174 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183717 | W/500116402/WS | KwaZulu-Natal | CHIEF LOKOTHWAYO PRIMARY SCHOOL | 500116402 | eThekwini | Construction 76% - 99% | Active - Contracted | 2016-06-15 | 2019-06-10 | 2023-03-21 | 2023-11-30 | 2024-11-30 | 482922 | 2648078 | 3131000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183718 | P9009664_ | Eastern Cape | LUDONDOLO JUNIOR SECONDARY SCHOOL | 200300237 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2018-06-01 | 2026-03-31 | 2021-03-31 | 2025-03-31 | 128989 | 819347 | 948336 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183720 | P9008563_ | Eastern Cape | LA-GRANGE SENIOR SECONDARY SCHOOL - Water (Phase I) | 200501091 | Matatiele | Design | Active - Not Contracted | 2019-03-28 |  | 2026-03-31 |  |  | 0 | 5262456 | 5262456 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183721 | W/500121323/WS | KwaZulu-Natal | DINABANYE PRIMARY SCHOOL | 500121323 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-03-04 | 2019-02-01 | 2023-06-30 | 2023-03-31 | 2024-05-31 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183725 | I/500105006/WS | KwaZulu-Natal | BAMBANANI H | 500105006 | uPhongolo | On Hold | Active - Not Contracted | 2019-05-06 |  | 2024-03-31 |  |  | 58000 | 44500 | 102500 | Education Infrastructure Grant | Upgrading and Additions
|  | 183727 | W/500424501/WS | KwaZulu-Natal | DUMAKUDE SECONDARY SCHOOL | 500424501 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2017-04-06 | 2019-02-01 | 2023-06-30 | 2020-03-31 | 2022-05-31 | 54000 | 246000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183728 | C/500102749/UA | KwaZulu-Natal | AMATIKWE PRIMARY SCHOOL | 500102749 | The Msunduzi | On Hold | Active - Not Contracted | 2019-05-10 |  | 2024-12-31 |  |  | 684000 | 3570000 | 4254000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183729 | DB/500137455/SDS | KwaZulu-Natal | ENJABULWENI PRIMARY SCHOOL | 500137455 | uMlalazi | Design | Active - Not Contracted | 2018-06-02 |  | 2024-03-30 |  |  | 1270269 | 5786782 | 7057051 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183730 | I/500108003/WS | KwaZulu-Natal | BHAQA PRIMARY SCHOOL | 500108003 | Richmond | Tender | Active - Contracted | 2019-05-03 |  | 2023-03-30 |  |  | 45000 | 102000 | 147000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183731 | I/500423798/WS | KwaZulu-Natal | BONGINCEBA SENIOR PRIMARY SCHOOL | 500423798 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2019-05-06 | 2019-09-18 | 2023-03-31 | 2022-04-12 | 2023-04-15 | 821000 | 3012000 | 3833000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183732 | LE19TMT17005 | Limpopo | David Nkoana Primary | 922222459 | Polokwane | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 283378 | 3579040 | 3862418 | Education Infrastructure Grant | Upgrading and Additions
|  | 183733 | W/500334961/WS | KwaZulu-Natal | DUMANE COMM HIGH SCHOOL | 500334961 | Ndwedwe | Tender | Active - Not Contracted | 2019-03-04 |  | 2023-06-30 |  |  | 808104 | 3681364 | 4489468 | Education Infrastructure Grant | Upgrading and Additions
|  | 183736 | ET/500225071/WS | KwaZulu-Natal | NDIMOSE PRIMARY SCHOOL | 500225071 | eThekwini | Construction 51% - 75% | Active - Contracted | 2018-08-01 | 2023-04-27 | 2023-04-27 | 2024-04-27 | 2025-04-27 | 855807 | 3898677 | 4754484 | Education Infrastructure Grant | Upgrading and Additions
|  | 183737 | LE19TMT17007 | Limpopo | DINAO SECONDARY | 923260130 | Lepele-Nkumpi | Construction 1% - 25% | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 46575 | 3060134 | 3106709 | Education Infrastructure Grant | Upgrading and Additions
|  | 183738 | W/500445591/WS | KwaZulu-Natal | ELOMO PRIMARY SCHOOL | W/500445591/WS | Nkandla | Tender | Active - Contracted | 2019-02-20 |  | 2024-03-30 |  |  | 100000 | 100000 | 200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183739 | W/500130351/WS | KwaZulu-Natal | EMAFA PRIMARY SCHOOL | 500130351 | Umhlabuyalingana | Practical Completion (100%) | Active - Contracted | 2018-01-04 | 2019-05-01 | 2023-06-30 | 2023-03-31 | 2024-05-31 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183740 | LE19TMT17010 | Limpopo | Gidjana Secondary | 911361262 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 475306 | 4483387 | 4958693 | Education Infrastructure Grant | Upgrading and Additions
|  | 183742 | LE19TMT17011 | Limpopo | Gogogo Primary | 929311083 | Thulamela | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 448944 | 3970160 | 4419104 | Education Infrastructure Grant | Upgrading and Additions
|  | 183743 | I/500130684/WS | KwaZulu-Natal | EMAHLEKWANE JUNIOR PRIMARY SCHOOL | 500130684 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2018-07-11 | 2019-01-23 | 2022-08-21 | 2022-10-23 | 2023-03-31 | 48000 | 182000 | 230000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183744 | LE19TMT17131 | Limpopo | Mapitikana Primary | 921140625 | Mogalakwena | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 280000 | 1120000 | 1400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183745 | LE19TMT17012 | Limpopo | Hlagatse Primary | 923260208 | Lepele-Nkumpi | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 5645194 | 5645194 | Education Infrastructure Grant | Upgrading and Additions
|  | 183747 | LE19TMT17014 | Limpopo | Ikageleng Makobe Primary | 922251716 | Polokwane | Construction 51% - 75% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 624917 | 4983389 | 5608306 | Education Infrastructure Grant | Upgrading and Additions
|  | 183748 | LE19TMT17132 | Limpopo | Rantjie Lower Primary | 921141154 | Mogalakwena | Tender | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 388000 | 1552000 | 1940000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183749 | LE19TMT17015 | Limpopo | Boxahuku Primary | 911360368 | Molemole | Design | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 400000 | 1600000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183751 | LE19TMT17133 | Limpopo | HLANEKI PRIMARY | 916410263 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 621505 | 4887262 | 5508767 | Education Infrastructure Grant | Upgrading and Additions
|  | 183752 | LE19TMT17017 | Limpopo | Ivy Park Primary School | 904222619 | Molemole | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 720000 | 2880000 | 3600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183755 | LE19TMT17019 | Limpopo | Kgwadu Primary | 919340791 | Molemole | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2023-03-31 |  |  | 0 | 8591019 | 8591019 | Education Infrastructure Grant | Upgrading and Additions
|  | 183756 | LE19TMT17121 | Limpopo | Chuchekani Primary School | 917420055 | Ba-Phalaborwa | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 884800 | 3539200 | 4424000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183757 | LE19TMT17020 | Limpopo | Khomanani Mbhalati Secondary | 916410393 | Collins Chabane | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 120000 | 480000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183759 | LE19TMT17021 | Limpopo | KHUDU HIGH | 926540072 | Maruleng | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 0 | 8148837 | 8148837 | Education Infrastructure Grant | Upgrading and Additions
|  | 183760 | LE19TMT17022 | Limpopo | Konoto Primary | 923240235 | Polokwane | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 5223402 | 5223402 | Education Infrastructure Grant | Upgrading and Additions
|  | 183761 | LE19TMT17122 | Limpopo | HIPAMBUKILE PRIMARY SCHOOL | 916410249 | Greater Giyani | Construction 51% - 75% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 5824567 | 5824567 | Education Infrastructure Grant | Upgrading and Additions
|  | 183762 | LE19TMT17023 | Limpopo | Ladzani Primary | 929310622 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 278000 | 1112000 | 1390000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183763 | LE19TMT17024 | Limpopo | Leakhale Primary | 918510194 | Greater Letaba | Design | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 536000 | 5000000 | 5536000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183765 | LE19TMT17025 | Limpopo | Lebeko Secondary | 913420192 | Ba-Phalaborwa | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 672000 | 2688000 | 3360000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183766 | LE19TMT17026 | Limpopo | Lekentle Secondary | 925610025 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 401474 | 4155637 | 4557111 | Education Infrastructure Grant | Upgrading and Additions
|  | 183769 | LE19TMT17027 | Limpopo | M.E Makgato Secondary School | 922220804 | Molemole | Construction 51% - 75% | Active - Contracted | 2019-04-01 |  | 2023-03-31 |  |  | 310607 | 2995693 | 3306300 | Education Infrastructure Grant | Upgrading and Additions
|  | 183770 | LE19TMT17028 | Limpopo | Madzikuse Primary School | 911360405 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 480757 | 4158396 | 4639153 | Education Infrastructure Grant | Upgrading and Additions
|  | 183774 | LE19TMT17030 | Limpopo | Maila 2 Primary | 931340203 | Makhado | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 4799965 | 4799965 | Education Infrastructure Grant | Upgrading and Additions
|  | 183776 | LE19TMT17031 | Limpopo | Makaepea Primary 2 | 924650092 | Elias Motsoaledi | Final Completion | Active - Contracted | 2019-04-01 |  | 2023-03-31 |  |  | 363259 | 3476744 | 3840003 | Education Infrastructure Grant | Upgrading and Additions
|  | 183777 | LE19TMT17032 | Limpopo | Makhwese Secondary | 925620480 | Greater Tubatse/Fetakgomo | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 432752 | 4248898 | 4681650 | Education Infrastructure Grant | Upgrading and Additions
|  | 183778 | LE19TMT17033 | Limpopo | Malenga Secondary | 916410546 | Ba-Phalaborwa | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 345000 | 1380000 | 1725000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183779 | LE19TMT17034 | Limpopo | Mapani Primary School | 928331896 | Musina | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 487169 | 4649158 | 5136327 | Education Infrastructure Grant | Upgrading and Additions
|  | 183780 | LE19TMT17035 | Limpopo | Marobala Primary | 923240730 | Polokwane | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 317255 | 3461330 | 3778585 | Education Infrastructure Grant | Upgrading and Additions
|  | 183781 | LE19TMT17091 | Limpopo | Mainganya Secondary School | 931341008 | Makhado | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 603920 | 4075133 | 4679053 | Education Infrastructure Grant | Upgrading and Additions
|  | 183782 | LE19TMT17039 | Limpopo | MKHACHANI MZAMANI PRIMARY | 915530013 | Collins Chabane | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 504000 | 2016000 | 2520000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183783 | LE19TMT17092 | Limpopo | Mutshalingana Primary School | 930350828 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 340000 | 1360000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183808 | LE19TMT17046 | Limpopo | Nakonkwetlou Secondary | 921140908 | Mogalakwena | Construction 26% - 50% | Active - Contracted | 2019-03-31 |  | 2024-03-31 |  |  | 0 | 4058624 | 4058624 | Education Infrastructure Grant | Upgrading and Additions
|  | 183809 | LE19TMT17049 | Limpopo | Nwaxinyamani Primary | 912520856 | Makhado | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 169000 | 676000 | 845000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183810 | LE19TMT17050 | Limpopo | Nweli Primary | 930350651 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 262000 | 1048000 | 1310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183816 | I/500142413/WS | KwaZulu-Natal | ETONGWE PRIMARY SCHOOL | 500142413 | Umvoti | Practical Completion (100%) | Active - Contracted | 2018-06-20 | 2019-01-07 | 2023-07-18 | 2023-07-09 | 2023-03-31 | 68000 | 1280000 | 1348000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183820 | LE19TMT17052 | Limpopo | O.R Mabotja Secondary | 922221227 | Polokwane | Construction 1% - 25% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 310861 | 3379851 | 3690712 | Education Infrastructure Grant | Upgrading and Additions
|  | 183822 | I/500145669/WS | KwaZulu-Natal | FUMANA SECONDARY SCHOOL | 500145669 | Nongoma | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2020-03-05 | 2023-03-30 | 2023-05-10 | 2023-08-01 | 585000 | 2665000 | 3250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183825 | DB/500109002/WS | KwaZulu-Natal | BHEKIZWE PRIMARY SCHOOL | 500109002 | Umvoti | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2024-03-11 | 2024-03-30 | 2024-07-30 | 2025-05-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183826 | LE19TMT17055 | Limpopo | Ralson Tshinanne Secondary | 930351449 | Thulamela | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 360000 | 1440000 | 1800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183828 | P9008567_ | Eastern Cape | QWE QWE JUNIOR SECONDARY SCHOOL | 200401334 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-10 | 2025-03-31 | 2020-03-31 | 2025-03-01 | 532873 | 3134551 | 3667424 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183831 | P9008568_ | Eastern Cape | ZAMUKULUNGISA SENIOR SECONDARY SCHOOL | 200401166 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2020-02-10 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 477933 | 2811373 | 3289306 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183832 | DB/500111185/WS | KwaZulu-Natal | BONGINHLANHLA SECONDARY SCHOOL | 500111185 | uPhongolo | Tender | Active - Not Contracted | 2017-06-06 |  | 2025-03-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183833 | P9009572_ | Eastern Cape | MAQANDA PRIMARY JUNIOR SCHOOL | 200400496 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-08 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 0 | 3982434 | 3982434 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183835 | DB/500303918/WS | KwaZulu-Natal | CHOTHWANE PRIMARY SCHOOL | 500303918 | Inkosi Langalibalele | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2026-09-30 | 338380 | 1541510 | 1879890 | Education Infrastructure Grant | Upgrading and Additions
|  | 183836 | LE19TMT17056 | Limpopo | Rambuda Secondary | 929311588 | Thulamela | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 458349 | 4074654 | 4533003 | Education Infrastructure Grant | Upgrading and Additions
|  | 183837 | MDOE/MAIN/49/21-22 | Mpumalanga | Gert Sibande District Offices | 0 | Msukaligwa | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-15 |  |  | 552000 | 4600000 | 5152000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183839 | DB/500129426/WS | KwaZulu-Natal | EKWANDENI COMBINED SCHOOL | 500129426 | Ulundi | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2022-06-01 | 2024-03-30 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183841 | P9009668_ | Eastern Cape | NTLABANE JUNIOR SECONDARY SCHOOL | 200300512 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-15 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 549922 | 2115087 | 2665009 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183842 | P9008570_ | Eastern Cape | LOWER NGQWARA JUNIOR SECONDARY SCHOOL | 200400386 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2020-02-11 | 2025-03-01 | 571295 | 2946305 | 3517600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183843 | LE19TMT17057 | Limpopo | Ramokgabudi Secondary | 921121327 | Mogalakwena | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 930000 | 3720000 | 4650000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183846 | P9009577_ | Eastern Cape | NTSELENI PRIMARY JUNIOR SCHOOL | 200400867 | Engcobo | Construction 76% - 99% | Active - Contracted | 2018-04-01 | 2018-06-04 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 590950 | 3476176 | 4067126 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183847 | DB/500133755/WS | KwaZulu-Natal | EMOYENI PRIMARY SCHOOL | 500133718 | Mthonjaneni | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2019-01-15 | 2023-03-30 | 2019-07-14 | 2024-07-14 | 1398974 | 5262807 | 6661781 | Education Infrastructure Grant | Upgrading and Additions
|  | 183848 | LE19TMT17060 | Limpopo | Sebushi Secondary | 922221425 | Polokwane | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 246000 | 984000 | 1230000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183849 | LE19TMT17061 | Limpopo | Segaeng Secondary | 921230689 | Lepele-Nkumpi | Construction 51% - 75% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 3846310 | 3846310 | Education Infrastructure Grant | Upgrading and Additions
|  | 183850 | P9009796_ | Eastern Cape | KANTOLO JUNIOR SECONDARY SCHOOL | 200500345 | Mbizana | Design | Approved | 2020-08-01 |  | 2026-03-31 |  |  | 0 | 12145056 | 12145056 | Education Infrastructure Grant | Upgrading and Additions
|  | 183851 | DB/500127502/WS | KwaZulu-Natal | 3365 ENGUNJINI & 3353 MEMEZA BISI RIVER PEDESTRIAN BRIDGE | 3365 ENGUNJINI & 3353 MEMEZA BISI RIVER PEDESTRIAN BRIDGE | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2020-05-31 | 2023-01-31 | 2023-03-25 | 2027-03-30 | 214313 | 976313 | 1190626 | Education Infrastructure Grant | Upgrading and Additions
|  | 183853 | P9009671_ | Eastern Cape | KIDSTON PRIMARY JUNIOR SCHOOL | 200400326 | Engcobo | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-04-01 | 2026-03-31 | 2021-03-31 | 2025-03-31 | 338661 | 2419007 | 2757668 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183854 | DB/500140637/WS | KwaZulu-Natal | ESIKHUMBUZWENI SECONDARY SCHOOL | 500140637 | Nqutu | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183855 | P9008571_ | Eastern Cape | UPPER NGQWARA JUNIOR SECONDARY SCHOOL | 200401106 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 26185130 | 1586605 | 27771735 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183856 | DB/500147482/WS | KwaZulu-Natal | GCILIMA PRIMARY SCHOOL | 500147482 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-03-01 | 2024-03-30 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183858 | LE19TMT17062 | Limpopo | Shakadza Primary | 920311229 | Musina | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 490904 | 4690658 | 5181562 | Education Infrastructure Grant | Upgrading and Additions
|  | 183859 | W/500266659/SDS | KwaZulu-Natal | SINKONKONKO HIGH SCHOOL | 500266659 | Nongoma | Design | Active - Not Contracted | 2018-06-02 |  | 2023-06-30 |  |  | 1230480 | 5605520 | 6836000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183860 | DB/500114922/WS | KwaZulu-Natal | GEM NTSHEBE PRIMARY SCHOOL | 500114922 | Umzumbe | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183861 | LE19TMT17063 | Limpopo | Shavhani Primary | 930332356 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 234000 | 936000 | 1170000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183863 | DB/500148555/WS | KwaZulu-Natal | GIBA PRIMARY SCHOOL | 500148555 | Msinga | Tender | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183864 | LE19TMT17064 | Limpopo | Shondoni Secondary | 930320681 | Thulamela | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2021-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 64918 | 7790 | 72708 | Education Infrastructure Grant | Upgrading and Additions
|  | 183867 | LE19TMT17065 | Limpopo | St.Josefs Technical Secondary Schools | 9966066089 | Elias Motsoaledi | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 615000 | 2460000 | 3075000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183868 | P9009797_ | Eastern Cape | HOLY CROSS JUNIOR SECONDARY SCHOOL | 200500307 | Ingquza Hill | Design | Approved | 2018-08-01 |  | 2026-03-31 |  |  | 0 | 17383061 | 17383061 | Education Infrastructure Grant | Upgrading and Additions
|  | 183869 | DB/500150479/WS | KwaZulu-Natal | GODLOZA H | 500150479 | Big Five Hlabisa | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183871 | DB/500152736/WS | KwaZulu-Natal | GWALIWENI PRIMARY SCHOOL | 500152736 | Jozini | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183875 | DB/500152884/WS | KwaZulu-Natal | GWIJA PRIMARY SCHOOL | 500152884 | Nqutu | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-03-01 | 2024-03-30 | 2024-03-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183877 | LE19TMT17067 | Limpopo | Thaba Dora Primary | 923241436 | Polokwane | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 183878 | DB/500442150/WS | KwaZulu-Natal | HHOYE SECONDARY SCHOOL | 500442150 | Jozini | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2020-05-31 | 2023-01-31 | 2023-03-25 | 2027-03-30 | 443641 | 2021029 | 2464670 | Education Infrastructure Grant | Upgrading and Additions
|  | 183879 | P9008572_ | Eastern Cape | CEZU PRIMARY SCHOOL | 200400075 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-03-25 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 469048 | 2716634 | 3185682 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183880 | I/500184963/WS | KwaZulu-Natal | LALELA PRIMARY SCHOOL | 500184963 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2018-04-26 | 2018-07-30 | 2023-03-14 | 2023-07-26 | 2023-11-28 | 78000 | 1328000 | 1406000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183882 | DB/500156621/WS | KwaZulu-Natal | HLAZAKAZI SENIOR PRIMARY SCHOOL | 500156621 | Nqutu | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183885 | P9009578_ | Eastern Cape | PHAKAMANI PRIMARY SCHOOL | 200600997 | Emalahleni | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-06-07 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 492562 | 2897424 | 3389986 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183886 | LE19TMT17069 | Limpopo | Thinashaka Secondary | 930351333 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 505130 | 4506638 | 5011768 | Education Infrastructure Grant | Upgrading and Additions
|  | 183887 | DB/500441632/WS | KwaZulu-Natal | ZIPHOSHENI PRIMARY SCHOOL | 500441632 | Jozini | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183889 | LE19TMT17071 | Limpopo | Tlhona Sedimong Secondary | 920211886 | Blouberg | Construction 26% - 50% | Approved | 2019-04-01 |  | 2024-03-31 |  |  | 0 | 5875305 | 5875305 | Education Infrastructure Grant | Upgrading and Additions
|  | 183891 | P9008573_ | Eastern Cape | MAXWELE SENIOR SECONDARY SCHOOL | 200400518 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 171021 | 1122304 | 1293325 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183893 | DB/500163096/WS | KwaZulu-Natal | INGAQA PRIMARY SCHOOL | 500163096 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2020-05-31 | 2023-01-31 | 2023-03-25 | 2027-03-30 | 602528 | 2744850 | 3347378 | Education Infrastructure Grant | Upgrading and Additions
|  | 183894 | LE19TMT17098 | Limpopo | Lerale Primary School | 918510231 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 574305 | 4642826 | 5217131 | Education Infrastructure Grant | Upgrading and Additions
|  | 183896 | P9009676_ | Eastern Cape | DALIWONGA SENIOR SECONDARY SCHOOL | 200601092 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 783036 | 5400251 | 6183287 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183898 | LE19TMT17073 | Limpopo | Tshikambe Primary | 930350156 | Thulamela | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 178000 | 712000 | 890000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183900 | DB/500164280/WS | KwaZulu-Natal | INHLWATHI PRIMARY SCHOOL | 500164280 | Big Five Hlabisa | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183901 | LE19TMT17075 | Limpopo | Tshimedzwa Primary | 930350903 | Thulamela | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 262000 | 1048000 | 1310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183902 | DB/500166500/WS | KwaZulu-Natal | INTUTHUKOYAMAZULU P | 500166500 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-09-12 | 2023-01-31 | 2023-03-09 | 2027-06-15 | 342995 | 1562533 | 1905528 | Education Infrastructure Grant | Upgrading and Additions
|  | 183903 | P9009677_ | Eastern Cape | NKULULEKO JUNIOR SECONDARY SCHOOL | 200600588 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-04-02 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 611938 | 4370988 | 4982926 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183904 | LE19TMT17076 | Limpopo | Tshirenzheni Primary | 928330152 | Thulamela | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 363419 | 3274151 | 3637570 | Education Infrastructure Grant | Upgrading and Additions
|  | 183907 | DB/500322344/WS | KwaZulu-Natal | ISIKHALISANAMUHLA JUNIOR PRIMARY SCHOOL | 500322344 | Jozini | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183908 | LE19TMT17078 | Limpopo | Tshivhazwaulu Primary | 930321059 | Makhado | Design | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 578000 | 5000000 | 5578000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183913 | LE19TMT17079 | Limpopo | Tshivhilidulu Primary | 930332370 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 300000 | 1200000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183915 | DB/500174788/WS | KwaZulu-Natal | KHONGELA PRIMARY SCHOOL | 500174788 | Big Five Hlabisa | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-04-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183916 | DOE/ADMIN/RRR/247 | KwaZulu-Natal | 247 BURGER STREETUMGUNGUNDLOVU | 247 HEAD OFFICE | Ndwedwe | Construction 76% - 99% | Active - Not Contracted | 2018-05-01 | 2019-04-27 | 2023-06-30 | 2020-06-30 | 2023-06-30 | 0 | 4800000 | 4800000 | Equitable Share | Upgrading and Additions
|  | 183917 | DB/500175084/WS | KwaZulu-Natal | KHULANGOLWAZI SENIOR PRIMARY SCHOOL | 500175084 | Mtubatuba | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2018-09-12 | 2023-03-30 | 2024-05-05 | 2025-06-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183918 | LE19TMT17080 | Limpopo | Tshivhilwi Primary | 930351579 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 460696 | 4062297 | 4522993 | Education Infrastructure Grant | Upgrading and Additions
|  | 183919 | W/500109298/SDS | KwaZulu-Natal | BHEKUZULU PRIMARY SCHOOL | 500109298 | Abaqulusi | Tender | Active - Not Contracted | 2018-06-02 |  | 2025-03-30 |  |  | 1200000 | 3500000 | 4700000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 183920 | DB/500179265/WS | KwaZulu-Natal | KWADOMBA HIGH SCHOOL | 500179265 | Nongoma | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2020-05-31 | 2023-01-31 | 2023-01-31 | 2025-01-31 | 475941 | 2168174 | 2644115 | Education Infrastructure Grant | Upgrading and Additions
|  | 183921 | P9008579_ | Eastern Cape | J F MATI SENIOR SECONDARY SCHOOL | 200200455 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 219119 | 1288940 | 1508059 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183922 | DB/500311355/WS | KwaZulu-Natal | KWAMFEMFENI PRIMARY SCHOOL | 500311355 | Nongoma | Tender | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183925 | DB/500181707/WS | KwaZulu-Natal | KWAMSHAYA PRIMARY SCHOOL | 500181707 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2023-05-05 | 2025-06-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183927 | DB/500442113/WS | KwaZulu-Natal | LUHLANGA PRIMARY SCHOOL | 500442113 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-06-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183928 | P9009680_ | Eastern Cape | NOBANDA JUNIOR SECONDARY SCHOOL | 200300466 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 504337 | 3602408 | 4106745 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183929 | P9009801_ | Eastern Cape | PONGOMA PRIMARY SCHOOL | 200400921 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-03 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 688830 | 2460108 | 3148938 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183930 | P9008580_ | Eastern Cape | NOBHOTWE JUNIOR PRIMARY SCHOOL | 200200591 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 213196 | 1254098 | 1467294 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183933 | I/500290746/WS | KwaZulu-Natal | UYIKHULU SECONDARY SCHOOL | 500290746 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 430000 | 1870000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183934 | DB/500201058/WS | KwaZulu-Natal | MASITHOKOZE PRIMARY SCHOOL | 500201058 | uPhongolo | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 253472 | 1154705 | 1408177 | Education Infrastructure Grant | Upgrading and Additions
|  | 183935 | P9009685_ | Eastern Cape | DALUXOLO JUNIOR SECONDARY SCHOOL | 200300060 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 559364 | 4554823 | 5114187 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183938 | DB/500311688/WS | KwaZulu-Natal | MATHEKU SECONDARY SCHOOL | 500311688 | uMlalazi | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183941 | DB/500201724/WS | KwaZulu-Natal | MATHIYA PRIMARY SCHOOL | 500201724 | Nkandla | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183944 | DB/500440818/WS | KwaZulu-Natal | MATHUTSHANA PRIMARY SCHOOL | 500440818 | Nqutu | Design | Active - Not Contracted | 2017-06-06 |  | 2023-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183945 | I/500415029/WS | KwaZulu-Natal | MABASO SECONDARY SCHOOL | 500415029 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2018-07-17 | 2018-11-27 | 2023-08-05 | 2023-11-28 | 2023-11-28 | 223000 | 1546788 | 1769788 | Education Infrastructure Grant | Upgrading and Additions
|  | 183946 | P9008581_ | Eastern Cape | THEMBEKA JUNIOR PRIMARY SCHOOL | 200200841 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-11 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 145480 | 855766 | 1001246 | Education Infrastructure Grant | Maintenance and Repairs
|  | 183949 | C/500489954/NS | KwaZulu-Natal | THEMBINKOSI PRIMARY SCHOOL | 500489954 | Newcastle | Tender | Active - Not Contracted | 2018-06-02 |  | 2023-03-30 |  |  | 5000000 | 30000000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 183951 | DB/500202168/WS | KwaZulu-Natal | MATSHANA PRIIMARY SCHOOL | 500202168 | Nkandla | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183952 | I/500283124/WS | KwaZulu-Natal | THORNVILLE ST AIDED PRIMARY SCHOOL | 500283124 | Richmond | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2020-04-01 | 2023-03-30 | 2022-05-01 | 2023-08-25 | 250000 | 1389000 | 1639000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183955 | DB/500202427/WS | KwaZulu-Natal | MAVANA PRIMARY SCHOOL | 500202427 | Mtubatuba | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183961 | I/500282828/WS | KwaZulu-Natal | THOLUKUKHANYA SECONDARY SCHOOL | 500282902 | uPhongolo | Construction 26% - 50% | Active - Contracted | 2019-05-03 | 2021-03-31 | 2024-03-30 | 2023-04-23 | 2024-06-15 | 410000 | 1870000 | 2280000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183970 | DB/500204536/WS | KwaZulu-Natal | ZOMBIZWE HIGH SCHOOL | 500301143 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-05-31 | 2023-01-31 | 2023-08-31 | 2027-01-31 | 347157 | 1581495 | 1928652 | Education Infrastructure Grant | Upgrading and Additions
|  | 183974 | LE19TMT17125 | Limpopo | Kgakoa Primary | 922220934 | Polokwane | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2019-04-06 | 2024-03-31 | 2019-08-01 | 2025-03-31 | 522000 | 2088000 | 2610000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183977 | DB/500204758/WS | KwaZulu-Natal | MBONGOLWANE PRIMARY SCHOOL | 500204758 | uMlalazi | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 422333 | 1923963 | 2346296 | Education Infrastructure Grant | Upgrading and Additions
|  | 183982 | DB/500205165/WS | KwaZulu-Natal | MBUSOMUSHA PRIMARY SCHOOL | 500205165 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2018-08-20 | 2023-03-30 | 2024-03-30 | 2025-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183988 | DB/500205683/WS | KwaZulu-Natal | MCELENI PRIMARY SCHOOL | 500205683 | Umdoni | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2022-06-25 | 2027-01-31 | 3193817 | 1968000 | 5161817 | Education Infrastructure Grant | Upgrading and Additions
|  | 183989 | LE19TMT17102 | Limpopo | Ralema Primary School | 922222626 | Polokwane | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 544000 | 2176000 | 2720000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183991 | DB/500310282/WS | KwaZulu-Natal | MDINWA PRIMARY SCHOOL | 500310282 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2018-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183992 | DB/500206349/WS | KwaZulu-Natal | MDOMBOLO PRIMARY SCHOOL | 500206349 | Nkandla | Tender | Approved | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183993 | LE20TMT17037 | Limpopo | Mapitlula Primary School | 918510446 | Greater Tzaneen | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 160000 | 640000 | 800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183995 | DB/500206497/WS | KwaZulu-Natal | MDUKU H | 500206497 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2024-05-05 | 2027-01-31 | 721113 | 3285070 | 4006183 | Education Infrastructure Grant | Upgrading and Additions
|  | 183996 | DB/500207052/WS | KwaZulu-Natal | MEHLOKUBHEKA PRIMARY SCHOOL | 500207052 | Mtubatuba | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 183998 | I/500273393/WS | KwaZulu-Natal | SONDABA PRIMARY SCHOOL | 500273393 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2019-05-03 | 2020-09-16 | 2022-10-01 | 2023-04-30 | 2024-03-30 | 390600 | 2139400 | 2530000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184000 | DB/500207089/WS | KwaZulu-Natal | MEHLOMANE COM P | 500207089 | uMuziwabantu | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2025-03-30 | 2026-06-20 | 2027-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184002 | I/500270544/WS | KwaZulu-Natal | SIYAZENZELA PRIMARY SCHOOL | 500270544 | uPhongolo | Construction 76% - 99% | Active - Contracted | 2019-05-03 | 2020-03-30 | 2024-03-30 | 2024-04-30 | 2024-05-30 | 441000 | 2009000 | 2450000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184003 | DB/500210012/WS | KwaZulu-Natal | MHAWU SECONDARY SCHOOL | 500210012 | Mthonjaneni | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 422333 | 1923963 | 2346296 | Education Infrastructure Grant | Upgrading and Additions
|  | 184004 | LE19TMT17090 | Limpopo | Thabakgone Primary School | 923241443 | Blouberg | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 364883 | 3820679 | 4185562 | Education Infrastructure Grant | Upgrading and Additions
|  | 184005 | DB/500122507/ECD | KwaZulu-Natal | DOLO COMBINED SCHOOL | 500122507 | Umvoti | Tender | Active - Not Contracted | 2018-06-02 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184006 | DB/500211418/WS | KwaZulu-Natal | MJILA P | 500211418 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184007 | ET/500211492/WS | KwaZulu-Natal | MJOJI PRIMARY SCHOOL | 500211492 | eThekwini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2022-03-30 | 2023-03-30 | 2024-03-30 | 2025-03-30 | 920330 | 4192616 | 5112946 | Education Infrastructure Grant | Upgrading and Additions
|  | 184008 | DB/500195064/WS | KwaZulu-Natal | mlalazini ps | 500212269 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184010 | DB/500132941/ECD | KwaZulu-Natal | EMKHAMBENI PRIMARY SCHOOL | 500132941 | KwaDukuza | Tender | Active - Contracted | 2018-06-02 |  | 2024-03-30 |  |  | 1080000 | 2500000 | 3580000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184012 | LE19TMT17072 | Limpopo | Tshifulanani Primary School | 930320537 | Greater Giyani | Final Completion | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 477900 | 4129817 | 4607717 | Education Infrastructure Grant | Upgrading and Additions
|  | 184014 | DB/500442520/WS | KwaZulu-Natal | Mnkangala Primary School (Mankazaka P.) | 500442510 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184015 | P9008583_ | Eastern Cape | R H GODLO JUNIOR PRIMARY SCHOOL | 200200986 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-03-30 | 2026-03-31 | 2025-03-01 | 2025-03-31 | 60429 | 355449 | 415878 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184016 | DB/500213601/WS | KwaZulu-Natal | MNQANDI PRIMARY SCHOOL | 500213601 | Nkandla | Construction 26% - 50% | Active - Not Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184017 | LE19TMT17077 | Limpopo | Tshirunzanani Primary School | 930321455 | Greater Giyani | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 234000 | 936000 | 1170000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184018 | DB/500134273/ECD | KwaZulu-Natal | EMPISINI PRIMARY SCHOOL | 500134273 | Endumeni | Tender | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184019 | DB/500214415/WS | KwaZulu-Natal | MONA PRIMARY SCHOOL (Completion Contract) | 500214415 | Nongoma | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184023 | DB/500215118/WS | KwaZulu-Natal | MORNINGSIDE C | 500215118 | Endumeni | Construction 1% - 25% | Active - Not Contracted | 2017-06-06 | 2020-05-01 | 2024-03-30 | 2025-12-20 | 2027-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184026 | P9008584_ | Eastern Cape | MORRISON JUNIOR PRIMARY SCHOOL | 200300359 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 271747 | 1598517 | 1870264 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184029 | DB/500216117/WS | KwaZulu-Natal | MPELENYANE PRIMARY SCHOOL | 500216117 | Big Five Hlabisa | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-30 | 2023-05-05 | 2027-01-31 | 284225 | 1294805 | 1579030 | Education Infrastructure Grant | Upgrading and Additions
|  | 184031 | P9008585_ | Eastern Cape | MAZIZINI HIGH SCHOOL | 200300801 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-08-09 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 552727 | 15000 | 567727 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184033 | DB/500157028/ECD | KwaZulu-Natal | HLINZEKA COMBINED PRIMARY SCHOOL | 500157028 | Nqutu | Tender | Active - Contracted | 2018-06-02 |  | 2025-03-30 |  |  | 500000 | 1612057 | 2112057 | Education Infrastructure Grant | Upgrading and Additions
|  | 184034 | DB/500216487/WS | KwaZulu-Natal | MPHELANDABA SS | NEW/FEN | uMshwathi | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184035 | P9008586_ | Eastern Cape | MTOMBOTI JUNIOR SECONDARY SCHOOL | 200300388 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-11 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 453066 | 2665094 | 3118160 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184038 | I/500265882/WS | KwaZulu-Natal | SILWANETSHE PRIMARY SCHOOL | 500265919 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2019-05-03 |  | 2024-03-30 |  |  | 497000 | 2762000 | 3259000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184051 | P9008589_ | Eastern Cape | VULINGCOBO SENIOR SECONDARY SCHOOL | 200300719 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 0 | 2807615 | 2807615 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184052 | DB/500216783/WS | KwaZulu-Natal | MPILONDE PRIMARY SCHOOL | 500216783 | Endumeni | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184054 | I/500265253/WS | KwaZulu-Natal | SIKHWAMA PRIMARY SCHOOL | 500265253 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2019-09-10 | 2023-03-30 | 2020-04-30 | 2023-04-30 | 9000 | 43000 | 52000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184061 | DB/500304436/WS | KwaZulu-Natal | MTHANDI PRIMARY SCHOOL | 500218707 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2020-06-30 | 2023-03-31 | 2023-06-30 | 2027-06-30 | 432362 | 1969649 | 2402011 | Education Infrastructure Grant | Upgrading and Additions
|  | 184066 | LE19TMT17107 | Limpopo | P.T Matlala Secondary School | 921142706 | Blouberg | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 256000 | 1024000 | 1280000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184068 | DB/500343286/WS | KwaZulu-Natal | MYEKENI SECONNDARY SCHOOL | 500343286 | Ulundi | Construction 1% - 25% | Active - Not Contracted | 2017-06-06 | 2019-01-01 | 2024-03-30 | 2025-12-20 | 2027-09-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184073 | DB/500324490/WS | KwaZulu-Natal | MZIMELA PRIMARY SCHOOL | 500324490 | Endumeni | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184076 | LE19TMT17108 | Limpopo | Maswikananoko Primary School | 921110532 | Blouberg | Design | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 318000 | 1270000 | 1588000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184079 | DB/500223480/WS | KwaZulu-Natal | NCECENI PRIMARY SCHOOL | 500223480 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2020-05-01 | 2023-01-30 | 2022-05-05 | 2027-12-20 | 330617 | 1506146 | 1836763 | Education Infrastructure Grant | Upgrading and Additions
|  | 184081 | DB/500223739/WS | KwaZulu-Natal | NCIYA HIGH SCHOOL | DB/500223406/SDS | uMuziwabantu | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184088 | LE19TMT17109 | Limpopo | Baseloane Primary School | 923261416 | Lepele-Nkumpi | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 471776 | 6786734 | 7258510 | Education Infrastructure Grant | Upgrading and Additions
|  | 184089 | DB/500325378/WS | KwaZulu-Natal | NEW ERA JUNIOR PRIMARY SCHOOL | 500325378 | Umhlabuyalingana | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2019-09-12 | 2024-03-30 | 2023-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184091 | DB/500228549/WS | KwaZulu-Natal | NGOTSHE SECONDARY SCHOOL | 500228549 | Abaqulusi | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2027-08-31 | 966500 | 4402944 | 5369444 | Education Infrastructure Grant | Upgrading and Additions
|  | 184093 | DB/500319754/WS | KwaZulu-Natal | NOGABISELA HIGH SCHOOL | DB/500233618/SDS | uMlalazi | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 398001 | 1813114 | 2211115 | Education Infrastructure Grant | Upgrading and Additions
|  | 184138 | DB/500241203/WS | KwaZulu-Natal | NUNGWANA PRIMARY SCHOOL | 500241203 | Umzumbe | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 298261 | 1358747 | 1657008 | Education Infrastructure Grant | Upgrading and Additions
|  | 184139 | DB/500242276/WS | KwaZulu-Natal | OBANJENI PRIMARY SCHOOL | 500242276 | uMlalazi | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184142 | DB/500252525/WS | KwaZulu-Natal | QEDUKOMA PRIMARY SCHOOL | 500252325 | Nqutu | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184144 | P9008742 | Eastern Cape | ULWAZI SECONDARY SCHOOL | 200200872 | Buffalo City | Design | Active - Not Contracted | 2018-04-23 |  | 2026-03-31 |  |  | 0 | 23246427 | 23246427 | Education Infrastructure Grant | Upgrading and Additions
|  | 184145 | DB/500253376/WS | KwaZulu-Natal | QINELANE PRIMARY SCHOOL | 500253376 | Msinga | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-06-30 | 457445 | 2083916 | 2541361 | Education Infrastructure Grant | Upgrading and Additions
|  | 184146 | DB/500253524/WS | KwaZulu-Natal | QINISO PRIMARY SCHOOL | 5000253524 | Msinga | Construction 26% - 50% | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184147 | DB/500325008/WS | KwaZulu-Natal | ROBERT HLONGWA SECONDARY SCHOOL | 500325008 | eThekwini | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 1185604 | 5401087 | 6586691 | Education Infrastructure Grant | Upgrading and Additions
|  | 184148 | DB/500262885/WS | KwaZulu-Natal | SIBHANGWANA PRIMARY SCHOOL | 5002652885 | Ray Nkonyeni | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184151 | DB/500267251/WS | KwaZulu-Natal | SIPHENI HP | 500267251 | Newcastle | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 78248 | 506697 | 584945 | Education Infrastructure Grant | Upgrading and Additions
|  | 184153 | DB/500267658/WS | KwaZulu-Natal | SIPHOKUHLE HIGH SCHOOL | 500267658 | Inkosi Langalibalele | Final Completion | Active - Contracted | 2017-06-06 | 2019-09-10 | 2023-03-30 | 2022-10-30 | 2022-04-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184154 | DB/500342694/WS | KwaZulu-Natal | SIPHOSETHU SECONDARY SCHOOL | 500168535 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184157 | DB/500222481/ECD | KwaZulu-Natal | MZOMUSHA INTERMEDIATE SCHOOL (TUGELA FERRY) | 500222481 | Msinga | Tender | Active - Contracted | 2018-06-02 |  | 2026-03-30 |  |  | 500000 | 1542026 | 2042026 | Education Infrastructure Grant | Upgrading and Additions
|  | 184158 | DB/500233100/ECD | KwaZulu-Natal | NKUNYANA PRIMARY SCHOOL | 500233100 | Nqutu | Tender | Active - Contracted | 2018-06-02 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184159 | DB/500239464/ECD | KwaZulu-Natal | NTANYEZULU PRIMARY SCHOOL | 500239464 | Msinga | Tender | Active - Contracted | 2018-06-02 |  | 2025-03-30 |  |  | 500000 | 1648943 | 2148943 | Education Infrastructure Grant | Upgrading and Additions
|  | 184160 | DB/500259000/ECD | KwaZulu-Natal | SAVELA PRIMARY SCHOOL | 500259000 | Ubuhlebezwe | Tender | Active - Not Contracted | 2018-06-02 |  | 2024-03-30 |  |  | 394920 | 1975580 | 2370500 | Education Infrastructure Grant | Upgrading and Additions
|  | 184161 | DB/500268028/WS | KwaZulu-Natal | SIQHAKAZILE PRIMARY SCHOOL | 500268028 | Umzumbe | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184162 | DB/500268657/WS | KwaZulu-Natal | SITHEKU HIGH SCHOOL | 500268657 | Mthonjaneni | Construction 26% - 50% | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184163 | DB/500269434/WS | KwaZulu-Natal | SIYABONGA SECONDARY SCHOOL | 500447293 | eThekwini | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184164 | DB/500269693/WS | KwaZulu-Natal | SIYAKHANYISA PRIMARY SCHOOL | 500269730 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184165 | DB/500320901/WS | KwaZulu-Natal | SIYATHOKOZA PRIMARY SCHOOL | 500320901 | eThekwini | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2020-05-01 | 2023-03-30 | 2022-07-14 | 2024-08-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184166 | DB/500344063/ECD | KwaZulu-Natal | LANDULWAZI PRIMARY SCHOOL | 500344063 | Msinga | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-30 |  |  | 500000 | 1555679 | 2055679 | Education Infrastructure Grant | Upgrading and Additions
|  | 184167 | DB/500272801/WS | KwaZulu-Natal | SOKHULU PRIMARY SCHOOL | 500272801 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-02-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184168 | DB/500274392/WS | KwaZulu-Natal | SOZABE HIGH SCHOOL | 500274392 | Ray Nkonyeni | Design | Active - Not Contracted | 2017-06-06 |  | 2025-04-25 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184169 | DB/500266723/WS | KwaZulu-Natal | ST PHILIPS PRIMARY SCHOOL | 500266723 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2023-03-15 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184177 | LE20TMT17035 | Limpopo | Botsikana Secondary School | 913420208 | Ba-Phalaborwa | Construction 26% - 50% | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 397975 | 2994884 | 3392859 | Education Infrastructure Grant | Upgrading and Additions
|  | 184180 | DB/500277685/WS | KwaZulu-Natal | STAR OF THE SEA PRIMARY SCHOOL | 500277685 | Umhlabuyalingana | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-22 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184181 | I/500212861/WS | KwaZulu-Natal | MLOMOKAZULU JUNIOR SCHOOL | 500212861 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2019-01-16 | 2019-12-01 | 2023-05-10 | 2022-07-05 | 2023-05-10 | 531000 | 2419000 | 2950000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184182 | LE19TMT17114 | Limpopo | Rev M.P Malatji Primary School | 922221395 | Molemole | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-05-31 |  |  | 480143 | 7750659 | 8230802 | Education Infrastructure Grant | Upgrading and Additions
|  | 184184 | DB/500278351/WS | KwaZulu-Natal | SUKAMUVA SECONDARY SCHOOL | 500278351 | Ray Nkonyeni | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184186 | LE19TMT17115 | Limpopo | Mahlora Primary School | 921140533 | Blouberg | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 544941 | 3753428 | 4298369 | Education Infrastructure Grant | Upgrading and Additions
|  | 184187 | DB/500280201/WS | KwaZulu-Natal | THANDANANI PRIMARY SCHOOL | 500340474 | Ubuhlebezwe | Design | Active - Not Contracted | 2017-06-06 |  | 2025-04-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184189 | DB/500281422/WS | KwaZulu-Natal | THEMBALESIZWE P | 500281422 | uMlalazi | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184190 | LE19TMT17116 | Limpopo | Diphuti Primary School | 9265405222 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2023-05-31 |  |  | 752093 | 6304397 | 7056490 | Education Infrastructure Grant | Upgrading and Additions
|  | 184191 | DB/500281681/WS | KwaZulu-Natal | THEMBELANI PRIMARY SCHOOL | 500281681 | KwaDukuza | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-28 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184192 | LE19TMT17117 | Limpopo | Lwaphungu Secondary School | 993302201 | Collins Chabane | Construction 1% - 25% | Approved | 2019-04-01 | 2020-08-20 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 81000 | 9720 | 90720 | Education Infrastructure Grant | Upgrading and Additions
|  | 184195 | DB/500282236/WS | KwaZulu-Natal | THOKOZA SECONDARY SCHOOL | 500282236 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2025-02-04 |  |  | 517732 | 2358555 | 2876287 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184196 | LE19TMT17118 | Limpopo | Mangaya Primary School | 929311533 | Thulamela | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 221644 | 1905440 | 2127084 | Education Infrastructure Grant | Upgrading and Additions
|  | 184198 | DB/500282606/WS | KwaZulu-Natal | THOLIMFUNDO SECONDARY SCHOOL | 500495948 | Ray Nkonyeni | Design | Active - Not Contracted | 2017-06-06 |  | 2024-03-25 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184203 | LE19TMT17120 | Limpopo | Dzindi Primary School | 930320155 | Collins Chabane | Design | Active - Contracted | 2019-04-01 | 2021-08-20 | 2025-03-31 | 2023-03-31 | 2025-06-30 | 782897 | 8532676 | 9315573 | Education Infrastructure Grant | Upgrading and Additions
|  | 184204 | LE20TMT17002 | Limpopo | dingamazi primary | 916410089 | Greater Giyani | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 130000 | 521000 | 651000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184206 | LE19TMT17123 | Limpopo | Hututu Secondary School | 924651910 | Lepele-Nkumpi | Practical Completion (100%) | Active - Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 711256 | 5473924 | 6185180 | Education Infrastructure Grant | Upgrading and Additions
|  | 184208 | EDDP184/184 | Limpopo | Maboa (Driekop) Secondary | 996604202 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2016-04-03 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 8910200 | 35640800 | 44551000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 184209 | LE19TMT17124 | Limpopo | Jack Lavhengwa Secondary School | 930330398 | Makhado | Construction 76% - 99% | Active - Contracted | 2019-05-01 |  | 2024-03-31 |  |  | 651084 | 4957251 | 5608335 | Education Infrastructure Grant | Upgrading and Additions
|  | 184210 | LE20TMT17043 | Limpopo | Dzumbuluwani Primary | 93032363 | Thulamela | Construction 1% - 25% | Active - Contracted | 2020-02-01 |  | 2024-03-31 |  |  | 476087 | 3724901 | 4200988 | Education Infrastructure Grant | Upgrading and Additions
|  | 184212 | LE20TMT17004 | Limpopo | Famandha High | 916410119 | Greater Giyani | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 58245 | 232980 | 291225 | Education Infrastructure Grant | Upgrading and Additions
|  | 184216 | DB/500328188/WS | KwaZulu-Natal | THOLISU HIGH SCHOOL | 500328188 | Umdoni | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-25 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184219 | DB/500283050/WS | KwaZulu-Natal | THONGWAMA SECONDARY SCHOOL | 500283050 | Umhlabuyalingana | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2020-05-29 | 2022-05-27 | 2022-06-15 | 2025-07-29 | 429083 | 1954710 | 2383793 | Education Infrastructure Grant | Upgrading and Additions
|  | 184220 | LE19TMT17127 | Limpopo | Kgarahara Secondary School | 919340678 | Polokwane | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 521382 | 7754577 | 8275959 | Education Infrastructure Grant | Upgrading and Additions
|  | 184223 | LE19TMT17128 | Limpopo | Kgolakaleleme Secondary School | 901340449 | Makhado | Construction 51% - 75% | Active - Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 762471 | 8569694 | 9332165 | Education Infrastructure Grant | Upgrading and Additions
|  | 184228 | LE19TMT17130 | Limpopo | Khekhutini Primary | 918510123 | Greater Letaba | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 732111 | 8566810 | 9298921 | Education Infrastructure Grant | Upgrading and Additions
|  | 184229 | LE20IDT09012 | Limpopo | NKOMO SECONDARY SCHOOL | 994401403 | Greater Giyani | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 3000000 | 15000000 | 18000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184231 | ET/500343619/WS | KwaZulu-Natal | UBUHLEBEPHUPHO PRIMARY SCHOOL | 500343619 | Ndwedwe | Final Completion | Active - Contracted | 2018-12-06 | 2019-09-10 | 2023-03-30 | 2023-12-24 | 2023-06-30 | 691376 | 3149604 | 3840980 | Education Infrastructure Grant | Upgrading and Additions
|  | 184232 | DB/500286047/WS | KwaZulu-Natal | UBUQHAWEBETHU | 500286047 | Mthonjaneni | Design | Active - Not Contracted | 2017-06-06 |  | 2025-04-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184234 | DB/500287009/WS | KwaZulu-Natal | UMBIYA SECONDARY SCHOOL | 500287009 | Mfolozi | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184235 | LE20IDT09008 | Limpopo | Kgwadu Primary School | 919340791 | Molemole | Feasibility | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 2480000 | 9920000 | 12400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184238 | DB/500322196/WS | KwaZulu-Natal | UMCEBOWOLWAZI PRIMARY SCHOOL | 500322196 | Newcastle | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184243 | DB/500290339/WS | KwaZulu-Natal | USIZO SECONDARY SCHOOL | 500290339 | Msinga | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184244 | DB/500291264/WS | KwaZulu-Natal | VELANGAYE HIGH SCHOOL | 500291264 | Nkandla | Design | Active - Not Contracted | 2017-06-06 |  | 2023-03-31 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184246 | DB/500292559/WS | KwaZulu-Natal | VONDLO PRIMARY SCHOOL | 500292559 | uMhlathuze | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2020-05-29 | 2023-03-31 | 2022-04-04 | 2027-04-11 | 196605 | 895647 | 1092252 | Education Infrastructure Grant | Upgrading and Additions
|  | 184247 | DB/500294927/WS | KwaZulu-Natal | WATERSMEET PRIMARY SCHOOL | 500294927 | Alfred Duma | Design | Active - Not Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184248 | DB/500297702/WS | KwaZulu-Natal | XHONYWA PRIMARY SCHOOL | 500297702 | Ray Nkonyeni | Construction 1% - 25% | Active - Not Contracted | 2017-06-06 | 2020-05-29 | 2023-01-28 | 2022-02-22 | 2025-06-03 | 586982 | 2674027 | 3261009 | Education Infrastructure Grant | Upgrading and Additions
|  | 184249 | DB/500307692/WS | KwaZulu-Natal | YETHENI PRIMARY SCHOOL | 500307692 | uMlalazi | Construction 76% - 99% | Active - Not Contracted | 2017-06-06 | 2020-05-29 | 2023-01-10 | 2022-02-07 | 2025-02-23 | 596329 | 2716611 | 3312940 | Education Infrastructure Grant | Upgrading and Additions
|  | 184251 | DB/500429422/WS | KwaZulu-Natal | ZAMOKUHLE PRIMARY SCHOOL | 500298960 | Impendle | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184253 | DB/500322973/WS | KwaZulu-Natal | ZAMUKWE P | 500322973 | Umdoni | Design | Active - Not Contracted | 2017-06-06 |  | 2025-04-22 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184254 | DB/500299700/WS | KwaZulu-Natal | ZIBONE PRIMARY SCHOOL | 500299700 | Mthonjaneni | Tender | Active - Not Contracted | 2017-06-06 |  | 2024-04-21 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184255 | DB/500299737/WS | KwaZulu-Natal | ZIBONELE JUNIOR SECONDARY | 500299737 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2017-06-06 |  | 2024-05-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184256 | I/500324786/WS | KwaZulu-Natal | SIBONILE PRIMARY SCHOOL | 500324786 | uPhongolo | Construction 51% - 75% | Active - Contracted | 2019-02-13 | 2020-04-22 | 2022-11-19 | 2023-04-30 | 2023-06-30 | 666000 | 3034000 | 3700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184257 | DB/500300329/WS | KwaZulu-Natal | ZIMEME SECONDARY SCHOOL | 500300329 | uMlalazi | Design | Active - Not Contracted | 2017-06-06 |  | 2027-06-18 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184258 | DB/500216302/WS | KwaZulu-Natal | MPEPHOSE SECONDARY SCHOOL | 500216302 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184259 | W/500282347/WS | KwaZulu-Natal | THOKOZWAYO SECONDARY SCHOOL | 500282347 | Richmond | Practical Completion (100%) | Active - Contracted | 2017-04-06 | 2019-02-01 | 2023-06-30 | 2020-03-31 | 2025-05-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184261 | W/500281792/WS | KwaZulu-Natal | THEMBUZULU SECONDARY SCHOOL | 500281792 | Umzumbe | Practical Completion (100%) | Active - Contracted | 2019-03-04 | 2019-09-12 | 2023-06-30 | 2023-05-05 | 2025-01-31 | 861714 | 3925586 | 4787300 | Education Infrastructure Grant | Upgrading and Additions
|  | 184263 | W/500279572/WS | KwaZulu-Natal | Tauricus Intermediate School | 500279572 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2018-01-04 | 2020-03-01 | 2025-06-30 | 2025-03-31 | 2025-05-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184265 | W/500274059/WS | KwaZulu-Natal | SOTOBE SECONDARY SCHOOL | 500274059 | Ndwedwe | On Hold | Active - Not Contracted | 2018-01-04 |  | 2023-06-30 |  |  | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184266 | EDDP184/246 | Limpopo | KWENA SELAKI H PRIMARY | 922250317 | Polokwane | Construction 76% - 99% | Active - Contracted | 2016-04-01 | 2016-06-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1065200 | 4260800 | 5326000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184269 | W/500133718/WS | KwaZulu-Natal | ELOMO PRIMARY SCHOOL | 50044559 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2017-01-20 | 2023-03-30 | 2023-06-20 | 2023-11-04 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184270 | W/500140045/WS | KwaZulu-Natal | ESIBILA PRIMARY SCHOOL | 500140045 | Umvoti | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2017-01-20 | 2023-03-30 | 2023-05-05 | 2023-03-29 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184271 | W/500140785/WS | KwaZulu-Natal | ESIMOZOMENI SENIOR PRIMARY SCHOOL | 500140785 | Richmond | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2017-01-20 | 2023-03-30 | 2023-05-05 | 2023-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184272 | W/500143782/WS | KwaZulu-Natal | EZULWINI PRIMARY SCHOOL | 500289599 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-12-01 | 2023-04-30 | 2024-05-05 | 2025-03-04 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184273 | W/500143967/WS | KwaZulu-Natal | FAHLAZA PRIMARY SCHOOL | 500143967 | Endumeni | Practical Completion (100%) | Active - Contracted | 2016-02-20 | 2018-12-01 | 2023-03-30 | 2023-05-05 | 2023-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184280 | MDOE/UPG/009/19-20(DPWRT/061/19/MP) | Mpumalanga | Chief K J Malaza Primary School | 800004663 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2019-06-03 | 2019-08-06 | 2023-03-31 | 2023-04-27 | 2023-04-27 | 399824 | 2855885 | 3255709 | Education Infrastructure Grant | Upgrading and Additions
|  | 184282 | MDOE/UPG/013/19-20(DPWRT/065/19/MP) | Mpumalanga | Ebuhleni Primary School | 800003087 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2019-09-02 | 2019-10-23 | 2023-03-31 | 2020-04-30 | 2020-04-30 | 279666 | 1997612 | 2277278 | Education Infrastructure Grant | Upgrading and Additions
|  | 184283 | W/500196803/WS | KwaZulu-Natal | MANGOMUNTU S PRIMARY SCHOOL | 5001911882 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2017-06-10 | 2023-03-30 | 2022-03-30 | 2023-03-30 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184284 | MDOE/P/GSD/Education Infrastructure Grant(EIG)/UPG/18-19/001(PWRT/SAN/004/19/MP) | Mpumalanga | Isifisosethu Primary School | 800006718 | Lekwa | Practical Completion (100%) | Active - Contracted | 2020-04-02 | 2020-04-03 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 0 | 2526408 | 2526408 | Education Infrastructure Grant | Upgrading and Additions
|  | 184288 | W/500306582/WS | KwaZulu-Natal | MATHOLE HIGH SCHOOL | 500201798 | Ulundi | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2019-12-01 | 2022-06-30 | 2023-05-05 | 2024-03-04 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184298 | LE20TMT17010 | Limpopo | Mabilu Primary School | 930350750 | Thulamela | Construction 1% - 25% | Active - Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184302 | P9010382 | Eastern Cape | BETHEL JUNIOR SECONDARY SCHOOL | 200500029 | Matatiele | Design | Active - Contracted | 2018-06-01 |  | 2026-03-31 |  |  | 0 | 2407397 | 2407397 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184329 | MDOE/UPG/1004/20-21( DPWRT/SA/104/20/MP) ( | Mpumalanga | Chief Charles Secondary School | 800002063 | Mbombela | Construction 76% - 99% | Active - Contracted | 2020-03-01 | 2021-08-04 | 2022-12-30 | 2022-03-30 | 2022-03-30 | 274523 | 1715769 | 1990292 | Education Infrastructure Grant | Upgrading and Additions
|  | 184333 | MDOE/SAN/257/2020(1) | Mpumalanga | Ekhiyeni Primary School (farm school) | 800003194 | Mbombela | Tender | Active - Contracted | 2020-04-01 |  | 2024-05-31 |  |  | 712480 | 3562400 | 4274880 | Education Infrastructure Grant | Upgrading and Additions
|  | 184334 | DPWRT/SAN/321/20/MP | Mpumalanga | Emtfonjeni Primary School | 800003632 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2022-03-31 | 2023-04-13 | 2023-04-12 | 2022-04-15 | 354711 | 2533651 | 2888362 | Education Infrastructure Grant | Upgrading and Additions
|  | 184336 | LE20TMT17005 | Limpopo | Hetiseka Sec | 915530099 | Greater Tzaneen | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184357 | LE20TMT17058 | Limpopo | Itereleng Secondary | 991104401 | Thabazimbi | Construction 1% - 25% | Active - Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 740000 | 2960000 | 3700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184377 | I/500205091/WS | KwaZulu-Natal | MBULWINI PRIMARY SCHOOL | 500205091 | KwaDukuza | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2019-05-10 | 2023-06-28 | 2023-05-28 | 2023-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184398 | P9010029_ | Eastern Cape | DALE COLLEGE | 200200103 | Buffalo City | Practical Completion (100%) | Approved | 2018-04-26 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1064966 | 1064966 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184404 | LE20TMT17013 | Limpopo | Mathulamisha Secondary School | 921142416 | Mogalakwena | Tender | Active - Not Contracted | 2020-01-04 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184409 | P9010443_ | Eastern Cape | Service Delivery Model | 200999925 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 157300000 | 157300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184415 | P9010030 | Eastern Cape | DALE COLLEGE BOYS` PRIMARY SCHOOL | 200200104 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-26 | 2018-05-27 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 0 | 1144532 | 1144532 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184431 | P9010446 | Eastern Cape | Professional Membership and Continuous Development | 200401130 | Buffalo City | Construction 76% - 99% | Approved | 2016-01-28 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 375000 | 0 | 375000 | Education Infrastructure Grant | Non-Infrastructure
|  | 184437 | P9008591_ | Eastern Cape | CANDU JUNIOR SECONDARY SCHOOL | 200300837 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 426127 | 2506632 | 2932759 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184509 | LE20TMT17059 | Limpopo | Manoe Secondary School | 9202210791 | Mogalakwena | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 484780 | 7751099 | 8235879 | Education Infrastructure Grant | Upgrading and Additions
|  | 184510 | P9009926_ | Eastern Cape | SIVE SPECIAL SCHOOL | 200501449 | Matatiele | Construction 76% - 99% | Active - Contracted | 2018-11-01 | 2018-11-26 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1383694 | 1383694 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184517 | P9008592_ | Eastern Cape | TSHAZIBANA PRIMARY SCHOOL | 200300608 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 777995 | 4205695 | 4983690 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184518 | P9013639 | Eastern Cape | DOE Disaster Package | 200999925 | Amahlathi | Construction 1% - 25% | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 240000000 | 240000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184530 | P9008594_ | Eastern Cape | GOVAN JUNIOR SECONDARY SCHOOL | 200300731 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 521355 | 3068620 | 3589975 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184536 | P9008596_ | Eastern Cape | NOMAHEYA SENIOR SECONDARY SCHOOL | 200300434 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 376083 | 2212254 | 2588337 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184548 | LE20TMT17017 | Limpopo | MUGWAZENI SECONDARY | 915530235 | Greater Tzaneen | Construction 1% - 25% | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184550 | LE20TMT17018 | Limpopo | MUHAWU SECONDARY | 916410669 | Greater Giyani | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184568 | P9008597_ | Eastern Cape | UPPER GWADU PRIMARY SCHOOL | 200300844 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 605119 | 3331524 | 3936643 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184582 | LE20TMT17019 | Limpopo | Nanga Primary School | 928330589 | Makhado | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184587 | P9010520 | Eastern Cape | LUTHOLI JUNIOR SECONDARY SCHOOL | 200400415 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 4666804 | 4666804 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184596 | P9008599_ | Eastern Cape | S E K MQHAYI HIGH SCHOOL | 200200737 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 73802 | 434133 | 507935 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184604 | P9008600_ | Eastern Cape | GQOBOZA JUNIOR SECONDARY SCHOOL | 200600225 | Intsika Yethu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2026-03-31 | 2026-03-01 | 2026-03-31 | 208128 | 1224285 | 1432413 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184609 | P9008601_ | Eastern Cape | EMVILO JUNIOR SECONDARY SCHOOL | 200400165 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 69057 | 406191 | 475248 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184610 | P9008602_ | Eastern Cape | NDINDIMENI JUNIOR SECONDARY SCHOOL | 200400721 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 163954 | 796838 | 960792 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184621 | P9008604_ | Eastern Cape | NCERANA JUNIOR SECONDARY SCHOOL | 200300414 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-03-29 | 2025-03-01 | 2025-03-01 | 2025-03-01 | 1424331 | 15000 | 1439331 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184638 | LE20TMT17016 | Limpopo | Motjere Secondary | 922250775 | Mogalakwena | Tender | Active - Not Contracted | 2020-01-04 |  | 2025-03-31 |  |  | 65914 | 263658 | 329572 | Education Infrastructure Grant | Upgrading and Additions
|  | 184649 | LE20TMT00195 | Limpopo | Mphakati Primary | 911360283 | Collins Chabane | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 420000 | 1680000 | 2100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184660 | LE20TMT17011 | Limpopo | Mafasa Secondary | 921141994 | Mogalakwena | Tender | Active - Not Contracted | 2020-01-04 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184665 | LE20TMT17021 | Limpopo | PLATLAND PRIMARY | 901511265 | Greater Letaba | Tender | Active - Not Contracted | 2019-04-01 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184670 | LE21TMT17195 | Limpopo | Poo Secondary School | 925631596 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 252000 | 1008000 | 1260000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184677 | LE20TMT17022 | Limpopo | RADIBAKI PRIMARY | 921110891 | Lephalale | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 73090 | 292361 | 365451 | Education Infrastructure Grant | Upgrading and Additions
|  | 184725 | LE20TMT17020 | Limpopo | Penighotsa Sec School | 905361637 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2019-06-30 | 2019-08-30 | 2025-03-31 | 2022-06-30 | 2023-03-31 | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184726 | LE20TMT17024 | Limpopo | Segale Primary | 921111023 | Lephalale | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 66246 | 264986 | 331232 | Education Infrastructure Grant | Upgrading and Additions
|  | 184741 | LE19TMT17051 | Limpopo | Nyahanelani Primary | 930350194 | Thulamela | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 | 2022-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 80641 | 9677 | 90318 | Education Infrastructure Grant | Upgrading and Additions
|  | 184750 | LE20TMT17070 | Limpopo | Selelo Primary | 920211732 | Greater Tubatse/Fetakgomo | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 62895 | 2515810 | 2578705 | Education Infrastructure Grant | Upgrading and Additions
|  | 184759 | LE20TMT17001 | Limpopo | BOKE SECONDARY SCHOOL | 918510026 | Greater Tzaneen | Construction 1% - 25% | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 97000 | 388000 | 485000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184784 | LE20TMT17027 | Limpopo | THABANG HIGH | 921111115 | Lephalale | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 184786 | LE20TMT17028 | Limpopo | Thase Sec School | 930351258 | Thulamela | Construction 1% - 25% | Active - Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 62881 | 251524 | 314405 | Education Infrastructure Grant | Upgrading and Additions
|  | 184792 | LE20TMT17029 | Limpopo | TLOU MATLALA SECONDARY | 921141321 | Mogalakwena | Construction 1% - 25% | Active - Contracted | 2019-06-30 | 2019-08-30 | 2025-03-31 | 2023-03-31 | 2023-03-31 | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184794 | LE20TMT17030 | Limpopo | TONDANI PRIMARY | 928330541 | Makhado | Tender | Active - Not Contracted | 2019-06-30 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184799 | LE20TMT17031 | Limpopo | Tshebedi Secondary ( Now Konyama primary) | 922251984 | Mogalakwena | Tender | Active - Not Contracted | 2020-01-04 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184826 | P9010461 | Eastern Cape | MQEKEZWENI PRIMARY SCHOOL | 200400656 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2017-04-03 | 2019-07-18 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 565848 | 3197360 | 3763208 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184843 | P9011566_ | Eastern Cape | ZWELITSHA HEAD OFFICE | 200999925 | Amahlathi | Feasibility | Active - Not Contracted | 2017-04-03 |  | 2026-03-31 |  |  | 0 | 32444276 | 32444276 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184849 | ET/500201095/WS | KwaZulu-Natal | MASIWELA COMBINE SCHOOL | 500201095 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2018-02-12 | 2018-07-01 | 2023-12-12 | 2023-03-30 | 2023-09-13 | 1277423 | 5819369 | 7096792 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 184854 | P9010985 | Eastern Cape | AMOS MLUNGWANA PRIMARY SCHOOL | 200600196 | Senqu | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2019-04-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 13989533 | 13989533 | Education Infrastructure Grant | Upgrading and Additions
|  | 184887 | P9008577_ | Eastern Cape | MBEKWENI SENIOR PRIMARY SCHOOL | 200400531 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-02-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 54263 | 319338 | 373601 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184892 | P9010623 | Eastern Cape | ZWELITSHA CUSTOMER CARE CENTRE | 200999925 | Amahlathi | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-07-30 | 2023-05-30 | 2020-11-30 | 2022-03-31 | 0 | 1179000 | 1179000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184897 | P9008613_ | Eastern Cape | MZOMHLE JUNIOR SECONDARY SCHOOL | 200400698 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 96145 | 565560 | 661705 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184905 | P0001514 | Eastern Cape | KING SABATA DALINDYEBO (CIVILS) | 200700004 | King Sabata Dalindyebo | Final Completion | Active - Contracted | 2007-01-18 | 2019-08-22 | 2025-03-31 | 2025-03-31 | 2025-03-01 | 1432000 | 8020606 | 9452606 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184917 | P9007292_ | Eastern Cape | EFATA SPECIAL SCHOOL - Water | 200401369 | King Sabata Dalindyebo | Construction 51% - 75% | Active - Contracted | 2016-06-24 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 11524545 | 11524545 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184930 | P9004825_ | Eastern Cape | SHAWBURY SENIOR SECONDARY SCHOOL | 200400989 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2016-05-17 | 2017-03-07 | 2025-03-30 | 2025-03-30 | 2025-03-31 | 1136959 | 4318263 | 5455222 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184935 | P9003549_ | Eastern Cape | DUMILE PRIMARY SCHOOL | 200401257 | Mbizana | Feasibility | Active - Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 1058886 | 6462047 | 7520933 | Education Infrastructure Grant | Upgrading and Additions
|  | 184938 | P0003601_ | Eastern Cape | TSOMO SENIOR SECONDARY SCHOOL | 200300612 | Intsika Yethu | Construction 76% - 99% | Active - Contracted | 2012-03-12 | 2017-02-15 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 277209 | 1695847 | 1973056 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184944 | P9004962_ | Eastern Cape | BUTTERWORTH HIGH SCHOOL (Emergency) | 200300741 | Mnquma | Construction 51% - 75% | Active - Contracted | 2012-10-01 | 2015-04-09 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1475796 | 6775454 | 8251250 | Education Infrastructure Grant | Maintenance and Repairs
|  | 184949 | P9005976_ | Eastern Cape | MCEULA SENIOR SECONDARY SCHOOL | 200600470 | Sakhisizwe | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2019-04-01 | 2025-03-31 | 2025-03-31 | 2026-03-31 | 5185100 | 29147900 | 34333000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184959 | P9005990_ | Eastern Cape | MBIZANA DISTRICT | 200999901 | Mbizana | Design | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 125107357 | 125107357 | Education Infrastructure Grant | Upgrading and Additions
|  | 184963 | P9006360 | Eastern Cape | SOPHATISANA SECONDARY SCHOOL | 200201050 | Buffalo City | Construction 26% - 50% | Approved | 2016-06-07 | 2018-06-01 | 2026-03-31 | 2025-03-31 | 2026-03-31 | 4381791 | 66803530 | 71185321 | Education Infrastructure Grant | Upgrading and Additions
|  | 184973 | DB/500309912/WS | KwaZulu-Natal | MALOBENI SECONDARY SCHOOL | 500309912 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2025-09-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184979 | EDDP316 | Limpopo | schoonoord circuit office | LP09097 | Makhuduthamaga | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2016-10-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1340048 | 5360193 | 6700241 | Education Infrastructure Grant | Upgrading and Additions
|  | 184980 | EDDP318 | Limpopo | Makobe Circuit Office | LP09024 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2015-04-01 | 2016-06-30 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1235000 | 4939000 | 6174000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184981 | W/500291301/WS | KwaZulu-Natal | VELANGEZWI SECONDARY SCHOOL | 500291301 | Maphumulo | Design | Active - Not Contracted | 2016-06-15 |  | 2024-06-30 |  |  | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184982 | DPW/UTHUKELA/ELE | KwaZulu-Natal | UTHUKELA ELECTRIFICATION | UTHUKELA | Okhahlamba | Pre - Feasibility | Active - Contracted | 2018-01-04 |  | 2022-12-30 |  |  | 997000 | 4540000 | 5537000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184983 | W/500290006/WS | KwaZulu-Natal | UNTUNJAMBILI PRIMARY SCHOOL | 500290006 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2016-06-13 | 2018-09-12 | 2023-03-31 | 2024-05-05 | 2025-01-31 | 155545 | 5688556 | 5844101 | Education Infrastructure Grant | Upgrading and Additions
|  | 184984 | DB/500146002/WS | KwaZulu-Natal | FUNDULWAZI SENIOR PRIMARY SCHOOL | 500146002 | Inkosi Langalibalele | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184985 | W/500268139/WS | KwaZulu-Natal | SIQONGWENI SECONDARY SCHOOL | 500222814 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2018-01-04 |  | 2023-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184987 | ET/500134754/WS | KwaZulu-Natal | EMTHANDENI PRIMARY SCHOOL | 500134754 | Maphumulo | Final Completion | Active - Contracted | 2018-06-16 | 2019-03-30 | 2023-06-30 | 2020-03-30 | 2023-03-30 | 500000 | 1000000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184988 | ET/500138158/WS | KwaZulu-Natal | ENSIKENI PRIMARY SCHOOL | 500138158 | KwaDukuza | Final Completion | Active - Contracted | 2018-06-16 | 2018-09-10 | 2023-12-30 | 2020-03-30 | 2023-03-30 | 500000 | 1000000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184989 | ET/500140822/WS | KwaZulu-Natal | ESINDI PRIMARY SCHOOL | 500140822 | Maphumulo | Final Completion | Active - Contracted | 2018-01-16 | 2018-07-10 | 2023-07-01 | 2020-03-30 | 2023-03-30 | 500000 | 1000000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 184993 | ET/500145188/WS | KwaZulu-Natal | FOLWENI HIGH SCHOOL | 500145188 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-01-16 | 2019-09-10 | 2024-06-30 | 2025-09-30 | 2025-06-30 | 973577 | 4435182 | 5408759 | Education Infrastructure Grant | Upgrading and Additions
|  | 184996 | ET/500324009/WS | KwaZulu-Natal | MANGCENGEZA JUNIOR SECONDARY SCHOOL | 500324009 | Maphumulo | Final Completion | Active - Contracted | 2018-11-23 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-06-30 | 892539 | 4066013 | 4958552 | Education Infrastructure Grant | Upgrading and Additions
|  | 185000 | DB/500201206/WS | KwaZulu-Natal | MASOTSHENI PRIMARY SCHOOL | 500201206 | Nqutu | Construction 26% - 50% | Active - Contracted | 2016-06-13 | 2018-09-12 | 2023-03-31 | 2024-05-05 | 2025-01-31 | 105660 | 481340 | 587000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185001 | W/500254042/WS | KwaZulu-Natal | QUBUKA PRIMARY SCHOOL | 500254042 | Mtubatuba | Design | Active - Not Contracted | 2020-08-21 |  | 2023-07-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185002 | DB/500201280/WS | KwaZulu-Natal | MASULUMANE COMBINED PRIMARY SCHOOL | 500201280 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2022-09-30 |  |  | 320000 | 1500000 | 1820000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185004 | DB/500202242/WS | KwaZulu-Natal | MATSHANHLOLA PRIMARY SCHOOL | 500202242 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185005 | DB/500213490/WS | KwaZulu-Natal | MNOTHO PRIMARY SCHOOL | 500213490 | Mtubatuba | Design | Active - Contracted | 2017-06-06 |  | 2024-12-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185006 | DB/500426906/WS | KwaZulu-Natal | MOYENI PRIMARY SCHOOL. | 500426906 | eThekwini | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185008 | I/500151441/WS | KwaZulu-Natal | GQUGQUMA PRIMARY SCHOOL | 500151441 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-05-03 | 2022-03-01 | 2022-09-30 | 2022-11-30 | 2023-02-04 | 191000 | 1304000 | 1495000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185010 | DB/500202612/WS | KwaZulu-Natal | MAVUNDLA PRIMARY SCHOOL | 500202612 | Ray Nkonyeni | Design | Active - Contracted | 2016-06-06 |  | 2022-09-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185011 | DB/500202908/WS | KwaZulu-Natal | MAWOMBE SECONDARY SCHOOL | 500202908 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2022-09-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185017 | I/500165871/WS | KwaZulu-Natal | INSUZE-GCWENSA PRIMARY SCHOOL | 500165834 | Alfred Duma | Practical Completion (100%) | Active - Contracted | 2019-08-20 | 2022-03-01 | 2022-07-30 | 2022-09-30 | 2023-11-30 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185038 | C/500126355/ECD | KwaZulu-Natal | EBUHLENIBENKOSI SECONDARY SCHOOL | 500126355 | Ulundi | Practical Completion (100%) | Active - Contracted | 2017-02-20 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 895000 | 2105000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185060 | W/500440411/WS | KwaZulu-Natal | NKAYISHANA PRIMARY SCHOOL | 500440411 | Msinga | Design | Active - Contracted | 2018-01-04 |  | 2024-06-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185066 | DB/500446923/WS | KwaZulu-Natal | HOLISIZWE PRIMARY SCHOOL | 500446923 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185067 | DB/500303733/WS | KwaZulu-Natal | MBOMVU PRIMARY SCHOOL | 500303733 | Umvoti | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 99341 | 541603 | 640944 | Education Infrastructure Grant | Upgrading and Additions
|  | 185068 | DB/500205387/WS | KwaZulu-Natal | MBUYISENI HIGH SCHOOL | 500205387 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2020-04-30 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 347157 | 1581495 | 1928652 | Education Infrastructure Grant | Upgrading and Additions
|  | 185069 | DB/500205757/WS | KwaZulu-Natal | MCHITHEKI HIGH SCHOOL | 500205757 | Nongoma | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185072 | DB/500205979/WS | KwaZulu-Natal | MCUTHUNGU SENIOR PRIMARY SCHOOL | 500205979 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185075 | DB/500206460/WS | KwaZulu-Natal | MDUDLA PRIMARY SCHOOL | 500206460 | Nkandla | Feasibility | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185076 | DB/500206682/WS | KwaZulu-Natal | MDUNA PRIMARY SCHOOL | 500206682 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 109227 | 678773 | 788000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185077 | DB/500207607/WS | KwaZulu-Natal | MENGU PRIMARY SCHOOL | 500207607 | Umhlabuyalingana | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2019-09-12 | 2023-01-31 | 2023-05-05 | 2027-01-31 | 497804 | 2267775 | 2765579 | Education Infrastructure Grant | Upgrading and Additions
|  | 185079 | DB/500208458/WS | KwaZulu-Natal | MFEKAYE PRIMARY SCHOOL | 500208458 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2023-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185080 | DB/500310097/WS | KwaZulu-Natal | MFULAWEZWE JUNIOR PRIMARY SCHOOL | 500310097 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185081 | DB/500209124/WS | KwaZulu-Natal | MGANGATHO PRIMARY SCHOOL | 500209124 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-31 | 2023-01-31 | 2027-01-31 | 406304 | 1850940 | 2257244 | Education Infrastructure Grant | Upgrading and Additions
|  | 185082 | DB/500209383/WS | KwaZulu-Natal | MGEDULA PRIMARY SCHOOL | 500209383 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185083 | DB/500210641/WS | KwaZulu-Natal | MHLUPHEKI JUNIOR SECONDARY SCHOOL | 500210641 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 110728 | 679272 | 790000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185085 | DB/500212047/WS | KwaZulu-Natal | MKHOMAZANA PRIMARY SCHOOL | 500212047 | Dr Nkosazana Dlamini Zuma | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185086 | DB/500212565/WS | KwaZulu-Natal | MLAMULA PRIMARY SCHOOL | 500212565 | Umhlabuyalingana | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2020-06-30 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 376034 | 1713044 | 2089078 | Education Infrastructure Grant | Upgrading and Additions
|  | 185090 | DB/500310245/WS | KwaZulu-Natal | MNANDI PRIMARY SCHOOL | 500310245 | Nkandla | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-30 | 2022-01-30 | 2027-01-30 | 392125 | 1786349 | 2178474 | Education Infrastructure Grant | Upgrading and Additions
|  | 185096 | DB/500211680/WS | KwaZulu-Natal | MPANZAKAZI PRIMARY SCHOOL | 500211680 | Big Five Hlabisa | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2019-09-12 | 2023-01-30 | 2023-05-05 | 2027-01-31 | 289698 | 1319736 | 1609434 | Education Infrastructure Grant | Upgrading and Additions
|  | 185097 | DB/500216228/WS | KwaZulu-Natal | MPEMVU PRIMARY SCHOOL | 500216228 | Mfolozi | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185098 | DB/500216339/WS | KwaZulu-Natal | MPHAHLENI SECONDARY SCHOOL | 500216339 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185099 | DB/500216376/WS | KwaZulu-Natal | MPHAKATHINI PRIMARY SCHOOL | 500216376 | Umhlabuyalingana | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 367834 | 1675687 | 2043521 | Education Infrastructure Grant | Upgrading and Additions
|  | 185100 | DB/500304843/WS | KwaZulu-Natal | MPHATHESITHA HIGH SCHOOL | 500304843 | Nkandla | Construction 1% - 25% | Active - Contracted | 2016-06-13 | 2018-09-12 | 2023-03-31 | 2024-05-05 | 2025-01-31 | 150300 | 684700 | 835000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185101 | DB/500217116/WS | KwaZulu-Natal | MPOLIMPOLINI PRIMARY SCHOOL | 500217116 | Nkandla | Construction 76% - 99% | Active - Contracted | 2016-06-13 | 2019-09-12 | 2023-01-30 | 2023-05-05 | 2027-01-31 | 414989 | 1890504 | 2305493 | Education Infrastructure Grant | Upgrading and Additions
|  | 185102 | DB/500301208/WS | KwaZulu-Natal | MPONTSHINI JUNIOR PRIMARY SCHOOL | 500301208 | Mtubatuba | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-03-31 | 2023-01-30 | 2022-01-30 | 2027-01-30 | 222761 | 1014800 | 1237561 | Education Infrastructure Grant | Upgrading and Additions
|  | 185103 | DB/500218189/WS | KwaZulu-Natal | MSELENI JUNIOR PRIMARY SCHOOL | 500218189 | Umhlabuyalingana | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2021-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 324517 | 1478356 | 1802873 | Education Infrastructure Grant | Upgrading and Additions
|  | 185104 | DB/500335035/WS | KwaZulu-Natal | MSESHI PRIMARY SCHOOL | 500335035 | Umhlabuyalingana | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185105 | DB/500218374/WS | KwaZulu-Natal | MSHANGUZANA HIGH SCHOOL | 500218374 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-09-12 | 2024-03-30 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185106 | DB/500309875/WS | KwaZulu-Natal | MSHUDU HIGH SCHOOL | 500309875 | Umhlabuyalingana | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2020-06-30 | 2023-02-28 | 2022-06-30 | 2027-06-30 | 266157 | 1212494 | 1478651 | Education Infrastructure Grant | Upgrading and Additions
|  | 185107 | DB/500410367/WS | KwaZulu-Natal | MSINDAZWE PRIMARY SCHOOL | 500410367 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2020-06-30 | 2023-03-30 | 2022-06-30 | 2027-06-30 | 42270 | 539730 | 582000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185110 | DB/500307842/WS | KwaZulu-Natal | MTHEKELEZI LOWER PRIMARY SCHOOL | 500307842 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 337959 | 1539590 | 1877549 | Education Infrastructure Grant | Upgrading and Additions
|  | 185111 | DB/500219373/WS | KwaZulu-Natal | MTHOMBOTHI PRIMARY SCHOOL | 500219373 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2019-05-01 | 2020-05-01 | 2023-03-15 | 2022-06-15 | 2025-06-15 | 596212 | 2716076 | 3312288 | Education Infrastructure Grant | Upgrading and Additions
|  | 185112 | DB/500219484/WS | KwaZulu-Natal | MTHONGA JUNIOR SECONDARY | 500219484 | uMhlathuze | Construction 26% - 50% | Active - Contracted | 2019-06-02 | 2020-05-20 | 2023-03-30 | 2023-05-05 | 2025-01-31 | 500000 | 2350000 | 2850000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185113 | DB/500327265/WS | KwaZulu-Natal | MTSHELEKWANE SECONDARY SCHOOL | 500327265 | Jozini | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185114 | ET/500220483/WS | KwaZulu-Natal | MUKELANI SENIOR PRIMARY SCHOOL | 500220483 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-06-02 | 2023-06-30 | 2023-06-30 | 2024-06-30 | 2025-06-30 | 737167 | 3358205 | 4095372 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185115 | DB/500220557/WS | KwaZulu-Natal | MUMBE PRIMARY SCHOOL | 500220557 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-06 | 2019-09-12 | 2022-09-30 | 2023-05-05 | 2025-01-31 | 450000 | 1250000 | 1700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185116 | DB/500222555/WS | KwaZulu-Natal | MZONDI PRIMARY SCHOOL | 500222555 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2019-09-12 | 2024-03-30 | 2023-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185118 | DB/500222999/WS | KwaZulu-Natal | NAMANENI HIGH SCHOOL | 500222999 | Jozini | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2019-09-12 | 2024-03-30 | 2023-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185119 | DB/500223554/WS | KwaZulu-Natal | NCECENI PRIMARY SCHOOL | 500223480 | Nongoma | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185120 | DB/500223591/WS | KwaZulu-Natal | NCEPHENI PRIMARY SCHOOL | 500223591 | Nqutu | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185121 | DB/500238391/WS | KwaZulu-Natal | NSONGWENI JUNIOR PRIMARY SCHOOL | 500238391 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-12-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185122 | DB/500310763/WS | KwaZulu-Natal | PHAKAMANI PRIMARY SCHOOL | 500310763 | Umhlabuyalingana | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185123 | DB/500247382/WS | KwaZulu-Natal | PHAKWE PRIMARY SCHOOL | 500247382 | Umvoti | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185124 | DB/500247419/WS | KwaZulu-Natal | PHALANE PRIMARY (NKANDLA) | 500247419 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 529000 | 2412000 | 2941000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185125 | DB/500448403/WS | KwaZulu-Natal | PHANDAPHANSI PRIMARY SCHOOL | 500448403 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 222000 | 1010000 | 1232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185126 | DB/500248011/WS | KwaZulu-Natal | PHATHWA SECONDARY SCHOOL | 500248011 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2019-05-15 | 2020-10-01 | 2023-03-15 | 2022-03-15 | 2025-10-15 | 476782 | 2172006 | 2648788 | Education Infrastructure Grant | Upgrading and Additions
|  | 185127 | DB/500248122/WS | KwaZulu-Natal | PHEMBELA SECONDARY SCHOOL | 500248122 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 457000 | 2081000 | 2538000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185128 | DB/500248344/WS | KwaZulu-Natal | PHEPHA JUNIOR PRIMARY SCHOOL | 500248344 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185129 | DB/500248640/WS | KwaZulu-Natal | PHIKWASE HIGH SCHOOL | 500248640 | Ulundi | Design | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185130 | DB/500249935/WS | KwaZulu-Natal | PHUMULANI SECONDARY SCHOOL | 500249935 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 284000 | 1292000 | 1576000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185131 | DB/500250083/WS | KwaZulu-Natal | PHUNGAZA HIGH SCHOOL | 500250083 | Jozini | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185132 | DB/500250157/WS | KwaZulu-Natal | PHUNYANE PRIMARY SCHOOL | 500250157 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185133 | DB/500252155/WS | KwaZulu-Natal | QALANGOKUHLE PRIMARY SCHOOL | 500252155 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185134 | DB/500252599/WS | KwaZulu-Natal | QEDUSIZI PRIMARY SCHOOL | 500252599 | Nqutu | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 383000 | 1743000 | 2126000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185135 | DB/500252784/WS | KwaZulu-Natal | QHINQA HIGH SCHOOL | 500252784 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 379000 | 2108000 | 2487000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185136 | DB/500253191/WS | KwaZulu-Natal | QHUBINYATHI SS | 500253191 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 151000 | 686000 | 837000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185137 | DB/500253487/WS | KwaZulu-Natal | QINISELANI SENIOR PRIMARY SCHOOL | 500253487 | eThekwini | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2025-09-30 | 363860 | 1657583 | 2021443 | Education Infrastructure Grant | Upgrading and Additions
|  | 185138 | DB/500253561/WS | KwaZulu-Natal | QOMUKUPHILA COMBINED PRIMARY SCHOOL | 500253561 | Big Five Hlabisa | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185139 | DB/500254338/WS | KwaZulu-Natal | QUNWANE PRIMARY SCHOOL | 500254338 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185140 | DB/500254856/WS | KwaZulu-Natal | RATANG PRIMARY SCHOOL | 500254856 | Nqutu | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185141 | DB/500256003/WS | KwaZulu-Natal | RIVERSBEND PRIMARY SCHOOL | 500256003 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-06 |  | 2024-11-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185142 | DB/500256706/WS | KwaZulu-Natal | RUSTFONTEIN PRIMARY SCHOOL | 500256706 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 189000 | 860000 | 1049000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185143 | DB/500257372/WS | KwaZulu-Natal | SAKHAYEDWA PRIMARY SCHOOL | 500257372 | Nkandla | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2025-09-30 | 341888 | 1557492 | 1899380 | Education Infrastructure Grant | Upgrading and Additions
|  | 185144 | DB/500446960/WS | KwaZulu-Natal | SAKHISIZWE SECONDARY SCHOOL | 500446960 | eThekwini | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2025-08-31 | 580760 | 2645683 | 3226443 | Education Infrastructure Grant | Upgrading and Additions
|  | 185145 | DB/500325045/WS | KwaZulu-Natal | SANDLASENKOSI SECONDARY SCHOOL | 500325045 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185146 | DB/500337625/WS | KwaZulu-Natal | SANDOKUVELA PRIMARY SCHOOL | 500337625 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-13 |  | 2024-11-30 |  |  | 450000 | 1892000 | 2342000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185147 | DB/500258334/WS | KwaZulu-Natal | SANGWENI PRIMARY SCHOOL | 500258334 | Umvoti | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2025-09-30 | 650656 | 2964099 | 3614755 | Education Infrastructure Grant | Upgrading and Additions
|  | 185148 | DB/500314685/WS | KwaZulu-Natal | SANQOBA JUNIOR PRIMARY SCHOOL | 500314685 | Umhlabuyalingana | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185149 | DB/500258667/WS | KwaZulu-Natal | SAPHUMULA SECONDARY SCHOOL | 500258667 | eThekwini | Construction 1% - 25% | Active - Not Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2022-05-05 | 2025-06-30 | 342033 | 1558152 | 1900185 | Education Infrastructure Grant | Upgrading and Additions
|  | 185150 | DB/500259370/WS | KwaZulu-Natal | SCHITSDRIFT PRIMARY SCHOOL | 500259370 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-06 |  | 2024-11-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185152 | ET/500260480/WS | KwaZulu-Natal | SENZWESIHLE SENIOR PRIMARY SCHOOL | 500260480 | eThekwini | Construction 76% - 99% | Active - Contracted | 2018-06-02 | 2021-03-01 | 2023-09-30 | 2022-09-30 | 2023-04-30 | 626733 | 2855117 | 3481850 | Education Infrastructure Grant | Upgrading and Additions
|  | 185153 | DB/500261923/WS | KwaZulu-Natal | SHESHANI PRIMARY SCHOOL | 500261923 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185154 | DB/500262108/WS | KwaZulu-Natal | SHIKISHELA PRIMARY SCHOOL | 500262108 | Mtubatuba | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2025-08-31 | 1098220 | 5003001 | 6101221 | Education Infrastructure Grant | Upgrading and Additions
|  | 185155 | DB/500307433/WS | KwaZulu-Natal | SHIYINKOSI SECONDARY SCHOOL | 500307433 | Big Five Hlabisa | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185156 | DB/500309246/WS | KwaZulu-Natal | SIBAHLENGEMVELO JUNIOR PRIMARY SCHOOL | 500309246 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185159 | W/500228845/WS. | KwaZulu-Natal | NGQOKWANE HIGH SCHOOL | 500228845 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2019-03-04 | 2020-03-01 | 2023-03-06 | 2023-03-06 | 2023-03-06 | 812887 | 3703153 | 4516040 | Education Infrastructure Grant | Upgrading and Additions
|  | 185161 | W/500228475/WS | KwaZulu-Natal | NGONO SECONDARY SCHOOL | 500228475 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-04-27 | 2023-03-30 | 2023-01-30 | 2023-03-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185163 | W/500227402/WS | KwaZulu-Natal | NGAYIPHI PRIMARY SCHOOL | 500227402 | Ndwedwe | Construction 51% - 75% | Active - Contracted | 2019-04-16 | 2020-05-30 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 775385 | 3532311 | 4307696 | Education Infrastructure Grant | Upgrading and Additions
|  | 185167 | W/Zul.New12/029/WS | KwaZulu-Natal | PRINCESS PHUMZILE PRIMARY SCHOOL (ULUNDI SECTION D) | 500494949 | Ulundi | Design | Active - Contracted | 2018-10-01 |  | 2024-03-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185173 | W/500222814/WS | KwaZulu-Natal | NADI PRIMARY SCHOOL | 500222814 | uMngeni | Design | Active - Not Contracted | 2018-01-04 |  | 2024-02-16 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185180 | W/500215821/WS | KwaZulu-Natal | MOYAMUHLE PRIMARY SCHOOL | 500215821 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2020-04-22 | 2021-04-01 | 2023-09-30 | 2021-12-31 | 2023-03-31 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185181 | I/500327746/WS | KwaZulu-Natal | INTABABUSIKA PRIMARY SCHOOL | 500327746 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2021-01-25 | 2023-03-30 | 2022-11-01 | 2023-02-05 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185183 | W/500213749/WS | KwaZulu-Natal | MNTONJANI SECONDARY SCHOOL | 500213749 | Mthonjaneni | Design | Active - Not Contracted | 2020-08-03 |  | 2025-03-30 |  |  | 50000 | 100000 | 150000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185187 | W/500211048/WS | KwaZulu-Natal | MIDDLEFIELD PRIMARY SCHOOL | 500211048 | Mpofana | Practical Completion (100%) | Active - Contracted | 2017-04-01 | 2018-04-27 | 2023-09-30 | 2022-03-19 | 2023-03-19 | 18000 | 82000 | 100000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185190 | I/500326118/UA | KwaZulu-Natal | MASIPHULA SECONDARY SCHOOL | 500326118 | uPhongolo | Design | Active - Contracted | 2019-05-03 |  | 2026-03-31 |  |  | 11700000 | 65000000 | 76700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185192 | C/500189255/WS | KwaZulu-Natal | LUVISI PRIMARY SCHOOL (RETENDER) | 500189255 | Nqutu | Practical Completion (100%) | Active - Contracted | 2017-10-20 | 2019-12-20 | 2023-04-20 | 2024-04-20 | 2025-04-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185193 | C/500269730/UA | KwaZulu-Natal | SIYAKHANYISA PRIMARY SCHOOL | 500269730 | uMhlathuze | Tender | Active - Not Contracted | 2019-01-20 |  | 2026-09-20 |  |  | 5025000 | 20100000 | 25125000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185194 | I/500209753/WS | KwaZulu-Natal | MGULWANE PRIMARY SCHOOL | 500209753 | uPhongolo | Construction 76% - 99% | Active - Contracted | 2019-05-03 | 2020-05-10 | 2023-03-30 | 2022-10-28 | 2023-10-30 | 504000 | 2296000 | 2800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185195 | I/New/WS | KwaZulu-Natal | MGUTHSWA SCHOOL | New | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185198 | I/500216709/WS | KwaZulu-Natal | MPIKANINA HIGH SCHOOL | 500216709 | Nongoma | Practical Completion (100%) | Active - Contracted | 2019-05-03 | 2019-05-10 | 2022-06-28 | 2022-10-28 | 2023-03-30 | 699000 | 3415000 | 4114000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185199 | I/500308987/WS | KwaZulu-Natal | NQOBANI PRIMARY SCHOOL | 500308987 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2017-06-13 | 2022-06-28 | 2022-01-28 | 2023-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185200 | I/500227920/WS | KwaZulu-Natal | NGENGENI PRIMARY SCHOOL | 500227920 | Nongoma | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2023-09-30 | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185202 | DB/500111222/WS | KwaZulu-Natal | BONGOKUHLE HIGH SCHOOL | 500111222 | Nongoma | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2022-02-02 | 2025-03-22 | 2025-02-01 | 2025-04-02 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185203 | DB/500262848/WS | KwaZulu-Natal | SIBHAMU HIGH SCHOOL | 500262848 | Jozini | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185205 | ET/500263477/WS | KwaZulu-Natal | SIBUKEYANA PRIMARY SCHOOL | 500263477 | eThekwini | Final Completion | Active - Contracted | 2018-06-02 | 2018-08-27 | 2023-03-30 | 2020-03-30 | 2023-03-30 | 679092 | 3093640 | 3772732 | Education Infrastructure Grant | Upgrading and Additions
|  | 185206 | DB/500263514/WS | KwaZulu-Natal | SIBUKOSETHU HIGH SCHOOL | 500263514 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185207 | DB/500429829/WS | KwaZulu-Natal | SIBUTHA SECONDARY SCHOOL | 500429829 | uMuziwabantu | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185208 | DB/500263736/WS | KwaZulu-Natal | SIBUYANE PRIMARY SCHOOL | 500263736 | Umvoti | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185209 | DB/500263810/WS | KwaZulu-Natal | SICELIMFUNDO PRIMARY SCHOOL | 500263810 | Nqutu | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2025-08-31 | 1007243 | 4588553 | 5595796 | Education Infrastructure Grant | Upgrading and Additions
|  | 185210 | DB/500264106/WS | KwaZulu-Natal | SIDUMUKA PRIMARY SCHOOL | 500264106 | Nkandla | Construction 1% - 25% | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185211 | DB/500326784/WS | KwaZulu-Natal | SIHAMBAKAHLE JUNIOR PRIMARY SCHOOL | 500326784 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185212 | DB/500264661/WS | KwaZulu-Natal | SIHANGWANA COMBINED PRIMARY SCHOOL | 500264661 | Umhlabuyalingana | Construction 26% - 50% | Active - Contracted | 2019-05-15 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2025-09-30 | 885747 | 4035071 | 4920818 | Education Infrastructure Grant | Upgrading and Additions
|  | 185213 | DB/500265105/WS | KwaZulu-Natal | SIKHULILE SECONDARY SCHOOL | 500265105 | uMshwathi | Construction 26% - 50% | Active - Contracted | 2019-05-15 | 2021-01-01 | 2023-03-01 | 2023-05-05 | 2025-08-31 | 44842 | 399854 | 444696 | Education Infrastructure Grant | Upgrading and Additions
|  | 185214 | DB/500265290/WS | KwaZulu-Natal | SIKOTHINI PRIMARY SCHOOL | 500265290 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-06-06 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2025-08-31 | 475878 | 2167890 | 2643768 | Education Infrastructure Grant | Upgrading and Additions
|  | 185215 | DB/500265364/WS | KwaZulu-Natal | SILANDA COMBINED PRIMARY SCHOOL | 500265364 | Nkandla | Construction 1% - 25% | Active - Contracted | 2017-06-06 | 2020-10-01 | 2023-01-29 | 2022-09-15 | 2025-09-15 | 950080 | 2328144 | 3278224 | Education Infrastructure Grant | Upgrading and Additions
|  | 185216 | DB/500266326/WS | KwaZulu-Natal | SINDAWONYE PRIMARY SCHOOL | 500266326 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 465000 | 2119000 | 2584000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185217 | DB/500323010/WS | KwaZulu-Natal | SINEVUSO SECONDARY SCHOOL | 500323010 | Ubuhlebezwe | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 282000 | 1283000 | 1565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185218 | DB/500429755/WS | KwaZulu-Natal | SINGISI SECONDARY SCHOOL | 500429755 | Umzimkhulu | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 316000 | 1438000 | 1754000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185219 | DB/500267177/WS | KwaZulu-Natal | SIPHELELE PRIMARY SCHOOL | 500267177 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185220 | DB/500337773/WS | KwaZulu-Natal | SISHISHILI PRIMARY SCHOOL | 500337773 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185221 | DB/500341325/WS | KwaZulu-Natal | SITHEMBINHLANHLA SECONDARY SCHOOL | 500341325 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 118000 | 538000 | 656000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185222 | DB/500269360/WS | KwaZulu-Natal | SIYABATHWA COMBINED PRIMARY SCHOOL | 500269360 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185223 | DB/500334184/WS | KwaZulu-Natal | SIYABONGA PRIMARY SCHOOL | 500334184 | Mtubatuba | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185224 | DB/500269545/WS | KwaZulu-Natal | SIYACATHULA PRIMARY SCHOOL | 500269545 | Nqutu | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185225 | DB/500269804/WS | KwaZulu-Natal | SIYAKHULA JUNIOR SECONDARY SCHOOL | 500269804 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185226 | DB/500339808/WS | KwaZulu-Natal | SIYANDA SECONDARY SCHOOL | 500339808 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185227 | DB/500445998/WS | KwaZulu-Natal | SIYAPHAMBILI PRIMARY SCHOOL | 500414955 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2017-06-06 | 2020-03-30 | 2023-03-30 | 2023-03-30 | 2024-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185228 | ET/500270359/WS | KwaZulu-Natal | SIYATHUTHUKA SECONDARY SCHOOL | 500270359 | eThekwini | Final Completion | Active - Contracted | 2018-06-23 | 2018-08-31 | 2023-10-02 | 2020-03-19 | 2023-03-30 | 410644 | 1870713 | 2281357 | Education Infrastructure Grant | Upgrading and Additions
|  | 185229 | DB/500270433/WS | KwaZulu-Natal | SIYAVUNA COMBINED PRIMARY SCHOOL | 500270433 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185230 | DB/500270655/WS | KwaZulu-Natal | SIYELULAMA HIGH SCHOOL | 500270655 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185231 | DB/500271321/WS | KwaZulu-Natal | SIZATHINA JUNIOR SECONDARY SCHOOL | 500342805 | Inkosi Langalibalele | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185232 | DB/500271543/WS | KwaZulu-Natal | SIZOFIKA PRIMARY SCHOOL | 500271543 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185233 | DB/500271580/WS | KwaZulu-Natal | SIZOMUNYE PRIMARY SCHOOL | 500271580 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 362000 | 1651000 | 2013000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185234 | DB/500272209/WS | KwaZulu-Natal | SLAVU JUNIOR PRIMARY SCHOOL | 500272209 | Umzumbe | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 356000 | 1620000 | 1976000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185235 | DB/500336256/WS | KwaZulu-Natal | SOGODI PRIMARY SCHOOL | 500167832 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-03-30 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185236 | DB/500272727/WS | KwaZulu-Natal | SOKESIMBONE HIGH SCHOOL | 500272727 | Okhahlamba | Design | Active - Contracted | 2017-06-06 |  | 2024-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185237 | DB/500273060/WS | KwaZulu-Natal | SOMFULA SECONDARY SCHOOL | 500273060 | Big Five Hlabisa | Construction 51% - 75% | Active - Contracted | 2017-06-06 | 2020-05-29 | 2023-01-29 | 2022-02-07 | 2025-03-14 | 180424 | 821933 | 1002357 | Education Infrastructure Grant | Upgrading and Additions
|  | 185238 | DB/500273578/WS | KwaZulu-Natal | SONGENI COMBINED PRIMARY SCHOOL | 500273578 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-28 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185239 | DB/500258371/WS | KwaZulu-Natal | SONKABI PRIMARY SCHOOL | 500258371 | Nkandla | Tender | Active - Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185240 | DB/500273800/WS | KwaZulu-Natal | SONQOBQSIMUNYE JUNIOR SECONDARY SCHOOL | 500273800 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 127000 | 576000 | 703000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185241 | DB/500274281/WS | KwaZulu-Natal | SOVANE PRIMARY SCHOOL | 500274281 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185242 | DB/500428053/WS | KwaZulu-Natal | ST ALOIS JUNIOR SECONDARY SCHOOL | 500428053 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185243 | DB/500428127/WS | KwaZulu-Natal | ST BARNABAS JUNIOR SECONDARY SCOOL | 500428127 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 310000 | 1413000 | 1723000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185244 | DB/500223702/WS | KwaZulu-Natal | ST CHADS HIGH SCHOOL | 500223702 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2025-01-29 |  |  | 163846 | 746408 | 910254 | Education Infrastructure Grant | Upgrading and Additions
|  | 185245 | DB/500275317/WS | KwaZulu-Natal | ST CHADS PRIMARY SCHOOL | 500275317 | Alfred Duma | Construction 26% - 50% | Approved | 2017-06-06 |  | 2025-01-25 |  |  | 380579 | 1733749 | 2114328 | Education Infrastructure Grant | Upgrading and Additions
|  | 185246 | DB/500428201/WS | KwaZulu-Natal | ST FAITH COMBINED SCHOOL | 500428201 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 511000 | 2328000 | 2839000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185247 | DB/500276427/WS | KwaZulu-Natal | ST NICHOLAUS PRIMARY SCHOOL | 500276427 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 408000 | 1858000 | 2266000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185248 | DB/500276464/WS | KwaZulu-Natal | ST NIVARDS COMBINED PRIMARY SCHOOL | 500276464 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 387000 | 1765000 | 2152000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185249 | DB/500278092/WS | KwaZulu-Natal | STOCKTON COMBINED PRIMARY SCHOOL | 500278092 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-04-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185250 | DB/500428534/WS | KwaZulu-Natal | TEX NYBERT JUNIOR SECONDARY SCHOOL | 500428534 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 306000 | 1395000 | 1701000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185252 | DB/500428571/WS | KwaZulu-Natal | THEMBALIHLE JUNIOR SECONDARY SCHOOL | 500428571 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 300000 | 1366000 | 1666000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185253 | DB/500308506/WS | KwaZulu-Natal | THUBALEMFUNDO JUNIOR SECONDARY SCHOOL | 500308506 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185254 | DB/500283420/WS | KwaZulu-Natal | THUKEYANA PRIMARY SCHOOL | 500283420 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 246000 | 1119000 | 1365000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185255 | DB/500283457/WS | KwaZulu-Natal | THULASIBONE HIGH SCHOOL | 500283457 | Nkandla | Construction 26% - 50% | Active - Contracted | 2017-06-06 |  | 2024-04-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185256 | DB/500442224/WS | KwaZulu-Natal | THULASIZWE PRIMARY SCHOOL | 500442224 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 494000 | 2249000 | 2743000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185258 | DB/500275169/WS | KwaZulu-Natal | THUTHUKANI SECONDARY SCHOOL | 500275169 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 385000 | 1754000 | 2139000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185259 | DB/500284086/WS | KwaZulu-Natal | TLOKWENG PRIMARY SCHOOL | 500284086 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-04-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185260 | ET/500284123/WS | KwaZulu-Natal | TOBI SENIOR PRIMARY SCHOOL | 500284123 | eThekwini | Final Completion | Active - Contracted | 2016-04-01 | 2019-03-30 | 2023-03-30 | 2020-03-30 | 2023-04-30 | 448136 | 2041508 | 2489644 | Education Infrastructure Grant | Upgrading and Additions
|  | 185261 | DB/500428682/WS | KwaZulu-Natal | TSAWULE JUNIOR SECONDARY SCHOOL | 500428682 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 172000 | 785000 | 957000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185262 | DB/500428719/WS | KwaZulu-Natal | TSHAKA`S SENIOR PRIMARY SCHOOL | 500428719 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185263 | ET/500258011/WS | KwaZulu-Natal | TSHANYANA PRIMARY SCHOOL | 500285011 | eThekwini | Final Completion | Active - Contracted | 2016-06-13 | 2019-01-27 | 2023-03-30 | 2022-03-30 | 2023-04-30 | 568050 | 2587781 | 3155831 | Education Infrastructure Grant | Upgrading and Additions
|  | 185264 | DB/500285307/WS | KwaZulu-Natal | TSHONGWE PRIMARY SCHOOL | 500285307 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2024-04-19 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185265 | DB/500287638/WS | KwaZulu-Natal | UMHLABASHANA JUNIOR PRIMARY SCHOOL | 500287638 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 249000 | 1133000 | 1382000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185266 | DB/500287601/WS | KwaZulu-Natal | UMHLABASHANA JUNIOR PRIMARY SCHOOL | 500287601 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 244000 | 1112000 | 1356000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185267 | DB/500401857/WS | KwaZulu-Natal | UMKHOSI HIGH SCHOOL | 500401857 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185268 | DB/500288563/WS | KwaZulu-Natal | Uymoya Omusha Primary School | DB/500288563/WS | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 189000 | 859000 | 1048000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185269 | DB/500289377/WS | KwaZulu-Natal | UMVULO PRIMARY SCHOOL | 500289377 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185270 | DB/500290043/WS | KwaZulu-Natal | UPHANDE PRIMARY SCHOOL | 500290043 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185272 | DB/500290635/WS | KwaZulu-Natal | UXOLO NOKUZWANA SECONDARY SCHOOL | 500290635 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185273 | DB/500290672/WS | KwaZulu-Natal | UYAYA SECONDARY SCHOOL | 500290672 | uMlalazi | Design | Active - Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185274 | DB/500291412/WS | KwaZulu-Natal | VELAPHI HIGH SCHOOL | 500291412 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185275 | DB/500291523/WS | KwaZulu-Natal | VELIMEMEZE PRIMARY SCHOOL | 500291523 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 362000 | 1651000 | 2013000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185276 | DB/500428941/WS | KwaZulu-Natal | VICTORY JUNIOR SECONDARY SCHOOL | 500428941 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 329000 | 1500000 | 1829000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185277 | DB/500292337/WS | KwaZulu-Natal | VILLA MARIA PRIMARY SCHOOL | 500292337 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 170000 | 775000 | 945000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185278 | DB/500293669/WS | KwaZulu-Natal | VULULWAZI PRIMARY SCHOOL | 500293669 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185279 | DB/500293780/WS | KwaZulu-Natal | VUMANDABA SECONDARY SCHOOL | 500293780 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 36000 | 165000 | 201000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185280 | DB/500293965/WS | KwaZulu-Natal | VUMUKUKHANYA JUNIOR PRIMARY SCHOOL | 500293965 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2027-06-07 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185281 | DB/500447367/WS | KwaZulu-Natal | W MTSHILO PRIMARY SCHOOL | 500447367 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185282 | DB/500296037/WS | KwaZulu-Natal | WETSIE SECONDARY SCHOOL | 500296037 | Nkandla | Practical Completion (100%) | Active - Contracted | 2017-06-06 |  | 2024-04-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185283 | DB/500296185/WS | KwaZulu-Natal | WILDER JUNIOR PRIMARY SCHOOL | 500296185 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 553000 | 2520000 | 3073000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185285 | DB/500297887/WS | KwaZulu-Natal | YAMELA SECONDARY SCHOOL | 500297887 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-15 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185287 | DB/500299367/WS | KwaZulu-Natal | Zashuke High School | 500299367 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-01 | 2023-03-01 | 2024-12-01 | 2025-08-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185289 | DB/500300477/WS | KwaZulu-Natal | ZINDLALELE SECONDARY SCHOOL | 500300477 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-13 |  | 2024-08-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185290 | DB/500300551/WS | KwaZulu-Natal | ZINQUNYANENI COMBINED PRIMARY SCHOOL | 500300551 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2025-03-12 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185292 | DB/500301365/WS | KwaZulu-Natal | ZUNGENI PRIMARY SCHOOL | 500301365 | Nkandla | Design | Active - Contracted | 2017-06-06 |  | 2027-03-13 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185293 | DB/500302105/WS | KwaZulu-Natal | ZWELONKE HIGH SCHOOL | 500302105 | Umzimkhulu | Practical Completion (100%) | Active - Not Contracted | 2017-06-06 | 2020-05-29 | 2023-01-06 | 2022-02-09 | 2027-03-28 | 128750 | 693250 | 822000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185294 | DB//WS | KwaZulu-Natal | NDUBEKE SCHOOL | NEW SCHOOL | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 305000 | 1390000 | 1695000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185295 | DB/500447145/ECD | KwaZulu-Natal | BAMBANANI PRIMARY SCHOOL | 500447145 | Nkandla | Tender | Active - Contracted | 2015-06-06 |  | 2026-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185297 | DB/500139786/ECD | KwaZulu-Natal | ESHANE PRIMARY SCHOOL | 500139786 | Umvoti | Tender | Active - Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185298 | DB/500140748/ECD | KwaZulu-Natal | ESIMANYAMA PRIMARY SCHOOL | 500140748 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2027-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185299 | DB/500143227/ECD | KwaZulu-Natal | EZIFUNDENI PRIMARY SCHOOL | 500143227 | Big Five Hlabisa | Design | Active - Not Contracted | 2018-06-02 |  | 2027-03-03 |  |  | 297000 | 1353000 | 1650000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185300 | DB/500143967/ECD | KwaZulu-Natal | FAHLAZA PRIMARY SCHOOL | 500143967 | Endumeni | Tender | Active - Contracted | 2016-01-01 |  | 2027-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185302 | DB/500145595/ECD | KwaZulu-Natal | FUKULA PRI SCHOOL | 500145595 | Nkandla | Design | Active - Contracted | 2016-06-13 |  | 2027-03-30 |  |  | 1074780 | 4896220 | 5971000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185303 | DB/500154327/SDS | KwaZulu-Natal | HAYINYAMA PRIMARY SCHOOL | 500154327 | uMlalazi | Design | Active - Contracted | 2016-06-06 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185304 | DB/500425648/ECD | KwaZulu-Natal | HILTOP PRIMARY SCHOOL | 500425648 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2025-03-30 |  |  | 1347000 | 539000 | 1886000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185305 | DB/500446923/ECD | KwaZulu-Natal | DB/500446923/ECD | 500446923 | Nqutu | Tender | Active - Contracted | 2018-01-01 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185307 | DB/500495467/ECD | KwaZulu-Natal | INKOSI JIYANE PRIMARY SCHOOL | 500495467 | Nkandla | Tender | Active - Contracted | 2013-04-01 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185308 | DB/500496503/ECD | KwaZulu-Natal | INKOSI NOGOTSHWA PRIMARY SCHOOL | 500496503 | Inkosi Langalibalele | Tender | Active - Contracted | 2019-04-01 |  | 2025-10-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185309 | DB/500440300/ECD | KwaZulu-Natal | LANDELANI PS | 500440300 | Nkandla | Tender | Active - Contracted | 2016-06-13 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185310 | DB/500201206/ECD | KwaZulu-Natal | MASOTSHENI PRIMARY SCHOOL | 500201206 | Nqutu | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185311 | DB/500208384/ECD | KwaZulu-Natal | MFANEFILE PRIMARY SCHOOL | 500208384 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 162000 | 835000 | 997000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185312 | DB/500210419/ECD | KwaZulu-Natal | MHLUNGWANE PRIMARY SCHOOL | 500210419 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185314 | DB/500327226/ECD | KwaZulu-Natal | MPUNGANENI PRIMARY SCHOOL | DB/500447071/RRR | Msinga | Tender | Active - Not Contracted | 2018-10-04 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185315 | DB/500221334/ECD | KwaZulu-Natal | MVAYIZA PRIMARY SCHOOL | 500221334 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185316 | DB/500224146/ECD | KwaZulu-Natal | NDABANKULU INTERMEDIATE SCHOOL | 500224146 | Msinga | Tender | Active - Contracted | 2018-01-01 |  | 2026-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185317 | DB/500343508/ECD | KwaZulu-Natal | NOMASHAKA PRIMARY SCHOOL | 500343508 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185318 | DB/500235468/ECD | KwaZulu-Natal | NONDWENI PRIMARY SCHOOL | 500235468 | Nqutu | Tender | Active - Contracted | 2016-06-06 |  | 2025-10-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185319 | DB/500239205/WS | KwaZulu-Natal | NTAMINEMIDWA HIGH SCHOOL | 500239205 | Big Five Hlabisa | Design | Proposed | 2016-06-06 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185320 | DB/500440522/ECD | KwaZulu-Natal | NTANYANA PRIMARY SCHOOL | 500440522 | Msinga | Tender | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185321 | DB/500239390/ECD | KwaZulu-Natal | NTANYANDLOVU PRIMARY SCHOOL | 500239390 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185323 | DB/500241425/ECD | KwaZulu-Natal | NYAKAZA PRIMARY SCHOOL | 500241425 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 185325 | DB/500252451/ECD | KwaZulu-Natal | QEDIPHIKA PRIMARY SCHOOL | 500252451 | Nqutu | Tender | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185326 | DB/500303770/ECD | KwaZulu-Natal | SIZAMOKUHLE PRIMARY SCHOOL | 500303770 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2025-11-30 |  |  | 241920 | 1102080 | 1344000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185327 | C/500428349/ECD | KwaZulu-Natal | STRAALHOEK PRIMARY SCHOOL | 500428349 | Dr Nkosazana Dlamini Zuma | Tender | Active - Not Contracted | 2019-02-20 |  | 2023-04-20 |  |  | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185328 | DB/500279165/ECD | KwaZulu-Natal | SWEBANE PRIMARY SCHOOL | 500279165 | Msinga | Tender | Active - Contracted | 2017-06-06 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185329 | DB/500448033/ECD | KwaZulu-Natal | ZIMINGAYE PRIMARY SCHOOL | 500448033 | Msinga | Tender | Active - Contracted | 2017-06-06 |  | 2027-04-28 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185330 | DB/500446812/ECD | KwaZulu-Natal | ZIZI PRIMARY SCHOOL | 500446812 | Nkandla | Tender | Active - Contracted | 2016-06-06 |  | 2027-08-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185332 | W/500209531/WS | KwaZulu-Natal | MGITSHWA SECONDARY SCHOOL | 500209531 | uMhlathuze | Tender | Active - Not Contracted | 2016-06-13 |  | 2025-01-30 |  |  | 2138000 | 9738000 | 11876000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185333 | ET/500209087/WS | KwaZulu-Natal | MGANDENI SECONDARY SCHOOL | 500209087 | Mandeni | Construction 51% - 75% | Active - Contracted | 2018-06-12 | 2023-04-06 | 2024-04-06 | 2025-04-06 | 2025-04-06 | 1839271 | 8378903 | 10218174 | Education Infrastructure Grant | Upgrading and Additions
|  | 185336 | W/500201909/WS | KwaZulu-Natal | MATHUNGELA PRIMARY SCHOOL | 500201909 | uMlalazi | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2025-03-31 | 200000 | 400000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185340 | W/500497132/WS | KwaZulu-Natal | MANDLA MTHETHWA COMPREHENSIVE HIGH SCHOOL | 500497132 | eThekwini | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2025-03-31 | 100000 | 200000 | 300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185341 | W/500496799/WS | KwaZulu-Natal | MAHLABENI LOWER PRIMARY SCHOOL | 500496799 | Jozini | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2022-06-30 | 2022-02-28 | 2023-03-31 | 200000 | 400000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185344 | W/500135383/WS | KwaZulu-Natal | EMXHAKENI PRIMARY SCHOOL | 500135383 | Emadlangeni | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2023-06-30 | 2023-04-30 | 2022-03-31 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185345 | W/500148703/WS | KwaZulu-Natal | GIJIMANA SECONDARY SCHOOL | 500148703 | Mfolozi | Tender | Active - Contracted | 2018-03-01 |  | 2026-06-30 |  |  | 300000 | 500000 | 800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185347 | W/500156806/WS | KwaZulu-Natal | HLELOLUSHA PRIMARY SCHOOL | 500156806 | Impendle | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2022-06-30 | 2023-06-30 | 2025-04-01 | 11000 | 51000 | 62000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185849 | BBB209-2020 | Northern Cape | PHILIPSTOWN PRIMARY SCHOOL | 300021305 | Renosterberg | Construction 76% - 99% | Active - Contracted | 2019-06-03 | 2021-02-26 | 2023-03-29 | 2023-03-30 | 2023-04-30 | 1291050 | 4500000 | 5791050 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 185850 | BBB020/2018 | Northern Cape | JJ BOOYSEN PRIMARY SCHOOL | 300024207 | Ubuntu | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 49994621 | 49994621 | Education Infrastructure Grant | Upgrading and Additions
|  | 185853 | LE20TMT17071 | Limpopo | Bochum circuit Office | 22012 | Polokwane | Practical Completion (100%) | Active - Contracted | 2019-03-31 | 2019-04-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 230744 | 1173426 | 1404170 | Education Infrastructure Grant | Upgrading and Additions
|  | 185854 | LE20TMT17041 | Limpopo | Akani Secondary School | 912520016 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 130200 | 520800 | 651000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185878 | DB/SAFE/500102157/WS | KwaZulu-Natal | AMANZABOMVU PRIMARY SCHOOL | 500102157 | uPhongolo | Practical Completion (100%) | Active - Contracted | 2018-06-02 | 2020-10-01 | 2023-03-30 | 2023-03-30 | 2025-05-30 | 520000 | 2100000 | 2620000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185886 | C/500257705/ECD | KwaZulu-Natal | SALIGNA PRIMARY SCHOOL | 500257705 | uMhlathuze | Tender | Active - Not Contracted | 2019-01-20 |  | 2023-04-20 |  |  | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185887 | C/500211788/ECD | KwaZulu-Natal | MKHAZENI PRIMARY SCHOOL | 500211788 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2019-01-20 | 2021-04-06 | 2023-05-20 | 2023-07-15 | 2023-12-20 | 61556 | 2091444 | 2153000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185888 | C/500152921/ECD | KwaZulu-Natal | GXALINGENWA PRIMARY SCHOOL | 500152921 | Dr Nkosazana Dlamini Zuma | Construction 76% - 99% | Active - Contracted | 2019-05-10 | 2024-04-01 | 2024-04-01 | 2024-06-01 | 2024-08-01 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185889 | C/500242609/ECD | KwaZulu-Natal | OCILWANA PRIMARY SCHOOL | 500242609 | Mthonjaneni | Design | Active - Not Contracted | 2019-01-20 |  | 2026-03-31 |  |  | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185891 | C/500114996/ECD | KwaZulu-Natal | CEBELIHLE PRIMARY SCHOOL | 500114996 | Newcastle | Design | Active - Not Contracted | 2019-01-20 |  | 2026-03-31 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185894 | C/500170385/ECD | KwaZulu-Natal | IZIKO PRIMARY SCHOOL | 500170385 | Newcastle | Feasibility | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185905 | C/500130388/ECD | KwaZulu-Natal | EMAFAKATHINI PRIMARY SCHOOL | 500130388 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185994 | DB/500110445/UA | KwaZulu-Natal | BLACKBANK PRIMARY SCHOOL | 500110445 | Dannhauser | Practical Completion (100%) | Active - Contracted | 2015-10-24 | 2018-01-12 | 2022-11-30 | 2022-05-05 | 2026-06-20 | 3085918 | 14058070 | 17143988 | Equitable Share | Upgrading and Additions
|  | 185998 | C/500162689/ECD | KwaZulu-Natal | INDONI JUNIOR PRIMARY SCHOOL | 500162689 | Newcastle | Design | Active - Not Contracted | 2019-01-20 |  | 2024-12-31 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 185999 | DB/500199838/SDS | KwaZulu-Natal | MARIA MEMORIAL PRIMARY SCHOOL | 500199838 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2015-10-24 | 2018-04-19 | 2023-03-31 | 2022-10-05 | 2025-06-20 | 717413 | 3268213 | 3985626 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186000 | DB/500305990/UA | KwaZulu-Natal | MARIANHILL PRIMARY SCHOOL | 500305990 | eThekwini | Construction 76% - 99% | Active - Contracted | 2015-10-24 | 2022-03-01 | 2022-09-30 | 2022-09-30 | 2027-09-30 | 5277931 | 24043907 | 29321838 | Education Infrastructure Grant | Upgrading and Additions
|  | 186002 | DB/500209864/UA | KwaZulu-Natal | MGWAZENI SECONDARY SCHOOL | 500209864 | Mtubatuba | Construction 26% - 50% | Active - Contracted | 2015-10-24 | 2018-04-19 | 2022-11-30 | 2022-05-05 | 2027-06-20 | 5331736 | 24289022 | 29620758 | Education Infrastructure Grant | Upgrading and Additions
|  | 186004 | DB/500221149/SDS | KwaZulu-Natal | MUZOMUHLE PRIMARY SCHOOL | 500221149 | eThekwini | Construction 76% - 99% | Active - Contracted | 2015-10-24 | 2018-04-19 | 2025-03-20 | 2020-05-05 | 2025-03-20 | 1971748 | 8982409 | 10954157 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186005 | DB/500263699/SDS | KwaZulu-Natal | SIBUSISO HIGH SCHOOL | 500263699 | Nongoma | Practical Completion (100%) | Active - Contracted | 2015-10-24 | 2018-04-19 | 2025-06-20 | 2020-05-05 | 2025-06-20 | 1624487 | 7400440 | 9024927 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186006 | DB/500294261/RRR | KwaZulu-Natal | VUTHELA PRIMARY SCHOOL | 500294261 | Ulundi | Practical Completion (100%) | Active - Not Contracted | 2015-10-24 | 2018-04-19 | 2022-11-04 | 2022-12-01 | 2027-12-09 | 943659 | 4298889 | 5242548 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186008 | DB/500110815/WS | KwaZulu-Natal | BOMBOLO COMBINED SCHOOL | 500110815 | Nongoma | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2024-03-11 | 2023-03-25 | 2024-07-07 | 2025-05-11 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186009 | DB/500118992/WS | KwaZulu-Natal | CWAKA PRIMARY SCHOOL | 500118992 | Mfolozi | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-22 | 2026-03-25 | 258678 | 1178422 | 1437100 | Education Infrastructure Grant | Upgrading and Additions
|  | 186010 | DB/500119584/WS | KwaZulu-Natal | DALUSIZO HIGH SCHOOL | 500119584 | Umdoni | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2023-03-29 | 2024-03-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186011 | DB/500120398/WS | KwaZulu-Natal | DAYENI COMBINED PRIMARY SCHOOL | 500120398 | Nongoma | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2023-03-30 | 2024-03-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186014 | DB/500121471/WS | KwaZulu-Natal | DINGEZWENI JUNIOR PRIMARY SCHOOL | 500121471 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-03-30 | 2025-05-03 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186016 | DB/500322899/WS | KwaZulu-Natal | DINGIZWE SECONDARY SCHOOL | 500322899 | Maphumulo | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186017 | DB/500122618/WS | KwaZulu-Natal | DOMREMY PRIMARY SCHOOL | 500122618 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-25 | 2024-06-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186018 | DB/500424538/WS | KwaZulu-Natal | DUMISA JUNIOR PRIMARY SCHOOL | 500424538 | Ubuhlebezwe | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-22 | 2027-03-25 | 374465 | 1705894 | 2080359 | Education Infrastructure Grant | Upgrading and Additions
|  | 186020 | DB500124542/WS | KwaZulu-Natal | DUMISA PRIMARY SCHOOL | 500124542 | Ubuhlebezwe | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-22 | 2024-03-30 | 706053 | 3216464 | 3922517 | Education Infrastructure Grant | Upgrading and Additions
|  | 186022 | DB/500126392/WS | KwaZulu-Natal | EBUKHALINI COMBINED PRIMARY SCHOOL | 500126392 | Nongoma | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-29 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186023 | DB/500126651/WS | KwaZulu-Natal | ECHWEBENI PRIMARY SCHOOL | 500126651 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186024 | DB/500128760/WS | KwaZulu-Natal | EKULINGENI JUNIOR PRIMARY SCHOOL | 500128760 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186025 | DB/500129130/WS | KwaZulu-Natal | EKUTHULENI PRIMARY SCHOOL | 500129130 | Mthonjaneni | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-29 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186026 | DB/500401191/WS | KwaZulu-Natal | EKUTHUTHUKENI SECONDARY SCHOOL | 500401191 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186028 | DB/500129315/WS | KwaZulu-Natal | EKUZWANENI COMBINED PRIMARY SCHOOL | 500129315 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-20 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186030 | DB/500424723/WS | KwaZulu-Natal | ELUKOLWENI JUNIOR PRIMARY SCHOOLL | 500424723 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-31 | 2024-03-30 | 2024-05-19 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186032 | DB/500131313/WS | KwaZulu-Natal | EMANQAYINI PRIMARY SCHOOL | 500131313 | Jozini | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186033 | 500135605 | KwaZulu-Natal | ENCANYINI PRIMARY SCHOOL | 500135605 | Umdoni | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186034 | DB/500136234/WS | KwaZulu-Natal | ENDWEBU COMBINED PRIMARY SCHOOL | 500136234 | Ubuhlebezwe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186040 | DB/500138565/WS | KwaZulu-Natal | ENTSHIZA COMBINED PRIMARY SCHOOL | 500138565 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186044 | DB/500138861/WS | KwaZulu-Natal | ENXOLOBENI PRIMARY SCHOOL | 500138861 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 299619 | 1364929 | 1664548 | Education Infrastructure Grant | Upgrading and Additions
|  | 186045 | DB/500425167/WS | KwaZulu-Natal | ENYANISWENI JUNIOR SECONDARY SCHOOL SCHOOL | 500425167 | Umzimkhulu | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 114533 | 561729 | 676262 | Education Infrastructure Grant | Upgrading and Additions
|  | 186047 | DB/500138935/WS | KwaZulu-Natal | ENYANISWENI PRIMARY SCHOOL | 500138935 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 482373 | 2197476 | 2679849 | Education Infrastructure Grant | Upgrading and Additions
|  | 186050 | DB/500140711/WS | KwaZulu-Natal | ESIKHWEBEZANE PRIMARY SCHOOL | 500140711 | Ulundi | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-03-01 | 2024-03-01 | 2024-03-30 | 2025-05-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186051 | DB/500141340/WS | KwaZulu-Natal | ESIQIWINI SECONDARY SCHOOL | 500141340 | Mtubatuba | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186052 | DB/500142524/WS | KwaZulu-Natal | ETSHENI PRIMARY SCHOOL | 500142524 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 96919 | 502081 | 599000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186053 | 500145484 | KwaZulu-Natal | FRANKLAND COMBINED PRIMARY SCHOOL | 500145484 | Umzumbe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186055 | DB/500146039/WS | KwaZulu-Natal | FUNIZWE PRIMARY SCHOOL | 500146039 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186056 | DB/500146742/WS | KwaZulu-Natal | GAJU SECONDARY SCHOOL | 500146742 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186057 | DB/500425426/WS | KwaZulu-Natal | GLENGARRY JUNIOR SECONDARY SCHOOL | 500425426 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2026-03-30 | 152102 | 692911 | 845013 | Education Infrastructure Grant | Upgrading and Additions
|  | 186061 | I/500100307/SDS | KwaZulu-Natal | ABATHWA PRIMARY SCHOOL | 500100307 | Endumeni | Design | Active - Not Contracted | 2019-08-02 |  | 2026-08-02 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186062 | I/500111703/SDS | KwaZulu-Natal | BOSCHKLOOF COMBINED SCHOOL | 500111703 | Endumeni | Design | Active - Not Contracted | 2019-08-02 |  | 2024-08-01 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186066 | I/500212343/SDS | KwaZulu-Natal | MKHUPHULANGWENYA PRIMARY SCHOOL | 500212343 | Msinga | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186069 | DB/500157546/WS | KwaZulu-Natal | HLUBI HIGH SCHOOL | 500157546 | Nqutu | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2025-03-30 | 401938 | 1831050 | 2232988 | Education Infrastructure Grant | Upgrading and Additions
|  | 186071 | DB500159063/WS | KwaZulu-Natal | HUNTLEY PRIMARY SCHOOL | 500159063 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186073 | DB/500425759/WS | KwaZulu-Natal | IBISI SECONDARY SCHOOL | 500425759 | Umzimkhulu | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 144588 | 854250 | 998838 | Education Infrastructure Grant | Upgrading and Additions
|  | 186075 | DB/500159803/WS | KwaZulu-Natal | IKAHENG PRIMARY SCHOOL | 500159803 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186076 | I/500281311/SDS | KwaZulu-Natal | THEMANE PRIMARY SCHOOL | I/500281311/SDS | Msinga | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186081 | DB/500161246/WS | KwaZulu-Natal | IMPOLWANE SECONDARY SCHOOL | 500161246 | Alfred Duma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186083 | DB/500326227/WS | KwaZulu-Natal | IMPUMELELO SENIOR PRIMARY SCHOOL | 500326227 | Ulundi | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186085 | DB/500161542/WS | KwaZulu-Natal | INALA PRIMARY SCHOOL | 500161542 | Ray Nkonyeni | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-01-14 | 2024-03-01 | 2024-06-30 | 2025-03-30 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186087 | DB/500447885/WS | KwaZulu-Natal | INDAWANA SECONDARY SCHOOL | 500447885 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 115607 | 564250 | 679857 | Education Infrastructure Grant | Upgrading and Additions
|  | 186088 | I/500101602/SDS | KwaZulu-Natal | AMAJUBA COMBINED SCHOOL | I/500101602/SDS | Newcastle | Design | Active - Not Contracted | 2019-08-21 |  | 2026-08-21 |  |  | 522000 | 16691000 | 17213000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186089 | DB/500162615/WS | KwaZulu-Natal | INDLUYAMANDLA PRIMARY SCHOOL | 500162615 | Ulundi | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 125013 | 569503 | 694516 | Education Infrastructure Grant | Upgrading and Additions
|  | 186092 | I/500101676/SDS | KwaZulu-Natal | AMAKHOLWA SECONDARY SCHOOL | I/500101676/SDS | The Msunduzi | Design | Active - Not Contracted | 2019-08-21 |  | 2026-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186095 | I/500101713/SDS | KwaZulu-Natal | AMAKHWATHA JUNIOR SECONDARY | I/500101713/SDS | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2026-08-21 |  |  | 522000 | 2728000 | 3250000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 186096 | DB/500168942/WS | KwaZulu-Natal | ISITHINTA PRIMARY SCHOOL | 500168942 | Mthonjaneni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 279000 | 1048000 | 1327000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186097 | DB/500169127/WS | KwaZulu-Natal | ISMONT HIGH SCHOOL | 500169127 | Mkhambathini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186098 | DB/500169312/WS | KwaZulu-Natal | ISONTO PRIMARY SCHOOL | 500169312 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186099 | I/500209531/SDS | KwaZulu-Natal | MGITSHWA HIGH SCHOOL | 500209531 | uMlalazi | Tender | Active - Not Contracted | 2019-08-20 |  | 2025-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186100 | I/500102416/SDS | KwaZulu-Natal | AMAPHUPHESIZWE SECONDARY SCHOOL | I/500102416/SDS | Maphumulo | Design | Active - Not Contracted | 2019-08-21 |  | 2026-08-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186101 | I/500102786/SDS | KwaZulu-Natal | AMATIMOFU PRIMARY SCHOOL | I/500102786/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2026-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186102 | I/500104081/SDS | KwaZulu-Natal | ASIZENZELE PRIMARY SCHOOL | I/500104081/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186103 | DB/500170274/WS | KwaZulu-Natal | IXOPO VILLAGE PRIMARY SCHOOL | 500170274 | Ubuhlebezwe | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2020-07-31 | 2024-01-31 | 2022-01-31 | 2027-01-31 | 163373 | 744256 | 907629 | Education Infrastructure Grant | Upgrading and Additions
|  | 186104 | DB500447589/WS | KwaZulu-Natal | KHANYAKUFIKILE PRIMARY SCHOOL | 500447589 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 428000 | 1609000 | 2037000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186106 | I/500209901/SDS | KwaZulu-Natal | MGWEMPISI HIGH SCHOOL | I/500209901/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186107 | DB500444629/WS | KwaZulu-Natal | KHINDI JOBE SECONDARY SCHOOL | 500444629 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1890000 | 2390000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186109 | I/500307322/WS | KwaZulu-Natal | NCOMBO PRIMARY SCHOOL | 500307322 | uMhlathuze | Practical Completion (100%) | Approved | 2019-06-02 | 2021-05-01 | 2022-06-02 | 2022-10-15 | 2023-01-10 | 700000 | 4000000 | 4700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186111 | DB/500175306/WS | KwaZulu-Natal | KHULUMA PRIMARY SCHOOL | 500175306 | Ubuhlebezwe | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186112 | I/500111851/SDS | KwaZulu-Natal | BOTHAS HILL SECONDARY SCHOOL | I/500111851/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-01 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186113 | I/500210012/SDS | KwaZulu-Natal | MHAWU PRIMARY SCHOOL | I/500210012/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186114 | DB/500175935/WS | KwaZulu-Natal | KING DINUZULU SECONDARY SCHOOL | 500175935 | eThekwini | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2023-01-01 | 2024-01-31 | 2025-12-20 | 2027-03-30 | 130179 | 593036 | 723215 | Education Infrastructure Grant | Upgrading and Additions
|  | 186116 | I/500114367/SDS | KwaZulu-Natal | CANAAN PRIMARY SCHOOL | I/500114367/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186117 | DB/500446590/WS | KwaZulu-Natal | KUBUYAKWEZWE PRIMARY SCHOOL | 500446590 | Msinga | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 198248 | 903128 | 1101376 | Education Infrastructure Grant | Upgrading and Additions
|  | 186118 | I/500324971/SDS | KwaZulu-Natal | CHARLESTOWN SECONDARY SCHOOL | I/500324971/SDS | Newcastle | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186119 | DB500426092/WS | KwaZulu-Natal | KUKHANYENI JUNIOR SECONDARY SCHOOL SCHOOL | 500426092 | eThekwini | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-01 | 2023-01-31 | 2022-07-14 | 2025-08-31 | 117000 | 568643 | 685643 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186120 | I/500123543/SDS | KwaZulu-Natal | DUBANDLELA HIGH SCHOOL | I/500123543/SDS | Umzumbe | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 500000 | 2000000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186121 | DB/500177896/WS | KwaZulu-Natal | KUMKANI PRIMARY SCHOOL | 500177896 | Dr Nkosazana Dlamini Zuma | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 115785 | 564667 | 680452 | Education Infrastructure Grant | Upgrading and Additions
|  | 186122 | I/500411144/SDS | KwaZulu-Natal | DUMANGEZE (MANDLEMFUNDO) SECONDARY SCHOOL | I/500411144/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186123 | I/500124135/SDS | KwaZulu-Natal | DUMANII JUNIOR PRIMARY SCHOOL | I/500124135/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 500000 | 2000000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186124 | DB/500179228/WS | KwaZulu-Natal | KWADLAMINI HIGH SCHOOL | 500179228 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 280619 | 1278375 | 1558994 | Education Infrastructure Grant | Upgrading and Additions
|  | 186125 | DB/500180005/WS | KwaZulu-Natal | KWAKHETHA PRIMARY SCHOOL | 500180005 | Impendle | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-01-31 | 2027-01-31 | 585710 | 2668233 | 3253943 | Education Infrastructure Grant | Upgrading and Additions
|  | 186131 | DB/500426314/WS | KwaZulu-Natal | LUKHASINI JUNIOR SECONDARY SCHOOL SCHOOL | 500426314 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186133 | DB/500189292/WS | KwaZulu-Natal | LUZINDELA PRIMARY SCHOOL | 500189292 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186134 | DB/500426388/WS | KwaZulu-Natal | MABANDLA SECONDARY SCHOOL | 500426388 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186135 | DB/500327004/WS | KwaZulu-Natal | MACEBA SECONDARY SCHOOL | 500327004 | Nqutu | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 268819 | 1224619 | 1493438 | Education Infrastructure Grant | Upgrading and Additions
|  | 186138 | I/500210641/SDS | KwaZulu-Natal | MHLUPHEKI HIGH SCHOOL | I/500210641/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186140 | I/500414363/SDS | KwaZulu-Natal | DUMAPHANSI SECONDARY SCHOOL | I/500414363/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186141 | I/500124653/SDS | KwaZulu-Natal | DUNDEE HIGH SCHOOL | I/500124653/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186143 | DB/500192844/WS | KwaZulu-Natal | MAGWABABA HIGH SCHOOL | 500192844 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186144 | DB/500193029/WS | KwaZulu-Natal | MAHAWULE JUNIOR PRIMARY SCHOOL | 500193029 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-03-01 | 2024-05-05 | 2025-06-20 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186145 | DB/500310319/WS | KwaZulu-Natal | MAHLAKWE LOWER PRIMARY SCHOOL | 500310319 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186146 | DB/500426462/WS | KwaZulu-Natal | MAHOBE JUNIOR SECONDARY SCHOOL SCHOOL | 500426462 | Umzimkhulu | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186147 | DB/500194361/WS | KwaZulu-Natal | MAKHAPHA COMBINED SCHOOL | 500194361 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 886000 | 6101000 | 6987000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186148 | DB/500195138/WS | KwaZulu-Natal | MALANGA PRIMARY SCHOOL | 500195138 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2025-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186150 | DB/500196396/WS | KwaZulu-Natal | MANDLENYOSI PRIMARY SCHOOL | 500196396 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186152 | I/500211788/SDS | KwaZulu-Natal | MKHAZENI PRIMARY SCHOOL | I/500211788/SDS | Endumeni | Design | Active - Not Contracted | 2016-04-01 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186153 | DB/500196988/WS | KwaZulu-Natal | MANGUZI PRIMARY SCHOOL | 500196988 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186155 | DB/500312576/WS | KwaZulu-Natal | MANYONYO LOWER PRIMARY SCHOOL | 500312576 | Mpofana | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186157 | DB/500197913/WS | KwaZulu-Natal | MANZAMNANDI PRIMARY SCHOOL | 500197913 | Mtubatuba | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186158 | I/500124764/SDS | KwaZulu-Natal | DUNDEE PRIMARY SCHOOL | I/500124764/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186159 | DB/500197950/WS | KwaZulu-Natal | MANZAMNYAMA COMBINED PRIMARY SCHOOL | 500197950 | uMlalazi | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186160 | I/500124801/SDS | KwaZulu-Natal | DUNDEE SECONDARY SCHOOL | I/500124801/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186161 | DB/500198542/WS | KwaZulu-Natal | MAPHUKANQOLA PRIMARY SCHOOL | 500198542 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186162 | DB/500146964/WS | KwaZulu-Natal | MAQAKALA PRIMARY SCHOOL | 500146964 | uMuziwabantu | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186163 | I/500125689/SDS | KwaZulu-Natal | DWARSRAND PRIMARY SCHOOL | I/500125689/SDS | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186164 | DB/500214008/WS | KwaZulu-Natal | MNYAMANA SECONDARY SCHOOL | 500214008 | Ulundi | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2018-01-05 | 2023-01-31 | 2023-01-31 | 2027-01-31 | 339564 | 1546901 | 1886465 | Education Infrastructure Grant | Upgrading and Additions
|  | 186165 | DB/500215377/WS | KwaZulu-Natal | MOUNT ERNESTINA COMBINED SCHOOL | 500215377 | Umvoti | Construction 26% - 50% | Active - Contracted | 2019-01-01 | 2020-06-02 | 2023-01-31 | 2021-07-05 | 2027-08-10 | 202334 | 921745 | 1124079 | Education Infrastructure Grant | Upgrading and Additions
|  | 186166 | I/500343175/SDS | KwaZulu-Natal | EKLOLWENI PRIMARY SCHOOL | I/500343175/SDS | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186167 | I/500129648/SDS | KwaZulu-Natal | ELANGENI HIGH SCHOOL | I/500129648/SDS | Mthonjaneni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186168 | I/500212417/SDS | KwaZulu-Natal | MKHWANTSHI PRIMARY SCHOOL | I/500212417/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186169 | I/500132682/SDS | KwaZulu-Natal | EMHLANGENI SECONDARY SCHOOL | I/500132682/SDS | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186170 | I/500132904/SDS | KwaZulu-Natal | EMJALISWENI PRIMARY SCHOOL | I/500132904/SDS | uMuziwabantu | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186171 | I/500133422/SDS | KwaZulu-Natal | EMNGCELENI PRIMARY SCHOOL | I/500133422/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186175 | I/500134754/SDS | KwaZulu-Natal | EMTHANDENI PRIMARY SCHOOL | I/500134754/SDS | Maphumulo | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186176 | I/500135901/SDS | KwaZulu-Natal | ENDLONDLWENI PRIMARY SCHOOL | I/500135901/SDS | Mandeni | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186177 | DB/500445073/WS | KwaZulu-Natal | NCUNJANA PRIMARY SCHOOL | 500445073 | Inkosi Langalibalele | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186178 | DB/500336996/WS | KwaZulu-Natal | NDABAZAMANINA SECONDARY SCHOOL | 500336996 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-30 | 2023-01-01 | 2027-08-31 | 90998 | 502863 | 593861 | Education Infrastructure Grant | Upgrading and Additions
|  | 186179 | DB/500224516/WS | KwaZulu-Natal | NDALELA HIGH SCHOOL | 500224516 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-31 | 2022-07-14 | 2027-06-20 | 451708 | 2057780 | 2509488 | Education Infrastructure Grant | Upgrading and Additions
|  | 186182 | DB/500228919/WS | KwaZulu-Natal | NGUBEVU PRIMARY SCHOOL | 500228919 | Msinga | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2025-01-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186183 | DB/500338106/WS | KwaZulu-Natal | NGUBUKAZI PRIMARY SCHOOL | 500338106 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186185 | DB/500230288/WS | KwaZulu-Natal | NHLOKOMO PRIMARY SCHOOL | 500230288 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186186 | DB/500230362/WS | KwaZulu-Natal | NHLONHLWENI PRIMARY SCHOOL | 500230362 | Alfred Duma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186187 | DB/500231768/WS | KwaZulu-Natal | NKASENI INTERMEDIATE SCHOOL | 500231768 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-02-14 | 2023-08-31 | 2023-08-31 | 2023-08-31 | 566000 | 2577000 | 3143000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186189 | DB/500235061/WS | KwaZulu-Natal | NOMPONDO PRIMARY SCHOOL | 500235061 | Big Five Hlabisa | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186192 | DB/500218929/WS | KwaZulu-Natal | NTENDEKA COMBINED SCHOOL | 500218929 | Dannhauser | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186193 | DB/500427498/WS | KwaZulu-Natal | NTLABENI JUNIOR SECONDARY SCHOOL SCHOOL | 500427498 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186194 | DB/500241610/WS | KwaZulu-Natal | NYANDU PRIMARY SCHOOL | 500241610 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186195 | DB/500427646/WS | KwaZulu-Natal | NYENYEZI SENIOR PRIMARY SCHOOL | 500427646 | Umzimkhulu | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186196 | DB/500242424/WS | KwaZulu-Natal | OBONJANENI PRIMARY SCHOOL | 500242424 | Okhahlamba | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186197 | DB/500244385/WS | KwaZulu-Natal | OPPERMANSKRAAL PUBLIC PRIMARY SCHOOL | 500244385 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186198 | DB/500245569/WS | KwaZulu-Natal | OVUKANENI PRIMARY SCHOOL | 500245569 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186199 | DB/500246568/WS | KwaZulu-Natal | PATSOANA PRIMARY SCHOOL | 500246568 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 347000 | 1579000 | 1926000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186200 | DB/500246753/WS | KwaZulu-Natal | PEACETOWN PRIMARY SCHOOL | 500246753 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186201 | DB/500247456/WS | KwaZulu-Natal | PHALANE P (KWADLANGEZWA) SCHOOL | 500247456 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186202 | DB/500247826/WS | KwaZulu-Natal | PHASIWE PRIMARY SCHOOL | 500247826 | Inkosi Langalibalele | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-03-01 | 2023-05-05 | 2025-08-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186206 | DB/500236763/WS | KwaZulu-Natal | SHEA O`CONNOR COMBINED SCHOOL (PREV. NOTTINGHAM RD) | 500236763 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 621000 | 2829000 | 3450000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186207 | DB/500444296/WS | KwaZulu-Natal | SIDINGULWAZI PRIMARY SCHOOL | 500444296 | Alfred Duma | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-10-01 | 2022-04-29 | 2022-04-29 | 2025-04-29 | 350981 | 1598914 | 1949895 | Education Infrastructure Grant | Upgrading and Additions
|  | 186209 | DB/500334554/WS | KwaZulu-Natal | SIQALOKUSHA PRIMARY SCHOOL | 500334554 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186211 | DB/500423539/WS | KwaZulu-Natal | SISIZAKELE SPECIAL SCHOOL | 500423539 | Newcastle | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 811000 | 2500000 | 3311000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186212 | I/500213601/SDS | KwaZulu-Natal | MNQANDI HIGH SCHOOL | I/500213601/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186213 | I/500214267/SDS | KwaZulu-Natal | MOFU JUNIOR PRIMARY SCHOOL | I/500214267/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186229 | DB/SAFE/500423576/WS | KwaZulu-Natal | AMAWUSHE JUNIOR SECONDARY SCHOOL SCHOOL | 500423576 | Nkandla | Practical Completion (100%) | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186230 | DB/500103674/WS | KwaZulu-Natal | ASANDE SECONDARY SCHOOL | 500103674 | Impendle | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-01-14 | 2024-03-01 | 2024-03-01 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186231 | DB/SAFE/500105339/WS | KwaZulu-Natal | BANGIBIZO JUNIOR PRIMARY SCHOOL | 500105339 | Nkandla | Practical Completion (100%) | Active - Not Contracted | 2018-01-01 | 2024-03-11 | 2024-03-01 | 2024-06-11 | 2025-05-11 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186232 | I/500215118/SDS | KwaZulu-Natal | MORNINGSIDE PRIMARY SCHOOL | I/500215118/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186233 | DB/500495319/WS | KwaZulu-Natal | BAWELISE SPECIAL SCHOOL | 500495319 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186234 | DB/500106634/WS | KwaZulu-Natal | BAZINI PRIMARY SCHOOL | 500106634 | uMuziwabantu | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2019-01-14 | 2023-03-01 | 2023-03-25 | 2025-03-26 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186235 | DB/500338328/WS | KwaZulu-Natal | BEKEZELANI JUNIOR SECONDARY SCHOOL | 500338328 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186236 | DB/500107855/WS | KwaZulu-Natal | BHADENI PRIMARY SCHOOL | 500107855 | eDumbe | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-03-25 | 2025-03-26 | 653281 | 2976056 | 3629337 | Education Infrastructure Grant | Upgrading and Additions
|  | 186237 | DB/500108040/WS | KwaZulu-Natal | BHAQALWESIZWE SECONDARY SCHOOL | 500108040 | Nongoma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186238 | DB/500108077/WS | KwaZulu-Natal | BHEDLANA JUNIOR PRIMARY SCHOOL | 500108077 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2024-03-11 | 2024-03-01 | 2024-06-11 | 2025-03-26 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186239 | DB/500308839/WS | KwaZulu-Natal | BHOBHE PRIMARY SCHOOL | 500308839 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-12 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186240 | DB/500109668/WS | KwaZulu-Natal | BHOKWE SECONDARY SCHOOL | 500109668 | Nongoma | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2024-03-11 | 2023-03-25 | 2024-06-11 | 2025-09-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186241 | I/500216709/SDS | KwaZulu-Natal | MPIKANINA HIGH SCHOOL | I/500216709/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186242 | DB/500109705/WS | KwaZulu-Natal | BHOKWENI PRIMARY SCHOOL | 500109705 | Ulundi | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2024-03-11 | 2023-03-25 | 2024-07-07 | 2025-05-11 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186243 | DB/500111148/WS | KwaZulu-Natal | BONGINDUNA COMBINED PRIMARY SCHOOL | 500111148 | Umzumbe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-25 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186244 | DB/500111555/WS | KwaZulu-Natal | BONOKUHLE HIGH SCHOOL | 500111555 | Inkosi Langalibalele | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-22 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186245 | DB/500423835/WS | KwaZulu-Natal | BONTRAND JUNIOR SECONDARY SCHOOL SCHOOL | 500423835 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-25 | 2024-03-01 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186246 | DB/500111962/WS | KwaZulu-Natal | BRACKENHAM PRIMARY SCHOOL | 500111962 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-02-28 | 2023-03-21 | 2025-03-25 | 91188 | 724411 | 815599 | Education Infrastructure Grant | Upgrading and Additions
|  | 186247 | DB/500113257/WS | KwaZulu-Natal | BUHLEBETHU SECONDARY SCHOOL | 500113257 | Umzumbe | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2021-01-15 | 2024-03-25 | 2024-03-25 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186249 | DB/500115551/WS | KwaZulu-Natal | CELUMUSA SECONDARY SCHOOL | 500115551 | Nqutu | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-03-22 | 2026-03-25 | 265497 | 1209488 | 1474985 | Education Infrastructure Grant | Upgrading and Additions
|  | 186250 | DB/500424057/WS | KwaZulu-Natal | CLYDESDALE JUNIOR SECONDARY SCHOOL SCHOOL | 500424057 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-03-30 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186251 | DB/500117734/WS | KwaZulu-Natal | COLLESSIE PRIMARY SCHOOL | 500117734 | Msinga | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2019-03-01 | 2024-03-20 | 2023-12-25 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186252 | DB/500119066/WS | KwaZulu-Natal | CWAYISA JUNIOR PRIMARY SCHOOL | 500119066 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-01 | 2023-12-25 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186253 | DB/500424279/WS | KwaZulu-Natal | DELAMUZI JUNIOR SECONDARY SCHOOL SCHOOL | 500424279 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-03-30 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186254 | DB/500121027/WS | KwaZulu-Natal | DIBI JUNIOR PRIMARY SCHOOL | 500121027 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-21 | 2024-03-30 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186255 | DB/500121249/WS | KwaZulu-Natal | DILIZELA HIGH SCHOOL | 500121249 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-03-19 | 2027-03-20 | 310904 | 1416341 | 1727245 | Education Infrastructure Grant | Upgrading and Additions
|  | 186256 | DB/500121434/WS | KwaZulu-Natal | DINGETON COMBINED PRIMARY SCHOOL | 500121434 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186257 | DB/500307988/WS | KwaZulu-Natal | DINGIMBIZA PRIMARY SCHOOL | 500307988 | Ubuhlebezwe | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186258 | DB/500121804/WS | KwaZulu-Natal | DLABE COMBINED PRIMARY SCHOOL | 500121804 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186259 | DB/500123025/WS | KwaZulu-Natal | DOROTHEA PRIMARY SCHOOL | 500123025 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186260 | DB/500123543/WS | KwaZulu-Natal | DUBANDLELA HIGH SCHOOL | 500123543 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-24 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186261 | DB/500124579/WS | KwaZulu-Natal | DUMUKA PRIMARY SCHOOL | 500124579 | Umzumbe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-25 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186262 | DB/500125060/WS | KwaZulu-Natal | DUNYWA PRIMARY SCHOOL | 500125060 | Ray Nkonyeni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186263 | DB/500401302/WS | KwaZulu-Natal | EBRAHIM LOCKAT SECONDARY SCHOOL | 500401302 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186264 | DB/500126762/WS | KwaZulu-Natal | EDAMBE PRIMARY SCHOOL | 500126762 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186265 | DB/500126910/WS | KwaZulu-Natal | EDILINI PRIMARY SCHOOL | 500126910 | Ulundi | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-03-22 | 2027-03-25 | 481720 | 2194501 | 2676221 | Education Infrastructure Grant | Upgrading and Additions
|  | 186266 | DB/500127391/WS | KwaZulu-Natal | EGQUMAWENI PRIMARY SCHOOL | 500127391 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186267 | DB/500127576/WS | KwaZulu-Natal | EHLANE PRIMARY SCHOOL | 500127576 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-20 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186268 | DB/500325822/WS | KwaZulu-Natal | EKUPHIWENI JUNIOR SECONDARY SCHOOL | 500325822 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186269 | DB/500129796/WS | KwaZulu-Natal | ELSIE MTSHALI COMBINED SCHOOL | 500129796 | Umvoti | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-31 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186270 | DB/500103203/WS | KwaZulu-Natal | EMADEKENI HIGHER PRIMARY SCHOOL | 500103203 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2022-06-01 | 2024-03-30 | 2024-03-30 | 2025-05-03 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186271 | DB/500131757/WS | KwaZulu-Natal | EMAZIZINI JUNIOR PRIMARY SCHOOL | 500131757 | Okhahlamba | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-15 | 2024-03-30 | 2024-03-30 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186272 | DB/500424871/WS | KwaZulu-Natal | EMBUZWENI JUNIOR SECONDARY SCHOOL SCHOOL | 500424871 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-15 | 2024-03-30 | 2024-03-30 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186273 | DB/500132349/WS | KwaZulu-Natal | EMCHAKWENI PRIMARY SCHOOL | 500132349 | Mtubatuba | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 383548 | 1747273 | 2130821 | Education Infrastructure Grant | Upgrading and Additions
|  | 186274 | DB/500134125/WS | KwaZulu-Natal | EMPHALWINI COMBINED PRIMARY SCHOOL | 500134125 | eThekwini | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-15 | 2023-03-30 | 2024-03-25 | 2024-03-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186275 | DB/500325970/WS | KwaZulu-Natal | EMPUMELELWENI JUNIOR PRIMARY SCHOOL | 500325970 | Mfolozi | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186276 | DB/500135013/WS | KwaZulu-Natal | EMTHULASIZWE HIGH SCHOOL | 500135013 | Ulundi | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-15 | 2024-03-30 | 2024-03-30 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186277 | DB/500135050/WS | KwaZulu-Natal | EMTHUNGWENI HIGH SCHOOL | 500135050 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-15 | 2023-03-30 | 2024-03-30 | 2025-03-25 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186278 | DB/500340511/WS | KwaZulu-Natal | EMTHUNZINI PRIMARY SCHOOL | 500340511 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186279 | DB/500310504/WS | KwaZulu-Natal | EMUNYWANA JUNIOR PRIMARY SCHOOL | 500310504 | Jozini | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 2500000 | 3000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186285 | I/500139823/SDS | KwaZulu-Natal | ESHOWE SECONDARY SCHOOL | I/500139823/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186286 | PSU001 | North West | PROGRAMME SUPPORT UNIT NW-DOESD | PSU001 | Mafikeng | Project Initiation | Active - Contracted | 2019-04-01 |  | 2025-03-30 |  |  | 2494558318 | 0 | 2494558318 | Education Infrastructure Grant | Non-Infrastructure
|  | 186287 | I/500217967/SDS | KwaZulu-Natal | MQHIYAMA PRIMARY SCHOOL | I/500217967/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186289 | I/500218189/SDS | KwaZulu-Natal | MSELENI PRIMARY SCHOOL | I/500218189/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186290 | I/500218337/SDS | KwaZulu-Natal | MSHANELOWESIZWE HIGH SCHOOL | I/500218337/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186293 | I/500219299/SDS | KwaZulu-Natal | MTHOLI PRIMARY SCHOOL | I/500219299/SDS | Ray Nkonyeni | Design | Active - Not Contracted | 2019-08-20 |  | 2024-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186294 | I/500220372/SDS | KwaZulu-Natal | MTHWAZI COMBINED SCHOOL | I/500220372/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2024-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186295 | I/500307211/SDS | KwaZulu-Natal | MUNTUYEDWA PRIMARY SCHOOL | I/500307211/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2024-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186296 | I/500309764/SDS | KwaZulu-Natal | KWABAMBA HIGH SCHOOL | I/500309764/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186297 | I/500140119/SDS | KwaZulu-Natal | ESIBONISWENI PRIMARY | I/500140119/SDS | Umhlabuyalingana | Design | Active - Not Contracted | 2016-04-01 |  | 2024-02-28 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186299 | I/500178969/SDS | KwaZulu-Natal | KWABULAWAYO HIGH SCHOOL | I/500178969/SDS | Big Five Hlabisa | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186302 | I/500141118/SDS | KwaZulu-Natal | ESIPHONDWENI HIGH SCHOOL | I/500141118/SDS | Umhlabuyalingana | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-31 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186303 | I/500223924/SDS | KwaZulu-Natal | NCWABAKAZI PRIMARY SCHOOL | I/500223924/SDS | Big Five Hlabisa | Design | Active - Not Contracted | 2019-08-20 |  | 2024-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186305 | I/500227661/SDS | KwaZulu-Natal | NGCONGANGCONGA SECONDARY SCHOOL | I/500227661/SDS | KwaDukuza | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186306 | I/500228253/SDS | KwaZulu-Natal | NGOLOTSHA PRIMARY SCHOOL | I/500228253/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186307 | I/500427276/SDS | KwaZulu-Natal | NGUSE JUINIOR PRIMARY SCHOOL | I/500427276/SDS | Ubuhlebezwe | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186308 | I/500229104/SDS | KwaZulu-Natal | NGWABI PRIMARY SCHOOL | I/500229104/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186309 | I/500229733/SDS | KwaZulu-Natal | NHLALWANE PRIMARY SCHOOL | I/500229733/SDS | Ray Nkonyeni | Feasibility | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 500000 | 2000000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186310 | ET/500100677/WS | KwaZulu-Natal | ALDENVILLE PRIMARY SCHOOL | 500100677 | KwaDukuza | Final Completion | Active - Contracted | 2018-08-01 | 2018-09-30 | 2024-03-27 | 2020-03-30 | 2023-04-30 | 1577500 | 7186391 | 8763891 | Education Infrastructure Grant | Upgrading and Additions
|  | 186313 | I/500179302/SDS | KwaZulu-Natal | KWADONSA PRIMARY SCHOOL | I/500179302/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186316 | I/500141969/SDS | KwaZulu-Natal | ESUSWENI PRIMARY SCHOOL | I/500141969/SDS | Ulundi | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186317 | I/500179709/SDS | KwaZulu-Natal | KWAGWEGWE PRIMARY SCHOOL | I/500179709/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186319 | I/500266252/SDS | KwaZulu-Natal | KWAMPUNGOSE PRIMARY SCHOOL | I/500266252/SDS | The Msunduzi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186321 | I/500182632/SDS | KwaZulu-Natal | KWANSELE PRIMARY SCHOOL | I/500182632/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186322 | I/500178488/SDS | KwaZulu-Natal | KWANXUSA HIGH SCHOOL | I/500178488/SDS | Mthonjaneni | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186323 | I/500231213/SDS | KwaZulu-Natal | NJOMELWANE PRIMARY SCHOOL | I/500231213/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186324 | I/500232952/SDS | KwaZulu-Natal | NKUME PRIMARY SCHOOL | I/500232952/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186325 | I/500233359/SDS | KwaZulu-Natal | NKWENKWEZI SECONDARY SCHOOL | I/500233359/SDS | Mandeni | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186326 | I/500234210/SDS | KwaZulu-Natal | NOKWEJA PRIMARY SCHOOL | I/500234210/SDS | Ubuhlebezwe | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186327 | DB/500135901/WS | KwaZulu-Natal | ENDLONDLWENI PRIMARY SCHOOL | 500135901 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186328 | DB/500136197/WS | KwaZulu-Natal | ENDUNDUMENI PRIMARY SCHOOL | 500136197 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186329 | DB/500136382/WS | KwaZulu-Natal | ENGCUBA PRIMARY SCHOOL | 500136382 | Nkandla | Tender | Active - Not Contracted | 2018-01-01 |  | 2025-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186330 | 500424982 | KwaZulu-Natal | ENGUNJINI JUNIOR SECONDARY SCHOOL SCHOOL | 500424982 | Umzimkhulu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186331 | DB/500137307/WS | KwaZulu-Natal | ENHLOSWENI PRIMARY SCHOOL | 500137307 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186332 | DB/500306508/WS | KwaZulu-Natal | EPHUSHENI PRIMARY SCHOOL | 500306508 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186333 | I/500234432/SDS | KwaZulu-Natal | NOMAGEJE PRIMARY SCHOOL | I/500234432/SDS | Ray Nkonyeni | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 500000 | 2000000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186334 | I/500234950/SDS | KwaZulu-Natal | NOMFIHLELA PRIMARY SCHOOL | I/500234950/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186335 | I/500183446/SDS | KwaZulu-Natal | KWASHUKELA PRIMARY SCHOOL | I/500183446/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186336 | I/500235505/SDS | KwaZulu-Natal | NONGAMLANA HIGH SCHOOL | I/500235505/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186337 | I/500235764/SDS | KwaZulu-Natal | NONOPHA PRIMARY SCHOOL | I/500235764/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186338 | I/500185407/SDS | KwaZulu-Natal | LANGALIBOMVU HIGH SCHOOL | I/500185407/SDS | Mfolozi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186339 | I/500238576/SDS | KwaZulu-Natal | NSUNGUZA PRIMARY SCHOOL | I/500238576/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186340 | I/500326782/SDS | KwaZulu-Natal | LIZWI HIGH SCHOOL | I/500326782/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186341 | I/500440485/SDS | KwaZulu-Natal | NTABAMHLOPHE PRIMARYSCHOOL | I/500440485/SDS | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186342 | I/500238872/SDS | KwaZulu-Natal | NTABANTUZUMA HIGH SCHOOL | I/500238872/SDS | uMlalazi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186343 | I/500311910/SDS | KwaZulu-Natal | ETHANGENI PRIMARY SCHOOL | I/500311910/SDS | Endumeni | Design | Active - Not Contracted | 2016-04-01 |  | 2024-03-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186344 | I/500188811/SDS | KwaZulu-Natal | LUNGISILE PRIMARY SCHOOL | I/500188811/SDS | The Msunduzi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186345 | I/500239797/SDS | KwaZulu-Natal | NTILI PRIMARY SCHOOL | I/500239797/SDS | Maphumulo | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186346 | I/500240833/SDS | KwaZulu-Natal | NTUKUSO PRIMARY SCHOOL | I/500240833/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2024-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186347 | I/500241351/SDS | KwaZulu-Natal | NXUSA PRIMARY SCHOOL | I/500241351/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186348 | I/500241499/SDS | KwaZulu-Natal | NYAMAZANE PRIMARY SCHOOL | I/500241499/SDS | Maphumulo | Design | Active - Not Contracted | 2019-11-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186349 | I/500242905/SDS | KwaZulu-Natal | OGAGWINI PRIMARY SCHOOL | I/500242905/SDS | Maphumulo | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186350 | I/500243534/SDS | KwaZulu-Natal | OKHUKHO PRIMARY SCHOOL | I/500243534/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186351 | I/500244163/SDS | KwaZulu-Natal | OPHANSI PRIMARY SCHOOL | I/500244163/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186352 | I/500244311/SDS | KwaZulu-Natal | OPHONGOLO HIGH SCHOOL | I/500244311/SDS | uPhongolo | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186354 | I/500246124/SDS | KwaZulu-Natal | PANORAMA COMBINE SCHOOL | I/500246124/SDS | Newcastle | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186355 | I/500189292/SDS | KwaZulu-Natal | LUZINDELA PRIMARY SCHOOL | I/500189292/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186356 | I/500246901/SDS | KwaZulu-Natal | PERMARY RIDGE PRIMARY SCHOOL | I/500246901/SDS | eThekwini | Design | Active - Contracted | 2019-08-20 |  | 2026-03-31 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186357 | I/500338069/SDS | KwaZulu-Natal | MABEDLANA PRIMARY SCHOOL | I/500338069/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186358 | I/500190032/SDS | KwaZulu-Natal | MABHILA PRIMARY SCHOOL | I/500190032/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186359 | I/500247530/SDS | KwaZulu-Natal | PHAMBILI PRIMARY SCHOOL | I/500247530/SDS | Newcastle | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186360 | I/500194324/SDS | KwaZulu-Natal | MAKHANYEZI PRIMARY SCHOOL | I/500194324/SDS | Nkandla | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186361 | I/500194583/SDS | KwaZulu-Natal | MAKHEME PRIMARY SCHOOL | I/500194583/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186362 | I/500247641/SDS | KwaZulu-Natal | PHAN PRIMARY SCHOOL | I/500247641/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186363 | I/500407888/SDS | KwaZulu-Natal | MANDATHANE PRIMARY SCHOOL | I/500407888/SDS | Nkandla | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186364 | I/500248603/SDS | KwaZulu-Natal | PHIKISWAYO PRIMARY SCHOOL | I/500248603/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186365 | I/500446442/SDS | KwaZulu-Natal | PHILIBANA PRIMARY SCHOOL | I/500446442/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186366 | I/500315573/SDS | KwaZulu-Natal | MANDLOSUTHI HIGH SCHOOL | I/500315573/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186367 | I/500252488/SDS | KwaZulu-Natal | QEDIZABA PRIMARY SCHOOL | I/500252488/SDS | Newcastle | Design | Active - Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186368 | I/500197247/SDS | KwaZulu-Natal | MANQAKULANA PRIMARY SCHOOL | I/500197247/SDS | Umhlabuyalingana | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186369 | I/500252525/SDS | KwaZulu-Natal | QEDUKOMA PRIMARY SCHOOL | I/500252525/SDS | Nqutu | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186370 | I/500197691/SDS | KwaZulu-Natal | MANYAMPISI PRIMARY SCHOOL | I/500197691/SDS | Umhlabuyalingana | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186371 | I/500197765/SDS | KwaZulu-Natal | MANYANE PRIMARY SCHOOL | I/500197765/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186372 | I/500198024/SDS | KwaZulu-Natal | MANZAMPOFU PRIMARY SCHOOL | I/500198024/SDS | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186373 | I/500198320/SDS | KwaZulu-Natal | MAPHAYA PRIMARY SCHOOL | I/500198320/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 557632 | 2947368 | 3505000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186374 | I/500326969/SDS | KwaZulu-Natal | MASOKANENI PRIMARY SCHOOL | I/500326969/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186375 | I/500499685/SDS | KwaZulu-Natal | QUEEN THOMO PRIMARY SCHOOL | I/500499685/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186377 | I/500255818/SDS | KwaZulu-Natal | RIETVALLEI COMBINE SCHOOL | I/500255818/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186378 | I/500204758/SDS | KwaZulu-Natal | MBONGOLWANE PRIMARY SCHOOL | I/500204758/SDS | uMlalazi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186379 | I/500206053/SDS | KwaZulu-Natal | MDEPHA SECONDARY SCHOOL | I/500206053/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186381 | I/500208310/SDS | KwaZulu-Natal | MFAKUBHEKA PRIMARY SCHOOL | I/500208310/SDS | Umhlabuyalingana | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186382 | I/500257594/SDS | KwaZulu-Natal | SAKHISIZWE SECONDARY SCHOOL | I/500257594/SDS | KwaDukuza | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186383 | I/500208754/SDS | KwaZulu-Natal | MFONGOSI COMBINED SCHOOL | I/500208754/SDS | Nkandla | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186384 | I/500342805/SDS | KwaZulu-Natal | SALEM PRIMARY SCHOOL | I/500342805/SDS | uMuziwabantu | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186385 | I/500208939/SDS | KwaZulu-Natal | MGABHANYONGO PRIMARY SCHOOL | I/500208939/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186386 | I/500143819/SDS | KwaZulu-Natal | EZWELETHU PRIMARY SCHOOL | 500143819 | Okhahlamba | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186387 | I/500258260/SDS | KwaZulu-Natal | SANGOYANA PRIMARY SCHOOL | I/500258260/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186388 | I/500145669/SDS | KwaZulu-Natal | FUMANA COMBINE SCHOOL | I/500145669/SDS | Nongoma | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186389 | I/500288637/SDS | KwaZulu-Natal | UMPHUMULO PRIMARY SCHOOL | I/500288637/SDS | Maphumulo | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186390 | I/500258815/SDS | KwaZulu-Natal | SARON PRIMARY SCHOOL | I/500258815/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186391 | I/500260036/SDS | KwaZulu-Natal | SEHOLE HIGH SCHOOL | I/500260036/SDS | uMuziwabantu | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186392 | I/500261738/SDS | KwaZulu-Natal | SHELEZA PRIMARY SCHOOL | I/500261738/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186393 | I/500289229/SDS | KwaZulu-Natal | UMTHUNZI SECONDARY SCHOOL | I/500289229/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186396 | I/500297665/SDS | KwaZulu-Natal | XASANA PRIMARY SCHOOL | I/500297665/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2027-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186398 | I/500298516/SDS | KwaZulu-Natal | ZALIZWI PRIMARY SCHOOL | I/500298516/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186399 | I/500442002/SDS | KwaZulu-Natal | ZAMINTUTHUKO HIGH SCHOOL | I/500442002/SDS | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186400 | I/500299256/SDS | KwaZulu-Natal | ZANDLAZETHU HIGH SCHOOL | I/500299256/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186402 | I/500411070/SDS | KwaZulu-Natal | ZIBAMBELE PRIMARY SCHOOL | I/500411070/SDS | uMlalazi | Design | Active - Not Contracted | 2019-08-21 |  | 2027-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186404 | I/500327635/SDS | KwaZulu-Natal | ZOMBODE PRIMARY SCHOOL | I/500327635/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186405 | I/500204536/SDS | KwaZulu-Natal | MBIZWE SENIOR SECONDARY SCHOOL | I/500204536/SDS | Nkandla | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186406 | I/500288600/SDS | KwaZulu-Natal | UMPHUMELA SECONDARY SCHOOL | I/500288600/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186407 | I/500287416/SDS | KwaZulu-Natal | UMGABHI COMBINED SCHOOL | I/500287416/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186408 | I/500263810/SDS | KwaZulu-Natal | SICELIMFUNDO COMBINED SCHOOL | I/500263810/SDS | Endumeni | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186410 | I/500264550/SDS | KwaZulu-Natal | SIGQAMISE HIGH SCHOOL | I/500264550/SDS | uPhongolo | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186421 | I/500285159/SDS | KwaZulu-Natal | TSHELENKOSI SECONDARY SCHOOL | I/500285159/SDS | KwaDukuza | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186423 | I/500265512/SDS | KwaZulu-Natal | SILINDELE PRIMARY SCHOOL | I/500265512/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186424 | I/500285529/SDS | KwaZulu-Natal | TWASANA PRIMARY SCHOOL | I/500285529/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186425 | I/500285603/SDS | KwaZulu-Natal | UBAMBISWANO HIGH SCHOOL | I/500285603/SDS | uMhlathuze | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186431 | DB/500139416/WS | KwaZulu-Natal | EQAKWINI HIGH SCHOOL | 500139416 | Big Five Hlabisa | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-05-31 | 2022-03-25 | 2027-03-30 | 98608 | 514816 | 613424 | Education Infrastructure Grant | Upgrading and Additions
|  | 186432 | DB/500140082/WS | KwaZulu-Natal | ESIBOMVINI PRIMARY SCHOOL | 500140082 | Dr Nkosazana Dlamini Zuma | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-03-01 | 2023-03-01 | 2024-03-30 | 2025-03-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186433 | DB/500140970/WS | KwaZulu-Natal | ESIPHAHLENI PRIMARY SCHOOL | 500140970 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186434 | DB/500425241/WS | KwaZulu-Natal | ETEMBENI PRIMARY SCHOOL | 500425241 | Mthonjaneni | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 405061 | 1845277 | 2250338 | Education Infrastructure Grant | Upgrading and Additions
|  | 186436 | I/500147038/SDS | KwaZulu-Natal | GANGEYANA PRIMARY SCHOOL | 500147038 | Endumeni | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186442 | DB/500341510/WS | KwaZulu-Natal | EYETHU PRIMARY SCHOOL | 500341510 | Umvoti | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 353970 | 1612530 | 1966500 | Education Infrastructure Grant | Upgrading and Additions
|  | 186444 | I/500306323/SDS | KwaZulu-Natal | UKUSAKWABASHWA PRIMARY SCHOOL | I/500306323/SDS | Mkhambathini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186445 | DB/500143301/WS | KwaZulu-Natal | EZIJIBENI SENIOR PRIMARY SCHOOL | 500143301 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186446 | I/500495504/SDS | KwaZulu-Natal | STEVEN DAVIDSON PRIMARY SCHOOL | I/500495504/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186447 | DB/500146335/WS | KwaZulu-Natal | GABADELA PRIMARY SCHOOL | 500146335 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-03-01 | 2024-03-01 | 2024-06-30 | 2025-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186448 | DB/500146668/WS | KwaZulu-Natal | GADELENI SECONDARY SCHOOL | 500146668 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186449 | I/500278388/SDS | KwaZulu-Natal | SUKUMA HIGH SCHOOL | I/500278388/SDS | The Msunduzi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186450 | DB/500148074/WS | KwaZulu-Natal | GELYKWATER PRIMARY SCHOOL | 500148074 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186453 | DB/500159211/WS | KwaZulu-Natal | HYDESWOOD PRIMARY SCHOOL | 500159211 | Alfred Duma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186465 | DB/500159396/WS | KwaZulu-Natal | IDLAMADODA SECONDARY SCHOOL | 500159396 | Nqutu | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2025-03-30 | 2022-03-25 | 2027-03-30 | 499676 | 2276304 | 2775980 | Education Infrastructure Grant | Upgrading and Additions
|  | 186466 | DB/500160691/WS | KwaZulu-Natal | IMBUBU PRIMARY SCHOOL | 500160691 | The Msunduzi | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-03-25 | 2027-03-30 | 246240 | 1121760 | 1368000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186467 | DB/500161135/WS | KwaZulu-Natal | IMPANDWINI PRIMARY SCHOOL | 500161135 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186468 | DB/500161357/WS | KwaZulu-Natal | IMPUNGA SECONDARY SCHOOL | 500161357 | Ubuhlebezwe | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-06-15 | 2022-06-20 | 2022-06-20 | 2027-06-20 | 1154607 | 3704322 | 4858929 | Education Infrastructure Grant | Upgrading and Additions
|  | 186469 | DB/500425796/WS | KwaZulu-Natal | INDAWANA JUNIOR SECONDARY SCHOOL SCHOOL | 500425796 | Umzimkhulu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186470 | DB/500162874/WS | KwaZulu-Natal | INDULWANA PRIMARY SCHOOL | 500162874 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186471 | DB/500162948/WS | KwaZulu-Natal | INDUMAKUDE PRIMARY SCHOOL | 500162948 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186472 | DB/500163614/WS | KwaZulu-Natal | INGULA HIGH SCHOOL | 500163614 | Alfred Duma | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-03-25 | 2027-03-30 | 432823 | 1971751 | 2404574 | Education Infrastructure Grant | Upgrading and Additions
|  | 186473 | DB/500165797/WS | KwaZulu-Natal | INSONGE PRIMARY SCHOOL | 500165797 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186474 | DB/500166352/WS | KwaZulu-Natal | INTUKU PRIMARY SCHOOL | 500166352 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186475 | DB/500166574/WS | KwaZulu-Natal | INUNGI PRIMARY SCHOOL | 500166574 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2025-03-26 | 2025-03-04 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186476 | DB/500167499/SDS | KwaZulu-Natal | ISIBONELO SECONDARY SCHOOL | 500167499 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 2059143 | 9380539 | 11439682 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186477 | DB/500339697/WS | KwaZulu-Natal | IZIMBUTHU PRIMARY SCHOOL | 500339697 | Emadlangeni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186478 | DB/500425833/WS | KwaZulu-Natal | JERICHO JUNIOR SECONDARY SCHOOL SCHOOL | 500425833 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186479 | DB/500171754/WS | KwaZulu-Natal | JOYLANDS PRIMARY SCHOOL | 500171754 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186480 | DB/500447552/WS | KwaZulu-Natal | KADWA SECONDARY SCHOOL | 500447552 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186481 | DB/500319014/WS | KwaZulu-Natal | KHABA JUNIOR SECONDARY SCHOOL | 500319014 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186482 | DB/500495763/WS | KwaZulu-Natal | KHANYISA SECONDARY SCHOOL | 500495763 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186483 | DB/500341473/WS | KwaZulu-Natal | KHANYISANI PRIMARY SCHOOL | 500341473 | uMshwathi | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186484 | DB/500174196/WS | KwaZulu-Natal | KHETHIMFUNDO PRIMARY SCHOOL | 500174196 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2025-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186485 | DB/500176712/WS | KwaZulu-Natal | KLWAYISI PRIMARY SCHOOL | 500176712 | Nqutu | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-01-31 | 2025-01-31 | 394268 | 1796108 | 2190376 | Education Infrastructure Grant | Upgrading and Additions
|  | 186486 | DB/500178340/WS | KwaZulu-Natal | KWA MPHATHA PRIMARY SCHOOL | 500178340 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186487 | DB/500179413/WS | KwaZulu-Natal | KWAFUZOKUHLE PRIMARY SCHOOL | 500179413 | Abaqulusi | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 352549 | 1606055 | 1958604 | Education Infrastructure Grant | Upgrading and Additions
|  | 186488 | DB/500180264/WS | KwaZulu-Natal | KWAMAGIDELA SECONDARY SCHOOL | 500180264 | Ulundi | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186489 | DB/500181485/WS | KwaZulu-Natal | KWAMPHELELWA COMBINED PRIMARY SCHOOL | 500181485 | Ray Nkonyeni | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-03-01 | 2023-05-05 | 2025-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186490 | DB/500338735/WS | KwaZulu-Natal | KWANANDI COMBINED PRIMARY SCHOOL | 500338735 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186492 | DB/500184260/WS | KwaZulu-Natal | KWAZIBUSELE LOWER PRIMARY SCHOOL | 500184260 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186493 | DB/500426166/WS | KwaZulu-Natal | LADAM SECONDARY SCHOOL | 500426166 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186494 | DB/500185333/WS | KwaZulu-Natal | LANGALETHU SENIOR PRIMARY SCHOOL | 500185333 | Alfred Duma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186495 | DB/500185407/WS | KwaZulu-Natal | LANGALIBOMVU HIGH SCHOOL | 500185407 | Mfolozi | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186496 | DB/500158888/WS | KwaZulu-Natal | LENEHA TUMISI SECONDARY SCHOOL | 500158888 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2022-01-31 | 2027-01-31 | 537638 | 2449238 | 2986876 | Education Infrastructure Grant | Upgrading and Additions
|  | 186497 | DB/500426203/WS | KwaZulu-Natal | LENFORD BALENI JUNIOR PRIMARY SCHOOL | 500426203 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-03-01 | 2024-05-05 | 2025-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186498 | DB/500337847/WS | KwaZulu-Natal | LESHMAN SECONDARY SCHOOL | 500337847 | Dr Nkosazana Dlamini Zuma | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186499 | DB/500187183/WS | KwaZulu-Natal | LITTLE FLOWER SECONDARY SCHOOL | 500187183 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2023-09-12 | 2024-01-31 | 2024-05-05 | 2027-06-20 | 873388 | 3978767 | 4852155 | Education Infrastructure Grant | Upgrading and Additions
|  | 186500 | DB/500429718/WS | KwaZulu-Natal | LOURDES JUNIOR SECONDARY SCHOOL SCHOOL | 500429718 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186501 | DB/500189366/WS | KwaZulu-Natal | LYNDHURST PRIMARY SCHOOL | LYNDHURST PRIMARY SCHOOL | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-01-31 | 2027-01-31 | 696840 | 3174491 | 3871331 | Education Infrastructure Grant | Upgrading and Additions
|  | 186502 | DB/500190587/WS | KwaZulu-Natal | MACELA PRIMARY SCHOOL | 500190587 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186503 | DB/500310134/WS | KwaZulu-Natal | MADLAKA JUNIOR SECONDARY SCHOOL | 500310134 | Ray Nkonyeni | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186504 | DB/500191216/WS | KwaZulu-Natal | MADLANGENI PRIMARY SCHOOL | 500191216 | Emadlangeni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186505 | DB/500191327/WS | KwaZulu-Natal | MADLOZI PRIMARY SCHOOL | 500191327 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2023-09-12 | 2024-03-01 | 2024-05-05 | 2025-01-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186506 | DB/500191623/WS | KwaZulu-Natal | MAFA PRIMARY SCHOOL | 500191623 | Big Five Hlabisa | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-03-01 | 2024-05-05 | 2025-01-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186507 | DB/500192696/WS | KwaZulu-Natal | MAGUGU PRIMARY SCHOOL | 500192696 | Jozini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186556 | I/500279350/SDS | KwaZulu-Natal | TABHANE SECONDARY SCHOOL | I/500279350/SDS | Okhahlamba | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186563 | DB/500195027/WS | KwaZulu-Natal | MALAMBULE SECONDARY SCHOOL | 500195027 | Dannhauser | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-05-31 | 2023-01-31 | 2023-01-03 | 2027-01-03 | 385243 | 1754997 | 2140240 | Education Infrastructure Grant | Upgrading and Additions
|  | 186565 | DB/500195397/WS | KwaZulu-Natal | MALUKHAKHA PRIMARY SCHOOL | 500195397 | Umzumbe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186566 | DB/500196914/WS | KwaZulu-Natal | MANGQUZUKA HIGH SCHOOL | 500196914 | Umzumbe | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186569 | DB/500197025/WS | KwaZulu-Natal | MANGWAZANA SECONDARY SCHOOL | 500197025 | Jozini | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186571 | DB/500197765/WS | KwaZulu-Natal | MANYANE PRIMARY SCHOOL | 500197765 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186572 | DB/500214785/WS | KwaZulu-Natal | MANYONGA LOWER PRIMARY SCHOOL | 500214785 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186573 | DB/500309653/WS | KwaZulu-Natal | MANZAWAYO LOWER PRIMARY SCHOOL | 500309653 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186576 | DB/500198246/WS | KwaZulu-Natal | MANZIMPOFU PRIMARY SCHOOL | 500198246 | uMhlathuze | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2020-09-12 | 2023-03-01 | 2024-05-05 | 2025-01-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186577 | DB/500325748/WS | KwaZulu-Natal | MAQHASHIYA PRIMARY SCHOOL | 500325748 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186578 | DB/500322048/WS | KwaZulu-Natal | MARIA TROST JUNIOR PRIMARY SCHOOL | 500322048 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186585 | DB/500203907/WS | KwaZulu-Natal | MBATHANI PRIMARY SCHOOL | 500203907 | Emadlangeni | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186586 | DB/500209605/WS | KwaZulu-Natal | MGOQOZI PRIMARY SCHOOL | 500209605 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186587 | DB/500210049/WS | KwaZulu-Natal | MHAWUKELWA COMBINED PRIMARY SCHOOL | 500210049 | Ulundi | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2019-09-12 | 2023-01-31 | 2024-05-05 | 2027-01-31 | 302323 | 1377251 | 1679574 | Education Infrastructure Grant | Upgrading and Additions
|  | 186589 | DB/500339475/WS | KwaZulu-Natal | MUNTUKABONI SECONDARY SCHOOL | 500339475 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186590 | DB/500303252/WS | KwaZulu-Natal | MYAYIZA PRIMARY SCHOOL | 500303252 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186591 | DB/500221889/WS | KwaZulu-Natal | MYEZANE PRIMARY SCHOOL | 500221889 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186592 | DB/500323417/WS | KwaZulu-Natal | MZIMELA PRIMARY SCHOOL | 500323417 | Alfred Duma | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186594 | DB/500223850/WS | KwaZulu-Natal | NCOME PRIMARY SCHOOL | 500223850 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186595 | DB/500223961/WS | KwaZulu-Natal | NCWADI PRIMARY SCHOOL | 500223961 | The Msunduzi | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2020-12-01 | 2024-01-30 | 2024-07-14 | 2027-08-31 | 159010 | 724379 | 883389 | Education Infrastructure Grant | Upgrading and Additions
|  | 186596 | DB/500224035/WS | KwaZulu-Natal | NDABAKAZIBUZWA SECONDARY SCHOOL | 500224035 | Nkandla | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-31 | 2023-01-01 | 2027-08-31 | 301231 | 1372273 | 1673504 | Education Infrastructure Grant | Upgrading and Additions
|  | 186597 | DB/500224664/WS | KwaZulu-Natal | NDAYA PRIMARY SCHOOL | 500224664 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186598 | DB/500224738/WS | KwaZulu-Natal | NDELA SECONDARY SCHOOL | 500224738 | Ubuhlebezwe | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2027-08-31 | 349148 | 1590563 | 1939711 | Education Infrastructure Grant | Upgrading and Additions
|  | 186599 | DB/500225256/WS | KwaZulu-Natal | NDLANGAMANDLA SECONDARY SCHOOL | 500225256 | Nqutu | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2027-08-31 | 378281 | 1723278 | 2101559 | Education Infrastructure Grant | Upgrading and Additions
|  | 186600 | DB/500225404/WS | KwaZulu-Natal | NDLONDLO PRIMARY SCHOOL | 500225404 | Nkandla | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2027-08-31 | 468716 | 2135263 | 2603979 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186601 | DB/500427202/WS | KwaZulu-Natal | NDLOZANA JUNIOR PRIMARY SCHOOL | 500427202 | Nongoma | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2023-05-05 | 2025-01-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186602 | DB/500226255/WS | KwaZulu-Natal | NENDE SECONDARY SCHOOL | 500226255 | Nkandla | Tender | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186603 | DB/500227476/WS | KwaZulu-Natal | NGAZINI JUNIOR SECONDARY SCHOOL | 500227476 | Jozini | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2023-05-05 | 2025-01-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186604 | DB/500313353/WS | KwaZulu-Natal | NGOTWENI PRIMARY SCHOOL | 500313353 | Mtubatuba | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2027-08-31 | 237166 | 1080423 | 1317589 | Education Infrastructure Grant | Upgrading and Additions
|  | 186605 | DB/500229252/WS | KwaZulu-Natal | NGWEGWENI PRIMARY SCHOOL | 500229252 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2027-08-31 | 315867 | 1438952 | 1754819 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186606 | DB/500442816/WS | KwaZulu-Natal | NGWEYONKE SECONDARY SCHOOL | 500442816 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186607 | DB/500340437/WS | KwaZulu-Natal | NHLAWE PRIMARY SCHOOL | 500340437 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186609 | DB/500230214/WS | KwaZulu-Natal | NHLIZIYO SECONDARY SCHOOL | 500230214 | Abaqulusi | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186610 | DB/500303178/WS | KwaZulu-Natal | NHLOMANE PRIMARY SCHOOL | 500303178 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186611 | DB/500230547/WS | KwaZulu-Natal | NHLOYANA SECONDARY SCHOOL | 500230547 | Mthonjaneni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186613 | DB/500231065/WS | KwaZulu-Natal | NJENGABANTU PRIMARY SCHOOL | 500231065 | Umvoti | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186614 | DB/500231546/WS | KwaZulu-Natal | NKANDE PRIMARY SCHOOL | 500231546 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186615 | DB/500231694/WS | KwaZulu-Natal | NKANYEZI PRIMARY SCHOOL | 500231694 | Endumeni | Construction 1% - 25% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 268143 | 1221542 | 1489685 | Education Infrastructure Grant | Upgrading and Additions
|  | 186616 | DB/500231879/WS | KwaZulu-Natal | NKEHLAMANDLA JUNIOR PRIMARY SCHOOL | 500231879 | Umzumbe | Construction 26% - 50% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2024-01-29 | 2024-07-14 | 2027-08-31 | 329457 | 1500858 | 1830315 | Education Infrastructure Grant | Upgrading and Additions
|  | 186617 | DB/500232027/WS | KwaZulu-Natal | NKLANGOZI PRIMARY SCHOOL | 500232027 | eDumbe | Construction 1% - 25% | Active - Not Contracted | 2018-01-01 | 2024-01-01 | 2025-01-29 | 2026-06-20 | 2027-03-30 | 177974 | 810769 | 988743 | Education Infrastructure Grant | Upgrading and Additions
|  | 186618 | DB/500232101/WS | KwaZulu-Natal | NKOLOKOTHO JUNIOR PRIMARY SCHOOL | 500232101 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186619 | DB/500232286/WS | KwaZulu-Natal | NKONISA PRIMARY SCHOOL | 500232286 | Nkandla | Practical Completion (100%) | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2027-08-31 | 253286 | 1153858 | 1407144 | Education Infrastructure Grant | Upgrading and Additions
|  | 186620 | DB/500232360/WS | KwaZulu-Natal | NKONKA HIGH SCHOOL | 500232360 | Ray Nkonyeni | Construction 26% - 50% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-05-05 | 2027-08-31 | 517407 | 2357075 | 2874482 | Education Infrastructure Grant | Upgrading and Additions
|  | 186621 | DB/500232434/WS | KwaZulu-Natal | NKONYANE PRIMARY SCHOOL | 500232434 | Msinga | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186622 | DB/500232767/WS | KwaZulu-Natal | NKOSITHANDILE SECONDARY SCHOOL | 500232767 | Mthonjaneni | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2027-08-31 | 401596 | 1829493 | 2231089 | Education Infrastructure Grant | Upgrading and Additions
|  | 186623 | DB/500232841/WS | KwaZulu-Natal | NKOWANE HIGH SCHOOL | 500232841 | Nongoma | Practical Completion (100%) | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2027-08-31 | 1338920 | 6099524 | 7438444 | Education Infrastructure Grant | Upgrading and Additions
|  | 186624 | DB/500232878/WS | KwaZulu-Natal | NKUKHU LOWER PRIMARY SCHOOLP | 500232878 | Nkandla | Construction 26% - 50% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2027-08-31 | 413506 | 1883751 | 2297257 | Education Infrastructure Grant | Upgrading and Additions
|  | 186625 | DB/500233063/WS | KwaZulu-Natal | NKUNSWANA PRIMARY SCHOOL | 500233063 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186626 | DB/500233877/WS | KwaZulu-Natal | NOGAWU PRIMARY SCHOOL | 500233877 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186627 | DB/500234210/WS | KwaZulu-Natal | NOKWEJA PRIMARY SCHOOL | 500234210 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186628 | DB/500234247/WS | KwaZulu-Natal | NOKWEJA SECONDARY SCHOOL | 500234247 | Ubuhlebezwe | Construction 1% - 25% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 362764 | 1652593 | 2015357 | Education Infrastructure Grant | Upgrading and Additions
|  | 186629 | DB/500234284/WS | KwaZulu-Natal | NOMABHUNGA LOWER PRIMARY SCHOOL | 500234284 | Umdoni | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186630 | DB/500234358/WS | KwaZulu-Natal | NOMAGAGA PRIMARY SCHOOL | 500234358 | Dr Nkosazana Dlamini Zuma | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-08-31 | 302977 | 1380227 | 1683204 | Education Infrastructure Grant | Upgrading and Additions
|  | 186631 | DB/500234506/WS | KwaZulu-Natal | NOMAKHANZANA PRIMARY SCHOOL | 500234506 | Umzumbe | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 451959 | 2058922 | 2510881 | Education Infrastructure Grant | Upgrading and Additions
|  | 186632 | DB/500427461/WS | KwaZulu-Natal | NOMPUMELELO SECONDARY SCHOOL | 500427461 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186633 | DB/500235431/WS | KwaZulu-Natal | NONDWAYIZA PRIMARY SCHOOL | 500235431 | uMshwathi | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186634 | I/500341325/SDS | KwaZulu-Natal | SITHEMBINHLAHLA HIGH SCHOOL | I/500341325/SDS | Jozini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186635 | I/500269915/SDS | KwaZulu-Natal | SIYAMUKELA SECONDARY SCHOOL(HOSTELS) | I/500269915/SDS | Newcastle | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186636 | I/500270544/SDS | KwaZulu-Natal | SIYAZENZELA HIGH SCHOOL | I/500270544/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186637 | DB/500235468/WS | KwaZulu-Natal | NONDWENI PRIMARY SCHOOL | 500235468 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186638 | I/500270729/SDS | KwaZulu-Natal | SIYETHEMBA PRIMARY SCHOOL | I/500270729/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186639 | I/500306286/UA | KwaZulu-Natal | ST JULIUS SECONDARY SCHOOL | I/500306286/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2026-03-31 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186640 | I/500276353/SDS | KwaZulu-Natal | ST MICHAELS PRIMARY SCHOOL | I/500276353/SDS | eThekwini | Design | Active - Not Contracted | 2019-08-20 |  | 2023-08-20 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186641 | DB/500235986/WS | KwaZulu-Natal | NOORDENVELD COMBINED SCHOOL | 500235986 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186642 | DB/500326044/WS | KwaZulu-Natal | NQOBIZAZI JUNIOR SECONDARY SCHOOL | 500326044 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186643 | DB/500237799/WS | KwaZulu-Natal | NSABEKHULUMA HIGH SCHOOL | 500237799 | Ulundi | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186644 | DB/500337958/WS | KwaZulu-Natal | NSIMBINI PRIMARY SCHOOL | 500337958 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186645 | DB/500238280/WS | KwaZulu-Natal | NSOMBOSI PRIMARY SCHOOL | 500238280 | Mtubatuba | Construction 76% - 99% | Active - Not Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2025-06-20 | 351153 | 1599697 | 1950850 | Education Infrastructure Grant | Upgrading and Additions
|  | 186647 | DB/500238465/WS | KwaZulu-Natal | NSUKAZI PRIMARY SCHOOL | 500238465 | uMlalazi | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186648 | DB/500238909/WS | KwaZulu-Natal | NTABASIBAHLE PRIMARY SCHOOL | 500238909 | Nqutu | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186650 | DB/500239353/WS | KwaZulu-Natal | NTANDOKAZI PRIMARY SCHOOL | 500239353 | Mtubatuba | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186651 | DB/500239427/WS | KwaZulu-Natal | NTANYENI JUNIOR PRIMARY SCHOOL | 500239427 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186652 | DB/500239723/WS | KwaZulu-Natal | NTENGA PRIMARY SCHOOL | 500239723 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186653 | I/500280756/SDS | KwaZulu-Natal | THAPHOKUHLE PRIMARY SCHOOL | I/500280756/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186654 | DB/500239797/WS | KwaZulu-Natal | NTILI PRIMARY SCHOOL | 500239797 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186655 | DB/500310541/WS | KwaZulu-Natal | NTSHINGWAYO SECONDARY SCHOOL | 500310541 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186656 | I/500282199/SDS | KwaZulu-Natal | THOKAZI PRIMARY SCHOOL | I/500282199/SDS | Nongoma | Design | Active - Not Contracted | 2019-08-21 |  | 2023-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186657 | DB/500240685/WS | KwaZulu-Natal | NTSHOSHO PRIMARY SCHOOL | 500240685 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186658 | DB/500240907/WS | KwaZulu-Natal | NTUMBENI PRIMARY SCHOOL | 500240907 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186659 | DB/500241351/WS | KwaZulu-Natal | NXUSA PRIMARY SCHOOL | 500241351 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186660 | DB/500309986/WS | KwaZulu-Natal | NYAMANE SECONDARY SCHOOL | 500309986 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186662 | DB/500241980/WS | KwaZulu-Natal | NYONYANA PRIMARY SCHOOL | 500241980 | Msinga | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186663 | DB/500242461/WS | KwaZulu-Natal | OBUKA SECONDARY SCHOOL | 500242461 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186664 | DB/500243164/WS | KwaZulu-Natal | OHLANGENI JUNIOR PRIMARY SCHOOL | 500243164 | eThekwini | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 358092 | 1631306 | 1989398 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186665 | DB/500243386/WS | KwaZulu-Natal | OKHAYENI PRIMARY SCHOOL | 500243386 | Jozini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186666 | DB/500243830/WS | KwaZulu-Natal | ONDINI PRIMARY SCHOOL | 500243830 | Ulundi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186667 | DB/500243978/WS | KwaZulu-Natal | ONTINGWENI PRIMARY SCHOOL | 500243978 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 557115 | 2537970 | 3095085 | Education Infrastructure Grant | Upgrading and Additions
|  | 186668 | DB/500244163/WS | KwaZulu-Natal | OPHANSI PRIMARY SCHOOL | 500244163 | Jozini | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 580879 | 2646226 | 3227105 | Education Infrastructure Grant | Upgrading and Additions
|  | 186669 | DB/500244459/WS | KwaZulu-Natal | OQONDWENI PRIMARY SCHOOL | 500244459 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186670 | DB/500244718/WS | KwaZulu-Natal | OSCARSBERG PRIMARY SCHOOL | 500244718 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186671 | DB/500245014/WS | KwaZulu-Natal | OTHOBOTHINI PRIMARY SCHOOL | 500245014 | Jozini | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-05-05 | 2025-08-31 | 775395 | 3532355 | 4307750 | Education Infrastructure Grant | Upgrading and Additions
|  | 186672 | DB/500245051/WS | KwaZulu-Natal | OTHUNGWINI PRIMARY SCHOOL | 500245051 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186673 | DB/500245495/WS | KwaZulu-Natal | OVERTOUN PRIMARY SCHOOL | 500245495 | Nkandla | Construction 26% - 50% | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186676 | DB/500245532/WS | KwaZulu-Natal | OVICENI PRIMARY SCHOOL | 500245532 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186678 | DB/500245606/WS | KwaZulu-Natal | OXOLWENI PRIMARY SCHOOL | 500245606 | KwaDukuza | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186679 | DB/500245680/WS | KwaZulu-Natal | OZABENI PRIMARY SCHOOL | 500245680 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186680 | DB/500245865/WS | KwaZulu-Natal | PADDOCK PRIMARY SCHOOL | 500245865 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Equitable Share | Upgrading and Additions
|  | 186682 | DB/500247160/WS | KwaZulu-Natal | PETERGATE PRIMARY SCHOOL | 500247160 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186683 | DB/500248714/WS | KwaZulu-Natal | PHILANI PRIMARY SCHOOL (NQUTU) | 500248714 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186685 | DB/500250823/WS | KwaZulu-Natal | POMEROY PRIMARY SCHOOL | 500250823 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186686 | DB/500250860/WS | KwaZulu-Natal | POMEROY PRIMARY SCHOOL | 500250860 | Nkandla | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2022-07-14 | 2025-08-31 | 607549 | 2767723 | 3375272 | Education Infrastructure Grant | Upgrading and Additions
|  | 186688 | DB/500253080/WS | KwaZulu-Natal | QHUBEKANI PRIMARY SCHOOL | 500253080 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186689 | DB500261072/WS | KwaZulu-Natal | SGODIPHOLA PRIMARY SCHOOL | 500261072 | Newcastle | Construction 26% - 50% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-01-29 | 2023-07-14 | 2027-08-31 | 230236 | 1048851 | 1279087 | Education Infrastructure Grant | Upgrading and Additions
|  | 186692 | DB/500264957/WS | KwaZulu-Natal | SIKHONA PRIMARY SCHOOL | 500264957 | Newcastle | Construction 1% - 25% | Active - Contracted | 2018-01-01 | 2021-01-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 111388 | 582122 | 693510 | Education Infrastructure Grant | Upgrading and Additions
|  | 186694 | DB/500271136/WS | KwaZulu-Natal | SIZANANI SECONDARY SCHOOL | 500271136 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186696 | DB/500274688/WS | KwaZulu-Natal | SPRINGLAKE HIGH SCHOOL | 500274688 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-02-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186700 | DB/500294372/WS | KwaZulu-Natal | WAAIHOEK PRIMARY SCHOOL | 500294372 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186701 | DB/500296666/WS | KwaZulu-Natal | WIT-UMFOLOZI SECONDARY SCHOOL | 500296666 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2023-04-28 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186704 | DB/500301032/WS | KwaZulu-Natal | ZIZUZELE PRIMARY SCHOOL | 500301032 | Nkandla | Construction 1% - 25% | Active - Not Contracted | 2018-01-01 | 2020-05-29 | 2023-01-29 | 2022-02-15 | 2025-03-14 | 234778 | 1069544 | 1304322 | Education Infrastructure Grant | Upgrading and Additions
|  | 186746 | E16/19/20 | Free State | CONV: TECHNICAL WORKHOP | E16/19/20 | Mangaung | Project Initiation | Proposed | 2020-01-03 |  | 2024-03-31 |  |  | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186747 | E13/19/20 | Free State | DBSA CURRNT MAINTENANCE | E13/19/20 | Metsimaholo | Project Initiation | Approved | 2019-12-10 |  | 2027-03-31 |  |  | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 186748 | DBSA17 | Free State | KRNSTD TEACHER DEV INST | DBSA 17 | Moqhaka | Project Initiation | Proposed | 2019-12-11 |  | 2025-04-01 |  |  | 0 | 7000000 | 7000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186749 | LE20IDT09018 | Limpopo | Masakona / Rasikhutuma Primary | 912521484 | Collins Chabane | Construction 26% - 50% | Active - Contracted | 2019-01-02 |  | 2024-03-30 |  |  | 2260000 | 9040000 | 11300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186750 | ET/500142080/WS | KwaZulu-Natal | ETETE SA FARM PRIMARY SCHOOL | 500142080 | KwaDukuza | Construction 76% - 99% | Active - Contracted | 2018-06-23 | 2019-09-10 | 2023-04-30 | 2025-04-30 | 2025-04-30 | 639425 | 2912934 | 3552359 | Equitable Share | Upgrading and Additions
|  | 186751 | E14/19/20 | Free State | MAINTENANCE CAPTL DBSA | E14/19/20 | Mangaung | Project Initiation | Proposed | 2019-12-05 |  | 2026-03-31 |  |  | 0 | 12000000 | 12000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186753 | E15/19/20 | Free State | UPGRADES & ADDITNS DBSA | 15/19/20 | Masilonyana | Site Handed - Over to Contractor | Active - Contracted | 2019-10-01 | 2020-07-02 | 2024-03-31 | 2024-03-31 | 2024-01-31 | 20000000 | 0 | 20000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186754 | E26/19/20 | Free State | CONDITION ASSESSMENT (DBSA) | E26/19/20 | Mangaung | Project Initiation | Proposed | 2019-12-11 |  | 2026-03-31 |  |  | 0 | 8000000 | 8000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 186755 | E25/19/20 | Free State | CONVERSN AUTISM SCHOOL | E25/19/20 | Mangaung | Project Initiation | Proposed | 2019-09-01 |  | 2025-04-01 |  |  | 0 | 5000000 | 5000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186760 | E24/19/20 | Free State | BFN: NEW : BERGMAN (DBSA) | E24/19/20 | Mangaung | Project Initiation | Approved | 2019-10-01 |  | 2024-03-31 |  |  | 0 | 5000000 | 5000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 186761 | E23/19/20 | Free State | CONVERSION ART SCHOOL | E23/19/20 | Mangaung | Project Initiation | Approved | 2019-10-01 |  | 2024-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186762 | DBSA21/19/20 | Free State | Bloemfontein: Mangaung:Matla 2 (DBSA) | DBSA21/19/20 | Mangaung | Construction 51% - 75% | Approved | 2019-10-01 |  | 2024-03-31 |  |  | 5000000 | 0 | 5000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 186763 | DBSA2-22/19/20 | Free State | Bloemfontein: Mangaung:Arbeidsgenot (DBSA) | DBSA-22/19/20 | Mangaung | Project Initiation | Approved | 2019-10-01 |  | 2024-03-31 |  |  | 5000000 | 0 | 5000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 186765 | E18/19/20 | Free State | SMART SCHOOLS | E18/19/20 | Mangaung | Project Initiation | Approved | 2019-11-01 |  | 2026-03-31 |  |  | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Infrastructure Transfers - Current
|  | 186766 | LE20IDT09011 | Limpopo | Machaka Robert Mamabolo Primary | 904241092 | Greater Tzaneen | Tender | Active - Not Contracted | 2019-02-20 |  | 2024-03-31 |  |  | 1600000 | 6400000 | 8000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 186773 | DB/500109927/SDS | KwaZulu-Natal | BHUNGANE HIGH SCHOOL | 500109927 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-01-01 | 2018-01-12 | 2023-11-30 | 2023-05-05 | 2023-06-20 | 1660578 | 7564857 | 9225435 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186774 | DB/500340178/SDS | KwaZulu-Natal | ENKOMOKAZINI TECHNICAL SCHOOL | 500340178 | Nkandla | Construction 76% - 99% | Active - Contracted | 2016-04-20 | 2018-04-19 | 2024-03-30 | 2020-05-05 | 2024-03-30 | 990737 | 4513358 | 5504095 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 186775 | E22/18/19 | Free State | Office Furniture | E22/18/19 | Masilonyana | Project Initiation | Approved | 2019-04-01 |  | 2026-03-31 |  |  | 282000 | 0 | 282000 | Infrastructure Enhancement Allocation | Non-Infrastructure
|  | 186777 | E20/19/20 | Free State | OFFICE RELOCATION | E20/19/20 | Masilonyana | Project Initiation | Approved | 2019-04-01 |  | 2026-03-31 |  |  | 2000000 | 0 | 2000000 | Infrastructure Enhancement Allocation | Non-Infrastructure
|  | 186789 | GDE00417 | Gauteng | MOBILE CLASSROOMS | N/A | City of Ekurhuleni | Tender | Proposed | 2019-04-01 |  | 2022-11-11 |  |  | 16272000 | 85428000 | 101700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187034 | MDOE/UPG/008/20-21(DPWRT/054/19/MP) | Mpumalanga | Lihawu secondary school | 800010413 | Mbombela | Design | Active - Not Contracted | 2019-08-05 |  | 2024-07-25 |  |  | 1755145 | 9750808 | 11505953 | Education Infrastructure Grant | Upgrading and Additions
|  | 187044 | P9006630 | Eastern Cape | MASAKHE PRIMARY SCHOOL | 200200420 | Buffalo City | Design | Active - Not Contracted | 2016-01-05 |  | 2026-10-31 |  |  | 0 | 12394970 | 12394970 | Education Infrastructure Grant | Upgrading and Additions
|  | 187049 | P9009598/ | Eastern Cape | MATOLWENI JUNIOR SECONDARY SCHOOL | 200300833 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-05-03 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 85514 | 610817 | 696331 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187130 | LE20TMT17012 | Limpopo | MALOVHANA SECONDARY | 912521224 | Collins Chabane | Tender | Active - Not Contracted | 2019-02-28 |  | 2024-03-31 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 187133 | LE19TMT17044 | Limpopo | Moloke Primary School | 925611042 | Greater Tubatse/Fetakgomo | Tender | Active - Not Contracted | 2019-03-31 |  | 2025-03-31 |  |  | 700000 | 2800000 | 3500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187134 | LE19TMT17041 | Limpopo | MODIPE HIGH | 918510637 | Greater Tzaneen | Tender | Active - Not Contracted | 2019-02-02 |  | 2025-03-31 |  |  | 464000 | 5000000 | 5464000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187166 | 600100093 | North West | BATLHALERWA PRIMARY SCHOOL 01 | BATLHALERWA 01 | Moses Kotane | Pre - Feasibility | Active - Contracted | 2019-11-01 |  | 2026-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187167 | 600100234 | North West | CHANENNG PRIMARY SCHOOL | CHANENG 01 | Rustenburg | Tender | Active - Contracted | 2019-11-01 |  | 2026-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187175 | SAMMUAEL PHIRI | North West | SAMMUAEL PHIRI PRIMARY SCHOOL | SAMMUAEL PHIRI | Maquassi Hills | Project Initiation | Approved | 2019-11-01 |  | 2025-03-31 |  |  | 0 | 12500000 | 12500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187177 | REPLACEMENT 01 | North West | REPLACEMENT OF ASBESTOS ROOFS | ASBESTOS ROOFS 01 | Mafikeng | Project Initiation | Proposed | 2019-04-01 |  | 2024-03-15 |  |  | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187180 | DB/500440374/WS | KwaZulu-Natal | MSAWENKOSI PRIMARY SCHOOL | 500440374 | Nkandla | Construction 26% - 50% | Active - Contracted | 2016-06-13 | 2018-04-05 | 2023-11-30 | 2020-05-05 | 2025-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187184 | C/500136419/ECD | KwaZulu-Natal | ENGOBHIYENI PRIMARY SCHOOL | 500213342 | Nkandla | Design | Active - Not Contracted | 2016-06-06 |  | 2024-05-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187188 | DB/500225119/WS | KwaZulu-Natal | KWAQONDILE PRIMARY SCHOOL | 500225119 | Nkandla | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2024-06-20 | 2020-05-05 | 2024-06-20 | 425000 | 1285000 | 1710000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187189 | DB/50031006/WS | KwaZulu-Natal | MALANGABI JUNIOR PRIMARY SCHOOL | 500310060 | Nkandla | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2024-06-20 | 2020-05-05 | 2024-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187190 | DB/500130980/SDS | KwaZulu-Natal | EMALAHLENI PRIMARY SCHOOL | 500130980 | Nkandla | Final Completion | Approved | 2016-06-06 | 2018-04-05 | 2023-11-30 | 2023-05-05 | 2024-03-30 | 1935344 | 8816565 | 10751909 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187194 | DB/500290006/UA | KwaZulu-Natal | UNTUNJAMBILI PRIMARY SCHOOL | DB/500290006/UA | Maphumulo | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2022-11-30 | 2022-12-05 | 2027-04-06 | 1656248 | 7545131 | 9201379 | Education Infrastructure Grant | Upgrading and Additions
|  | 187195 | DB/500140970/ECD | KwaZulu-Natal | ESIPHAHLENI PRIMARY | 500140970 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187196 | DB/500491397/ECD | KwaZulu-Natal | NGULUZANA PRIMARY SCHOOL | 500491397 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2026-03-31 |  |  | 1112040 | 5065960 | 6178000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187197 | DB/500120065/RRR | KwaZulu-Natal | DASSENHOEK HIGH SCHOOL | 500120065 | Nkandla | Design | Active - Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 2968817 | 13524611 | 16493428 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187198 | DB/500133496/RRR | KwaZulu-Natal | EMNQUNDEKWENI PRIMARY SCHOOL | 500133496 | Nkandla | Design | Active - Not Contracted | 2016-06-06 |  | 2027-03-30 |  |  | 313109 | 1426387 | 1739496 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187199 | LE20TMT17072 | Limpopo | Bahananwa Circuit | LP09044 | Blouberg | Construction 76% - 99% | Active - Contracted | 2017-03-04 | 2019-08-30 | 2023-03-31 | 20203-03-31 | 2023-03-31 | 186059 | 1860594 | 2046653 | Education Infrastructure Grant | Upgrading and Additions
|  | 187200 | LE19TMT17096 | Limpopo | Boreletsana Primary | 918510057 | Greater Letaba | Construction 76% - 99% | Active - Contracted | 2018-02-03 |  | 2024-03-31 |  |  | 192000 | 768000 | 960000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187201 | LE19TMT17013 | Limpopo | HLANGANANI SOUTH CIRCUIT | 33033 | Collins Chabane | Construction 26% - 50% | Active - Contracted | 2018-02-03 |  | 2023-03-31 |  |  | 105818 | 398337 | 504155 | Education Infrastructure Grant | Upgrading and Additions
|  | 187202 | LE20TMT17009 | Limpopo | Mabande Primary | 996606517 | Elias Motsoaledi | Practical Completion (100%) | Active - Contracted | 2018-02-03 | 2018-05-01 | 2024-06-29 | 2024-06-29 | 2024-06-30 | 584131 | 5158917 | 5743048 | Education Infrastructure Grant | Upgrading and Additions
|  | 187203 | LE20TMT17055 | Limpopo | Vari Primary School | 93134119 | Makhado | Construction 76% - 99% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 0 | 5648948 | 5648948 | Education Infrastructure Grant | Upgrading and Additions
|  | 187205 | LE19TMT17037 | Limpopo | MASIKHWA PRIMARY | 930350231 | Thulamela | Practical Completion (100%) | Active - Contracted | 2018-02-03 |  | 2023-03-31 |  |  | 520853 | 4663862 | 5184715 | Education Infrastructure Grant | Upgrading and Additions
|  | 187206 | LE20TMT17015 | Limpopo | Mokolo Primary | 910133078 | Modimolle/Mookgophong | Tender | Active - Not Contracted | 2018-02-03 |  | 2025-03-31 |  |  | 0 | 8148837 | 8148837 | Education Infrastructure Grant | Upgrading and Additions
|  | 187207 | LE19TMT17113 | Limpopo | Raserite Primary | 921111443 | Lephalale | Tender | Active - Not Contracted | 2018-02-03 |  | 2025-03-30 |  |  | 203800 | 815200 | 1019000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187212 | LE19TMT17053 | Limpopo | Phaweni Primary | 993301402 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2018-02-03 |  | 2024-03-30 |  |  | 584980 | 5200620 | 5785600 | Education Infrastructure Grant | Upgrading and Additions
|  | 187213 | LE19TMT17093 | Limpopo | THABISONG PRIMARY | 918511432 | Greater Letaba | Tender | Active - Contracted | 2018-02-03 |  | 2024-03-30 |  |  | 0 | 4916437 | 4916437 | Education Infrastructure Grant | Upgrading and Additions
|  | 187214 | LE19TMT17058 | Limpopo | ramushasha primary school | 930350187 | Thulamela | Design | Active - Not Contracted | 2018-02-03 |  | 2025-03-31 |  |  | 262000 | 1048000 | 1310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187219 | LE20TMT17042 | Limpopo | ALLDAYS PRIMARY | 920213146 | Blouberg | Final Completion | Active - Contracted | 2018-02-03 | 2018-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 159786 | 2282657 | 2442443 | Education Infrastructure Grant | Upgrading and Additions
|  | 187231 | LE19TMT17088 | Limpopo | MATSHAVHAWE PRIMARY | 928331308 | Makhado | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2024-03-30 | 2020-03-31 | 2024-03-31 | 280000 | 1120000 | 1400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187234 | LE19TMT17036 | Limpopo | Masakona / Rasikhutuma Primary | 912521484 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 533054 | 3573090 | 4106144 | Education Infrastructure Grant | Upgrading and Additions
|  | 187235 | LE19TMT17119 | Limpopo | BYSONDERHEID PRIMARY | 906120515 | Modimolle/Mookgophong | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2024-03-31 | 2024-03-31 | 2025-03-31 | 452000 | 1808000 | 2260000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187236 | LE19TMT17111 | Limpopo | MMASESHA PRIMARY SCHOOL | 992205606 | Polokwane | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2025-03-30 | 2024-03-30 | 2024-03-31 | 197200 | 788800 | 986000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187237 | LE19TMT17129 | Limpopo | Khataza High School | 9265400652 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2018-02-03 |  | 2023-05-30 |  |  | 297069 | 2169594 | 2466663 | Education Infrastructure Grant | Upgrading and Additions
|  | 187239 | LE19TMT17097 | Limpopo | MOHOKONE PRIMARY | 918511050 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2023-05-30 | 2023-05-30 | 2023-05-31 | 473126 | 3697231 | 4170357 | Education Infrastructure Grant | Upgrading and Additions
|  | 187243 | LE19TMT17106 | Limpopo | Ramokhutlwane Combined School | 996606615 | Mogalakwena | Design | Active - Not Contracted | 2018-02-03 |  | 2025-03-31 |  |  | 128000 | 512000 | 640000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187371 | LE20TMT17032 | Limpopo | Tsheesebe Primary | 921111160 | Lephalale | Tender | Active - Contracted | 2019-03-01 |  | 2025-03-31 |  |  | 61148 | 244590 | 305738 | Education Infrastructure Grant | Upgrading and Additions
|  | 187372 | C/500196137/RRR | KwaZulu-Natal | MANDLAKAZULU PRIMARY SCHOOL | 500196137 | eThekwini | Tender | Active - Not Contracted | 2019-06-02 |  | 2026-03-30 |  |  | 220000 | 5953000 | 6173000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187374 | C/500489954/ECD | KwaZulu-Natal | THEMBINKOSI PRIMARY SCHOOL | 500489954 | Newcastle | Design | Active - Not Contracted | 2018-03-31 |  | 2023-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187375 | C/500102860/RRR | KwaZulu-Natal | AMATSHEZULU HIGH SCHOOL | 500102860 | eThekwini | On Hold | Active - Not Contracted | 2018-03-31 |  | 2024-03-31 |  |  | 1800000 | 3400000 | 5200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187376 | LE20TMT17026 | Limpopo | Thabane Primary | 925621162 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2017-03-04 | 2019-04-01 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 362307 | 3720443 | 4082750 | Education Infrastructure Grant | Upgrading and Additions
|  | 187377 | C/500122877/RRR | KwaZulu-Natal | DOON HEIGHTS PRIMARY SCHOOL | 500122877 | eThekwini | Tender | Active - Not Contracted | 2019-03-31 |  | 2024-01-03 |  |  | 700000 | 2500000 | 3200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187378 | C/500322159/RRR | KwaZulu-Natal | GEZA PRIMARY SCHOOL | 500322159 | Umhlabuyalingana | Final Completion | Active - Contracted | 2019-05-10 |  | 2023-04-30 |  |  | 1800000 | 3400000 | 5200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187383 | DB/500279276/SDS | KwaZulu-Natal | SYDNENHAM PRIMARY SCHOOL | 500279276 | Nkandla | Practical Completion (100%) | Active - Contracted | 2020-01-05 | 2020-08-21 | 2022-09-02 | 2022-09-30 | 2022-10-28 | 379706 | 1729770 | 2109476 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187387 | DB/500203944/SDS | KwaZulu-Natal | MBATSHAZWA SECONDARY SCHOOL | 500203944 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-04-05 | 2023-11-30 | 2020-05-05 | 2023-05-05 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187410 | DB/500130647/SDS | KwaZulu-Natal | EMAHHASHINI PRIMARY SCHOOL | 500130647 | Inkosi Langalibalele | Construction 76% - 99% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2023-03-25 | 2023-03-25 | 2025-03-25 | 1450113 | 6606071 | 8056184 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187420 | DB/500262589/SDS | KwaZulu-Natal | SIBANESIHLE HIGH | 500262589 | The Msunduzi | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-04-05 | 2025-06-20 | 2020-05-05 | 2025-06-20 | 1404473 | 6398153 | 7802626 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187427 | C/500163503/RRR | KwaZulu-Natal | INGQUBEKO PRIMARY SCHOOL | 500163503 | Abaqulusi | On Hold | Active - Not Contracted | 2019-05-10 |  | 2024-06-01 |  |  | 1800000 | 3400000 | 5200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187432 | C/500213157/RRR | KwaZulu-Natal | MNAFU SECONDARY SCHOOL | 500213157 | Umzumbe | On Hold | Active - Contracted | 2019-05-10 |  | 2023-04-25 |  |  | 1602000 | 7298000 | 8900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187434 | GDE00018 | Gauteng | BIRCH ACRES SECONDARY SCHOOL | N/A | City of Ekurhuleni | Design | Active - Not Contracted | 2019-01-04 |  | 2026-02-13 |  |  | 11200000 | 58800000 | 70000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187436 | C/500324157/RRR | KwaZulu-Natal | MTHULI SECONDARY SCHOOL | 500324157 | uMshwathi | On Hold | Active - Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1500000 | 3500000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187437 | C/500190735/RRR | KwaZulu-Natal | MUZI THUSI PRIMARY SCHOOL | 190735 | The Msunduzi | On Hold | Active - Contracted | 2019-05-10 | 2021-07-01 | 2024-04-01 | 2024-03-25 | 2024-12-20 | 755000 | 4768000 | 5523000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187439 | C/500237096/RRR | KwaZulu-Natal | NQABAKAZULU COMPREHENSIVE HIGH SCHOOL | 500237096 | eThekwini | Design | Active - Contracted | 2019-05-10 |  | 2026-04-01 |  |  | 1800000 | 3400000 | 5200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187441 | C/500253820/RRR | KwaZulu-Natal | QOPHINDLELA HIGH SCHOOL | 500253820 | Alfred Duma | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1800000 | 3512000 | 5312000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187444 | C/500263218/RRR | KwaZulu-Natal | SIBONGUMBOMVU COMBINED SCHOOL | 500263218 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1500000 | 5300000 | 6800000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187448 | W/500150886/SDS | KwaZulu-Natal | GOLOKODO PRIMARY SCHOOL | 500150886 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-07-01 | 2022-08-30 | 2023-03-30 | 2024-03-30 | 2025-04-30 | 350000 | 1302000 | 1652000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187449 | C/500281383/RRR | KwaZulu-Natal | THEMBALENTSHA HIGH SCHOOL | 500281383 | Newcastle | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1602000 | 7298000 | 8900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187451 | C/500103637/ECD | KwaZulu-Natal | ASAMUKELE PRIMARY SCHOOL | 500103637 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187452 | ET/500224257/WS | KwaZulu-Natal | NDABENHLE PRIMARY SCHOOL (INANDA) | 500224257 | eThekwini | Construction 51% - 75% | Active - Contracted | 2019-09-12 | 2024-08-24 | 2024-08-24 | 2025-08-24 | 2025-08-24 | 642600 | 2927400 | 3570000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187456 | DB/500211529/SDS | KwaZulu-Natal | INKOSI MJWAYELI PRIMARY SCHOOL | 500211529 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-01-12 | 2023-11-30 | 2023-05-05 | 2025-06-20 | 1580875 | 7201763 | 8782638 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187465 | DB/500286121/SDS | KwaZulu-Natal | Udumo Primary School | 500286084 | eThekwini | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2023-06-30 | 2022-10-05 | 2022-06-20 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187474 | C/500106412/ECD | KwaZulu-Natal | BAXOLELENI PRIMARY SCHOOL | 500106412 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187475 | C/500111037/ECD | KwaZulu-Natal | BONGELA INTERMEDIATE SCHOOL | 500111037 | uMlalazi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187476 | C/500121360/ECD | KwaZulu-Natal | DINDI PRIMARY SCHOOL | 500121360 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-03-31 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187477 | C/500122174/ECD | KwaZulu-Natal | DLOKWAKHE PRIMARY SCHOOL | 500122174 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187479 | C/500114811/ECD | KwaZulu-Natal | CATHULANI PRIMARY SCHOOL | 500114811 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187480 | C/500115292/ECD | KwaZulu-Natal | CELANI PRIMARY SCHOOL | 500449291 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187481 | C/500303918/ECD | KwaZulu-Natal | CHOTHWANE PRIMARY SCHOOL | 500303918 | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187482 | DB/500101232/LSEN | KwaZulu-Natal | A M MOOLLA SPES NOVA LSEN SCHOOL | 500101232 | eThekwini | Tender | Active - Contracted | 2018-01-01 |  | 2026-03-20 |  |  | 754868 | 3438844 | 4193712 | Education Infrastructure Grant | Upgrading and Additions
|  | 187483 | C/500117068/ECD | KwaZulu-Natal | CLAVIS PRIMARY SCHOOL | 500117068 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187484 | DB/500227069/LSEN | KwaZulu-Natal | NEWTON SECONDARY SCHOOL (SPECIAL SCHOOL) | 500227069 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 4724436 | 21522432 | 26246868 | Education Infrastructure Grant | Upgrading and Additions
|  | 187485 | DB/500247123/LSEN | KwaZulu-Natal | PETER PAN SPECIAL SCHOOL | 500247123 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 3319558 | 15122430 | 18441988 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187486 | DB/500150331/UA | KwaZulu-Natal | GOBIZEMBE HIGH SCHOOL | 500150331 | uMshwathi | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187487 | DB/500153069/UA | KwaZulu-Natal | HAFULENI SECONDARY SCHOOL | 500153069 | uMuziwabantu | Construction 76% - 99% | Active - Contracted | 2018-01-01 | 2019-08-31 | 2023-03-01 | 2022-03-25 | 2027-03-30 | 2689439 | 12251888 | 14941327 | Education Infrastructure Grant | Upgrading and Additions
|  | 187488 | DB/500184778/UA | KwaZulu-Natal | LADUMA HIGH SCHOOL | 500184778 | The Msunduzi | Design | Active - Not Contracted | 2016-06-06 |  | 2027-11-30 |  |  | 4853945 | 22112417 | 26966362 | Education Infrastructure Grant | Upgrading and Additions
|  | 187489 | DB/500199023/UA | KwaZulu-Natal | MAQWABE PRIMARY SCHOOL | 500199023 | Mfolozi | Design | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 5827831 | 26549007 | 32376838 | Education Infrastructure Grant | Upgrading and Additions
|  | 187490 | DB/500227106/UA | KwaZulu-Natal | NEWTONVILLE PRIMARY SCHOOL | 500227106 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187491 | DB/500236948/UA | KwaZulu-Natal | NOVUKA PRIMARY SCHOOL | 500236948 | Impendle | Design | Active - Not Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187492 | DB/500244089/UA | KwaZulu-Natal | OPEN AIR SPECIAL SCHOOL | 500244089 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 1977141 | 9006973 | 10984114 | Education Infrastructure Grant | Upgrading and Additions
|  | 187493 | DB/500248603/UA | KwaZulu-Natal | PHIKISWAYO PRIMARY SCHOOL | 500248603 | eThekwini | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187494 | DB/500258223/UA | KwaZulu-Natal | SANELISIWE PRIMARY SCHOOL | 500258223 | The Msunduzi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 4033464 | 18374667 | 22408131 | Education Infrastructure Grant | Upgrading and Additions
|  | 187496 | DB/500265549/UA | KwaZulu-Natal | SLIDNOKUHLE PRIMARY SCHOOL | 500265549 | The Msunduzi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187497 | DB/500282791/UA | KwaZulu-Natal | THOLOKUHLE HIGH SCHOOL | 500282791 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-04-25 |  |  | 3943222 | 17963566 | 21906788 | Education Infrastructure Grant | Upgrading and Additions
|  | 187499 | DB/500111555/RRR | KwaZulu-Natal | BONOKUHLE HIGH SCHOOL | 500111555 | Inkosi Langalibalele | Design | Active - Not Contracted | 2018-01-01 |  | 2026-03-22 |  |  | 2139295 | 9745675 | 11884970 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187500 | DB/500123617/RRR | KwaZulu-Natal | DUCK PONDS SECONDARY SCHOOL | 500123617 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187501 | DB/500144781/RRR | KwaZulu-Natal | FILIDI SECONDARY SCHOOL | 500144781 | Abaqulusi | Design | Active - Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 3659401 | 16670606 | 20330007 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187502 | DB/500157953/RRR | KwaZulu-Natal | IMBALENHLE PRIMARY SCHOOL | 500157953 | Newcastle | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 1905574 | 8680948 | 10586522 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187503 | DB/500161357/RRR | KwaZulu-Natal | IMPUNGA SECONDARY SCHOOL | 500161357 | Ubuhlebezwe | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 1030180 | 4693040 | 5723220 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187504 | DB/500163540/RRR | KwaZulu-Natal | INGQUNGQULU HIGH SCHOOL | 500163540 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 2568819 | 11702397 | 14271216 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187506 | DB/500174233/RRR | KwaZulu-Natal | KHETHIMFUNDO SECONDARY SCHOOL | 500174233 | Ndwedwe | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2019-09-12 | 2024-03-01 | 2024-05-05 | 2027-06-20 | 358429 | 1632843 | 1991272 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187507 | DB/500337847/RRR | KwaZulu-Natal | LESHMAN SECONDARY SCHOOL | 500337847 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 318819 | 1452398 | 1771217 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187508 | DB/500198801/RRR | KwaZulu-Natal | MAQHINGENDODA HIGH SCHOOL | 500198801 | Ulundi | Design | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 1401688 | 6385468 | 7787156 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187509 | DB/500212195/RRR | KwaZulu-Natal | MKHONTO HIGH SCHOOL | 500212195 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 1945261 | 8861745 | 10807006 | Education Infrastructure Grant | Upgrading and Additions
|  | 187510 | DB/500442187/RRR | KwaZulu-Natal | MVUZOMUHLE HIGH SCHOOL | 500442187 | Umhlabuyalingana | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 3297956 | 15024023 | 18321979 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187511 | DB/500243053/RRR | KwaZulu-Natal | OGWINI COMPREHENSIVE TECHNICAL SCHOOL | 500243053 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Equitable Share | Maintenance and Repairs
|  | 187512 | DB/500295519/RRR | KwaZulu-Natal | QINISANI HIGH SCHOOL | 500295519 | Nkandla | Construction 51% - 75% | Active - Contracted | 2018-01-01 | 2020-05-01 | 2025-08-31 | 2022-07-14 | 2025-08-31 | 1257335 | 5727860 | 6985195 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187513 | DB/500286343/RRR | KwaZulu-Natal | UKHAHLAMBA HIGH SCHOOL | 500286343 | Okhahlamba | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 4334165 | 19744531 | 24078696 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187514 | DB/500117771/NS | KwaZulu-Natal | COLLINGWOOD PRIMARY SCHOOL | 500117771 | Nkandla | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2025-06-20 | 2026-06-20 | 2028-06-20 | 15711122 | 71572891 | 87284013 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187515 | DB/UML.NEW16/001/NS | KwaZulu-Natal | MARITIME SCHOOL OF EXCELLENCE : ACTON ROAD | Uml,New16/001 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 10719527 | 48833399 | 59552926 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187516 | C/500126503/ECD | KwaZulu-Natal | EBUSINGATHA PRIMARY SCHOOL | 500126503 | Okhahlamba | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187517 | C/500131609/ECD | KwaZulu-Natal | EMASWAZINI PRIMARY SCHOOL | 500131609 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187518 | C/500132423/ECD | KwaZulu-Natal | EMFENI PRIMARY SCHOOL | 500132423 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187519 | C/500340067/ECD | KwaZulu-Natal | ENHLANGWINI INTERMEDIATE SCHOOL | 500340067 | Ubuhlebezwe | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187520 | C/500137159/ECD | KwaZulu-Natal | ENHLOKWENI PRIMARY SCHOOL | 500137159 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187521 | C/500138121/ECD | KwaZulu-Natal | ENQOLENI PRIMARY SCHOOL | 500138121 | uMlalazi | Design | Active - Not Contracted | 2019-05-10 |  | 2026-04-01 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187522 | C/500260591/ECD | KwaZulu-Natal | UMBULWANE PRIMARY SCHOOL | 500260591 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187523 | C/500140378/ECD | KwaZulu-Natal | ESIGODINI PRIMARY SCHOOL | 500140378 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187524 | C/500142117/ECD | KwaZulu-Natal | ETHAFENI PRIMARY SCHOOL | 500142117 | uMlalazi | Design | Active - Not Contracted | 2019-05-10 |  | 2025-04-01 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187525 | C/500341510/ECD | KwaZulu-Natal | EYETHU PRIMARY SCHOOL | 500341510 | Umvoti | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187526 | C/500144744/ECD | KwaZulu-Natal | FEZOKUHLE PRIMARY SCHOOL | 500144744 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187527 | C/500145225/ECD | KwaZulu-Natal | FORBESDALE PRIMARY SCHOOL | 500145225 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187528 | C/500146409/ECD | KwaZulu-Natal | GABANGEMFUNDO PRIMARY SCHOOL | 500146409 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187529 | C/500152625/ECD | KwaZulu-Natal | GULUBE PRIMARY SCHOOL | 500152625 | Mkhambathini | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187530 | C/500236763/ECD | KwaZulu-Natal | HEA O`CONNOR COMBINED SCHOOL | 500236763 | Mpofana | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187531 | C/500263144/ECD | KwaZulu-Natal | SIBONGILE PRIMARY SCHOOL | 500263144 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187532 | C/500264217/ECD | KwaZulu-Natal | SIFISESIHLE PRIMARY SCHOOL | 500264217 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187533 | C/500269323/ECD | KwaZulu-Natal | SIWELILE PRIMARY SCHOOL | 500269323 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-30 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187535 | DB/500283975/ECD | KwaZulu-Natal | TINLEY MANOR PRIMARY SCHOOL | 500283975 | KwaDukuza | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-20 |  |  | 254197 | 1158010 | 1412207 | Education Infrastructure Grant | Upgrading and Additions
|  | 187536 | DB/500105857/ECD | KwaZulu-Natal | BAQOQE PRIMARY SCHOOL | 500105857 | Mfolozi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187537 | DB/500106930/ECD | KwaZulu-Natal | BHEJANE PRIMARY SCHOOL | 500106930 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187538 | C/500414955/ECD | KwaZulu-Natal | SIYAPHAMBILI PRIMARY SCHOOL | 500414955 | Abaqulusi | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187539 | C/500273319/ECD | KwaZulu-Natal | SOMTSEWU PRIMARY SCHOOL | 500273319 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187540 | C/500273985/ECD | KwaZulu-Natal | SOSINDA PRIMARY SCHOOL | 500273985 | Dannhauser | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187541 | DB/500110149/ECD | KwaZulu-Natal | BINGOMA PRIMARY SCHOOL | 500110149 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-25 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187542 | DB/500111592/ECD | KwaZulu-Natal | BONOMUNYE I | 500111592 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-25 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187543 | C/500279202/ECD | KwaZulu-Natal | SWEETWATERS PRIMARY SCHOOL | 500279202 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187544 | DB/500122285/ECD | KwaZulu-Natal | DLOZEYANE PRIMARY SCHOOL | 500122285 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-20 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187545 | C/500279387/ECD | KwaZulu-Natal | TABLE MOUNTAIN PRIMARY SCHOOL | 500279387 | Mkhambathini | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187546 | DB/500197173/ECD | KwaZulu-Natal | EMANKWATHINI PRIMARY SCHOOL | 500197173 | Mfolozi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187547 | C/500281977/ECD | KwaZulu-Natal | THIYASIZWE PRIMARY SCHOOL | 500281977 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187548 | DB/500135309/ECD | KwaZulu-Natal | EMVUTSHINI PRIMARY SCHOOL | 500135309 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187549 | C/500334702/ECD | KwaZulu-Natal | THOLULWAZI PRIMARY SCHOOL | 500334702 | uPhongolo | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187550 | C/500337588/ECD | KwaZulu-Natal | THUTHUKANI PRIMARY SCHOOL | 500337588 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187551 | C/500130980/ECD | KwaZulu-Natal | EMALAHLENI COMBINED SCHOOL (UTRECHT) | 500130980 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187552 | C/500165538/ECD | KwaZulu-Natal | INSEBENZWENHLE PRIMARY SCHOOL | 500165538 | Okhahlamba | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187553 | C/500166389/ECD | KwaZulu-Natal | INTUMBANE PRIMARY SCHOOL | 500166389 | Okhahlamba | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187554 | C/500166796/ECD | KwaZulu-Natal | INYANINGA PRIMARY SCHOOL | 500166796 | eThekwini | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187555 | C/500167536/ECD | KwaZulu-Natal | ISIBONGO PRIMARY SCHOOL | 500167536 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187556 | DB/500141266/ECD | KwaZulu-Natal | ESIQHOMANENI PRIMARY SCHOOL | 500141266 | Mthonjaneni | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187557 | C/500170052/ECD | KwaZulu-Natal | IWAHLANGA PRIMARY SCHOOL | 500170052 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187558 | C/500170200/ECD | KwaZulu-Natal | IXOPO PRIMARY SCHOOL | 500170200 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2019-05-10 | 2020-03-20 | 2024-04-15 | 2024-04-15 | 2024-08-15 | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187559 | DB/500142154/ECD | KwaZulu-Natal | ETHAKASANI PRIMARY SCHOOL | 500142154 | uMhlathuze | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187560 | DB/500320050/ECD | KwaZulu-Natal | EZISHABENI PRIMARY SCHOOL | 500320050 | uMhlathuze | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187561 | C/500339697/ECD | KwaZulu-Natal | IZIMBUTHU INTERMEDIATE SCHOOL | 500339697 | Emadlangeni | Final Completion | Active - Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187562 | C/500171421/ECD | KwaZulu-Natal | JOBSTOWN PRIMARY SCHOOL | 500171421 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187563 | GDE00074 | Gauteng | EZIBELENI SCHOOL FOR PHYSICALLY DISABLED CHILDREN | 700341552 | City of Ekurhuleni | Feasibility | Approved | 2016-04-01 |  | 2026-01-09 |  |  | 2200000 | 7980000 | 10180000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187564 | C/500171680/ECD | KwaZulu-Natal | JONONOSKOP PRIMARY SCHOOL | 500171680 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187565 | C/500171939/ECD | KwaZulu-Natal | JULUKANDODA PRIMARY SCHOOL | 500171939 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187566 | C/500185629/ECD | KwaZulu-Natal | LANGSYDE PRIMARY SCHOOL | 500185629 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187567 | C/500334443/ECD | KwaZulu-Natal | MAKHOYANE PRIMARY SCHOOL | 500334443 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187568 | C/500341880/ECD | KwaZulu-Natal | MT PRIMARY SCHOOLLEASANT PRIMARY SCHOOL | 500341880 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187569 | C/500203537/ECD | KwaZulu-Natal | MBALENHLE PRIMARY SCHOOL | 500203537 | Newcastle | Final Completion | Active - Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187570 | C/500203833/ECD | KwaZulu-Natal | MBANJWA PRIMARY SCHOOL | 500203833 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187571 | C/500207718/ECD | KwaZulu-Natal | MENZIWA PRIMARY SCHOOL | 500207718 | Richmond | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187572 | C/500211048/ECD | KwaZulu-Natal | MIDDLEFIELD PRIMARY SCHOOL | 500211048 | Mpofana | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187573 | C/500217893/ECD | KwaZulu-Natal | MQHATHI PRIMARY SCHOOL | 500217893 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187574 | C/500340141/ECD | KwaZulu-Natal | MTHANIYA COMBINED SCHOOL | 500340141 | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187575 | C/500222814/ECD | KwaZulu-Natal | NADI PRIMARY SCHOOL | 500222814 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187579 | DB/500147667/ECD | KwaZulu-Natal | GCINUKUTHULA PRIMARY SCHOOL | 500147667 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187580 | DB/500151478/ECD | KwaZulu-Natal | GQUMENI PRIMARY SCHOOL | 500151478 | Dr Nkosazana Dlamini Zuma | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187581 | DB/500340881/ECD | KwaZulu-Natal | GUBHETHUKA PRIMARY SCHOOL | 500340881 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187582 | DB/500165612/ECD | KwaZulu-Natal | INSELENYANA PRIMARY SCHOOL | 500165612 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187583 | DB/500167277/ECD | KwaZulu-Natal | ISANGOYANA PRIMARY SCHOOL | 500167277 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187584 | DB/500179598/ECD | KwaZulu-Natal | KWAGUGU PRIMARY SCHOOL | 500179598 | Umzumbe | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 641700 | 2923300 | 3565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187585 | DB/500401672/ECD | KwaZulu-Natal | KWAZIKWAKHE PRIMARY SCHOOL | 500401672 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187586 | DB/500189588/ECD | KwaZulu-Natal | M L SULTAN KRANTZKLOOF PRIMARY SCHOOL | 500189588 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187587 | DB/500189995/ECD | KwaZulu-Natal | MABHENSA PRIMARY SCHOOL | 500189995 | Mthonjaneni | Design | Active - Contracted | 2018-01-01 |  | 2024-04-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187588 | DB/500195582/ECD | KwaZulu-Natal | MAMBA PRIMARY SCHOOL | 500195582 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187589 | DB/500197506/ECD | KwaZulu-Natal | MANTINGWANE PRIMARY SCHOOL | 500197506 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2026-03-31 |  |  | 798444 | 3637354 | 4435798 | Education Infrastructure Grant | Upgrading and Additions
|  | 187590 | DB/500198727/ECD | KwaZulu-Natal | MAQHAMA PRIMARY SCHOOL | 500198727 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187591 | DB/500198838/ECD | KwaZulu-Natal | MAQHUBANDABA PRIMARY SCHOOL | 500198838 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187593 | DB/500202797/ECD | KwaZulu-Natal | MAWANDA PRIMARY SCHOOL | 500202797 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187594 | DB/500401043/ECD | KwaZulu-Natal | MBONOMUHLE PRIMARY SCHOOL | 500401043 | KwaDukuza | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187595 | DB/500206275/ECD | KwaZulu-Natal | MDLELANG PRIMARY SCHOOL | 500206275 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187596 | DB/500217486/ECD | KwaZulu-Natal | MPUMAZE PRIMARY SCHOOL | 500217486 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187597 | DB/500221667/ECD | KwaZulu-Natal | MVUZANE PRIMARY SCHOOL | 500221667 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187598 | DB/500315314/ECD | KwaZulu-Natal | MVUZEMVUZE PRIMARY SCHOOL | 500315314 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187599 | DB/500221186/ECD | KwaZulu-Natal | MZUVUKILE PRIMARY SCHOOL | 500221186 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Equitable Share | Upgrading and Additions
|  | 187600 | DB/500225108/ECD | KwaZulu-Natal | NDINDINDI PRIMARY SCHOOL | 500225108 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187601 | DB/500225700/ECD | KwaZulu-Natal | NDONGANDE PRIMARY SCHOOL | 500225700 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187602 | DB/500229252/ECD | KwaZulu-Natal | NGWEGWENI PRIMARY SCHOOL | 500229252 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187603 | DB/500231768/ECD | KwaZulu-Natal | NKASENI INTERMEDIATE SCHOOL | 500231768 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 565740 | 2577260 | 3143000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187604 | DB/500232249/ECD | KwaZulu-Natal | NKONINGA PRIMARY SCHOOL | 500232249 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187605 | DB/500237910/ECD | KwaZulu-Natal | NSEZI PRIMARY SCHOOL | 500237910 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187606 | DB/500238243/ECD | KwaZulu-Natal | NSIWA PRIMARY SCHOOL | 500238243 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187607 | DB/500238502/ECD | KwaZulu-Natal | NSUNDUKAZI PRIMARY SCHOOL | 500238502 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187608 | DB/500239575/ECD | KwaZulu-Natal | NTATSHANA PRIMARY SCHOOL | 500239575 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187609 | DB/500240944/ECD | KwaZulu-Natal | NTUMENI PRIMARY SCHOOL | 500240944 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187610 | DB/500242054/ECD | KwaZulu-Natal | NZALABANTU PRIMARY SCHOOL | 500242054 | Mfolozi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187611 | DB/500243238/ECD | KwaZulu-Natal | OHLELO PRIMARY SCHOOL | 500243238 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187612 | DB/500247604/ECD | KwaZulu-Natal | PHANGANDAWO PRIMARY SCHOOL | 500247604 | eThekwini | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187613 | DB/500250786/ECD | KwaZulu-Natal | PLANT MEMORIAL PRIMARY SCHOOL | 500250786 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187614 | DB/500341177/ECD | KwaZulu-Natal | PRINCE VELESHOWE PRIMARY SCHOOL | 500341177 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187615 | DB/500252229/ECD | KwaZulu-Natal | QALUKUVUKA PRIMARY SCHOOL | 500252229 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187616 | DB/500253228/ECD | KwaZulu-Natal | QHUDENI PRIMARY SCHOOL | 500253228 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187617 | DB/500257890/ECD | KwaZulu-Natal | SAMUNGU PRIMARY SCHOOL | 500257890 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187618 | DB/500266289/ECD | KwaZulu-Natal | SINAYE PRIMARY SCHOOL | 500266289 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187619 | DB/500269730/ECD | KwaZulu-Natal | SIYAKHANYISA PRIMARY SCHOOL | 500269730 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187620 | DB/500274355/ECD | KwaZulu-Natal | SOYA PRIMARY SCHOOL | 500274355 | Mfolozi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-29 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187621 | DB/500280312/ECD | KwaZulu-Natal | THANDINKOSI PRIMARY SCHOOL | 500280312 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187627 | DB/500304658/LSEN | KwaZulu-Natal | INKANYISO SPECIAL SCHOOL | 500304658 | Abaqulusi | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-11-30 |  |  | 4990297 | 22733573 | 27723870 | Education Infrastructure Grant | Upgrading and Additions
|  | 187628 | DB/AGRICULTURE/NS | KwaZulu-Natal | AGRICULTURAL SCHOOL OF EXCELLENCE (DABULAMANZI) | New School | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2026-03-30 |  |  | 7000000 | 20000000 | 27000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187629 | DB/NEW/NS | KwaZulu-Natal | INKOSI UMKHUPHUKILE HIGH SCHOOL | NEW SCHOOL | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 15300000 | 69700000 | 85000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187632 | DB/500444296/NS | KwaZulu-Natal | SIDINGULWAZI PRIMARY SCHOOL | 500444296 | Nkandla | Feasibility | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 13500000 | 61500000 | 75000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187633 | C/500153476/ECD | KwaZulu-Natal | HAMBROOK PRIMARY SCHOOL | 500153476 | Okhahlamba | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187634 | C/500154697/ECD | KwaZulu-Natal | HENLEY PRIMARY SCHOOL | 500154697 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187635 | C/500156769/ECD | KwaZulu-Natal | HLELINGOMUSO PRIMARY SCHOOL | 500156769 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187636 | C/500156806/ECD | KwaZulu-Natal | HLELOLUSHA PRIMARY SCHOOL | 500156806 | Impendle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187637 | C/500157213/ECD | KwaZulu-Natal | HLOKOMANI PRIMARY SCHOOL | 500157213 | Dannhauser | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187638 | C/500158027/ECD | KwaZulu-Natal | HLWEMINI PRIMARY SCHOOL | 500158027 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187639 | C/500158545/ECD | KwaZulu-Natal | HOPEWELL PRIMARY SCHOOL | 500158545 | Richmond | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187640 | C/500160691/ECD | KwaZulu-Natal | IMBUBU PRIMARY SCHOOL | 500160691 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187641 | C/500165094/ECD | KwaZulu-Natal | INKULULEKO PRIMARY SCHOOL | 500165094 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187642 | C/500498094/ECD | KwaZulu-Natal | SINGAYO-IMFUNDO PRIMARY SCHOOL | 500498094 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187643 | C/500224294/ECD | KwaZulu-Natal | NDABENHLE PRIMARY SCHOOL | 500224294 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187644 | C/500224775/ECD | KwaZulu-Natal | NDELESHANE PRIMARY SCHOOL | 500224775 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187645 | C/500230695/ECD | KwaZulu-Natal | NICHOLS PRIMARY SCHOOL | 500230695 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187646 | DB/500198505/UA | KwaZulu-Natal | MAPHOVELA HIGH SCHOOL | 500198505 | Ulundi | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 4450500 | 20274500 | 24725000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187647 | DB/500201539/UA | KwaZulu-Natal | MATHAMO PRIMARY SCHOOL | 500201539 | Inkosi Langalibalele | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 4657500 | 21217500 | 25875000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187648 | DB/500225367/UA | KwaZulu-Natal | NDLOLOTHI SECONDARY SCHOOL | 500225367 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 5485500 | 24989500 | 30475000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187649 | DB/500303992/UA | KwaZulu-Natal | NJEZA HIGH SCHOOL | 500303992 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 4108950 | 18718550 | 22827500 | Education Infrastructure Grant | Upgrading and Additions
|  | 187650 | DB/500444333/NS | KwaZulu-Natal | SIBONGINTUTHUKO PRIMARY SCHOOL | 500444333 | Alfred Duma | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 4026150 | 18341350 | 22367500 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187651 | DB/500414511/UA | KwaZulu-Natal | VS ZULU PRIMARY SCHOOL | 500414511 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-26 |  |  | 6106500 | 27818500 | 33925000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187652 | GDE00396 | Gauteng | Unicaskool | 700211177 | City of Tshwane | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 17600000 | 92400000 | 110000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187654 | C/500222962/ECD | KwaZulu-Natal | NAMAKAZI PRIMARY SCHOOL | 500222962 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187655 | C/500233840/ECD | KwaZulu-Natal | NOGASELA PRIMARY SCHOOL | 500233840 | Impendle | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187656 | C/500236837/ECD | KwaZulu-Natal | NOTTINGHAM RD PRIMARY SCHOOL | 500236837 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187657 | C/500240019/ECD | KwaZulu-Natal | NTINTISA PRIMARY SCHOOL | 500240019 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187658 | C/500242757/ECD | KwaZulu-Natal | ODLAMENI PRIMARY SCHOOL | 500242757 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187659 | C/500243349/ECD | KwaZulu-Natal | OKHALWENI PRIMARY SCHOOL (DUNDEE) | 500243349 | Dannhauser | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187660 | C/500246864/ECD | KwaZulu-Natal | PELLA PRIMARY SCHOOL | 500246864 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187661 | C/500252414/ECD | KwaZulu-Natal | QAPHELANI PRIMARY SCHOOL | 500252414 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187662 | C/500249047/RRR | KwaZulu-Natal | BROOKDALE SECONDARY SCHOOL | 500249047 | eThekwini | Final Completion | Active - Contracted | 2019-05-10 |  | 2022-04-15 |  |  | 700000 | 8538000 | 9238000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187664 | C/500100048/ECD | KwaZulu-Natal | A I KAJEE PRIMARY SCHOOL | 500100048 | Mpofana | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187665 | C/500101047/ECD | KwaZulu-Natal | ALSTON PRIMARY SCHOOL | 500101047 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187666 | DB/500219743/WS | KwaZulu-Natal | MTHWANA PRIMARY SCHOOL | 500219743 | Mfolozi | Construction 76% - 99% | Active - Contracted | 2019-05-01 | 2020-01-01 | 2023-03-15 | 2023-03-15 | 2027-09-15 | 545473 | 3523527 | 4069000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187667 | DB/500233248/WS | KwaZulu-Natal | NKWE PRIMARY SCHOOL | 500233248 | Nqutu | Construction 76% - 99% | Active - Not Contracted | 2019-05-15 | 2021-01-01 | 2023-03-15 | 2023-07-14 | 2025-08-31 | 417367 | 1901338 | 2318705 | Education Infrastructure Grant | Upgrading and Additions
|  | 187668 | C/500160654/ECD | KwaZulu-Natal | IMBOYI PRIMARY SCHOOL | 500160654 | Mkhambathini | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187669 | DB/500264402/SDS | KwaZulu-Natal | SIGANANDA PRIMARY SCHOOL | 500264402 | Nkandla | Design | Active - Not Contracted | 2019-03-05 |  | 2024-04-27 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187670 | DB/500343693/SDS | KwaZulu-Natal | SIYATHUTHUKA PRIMARY SCHOOL | 500343693 | Mtubatuba | Design | Active - Not Contracted | 2019-10-05 |  | 2024-04-30 |  |  | 8694000 | 39606000 | 48300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187672 | DoE/Boh/MAIN/160 | Mpumalanga | Sediba sa Thuto Primary School | 800035459 | Bushbuckridge | Project Initiation | Proposed | 2021-04-01 |  | 2023-03-31 |  |  | 22545 | 247999 | 270544 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187673 | C/500259999/ECD | KwaZulu-Natal | SEBENZANI PRIMARY SCHOOL | 500259999 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187675 | MDOE/MAIN/05/21-22 | Mpumalanga | Makoko Primary School | 800011932 | Mbombela | Project Initiation | Proposed | 2021-04-01 |  | 2024-09-30 |  |  | 343033 | 2450236 | 2793269 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187676 | MDOE/MAIN/06/21-22 | Mpumalanga | Jacob Mdluli Secondary School | 800006957 | Mbombela | Project Initiation | Proposed | 2021-04-30 |  | 2024-08-30 |  |  | 334679 | 2390565 | 2725244 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187677 | C/500286713/ECD | KwaZulu-Natal | UKWENZAKWETHU PRIMARY SCHOOL | 500286713 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187679 | C/500290598/ECD | KwaZulu-Natal | UTRECHT PRIMARY SCHOOL | 500290598 | Emadlangeni | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187680 | MDOE/MAIN/055/22 | Mpumalanga | SH Nyalungu Primary School | 800035089 | Bushbuckridge | Project Initiation | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 14502 | 159523 | 174025 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187683 | C/500291856/ECD | KwaZulu-Natal | VEYISI PRIMARY SCHOOL | 500291856 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187686 | C/500292892/ECD | KwaZulu-Natal | VRYSTAAT JUNIOR PRIMARY SCHOOL | 500292892 | uMngeni | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187690 | C/500292929/ECD | KwaZulu-Natal | VUKA PRIMARY SCHOOL | 500292929 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187691 | DoE/NKD/MAIN/089 | Mpumalanga | Silindokuhle Special School | 800021121 | Nkomazi | Project Initiation | Proposed | 2020-08-02 |  | 2024-03-31 |  |  | 361799 | 2584281 | 2946080 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187693 | C/500302068/ECD | KwaZulu-Natal | ZWELIYAZUZA PRIMARY SCHOOL | 500302068 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 2709180 | 12341820 | 15051000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187698 | C/500102638/ECD | KwaZulu-Natal | AMATHULI PRIMARY SCHOOL | 500102638 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1188000 | 5412000 | 6600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187700 | C/500102009/ECD | KwaZulu-Natal | AMANDUS HILL PRIMARY SCHOOL | 500102009 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187703 | C/500169904/ECD | KwaZulu-Natal | IVANHOE PRIMARY SCHOOL | 500169904 | Impendle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187706 | C/500176231/ECD | KwaZulu-Natal | KIRKINTULLOCH PRIMARY SCHOOL | 500176231 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 1782000 | 8118000 | 9900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187709 | MDOE/MAIN/100/21-22 | Mpumalanga | Nkomazi East | n/a | Nkomazi | Project Initiation | Proposed | 2020-04-01 |  | 2024-03-31 |  |  | 322548 | 2866917 | 3189465 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187711 | MDOE/B/ALL/Education Infrastructure Grant (EIG)/UPG/17-18/387 | Mpumalanga | Circuit Back Up Generator | Circuit/District Maintenance | Emakhazeni | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 5000000 | 5000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187712 | C/500189292/ECD | KwaZulu-Natal | LUZINDELA PRIMARY SCHOOL | 500189292 | uMhlathuze | Tender | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187713 | MDOE/MAIN/10/21-22 | Mpumalanga | Chief Charles Secondary School | 800002063 | Mbombela | Project Initiation | Proposed | 2021-03-31 |  | 2025-12-01 |  |  | 340054 | 2428963 | 2769017 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187714 | C/500203981/ECD | KwaZulu-Natal | MBAVA PRIMARY SCHOOL | 500203981 | uMshwathi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187717 | C/500340437/ECD | KwaZulu-Natal | NHLAWE PRIMARY SCHOOL | 500340437 | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187719 | C/500444444/ECD | KwaZulu-Natal | NHLOLAMVULA PRIMARY SCHOOL | 500444444 | Alfred Duma | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187720 | C/500241573/ECD | KwaZulu-Natal | NYANDA PRIMARY SCHOOL | 500241573 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187721 | C/500249824/ECD | KwaZulu-Natal | PHUMELELANI PRIMARY SCHOOL | 500249824 | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187722 | C/500186221/ECD | KwaZulu-Natal | LETHUKUTHULA PRIMARY SCHOOL | 500186221 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187723 | MDOE/MAIN/092/22 | Mpumalanga | Lumukisa Primary School | 800034969 | Bushbuckridge | Project Initiation | Proposed | 2020-04-01 |  | 2024-03-31 |  |  | 43246 | 544511 | 587757 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187725 | MDOE/MAIN/08/21-22 | Mpumalanga | Mathethe Primary School | 800013219 | Dr JS Moroka | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-31 |  |  | 183576 | 1311258 | 1494834 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187726 | MDOE/MAIN/09/21-22 | Mpumalanga | Seruane Secondary School | 800020362 | Dr JS Moroka | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-31 |  |  | 35290 | 1542304 | 1577594 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187730 | C/500247826/ECD | KwaZulu-Natal | PHASIWE PRIMARY SCHOOL | 500247826 | Inkosi Langalibalele | Design | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187731 | C/500253154/ECD | KwaZulu-Natal | QHUBIMFUNDO PRIMARY SCHOOL | 500253154 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 2376000 | 10824000 | 13200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187733 | C/500259000/ECD | KwaZulu-Natal | SAVELA PRIMARY SCHOOL | 500259000 | Ubuhlebezwe | Tender | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 486000 | 2214000 | 2700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187735 | C/500298812/ECD | KwaZulu-Natal | ZAMELISIZWE PRIMARY SCHOOL | 500298812 | The Msunduzi | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187736 | MDOE/UPG/014/20-21 | Mpumalanga | Mbongeni Primary School | 800034132 | Mbombela | Construction 76% - 99% | Active - Contracted | 2020-03-31 | 2020-04-29 | 2024-04-11 | 2021-03-31 | 2020-08-09 | 503412 | 6123750 | 6627162 | Education Infrastructure Grant | Upgrading and Additions
|  | 187738 | MDOE/MAIN/11/21-22 | Mpumalanga | Buhlebuyeta Primary School | 800001727 | Mbombela | Project Initiation | Proposed | 2021-05-14 |  | 2025-05-15 |  |  | 111419 | 795855 | 907274 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187739 | DoE/EHL/MAIN/116 | Mpumalanga | Malekutu primary school | 800012070 | Mbombela | Project Initiation | Proposed | 2020-05-14 |  | 2024-03-31 |  |  | 32146 | 321456 | 353602 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187741 | MDOE/MAIN/12/21-22 | Mpumalanga | Mzimba Secondary School | 800035167 | Bushbuckridge | Project Initiation | Proposed | 2021-03-02 |  | 2024-03-31 |  |  | 43565 | 1771175 | 1814740 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187743 | MDOE/MAIN/13/21-22 | Mpumalanga | Masilela Secondary School | 800034944 | Bushbuckridge | Project Initiation | Proposed | 2021-04-30 |  | 2024-04-30 |  |  | 339341 | 2423865 | 2763206 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187747 | DB/500288267/SDS | KwaZulu-Natal | UMLAZI COMTECH SECONDARY SCHOOL | 500288267 | eThekwini | Final Completion | Approved | 2019-03-05 | 2019-08-12 | 2023-10-30 | 2023-05-05 | 2023-01-10 | 1695942 | 7725959 | 9421901 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187756 | DoE/Boh/MAIN/190 | Mpumalanga | Thulamahashe Circuit | 1 | Bushbuckridge | Project Initiation | Proposed | 2022-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187757 | DoE/Boh/MAIN/117 | Mpumalanga | Mapulaneng Teacher Development Centre | OFFICES | Bushbuckridge | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 214457 | 2144569 | 2359026 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187758 | DoE/Boh/MAIN/113 | Mpumalanga | Powerline Primary School | 800034789 | Bushbuckridge | Project Initiation | Proposed | 2022-05-14 |  | 2024-03-31 |  |  | 21211 | 209993 | 231204 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187761 | I/500147223/SDS | KwaZulu-Natal | GAWOZI SECONDARY SCHOOL | 500147223 | uMlalazi | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187762 | I/500147963/SDS | KwaZulu-Natal | GEGEDE PRIMARY SCHOOL | 500147963 | uMhlathuze | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187763 | I/500151367/SDS | KwaZulu-Natal | GQOKINSIMBI HIGH SCHOOL | 500151367 | uMlalazi | Design | Active - Not Contracted | 2016-04-01 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187764 | C/500102305/NS | KwaZulu-Natal | AMAOTI NO3 SECONDARY SCHOOL | 500102305 | eThekwini | Feasibility | Active - Contracted | 2019-05-10 |  | 2026-04-15 |  |  | 3200000 | 9500000 | 12700000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187765 | I/500153143/SDS | KwaZulu-Natal | HALADU PRIMARY SCHOOL | 500153143 | Nqutu | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187766 | GDE00138 | Gauteng | L.G. HOLELE SECONDARY SCHOOL | 700910794 | City of Tshwane | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 0 | 22284000 | 22284000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187767 | C/500285899/ECD | KwaZulu-Natal | UBUHLEBESIZWE JUNIOR SECONDARY SCHOOL | 500285899 | Ndwedwe | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187768 | C/500343730/ECD | KwaZulu-Natal | VULINDLELA PRIMARY SCHOOL | 500343730 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2025-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187769 | C/500293854/ECD | KwaZulu-Natal | VUMELANI PRIMARY SCHOOL | 500293854 | Newcastle | Tender | Active - Not Contracted | 2019-05-10 |  | 2027-04-15 |  |  | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187771 | DB/500173049/SDS | KwaZulu-Natal | KHAMANGWA S | 500173049 | eThekwini | Design | Active - Not Contracted | 2020-05-29 |  | 2023-02-26 |  |  | 2918892 | 13297177 | 16216069 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187775 | DB/500179524/SDS | KwaZulu-Natal | KWAGIBA HIGH SCHOOL | 500179524 | Big Five Hlabisa | Project Initiation | Active - Not Contracted | 2019-05-01 |  | 2025-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187777 | DB/500304843/SDS | KwaZulu-Natal | MPHATHESITHA HIGH SCHOOL | 500304843 | Nkandla | Design | Active - Not Contracted | 2020-05-28 |  | 2024-03-10 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187778 | DB/500170718/SDS | KwaZulu-Natal | JABULANI PRIMARY SCHOOL | 500170718 | Nkandla | Practical Completion (100%) | Active - Contracted | 2016-06-06 | 2018-04-05 | 2024-06-20 | 2023-05-05 | 2024-06-20 | 422144 | 1923099 | 2345243 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187779 | DB/500180375/SDS | KwaZulu-Natal | KWAMAKHONYENI PRIMARY | 500180375 | Jozini | Design | Active - Not Contracted | 2019-04-01 |  | 2024-02-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187780 | DB/500343138/SDS | KwaZulu-Natal | MQUBULA PRIMARY SCHOOL | 500343138 | Nongoma | Design | Active - Not Contracted | 2020-05-01 |  | 2024-03-17 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187781 | C/500167499/RRR | KwaZulu-Natal | ISIBONELO HIGH SCHOOL | 500167499 | eThekwini | On Hold | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187783 | C/500306212/RRR | KwaZulu-Natal | MATHINTA SECONDARY SCHOOL | 500306212 | eThekwini | On Hold | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 1602000 | 7298000 | 8900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187784 | DB/500218337/SDS | KwaZulu-Natal | MSHANELOWESIZWE HIGH SCHOOL | 500218337 | Nongoma | Design | Active - Not Contracted | 2020-04-03 |  | 2024-02-25 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187785 | DB/500218596/SDS | KwaZulu-Natal | MSIMBU SECONDARY SCHOOL | 500218596 | Nqutu | Design | Active - Not Contracted | 2020-04-30 |  | 2024-02-25 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187786 | DB/500181374/SDS | KwaZulu-Natal | KWAMNYANDU PRIMARY SCHOOL | 500181374 | The Msunduzi | Design | Active - Not Contracted | 2019-02-01 |  | 2024-03-31 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187788 | DB/500221482/RRR | KwaZulu-Natal | MVULASI PRIMARY SCHOOL | 500221482 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 1542357 | 7026293 | 8568650 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187789 | DB/500219706/SDS | KwaZulu-Natal | MTHWADLANA PRIMARY SCHOOL | 500219706 | Nongoma | Design | Active - Not Contracted | 2020-04-30 |  | 2024-02-25 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187791 | DB/500190735/SDS | KwaZulu-Natal | MUZI THUSI PRIMARY SCHOOL | 500190735 | The Msunduzi | Design | Active - Not Contracted | 2020-04-09 |  | 2024-02-24 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187792 | DB/500181929/SDS | KwaZulu-Natal | KWAMUSI PRIMARY SCHOOL | 500181929 | Nongoma | Design | Active - Not Contracted | 2019-03-01 |  | 2024-02-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187793 | DB/500265993/SDS | KwaZulu-Natal | SIMANGANYAWO PRIMARY SCHOOL | 500265993 | Dannhauser | Design | Active - Not Contracted | 2020-10-05 |  | 2024-01-05 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187794 | C/500208458/RRR | KwaZulu-Natal | MFEKAYI PRIMARY SCHOOL | 500208458 | Mtubatuba | On Hold | Active - Not Contracted | 2019-05-10 |  | 2022-04-15 |  |  | 1800000 | 3548000 | 5348000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187795 | DB/SAFE/500423650/WS | KwaZulu-Natal | BAMBANANI JUNIOR SECONDARY SCHOOL SCHOOL | 500423650 | Ubuhlebezwe | Practical Completion (100%) | Active - Not Contracted | 2019-05-15 | 2020-08-01 | 2023-03-15 | 2023-05-15 | 2023-05-15 | 756000 | 3444000 | 4200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187796 | DB/500182780/SDS | KwaZulu-Natal | KWANYEZI PRIMARY SCHOOL | 500182780 | Endumeni | Design | Active - Not Contracted | 2019-02-01 |  | 2024-02-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187797 | DB/500285529/RRR | KwaZulu-Natal | TWASANA PRIMARY SCHOOL | 500285529 | Ulundi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-28 |  |  | 1362909 | 6208806 | 7571715 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187798 | C/500169645/ECD | KwaZulu-Natal | ITHONGASI PRIMARY SCHOOL | 500169645 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2019-05-10 | 2021-04-15 | 2023-04-15 | 2021-04-30 | 2024-06-15 | 500000 | 2800000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187799 | I/500156584/SDS | KwaZulu-Natal | HLATHINGWE PRIMARY SCHOOL | 500156584 | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187800 | I/500121175/RRR | KwaZulu-Natal | DIKANA HIGH SCHOOL | 500121175 | Ulundi | Design | Active - Not Contracted | 2019-05-15 |  | 2026-03-31 |  |  | 2700000 | 12300000 | 15000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187801 | DB/500496540/SDS | KwaZulu-Natal | SIZWE SITHOLE PRIMARY | 500496540 | Endumeni | Design | Active - Not Contracted | 2019-10-05 |  | 2024-01-05 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187802 | I/500123543/RRR | KwaZulu-Natal | DUBANDLELA HIGH SCHOOL | 500123543 | Umzumbe | Tender | Active - Not Contracted | 2019-05-15 |  | 2026-03-31 |  |  | 2326140 | 10596860 | 12923000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187803 | I/500333777/SDS | KwaZulu-Natal | HLAZAZANE HIGH SCHOOL | 500333777 | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187804 | DB/500280534/SDS | KwaZulu-Natal | THANDOLWABASHA PRIMARY SCHOOL | 500280534 | The Msunduzi | Design | Active - Not Contracted | 2019-08-30 |  | 2024-01-11 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187806 | I/500429792/RRR | KwaZulu-Natal | EBUNGUNI SECONDARY SCHOOLI | 500429792 | Umvoti | Design | Active - Not Contracted | 2018-06-02 |  | 2026-03-31 |  |  | 2700000 | 12300000 | 15000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187807 | I/500171125/SDS | KwaZulu-Natal | IGUGULAMANYONI PRIMARY SCHOOL | 500171125 | Ndwedwe | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187808 | I/500126651/WS | KwaZulu-Natal | ECHWEBENI PRIMARY SCHOOL | 500126651 | Jozini | Practical Completion (100%) | Active - Not Contracted | 2019-05-19 | 2020-08-12 | 2023-03-01 | 2023-05-16 | 2023-06-22 | 320400 | 1459600 | 1780000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187809 | DB/500280608/SDS | KwaZulu-Natal | THANDUKWAZI PRIMARY SCHOOL | DB/500280608/SDS | eThekwini | Design | Active - Not Contracted | 2020-10-05 |  | 2024-01-05 |  |  | 581474 | 2648938 | 3230412 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187810 | I/500162023/SDS | KwaZulu-Natal | INCHANGA PRIMARY SCHOOL | 500162023 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187811 | DB/500189773/SDS | KwaZulu-Natal | MABANDLENI HIGH SCHOOL | 500189773 | Jozini | Design | Active - Not Contracted | 2019-02-01 |  | 2024-02-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187812 | C/500238095/RRR | KwaZulu-Natal | NSIKAYEZWE COMBINED SCHOOL | 500238095 | Alfred Duma | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1800000 | 3400000 | 5200000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187813 | I/500163392/SDS | KwaZulu-Natal | INGOMEZULU PRIMARY SCHOOOL | 500163392 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187814 | I/500132867/RRR | KwaZulu-Natal | EMINYEZANENI H | 500132867 | Mpofana | Construction 76% - 99% | Approved | 2017-05-15 | 2019-06-16 | 2023-07-19 | 2021-06-19 | 2023-07-19 | 5534218 | 30745656 | 36279874 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187815 | DB/500299034/SDS | KwaZulu-Natal | ZAMOKWAKHE SECONDARY SCHOOL | DB/500299034/SDS | Nqutu | Design | Active - Not Contracted | 2020-10-05 |  | 2024-01-31 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187817 | C/500132608/NS | KwaZulu-Natal | EMNGWENYA PRIMARY SCHOOL | 500132608 | Inkosi Langalibalele | Design | Active - Not Contracted | 2018-06-02 |  | 2023-04-30 |  |  | 5280000 | 25800000 | 31080000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187818 | DB/500299256/SDS | KwaZulu-Natal | ZANDLAZETHU HIGH | DB/500299256/SDS | Ulundi | Design | Active - Not Contracted | 2019-08-30 |  | 2025-01-05 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187819 | DB/500186369/SDS | KwaZulu-Natal | LIFALETHU SECONDARY | 500186369 | Jozini | Design | Active - Not Contracted | 2019-02-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187820 | I/500321789/SDS | KwaZulu-Natal | INTATHAKUSA PRIMARY SCHOOL | 500321789 | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187821 | C/500200503/UA | KwaZulu-Natal | MASHIYAMAHLE SECONDARY SCHOOL | 500200503 | Ndwedwe | Design | Active - Not Contracted | 2019-05-10 |  | 2024-03-01 |  |  | 5200000 | 10000000 | 15200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187822 | DB/500222407/SDS | KwaZulu-Natal | MZIWETHU SECONDARY SCHOOL | 500222407 | Dannhauser | Design | Active - Not Contracted | 2020-04-30 |  | 2024-02-25 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187823 | I/500144781/UA | KwaZulu-Natal | FILIDI SECONDARY SCHOOL | 500144781 | Abaqulusi | Design | Active - Not Contracted | 2019-05-15 |  | 2024-11-01 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187824 | I/500168017/SDS | KwaZulu-Natal | ISIHLANGWINI PRIMARY SCHOOL | 500168017 | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187826 | I/500169793/SDS | KwaZulu-Natal | ITSHELEJUBA PRIMARY SCHOOL | 500169793 | uPhongolo | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187827 | I/500148444/WS | KwaZulu-Natal | GEZAMEHLO PRIMARY SCHOOL | 500148444 | Ulundi | Construction 1% - 25% | Active - Not Contracted | 2019-05-15 |  | 2024-03-15 |  |  | 320400 | 1490600 | 1811000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187829 | C/500212935/UA | KwaZulu-Natal | MLONDOZI HIGH SCHOOL | 500212935 | Newcastle | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-12-31 |  |  | 5200000 | 10000000 | 15200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187830 | I/500156769/UA | KwaZulu-Natal | HLELINGOMUSO PRIMARY SCHOOL | 500156769 | The Msunduzi | Design | Active - Not Contracted | 2019-05-15 |  | 2026-03-31 |  |  | 360000 | 2877000 | 3237000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187831 | I/500169904/SDS | KwaZulu-Natal | IVANHOE PRIMARY SCHOOL | 500169904 | Impendle | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187832 | DB/500201502/SDS | KwaZulu-Natal | MATHAFENI PRIMARY SCHOOL | 500201502 | uMshwathi | Design | Active - Not Contracted | 2019-02-04 |  | 2024-03-04 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187833 | C/500232730/RRR | KwaZulu-Natal | NKOSINATHI SECONDARY SCHOOL | 500232730 | eThekwini | On Hold | Active - Not Contracted | 2019-05-10 | 2020-07-05 | 2024-04-15 | 2026-05-15 | 2026-06-01 | 4500000 | 20500000 | 25000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187834 | I/500157250/UA | KwaZulu-Natal | HLOKOZI HIGH | 500157250 | Ubuhlebezwe | Design | Active - Not Contracted | 2019-05-15 |  | 2026-03-31 |  |  | 720000 | 3637000 | 4357000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187835 | DB/500231398/SDS | KwaZulu-Natal | NKALAKUTHABA JUNIOR SEC SCHOOL | 500231398 | Nongoma | Design | Active - Not Contracted | 2020-04-30 |  | 2024-02-26 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187836 | I/500171421/SDS | KwaZulu-Natal | JOBSTOWN PRIMARY SCHOOL | 500171421 | Newcastle | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187838 | I/500292707/RRR | KwaZulu-Natal | HO?R LANDBOUSKOOL VRYHEID | 500292707 | Abaqulusi | Practical Completion (100%) | Active - Contracted | 2018-03-15 | 2019-05-30 | 2023-03-15 | 2020-03-15 | 2023-03-15 | 11651760 | 53080240 | 64732000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187839 | DB/500231620/SDS | KwaZulu-Natal | NKANGALA PRIMARY SCHOOL | 500231620 | Jozini | Design | Active - Contracted | 2020-04-30 |  | 2024-03-09 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187840 | I/500171606/SDS | KwaZulu-Natal | JONASE SECONDARY SCHOOL | 500171606 | KwaDukuza | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187841 | I/500171643/SDS | KwaZulu-Natal | JONGIMFUNDO PRIMARY SCHOOL | 500171643 | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187842 | DB/500208421/SDS | KwaZulu-Natal | MFEKA PRIMARY SCHOOL | 500208421 | Endumeni | Design | Active - Not Contracted | 2019-02-01 |  | 2024-04-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187843 | I/500167758/UA | KwaZulu-Natal | ISIFISOSETHU SECONDARY SCHOOL | 500167758 | KwaDukuza | Construction 76% - 99% | Active - Contracted | 2017-05-15 | 2019-04-15 | 2023-08-15 | 2021-08-15 | 2023-08-10 | 4872060 | 22194940 | 27067000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187844 | DB/500327709/SDS | KwaZulu-Natal | NKOMO PRIMARY SCHOOL | 500327709 | Big Five Hlabisa | Design | Active - Not Contracted | 2020-04-30 |  | 2024-03-10 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187845 | I/500304917/SDS | KwaZulu-Natal | KHOBONGO HIGH SCHOOL | 500304917 | Jozini | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187846 | C/500250823/FSS | KwaZulu-Natal | POMEROY CP | 500250823 | Msinga | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 900000 | 5895000 | 6795000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187847 | DB/500216006/SDS | KwaZulu-Natal | MPANDE HIGH SCHOOL | 500216006 | The Msunduzi | Design | Active - Not Contracted | 2019-04-08 |  | 2024-04-08 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187849 | I/500174603/SDS | KwaZulu-Natal | KHOFI PRIMARY SCHOOL | 500174603 | Umhlabuyalingana | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187850 | DB/500446627/SDS | KwaZulu-Natal | NTABENDE PRIMARY | 500446627 | Endumeni | Design | Active - Not Contracted | 2020-04-30 |  | 2024-03-24 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187852 | I/500176342/SDS | KwaZulu-Natal | KLEIN EDEN COMBINE SCHOOL | 500176342 | Abaqulusi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187853 | I/500177156/SDS | KwaZulu-Natal | KONINGSDAL PRIMARY SCHOOL | 500177156 | Ulundi | Design | Active - Not Contracted | 2019-08-21 |  | 2024-08-21 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187854 | I/500180153/WS | KwaZulu-Natal | KWAMADAMU INTERMEDIATE SCHOOL | 500180153 | Ulundi | Construction 51% - 75% | Active - Contracted | 2018-08-15 | 2020-01-15 | 2023-04-01 | 2021-04-01 | 2024-04-01 | 214000 | 1187000 | 1401000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187855 | C/500253894/UA | KwaZulu-Natal | QOQISIZWE HIGH SCHOOL | 500253894 | The Msunduzi | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 1450000 | 4500000 | 5950000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187857 | C/500276538/UA | KwaZulu-Natal | ST OSWALD SECONDARY SCHOOL | 500276538 | Newcastle | On Hold | Active - Not Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 5200000 | 10000000 | 15200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187859 | C/500444925/ECD | KwaZulu-Natal | VIMBUKHALO PRIMARY SCHOOL | 500444925 | Umhlabuyalingana | Design | Active - Not Contracted | 2019-05-10 |  | 2023-04-15 |  |  | 594000 | 2706000 | 3300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187861 | I/500427165/NS | KwaZulu-Natal | MZOKHANYAYO JUNIOR SECONDARY SCHOOL | 500427165 | Umzimkhulu | Design | Active - Not Contracted | 2018-06-02 |  | 2026-03-31 |  |  | 8581860 | 39095140 | 47677000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 187862 | I/500228993/UA | KwaZulu-Natal | NGUNGWINI HIGH SCHOOL | 500228993 | Ndwedwe | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 360000 | 2877000 | 3237000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187863 | I/500229733/RRR | KwaZulu-Natal | NHLALWANE PRIMARY SCHOOL | 500229733 | Umzumbe | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 2934000 | 13366000 | 16300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187864 | I/500234432/RRR | KwaZulu-Natal | NOMAGEJE PRIMARY SCHOOL | 500234432 | Umzumbe | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 2363940 | 10769060 | 13133000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187865 | I/500248529/UA | KwaZulu-Natal | PHEZULU HIGH SCHOOL | 500248529 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 1800000 | 8200000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187866 | I/500252377/UA | KwaZulu-Natal | QANTAYI SECONDARY SCHOOL | 500252377 | uMhlathuze | Construction 76% - 99% | Active - Not Contracted | 2016-04-01 | 2018-03-30 | 2024-08-21 | 2024-10-01 | 2024-10-01 | 7622820 | 34726180 | 42349000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187867 | I/500263292/UA | KwaZulu-Natal | SIBONGUMUSA SECONDARY SCHOOL | 500263292 | uMshwathi | Practical Completion (100%) | Active - Contracted | 2016-04-01 | 2018-03-30 | 2023-08-21 | 2023-06-15 | 2023-03-30 | 6307706 | 28735104 | 35042810 | Education Infrastructure Grant | Upgrading and Additions
|  | 187868 | I/500299552/RRR | KwaZulu-Natal | ZEPH DHLOMO SECONDARY SCHOOL | 500299552 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 1602000 | 7298000 | 8900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187869 | I/500300884/UA | KwaZulu-Natal | ZITHUME HIGH | 500300884 | uMlalazi | Design | Active - Not Contracted | 2019-08-21 |  | 2026-03-31 |  |  | 720000 | 3637000 | 4357000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187935 | LE20TMT17025 | Limpopo | SEGOBOKO SECONDARY | 921142195 | Mogalakwena | Tender | Active - Not Contracted | 2019-02-20 |  | 2025-03-31 |  |  | 184000 | 736000 | 920000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187936 | LE20TMT17053 | Limpopo | Tshivhade Primary | 930321493 | Makhado | Tender | Active - Not Contracted | 2019-02-20 | 2019-04-02 | 2024-06-30 | 2024-06-30 | 2024-07-30 | 471988 | 6735520 | 7207508 | Education Infrastructure Grant | Upgrading and Additions
|  | 187937 | LE20TMT17051 | Limpopo | Tshapasha Primary | 929311422 | Thulamela | Tender | Active - Contracted | 2019-04-01 | 2019-08-30 | 2025-07-30 | 2024-07-30 | 2024-07-30 | 244000 | 976000 | 1220000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187943 | LE20TMT17052 | Limpopo | Tshiendeulu Primary | 928330275 | Thulamela | Tender | Active - Contracted | 2019-04-01 | 2019-06-30 | 2024-06-30 | 2024-06-30 | 2025-03-31 | 212800 | 851200 | 1064000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187947 | TBA 05 | Western Cape | Sunningdale PS | TBC | City of Cape Town | Project Initiation | Proposed | 2020-04-01 |  | 2027-03-31 |  |  | 13000000 | 62000000 | 75000000 | Equitable Share | New or Replaced Infrastructure
|  | 187948 | GDE00006 | Gauteng | Allanridge Secondary School | 700150011 | City of Johannesburg | Project Initiation | Proposed | 2020-04-01 |  | 2026-06-13 |  |  | 1213000 | 6367000 | 7580000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187988 | DoE/EHL/MAIN/108 | Mpumalanga | Sikhwahlane Primary School | 800021071 | Nkomazi | Project Initiation | Active - Contracted | 2020-07-31 |  | 2023-03-31 |  |  | 12459 | 124587 | 137046 | Education Infrastructure Grant | Maintenance and Repairs
|  | 187991 | (MDOE/UPG/012/20-21) | Mpumalanga | Kusile Primary School | 800008599 | Mbombela | Tender | Active - Not Contracted | 2020-04-01 |  | 2024-12-20 |  |  | 3342514 | 19100083 | 22442597 | Education Infrastructure Grant | Upgrading and Additions
|  | 187992 | DB/500240759/SDS | KwaZulu-Natal | NTSINDE SECONDARY SCHOOL | 500240759 | Jozini | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187993 | DB/500326155/SDS | KwaZulu-Natal | NTSONYANE PRIMARY SCHOOL | 500326155 | Nongoma | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187994 | DB/500240796/SDS | KwaZulu-Natal | NTSWALAKAHLA PRIMARY SCHOOL | 500240796 | Abaqulusi | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187996 | DB/500241425/SDS | KwaZulu-Natal | NYAKAZA PRIMARY SCHOOL | 500241425 | Nqutu | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 187998 | DB/500337736/SDS | KwaZulu-Natal | PHUZUKUBONA SECONDARY SCHOOL | 500337736 | Dannhauser | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Upgrading and Additions
|  | 187999 | DB/500251970/SDS | KwaZulu-Natal | PUMULA PRIMARY SCHOOL | 500251970 | uPhongolo | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188000 | DB/500440041/SDS | KwaZulu-Natal | QHAWELESIZWE PRIMARY SCHOOL | 500440041 | Newcastle | Design | Active - Not Contracted | 2019-05-10 |  | 2024-04-15 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188001 | DB/500255189/SDS | KwaZulu-Natal | REUNION SECONDARY SCHOOL | 500255189 | eThekwini | Final Completion | Approved | 2019-05-10 | 2020-05-01 | 2023-04-15 | 2022-07-14 | 2025-06-20 | 406975 | 1853996 | 2260971 | Education Infrastructure Grant | Maintenance and Repairs
|  | 188002 | DB/500263440/SDS | KwaZulu-Natal | SBONOKUHLE SECONDARY SCHOOL | 500263440 | Ray Nkonyeni | Practical Completion (100%) | Active - Contracted | 2019-05-10 | 2022-12-01 | 2023-04-15 | 2023-07-31 | 2025-06-15 | 452144 | 2059769 | 2511913 | Education Infrastructure Grant | Maintenance and Repairs
|  | 188033 | MDOE/UPG/002/20-21 | Mpumalanga | Mahhushe Secondary School | 800011734 | Nkomazi | Design | Proposed | 2020-04-01 |  | 2024-05-30 |  |  | 1391320 | 9938000 | 11329320 | Education Infrastructure Grant | Upgrading and Additions
|  | 188034 | MDOE/UPG/1019/21-22 | Mpumalanga | Victory Park Primary School | 800024661 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2025-01-16 |  |  | 1050267 | 7501904 | 8552171 | Education Infrastructure Grant | Upgrading and Additions
|  | 188035 | MDOE/UPG/1013/20-21 | Mpumalanga | Shayaza Secondary School | 800020495 | Nkomazi | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2023-04-01 | 2024-10-01 | 2024-10-01 | 2025-10-01 | 1661642 | 11868870 | 13530512 | Education Infrastructure Grant | Upgrading and Additions
|  | 188046 | Tikhuni High School(Phase two) | Mpumalanga | Tikhuni High School | 800023515 | Nkomazi | Project Initiation | Proposed | 2020-04-01 |  | 2022-11-30 |  |  | 961586 | 8013214 | 8974800 | Education Infrastructure Grant | Upgrading and Additions
|  | 188049 | MDOE/UPG/1025/20-21 | Mpumalanga | Matsamo Primary School | 800013391 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2022-11-01 |  |  | 1981181 | 14151296 | 16132477 | Education Infrastructure Grant | Upgrading and Additions
|  | 188108 | MDOE/SAN/028/2020(DPWRT/SAN/151/20/MP) | Mpumalanga | Hillaria Mthethwa Secondary School | 800003921 | Mbombela | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-11-14 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 134962 | 964018 | 1098980 | Education Infrastructure Grant | Upgrading and Additions
|  | 188113 | MDOE/MAIN/01/22-23 | Mpumalanga | Impumelelo Primary School | 800006239 | Nkomazi | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-06-16 |  |  | 390600 | 2790000 | 3180600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 188292 | TBA 01 | Western Cape | Hermanus Technical OBTSS1 Tech School | TBC | Overstrand | Project Initiation | Proposed | 2020-04-01 |  | 2027-03-31 |  |  | 11000000 | 86000000 | 97000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 188366 | TBA 06 | Western Cape | Silversands New Campus School (MEILE2) | TBC | City of Cape Town | Project Initiation | Proposed | 2020-04-01 |  | 2028-03-31 |  |  | 17000000 | 106000000 | 123000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 188451 | GDE00063 | Gauteng | Edleen Primary School | 700260091 | City of Ekurhuleni | Project Initiation | Proposed | 2019-04-01 |  | 2026-03-13 |  |  | 2550000 | 0 | 2550000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188453 | GDE00086 | Gauteng | General Smuts High School | 700330126 | Emfuleni | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 600000 | 9600000 | 10200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188456 | GDE00087 | Gauteng | Germiston High school | 700340141 | City of Ekurhuleni | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-20 |  |  | 1170000 | 5880000 | 7050000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188540 | GDE00097 | Gauteng | Hlangabeza Primary School | 70027270736 | Merafong City | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 1780000 | 8820000 | 10600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188567 | GDE00100 | Gauteng | HOERSKOOL CENTURION | 700210229 | City of Tshwane | Design | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 50000 | 0 | 50000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188569 | TBA 09 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 30000000 | 150000000 | 180000000 | Equitable Share | Infrastructure Transfers - Capital
|  | 188574 | 30550051/30553051. | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 10000000 | 110000000 | 120000000 | Equitable Share | Infrastructure Transfers - Capital
|  | 188598 | GDE00101 | Gauteng | Hoerskool Centurion | 700210229 | City of Tshwane | Feasibility | Approved | 2021-02-12 |  | 2025-03-21 |  |  | 50000 | 0 | 50000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188609 | GDE00102 | Gauteng | Hoerskool Die Adelaar SS | 700250217 | City of Johannesburg | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 828000 | 2772000 | 3600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188636 | GDE00109 | Gauteng | Hoerskool Roodepoort | 700250274 | City of Johannesburg | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 2060000 | 9240000 | 11300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188637 | GDE00110 | Gauteng | HOERSKOOL SILVERTON | 700220186 | City of Tshwane | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 2700000 | 12600000 | 15300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188638 | GDE00112 | Gauteng | HOERSKOOL VORENTOE | 700140186 | City of Johannesburg | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 820000 | 1680000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188639 | GDE00113 | Gauteng | HOERSKOOL WONDERFONTEIN | 700270140 | Merafong City | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 1480000 | 2520000 | 4000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188644 | GDE00125 | Gauteng | Job Rathebe Combined School | 700132332 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-14 |  |  | 1460000 | 5040000 | 6500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188704 | DPWRT/SAN/331/20/MP MDOE/SAN/142/2020 | Mpumalanga | S`bongile Primary School | 800030734 | Mbombela | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 |  | 2022-05-16 |  |  | 284800 | 2034286 | 2319086 | Education Infrastructure Grant | Upgrading and Additions
|  | 188712 | MDOE/SAN/146/2020 (DPWRT/SAN/163/20/MP) | Mpumalanga | Lungisani Secondary School | 800010868 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2021-07-29 | 2022-05-16 | 2022-03-31 | 2022-11-30 | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188713 | MDOE/SAN/148/2020 (DPWRT/SAN/164/20/MP) | Mpumalanga | Manzini Primary School | 800012435 | Mbombela | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 | 2021-09-28 | 2022-05-16 | 2022-03-31 | 2022-07-19 | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188716 | MDOE/SAN/155/2020 (DPWRT/SAN/158/20/MP) | Mpumalanga | Mpunzana Primary School | 800015743 | Mbombela | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2021-07-29 | 2022-05-16 | 2022-03-30 | 2022-03-30 | 315000 | 2250000 | 2565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188718 | MDOE/SAN/156/2020(DPWRT/SAN/077/20/MP) | Mpumalanga | Mshengu Primary School | 800015784 | Mbombela | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2022-07-31 | 2022-05-16 | 2023-03-31 | 2023-03-31 | 201600 | 1440000 | 1641600 | Education Infrastructure Grant | Upgrading and Additions
|  | 188719 | MDOE/SAN/180/2020(DPWRT/SAN/059/20/MP ) | Mpumalanga | Nyalunga Primary School | 800017491 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-09-30 | 2021-08-03 | 2023-10-01 | 2021-11-08 | 2022-05-31 | 651000 | 3255000 | 3906000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188731 | GDE00151 | Gauteng | Kosisi Primary School | 700930749 | Rand West City | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 1040000 | 5460000 | 6500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 188732 | MDOE/SAN/185/2020(DPWRT/SAN/171/20/MP) | Mpumalanga | Makoko Primary School | 800011932 | Mbombela | Design | Active - Contracted | 2020-10-31 |  | 2023-10-01 |  |  | 256927 | 1835192 | 2092119 | Education Infrastructure Grant | Upgrading and Additions
|  | 188736 | MDOE/SAN/187/2020(DPWRT/SAN/119/20/MP) | Mpumalanga | Mbazima Primary School | 800013680 | Nkomazi | Construction 51% - 75% | Active - Contracted | 2020-10-31 |  | 2023-10-01 |  |  | 466200 | 3330000 | 3796200 | Education Infrastructure Grant | Upgrading and Additions
|  | 188741 | MDOE/SAN/189/2020(DPWRT/SA/108/20/MP) | Mpumalanga | Sibambisene Primary School | 800020610 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 298660 | 1737910 | 2036570 | Education Infrastructure Grant | Upgrading and Additions
|  | 188749 | DPWRT/SAN/173/20MP( MDOE/SAN/026/2020) --------- | Mpumalanga | Chweni Primary School | 800002147 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2021-01-18 | 2023-10-01 | 2022-03-30 | 2022-03-30 | 355823 | 2541596 | 2897419 | Equitable Share | Upgrading and Additions
|  | 188750 | DPWRT/SAN/101/20/MP (SABATHA P) --------- | Mpumalanga | Sabatha Primary School | 800019646 | Nkomazi | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2021-07-29 | 2023-10-01 | 2021-10-29 | 2021-10-29 | 201600 | 1440000 | 1641600 | Education Infrastructure Grant | Upgrading and Additions
|  | 188752 | DPWRT/SAN/131/20/MP | Mpumalanga | Sigweje Secondary School | 800020958 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 379857 | 1334450 | 1714307 | Education Infrastructure Grant | Upgrading and Additions
|  | 188756 | MDOE/SAN/197/2020(DPWRT/SAN/146/20/MP) | Mpumalanga | Sehlulile Primary School | 800020131 | Mbombela | Site Handed - Over to Contractor | Active - Contracted | 2020-10-31 |  | 2023-10-01 |  |  | 378000 | 2700000 | 3078000 | Education Infrastructure Grant | Upgrading and Additions
|  | 188759 | DPWRT/SAN/132/20/MP | Mpumalanga | Idlangemabala Secondary School | 800032870 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 291995 | 2085678 | 2377673 | Education Infrastructure Grant | Upgrading and Additions
|  | 188761 | MDOE/SAN/199/2020 (DPWRT/SAN/166/20/MP) | Mpumalanga | Mganduzweni Primary School | 800014050 | Mbombela | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-07-30 | 2023-10-01 | 2022-03-31 | 2022-03-31 | 289800 | 2070000 | 2359800 | Education Infrastructure Grant | Upgrading and Additions
|  | 188765 | DPWRT/SAN/174/20MP(NGAZINDLOVU S--------- | Mpumalanga | NgaziNdlovu Secondary School | 800034635 | Mbombela | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-01-28 | 2023-10-01 | 2022-02-16 | 2022-03-24 | 305262 | 2180440 | 2485702 | Equitable Share | Upgrading and Additions
|  | 188768 | MDOE/SAN/201/2020 | Mpumalanga | Phambanisa Primary School | 800018127 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 403200 | 2880000 | 3283200 | Equitable Share | Upgrading and Additions
|  | 188773 | MDOE/SAN/305/2020(DPWRT/SAN/061/19/MP) | Mpumalanga | Khutsalani Secondary School | 800008607 | Mbombela | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2022-01-15 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 352800 | 2520000 | 2872800 | Education Infrastructure Grant | Upgrading and Additions
|  | 188777 | MDOE/SAN/204/2020 (DPWRT/SAN/134/MP) | Mpumalanga | Gebhuza Secondary School | 800004424 | Nkomazi | Construction 1% - 25% | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 465000 | 2325000 | 2790000 | Equitable Share | Upgrading and Additions
|  | 188785 | MD0E/SAN/205/2020 ( DPWRT/SAN/080/20/MP) | Mpumalanga | Gebhundlovu Primary School | 800004416 | Nkomazi | Terminated | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 362024 | 2585884 | 2947908 | Equitable Share | Upgrading and Additions
|  | 188789 | DPWRT/SAN/175/20MP(MTUNGWA SEC) --------- | Mpumalanga | Mtungwa Secondary School | 800014761 | Mbombela | Tender | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 301145 | 2151037 | 2452182 | Equitable Share | Upgrading and Additions
|  | 188794 | DPWRT/SAN/082/20/MP | Mpumalanga | Lomahasha Secondary School | 800003038 | Nkomazi | Construction 76% - 99% | Active - Not Contracted | 2020-04-01 | 2020-10-02 | 2023-10-01 | 2022-03-23 | 2022-03-23 | 270606 | 1932896 | 2203502 | Equitable Share | Upgrading and Additions
|  | 188799 | DPWRT/SAN/069/20(MAGUBHA P)-------------- | Mpumalanga | Magubha Combined School | 800011551 | Nkomazi | Construction 51% - 75% | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 403908 | 2885060 | 3288968 | Equitable Share | Upgrading and Additions
|  | 188803 | MDOE/SAN/214/2020 | Mpumalanga | Mahlatsi Secondary School | 800011676 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 315000 | 2250000 | 2565000 | Equitable Share | Upgrading and Additions
|  | 188804 | DPWRT/SAN/083/20/MP (MDOE/SAN/215/2020) | Mpumalanga | Zenzele Secondary School | 800025866 | Nkomazi | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2021-02-09 | 2023-10-01 | 2022-03-24 | 2022-03-24 | 301202 | 2151446 | 2452648 | Equitable Share | Upgrading and Additions
|  | 188811 | DPWRT/SAN/062/20/MP (UMPOPOLI P)--------- | Mpumalanga | Umpopoli Primary School | 800024354 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 442210 | 2901880 | 3344090 | Equitable Share | Upgrading and Additions
|  | 188829 | DPWRT/SAN/070/20/MP(MDOE/SAN/220/2020) | Mpumalanga | Sogasa Primary School | 800021931 | Nkomazi | Construction 26% - 50% | Active - Not Contracted | 2020-04-01 | 2022-10-31 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 201600 | 1440000 | 1641600 | Equitable Share | Upgrading and Additions
|  | 188830 | DPWRT/SAN/080/20MP(NDLAVELA PRIM--------- | Mpumalanga | Ndlavela Primary School | 800016451 | Nkomazi | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2021-02-19 | 2023-10-01 | 2022-03-24 | 2022-03-24 | 243819 | 1741562 | 1985381 | Equitable Share | Upgrading and Additions
|  | 188836 | DPWRT/SAN/154/20/MP (MDOE/SAN/223/2020) | Mpumalanga | Bongani Primary School | 800001347 | Mbombela | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-11-12 | 2023-10-01 | 2022-03-21 | 2022-03-21 | 315000 | 2807244 | 3122244 | Equitable Share | Upgrading and Additions
|  | 188839 | DPWRT/SAN/086/20/MP | Mpumalanga | Steenbok Secondary School | 800029314 | Nkomazi | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-07-07 | 2023-10-01 | 2021-10-07 | 2021-10-07 | 303888 | 2170629 | 2474517 | Equitable Share | Upgrading and Additions
|  | 188849 | MDOE/SAN/226/2020(DPWRT/SAN/087/20/MP ) | Mpumalanga | Luthango Primary School | 800010892 | Nkomazi | Construction 26% - 50% | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 315000 | 2250000 | 2565000 | Equitable Share | Upgrading and Additions
|  | 188858 | DPWRT/SAN/093/20MP(ZANDILE PRIM)--------- | Mpumalanga | Zandile Primary School | 800025833 | Nkomazi | Tender | Active - Not Contracted | 2022-03-30 |  | 2024-03-30 |  |  | 289800 | 2070000 | 2359800 | Education Infrastructure Grant | Upgrading and Additions
|  | 189090 | GDE00162 | Gauteng | Laerskool Fluer | 700210708 | City of Johannesburg | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-13 |  |  | 913000 | 1680000 | 2593000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189091 | GDE00166 | Gauteng | Laersool Glenharvie Combined | 700270306 | Rand West City | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1260000 | 5040000 | 6300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189092 | GDE00167 | Gauteng | Laerskool Handhawer | 700330373 | Emfuleni | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 1640000 | 3360000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189097 | GDE00174 | Gauteng | Laerskool Noordhoek PS | 700320127 | Emfuleni | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 800000 | 12200000 | 13000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189102 | GDE00180 | Gauteng | Laerskool Uniefees PS | 700240333 | City of Tshwane | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 1148000 | 4452000 | 5600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189119 | GDE00187 | Gauteng | Laerskool Wonsderboom-Suid | 700231035 | City of Tshwane | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 700000 | 2100000 | 2800000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189127 | GDE00194 | Gauteng | Lenasia Secondary School | 700110155 | City of Johannesburg | Design | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 820000 | 1680000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189135 | GDE00200 | Gauteng | Letsibogo Secondary School | 700140715 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 915000 | 1260000 | 2175000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189151 | GDE00228 | Gauteng | Meyerton Primary School | 700330498 | Midvaal | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1212000 | 4788000 | 6000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189162 | GDE00236 | Gauteng | Moletsane Secondary School | 700121574 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1190000 | 2310000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189177 | GDE00260 | Gauteng | Northview High school | 700151050 | City of Johannesburg | Feasibility | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 2380000 | 10920000 | 13300000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189204 | GDE00288 | Gauteng | Pro Arte Alphen (Creative and Creative and Performing Arts) LSEN | 700232454 | City of Tshwane | Project Initiation | Approved | 2020-04-01 |  | 2025-06-13 |  |  | 0 | 6115000 | 6115000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189217 | GDE00313 | Gauteng | Rivoningo Primary School | 700241216 | City of Tshwane | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 459000 | 14333000 | 14792000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189219 | GDE00326 | Gauteng | Sandown High School | 700151498 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 3040000 | 15960000 | 19000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189221 | GDE00335 | Gauteng | Setholela Primary School | 700271064 | Rand West City | Design | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1104000 | 5796000 | 6900000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189231 | GDE00350 | Gauteng | Springs Boy`s High Schhol | 700350041 | City of Ekurhuleni | Project Initiation | Approved | 2020-04-01 |  | 2026-03-21 |  |  | 771200 | 4048800 | 4820000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189236 | GDE00360 | Gauteng | Tembisa (Hospitality)LSEN | 700261305 | City of Ekurhuleni | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 2080000 | 10920000 | 13000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189246 | GDE00367 | Gauteng | Thembu Primary School | 700121806 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 0 | 1800000 | 1800000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189326 | GDE00391 | Gauteng | Tshirela Primary School | 700321653 | Emfuleni | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 1097600 | 5763000 | 6860600 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189371 | DB/500121027/SDS | KwaZulu-Natal | DIBI PRIMARY SCHOOL | 500121027 | Nkandla | Project Initiation | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189391 | GDE00421 | Gauteng | Waverley Girls High School | 700151910 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2024-03-21 |  |  | 1062560 | 5578440 | 6641000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189408 | GDE00425 | Gauteng | Westonaria Primary School | 700270587 | Rand West City | Final Completion | Approved | 2019-04-01 | 2019-05-08 | 2023-05-09 | 2023-07-20 | 2023-07-21 | 50000 | 450000 | 500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189410 | GDE00428 | Gauteng | Willow Crescent Secondary School | 700120386 | City of Johannesburg | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 2400000 | 12600000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189541 | GDE00058 | Gauteng | ECD centre: Northern Corridor | N/A | City of Tshwane | Project Initiation | Approved | 2020-04-01 |  | 2026-02-13 |  |  | 6720000 | 35280000 | 42000000 | Equitable Share | New or Replaced Infrastructure
|  | 189553 | GDE00140 | Gauteng | Kgolagano Primary School | 700340752 | City of Ekurhuleni | Project Initiation | Approved | 2020-04-01 |  | 2026-03-13 |  |  | 800000 | 4200000 | 5000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189797 | DPWRT/SAN/109/20/MP (MDOE/SAN/001/2020) | Mpumalanga | Sidungeni Secondary School | 800020875 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2021-08-03 | 2022-11-16 | 2021-11-03 | 2021-11-03 | 382676 | 1518621 | 1901297 | Education Infrastructure Grant | Upgrading and Additions
|  | 189810 | DPWRT/SAN/147/20/MP | Mpumalanga | Masitakhe Secondary School | 800013011 | Mbombela | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2022-06-30 | 2022-06-30 | 2023-03-31 | 2023-03-31 | 403200 | 2880000 | 3283200 | Education Infrastructure Grant | Upgrading and Additions
|  | 189847 | DB/500140267/RRR | KwaZulu-Natal | ESIDUMBINI PRIMARY SCHOOL | 500140267 | Ndwedwe | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2019-03-01 | 2024-03-29 | 2024-03-30 | 2027-05-30 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 189869 | P9010934 | Eastern Cape | MGEZWA SENIOR SECONDARY SCHOOL | 200500664 | Ingquza Hill | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189870 | P9010990 | Eastern Cape | MPONDOMBINI SENIOR SECONDARY SCHOOL | 200500764 | Mbizana | Practical Completion (100%) | Approved | 2020-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2328042 | 2328042 | Education Infrastructure Grant | Upgrading and Additions
|  | 189871 | P9011024 | Eastern Cape | MTYOBO PUBLIC PRIMARY SCHOOL | 200100537 | Ndlambe | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189875 | P9011025 | Eastern Cape | QHAYIYA PRIMARY SCHOOL | 200100639 | Makana | Tender | Active - Not Contracted | 2020-04-01 |  | 2025-05-30 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189876 | P9010936 | Eastern Cape | WILLOWMORE SECONDARY SCHOOL | 200100858 | Dr Beyers Naude | Design | Approved | 2020-04-01 |  | 2026-05-30 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189877 | P9010937 | Eastern Cape | MDATYA SENIOR SECONDARY SCHOOL | 200500639 | Mbizana | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1194026 | 1194026 | Education Infrastructure Grant | Upgrading and Additions
|  | 189878 | P9010938 | Eastern Cape | PORT ALFRED JUNIOR SECONDARY SCHOOL | 200100633 | Ndlambe | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 3643566 | 3643566 | Education Infrastructure Grant | Upgrading and Additions
|  | 189879 | P9011567 | Eastern Cape | NYIBIBA PRIMARY SCHOOL | 200100338 | Raymond Mhlaba | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2020-06-30 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 11533302 | 11533302 | Education Infrastructure Grant | Upgrading and Additions
|  | 189880 | P9010939 | Eastern Cape | ENYANISWENI SENIOR SECONDARY SCHOOL | 200500208 | Mbizana | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2289546 | 2289546 | Education Infrastructure Grant | Upgrading and Additions
|  | 189881 | P9010940 | Eastern Cape | ENGCOBO VILLAGE SENIOR SECONDARY SCHOOL | 200400167 | Engcobo | Design | Approved | 2020-03-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189882 | P9010941 | Eastern Cape | GERMAN VILLAGE JUNIOR SECONDARY SCHOOL | 200200205 | Ngqushwa | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 3048594 | 3048594 | Education Infrastructure Grant | Upgrading and Additions
|  | 189884 | P9010997 | Eastern Cape | NTSONKOTA SECONDARY SCHOOL | 200200658 | Buffalo City | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189886 | P9010942 | Eastern Cape | MDENGENTONGA PRIMARY SCHOOL | 200100504 | Nelson Mandela Bay | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-05-30 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189887 | P9010943 | Eastern Cape | BASHEE COMPREHENSIVE HIGH SCHOOL | 200300011 | Mbhashe | Design | Approved | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189889 | P9010945 | Eastern Cape | NOMAGQWATHEKANA COMPREHENSIVE TECHNICAL SCHOOL | 200501457 | Mbizana | Practical Completion (100%) | Approved | 2020-04-01 | 2020-07-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2338438 | 2338438 | Education Infrastructure Grant | Upgrading and Additions
|  | 189892 | P9010994 | Eastern Cape | NOBANGILE SENIOR SECONDARY SCHOOL | 200400808 | Mbhashe | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189895 | P9010949 | Eastern Cape | DORDRECHT HIGH SCHOOL | 200600139 | Emalahleni | Design | Approved | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 189898 | P9010951 | Eastern Cape | JAMES JOLOBE SECONDARY SCHOOL | 200100347 | Nelson Mandela Bay | Tender | Active - Not Contracted | 2020-03-01 |  | 2024-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190035 | P9010952 | Eastern Cape | AM ZANTSI SENIOR SECONDARY SCHOOL | 200600003 | Sakhisizwe | Design | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190036 | P9009805_ | Eastern Cape | MNGCANGCATHELO JUNIOR SECONDARY SCHOOL | 200300355 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 635617 | 4540126 | 5175743 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190037 | P9010953 | Eastern Cape | JONGINTABA SENIOR SECONDARY SCHOOL | 200400300 | King Sabata Dalindyebo | Design | Approved | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190040 | P9010954 | Eastern Cape | FORT BEAUFORT PRIMARY SCHOOL | 200100942 | Raymond Mhlaba | Tender | Active - Not Contracted | 2020-03-30 |  | 2026-03-31 |  |  | 0 | 2499244 | 2499244 | Education Infrastructure Grant | Upgrading and Additions
|  | 190041 | P9006990_ | Eastern Cape | BELMORE SENIOR PRIMARY SCHOOL | 200600040 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 594851 | 2124470 | 2719321 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190043 | P9010955 | Eastern Cape | NCORA FLATS JUNIOR PRIMARY SCHOOL | 200600551 | Intsika Yethu | Site Handed - Over to Contractor | Approved | 2020-03-30 | 2020-05-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190045 | P9011011 | Eastern Cape | SIMPHIWE KHETHWA SECONDARY SCHOOL | 200601001 | Walter Sisulu | Tender | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2142673 | 2142673 | Education Infrastructure Grant | Upgrading and Additions
|  | 190048 | P9006984_ | Eastern Cape | EZINTATYANENI SENIOR PRIMARY SCHOOL | 200600194 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-04-06 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 592265 | 1850829 | 2443094 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190050 | P9011022 | Eastern Cape | MZIMVUBU JUNIOR SECONDARY SCHOOL | 200401355 | King Sabata Dalindyebo | Design | Approved | 2020-03-30 |  | 2026-03-31 |  |  | 0 | 2993444 | 2993444 | Education Infrastructure Grant | Upgrading and Additions
|  | 190069 | DoE/NKD/MAIN/ 063 | Mpumalanga | Sibukosethu Primary School | 800020776 | Emalahleni | Project Initiation | Proposed | 2020-06-01 |  | 2023-12-31 |  |  | 0 | 3429415 | 3429415 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190087 | P9010957 | Eastern Cape | BUWA SENIOR SECONDARY SCHOOL | 200500072 | Mhlontlo | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190090 | DPWRT/337/20/MP(MASINAKANE SPECI--------- | Mpumalanga | Masinakane Special School | 800003763 | Dr JS Moroka | Project Initiation | Proposed | 2020-06-01 |  | 2024-05-31 |  |  | 0 | 615883 | 615883 | Education Infrastructure Grant | Upgrading and Additions
|  | 190092 | P9011013 | Eastern Cape | ETYENI JUNIOR SECONDARY SCHOOL | 200400177 | Walter Sisulu | Tender | Active - Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1360131 | 1360131 | Education Infrastructure Grant | Upgrading and Additions
|  | 190093 | P9010959 | Eastern Cape | PATRICIA NOAH JUNIOR SECONDARY SCHOOL | 200300536 | Mnquma | Tender | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190098 | P9011023 | Eastern Cape | MBONGWENI JUNIOR SECONDARY SCHOOL | 200500626 | Ntabankulu | Tender | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190099 | P9005964_ | Eastern Cape | PHANDULWAZI AGRICULTURAL HIGH SCHOOL | 200200684 | Raymond Mhlaba | Tender | Active - Not Contracted | 2020-03-30 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190102 | P9011026 | Eastern Cape | WOODLANDS PRIMARY SCHOOL | 200100868 | Nelson Mandela Bay | Design | Approved | 2020-03-30 |  | 2026-03-31 |  |  | 0 | 2558263 | 2558263 | Education Infrastructure Grant | Upgrading and Additions
|  | 190105 | P9010961 | Eastern Cape | GOBIZIZWE SENIOR SECONDARY SCHOOL | 200400581 | King Sabata Dalindyebo | Tender | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 6175511 | 6175511 | Education Infrastructure Grant | Upgrading and Additions
|  | 190109 | P9010963 | Eastern Cape | MANDILENI PRIMARY SCHOOL | 200500560 | Umzimvubu | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 3252556 | 3252556 | Education Infrastructure Grant | Upgrading and Additions
|  | 190112 | P9010977_ | Eastern Cape | ST CHARLES SOJOLA HIGH SCHOOL | 200200977 | Ngqushwa | Construction 51% - 75% | Active - Contracted | 2020-03-30 | 2020-04-30 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 1831571 | 1831571 | Education Infrastructure Grant | Upgrading and Additions
|  | 190114 | MDOE/SAN/010/2020 (DPWRT/SAN/159/20/MP) | Mpumalanga | Inkunzi Primary School | 800006478 | Mbombela | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2021-07-29 | 2022-07-15 | 2022-03-14 | 2022-03-14 | 352800 | 2520000 | 2872800 | Education Infrastructure Grant | Upgrading and Additions
|  | 190117 | P9010992 | Eastern Cape | MNUKWA SENIOR SECONDARY SCHOOL | 200500725 | Matatiele | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2221645 | 2221645 | Education Infrastructure Grant | Upgrading and Additions
|  | 190118 | P9010964 | Eastern Cape | ZIBI MEYER SENIOR SECONDARY SCHOOL | 200501321 | Matatiele | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2260292 | 2260292 | Education Infrastructure Grant | Upgrading and Additions
|  | 190121 | P9010965 | Eastern Cape | MASIHLANGANE SECONDARY SCHOOL | 200201011 | Amahlathi | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2603179 | 2603179 | Education Infrastructure Grant | Upgrading and Additions
|  | 190123 | P9011006 | Eastern Cape | MAIN JUNIOR SECONDARY SCHOOL | 200600420 | Intsika Yethu | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190124 | DPWRT/SAN/089/20/MP (MDOE/SAN/013/2020) | Mpumalanga | Sambo Primary School | 800029314 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2020-04-01 |  | 2022-07-15 |  |  | 0 | 1907955 | 1907955 | Education Infrastructure Grant | Upgrading and Additions
|  | 190127 | P9010968 | Eastern Cape | BURU JUNIOR SECONDARY SCHOOL | 200300721 | Mnquma | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190131 | DPWRT/148/20/MP | Mpumalanga | Sicelosetfu Secondary school | 800034207 | Mbombela | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-10-30 | 2022-11-01 | 2022-03-30 | 2022-03-30 | 266971 | 1906938 | 2173909 | Education Infrastructure Grant | Upgrading and Additions
|  | 190135 | P9011027 | Eastern Cape | GCINUBUZWE COMBINED SCHOOL | 200100240 | Dr Beyers Naude | Tender | Active - Not Contracted | 2020-03-30 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190139 | P9010971 | Eastern Cape | ENKALWENI JUNIOR PRIMARY SCHOOL | 200401266 | Elundini | Tender | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1448675 | 1448675 | Education Infrastructure Grant | Upgrading and Additions
|  | 190141 | P9010972 | Eastern Cape | MASIBONISANE SENIOR SECONDARY SCHOOL | 200200424 | Ngqushwa | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1865002 | 1865002 | Education Infrastructure Grant | Upgrading and Additions
|  | 190145 | DPWRT/SAN/095/20MP(TINHLONHLA S)--------- | Mpumalanga | Tinhlonhla Secondary School | 800023564 | Nkomazi | Construction 1% - 25% | Active - Contracted | 2020-04-01 |  | 2022-07-15 |  |  | 551400 | 2757000 | 3308400 | Education Infrastructure Grant | Upgrading and Additions
|  | 190147 | P9011012 | Eastern Cape | IMPUMELELO SENIOR SECONDARY SCHOOL | 200600291 | Senqu | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 2792214 | 2792214 | Education Infrastructure Grant | Upgrading and Additions
|  | 190153 | P9011007 | Eastern Cape | NGUBESIZWE SENIOR SECONDARY SCHOOL | 200300443 | King Sabata Dalindyebo | Design | Approved | 2021-09-22 |  | 2026-03-31 |  |  | 0 | 2647342 | 2647342 | Education Infrastructure Grant | Upgrading and Additions
|  | 190155 | P9011020 | Eastern Cape | MQIKELA SENIOR SECONDARY SCHOOL | 200500776 | Ingquza Hill | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190156 | P9011021 | Eastern Cape | LUQOQWENI JUNIOR SECONDARY SCHOOL | 200500473 | Port St Johns | Design | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190157 | P9010974 | Eastern Cape | MPUTEKANE PRIMARY SCHOOL | 200500770 | Nyandeni | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1144752 | 1144752 | Education Infrastructure Grant | Upgrading and Additions
|  | 190158 | P9010975 | Eastern Cape | BETHESDA PRIMARY SCHOOL | 200500031 | Matatiele | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 1484284 | 1484284 | Education Infrastructure Grant | Upgrading and Additions
|  | 190159 | P9011539_ | Eastern Cape | NONCEDO COMBINED SCHOOL | 200200619 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2020-06-30 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 10717765 | 10717765 | Education Infrastructure Grant | Upgrading and Additions
|  | 190161 | P9011538 | Eastern Cape | MZAMOWETHU PUBLIC SCHOOL | 200200521 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2020-03-30 | 2020-06-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5422898 | 5422898 | Education Infrastructure Grant | Upgrading and Additions
|  | 190162 | P9011537 | Eastern Cape | FORT WARWICK FARM SCHOOL | 200200187 | Great Kei | Practical Completion (100%) | Active - Contracted | 2020-03-30 |  | 2025-05-30 |  |  | 0 | 3796106 | 3796106 | Education Infrastructure Grant | Upgrading and Additions
|  | 190180 | P9010929 | Eastern Cape | DALAGUBA JUNIOR SECONDARY SCHOOL | 200400099 | King Sabata Dalindyebo | Construction 51% - 75% | Active - Contracted | 2019-10-11 | 2022-08-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2427229 | 2427229 | Education Infrastructure Grant | Upgrading and Additions
|  | 190181 | P9010930_ | Eastern Cape | NGQWARA JUNIOR SECONDARY SCHOOL | 200300441 | Amahlathi | Construction 76% - 99% | Active - Contracted | 2019-10-11 | 2019-10-14 | 2023-03-31 | 2024-03-31 | 2025-03-31 | 0 | 2491706 | 2491706 | Education Infrastructure Grant | Upgrading and Additions
|  | 190240 | DPWRT/SAN/284/20/MP | Mpumalanga | Manyano Primary School | 80012385 | Steve Tshwete | Practical Completion (100%) | Active - Contracted | 2020-07-01 |  | 2024-09-28 |  |  | 40918 | 292277 | 333195 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190252 | P9010976 | Eastern Cape | NQABA PRIMARY SCHOOL | 200100591 | Raymond Mhlaba | Tender | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 4631268 | 4631268 | Education Infrastructure Grant | Upgrading and Additions
|  | 190266 | P9005788 | Eastern Cape | ALHEIT VAN DER MERWE PRIMARY SCHOOL | 200600011 | Walter Sisulu | Design | Approved | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 900000 | 900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190267 | P9010636 | Eastern Cape | LUSIKISIKI VILLAGE JUNIOR SECONDARY SCHOOL | 200500475 | Ingquza Hill | Design | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 10586388 | 10586388 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190269 | P0001590_ | Eastern Cape | XOLOBENI JUNIOR SECONDARY SCHOOL | 200501296 | Mbizana | Design | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 3949314 | 3949314 | Education Infrastructure Grant | Upgrading and Additions
|  | 190272 | MDOE/MAIN/16/21-22 | Mpumalanga | Ramodiegi Primary School | 800019075 | Dr JS Moroka | Design | Active - Not Contracted | 2022-04-30 |  | 2024-03-31 |  |  | 35675 | 1469355 | 1505030 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190284 | DPWRT/MAIN/066/19/MP | Mpumalanga | Soshangane Secondary School | 800022186 | Nkomazi | Project Initiation | Proposed | 2020-05-31 |  | 2023-10-27 |  |  | 357332 | 5873321 | 6230653 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190320 | MDOE//MAIN/113 | Mpumalanga | Dwarsloop Circuit | n/a | Bushbuckridge | Project Initiation | Proposed | 2021-04-01 |  | 2024-12-15 |  |  | 10989 | 109887 | 120876 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190330 | DoE/GERT/MAIN/114 | Mpumalanga | Ngilandi Secondary School | 800016758 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190334 | MDOE/MAIN/01/21-22 | Mpumalanga | Chief Jerry Secondary School | 800002071 | Chief Albert Luthuli | Project Initiation | Proposed | 2021-04-01 |  | 2025-03-31 |  |  | 338851 | 2420365 | 2759216 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190365 | P9010515_ | Eastern Cape | QHOBOSHENDLINI SENIOR PRIMARY SCHOOL | 200400943 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 2136855 | 2136855 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190366 | P9006378a | Eastern Cape | CEDARBERG PRIMARY SCHOOL | 200100110 | Nelson Mandela Bay | Feasibility | Approved | 2020-04-01 |  | 2024-03-31 |  |  | 0 | 2826557 | 2826557 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190432 | P9010468 | Eastern Cape | MANDLUNTSHA JUNIOR SECONDARY SCHOOL | 200300278 | Buffalo City | Construction 51% - 75% | Active - Contracted | 2018-03-20 | 2018-03-22 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3509806 | 3509806 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190563 | DB/500136641/SDS | KwaZulu-Natal | ENGQONDWENI HIGH SCHOOL | 500136641 | Alfred Duma | Construction 51% - 75% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2023-11-30 | 2023-05-05 | 2025-06-20 | 1600702 | 7292087 | 8892789 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190574 | P9011565 | Eastern Cape | MODULAR CLASSROOOMS | 200999925 | Buffalo City | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2025-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 66300000 | 66300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190579 | P9006986_ | Eastern Cape | PELANDABA JUNIOR SECONDARY SCHOOL | 200600661 | Senqu | Practical Completion (100%) | Active - Contracted | 2018-04-01 | 2018-05-30 | 2024-03-31 | 2021-07-20 | 2024-03-31 | 0 | 4346689 | 4346689 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190581 | P9010680 | Eastern Cape | SIBONILE SENIOR SECONDARY SCHOOL | 200600738 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2018-04-01 | 2018-07-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 1873613 | 1873613 | Education Infrastructure Grant | Upgrading and Additions
|  | 190582 | P9007263_ | Eastern Cape | MCHENI JUNIOR PRIMARY SCHOOL | 200400551 | Mhlontlo | Construction 76% - 99% | Active - Contracted | 2020-03-30 | 2022-03-30 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1100000 | 9576185 | 10676185 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190611 | P9005221_ | Eastern Cape | LOYISO SENIOR SECONDARY SCHOOL | 200500438 | Umzimvubu | Practical Completion (100%) | Approved | 2014-03-30 | 2014-05-10 | 2026-03-31 | 2022-07-20 | 2024-07-20 | 92621 | 595273 | 687894 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190613 | P9005339_ | Eastern Cape | NOMAHEYA JUNIOR SECONDARY SCHOOL | 200300475 | Mnquma | Final Completion | Approved | 2014-03-19 | 2015-05-20 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 150000 | 883224 | 1033224 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190647 | LE20IDT09001 | Limpopo | Bale Primary School | 929310302 | Musina | Tender | Active - Not Contracted | 2019-04-01 |  | 2024-03-31 |  |  | 120000 | 480000 | 600000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190649 | LE06LDOE0002 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-12-31 | 2025-03-31 | 2025-03-31 | 0 | 20000000 | 20000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190653 | W/500325452/LSEN | KwaZulu-Natal | TONGAAT SCHOOL FOR LSEN | 500325452 | eThekwini | Construction 26% - 50% | Active - Contracted | 2019-05-10 | 2019-09-12 | 2023-06-30 | 2024-05-05 | 2025-01-31 | 37670165 | 171608528 | 209278693 | Education Infrastructure Grant | Upgrading and Additions
|  | 190654 | W/500429089/LSEN | KwaZulu-Natal | VULEKANI LSEN SCHOOL | 500429089 | Umzimkhulu | Final Completion | Active - Contracted | 2019-05-10 | 2020-12-01 | 2022-12-31 | 2025-03-31 | 2025-06-01 | 6304308 | 28719624 | 35023932 | Education Infrastructure Grant | Upgrading and Additions
|  | 190655 | W/500499463/NS | KwaZulu-Natal | SIBONGINHLANHLA PRIMARY SCHOOL | 500499463 | eThekwini | Tender | Active - Contracted | 2019-05-10 |  | 2025-06-30 |  |  | 6355620 | 28953380 | 35309000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190656 | W/500236097/RRR | KwaZulu-Natal | NORTH CREST PRIMARY SCHOOL | 500236097 | eThekwini | Tender | Active - Not Contracted | 2019-05-10 |  | 2026-03-31 |  |  | 504000 | 2296000 | 2800000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190660 | DB/500327302/SDS | KwaZulu-Natal | BENJOBE PRIMARY SCHOOL | 500327302 | Jozini | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190662 | DB/500109594/SDS | KwaZulu-Natal | BHILIYA PRIMARY SCHOOL | 500109594 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-12 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190681 | LE20IDT00001 | Limpopo | RIVONI SCHOOL FOR THE BLIND | 929332041 | Makhado | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-04-01 | 2024-05-31 | 2025-03-31 | 2025-03-31 | 40000000 | 160000000 | 200000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190682 | LE20IDT06001 | Limpopo | Mhinga Special School | 911361675 | Collins Chabane | Tender | Active - Not Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 30000000 | 120000000 | 150000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190685 | DB/500414363/SDS | KwaZulu-Natal | DUMAPHANSI SECONDARY SCHOOL | 500414363 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190687 | 600100694 | North West | KGOSI SHOPE GET BAND | GET BAND 002 | Ratlou | Tender | Active - Contracted | 2010-04-01 |  | 2026-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190691 | NEW BOIKHUTSO 001 | North West | NEW BOIKHUSO PRIMARY SCHOOL | BOIKHUTSO 001 | Ditsobotla | Feasibility | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 50000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190692 | DB/500125467/LSEN | KwaZulu-Natal | DURBAN SCHOOL FOR THE HEARING IMPAIRED | 500125467 | eThekwini | Design | Active - Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 1500000 | 2000000 | 3500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190704 | LE20TMT17068 | Limpopo | Phalaborwa Primary | 913420543 | Ba-Phalaborwa | Construction 51% - 75% | Active - Contracted | 2018-02-03 | 2018-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 6074902 | 6074902 | Education Infrastructure Grant | Upgrading and Additions
|  | 190707 | NEW KOSTER 001 | North West | NEW KOSTER SECONDARY SCHOOL | KOSTER 001 | Kgetlengrivier | Construction 26% - 50% | Active - Contracted | 2020-04-01 | 2021-09-16 | 2026-03-10 | 2025-03-10 | 2026-03-31 | 12294814 | 69678851 | 81973665 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190717 | PHAKISANG PRIMARY001 | North West | PHAKISANG PRIMARY SCHOOL | PHAKISANG001 | Ditsobotla | Feasibility | Active - Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 50000000 | 50000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190719 | GAMALOKA PRIMARY SCHOOL | North West | RAMADINGOANA PRIMARY SCHOOL | RAMADINGOANA | Tswaing | Feasibility | Active - Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 60000000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190720 | DB/500497872/SDS | KwaZulu-Natal | EHAWINI HIGH SCHOOL | 500497872 | Nkandla | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 650000 | 2200000 | 2850000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190736 | DB/500129759/SDS | KwaZulu-Natal | ELORA PRIMARY SCHOOL | 500129759 | eThekwini | Design | Active - Not Contracted | 2018-01-01 |  | 2023-03-30 |  |  | 1414107 | 6442041 | 7856148 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190756 | DORA ALLOCATION_ 2021/22 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-30 |  |  | 0 | 139548210 | 139548210 | Education Infrastructure Grant | Non-Infrastructure
|  | 190757 | W/500136789/SDS | KwaZulu-Natal | ENGWENI PRIMARY SCHOOL | 500136789 | uMhlathuze | Feasibility | Active - Contracted | 2018-01-01 |  | 2023-08-30 |  |  | 807840 | 3680160 | 4488000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190758 | EF001 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Project Initiation | Proposed | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Non-Infrastructure
|  | 190759 | DB/500140119/SDS | KwaZulu-Natal | ESIBONISWENI PRIMARY SCHOOL | 500140119 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190760 | W/500287046/RRR | KwaZulu-Natal | UMBOGINTWINI PRIMARY SCHOOL | 500287046 | eThekwini | Feasibility | Active - Not Contracted | 2019-05-10 |  | 2023-06-30 |  |  | 550000 | 1900000 | 2450000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190762 | W/500284234/UA | KwaZulu-Natal | TONGAAT PRIMARY SCHOOL | 500284234 | eThekwini | Project Initiation | Active - Not Contracted | 2019-05-10 |  | 2023-06-30 |  |  | 35910000 | 2500000 | 38410000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190770 | EQ-1/20/1 | Free State | INVENT:SCHL SPRT&RECR | EQ -1/20/1 | Mangaung | Project Initiation | Approved | 2019-05-01 |  | 2026-03-31 |  |  | 5000000 | 0 | 5000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 190786 | P9010481_ | Eastern Cape | NONYEMBEZI JUNIOR SECONDARY SCHOOL | 200300813 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2018-04-06 | 2018-04-08 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 4899123 | 4899123 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190787 | P9010478 | Eastern Cape | KULO-MBOMBO SENIOR PRIMARY SCHOOL | 200300191 | Buffalo City | Construction 26% - 50% | Active - Contracted | 2018-03-20 | 2018-03-22 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 2864358 | 2864358 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190789 | P9010462 | Eastern Cape | BOMELA SENIOR SECONDARY SCHOOL | 200300028 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5563225 | 5563225 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190791 | W/500140341/SDS | KwaZulu-Natal | ESIGAGANENI PRIMARY SCHOOL | 500140341 | Nkandla | Feasibility | Active - Contracted | 2018-01-01 |  | 2023-09-01 |  |  | 812880 | 3703120 | 4516000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190792 | DB/500143042/SDS | KwaZulu-Natal | EZAKHENI HIGH SCHOOL | 500143042 | Alfred Duma | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190793 | DB/500146742/SDS | KwaZulu-Natal | GAJU SECONDARY SCHOOL | 500146742 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190794 | DB/500152070/UA | KwaZulu-Natal | GROENVLEI COMBINED SCHOOL | 500152070 | Emadlangeni | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 300559 | 1369213 | 1669772 | Education Infrastructure Grant | Upgrading and Additions
|  | 190796 | DB/500156769/SDS | KwaZulu-Natal | HLELINGOMUSO PRIMARY SCHOOL | 500156769 | The Msunduzi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190800 | W/500494911/SDS | KwaZulu-Natal | INHLOSENHLE SECONDARY SCHOOL | 500495911 | Nkandla | Feasibility | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 48600 | 221400 | 270000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190811 | 600100443 | North West | GOAKGANYA PRIMARY SCHOOL | GOAKGANYA 001 | Local Municipality of Madibeng | Tender | Active - Contracted | 2019-11-01 |  | 2025-03-30 |  |  | 0 | 20000000 | 20000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190812 | DB/500170274/ECD | KwaZulu-Natal | IXOPO VILLAGE INTERMEDIATE SCHOOL | 500170274 | Ubuhlebezwe | Design | Active - Not Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 700000 | 2200000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190814 | DB/500174603/SDS | KwaZulu-Natal | KHOFI PRIMARY SCHOOL | 500174603 | Umhlabuyalingana | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190815 | DB/500182632/SDS | KwaZulu-Natal | KWANSELE PRIMARY SCHOOL | 500182632 | Nongoma | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190817 | DB/500194361/UA | KwaZulu-Natal | MAKHAPHA COMBINED SCHOOL | 500194361 | eThekwini | Design | Active - Contracted | 2018-01-01 |  | 2023-03-01 |  |  | 2885848 | 9643152 | 12529000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190820 | DB/500220890/SDS | KwaZulu-Natal | MUTHIDLWE PRIMARY SCHOOL | 500220890 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190822 | DB/500220927/SDS | KwaZulu-Natal | MUZIKAWUTHANDWA HIGH SCHOOL | 500220927 | uMshwathi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190826 | DB/500232989/SDS | KwaZulu-Natal | NKUNGUMATHE PRIMARY SCHOOL | 500232989 | Nkandla | Design | Active - Contracted | 2018-01-01 |  | 2024-03-30 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190836 | DB/500286195/ECD | KwaZulu-Natal | UFASIMBA PRIMARY SCHOOL | 500286195 | uMhlathuze | Design | Active - Contracted | 2018-01-01 |  | 2024-03-01 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 190838 | DB/500287971/ECD | KwaZulu-Natal | UMKHUKHUZE PRIMARY SCHOOL | 500287971 | uMlalazi | Design | Active - Contracted | 2018-01-01 |  | 2024-03-27 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 190839 | DB/500290191/ECD | KwaZulu-Natal | UPPER MHLATHUZE PRIMARY SCHOOL | 500290191 | Nkandla | Project Initiation | Active - Contracted | 2018-01-01 |  | 2027-04-12 |  |  | 320850 | 1461650 | 1782500 | Education Infrastructure Grant | Upgrading and Additions
|  | 190840 | DB/500444888/SDS | KwaZulu-Natal | VEZUKUKHANYA JUNIOR PRIMARY SCHOOL | 500444888 | eThekwini | Design | Active - Contracted | 2018-01-01 |  | 2024-03-29 |  |  | 724500 | 3300500 | 4025000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 190852 | P9010436_ | Eastern Cape | KAMBI PRIMARY SCHOOL | 200400315 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2019-09-29 | 2019-09-30 | 2024-03-31 | 2024-03-31 | 2025-03-01 | 185699 | 1092347 | 1278046 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190853 | P9010494 | Eastern Cape | SOBUZA PRIMARY JUNIOR SCHOOL | 200401018 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6694557 | 6694557 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190855 | P9010527_ | Eastern Cape | NGANGENYATI JUNIOR SECONDARY SCHOOL | 200400733 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2018-03-20 | 2018-03-22 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3703000 | 3703000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190856 | P9010493_ | Eastern Cape | SENTUBE PRIMARY SCHOOL | 200400987 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2018-10-04 | 2018-10-05 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4212897 | 4212897 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190857 | P9010472 | Eastern Cape | MBOYA PRIMARY SCHOOL | 200300310 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 2207740 | 2207740 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190858 | P9010601 | Eastern Cape | NCAMBELE JUNIOR SECONDARY SCHOOL | 200400705 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3041945 | 137000 | 3178945 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190859 | P9010516 | Eastern Cape | MANZABILA SENIOR PRIMARY SCHOOL | 200400485 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1573088 | 686108 | 2259196 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190860 | P9010596 | Eastern Cape | UPPER GQUMASHE PRIMARY SCHOOL | 200200878 | Raymond Mhlaba | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1665450 | 1665450 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190861 | P9010511 | Eastern Cape | MYOLWA PRIMARY SCHOOL | 200404035 | King Sabata Dalindyebo | Design | Active - Contracted | 2018-03-20 |  | 2026-03-31 |  |  | 0 | 4000000 | 4000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190872 | W/500325489/WS | KwaZulu-Natal | SIBONGINHLANHLA SECONDARY SCHOOL | 500325489 | Ndwedwe | Tender | Active - Not Contracted | 2019-05-10 |  | 2026-07-31 |  |  | 300818 | 1561182 | 1862000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190873 | W/500323639/WS | KwaZulu-Natal | SINENHLANHLA SECONDARY SCHOOL | 500323639 | Maphumulo | Construction 76% - 99% | Active - Contracted | 2019-05-10 | 2023-06-01 | 2023-06-30 | 2023-06-30 | 2024-06-01 | 1347720 | 6139613 | 7487333 | Education Infrastructure Grant | Upgrading and Additions
|  | 190874 | W/500270100/WS | KwaZulu-Natal | SIYAPHAMBILI SECONDARY SCHOOL | 500270100 | uMuziwabantu | Tender | Active - Contracted | 2019-05-10 |  | 2025-04-15 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190900 | P9010440_ | Eastern Cape | MKHOMANZI JUNIOR PRIMARY SCHOOL | 200500694 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 464525 | 2732502 | 3197027 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190924 | EDDP184/126 | Limpopo | EDDP184/126 | 921111436 | Lephalale | Tender | Active - Not Contracted | 2014-04-01 |  | 2024-03-31 |  |  | 2261000 | 9045000 | 11306000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190927 | ST013/2022-23 | Northern Cape | HO?RSKOOL WARRENTON | 300017403 | Magareng | Pre - Feasibility | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 700000 | 700000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190940 | MDOE/NEW//19-20/010(DPWRT/020/19/MP) | Mpumalanga | Osizweni Primary School | 800012617 | Govan Mbeki | Design | Active - Contracted | 2020-04-01 |  | 2024-12-15 |  |  | 7318268 | 40657043 | 47975311 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190941 | MDOE/NEW/19-20/011(TBC) | Mpumalanga | Osizweni Secondary School | 800012617 | Govan Mbeki | Design | Active - Not Contracted | 2021-04-01 |  | 2027-02-15 |  |  | 8526238 | 47367988 | 55894226 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 190943 | MDOE/UPG/010/20-21 | Mpumalanga | Tholukwazi Primary School | 800023259 | Govan Mbeki | Design | Active - Not Contracted | 2020-04-01 |  | 2024-04-26 |  |  | 2081587 | 15380616 | 17462203 | Education Infrastructure Grant | Upgrading and Additions
|  | 190944 | MDOE/UPG/1006/20-21 | Mpumalanga | The Gem Combined School | 800023028 | Msukaligwa | Design | Active - Not Contracted | 2022-01-28 |  | 2024-05-31 |  |  | 1854121 | 13243722 | 15097843 | Education Infrastructure Grant | Upgrading and Additions
|  | 190945 | MDOE/UPG/1008/20-21 | Mpumalanga | Zamokuhle Primary School | 800025825 | Govan Mbeki | Design | Active - Not Contracted | 2022-04-01 |  | 2024-05-31 |  |  | 1327880 | 9484856 | 10812736 | Education Infrastructure Grant | Upgrading and Additions
|  | 190947 | MDOE/UPG/1021/20-21(DPWRT/SAN/206/20/MP) | Mpumalanga | Sithuthukile Secondary School | 800021402 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2021-01-15 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 463305 | 1477634 | 1940939 | Education Infrastructure Grant | Upgrading and Additions
|  | 190948 | MDOE/UPG/1022/20-21(DPWRT/SAN/188/20/MP) | Mpumalanga | Khuzulwandle Secondary School | 800006262 | Chief Albert Luthuli | Tender | Proposed | 2020-04-01 |  | 2023-03-31 |  |  | 263889 | 1884919 | 2148808 | Education Infrastructure Grant | Upgrading and Additions
|  | 190949 | W/500237577/SDS | KwaZulu-Natal | NQUNDU COMBINED SCHOOL | 500237577 | uMhlathuze | Design | Active - Not Contracted | 2019-05-10 |  | 2024-03-31 |  |  | 720000 | 3280000 | 4000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 190950 | W/500248418/WS | KwaZulu-Natal | PHESHE PRIMARY SCHOOL | 500248418 | uMhlathuze | Practical Completion (100%) | Active - Contracted | 2018-03-31 | 2019-12-01 | 2023-05-31 | 2023-05-05 | 2023-08-01 | 1247000 | 5680000 | 6927000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190952 | MDOE/UPG/1029/20-21(DPWRT/SAN/221/20MP) | Mpumalanga | Bethamoya Primary School | 800008821 | Dr Pixley Ka Isaka Seme | Project Initiation | Proposed | 2021-05-01 |  | 2023-05-15 |  |  | 298818 | 2134415 | 2433233 | Education Infrastructure Grant | Upgrading and Additions
|  | 190957 | MDOE/SAN/032/2020(DPWRT/SAN/185/20MP) | Mpumalanga | Mhola Primary School | 800014258 | Chief Albert Luthuli | Construction 76% - 99% | Proposed | 2021-04-01 |  | 2022-06-16 |  |  | 264600 | 1350000 | 1614600 | Education Infrastructure Grant | Upgrading and Additions
|  | 190959 | MDOE/SAN/050/2020( DPWRT/SAN/207/20/MP ) | Mpumalanga | Delfkom Primary School | 800002410 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2021-10-15 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 259601 | 1854296 | 2113897 | Education Infrastructure Grant | Upgrading and Additions
|  | 190960 | MDOE/SAN/051/2020( DPWRT/SAN/208/20/MP ) | Mpumalanga | Diposi Primary School | 800002634 | Mkhondo | Tender | Proposed | 2020-04-01 |  | 2023-10-16 |  |  | 198809 | 1420063 | 1618872 | Education Infrastructure Grant | Upgrading and Additions
|  | 190961 | MDOE/SAN/052/2020( DPWRT/SAN/198/20/MP ) | Mpumalanga | Emdibini Combined School | 800003541 | Govan Mbeki | Design | Proposed | 2020-04-01 |  | 2023-06-16 |  |  | 275876 | 1970545 | 2246421 | Education Infrastructure Grant | Upgrading and Additions
|  | 190966 | MDOE/SAN/054/2020(DPWRT/SAN/199/20/MP) | Mpumalanga | Funduqhubeka Primary School | 800004358 | Msukaligwa | Design | Proposed | 2021-04-01 |  | 2023-06-16 |  |  | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190972 | MDOE/SAN/055/2020(DPWRT/SAN/203/20MP ) | Mpumalanga | Grootboom Primary School | 800004820 | Chief Albert Luthuli | Design | Active - Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 138600 | 990000 | 1128600 | Education Infrastructure Grant | Upgrading and Additions
|  | 190984 | MDOE/SAN/057/2020(DPWRT/SAN/204/20/MP) | Mpumalanga | Lubhaqa Primary School | 800010744 | Chief Albert Luthuli | Design | Active - Contracted | 2020-04-01 |  | 2022-08-31 |  |  | 75600 | 540000 | 615600 | Education Infrastructure Grant | Upgrading and Additions
|  | 190985 | MDOE/SAN/058/2020(DPWRT/SAN/186/20/MP) | Mpumalanga | Siyeta Primary School | 800021618 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2021-05-01 | 2021-10-15 | 2023-06-16 | 2023-06-16 | 2023-06-16 | 289800 | 2070000 | 2359800 | Education Infrastructure Grant | Upgrading and Additions
|  | 190990 | MDOE/SAN/173/2020(DPWRT/SAN/196/20/MP) | Mpumalanga | Ntababomvu Primary School | 800017269 | Chief Albert Luthuli | Design | Active - Not Contracted | 2021-04-01 |  | 2023-10-01 |  |  | 163800 | 1170000 | 1333800 | Equitable Share | Upgrading and Additions
|  | 190991 | MDOE/SAN/174/2020( DPWRT/SAN/212/20/MP ) | Mpumalanga | Moolman Primary School | 800015149 | Mkhondo | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2021-02-23 | 2022-05-02 | 2021-12-23 | 2022-12-23 | 338406 | 2417188 | 2755594 | Equitable Share | Upgrading and Additions
|  | 190992 | MDOE/SAN/175/2020 | Mpumalanga | Azalia Combined School | 800000398 | Lekwa | Design | Active - Not Contracted | 2021-04-01 |  | 2023-10-01 |  |  | 152320 | 1088000 | 1240320 | Education Infrastructure Grant | Upgrading and Additions
|  | 190994 | MDOE/SAN/178/2020(DPWRT/SAN/219/20MP) | Mpumalanga | Sanqotho Primary School | 800019877 | Dr Pixley Ka Isaka Seme | Design | Proposed | 2021-04-01 |  | 2023-10-01 |  |  | 189000 | 1350000 | 1539000 | Education Infrastructure Grant | Upgrading and Additions
|  | 190995 | MDOE/SAN/249/2020(DPWRT/SAN/217/20/MP) | Mpumalanga | Umfudlana Combined School | 800024265 | Msukaligwa | Design | Active - Not Contracted | 2021-04-01 |  | 2023-10-01 |  |  | 189000 | 1350000 | 1539000 | Equitable Share | Upgrading and Additions
|  | 190996 | MDOE/SAN/250/2020(DPWRT/SAN/181/20/MP) | Mpumalanga | Vulandlela Primary School | 800024935 | Mkhondo | Construction 51% - 75% | Active - Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 336805 | 2405748 | 2742553 | Education Infrastructure Grant | Upgrading and Additions
|  | 190999 | BBB329-2022 | Northern Cape | PHAKANE SECONDARY SCHOOL | 300101617 | Renosterberg | Construction 1% - 25% | Approved | 2020-04-22 |  | 2023-12-31 |  |  | 1985002 | 9042789 | 11027791 | Education Infrastructure Grant | Upgrading and Additions
|  | 191000 | BBB208/2020 | Northern Cape | MOOKI-LOBELO PRIMARY SCHOOL | 300101371 | Phokwane | Practical Completion (100%) | Approved | 2020-04-24 |  | 2023-03-31 |  |  | 3997384 | 15572199 | 19569583 | Education Infrastructure Grant | Upgrading and Additions
|  | 191003 | A-526128_FENCING | Northern Cape | HOMEVALE HIGH SCHOOL | 300012402 | Sol Plaatjie | Practical Completion (100%) | Approved | 2022-02-01 | 2022-02-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 2272038 | 2272038 | Education Infrastructure Grant | Upgrading and Additions
|  | 191010 | W/500327746/WS | KwaZulu-Natal | NTABABUSUKU SECONDARY SCHOOL | 500327746 | Ulundi | Tender | Active - Contracted | 2019-05-10 |  | 2023-04-01 |  |  | 2075073 | 2530577 | 4605650 | Education Infrastructure Grant | Upgrading and Additions
|  | 191011 | W/500285973/SDS | KwaZulu-Natal | UBUMBANO PRIMARY SCHOOL | 500285973 | Nongoma | Design | Active - Not Contracted | 2019-05-10 |  | 2023-12-31 |  |  | 486180 | 2214820 | 2701000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191012 | EDDP184/391B | Limpopo | MANGOAKO SECONDARY SCHOOL | 919341053 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2019-04-01 | 2019-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 1473000 | 5892000 | 7365000 | Education Infrastructure Grant | Upgrading and Additions
|  | 191014 | W/500343693/WS | KwaZulu-Natal | SIYATHUTHUKA PRIMARY SCHOOL | 500343693 | Newcastle | Tender | Active - Not Contracted | 2019-05-10 |  | 2023-06-01 |  |  | 1089000 | 4961000 | 6050000 | Education Infrastructure Grant | Upgrading and Additions
|  | 191015 | W/500289673/SDS | KwaZulu-Natal | UMZOKHANYAYO PRIMARY SCHOOL | 500289673 | uMuziwabantu | Tender | Active - Contracted | 2019-05-10 |  | 2025-06-30 |  |  | 2001439 | 9117667 | 11119106 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191037 | BBB326-2022_CLASSROOM BLOCK | Northern Cape | LUTZBURG (SSKV) INTERMEDI?RE SKOOL | 300043218 | Kai !Garib | Construction 51% - 75% | Active - Contracted | 2022-03-01 | 2022-03-03 | 2025-03-31 | 2025-04-01 | 2025-05-01 | 0 | 3763972 | 3763972 | Education Infrastructure Grant | Upgrading and Additions
|  | 191068 | REMEDIAL WORK:STRUCTURAL ASSESSMENT | Northern Cape | VAN ZYLSRUS INTERMEDI?RE SKOOL | 300045213 | Joe Morolong | Feasibility | Approved | 2022-07-12 |  | 2023-03-31 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191147 | P9011574 | Eastern Cape | DOE SPECIAL SCHOOL MAINTENANCE | 200999925 | Buffalo City | Design | Approved | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 55000000 | 55000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191183 | LE19DPW00056 | Limpopo | Mamolobela Secondary | 925620541 | Greater Tubatse/Fetakgomo | Construction 1% - 25% | Active - Contracted | 2018-02-03 | 2018-04-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1200000 | 6000000 | 7200000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 191184 | LE19DPW00080 | Limpopo | Mokgoko Primary | 925643186 | Makhuduthamaga | Construction 1% - 25% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2025-03-30 | 2024-03-30 | 2024-03-31 | 600000 | 6000000 | 6600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191213 | P9010522 | Eastern Cape | MANGQUKWANA JUNIOR SECONDARY SCHOOL | 200400482 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-03-20 |  | 2025-03-31 |  |  | 0 | 4891934 | 4891934 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191236 | P9010598 | Eastern Cape | MATSHONGWE PRIMARY SCHOOL | 200400512 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-30 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 10918212 | 10918212 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191269 | TBD:NEW SCHOOL-RIETVALE/HS | Northern Cape | RIETVALE HIGH SCHOOL | TBD | Sol Plaatjie | Feasibility | Approved | 2021-04-01 |  | 2025-03-31 |  |  | 9751102 | 70000000 | 79751102 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 191327 | CONDITIONAL ASSESSEMENTS | Northern Cape | CONDITIONAL ASSESSMENTS | N/A | Sol Plaatjie | Project Initiation | Active - Not Contracted | 2022-03-01 |  | 2025-03-31 |  |  | 0 | 33420000 | 33420000 | Education Infrastructure Grant | Non-Infrastructure
|  | 191329 | ST053/2022-23 | Northern Cape | GAKGATSANA PRIMARY SCHOOL | 300100395 | Joe Morolong | Design | Active - Not Contracted | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 1471166 | 1471166 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191332 | TBD:CONVERSION TO FLUSH TOILETS | Northern Cape | MATSHANENG INTERMEDIATE SCHOOL | 300101163 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191344 | TBD:ERADICATION/CONVERSION | Northern Cape | NORAP MET PRIM?RE SKOOL | 300034207 | Khi-Ma | Feasibility | Approved | 2022-07-20 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191347 | ST366/2021 | Northern Cape | OREEDITSE PRIMARY SCHOOL | 300101579 | Joe Morolong | Project Initiation | Active - Not Contracted | 2023-04-01 |  | 2024-03-30 |  |  | 0 | 453515 | 453515 | Education Infrastructure Grant | Upgrading and Additions
|  | 191350 | ST369/2021 | Northern Cape | SEUPE PRIMARY SCHOOL | 300101985 | Ga-Segonyana | Project Initiation | Active - Not Contracted | 2023-04-01 |  | 2024-03-30 |  |  | 0 | 288102 | 288102 | Education Infrastructure Grant | Upgrading and Additions
|  | 191354 | FURNITURE_ALL SCHOOLS | Northern Cape | FURNITURE | N/A | Sol Plaatjie | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 | 2021-02-26 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 971058 | 17192906 | 18163964 | Education Infrastructure Grant | Non-Infrastructure
|  | 191369 | DRPW/TBD | Northern Cape | GAOSHUPE MAKODI PRIMARY SCHOOL | 300100415 | Phokwane | Feasibility | Approved | 2020-10-01 |  | 2023-03-31 |  |  | 381472 | 8000000 | 8381472 | Education Infrastructure Grant | Upgrading and Additions
|  | 191448 | LE19LDE00002 | Limpopo | MAGATLE CIRCUIT (2) | 912143000 | Lepele-Nkumpi | Site Handed - Over to Contractor | Active - Not Contracted | 2018-03-01 | 2019-03-31 | 2024-03-31 | 2024-02-10 | 2025-03-31 | 24000 | 96000 | 120000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191473 | P9006669_ | Eastern Cape | ESINYAMENI SENIOR PRIMARY SCHOOL | 200500216 | Mbizana | Practical Completion (100%) | Active - Contracted | 2018-04-10 | 2018-04-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 229977 | 229977 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191476 | P0004412_ | Eastern Cape | MAKAULA SENIOR SECONDARY SCHOOL | 200500534 | Umzimvubu | Practical Completion (100%) | Approved | 2013-01-23 | 2013-01-28 | 2024-03-31 | 2024-03-31 | 2026-03-31 | 0 | 10301282 | 10301282 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191478 | P9007296_ | Eastern Cape | MANDELA SCHOOL OF SCIENCE AND TECHNOLOGY | 200400285 | King Sabata Dalindyebo | Final Completion | Approved | 2017-11-25 | 2017-11-29 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1015748 | 1015748 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191479 | P9010482 | Eastern Cape | MENTE JUNIOR SECONDARY SCHOOL | 200300848 | Mnquma | Practical Completion (100%) | Active - Contracted | 2018-03-20 | 2018-03-27 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 5994740 | 5994740 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191482 | LEASES:2020/21 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 300100101 | Sol Plaatjie | Construction 1% - 25% | Approved | 2020-04-01 | 2020-04-03 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 0 | 18000000 | 18000000 | Education Infrastructure Grant | Infrastructure Leases
|  | 191488 | P9010437 | Eastern Cape | MPAKO JUNIOR SECONDARY SCHOOL | 200400636 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2019-09-28 | 2019-09-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 2778000 | 2778000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191491 | P9006786. | Eastern Cape | NGUBESIZWE SENIOR SECONDARY SCHOOL | 200400773 | Engcobo | Practical Completion (100%) | Approved | 2018-04-13 | 2018-04-18 | 2022-04-30 | 2022-04-30 | 2022-04-30 | 0 | 221237 | 221237 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191493 | P9006789_ | Eastern Cape | NTSHILINI SENIOR SECONDARY SCHOOL | 200401329 | Nyandeni | Practical Completion (100%) | Approved | 2018-02-20 | 2018-02-24 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 209062 | 209062 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191494 | P9010438 | Eastern Cape | NXELE JUNIOR SECONDARY SCHOOL | 200400889 | King Sabata Dalindyebo | Practical Completion (100%) | Active - Contracted | 2015-04-01 | 2019-09-30 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 439359 | 2584468 | 3023827 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191501 | P9010425 | Eastern Cape | VINISH JUNIOR SECONDARY SCHOOL | 200401117 | Nyandeni | Practical Completion (100%) | Active - Contracted | 2018-03-01 | 2018-04-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 4411246 | 4411246 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191502 | P9010518 | Eastern Cape | VUKANDLULE JUNIOR SECONDARY SCHOOL | 200401120 | Port St Johns | Practical Completion (100%) | Active - Contracted | 2018-03-31 | 2022-02-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4789271 | 4789271 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191506 | P9010931_ | Eastern Cape | ZANEWONGA SENIOR SECONDARY SCHOOL | 200300677 | Mnquma | Practical Completion (100%) | Approved | 2019-10-11 | 2019-10-15 | 2023-07-20 | 2023-07-20 | 2023-07-20 | 0 | 648653 | 648653 | Education Infrastructure Grant | Upgrading and Additions
|  | 191510 | P0001839 | Eastern Cape | SIVE SPECIAL SCHOOL (PHASE II) | 200501449 | Matatiele | Feasibility | Approved | 2019-12-12 |  | 2023-03-30 |  |  | 0 | 118946211 | 118946211 | Education Infrastructure Grant | Maintenance and Repairs
|  | 191587 | LDPW-B/08173 | Limpopo | MUSWODI PRIMARY SCHOOL | 929310035 | Musina | Final Completion | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-30 | 646000 | 2586000 | 3232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 191610 | MDOE/NEW/19-20/005(2) | Mpumalanga | Phulani Secondary School | 800035209 | Bushbuckridge | Tender | Active - Contracted | 2020-09-01 |  | 2025-03-31 |  |  | 3150650 | 26255415 | 29406065 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 191690 | LE18DBS08002 | Limpopo | HUMULA HIGH SCHOOL | 911361774 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2303000 | 9213000 | 11516000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191691 | LE20IDT09020 | Limpopo | MKHACHANI MZAMANI PRIMARY | 915530013 | Collins Chabane | Site Handed - Over to Contractor | Active - Not Contracted | 2019-01-02 | 2019-04-01 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 1860000 | 7440000 | 9300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 191692 | LE20IDT09030 | Limpopo | Sunduza Primary | 911360344 | Collins Chabane | Site Handed - Over to Contractor | Active - Not Contracted | 2019-01-02 | 2019-04-01 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 3860000 | 15440000 | 19300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 191701 | LE18DBS04001 | Limpopo | BEGWA TSHITUMBE PRIMARY SCHOOL | 930360498 | Thulamela | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2016-03-31 | 2021-03-31 | 1672000 | 6686000 | 8358000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191702 | LE18DBS01004 | Limpopo | MASHIGOANA PRIMARY SCHOOL | 921230449 | Lepele-Nkumpi | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 3393897 | 13575590 | 16969487 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191704 | LE18DBS02004 | Limpopo | KHETO - NXUMALO AGRICULTURAL HIGH SCHOOL | 916410379 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 2029000 | 8116000 | 10145000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191705 | LE18DBS02005 | Limpopo | MALEBALONG PRIMARY SCHOOL | 926540829 | Maruleng | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 1929000 | 7714000 | 9643000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191707 | LE18DBS02008 | Limpopo | TIRHANI PRIMARY SCHOOL | 911411105 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2016-03-31 | 2021-03-31 | 2209000 | 8834000 | 11043000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191709 | LE18DBS08009 | Limpopo | NWARIDI SECONDARY SCHOOL | 916321868 | Makhado | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 2419000 | 9674000 | 12093000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191711 | LE18DBS02001 | Limpopo | BEREA PRIMARY SCHOOL | 912521491 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1320437 | 5281750 | 6602187 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191714 | LE18DBS08008 | Limpopo | MUVIMBI PRIMARY SCHOOL | 931520757 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2024-03-31 | 1786000 | 7145000 | 8931000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191719 | LE19TMT16113 | Limpopo | Nkoshilo Secondary | 923241122 | Polokwane | Site Handed - Over to Contractor | Active - Contracted | 2019-01-02 | 2019-04-01 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 65553 | 262212 | 327765 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 191727 | LE18DBS02002 | Limpopo | DUMAZI HIGH SCHOOL | 916410096 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2016-03-31 | 2024-04-30 | 1750000 | 7002000 | 8752000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191728 | LE18DBS02007 | Limpopo | MOLATE HIGH SCHOOL | 918521354 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1324000 | 5297000 | 6621000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191731 | LE18DBS02003 | Limpopo | Khethapoye Primary School | 918510163 | Greater Tzaneen | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 1318000 | 5273000 | 6591000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191737 | LE18DBS08010 | Limpopo | SAMBANDOU PRIMARY SCHOOL | 929310820 | Thulamela | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 77816 | 311265 | 389081 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191738 | LE18DBS08006 | Limpopo | Mavhina Primary School | 930321325 | Makhado | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1357000 | 5430000 | 6787000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191739 | LE18DBS08001 | Limpopo | FRANK MUKHASWAKULE PRIMARY SCHOOL | 916321431 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1521000 | 6085000 | 7606000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191742 | LE18DBS08004 | Limpopo | Lupedze primary School | 930321400 | Polokwane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1208000 | 4834000 | 6042000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191743 | LE18DBS08007 | Limpopo | MPHAGANE PRIMARY SCHOOL | 930321349 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1311000 | 5245000 | 6556000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191747 | LE18DBS08005 | Limpopo | MASHAA PRIMARY SCHOOL | 930321332 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1028000 | 4111000 | 5139000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191749 | LE18DBS07005 | Limpopo | SEBILOANE PRIMARY SCHOOL | 921121358 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 2873000 | 11491000 | 14364000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191751 | LE18DBS08003 | Limpopo | JOHANNES RAMAVHOYA HIGH SCHOOL | 911361895 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 778000 | 3112000 | 3890000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191758 | LE18DBS07006 | Limpopo | TETEMA SECONDARY SECONDARY | 921121464 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1393000 | 5574000 | 6967000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191763 | LE18DBS07003 | Limpopo | RABASOTHO PRIMARY SCHOOL | 921142027 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 1488000 | 5952000 | 7440000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191767 | LE18DBS07004 | Limpopo | RAPHELA PRIMARY SCHOOL | 921121334 | Mogalakwena | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 1359000 | 5438000 | 6797000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191805 | EDDP184/370A | Limpopo | SEGOLOLA SECONDARY | 924650733 | Elias Motsoaledi | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-30 | 2023-03-30 | 2023-03-31 | 1118000 | 4473000 | 5591000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 191811 | EDDP184/335R | Limpopo | Ritlhavile Secondary | 916410980 | Greater Giyani | Construction 76% - 99% | Active - Contracted | 2014-04-01 | 2014-04-02 | 2024-03-30 | 2024-03-30 | 2025-03-31 | 5044818 | 35765247 | 40810065 | Education Infrastructure Grant | Upgrading and Additions
|  | 191910 | LE6HRCOE2223 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Other - Compensation of Employees | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-03-30 | 2030-03-30 | 2030-03-31 | 0 | 21323000 | 21323000 | Education Infrastructure Grant | Non-Infrastructure
|  | 191911 | LE6HRGAS2223 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Other - Compensation of Employees | Active - Not Contracted | 2020-04-01 | 2020-04-06 | 2030-03-30 | 2030-03-30 | 2030-03-31 | 0 | 28603884 | 28603884 | Education Infrastructure Grant | Non-Infrastructure
|  | 191913 | DPWRT/SAN/283/20/MP (MKHUHLU PR)--------- | Mpumalanga | Mkhuhlu Township Secondary School | new | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-06-01 |  | 2025-03-31 |  |  | 6588532 | 36602954 | 43191486 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 191917 | LE18DBS02009 | Limpopo | Zava Secondary | 917420789 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2014-04-01 | 2014-04-02 | 2023-03-31 | 2022-03-30 | 2022-03-31 | 1499000 | 5995000 | 7494000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 192092 | (3/20/21) | Free State | MANGAUNG ARTISAN SCHOOL | (3/20/21) | Mangaung | Project Initiation | Active - Not Contracted | 2020-03-31 |  | 2026-03-31 |  |  | 0 | 45000000 | 45000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 192831 | DPWRT/336/19/MP (ANIVA P)---------------- | Mpumalanga | Aniva (Boschfontein) Primary School | new | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2024-05-01 |  |  | 6363086 | 35350480 | 41713566 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192837 | MDOE/NEW/20-21/002(s) | Mpumalanga | Sidlamafa Secondary School | 800020834 | Nkomazi | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 5267441 | 37624576 | 42892017 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192844 | LE19DPW00045 | Limpopo | Matlerekeng Primary School | 996606807 | Ephraim Mogale | Feasibility | Active - Contracted | 2020-08-01 |  | 2025-11-30 |  |  | 287000 | 1148000 | 1435000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 192849 | LE19DPW00084 | Limpopo | Seboeng Primary School | 925661177 | Makhuduthamaga | Design | Active - Contracted | 2020-08-01 |  | 2025-03-31 |  |  | 6560965 | 26243859 | 32804824 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 192863 | DPWRT/169/17MP | Mpumalanga | Chayaza Secondary School | 800035091 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-06-15 |  | 2025-03-31 |  |  | 6134212 | 34078954 | 40213166 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192876 | LE23MON00001 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-03-31 | 2024-03-31 | 2025-03-31 | 0 | 273249600 | 273249600 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192887 | MDOE/NEW/20-21/001 | Mpumalanga | Makgahlishe Primary School | 800034916 | Bushbuckridge | Tender | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 4051150 | 28936788 | 32987938 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192937 | MDOE/UPG/004/20-21 | Mpumalanga | Hlangalezwe Primary School | 800034992 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2025-12-31 |  |  | 638713 | 4562234 | 5200947 | Education Infrastructure Grant | Upgrading and Additions
|  | 192940 | DPWRT/041/19/MP | Mpumalanga | Magwagwaza Secondary School | 800034971 | Bushbuckridge | Terminated | Active - Not Contracted | 2020-04-01 | 2020-10-12 | 2024-04-25 | 2021-01-28 | 2021-06-30 | 3187484 | 14440433 | 17627917 | Education Infrastructure Grant | Upgrading and Additions
|  | 192941 | DPWRT/046/19/MP | Mpumalanga | Saselani Primary School | MDOE/MAIN/044/20-21 | Bushbuckridge | Tender | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 3775182 | 17321858 | 21097040 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 192946 | MDOE/UPG/004/20-21__ | Mpumalanga | Hlangelezwe Primary School | 800034992 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-04-30 |  |  | 1916398 | 13688554 | 15604952 | Education Infrastructure Grant | Upgrading and Additions
|  | 192947 | MDOE/MAIN/07/22-23 | Mpumalanga | Lydenburg Primary School | 800017764 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-04-15 |  |  | 1066763 | 7619738 | 8686501 | Education Infrastructure Grant | Maintenance and Repairs
|  | 192948 | MDOE/SAN/230/2020 | Mpumalanga | Kaapvallei Primary School | 800007203 | Mbombela | Design | Active - Not Contracted | 2020-07-01 |  | 2022-12-28 |  |  | 189000 | 1350000 | 1539000 | Equitable Share | Upgrading and Additions
|  | 192951 | DPWRT/SAN/005/22MP(LOTI PRIM)------------ | Mpumalanga | Loti Primary School | 800010694 | Nkomazi | Design | Active - Not Contracted | 2020-04-01 |  | 2023-06-16 |  |  | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 192953 | MDOE/SAN/1033/2020 | Mpumalanga | Bambanani primary school | 800000521 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2025-08-01 |  |  | 315000 | 2250000 | 2565000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 192956 | DPWRT/SAN/020/21MP(KHANYISANI SE--------- | Mpumalanga | Khanyisani Secondary School | 800007633 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2022-10-01 |  |  | 100800 | 720000 | 820800 | Education Infrastructure Grant | Upgrading and Additions
|  | 192958 | DPWRT/SAN/323/20/MP | Mpumalanga | Sikhutsele Primary School | 800029702 | Mbombela | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 545582 | 3897015 | 4442597 | Education Infrastructure Grant | Upgrading and Additions
|  | 192961 | DPWRT/SAN/002/22MP MASIHAMBISANE--------- | Mpumalanga | Masihambisane Combined School | 800012971 | Mbombela | Design | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 126000 | 900000 | 1026000 | Education Infrastructure Grant | Upgrading and Additions
|  | 192969 | MDOE/SAN/1034/2020 (5) | Mpumalanga | Bonginhlanhla Secondary School | 800001404 | Mbombela | Design | Proposed | 2020-04-01 |  | 2025-05-16 |  |  | 21000 | 150000 | 171000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 192971 | MDOE/UPG/1010/20-21 | Mpumalanga | Pilgrims Rest Primary School | 800017947 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2022-04-15 |  |  | 1004080 | 7172000 | 8176080 | Education Infrastructure Grant | Upgrading and Additions
|  | 192976 | DPWRT/MAIN/088/20/MP | Mpumalanga | Sizimisele Primary School | 800021741 | Nkomazi | Design | Proposed | 2020-04-01 |  | 2023-10-16 |  |  | 210000 | 1500000 | 1710000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193019 | MDOE/UPG/012/19-20(DPWRT/064/19/MP) | Mpumalanga | Ethembeni Primary School | 800004010 | Dr Pixley Ka Isaka Seme | Design | Active - Contracted | 2019-09-01 |  | 2023-12-30 |  |  | 561073 | 4007665 | 4568738 | Education Infrastructure Grant | Upgrading and Additions
|  | 193040 | MDOE/MAIN/068/22 | Mpumalanga | Mathule Primary School | 800035128 | Bushbuckridge | Tender | Active - Not Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 40246 | 402455 | 442701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193057 | MDOE/SAN/128/2020 | Mpumalanga | Sedibeng Primary School | 800035142 | Bushbuckridge | Terminated | Proposed | 2021-05-01 |  | 2024-11-01 |  |  | 147460 | 1055428 | 1202888 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193061 | DPWRT/SAN/030/20/MP | Mpumalanga | Dlumana Secondary School | 800035022 | Bushbuckridge | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2020-10-08 | 2022-09-15 | 2021-01-22 | 2024-03-31 | 214000 | 1530000 | 1744000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193064 | MDOE/SAN/1027/2020(DPWRT/SAN/182/20/MP) | Mpumalanga | Amanzi Primary School | 800000166 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-11-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 245239 | 1751709 | 1996948 | Education Infrastructure Grant | Upgrading and Additions
|  | 193081 | DOEMPUR022 | Mpumalanga | Vanstaden Dam Primary School | 800024547 | Govan Mbeki | Site Handed - Over to Contractor | Proposed | 2020-04-01 | 2021-01-26 | 2023-05-16 | 2023-07-28 | 2023-07-28 | 138600 | 990000 | 1128600 | Education Infrastructure Grant | Upgrading and Additions
|  | 193083 | MDOE/SAN/0010/2020(DOEMPUR017) | Mpumalanga | Thjakastad Secondary School | 800023630 | Chief Albert Luthuli | Design | Proposed | 2021-05-01 |  | 2022-05-16 |  |  | 138600 | 990000 | 1128600 | Education Infrastructure Grant | Upgrading and Additions
|  | 193092 | MDOE/SAN/1057/2020 | Mpumalanga | Phumula Primary School | 800018416 | Msukaligwa | Design | Proposed | 2021-06-01 |  | 2022-09-15 |  |  | 239400 | 1710000 | 1949400 | Education Infrastructure Grant | Upgrading and Additions
|  | 193094 | MDOE/SAN/1056/2020 | Mpumalanga | Salem Combined School | 800019752 | Mkhondo | Design | Proposed | 2021-05-01 |  | 2022-09-15 |  |  | 176400 | 1260000 | 1436400 | Education Infrastructure Grant | Upgrading and Additions
|  | 193097 | DPWRT/SAN/328/20MP ZITHOBE--------------- | Mpumalanga | Zithobe Primary School | 800026005 | Chief Albert Luthuli | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 240000 | 1440000 | 1680000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193099 | DPWRT/SAN/029/20MP(MATIKINYA PRI--------- | Mpumalanga | Matikinya Primary School | 800035033 | Bushbuckridge | Practical Completion (100%) | Active - Contracted | 2020-07-01 |  | 2022-09-15 |  |  | 315000 | 2250000 | 2565000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193109 | DPWRT/SAN/001/21/MP | Mpumalanga | Phatshedi Primary School | 800034874 | Bushbuckridge | Construction 76% - 99% | Active - Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 126000 | 1233773 | 1359773 | Education Infrastructure Grant | Upgrading and Additions
|  | 193123 | MDOE/SAN/1034/2020 (1) | Mpumalanga | Mkhweyantaba Primary School | 800034947 | Bushbuckridge | Design | Active - Not Contracted | 2020-06-01 |  | 2022-09-15 |  |  | 21000 | 150000 | 171000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193135 | MDOE/MAIN/08/22-23 | Mpumalanga | Mahuvo Secondary School | 800035160 | Bushbuckridge | Construction 76% - 99% | Active - Contracted | 2020-09-01 | 2022-05-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 241724 | 1726602 | 1968326 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193149 | DPWRT/SAN/044/20/MP | Mpumalanga | Lehlasedi High School | 800035125 | Bushbuckridge | Design | Active - Not Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 121641 | 188769 | 310410 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193155 | DPWRT/SAN/052/20/MP | Mpumalanga | Dyondzekani Primary School | 800035184 | Bushbuckridge | Design | Active - Not Contracted | 2020-07-01 |  | 2025-12-30 |  |  | 216065 | 1200360 | 1416425 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193168 | MDOE/SAN/0276/2020 | Mpumalanga | Rhandzekile Primary School | 800035210 | Bushbuckridge | Project Initiation | Active - Contracted | 2020-07-01 |  | 2025-09-15 |  |  | 900084 | 9000840 | 9900924 | Education Infrastructure Grant | Upgrading and Additions
|  | 193376 | I/WATER TANKA/COVID-19 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2019-05-02 |  | 2023-03-30 |  |  | 0 | 67872000 | 67872000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193378 | I/CHEMICAL TOILETS/COVID-19 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2020-06-02 |  | 2023-10-03 |  |  | 0 | 100880000 | 100880000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193558 | GDE00064 | Gauteng | Eersterus Secondary School | 700220020 | City of Tshwane | Pre - Feasibility | Approved | 2020-08-14 |  | 2026-01-09 |  |  | 3360000 | 13440000 | 16800000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193559 | GDE00088 | Gauteng | Gillview secondary school (Winchester HillS) | N/A | City of Johannesburg | Project Initiation | Approved | 2020-08-14 |  | 2026-03-13 |  |  | 3980000 | 19320000 | 23300000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193567 | GDE00237 | Gauteng | MONTIC FACTORY PRIMARY SCHOOL | 700340950 | City of Ekurhuleni | Feasibility | Approved | 2019-07-12 |  | 2026-03-13 |  |  | 9500000 | 50500000 | 60000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193575 | GDE00429 | Gauteng | Windmill Park Secondary School | 700400139 | City of Ekurhuleni | Project Initiation | Approved | 2019-04-01 |  | 2026-03-13 |  |  | 9500000 | 5156000 | 14656000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193597 | CONVERSION:_FLUSH TOILETS | Northern Cape | GARAPOWANA PRIMARY SCHOOL | 300100418 | Joe Morolong | Feasibility | Active - Not Contracted | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193602 | TBD:NEW SCHOOL-KATHU OFF-SHOOT | Northern Cape | LAERSKOOL KATHU | TBD | Gamagara | Project Initiation | Approved | 2021-04-01 |  | 2025-03-31 |  |  | 16599739 | 60000000 | 76599739 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193604 | UPGRADE OF SEWERAGE SYSTEM | Northern Cape | GREENPOINT HIGH SCHOOL | 300016403 | Sol Plaatjie | Feasibility | Approved | 2022-06-20 |  | 2024-03-29 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193607 | GDE00303 | Gauteng | Reiger Park No.2 Secondary School | 700160069 | City of Ekurhuleni | Project Initiation | Approved | 2019-12-09 |  | 2025-06-13 |  |  | 1000000 | 8921000 | 9921000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193608 | TBD_ ASSMANG PRIMARY SCHOOL | Northern Cape | ASSMANG PRIMARY SCHOOL | 300044202 | Tsantsabane | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-09-30 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193627 | TBD:STRUCTURAL | Northern Cape | BONGANI PRIMARY SCHOOL | 300011301 | Siyancuma | Project Initiation | Proposed | 2022-01-28 |  | 2024-03-29 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193633 | ST009/2022-23 | Northern Cape | VUYOLWETHU SECONDARY SCHOOL | 300012404 | Sol Plaatjie | Project Initiation | Proposed | 2022-05-04 |  | 2023-03-31 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193640 | IK NKOANE:TBD | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 300010101 | Sol Plaatjie | Tender | Active - Not Contracted | 2020-05-04 |  | 2023-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193641 | ISJX030/2019 | Northern Cape | Kimberley | TBD | Sol Plaatjie | Tender | Active - Not Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 19818240 | 50000000 | 69818240 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193648 | ST305-2021_ELECTRICITY | Northern Cape | DR EP LEKHELA HIGH SCHOOL | 300015406 | Sol Plaatjie | Construction 76% - 99% | Active - Contracted | 2020-05-25 | 2020-06-05 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 661480 | 661480 | Education Infrastructure Grant | Upgrading and Additions
|  | 193650 | MAINTENANCE_ELECTRICITY_FENCE&ROOF | Northern Cape | OKIEP HOER SKOOL | 300034309 | Nama Khoi | Project Initiation | Approved | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 1500001 | 1500001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193653 | TBD_ ELIZABETH | Northern Cape | ELIZABETH CONRADIE SPECIAL SCHOOL | 300010706 | Sol Plaatjie | Feasibility | Active - Not Contracted | 2022-05-05 |  | 2022-10-27 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193656 | ST287/2021 | Northern Cape | KGABANG PRIMARY SCHOOL | 300014302 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-09-09 |  | 2023-03-03 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193657 | REPAIRS AND RENOVATIONS | Northern Cape | REEBONE INTERMEDIATE SCHOOL | 300100774 | Joe Morolong | Project Initiation | Approved | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 800000 | 800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193660 | ST271/2021:MAINTENANCE TO ROOF | Northern Cape | REKGARATLHILE HIGH SCHOOL | 300101821 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 78208 | 78208 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193662 | CONVERSION_TOILETS | Northern Cape | MCTAGGARTSKAMP PRIMARY SCHOOL | 300042212 | Kai !Garib | Feasibility | Active - Not Contracted | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193666 | ST026/2022-23:CONVERSION &ERADICATION | Northern Cape | LERUMO PRIMARY SCHOOL | 300100869 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193670 | MAINTENANCE TO SCHOOL HALL ROOF | Northern Cape | PRIESKA PRIMARY SCHOOL | 300022302 | Siyathemba | Feasibility | Approved | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 590000 | 590000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193673 | TBD 15 | Northern Cape | FERDINAND BRECHER PRIMARY SCHOOL | 300031205 | Nama Khoi | Feasibility | Active - Not Contracted | 2022-08-12 |  | 2023-03-31 |  |  | 0 | 1500001 | 1500001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193682 | ST327/2021 | Northern Cape | THABANE HIGH SCHOOL | 300012403 | Sol Plaatjie | Construction 76% - 99% | Active - Contracted | 2022-04-01 | 2022-04-03 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 0 | 1062598 | 1062598 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193684 | ST426/2022 | Northern Cape | RENEILWE PRIMARY SCHOOL | 300014207 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 589828 | 589828 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193686 | CONVERSION_FLUSH_TOILETS | Northern Cape | WILGENHOUDTSDRIF PRIMARY SCHOOL | 300043216 | !Kheis | Feasibility | Approved | 2021-03-31 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193702 | CONVERSION_FLUSH TOILETS | Northern Cape | LETLHAKAJANENG PRIMARY SCHOOL | 300100890 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193705 | TBD:DEBEN P/S | Northern Cape | DEBEN PRIMERE SCHOOL | 300044203 | Gamagara | Feasibility | Approved | 2020-04-01 |  | 2025-03-31 |  |  | 6599739 | 70000000 | 76599739 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 193772 | ST325/2021:R&R_ROOF_WATER RETICULATION | Northern Cape | STAATS PRIMARY SCHOOL | 300013209 | Sol Plaatjie | Design | Active - Contracted | 2022-04-01 | 2022-04-18 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193773 | ST357-2021_ | Northern Cape | STRYDENBURG COMBINED SCHOOL | 300022307 | Thembelihle | Construction 26% - 50% | Active - Contracted | 2022-02-18 | 2022-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193784 | DoE/Boh/MAIN/162 | Mpumalanga | Mavimbela Primary School | 800035104 | Bushbuckridge | Project Initiation | Active - Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 9875 | 98745 | 108620 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193801 | COVID_WATER_TBD 28 | Northern Cape | ITSHOKENG PRIMARY SCHOOL | 300100575 | Joe Morolong | Design | Active - Not Contracted | 2022-03-02 | 2022-03-30 | 2022-10-31 | 2022-11-30 | 2022-12-30 | 0 | 939552 | 939552 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193806 | MDOE/MAIN/60/21-22 | Mpumalanga | Mpumelelo Primary School | 800015727 | Nkomazi | Construction 1% - 25% | Active - Contracted | 2021-04-01 | 2021-06-19 | 2022-05-31 | 2022-03-31 | 2024-03-31 | 102442 | 2307841 | 2410283 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193827 | MDOE/MAIN/091/22 | Mpumalanga | Mzila Secondary School | 800034839 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 21141 | 211414 | 232555 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193828 | MDOE/MAIN/89/21-22 | Mpumalanga | Mzimba primary School | 800035167 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 154779 | 1547787 | 1702566 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193846 | ST429/2022:SCHOOL & HOSTEL | Northern Cape | VICTORIA WES INTERMEDIATE SCHOOL | 300024307 | Ubuntu | Tender | Active - Not Contracted | 2022-06-30 |  | 2025-03-31 |  |  | 0 | 7031773 | 7031773 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193852 | TBD:REPAIRS TO WATER INFRASTRUCTURE | Northern Cape | VORSTER EILAND PRIMARY SCHOOL | 300042220 | Kai !Garib | Project Initiation | Approved | 2022-04-07 |  | 2023-03-31 |  |  | 0 | 400000 | 400000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193854 | ST014/2022-23 | Northern Cape | HO?RSKOOL WARRENTON | 300017403 | Magareng | Project Initiation | Proposed | 2022-05-05 |  | 2022-11-30 |  |  | 0 | 400000 | 400000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193861 | MDOE/MAIN/039/22 | Mpumalanga | Pitas Primary School | 800028571 | Thaba Chweu | Project Initiation | Active - Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 8957 | 204697 | 213654 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193863 | DoE/Boh/MAIN/107 | Mpumalanga | Qcetswayo Primary School | 800034844 | Bushbuckridge | Project Initiation | Active - Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 36989 | 406878 | 443867 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193879 | COVID_MAINTENANCE_ST235/2020 | Northern Cape | VOORSPOED PRIMARY SCHOOL | 300012208 | Phokwane | Site Handed - Over to Contractor | Active - Contracted | 2022-02-18 | 2022-04-05 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 90220 | 90220 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193933 | ST342/2021 | Northern Cape | LANGBERG HIGH SCHOOL | 300044302 | Gamagara | Tender | Approved | 2022-05-05 |  | 2022-11-30 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193941 | TBD:R&R SCHOOL INFRASTRUCTURE | Northern Cape | MAIKAELELO INTERMEDIATE SCHOOL | 300044303 | Joe Morolong | Tender | Active - Not Contracted | 2022-08-05 |  | 2024-03-31 |  |  | 0 | 1200000 | 1200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 193950 | DOE/MOBILE CLASSROOMS/COVID-19 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2020-06-02 |  | 2023-03-30 |  |  | 0 | 200000000 | 200000000 | Equitable Share | Upgrading and Additions
|  | 193951 | C/MOBILE CLASSROOMS/COVID-19 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2020-06-02 |  | 2023-03-30 |  |  | 0 | 100000000 | 100000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 193954 | I/Disludging/Covid-19 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2020-06-02 |  | 2023-03-30 |  |  | 0 | 245000000 | 245000000 | Equitable Share | Maintenance and Repairs
|  | 194088 | TBD_ELECTRICAL UPGRADES | Northern Cape | IKHWEZI LOKUSA PRIMARY SCHOOL | 300023280 | Tsantsabane | Pre - Feasibility | Proposed | 2022-06-09 |  | 2022-12-30 |  |  | 0 | 3065298 | 3065298 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194092 | FENCING8 | Northern Cape | REAKANTSWE SECONDARY SCHOOL | 300012304 | Dikgatlong | Pre - Feasibility | Active - Not Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 2500000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194099 | TBD_R&R_HOSTEL | Northern Cape | VAN ZYLSRUS INTERMEDI?RE SKOOL | 300045213 | Joe Morolong | Feasibility | Approved | 2022-10-02 |  | 2023-03-31 |  |  | 0 | 4796900 | 4796900 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194100 | ST339/2021 | Northern Cape | STEINKOPF SEKONDERE SKOOL | 300031403 | Nama Khoi | Construction 1% - 25% | Approved | 2022-02-28 | 2022-03-02 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 8334256 | 8334256 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194101 | ST401/2021&ST417/2022 | Northern Cape | SC KEARNS | 300043306 | Dawid Kruiper | Construction 26% - 50% | Approved | 2020-04-01 |  | 2023-03-30 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194105 | R&R_TBD6 | Northern Cape | HOERSKOOL RICHMOND | 300024303 | Ubuntu | Project Initiation | Approved | 2022-03-31 |  | 2025-03-31 |  |  | 0 | 2104253 | 2104253 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194106 | MAINTENANCE:CO-FUNDING | Northern Cape | HOERSKOOL BOESMANLAND | 300001030 | Khi-Ma | Project Initiation | Approved | 2022-08-05 |  | 2025-03-30 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194107 | TBD_ LANDBOU | Northern Cape | HOER LANDBOUSKOOL NOORD-KAAPLAND | 300012601 | Phokwane | Project Initiation | Approved | 2022-06-14 |  | 2022-10-28 |  |  | 0 | 650000 | 650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194108 | TBD_ DELPORTSHOOP | Northern Cape | DELPORTSHOOP GEKOMBINEERDE SKOOL | 300011304 | Dikgatlong | Project Initiation | Approved | 2022-07-07 |  | 2023-01-12 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194109 | ST346/2021 | Northern Cape | DEBEN PRIMERE SKOOL | 300044203 | Gamagara | Project Initiation | Approved | 2022-05-06 |  | 2022-08-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194110 | TBD_ CARNARVON SECONDARY SCHOOL | Northern Cape | CARNAVON SECONDARY SCHOOL | 300024302 | Kareeberg | Project Initiation | Proposed | 2020-04-01 |  | 2023-04-30 |  |  | 0 | 836407 | 836407 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194113 | ISJX031-2020 REPLACEMENT SCHOOL | Northern Cape | PETRUSVILLE(NEW) PRIMARY SCHOOL | N/A | Renosterberg | Construction 1% - 25% | Approved | 2020-04-01 | 2021-10-26 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 9741867 | 72709732 | 82451599 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194114 | TBD:CLASSROOM BLOCK | Northern Cape | KIMBERLEY GIRLS HIGH SCHOOL | 300011403 | Sol Plaatjie | Feasibility | Approved | 2022-04-01 |  | 2024-03-31 |  |  | 848736 | 3000000 | 3848736 | Education Infrastructure Grant | Upgrading and Additions
|  | 194115 | BBB210/2020_ | Northern Cape | DL JANSEN PRIMARY SCHOOL | 300012302 | Dikgatlong | Practical Completion (100%) | Active - Not Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 4232874 | 16488409 | 20721283 | Education Infrastructure Grant | Upgrading and Additions
|  | 194122 | I/500448366/NS | KwaZulu-Natal | Ntikili High Scool | 500448366 | Jozini | Project Initiation | Active - Not Contracted | 2019-08-20 |  | 2024-03-31 |  |  | 6300000 | 35000000 | 41300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194141 | LE21DOE42204 | Limpopo | Matienyane Primary School | 925631480 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-31 | 2022-12-30 | 2023-03-31 | 424324 | 2357355 | 2781679 | Education Infrastructure Grant | Upgrading and Additions
|  | 194142 | LE21DOE08035 | Limpopo | Tshiluwi Primary | 928330688 | Makhado | Final Completion | Active - Contracted | 2019-04-01 | 2020-10-05 | 2022-12-31 | 2022-02-05 | 2023-06-05 | 435203 | 2417793 | 2852996 | Education Infrastructure Grant | Upgrading and Additions
|  | 194144 | LE21DOE28137 | Limpopo | Tshivhambe Primary School | 930320063 | Thulamela | Tender | Active - Not Contracted | 2020-01-04 |  | 2023-03-20 |  |  | 322185 | 1789914 | 2112099 | Education Infrastructure Grant | Upgrading and Additions
|  | 194145 | LE21DOE38187 | Limpopo | Matswake Secondary | 920210968 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 436748 | 2426379 | 2863127 | Education Infrastructure Grant | Upgrading and Additions
|  | 194146 | LE21DOE22103 | Limpopo | Matodzi Secondary School | 930321172 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-06-25 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 463058 | 2572546 | 3035604 | Education Infrastructure Grant | Upgrading and Additions
|  | 194148 | LE21DOE13058 | Limpopo | Ulando Combined School | 910131775 | Bela-Bela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 510734 | 2837412 | 3348146 | Education Infrastructure Grant | Upgrading and Additions
|  | 194149 | LE21DOE33161 | Limpopo | Nokotlou Secondary | 923261010 | Lepele-Nkumpi | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 464701 | 2581675 | 3046376 | Education Infrastructure Grant | Upgrading and Additions
|  | 194150 | LE21DOE17077 | Limpopo | Mamokgalake Primary School | 925630142 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 460940 | 2560775 | 3021715 | Education Infrastructure Grant | Upgrading and Additions
|  | 194151 | LE21DOE10043 | Limpopo | MAJE PRIMARY | 926540799 | Greater Tzaneen | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-12-30 | 2023-03-31 | 469535 | 2608525 | 3078060 | Education Infrastructure Grant | Upgrading and Additions
|  | 194152 | LE21DOE38186 | Limpopo | Mphokaneng Primary School | 920211244 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 452071 | 2511507 | 2963578 | Education Infrastructure Grant | Upgrading and Additions
|  | 194155 | LE21DOE20089 | Limpopo | Maolwe Primary | 918510422 | Greater Letaba | Construction 1% - 25% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 452917 | 2516207 | 2969124 | Education Infrastructure Grant | Upgrading and Additions
|  | 194157 | LE21DOE41198 | Limpopo | Tshikannoshi Secondary | 996606828 | Ephraim Mogale | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 411130 | 2284053 | 2695183 | Education Infrastructure Grant | Upgrading and Additions
|  | 194158 | LE21DOE16071 | Limpopo | LEGOLENG PRIMARY | 925620251 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-17 | 2027-05-27 | 2027-05-27 | 2027-05-27 | 469271 | 2607060 | 3076331 | Education Infrastructure Grant | Upgrading and Additions
|  | 194159 | LE21DOE24113 | Limpopo | Moleijane Primary | 924641838 | Makhuduthamaga | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 504964 | 2805358 | 3310322 | Education Infrastructure Grant | Upgrading and Additions
|  | 194160 | LE21DOE24112 | Limpopo | Kgopolo E Botse Primary | 924640439 | Ephraim Mogale | Construction 76% - 99% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 422114 | 2345078 | 2767192 | Education Infrastructure Grant | Upgrading and Additions
|  | 194161 | LE21DOE19085 | Limpopo | Tseke Primary | 925610421 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 441185 | 2451030 | 2892215 | Education Infrastructure Grant | Upgrading and Additions
|  | 194162 | LE21DOE27131 | Limpopo | Ximixoni Primary School | 929311250 | Musina | Construction 76% - 99% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 423611 | 2353397 | 2777008 | Education Infrastructure Grant | Upgrading and Additions
|  | 194163 | LE21DOE33162 | Limpopo | Morebela Kganyago Primary | 922221005 | Polokwane | Site Handed - Over to Contractor | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 490218 | 2723432 | 3213650 | Education Infrastructure Grant | Upgrading and Additions
|  | 194165 | LE21DOE28134 | Limpopo | Dididi Primary | 930350491 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 382561 | 2125339 | 2507900 | Education Infrastructure Grant | Upgrading and Additions
|  | 194166 | LE21DOE31147 | Limpopo | Mamolemane Secondary | 922220613 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-09-16 | 2020-09-17 | 2022-12-16 | 2023-12-16 | 2023-06-30 | 48623 | 270131 | 318754 | Education Infrastructure Grant | Upgrading and Additions
|  | 194168 | LE21DOE21098 | Limpopo | Scheiding Primary School | 923261164 | Lepele-Nkumpi | Construction 26% - 50% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 445676 | 2475976 | 2921652 | Education Infrastructure Grant | Upgrading and Additions
|  | 194169 | LE21DOE25121 | Limpopo | SEKGALABYANA SECONDARY SCHOOL | 926540530 | Maruleng | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 553674 | 3075967 | 3629641 | Education Infrastructure Grant | Upgrading and Additions
|  | 194170 | LE21DOE14064 | Limpopo | Matshiphe Combined School | 996606616 | Elias Motsoaledi | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 546167 | 3034258 | 3580425 | Education Infrastructure Grant | Upgrading and Additions
|  | 194171 | LE21DOE28136 | Limpopo | MAPATE PRIMARY SCHOOL | 930320124 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 434095 | 2411642 | 2845737 | Education Infrastructure Grant | Upgrading and Additions
|  | 194172 | LE21DOE43207 | Limpopo | Mhitlwa Primary School | 916420390 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 497586 | 2764367 | 3261953 | Education Infrastructure Grant | Upgrading and Additions
|  | 194173 | LE21DOE07030 | Limpopo | Nkatini Secondary | 911360863 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 523816 | 2910091 | 3433907 | Education Infrastructure Grant | Upgrading and Additions
|  | 194174 | LE21DOE04017 | Limpopo | Molalana Primary | 926541020 | Maruleng | Construction 1% - 25% | Active - Contracted | 2020-01-04 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 494634 | 2747965 | 3242599 | Education Infrastructure Grant | Upgrading and Additions
|  | 194175 | LE21DOE43209 | Limpopo | Magome Primary | 916410508 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 659925 | 2639700 | 3299625 | Education Infrastructure Grant | Upgrading and Additions
|  | 194176 | LE21DOE39188 | Limpopo | Mudzinga primary | 928331957 | Makhado | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 573159 | 3184217 | 3757376 | Education Infrastructure Grant | Upgrading and Additions
|  | 194178 | LE21DOE44211 | Limpopo | Khutsong Primary | 918510194 | Greater Letaba | Construction 76% - 99% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 332864 | 1849242 | 2182106 | Education Infrastructure Grant | Upgrading and Additions
|  | 194179 | LE21DOE12049 | Limpopo | Bordeaux Primary | 915540492 | Greater Tzaneen | Construction 51% - 75% | Active - Not Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 511639 | 2842441 | 3354080 | Education Infrastructure Grant | Upgrading and Additions
|  | 194181 | LE21DOE21093 | Limpopo | THAMAGANE PRIMARY SCHOOL | 923261317 | Lepele-Nkumpi | Construction 26% - 50% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 458512 | 2547292 | 3005804 | Education Infrastructure Grant | Upgrading and Additions
|  | 194182 | LE21DOE32155 | Limpopo | Poguti Maribula Primary | 923241184 | Polokwane | Construction 26% - 50% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 507549 | 2819715 | 3327264 | Education Infrastructure Grant | Upgrading and Additions
|  | 194183 | ISJX20/2020 | Northern Cape | CARLTON VAN HEERDEN SEKONDERE SKOOL | 300043401 | Dawid Kruiper | Design | Active - Not Contracted | 2020-07-01 |  | 2025-03-28 |  |  | 14836427 | 60581573 | 75418000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194184 | LE21DOE14066 | Limpopo | THEJANE SECONDARY SCHOOL | 996606630 | Elias Motsoaledi | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-04-30 | 535396 | 2974421 | 3509817 | Education Infrastructure Grant | Upgrading and Additions
|  | 194186 | LE21DOE39192 | Limpopo | Tshilongoni Secondary | 928330404 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 549173 | 3050959 | 3600132 | Education Infrastructure Grant | Upgrading and Additions
|  | 194187 | LE21DOE22099 | Limpopo | RALUTHAGA SENIOR PRIMARY | 930320414 | Makhado | Final Completion | Active - Contracted | 2019-04-01 | 2020-08-27 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 494365 | 2746470 | 3240835 | Education Infrastructure Grant | Upgrading and Additions
|  | 194188 | LE21DOE38184 | Limpopo | MALEBOHO SECONDARY SCHOOL | 920210630 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 475977 | 2644318 | 3120295 | Education Infrastructure Grant | Upgrading and Additions
|  | 194189 | LE21DOE03011 | Limpopo | KEDIKETSE PRIMARY SCHOOL | 924640378 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 680449 | 3780550 | 4460999 | Education Infrastructure Grant | Upgrading and Additions
|  | 194190 | LE21DOE39190 | Limpopo | Vhulaudzi Secondary | 928330930 | Makhado | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 303621 | 1686781 | 1990402 | Education Infrastructure Grant | Upgrading and Additions
|  | 194191 | LE21DOE20091 | Limpopo | MOKWASELE PRIMARY | 924320468 | Greater Letaba | Practical Completion (100%) | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 475940 | 2644113 | 3120053 | Education Infrastructure Grant | Upgrading and Additions
|  | 194192 | LE21DOE34164 | Limpopo | Mathibadifate Secondary | 919341077 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 415956 | 2310868 | 2726824 | Education Infrastructure Grant | Upgrading and Additions
|  | 194193 | LE21DOE40193 | Limpopo | MAKIKELA PRIMARY SCHOOL | 913420291 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 381524 | 2119577 | 2501101 | Education Infrastructure Grant | Upgrading and Additions
|  | 194194 | LE21DOE16074 | Limpopo | Rehlahleng Special School | 996606318 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2020-09-01 | 2020-09-02 | 2022-12-01 | 2023-12-01 | 2023-10-29 | 267769 | 1487609 | 1755378 | Education Infrastructure Grant | Upgrading and Additions
|  | 194196 | LE21DOE32154 | Limpopo | Mapeloana Secondary | 923240686 | Polokwane | Construction 51% - 75% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 295913 | 1643963 | 1939876 | Education Infrastructure Grant | Upgrading and Additions
|  | 194197 | LE21DOE09040 | Limpopo | Sara Primary | 918511319 | Greater Tzaneen | Tender | Active - Not Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 281684 | 1564911 | 1846595 | Education Infrastructure Grant | Upgrading and Additions
|  | 194198 | LE21DOE38183 | Limpopo | MAHLASE SECONDARY SCHOOL | 920210548 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 508724 | 2826247 | 3334971 | Education Infrastructure Grant | Upgrading and Additions
|  | 194199 | LE21DOE11047 | Limpopo | Mapheto Secondary | 915530181 | Greater Tzaneen | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 270347 | 1501926 | 1772273 | Education Infrastructure Grant | Upgrading and Additions
|  | 194200 | LE21DOE36173 | Limpopo | MAPALEDI PRIMARY SCHOOL | 919340463 | Modimolle/Mookgophong | Construction 76% - 99% | Active - Contracted | 2020-10-13 | 2020-10-14 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 638190 | 3545502 | 4183692 | Education Infrastructure Grant | Upgrading and Additions
|  | 194202 | LE21DOE22104 | Limpopo | Munwai Primary School | 930321387 | Makhado | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-08-27 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 311206 | 1728921 | 2040127 | Education Infrastructure Grant | Upgrading and Additions
|  | 194204 | LE21DOE25119 | Limpopo | Lekane Primary | 926540638 | Maruleng | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-01-30 | 2023-03-31 | 359968 | 1999824 | 2359792 | Education Infrastructure Grant | Upgrading and Additions
|  | 194205 | LE21DOE06027 | Limpopo | FEDILE SECONDARY SCHOOL | 919341114 | Modimolle/Mookgophong | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3234153 | 3234153 | Education Infrastructure Grant | Upgrading and Additions
|  | 194206 | LE21DOE39191 | Limpopo | Nnditsheni Secondary | 928330473 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 388369 | 2157607 | 2545976 | Education Infrastructure Grant | Upgrading and Additions
|  | 194207 | LE21DOE44215 | Limpopo | SIYANDANI PRIMARY | 916411044 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-12-30 | 2023-03-31 | 332864 | 1849242 | 2182106 | Education Infrastructure Grant | Upgrading and Additions
|  | 194209 | LE21DOE26124 | Limpopo | Gojela Secondary | 921120256 | Mogalakwena | Final Completion | Approved | 2020-08-04 | 2020-10-01 | 2023-03-31 | 2023-03-31 | 2022-03-31 | 301449 | 1674717 | 1976166 | Education Infrastructure Grant | Upgrading and Additions
|  | 194210 | LE21DOE32159 | Limpopo | TLOUKOLOBE PRIMARY SCHOOL | 904242309 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 560892 | 3116066 | 3676958 | Education Infrastructure Grant | Upgrading and Additions
|  | 194212 | LE21DOE15069 | Limpopo | Mohlahlane Primary | 921230368 | Ephraim Mogale | Construction 26% - 50% | Active - Contracted | 2020-08-25 | 2020-08-26 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 366331 | 3274151 | 3640482 | Education Infrastructure Grant | Upgrading and Additions
|  | 194213 | LE21DOE09041 | Limpopo | KHESETHWANE SECONDARY SCHOOL | 918510156 | Greater Letaba | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 508229 | 2823495 | 3331724 | Education Infrastructure Grant | Upgrading and Additions
|  | 194214 | LE21DOE17079 | Limpopo | S.M. Nkoana Primary | 924623704 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-01-04 |  | 2023-12-20 |  |  | 349505 | 1941694 | 2291199 | Education Infrastructure Grant | Upgrading and Additions
|  | 194216 | LE21DOE29139 | Limpopo | TSHIOMO PRIMARY SCHOOL | 929310813 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 609742 | 3387454 | 3997196 | Education Infrastructure Grant | Upgrading and Additions
|  | 194218 | LE21DOE21094 | Limpopo | Serutle Secondary | 921230733 | Lepele-Nkumpi | Construction 76% - 99% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 293530 | 1630722 | 1924252 | Education Infrastructure Grant | Upgrading and Additions
|  | 194219 | LE21DOE28133 | Limpopo | Ratshiedana Primary | 930321783 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 |  | 2023-12-20 |  |  | 315557 | 1753093 | 2068650 | Education Infrastructure Grant | Upgrading and Additions
|  | 194220 | LE21DOE34165 | Limpopo | Namatsabo Primary | 919341919 | Greater Letaba | Practical Completion (100%) | Active - Not Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 429051 | 2383614 | 2812665 | Education Infrastructure Grant | Upgrading and Additions
|  | 194222 | LE21DOE33160 | Limpopo | Magoshi Secondary | 922250461 | Molemole | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 480062 | 1920249 | 2400311 | Education Infrastructure Grant | Upgrading and Additions
|  | 194223 | LE21DOE36174 | Limpopo | MASWAHLANE PRIMARY SCHOOL | 919340876 | Modimolle/Mookgophong | Practical Completion (100%) | Active - Contracted | 2020-10-13 | 2020-10-14 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 475280 | 2640445 | 3115725 | Education Infrastructure Grant | Upgrading and Additions
|  | 194224 | LE21DOE22102 | Limpopo | Ratshikwekwete Secondary | 930321134 | Collins Chabane | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2020-06-25 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 366683 | 2037128 | 2403811 | Education Infrastructure Grant | Upgrading and Additions
|  | 194225 | LE21DOE10042 | Limpopo | Mahlane Secondary | 926540171 | Greater Tzaneen | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 370608 | 2058934 | 2429542 | Education Infrastructure Grant | Upgrading and Additions
|  | 194226 | LE21DOE38181 | Limpopo | Nakedi Secondary | 920211275 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 343671 | 1909282 | 2252953 | Education Infrastructure Grant | Upgrading and Additions
|  | 194227 | LE21DOE13060 | Limpopo | RASERITE HIGH | 921111443 | Lephalale | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 308971 | 1716503 | 2025474 | Education Infrastructure Grant | Upgrading and Additions
|  | 194228 | LE21DOE43210 | Limpopo | NYUMBANI SECONDARY SCHOOL | 916420529 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 570156 | 3176531 | 3746687 | Education Infrastructure Grant | Upgrading and Additions
|  | 194229 | LE21DOE01002 | Limpopo | Lenkwane Primary | 921140403 | Mogalakwena | Final Completion | Approved | 2020-08-17 | 2020-08-25 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 414741 | 2304119 | 2718860 | Education Infrastructure Grant | Upgrading and Additions
|  | 194230 | LE21DOE03012 | Limpopo | Mampana primary | 924641104 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 339002 | 1883347 | 2222349 | Education Infrastructure Grant | Upgrading and Additions
|  | 194231 | LE21DOE29141 | Limpopo | Khangale Secondary | 929310738 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 410686 | 2281591 | 2692277 | Education Infrastructure Grant | Upgrading and Additions
|  | 194234 | LE21DOE38185 | Limpopo | Maphutha Secondary | 904210821 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 561146 | 3117478 | 3678624 | Education Infrastructure Grant | Upgrading and Additions
|  | 194235 | LE21DOE03010 | Limpopo | Katang Primary | 924640316 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2023-11-30 | 2023-03-31 | 340045 | 1889141 | 2229186 | Education Infrastructure Grant | Upgrading and Additions
|  | 194237 | LE21DOE09039 | Limpopo | Fobeni Secondary | 918510811 | Greater Tzaneen | Tender | Active - Not Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 306573 | 1703185 | 2009758 | Education Infrastructure Grant | Upgrading and Additions
|  | 194238 | LE21DOE14061 | Limpopo | Rehlahlilwe Orimary | 996606527 | Elias Motsoaledi | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 395989 | 2199941 | 2595930 | Education Infrastructure Grant | Upgrading and Additions
|  | 194239 | LE21DOE16073 | Limpopo | Sekibidi Primary | 925621100 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2020-09-01 | 2020-09-02 | 2022-12-01 | 2023-12-01 | 2023-06-30 | 358540 | 1991891 | 2350431 | Education Infrastructure Grant | Upgrading and Additions
|  | 194240 | LE21DOE30145 | Limpopo | Funzwani Secondary | 930360535 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 362450 | 2013611 | 2376061 | Education Infrastructure Grant | Upgrading and Additions
|  | 194241 | LE21DOE19084 | Limpopo | Phutakwe Secondary | 925610223 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 417158 | 2317546 | 2734704 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194242 | LE21DOE29142 | Limpopo | Mubalanganyi Secondary | 929310684 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 440632 | 2447953 | 2888585 | Education Infrastructure Grant | Upgrading and Additions
|  | 194243 | LE21DOE30146 | Limpopo | Luphai Secondary | 902351487 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 391012 | 2172288 | 2563300 | Education Infrastructure Grant | Upgrading and Additions
|  | 194244 | LE21DOE41197 | Limpopo | Mabake Secondary | 996606812 | Ephraim Mogale | Construction 26% - 50% | Active - Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 362409 | 2013381 | 2375790 | Education Infrastructure Grant | Upgrading and Additions
|  | 194245 | LE21DOE08033 | Limpopo | KOKWANE PRIMARY SCHOOL | 928330640 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 | 2020-10-05 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 543014 | 3016747 | 3559761 | Education Infrastructure Grant | Upgrading and Additions
|  | 194246 | LE21DOE11048 | Limpopo | MAVELE PRIMARY SCHOOL | 915530761 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 519940 | 2888558 | 3408498 | Education Infrastructure Grant | Upgrading and Additions
|  | 194247 | LE21DOE35168 | Limpopo | LETHEBA SECONDARY SCHOOL | 919340685 | Polokwane | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 446355 | 2479748 | 2926103 | Education Infrastructure Grant | Upgrading and Additions
|  | 194248 | LE21DOE03014 | Limpopo | MOLWETSI SECONDARY SCHOOL | 924641913 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 522711 | 2903949 | 3426660 | Education Infrastructure Grant | Upgrading and Additions
|  | 194249 | LE21DOE31149 | Limpopo | NARE SECONDARY SCHOOL | 922221142 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-09-16 | 2020-09-17 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 551375 | 3063192 | 3614567 | Education Infrastructure Grant | Upgrading and Additions
|  | 194250 | LE21DOE32153 | Limpopo | MOKGOBA PRIMARY SCHOOL | 922220972 | Polokwane | Construction 51% - 75% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 585453 | 3252516 | 3837969 | Education Infrastructure Grant | Upgrading and Additions
|  | 194251 | LE21DOE42205 | Limpopo | PHAFANE SECONDARY SCHOOL | 925631589 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 523456 | 2908090 | 3431546 | Education Infrastructure Grant | Upgrading and Additions
|  | 194252 | LE21DOE31148 | Limpopo | MASEGELA PRIMARY SCHOOL | 922220682 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-09-16 | 2020-09-17 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 596203 | 3312240 | 3908443 | Education Infrastructure Grant | Upgrading and Additions
|  | 194253 | LE21DOE21095 | Limpopo | SEKURWANENG PRIMARY SCHOOL | 923261225 | Lepele-Nkumpi | Construction 26% - 50% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 520916 | 2893979 | 3414895 | Education Infrastructure Grant | Upgrading and Additions
|  | 194254 | LE21DOE38180 | Limpopo | MATHIPA MAKGATO SECONDARY SCHOOL | 920210913 | Blouberg | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 507546 | 2819701 | 3327247 | Education Infrastructure Grant | Upgrading and Additions
|  | 194255 | LE21DOE32156 | Limpopo | DIOPONG PRIMARY SCHOOL | 920235734 | Polokwane | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 601118 | 3339544 | 3940662 | Education Infrastructure Grant | Upgrading and Additions
|  | 194256 | LE21DOE19083 | Limpopo | MAEBE PRIMARY SCHOOL | 925610773 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3507910 | 3507910 | Education Infrastructure Grant | Upgrading and Additions
|  | 194257 | LE21DOE25120 | Limpopo | MOLALATLADI PRIMARY SCHOOL | 926541037 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-01-30 | 650241 | 3612449 | 4262690 | Education Infrastructure Grant | Upgrading and Additions
|  | 194258 | LE21DOE21096 | Limpopo | MAGATLE PRIMARY SCHOOL | 921230184 | Polokwane | Construction 26% - 50% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-01-30 | 546331 | 3035174 | 3581505 | Education Infrastructure Grant | Upgrading and Additions
|  | 194259 | LE21DOE09037 | Limpopo | KHOPO PRIMARY SCHOOL | 915531344 | Ba-Phalaborwa | Practical Completion (100%) | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 513378 | 2852101 | 3365479 | Education Infrastructure Grant | Upgrading and Additions
|  | 194260 | LE21DOE30144 | Limpopo | RATSHITANGA PRIMARY SCHOOL | 930351142 | Musina | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 595922 | 3310678 | 3906600 | Education Infrastructure Grant | Upgrading and Additions
|  | 194261 | LE21DOE17076 | Limpopo | MAROTA PRIMARY SCHOOL | 925620640 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 788748 | 4381934 | 5170682 | Education Infrastructure Grant | Upgrading and Additions
|  | 194262 | LE21DOE44213 | Limpopo | MOTLOBONI PRIMARY SCHOOL | 918512183 | Ba-Phalaborwa | Construction 76% - 99% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 614776 | 3415424 | 4030200 | Education Infrastructure Grant | Upgrading and Additions
|  | 194263 | LE21DOE13057 | Limpopo | MORAKOLO SECONDARY SCHOOL | 921110709 | Lephalale | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 529350 | 2940832 | 3470182 | Education Infrastructure Grant | Upgrading and Additions
|  | 194264 | DRPW016/2018 | Northern Cape | BAITIREDI TECH & COM SECONDARY SCHOOL | 300100055 | Ga-Segonyana | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2020-05-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 4210648 | 4210648 | Education Infrastructure Grant | Upgrading and Additions
|  | 194265 | LE21DOE04015 | Limpopo | KOBJANAME PRIMARY SCHOOL | 926540607 | Greater Tzaneen | Practical Completion (100%) | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3059293 | 3059293 | Education Infrastructure Grant | Upgrading and Additions
|  | 194270 | LE21DOE07032 | Limpopo | SHIBANGWA PRIMARY SCHOOL | 911361347 | Makhado | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 605433 | 3363519 | 3968952 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194271 | LE21DOE08036 | Limpopo | PATRIC RAMANO SECONDARY SCHOOL | 928330923 | Musina | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-10-05 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 864090 | 4800499 | 5664589 | Education Infrastructure Grant | Upgrading and Additions
|  | 194272 | LE21DOE40194 | Limpopo | SELWANA PRIMARY SCHOOL | 913420680 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 549568 | 3053155 | 3602723 | Education Infrastructure Grant | Upgrading and Additions
|  | 194273 | LE21DOE31152 | Limpopo | SOLOMONDALE PRIMARY SCHOOL | 923241405 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-09-16 | 2020-09-17 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 618954 | 3438632 | 4057586 | Education Infrastructure Grant | Upgrading and Additions
|  | 194276 | LE21DOE01001 | Limpopo | BAKENBERG SECONDARY SCHOOL | 921142454 | Mogalakwena | Final Completion | Active - Not Contracted | 2020-08-03 | 2020-08-25 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 692415 | 3846750 | 4539165 | Education Infrastructure Grant | Upgrading and Additions
|  | 194277 | LE21DOE26126 | Limpopo | ALFRED MASIBE PRIMARY SCHOOL | 921120027 | Mogalakwena | Final Completion | Approved | 2020-08-04 | 2020-08-20 | 2022-08-31 | 2023-09-01 | 2023-01-30 | 671098 | 3728324 | 4399422 | Education Infrastructure Grant | Upgrading and Additions
|  | 194280 | LE21DOE14062 | Limpopo | ZWANANI PRIMARY SCHOOL | 921120027 | Mogalakwena | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 637856 | 3543642 | 4181498 | Education Infrastructure Grant | Upgrading and Additions
|  | 194283 | LE21DOE04016 | Limpopo | MAUPYAE PRIMARY SCHOOL | 922210975 | Polokwane | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3723836 | 3723836 | Education Infrastructure Grant | Upgrading and Additions
|  | 194284 | LE21DOE12050 | Limpopo | TINGWAZI PRIMARY SCHOOL | 915541297 | Ba-Phalaborwa | Construction 51% - 75% | Active - Not Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 849000 | 3369000 | 4218000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194285 | LE21DOE12051 | Limpopo | MAROBONI PRIMARY SCHOOL | 926540881 | Ba-Phalaborwa | Construction 51% - 75% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 630595 | 3503307 | 4133902 | Education Infrastructure Grant | Upgrading and Additions
|  | 194286 | LE21DOE20088 | Limpopo | MANTSHA PRIMARY SCHOOL | 901340470 | Ba-Phalaborwa | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3280519 | 3280519 | Education Infrastructure Grant | Upgrading and Additions
|  | 194287 | LE21DOE18081 | Limpopo | MAMPURU PRIMARY SCHOOL | 925660563 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 3499066 | 3499066 | Education Infrastructure Grant | Upgrading and Additions
|  | 194288 | LE21DOE25118 | Limpopo | MMAKAU PRIMARY SCHOOL | 926540959 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2022-08-31 | 2022-09-01 | 2023-01-30 | 591893 | 3288294 | 3880187 | Education Infrastructure Grant | Upgrading and Additions
|  | 194289 | LE21DOE20087 | Limpopo | MAMERIRI SECONDARY SCHOOL | 901341176 | Ba-Phalaborwa | Practical Completion (100%) | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 543191 | 3017727 | 3560918 | Education Infrastructure Grant | Upgrading and Additions
|  | 194290 | LE21DOE42202 | Limpopo | BOGALATLADI SECONDARY SCHOOL | 925631329 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2022-08-31 | 2022-09-01 | 2023-03-31 | 575501 | 3197227 | 3772728 | Education Infrastructure Grant | Upgrading and Additions
|  | 194291 | LE21DOE18080 | Limpopo | TSWELOPELE PRIMARY SCHOOL | 925621216 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 518869 | 2882606 | 3401475 | Education Infrastructure Grant | Upgrading and Additions
|  | 194292 | LE21DOE41199 | Limpopo | METSANANGWANA PRIMARY SCHOOL | 996606823 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 726126 | 4034035 | 4760161 | Education Infrastructure Grant | Upgrading and Additions
|  | 194293 | LE21DOE35169 | Limpopo | MOLEMOLE PRIMARY SCHOOL | 919340890 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-08-31 |  | 2023-03-31 |  |  | 608853 | 3382519 | 3991372 | Education Infrastructure Grant | Upgrading and Additions
|  | 194294 | LE21DOE17075 | Limpopo | MAFEMANE PRIMARY SCHOOL | 925620404 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 649589 | 3608826 | 4258415 | Education Infrastructure Grant | Upgrading and Additions
|  | 194295 | LE21DOE34167 | Limpopo | SENWAMOKGOPE PRIMARY SCHOOL | 919340777 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 500799 | 2782220 | 3283019 | Education Infrastructure Grant | Upgrading and Additions
|  | 194296 | LE21DOE29138 | Limpopo | MAKONDE PRIMARY SCHOOL | 930350248 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 682429 | 3791271 | 4473700 | Education Infrastructure Grant | Upgrading and Additions
|  | 194297 | LE21DOE43208 | Limpopo | MAFUMANI SECONDARY SCHOOL | 916411341 | Ba-Phalaborwa | Construction 76% - 99% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-08-31 | 2023-09-01 | 2023-01-30 | 677646 | 3764703 | 4442349 | Education Infrastructure Grant | Upgrading and Additions
|  | 194298 | LE21DOE20086 | Limpopo | LELENI PRIMARY SCHOOL | 916410461 | Ba-Phalaborwa | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 599290 | 3329389 | 3928679 | Education Infrastructure Grant | Upgrading and Additions
|  | 194299 | LE21DOE12054 | Limpopo | TOURS PRIMARY SCHOOL | 926541310 | Ba-Phalaborwa | Construction 51% - 75% | Active - Not Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 603155 | 3350861 | 3954016 | Education Infrastructure Grant | Upgrading and Additions
|  | 194300 | LE21DOE43206 | Limpopo | HATSHAMA PRIMARY SCHOOL | 916410225 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 687619 | 3820107 | 4507726 | Education Infrastructure Grant | Upgrading and Additions
|  | 194301 | LE21DOE36171 | Limpopo | BODUMA PRIMARY SCHOOL | 919340593 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-10-13 | 2020-10-14 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 675307 | 3751706 | 4427013 | Education Infrastructure Grant | Upgrading and Additions
|  | 194303 | LE21DOE08034 | Limpopo | MUNGOMANI PRIMARY SCHOOL | 928330565 | Thulamela | Final Completion | Active - Contracted | 2019-04-01 | 2020-10-05 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 642620 | 3570110 | 4212730 | Education Infrastructure Grant | Upgrading and Additions
|  | 194304 | LE21DOE31150 | Limpopo | Mantheding Primary School | 923240679 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-09-16 | 2020-09-17 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 628359 | 3490883 | 4119242 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194305 | LE21DOE10044 | Limpopo | PONANI PRIMARY SCHOOL | 915541112 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2021-08-20 | 2022-08-31 | 2022-09-01 | 2023-01-30 | 697242 | 3873565 | 4570807 | Education Infrastructure Grant | Upgrading and Additions
|  | 194306 | LE21DOE04018 | Limpopo | RAKGOLOKWANA SECONDARY SCHOOL | 926540379 | Ba-Phalaborwa | Construction 76% - 99% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 3870705 | 3870705 | Education Infrastructure Grant | Upgrading and Additions
|  | 194307 | LE21DOE44214 | Limpopo | SENAKWE PRIMARY SCHOOL | 918511357 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 713754 | 3965302 | 4679056 | Education Infrastructure Grant | Upgrading and Additions
|  | 194308 | LE21DOE07029 | Limpopo | LANGUTANI PRIMARY SCHOOL | 911361323 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 693799 | 3854441 | 4548240 | Education Infrastructure Grant | Upgrading and Additions
|  | 194310 | LE21DOE13059 | Limpopo | MOTLHASEDI PRIMARY SCHOOL | 908110761 | Lephalale | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 437724 | 2431798 | 2869522 | Education Infrastructure Grant | Upgrading and Additions
|  | 194312 | LE21DOE28135 | Limpopo | MANIINI PRIMARY SCHOOL | 930350422 | Musina | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 595700 | 3309443 | 3905143 | Education Infrastructure Grant | Upgrading and Additions
|  | 194313 | LE21DOE12052 | Limpopo | MOGAPENG PRIMARY SCHOOL | 926540997 | Ba-Phalaborwa | Construction 51% - 75% | Active - Not Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 704822 | 3915680 | 4620502 | Education Infrastructure Grant | Upgrading and Additions
|  | 194314 | LE21DOE24114 | Limpopo | MADIKANONO PRIMARY SCHOOL | 925660396 | Elias Motsoaledi | Construction 51% - 75% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 4462418 | 4462418 | Education Infrastructure Grant | Upgrading and Additions
|  | 194315 | LE21DOE07031 | Limpopo | HANGALAKANI PRIMARY SCHOOL | 911321806 | Collins Chabane | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 616463 | 3424793 | 4041256 | Education Infrastructure Grant | Upgrading and Additions
|  | 194316 | LE21DOE44212 | Limpopo | MASHENGANI PRIMARY SCHOOL | 916410577 | Ba-Phalaborwa | Construction 76% - 99% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 713754 | 3965302 | 4679056 | Education Infrastructure Grant | Upgrading and Additions
|  | 194317 | LE21DOE13056 | Limpopo | IKITSENG PRIMARY SCHOOL | 908111528 | Lephalale | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 706154 | 3923077 | 4629231 | Education Infrastructure Grant | Upgrading and Additions
|  | 194318 | LE21DOE33163 | Limpopo | Paxana Primary School | 90221258 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 780716 | 4337309 | 5118025 | Education Infrastructure Grant | Upgrading and Additions
|  | 194319 | LE21DOE09038 | Limpopo | NYANTSHIRI PRIMARY SCHOOL | 915530976 | Ba-Phalaborwa | Practical Completion (100%) | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 702385 | 3902140 | 4604525 | Education Infrastructure Grant | Upgrading and Additions
|  | 194320 | LE21DOE12053 | Limpopo | NTWANANO PRIMARY SCHOOL | 915541082 | Ba-Phalaborwa | Construction 51% - 75% | Active - Not Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-01 | 2023-03-31 | 597786 | 3321033 | 3918819 | Education Infrastructure Grant | Upgrading and Additions
|  | 194321 | LE21DOE40195 | Limpopo | MAPHOKWANA SECONDARY SCHOOL | 913420307 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 734951 | 4083060 | 4818011 | Education Infrastructure Grant | Upgrading and Additions
|  | 194322 | LE21DOE27129 | Limpopo | RATSHISASE PRIMARY SCHOOL | 929310387 | Musina | Construction 51% - 75% | Active - Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 432660 | 2403666 | 2836326 | Education Infrastructure Grant | Upgrading and Additions
|  | 194325 | LE21DOE24115 | Limpopo | MAROTA MAKGANE PRIMARY SCHOOL | 925660662 | Makhuduthamaga | Construction 76% - 99% | Active - Not Contracted | 2022-02-01 |  | 2023-03-31 |  |  | 666429 | 3702381 | 4368810 | Education Infrastructure Grant | Upgrading and Additions
|  | 194326 | LE21DOE35170 | Limpopo | PULEDI PRIMARY SCHOOL | 919340913 | Polokwane | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 4193288 | 4193288 | Education Infrastructure Grant | Upgrading and Additions
|  | 194327 | LE21DOE14065 | Limpopo | MOTETI PRIMARY SCHOOL | 996606621 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 833539 | 4630775 | 5464314 | Education Infrastructure Grant | Upgrading and Additions
|  | 194328 | LE21DOE30143 | Limpopo | JOHN MARUBINI PRIMARY SCHOOL | 930351029 | Musina | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2022-08-31 | 2022-09-01 | 2023-01-30 | 809514 | 4497296 | 5306810 | Education Infrastructure Grant | Upgrading and Additions
|  | 194329 | LE21DOE14063 | Limpopo | HOSIA APHANE COMBINED SCHOOOL | 996606612 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 851243 | 4729129 | 5580372 | Education Infrastructure Grant | Upgrading and Additions
|  | 194330 | LE21DOE21097 | Limpopo | SEKUTUPU PRIMARY SCHOOL | 921230702 | Polokwane | Construction 26% - 50% | Active - Contracted | 2020-08-03 | 2020-08-20 | 2023-03-31 | 2023-03-01 | 2023-03-31 | 823794 | 4576634 | 5400428 | Education Infrastructure Grant | Upgrading and Additions
|  | 194333 | LE21DOE18082 | Limpopo | TIBAMOSHITO PRIMARY SCHOOL | 925661320 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 4971850 | 4971850 | Education Infrastructure Grant | Upgrading and Additions
|  | 194334 | LE21DOE06028 | Limpopo | LEPHALALA PRIMARY SCHOOL | 919340821 | Polokwane | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-03-31 |  |  | 0 | 4272948 | 4272948 | Education Infrastructure Grant | Upgrading and Additions
|  | 194335 | LE21DOE31151 | Limpopo | SEBAYENG PRIMARY SCHOOL | 923241290 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-09-16 | 2020-09-17 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 806964 | 4483134 | 5290098 | Education Infrastructure Grant | Upgrading and Additions
|  | 194336 | LE21DOE38182 | Limpopo | JOHN MOLOKOMME PRIMARY SCHOOL | 920210227 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-09-18 | 2020-09-21 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 837409 | 4652274 | 5489683 | Education Infrastructure Grant | Upgrading and Additions
|  | 194337 | LE21DOE40196 | Limpopo | NTSHUXEKO SECONDARY SCHOOL | 917420482 | Ba-Phalaborwa | Final Completion | Active - Contracted | 2020-08-03 | 2020-08-20 | 2027-01-30 | 2027-01-30 | 2027-01-30 | 1095463 | 6085904 | 7181367 | Education Infrastructure Grant | Upgrading and Additions
|  | 194338 | LE21DOE36172 | Limpopo | Makgato Secondary | 919340661 | Molemole | Final Completion | Active - Contracted | 2020-10-13 | 2020-10-14 | 2022-12-11 | 2022-02-11 | 2023-06-30 | 448028 | 2489047 | 2937075 | Education Infrastructure Grant | Upgrading and Additions
|  | 194339 | LE21DOE10045 | Limpopo | Tinghitsi Primary School | 915541280 | Greater Tzaneen | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-04-01 | 2023-03-31 | 408710 | 2270611 | 2679321 | Education Infrastructure Grant | Upgrading and Additions
|  | 194340 | LE21DOE29140 | Limpopo | Tshidimbini Secondary | 930351340 | Thulamela | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 445777 | 2476541 | 2922318 | Education Infrastructure Grant | Upgrading and Additions
|  | 194341 | LE21DOE32157 | Limpopo | Malesa Primary | 923240518 | Polokwane | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 412673 | 2292627 | 2705300 | Education Infrastructure Grant | Upgrading and Additions
|  | 194342 | LE21DOE22100 | Limpopo | Mboswobeni Primary | 930320551 | Makhado | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-06-25 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 412923 | 2294017 | 2706940 | Education Infrastructure Grant | Upgrading and Additions
|  | 194343 | LE21DOE16072 | Limpopo | Mahlahle Primary | 925620435 | Greater Tubatse/Fetakgomo | Construction 76% - 99% | Active - Contracted | 2020-09-01 | 2020-09-02 | 2022-12-01 | 2023-12-01 | 2023-06-30 | 457482 | 2541564 | 2999046 | Education Infrastructure Grant | Upgrading and Additions
|  | 194344 | LE21DOE17078 | Limpopo | Morwakgwadi Primary School | 925620848 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Not Contracted | 2021-01-04 | 2022-05-01 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 618588 | 3436598 | 4055186 | Education Infrastructure Grant | Upgrading and Additions
|  | 194345 | LE21DOE39189 | Limpopo | Tshifhire Primary | 928331193 | Makhado | Final Completion | Active - Contracted | 2019-04-01 | 2020-09-15 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 559266 | 3107035 | 3666301 | Education Infrastructure Grant | Upgrading and Additions
|  | 194346 | LE21DOE22101 | Limpopo | Nndamuleleni Secondary | 930320759 | Makhado | Practical Completion (100%) | Active - Contracted | 2019-04-01 | 2020-06-25 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 423503 | 2352796 | 2776299 | Education Infrastructure Grant | Upgrading and Additions
|  | 194347 | LE21DOE41200 | Limpopo | Tlhakanang Secondary | 996606810 | Ephraim Mogale | Construction 26% - 50% | Active - Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 344667 | 1914817 | 2259484 | Education Infrastructure Grant | Upgrading and Additions
|  | 194350 | LE21DOE21092 | Limpopo | Morotse Primary | 923260901 | Lepele-Nkumpi | Construction 26% - 50% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 362963 | 2016463 | 2379426 | Education Infrastructure Grant | Upgrading and Additions
|  | 194351 | LE21DOE34166 | Limpopo | Pelo Ya Kgomo Secondary | 919341107 | Greater Letaba | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-03-30 | 2023-03-31 | 314847 | 1749149 | 2063996 | Education Infrastructure Grant | Upgrading and Additions
|  | 194353 | LE21DOE15068 | Limpopo | Immerpan Primary | 906120348 | Ephraim Mogale | Construction 26% - 50% | Active - Contracted | 2020-08-25 | 2020-08-26 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 471965 | 2622027 | 3093992 | Education Infrastructure Grant | Upgrading and Additions
|  | 194354 | LE21DOE27132 | Limpopo | MATONDONI PRIMARY | 930350774 | Thulamela | Construction 51% - 75% | Active - Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 347843 | 1932464 | 2280307 | Education Infrastructure Grant | Upgrading and Additions
|  | 194357 | LE21DOE13055 | Limpopo | Baitswe Secondary | 908110020 | Lephalale | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2026-06-03 | 2026-12-30 | 2026-03-31 | 421065 | 2339251 | 2760316 | Education Infrastructure Grant | Upgrading and Additions
|  | 194359 | LE21DOE32158 | Limpopo | Moria Primary | 923240969 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 451534 | 2508520 | 2960054 | Education Infrastructure Grant | Upgrading and Additions
|  | 194360 | BBB/2018/003 | Northern Cape | SONSKYN INTERMEDIATE SCHOOL | 300022306 | Siyathemba | Construction 1% - 25% | Active - Contracted | 2020-05-01 | 2020-05-16 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 448853 | 20000000 | 20448853 | Education Infrastructure Grant | Upgrading and Additions
|  | 194361 | LE21DOE24116 | Limpopo | MOGASHOA PRIMARY | N/A | Makhuduthamaga | Construction 76% - 99% | Active - Not Contracted | 2020-01-04 |  | 2023-03-31 |  |  | 428071 | 2378170 | 2806241 | Education Infrastructure Grant | Upgrading and Additions
|  | 194364 | LE21DOE15067 | Limpopo | Goshetseng Primary | 924650047 | Ephraim Mogale | Construction 26% - 50% | Active - Contracted | 2020-08-25 | 2020-08-26 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 507131 | 2817397 | 3324528 | Education Infrastructure Grant | Upgrading and Additions
|  | 194365 | LE21DOE42203 | Limpopo | Ledingwe Primary | 925631398 | Greater Tubatse/Fetakgomo | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-12-30 | 2023-03-31 | 427128 | 2372933 | 2800061 | Education Infrastructure Grant | Upgrading and Additions
|  | 194366 | ST060/2022-23:R&R & ELECTRICITY | Northern Cape | CARNARVON SECONDARY SKOOL | 300024302 | Kareeberg | Project Initiation | Active - Contracted | 2022-06-08 |  | 2022-10-27 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194368 | LE21DOE25117 | Limpopo | Lefoke Primary | 926540614 | Maruleng | Practical Completion (100%) | Active - Contracted | 2020-01-04 | 2020-06-01 | 2022-12-20 | 2022-01-30 | 2023-03-31 | 454315 | 2523974 | 2978289 | Education Infrastructure Grant | Upgrading and Additions
|  | 194369 | LE21DOE11046 | Limpopo | Ramoba Secondary | 926540393 | Greater Tzaneen | Final Completion | Active - Contracted | 2020-01-04 | 2020-06-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 476871 | 2649281 | 3126152 | Education Infrastructure Grant | Upgrading and Additions
|  | 194372 | Covid-19 Response | Limpopo | Various Schools | Various Schools | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-01-04 | 2020-04-01 | 2030-12-20 | 2021-01-30 | 2022-03-31 | 5000000 | 20000000 | 25000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194374 | W/500244866/SDS | KwaZulu-Natal | OSIZWENI PRIMARY SCHOOL | 500244866 | KwaDukuza | Design | Active - Not Contracted | 2019-08-21 |  | 2024-03-30 |  |  | 1368000 | 2648000 | 4016000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194376 | ST322-2021 | Northern Cape | EMTHANJENI PUBLIC PRIMARY SCHOOL | 300021202 | Emthanjeni | Construction 1% - 25% | Active - Contracted | 2022-01-13 |  | 2022-11-30 |  |  | 0 | 762154 | 762154 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194378 | TBD-MAINTENANCE | Northern Cape | FLOORS HIGH SCHOOL | 300011401 | Sol Plaatjie | Tender | Active - Contracted | 2022-05-05 |  | 2022-11-30 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194385 | W/500246457/SDS | KwaZulu-Natal | PARLOCK PRIMARY SCHOOL | 500246457 | eThekwini | Feasibility | Active - Not Contracted | 2019-08-21 |  | 2024-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194386 | W/50000000/SDS | KwaZulu-Natal | PERMARY RIDGE PRIMARY SCHOOL | 50000000 | eThekwini | Feasibility | Active - Not Contracted | 2019-08-21 |  | 2024-03-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194400 | ST336/2021& ST024/2022-23 | Northern Cape | VAN RENSBURG PRIMARY SCHOOL | 300016207 | Sol Plaatjie | Tender | Active - Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 1753341 | 1753341 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194404 | ST353/2021 | Northern Cape | KIM KGOLO PRIMARY SCHOOL | 300015209 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-06-06 |  | 2022-12-30 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194405 | MAINTENANCE_TBD_KLIPFONTEIN | Northern Cape | KLIPFONTEIN MET PRIMERE SKOOL | 300032203 | Kamiesberg | Project Initiation | Proposed | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 829172 | 829172 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194418 | TBD_ PABALLELO PRIMARY SCHOOL | Northern Cape | NEW SCHOOL PABALLELO | NEW | Dawid Kruiper | Project Initiation | Proposed | 2022-05-05 |  | 2022-09-30 |  |  | 0 | 753341 | 753341 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194422 | TBD_CONVERSION OF TOILETS | Northern Cape | RELEKILE PRIMARY SCHOOL | 300101825 | Ga-Segonyana | Project Initiation | Active - Contracted | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194427 | W/500247308/SDS | KwaZulu-Natal | PHAKATHI SECONDARY SCHOOL | 500247308 | eThekwini | Feasibility | Active - Not Contracted | 2020-11-01 |  | 2024-03-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194432 | ST332/2021 | Northern Cape | TSHIMOLOGO INTERMEDIATE SCHOOL | 300102234 | Ga-Segonyana | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 764527 | 764527 | Education Infrastructure Grant | Upgrading and Additions
|  | 194434 | W/500248677/SDS | KwaZulu-Natal | PHILA PRIMARY SCHOOL | 500248677 | eThekwini | Feasibility | Active - Not Contracted | 2019-08-21 |  | 2024-03-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194436 | W/500248825/WS | KwaZulu-Natal | PHINDELA PRIMARY SCHOOL | 500248825 | eThekwini | Construction 51% - 75% | Active - Contracted | 2019-08-21 |  | 2023-03-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194439 | ST059/2022-23:R&R_STRUCTURAL DAMAGE | Northern Cape | VICTORIA-WES GEKOMBINEERDE SKOOL | 300024304 | Ubuntu | Tender | Active - Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 2694472 | 2694472 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194451 | W/500250120/RRR | KwaZulu-Natal | PHUNGULA PRIMARY SCHOOL | 500250120 | Ray Nkonyeni | Project Initiation | Proposed | 2019-08-21 |  | 2024-03-30 |  |  | 1655000 | 1975000 | 3630000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194452 | W/500250194/SDS | KwaZulu-Natal | PHUPHUMA PRIMARY SCHOOL | 500250194 | Msinga | Feasibility | Active - Not Contracted | 2020-11-01 |  | 2024-03-30 |  |  | 35000 | 1250000 | 1285000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194468 | W/500338513/SDS | KwaZulu-Natal | PLATT DRIVE PRIMARY SCHOOL | 500338513 | eThekwini | Practical Completion (100%) | Active - Contracted | 2019-08-21 | 2020-08-19 | 2023-05-01 | 2021-04-30 | 2022-02-01 | 699000 | 3186000 | 3885000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194469 | DoE/EHL/MAIN/104 | Mpumalanga | BHEKISWAKO SECONDARY | 800001065 | Mbombela | Project Initiation | Proposed | 2021-08-01 |  | 2025-02-01 |  |  | 22479 | 224787 | 247266 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194470 | MDOE/MAIN/001/21-22 | Mpumalanga | Hluvukani Primary School | 800034828 | Bushbuckridge | Project Initiation | Proposed | 2021-01-01 |  | 2024-04-28 |  |  | 0 | 270400 | 270400 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194471 | MDOE/MAIN/22-23/104 | Mpumalanga | Hoerskool Delmas | 800005769 | Victor Khanye | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 745889 | 7458898 | 8204787 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194472 | MDOE/MAIN/22-23/14 | Mpumalanga | Intfutfuko Secondary School | 800006551 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-08-01 |  | 2024-02-01 |  |  | 469634 | 4696345 | 5165979 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194473 | DoE/EHL/MAIN/119 | Mpumalanga | Khumbula Secondary School | 800007872 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 776185 | 5544185 | 6320370 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194476 | MDOE/UPG/1025/21-22 (DPWRT/325/19/MP) | Mpumalanga | Laerskool Nelspruit | 800009480 | Mbombela | Construction 1% - 25% | Active - Contracted | 2021-01-01 | 2021-12-02 | 2024-04-26 | 2022-12-31 | 2022-12-31 | 41154 | 411536 | 452690 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194478 | MDOE/MAIN/22-23/29 | Mpumalanga | Mahushe Secondary School | 800011734 | Nkomazi | Feasibility | Proposed | 2021-04-15 |  | 2024-09-30 |  |  | 359671 | 3596713 | 3956384 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194480 | MDOE/MAIN/005/21-22 | Mpumalanga | Manyakatana Primary School | 800034835 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 135200 | 135200 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194482 | MDOE/MAIN/007/21-22 | Mpumalanga | Mavimbela Primary School | tbc | Bushbuckridge | Project Initiation | Proposed | 2021-04-01 |  | 2024-09-15 |  |  | 0 | 169000 | 169000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194483 | W/500494949/NS | KwaZulu-Natal | PRINCESS PHUMZILE PRIMARY SCHOOL (ULUNDI SECTION D) | 500494949 | Ulundi | Final Completion | Active - Contracted | 2020-11-01 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-04-01 | 15000 | 68000 | 83000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194485 | DoE/EHL/MAIN/118 | Mpumalanga | Mehlobovu Secondary school | 800013961 | Nkomazi | Project Initiation | Proposed | 2021-04-01 |  | 2023-03-31 |  |  | 204790 | 2047896 | 2252686 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194487 | W/OFFICE BUTHELEZIRD/RRR | KwaZulu-Natal | PROVINCIAL OFFICES - MPUMALANGA - BUTHELEZI ROAD | OFFICE BUTHELEZIRD | eThekwini | Project Initiation | Active - Contracted | 2020-11-01 |  | 2025-07-30 |  |  | 1802000 | 3082000 | 4884000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 194488 | DPWRT/SAN/175/20/MP | Mpumalanga | Mntungwa Secondary school | 800014761 | Mbombela | Site Handed - Over to Contractor | Proposed | 2020-04-01 | 2021-03-04 | 2023-11-01 | 2023-11-13 | 2023-11-13 | 0 | 2885924 | 2885924 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194489 | W/500252710/RRR | KwaZulu-Natal | QHAMUKILE PRIMARY SCHOOL | 500252710 | The Msunduzi | Project Initiation | Proposed | 2019-08-21 |  | 2024-03-30 |  |  | 1871000 | 2191000 | 4062000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194495 | W/500252895/SDS | KwaZulu-Natal | QHOSHEYIPHETHE PRIMARY SCHOOL | 500252895 | eThekwini | Feasibility | Active - Not Contracted | 2020-11-01 |  | 2023-07-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194496 | MDOE/MAIN/001/21-22 other | Mpumalanga | Qokiso Secondary School | 800034954 | Bushbuckridge | Project Initiation | Potential | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 202800 | 202800 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194498 | MDOE/UPG/1018/21-22 | Mpumalanga | Siboshwa Primary School | 800020743 | Nkomazi | Design | Active - Not Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 4130357 | 29502552 | 33632909 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194505 | DPWRT/055/21MP VUKASAMBE P--------------- | Mpumalanga | Vukasambe Primary School | 800024810 | Mbombela | Terminated | Proposed | 2021-04-01 |  | 2023-12-15 |  |  | 288120 | 2058000 | 2346120 | Education Infrastructure Grant | Upgrading and Additions
|  | 194507 | MDOE/MAIN/93/21-22 | Mpumalanga | White-river Primary School | 800009753 | Mbombela | Project Initiation | Proposed | 2022-04-01 |  | 2024-03-31 |  |  | 301125 | 3011245 | 3312370 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194508 | MDOE/MAIN/030/22 | Mpumalanga | ZakheleniPrimary School | 800025742 | Thaba Chweu | Project Initiation | Proposed | 2022-04-01 |  | 2024-03-31 |  |  | 245889 | 2458893 | 2704782 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194512 | W/500253672/SDS | KwaZulu-Natal | QONDOKUHLE PRIMARY SCHOOL | 500253672 | eThekwini | Pre - Feasibility | Proposed | 2019-08-21 |  | 2023-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194513 | W/500443482/WS | KwaZulu-Natal | QUARRY HEIGHTS PRIMARY SCHOOL | 500443482 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194514 | W/500255041/RRR | KwaZulu-Natal | REICHENAU PRIMARY SCHOOL | 500255041 | Dr Nkosazana Dlamini Zuma | Project Initiation | Proposed | 2019-08-21 |  | 2023-06-30 |  |  | 910000 | 1230000 | 2140000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194525 | W/500255818/SDS | KwaZulu-Natal | RIETVALLEI COMBINED SCHOOL | 500255818 | eThekwini | Pre - Feasibility | Proposed | 2019-08-21 |  | 2023-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194526 | W/500255744/RRR | KwaZulu-Natal | RIDGE PARK COLLEGE | 500255744 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-06-30 |  |  | 225000 | 1025000 | 1250000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194528 | W/500257187/UA | KwaZulu-Natal | SACRED HIGH SCHOOLEART S | 500257187 | eThekwini | Design | Active - Not Contracted | 2019-08-21 |  | 2023-05-01 |  |  | 2048000 | 9330000 | 11378000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194531 | ST315/2021:STRUCTURAL ASSESSMENT | Northern Cape | HO?RSKOOL KATHU | 300044402 | Gamagara | Feasibility | Active - Contracted | 2022-05-05 |  | 2022-10-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194533 | ST418/2022 & ST044/2022-23 | Northern Cape | GAMOCWAEDI PRIMARY SCHOOL | 100403 | Joe Morolong | Construction 51% - 75% | Approved | 2022-03-11 |  | 2023-02-24 |  |  | 0 | 1612375 | 1612375 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194536 | TBD- HTT | Northern Cape | HTT BIDI MEMORIAL PRIMARY SCHOOL | 300044205 | Tsantsabane | Feasibility | Approved | 2022-05-05 |  | 2022-10-28 |  |  | 0 | 753341 | 753341 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194541 | TBD_. | Northern Cape | MOGOMOTSI HIGH SCHOOL | 300017404 | Magareng | Project Initiation | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194545 | TBD2022/23-6 | Northern Cape | MAIKAELELO INTERMEDIATE SCHOOL | 300044303 | Joe Morolong | Feasibility | Active - Contracted | 2023-04-01 |  | 2025-03-31 |  |  | 0 | 7112030 | 7112030 | Education Infrastructure Grant | Upgrading and Additions
|  | 194547 | REPLACEMENT OF ASBESTOS HOSTEL ROOF | Northern Cape | PRIESKA PRIMARY SCHOOL | 300022302 | Siyathemba | Feasibility | Approved | 2022-07-07 |  | 2023-03-31 |  |  | 0 | 2800000 | 2800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194551 | ST309/2021 | Northern Cape | VALSPAN INTERMEDIATE SCHOOL | 300017214 | Phokwane | Tender | Active - Not Contracted | 2022-04-10 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194555 | ST348/2021 | Northern Cape | LAERSKOOL HARTSVAAL | 300013207 | Phokwane | Practical Completion (100%) | Active - Contracted | 2022-02-28 | 2022-03-02 | 2023-03-31 | 2023-04-01 | 2025-03-31 | 0 | 4850718 | 4850718 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194563 | LAERSKOOL CALVINIA | Northern Cape | CALVINIA PRIMARY SCHOOL | 300033209 | Hantam | Design | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 800000 | 800000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194571 | UPINGTON NEW ENGLISH MEDIUM | Northern Cape | UPINGTON NEW ENGLISH MEDUIM PRIMARY SCHOOL | 30001000 | Dawid Kruiper | Feasibility | Proposed | 2022-04-01 |  | 2025-03-31 |  |  | 16599739 | 60000000 | 76599739 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194578 | TBD2022/23-13 | Northern Cape | THAGANYANE PS | 300102081 | Joe Morolong | Feasibility | Active - Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 2479149 | 2479149 | Education Infrastructure Grant | Upgrading and Additions
|  | 194582 | ST313/2021 | Northern Cape | LAERSKOOL SEODIN | 300045211 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-11-30 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194585 | TBD_CONVERSION_TOILETS | Northern Cape | MAMORATWA INTERMEDIATE SCHOOL | 300101061 | Ga-Segonyana | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194586 | TBD:CONVERSION OF TOILETS | Northern Cape | MOTSHWARAKGOLE INTERMEDIATE SCHOOL | 300101450 | Joe Morolong | Feasibility | Active - Not Contracted | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194588 | TBD2022/23-23 | Northern Cape | PABALLELO SENIOR SECONDARY | 300042402 | Phokwane | Feasibility | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 326765 | 3000000 | 3326765 | Education Infrastructure Grant | Upgrading and Additions
|  | 194594 | TBD_ MAREMANE | Northern Cape | MAREMANE PRIMARY SCHOOL | 300101105 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 616272 | 616272 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194595 | TBD2021/23-5 | Northern Cape | PORT NOLLOTH HIGH SCHOOL | 300032308 | Richtersveld | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 361379 | 2500000 | 2861379 | Education Infrastructure Grant | Upgrading and Additions
|  | 194600 | ST301/2021 | Northern Cape | LEARAMELE SPECIAL SCHOOL FOR THE SMH | 300102379 | Ga-Segonyana | Feasibility | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194603 | ST036/2022-23 | Northern Cape | LOWRYVILLE INTERMEDIERE SKOOL | 300023304 | Umsobomvu | Project Initiation | Active - Not Contracted | 2022-05-04 |  | 2024-10-31 |  |  | 0 | 420000 | 420000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194607 | TBD- SOL PLAATJIE | Northern Cape | SOL PLAATJIE PRIMARY SCHOOL | 300016215 | Sol Plaatjie | Feasibility | Active - Contracted | 2022-04-20 |  | 2022-10-28 |  |  | 0 | 1960322 | 1960322 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194612 | TBD_ LANGBERG | Northern Cape | LANGBERG HIGH SCHOOL | 300044302 | Gamagara | Project Initiation | Active - Not Contracted | 2022-05-05 |  | 2023-04-30 |  |  | 0 | 1529172 | 1529172 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194614 | TBD2022/23-44 | Northern Cape | LUVUYO PRIMARY SCHOOL | 300022304 | Emthanjeni | Feasibility | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 506400 | 506400 | Education Infrastructure Grant | Upgrading and Additions
|  | 194617 | ST058/2022-23_ELECTRICAL WORKS_R&R | Northern Cape | SC KEARNS | 300043306 | Dawid Kruiper | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1749570 | 1749570 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194622 | TBD:RIETVALE_REPAIRS AND RENOVATIONS | Northern Cape | RIETVALE HIGH SCHOOL | 300014303 | Sol Plaatjie | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 773301 | 773301 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194630 | W/500257705/WS | KwaZulu-Natal | SALIGNA PRIMARY SCHOOL | 500257705 | uMlalazi | Design | Active - Not Contracted | 2020-11-01 |  | 2023-09-30 |  |  | 522000 | 2378000 | 2900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194631 | W/500257927/SDS | KwaZulu-Natal | SANDAKAHLE PRIMARY SCHOOL | 500257927 | eThekwini | Feasibility | Proposed | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194632 | W/500258001/SDS | KwaZulu-Natal | SANDANOLWAZI PRIMARY SCHOOL | 500258001 | Umdoni | Feasibility | Proposed | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194633 | W/500258630/SDS | KwaZulu-Natal | SAPHUMELELA PRIMARY SCHOOL | 500258630 | eThekwini | Feasibility | Proposed | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194634 | W/500259074/SDS | KwaZulu-Natal | SAWELA PRIMARY SCHOOL | 500259074 | eThekwini | Feasibility | Proposed | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194635 | W/500259148/SDS | KwaZulu-Natal | SAWPITS PRIMARY SCHOOL | 500259148 | eThekwini | Feasibility | Proposed | 2022-03-01 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194636 | W/500323528/UA | KwaZulu-Natal | SENZOKWETHU SECONDARY SCHOOL | 500323528 | eThekwini | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 900000 | 4100000 | 5000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194637 | W/500261035/SDS | KwaZulu-Natal | SEZELA PRIMARY SCHOOL | 500261035 | Umdoni | Pre - Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194638 | W/500261294/SDS | KwaZulu-Natal | SHALLCROSS SECONDARY SCHOOL | 500261294 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194641 | MDOE/UPG/129/21-22 | Mpumalanga | Nelsville Primary School | 800005934 | Mbombela | Design | Active - Not Contracted | 2021-04-01 |  | 2025-09-15 |  |  | 1659704 | 8298520 | 9958224 | Education Infrastructure Grant | Upgrading and Additions
|  | 194643 | MDOE/MAIN/22-23/119 | Mpumalanga | KaMhola Secondary School | 800034505 | Mbombela | Design | Proposed | 2021-04-01 |  | 2024-09-15 |  |  | 877874 | 8778743 | 9656617 | Education Infrastructure Grant | Maintenance and Repairs
|  | 194644 | MDOE/UPG/106/22-23 | Mpumalanga | Intfutfuko Primary School | 800006551 | Nkomazi | Design | Proposed | 2021-04-01 |  | 2025-09-15 |  |  | 252000 | 1800000 | 2052000 | Equitable Share | Upgrading and Additions
|  | 194645 | MDOE/UPG/107/22-23 | Mpumalanga | Mdzabu Secondary School | 800013920 | Nkomazi | Feasibility | Proposed | 2021-04-01 |  | 2025-09-15 |  |  | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194648 | KLIPSPRINGER UPGRADES | Mpumalanga | Klipspringer Primary School | 800008177 | Mbombela | Feasibility | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 1460141 | 10429579 | 11889720 | Education Infrastructure Grant | Upgrading and Additions
|  | 194649 | MDOE/MAIN/018/20-21(DPWRT/SAN/005/21/MP) | Mpumalanga | Phumalanga Primary School | 800005545 | Mbombela | Construction 51% - 75% | Active - Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 126000 | 900000 | 1026000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194656 | W/500262293/SDS | KwaZulu-Natal | SHONKWENI PRIMARY SCHOOL | 500262293 | Umdoni | Feasibility | Proposed | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194657 | W/500504088/SDS | KwaZulu-Natal | SICELIMPILO PRIMARY SCHOOL | 500504088 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194663 | W/500265512/SDS | KwaZulu-Natal | SILINDELE PRIMARY SCHOOL | 500265512 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194665 | W/500323639/SDS | KwaZulu-Natal | SINENHLANHLA SECONDARY SCHOOL | 500323639 | Maphumulo | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 1377000 | 2657000 | 4034000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194666 | W/500266511/WS | KwaZulu-Natal | SINENHLANHLA PRIMARY SCHOOL (LADYSMITH) | 500266511 | Alfred Duma | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 612000 | 2788000 | 3400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194672 | TBA 11 | Western Cape | Cathkin SS | TBC | City of Cape Town | Construction 1% - 25% | Active - Contracted | 2020-09-21 | 2022-04-29 | 2024-03-29 | 2023-09-05 | 2023-09-05 | 7000000 | 28000000 | 35000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194681 | TBA 12 | Western Cape | New Ashton HS | TBC | Langeberg | Feasibility | Active - Not Contracted | 2021-05-06 |  | 2026-03-31 |  |  | 12500000 | 48000000 | 60500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194683 | 31962051/31968051 | Western Cape | Nieuwoudt PS | TBC | Matzikama | Design | Active - Not Contracted | 2021-05-31 |  | 2026-03-31 |  |  | 14500000 | 71000000 | 85500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194684 | 31963051 | Western Cape | Hopefield PS | TBC | Saldanha Bay | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 13000000 | 58000000 | 71000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 194690 | TBA 13 | Western Cape | New Klapmuts PS | TBC | Stellenbosch | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2027-03-31 |  |  | 11500000 | 52000000 | 63500000 | Equitable Share | New or Replaced Infrastructure
|  | 194698 | W/500320901/SDS | KwaZulu-Natal | SIYATHOKOZA PRIMARY SCHOOL | 500320901 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194707 | W/500272279/SDS | KwaZulu-Natal | SLAVU PRIMARY SCHOOL | 500272279 | Umzumbe | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 35000 | 1250000 | 1285000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194708 | W/500272468/SDS | KwaZulu-Natal | SOBANTU SECONDARY SCHOOL | 500272468 | The Msunduzi | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 488000 | 2224000 | 2712000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194709 | W/500272653/SDS | KwaZulu-Natal | SOJUBA SENIOR PRIMARY SCHOOL | 500272653 | Umzumbe | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2027-06-30 |  |  | 350000 | 1250000 | 1600000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194710 | GRADE001 | North West | GRADE R | GRADE 001 | Mafikeng | Project Initiation | Proposed | 2020-04-01 |  | 2025-03-31 |  |  | 0 | 45000000 | 45000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194712 | MDOE/SAN/286/2020 | Mpumalanga | Sikhutsele Primary School | 800029702 | Mbombela | Feasibility | Proposed | 2021-04-01 |  | 2024-09-15 |  |  | 740600 | 3703000 | 4443600 | Education Infrastructure Grant | Upgrading and Additions
|  | 194713 | MDOE/SAN/287/2020 | Mpumalanga | Sitintile Secondary School | 800021410 | Mbombela | Tender | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 330000 | 1980000 | 2310000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194716 | MDOE/SAN/305/2020 | Mpumalanga | Khutsalani Secondary School | 800008607 | Mbombela | Feasibility | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 209160 | 1494000 | 1703160 | Education Infrastructure Grant | Upgrading and Additions
|  | 194717 | MDOE/SAN/307/2020 | Mpumalanga | Nsizwane Primary School | 800017251 | Nkomazi | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 233800 | 1670000 | 1903800 | Education Infrastructure Grant | Upgrading and Additions
|  | 194719 | MDOE/SAN/309/2020 | Mpumalanga | Lekazi Primary School | 800010116 | Mbombela | Tender | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 1022000 | 7300000 | 8322000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194722 | GDE00246 | Gauteng | MUZOMUHLE PRIMARY SCHOOL | 700152454 | City of Johannesburg | Project Initiation | Active - Not Contracted | 2020-09-08 |  | 2025-05-14 |  |  | 9440000 | 49560000 | 59000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194748 | W/500276316/WS | KwaZulu-Natal | ST MICHAELS PRIMARY SCHOOL (UMZINTO) | 500276316 | eThekwini | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2023-07-13 | 2023-06-30 | 2023-07-15 | 2023-12-31 | 85000 | 385000 | 470000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194755 | W/500276316/RRR | KwaZulu-Natal | ST MICHAELS PRIMARY SCHOOL (UMZINTO) | 500276316 | eThekwini | Project Initiation | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 912000 | 1232000 | 2144000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194763 | W/500276464/RRR | KwaZulu-Natal | ST NIVARDS PRIMARY SCHOOL | 500276464 | Umzumbe | Project Initiation | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 1662000 | 1982000 | 3644000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194769 | W/500342620/RRR | KwaZulu-Natal | ST WENDOLINS PRIMARY SCHOOL | 500342620 | eThekwini | Project Initiation | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 1533000 | 1853000 | 3386000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194776 | W/500277537/SDS | KwaZulu-Natal | STANGER SOUTH SECONDARY SCHOOL | 500277537 | KwaDukuza | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 300000 | 1700000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194787 | W/500278425/SDS | KwaZulu-Natal | SUKUMA PRIMARY SCHOOL | 500278425 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 350000 | 1225000 | 1575000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194820 | W/500279794/SDS | KwaZulu-Natal | TENDELA COMBINED SCHOOL | 500279794 | Mpofana | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 2181000 | 3461000 | 5642000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194851 | W/500280608/SDS | KwaZulu-Natal | THANDUKWAZI PRIMARY SCHOOL | 500280608 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 350000 | 1225000 | 1575000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194883 | ADDITIONS PROGRAMMES | North West | ADDITIONS PROGRAMME | ADDITONS PROGRAMME 001 | Mafikeng | Project Initiation | Proposed | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 115000000 | 115000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194928 | W/500281829/UA | KwaZulu-Natal | THETHANDABA PRIMARY SCHOOL | 500281829 | KwaDukuza | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 900000 | 4100000 | 5000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194956 | W/500282569/RRR | KwaZulu-Natal | THOLIMFUNDO PRIMARY SCHOOL | 500282569 | Umdoni | Project Initiation | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 1663000 | 1983000 | 3646000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 194972 | W/500283531/WS | KwaZulu-Natal | THULINI PRIMARY SCHOOL | 500283531 | Maphumulo | Design | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 194980 | W/500284123/SDS | KwaZulu-Natal | TOBI SENIOR PRIMARY SCHOOL | 500284123 | eThekwini | Feasibility | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 350000 | 1225000 | 1575000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195293 | TBA 36 | Western Cape | Heathfield PS | TBC | City of Cape Town | Feasibility | Active - Not Contracted | 2021-05-05 |  | 2025-03-31 |  |  | 9000000 | 41000000 | 50000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195297 | TBA 37 | Western Cape | Protea Park PS | TBC | City of Cape Town | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 9000000 | 41000000 | 50000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195337 | GDE00126 | Gauteng | JOHANNESBURG HOSPITAL LSEN | 700132340 | City of Johannesburg | Design | Approved | 2020-08-31 |  | 2025-12-07 |  |  | 10000000 | 70000000 | 80000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 195439 | P9008789 | Eastern Cape | NON INFRASTRUCTURE SOLUTIONS | 200999925 | Buffalo City | Feasibility | Approved | 2021-03-31 |  | 2026-03-31 |  |  | 0 | 15422773 | 15422773 | Education Infrastructure Grant | Non-Infrastructure
|  | 195443 | P9013222 | Eastern Cape | MASIJONGANE JUNIOR PRIMARY SCHOOL | 200200426 | Buffalo City | Project Initiation | Active - Not Contracted | 2022-03-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 195553 | I/500302919/WS | KwaZulu-Natal | DUBEYANE PRIMARY SCHOOL | 500302919 | KwaDukuza | Practical Completion (100%) | Active - Not Contracted | 2016-04-01 | 2017-05-01 | 2023-03-30 | 2023-06-15 | 2023-03-31 | 13000 | 61000 | 74000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195555 | I/500152477/WS | KwaZulu-Natal | GUDU SECONDARY SCHOOL | 500152477 | Abaqulusi | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-05-01 | 2023-03-30 | 2023-06-15 | 2023-03-30 | 475000 | 1950000 | 2425000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195559 | I/500441669/WS | KwaZulu-Natal | LUBELO SECONDARY SCHOOL | 500441669 | Jozini | Practical Completion (100%) | Active - Not Contracted | 2019-08-20 | 2020-04-01 | 2023-04-15 | 2022-10-01 | 2023-03-30 | 500000 | 1800000 | 2300000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195575 | DB/500411181/WS | KwaZulu-Natal | NOMAKHALADI PRIMARY SCHOOL | 500411181 | Nkandla | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195576 | DB/500427424/WS | KwaZulu-Natal | NOMEVA VUKAZI PRIMARY SCHOOL | 500427424 | Umzimkhulu | Practical Completion (100%) | Active - Contracted | 2018-01-01 | 2021-01-01 | 2023-03-01 | 2023-05-05 | 2025-08-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195577 | DB/500168720/SDS | KwaZulu-Natal | ISIPHINGO SECONDARY SCHOOL | 500168720 | eThekwini | Construction 76% - 99% | Active - Contracted | 2017-06-06 | 2019-01-15 | 2025-08-31 | 2021-02-26 | 2025-08-31 | 873000 | 3283000 | 4156000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195581 | DB/500196026/WS | KwaZulu-Natal | MANDENI PRIMARY SCHOOL | 500196026 | Mandeni | Tender | Active - Contracted | 2018-01-01 |  | 2025-03-01 |  |  | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195614 | P0002355_ | Eastern Cape | CEGCUANA JUNIOR SECONDARY SCHOOL | 200300044 | Mnquma | Final Completion | Active - Contracted | 2011-10-27 | 2011-11-27 | 2023-03-30 | 2023-03-30 | 2023-03-30 | 0 | 145287 | 145287 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 195642 | I/500205572/WS | KwaZulu-Natal | MCATHU PRIMARY SCHOOL | 500205572 | Ndwedwe | Practical Completion (100%) | Active - Not Contracted | 2016-08-20 | 2017-05-01 | 2023-08-20 | 2023-06-15 | 2023-03-31 | 3000 | 14000 | 17000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195646 | I/500219410/WS | KwaZulu-Natal | MTHOMBOWESIZWE HIGH SCHOOL | 500219410 | Nongoma | Practical Completion (100%) | Active - Not Contracted | 2016-08-20 | 2018-05-01 | 2023-03-30 | 2023-06-15 | 2023-03-31 | 45000 | 205000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195647 | I/500220039/WS | KwaZulu-Natal | MTUBA PRIMARY SCHOOL | 500220039 | Mtubatuba | Practical Completion (100%) | Active - Not Contracted | 2016-06-22 | 2018-05-01 | 2023-03-30 | 2023-06-15 | 2023-03-31 | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195648 | I/500445517/NS | KwaZulu-Natal | MVALO SECONDARY SCHOOL | 500445517 | Ulundi | Practical Completion (100%) | Active - Not Contracted | 2016-04-01 | 2022-05-01 | 2023-03-30 | 2023-10-01 | 2024-03-31 | 6145000 | 27996000 | 34141000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 195650 | I/500222777/WS | KwaZulu-Natal | MZWILILI PRIMARY SCHOOL | 500222777 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2016-06-06 | 2018-05-01 | 2023-03-30 | 2023-06-15 | 2023-03-31 | 200000 | 1700000 | 1900000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195653 | I/500265401/RRR | KwaZulu-Natal | SILIMELA PRIMARY SCHOOL | 500265401 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2016-04-01 | 2018-05-01 | 2023-03-30 | 2020-06-15 | 2023-03-31 | 3083000 | 14679000 | 17762000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195654 | I/500265401/WS | KwaZulu-Natal | SILIMELA PRIMARY SCHOOL | 500265401 | eThekwini | Practical Completion (100%) | Active - Not Contracted | 2016-04-01 | 2018-04-01 | 2023-03-30 | 2023-10-01 | 2023-03-31 | 300000 | 2200000 | 2500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195655 | I/500414918/WS | KwaZulu-Natal | THEMBISIZWE PRIMARY SCHOOL | 500414918 | Alfred Duma | Construction 76% - 99% | Active - Contracted | 2016-08-20 | 2018-05-01 | 2023-03-30 | 2023-10-01 | 2023-03-31 | 432000 | 1968000 | 2400000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195670 | W/500342250/SDS | KwaZulu-Natal | BATSHAZWAYO SECONDARY SCHOOL | 500342250 | uMlalazi | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 1647000 | 2927000 | 4574000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195674 | W/500109964/RRR | KwaZulu-Natal | BHUQWINI HIGH SCHOOL | 500109964 | Nkandla | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2023-03-30 | 2022-02-28 | 2023-05-31 | 941000 | 4287000 | 5228000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195678 | W/500114441/WS | KwaZulu-Natal | CARISBROOKE PRIMARY SCHOOL | 500114441 | Ubuhlebezwe | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2021-02-26 | 2023-06-30 | 2023-02-28 | 2024-04-01 | 250000 | 2000000 | 2250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 195682 | W/500124653/NS | KwaZulu-Natal | DUNDEE HIGH SCHOOL | 500124653 | Endumeni | Practical Completion (100%) | Active - Contracted | 2020-08-03 | 2020-09-10 | 2023-06-30 | 2020-10-30 | 2022-05-31 | 11327000 | 51599000 | 62926000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 195688 | W/500160728/SDS | KwaZulu-Natal | IMBUTHUMA PRIMARY SCHOOL | 500160728 | Abaqulusi | Tender | Active - Contracted | 2020-08-03 |  | 2025-06-30 |  |  | 100000 | 325000 | 425000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195699 | FSDOE New Sec 21/22 | Free State | Bloemfontein Caleb Motshabi 2 Sec School | FSDOE Caleb 2/22 | Mangaung | Project Initiation | Proposed | 2021-04-02 |  | 2027-03-31 |  |  | 95000 | 95000000 | 95095000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 195707 | W/500200355/RRR | KwaZulu-Natal | MASHESHISA PRIMARY SCHOOL | 500200355 | Ubuhlebezwe | Tender | Active - Not Contracted | 2020-08-03 |  | 2023-06-30 |  |  | 100000 | 300000 | 400000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 195723 | 30252051 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2016-04-01 |  | 2027-03-31 |  |  | 37754000 | 417579000 | 455333000 | Equitable Share | Maintenance and Repairs
|  | 195730 | TBA 17 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Proposed | 2021-04-01 |  | 2027-03-31 |  |  | 17000000 | 71000000 | 88000000 | Equitable Share | Upgrading and Additions
|  | 195975 | 200501404 | Eastern Cape | CHIEF DUMILE SENIOR SECONDARY SCHOOL | 200501404 | Mbizana | Feasibility | Active - Not Contracted | 2024-04-01 |  | 2025-05-31 |  |  | 0 | 36871772 | 36871772 | Education Infrastructure Grant | Upgrading and Additions
|  | 196168 | DB/500343693/WS | KwaZulu-Natal | SIYATHUTHUKA PRIMARY SCHOOL | 500343693 | Newcastle | Construction 1% - 25% | Active - Contracted | 2016-06-06 | 2018-04-05 | 2024-11-30 | 2024-05-05 | 2025-08-31 | 500000 | 1500000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 196279 | AGGENEYS LAERSKOOL _ TBD | Northern Cape | AGGENEYS LAERSKOOL | 300034301 | Khi-Ma | Project Initiation | Active - Not Contracted | 2022-04-05 |  | 2024-03-31 |  |  | 0 | 650000 | 650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196293 | MAINTENANCE & REPAIRS 2021/22 | Northern Cape | Maintenance on all offices | 1 | Sol Plaatjie | Construction 26% - 50% | Approved | 2021-04-01 | 2022-04-01 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 196296 | ST049/2022-23 | Northern Cape | BOTHITHONG HIGH SCHOOL | 300100557 | Joe Morolong | Tender | Approved | 2022-03-31 |  | 2022-08-04 |  |  | 0 | 1190137 | 1190137 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196302 | BBB340-2022 | Northern Cape | HEAD OFFICE: IK NKOANE EDUCATION HOUSE | N/A | Sol Plaatjie | Construction 1% - 25% | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196304 | HOERSKOOL NAMAKWALAND_TBD | Northern Cape | NAMAKWALAND HIGH SCHOOL | 300032401 | Nama Khoi | Feasibility | Proposed | 2022-06-08 |  | 2025-03-31 |  |  | 0 | 20000000 | 20000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 196306 | OR-032052 | Northern Cape | HOERSKOOL RICHMOND | 300024303 | Ubuntu | Practical Completion (100%) | Active - Contracted | 2022-02-11 |  | 2022-09-29 |  |  | 0 | 699856 | 839827 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196308 | JOHN TAOLO GAETSEWE DISTRICT OFFICE_BAITIREDI | Northern Cape | JOHN TAOLO GAETSEWE DISTRICT OFFICE | 300050205 | Ga-Segonyana | Project Initiation | Proposed | 2022-04-01 |  | 2025-03-29 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196310 | ST349/2021 | Northern Cape | KEIMOES INTERMEDIATE SCHOOL | 300042303 | Dawid Kruiper | Feasibility | Approved | 2021-11-26 |  | 2024-03-29 |  |  | 0 | 1801983 | 1801983 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196312 | KEVIN NKOANE PRIMARY SCHOOL_TBD | Northern Cape | KEVIN NKOANE PRIMARY SCHOOL | 300012207 | Sol Plaatjie | Project Initiation | Proposed | 2022-05-20 |  | 2025-03-31 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 196316 | TBD_ LAERSKOOL CURRIESCAMP_TBD | Northern Cape | LAERSKOOL CURRIESKAMP | 300042203 | Kai !Garib | Tender | Proposed | 2022-05-05 |  | 2022-12-29 |  |  | 0 | 337064 | 337064 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196322 | LUKHANYISO PRIMARY SCHOOL_TBD | Northern Cape | LUKHANYISO PRIMARY SCHOOL | 300043217 | Dawid Kruiper | Project Initiation | Proposed | 2022-05-05 |  | 2022-10-31 |  |  | 0 | 680588 | 680588 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196327 | ST328/2021 | Northern Cape | MOLEHABANGWE PRIMARY SCHOOL | 300011206 | Sol Plaatjie | Construction 76% - 99% | Proposed | 2022-04-01 | 2022-04-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 1590001 | 1590001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196328 | MORESON INTERMEDIATE SCHOOL_TBD | Northern Cape | MORESON INTERMEDI?RE SKOOL | 300043307 | Siyathemba | Project Initiation | Proposed | 2022-02-28 |  | 2023-03-29 |  |  | 0 | 1500001 | 1500001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196329 | MAINTENANCE:ABLUTION&KITCHEN | Northern Cape | NAMAKWA CIRCUIT OFFICE | 300090909 | Khi-Ma | Project Initiation | Proposed | 2023-02-28 |  | 2025-03-29 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196330 | MAINTENANCE_REPAIRS TO ROOF_TBD | Northern Cape | OKIEP LAERSKOOL | 300034306 | Nama Khoi | Project Initiation | Approved | 2023-02-28 |  | 2024-03-31 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196331 | PIXLEY KA SEME DISTRICT OFFICE_TBD | Northern Cape | PIXLEY KA SEME DISTRICT OFFICE - DE AAR | 300020202 | Emthanjeni | Feasibility | Approved | 2021-02-28 |  | 2025-03-29 |  |  | 0 | 499899 | 499899 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196333 | RAPELANG INTERMEDIATE SCHOOL_TBD | Northern Cape | RAPELANG INTERMEDIATE SCHOOL | 300101753 | Joe Morolong | Project Initiation | Proposed | 2023-02-28 |  | 2024-03-29 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196334 | REAITEKA INTERMEDIATE SCHOOL_TBD | Northern Cape | REAITEKA INTERMEDIATE SCHOOL | 300101776 | Joe Morolong | Project Initiation | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 585121 | 585121 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196338 | ST308/2021:STRUCTURAL ASSESSMENT | Northern Cape | ROODEPAN SECONDARY SCHOOL (NEW) | NEW | Sol Plaatjie | Tender | Active - Not Contracted | 2023-02-28 |  | 2024-03-29 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196342 | TBD:MAINTENANCE | Northern Cape | BATSWELETSE PRIMARY SCHOOL | 300100102 | Joe Morolong | Feasibility | Active - Contracted | 2022-08-05 |  | 2025-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196356 | ST052/2022-23 | Northern Cape | DIBOTSWA SECONDARY SCHOOL | 300100271 | Joe Morolong | Tender | Proposed | 2022-02-01 |  | 2022-10-20 |  |  | 0 | 1854939 | 1854939 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196357 | TBD_ DITSHIPENG | Northern Cape | DITSHIPENG INTERMEDIATE SCHOOL | 300100316 | Joe Morolong | Design | Proposed | 2022-02-11 |  | 2022-11-30 |  |  | 0 | 550000 | 550000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196359 | ST436/2022 | Northern Cape | STERNHAM INTERMEDIERE SKOOL | 300043308 | !Kheis | Construction 51% - 75% | Proposed | 2022-04-01 |  | 2024-03-29 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196363 | HALL | Northern Cape | FLOORS HIGH SCHOOL | 300011401 | Sol Plaatjie | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 3586114 | 3586114 | Education Infrastructure Grant | Upgrading and Additions
|  | 196365 | TBD- FRANCOIS VISSER | Northern Cape | FRANCOIS VISSER PRIMERE SKOOL | 300034303 | Khi-Ma | Project Initiation | Active - Contracted | 2022-05-11 |  | 2022-11-30 |  |  | 0 | 829172 | 829172 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196382 | ST033/2022-23:STRUCTURAL ASSESSMENT | Northern Cape | HO?RSKOOL ADAMANTIA | 300012401 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-10-28 |  |  | 0 | 1250000 | 1250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196387 | TBD1593578 | Northern Cape | HOERSKOOL HARTSWATER | 300017401 | Phokwane | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 5000 | 2000000 | 2005000 | Education Infrastructure Grant | Upgrading and Additions
|  | 196395 | R&R:FLOOD DAMAGE | Northern Cape | VAALLUS (NGK) PRIM?RE SKOOL | 300015208 | Siyancuma | Feasibility | Approved | 2023-02-28 |  | 2024-03-29 |  |  | 0 | 550000 | 550000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196411 | VREDESVALLEI PRIMARY SCHOOL_TBD | Northern Cape | VREDESVALLEI PRIMARY SCHOOL | 300041219 | Kai !Garib | Tender | Active - Not Contracted | 2022-05-05 |  | 2024-03-29 |  |  | 0 | 680588 | 680588 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196414 | TBD_ | Northern Cape | LEERKKRANS INTERMEDIATE SCHOOL | 300043305 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-10-31 |  |  | 0 | 461809 | 461809 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196415 | CONVERSION:FLUSH TOILETS | Northern Cape | LEHIKENG INTERMEDIATE SCHOOL | 300100840 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196428 | TBD_ MAOKA | Northern Cape | MAOKA PRIMARY SCHOOL | 300104003 | Joe Morolong | Feasibility | Active - Contracted | 2022-08-11 |  | 2024-03-31 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196430 | TBD_ MOEDI | Northern Cape | MOEDI PRIMARY SCHOOL | 300101273 | Joe Morolong | Project Initiation | Active - Contracted | 2022-06-10 |  | 2022-12-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196445 | TBD:SESHEN_CONVERSION | Northern Cape | SESHENG PRIMARY SCHOOL | 300101974 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196449 | R&R_SCHOOL & DAMAGED ROOF | Northern Cape | VELA-LANGA PRIMARY SCHOOL | 300041215 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-05-05 |  | 2024-03-31 |  |  | 0 | 1200000 | 1200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196452 | WRENCHVILLE PRIMARY SCHOOL_TBD | Northern Cape | WRENCHVILLE PRIMERE SKOOL | 300045218 | Ga-Segonyana | Feasibility | Approved | 2022-07-12 |  | 2024-03-29 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196847 | Maintenance 01 | Limpopo | Maitenance Project | Maintenance 01 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-05-01 | 2030-03-31 | 2021-04-01 | 2030-04-30 | 0 | 1 | 1 | Education Infrastructure Grant | Maintenance and Repairs
|  | 196920 | New 01 | Limpopo | New Building | 113 Biccard Street | Polokwane | Site Handed - Over to Contractor | Active - Contracted | 2020-04-01 | 2020-05-01 | 2030-03-31 | 2030-04-30 | 2030-04-30 | 1 | 1 | 2 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 196997 | LE21DPW00001 | Limpopo | ALLDAYS PRIMARY | 920213146 | Blouberg | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2021-02-01 | 2022-08-01 | 2022-08-01 | 2023-03-01 | 0 | 32400470 | 32400470 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 196998 | LE21DPW00002 | Limpopo | Leduma Mahume(At old Moreku Secondary Site) | 924641968 | Makhuduthamaga | Construction 76% - 99% | Active - Contracted | 2019-04-01 | 2021-02-04 | 2022-08-04 | 2022-08-04 | 2023-03-01 | 0 | 28887547 | 28887547 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 196999 | LE21DPW00003 | Limpopo | MAHLAGAUME PRIMARY | 925620428 | Greater Tubatse/Fetakgomo | Construction 51% - 75% | Active - Contracted | 2019-04-01 | 2021-01-29 | 2023-07-29 | 2022-07-29 | 2022-07-29 | 0 | 32202523 | 32202523 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197000 | LE21DPW00004 | Limpopo | NALEDI YA MESO SECONDARY | 924650238 | Elias Motsoaledi | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2021-02-05 | 2023-03-31 | 2022-08-04 | 2022-08-18 | 0 | 26895479 | 26895479 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197002 | LE21DPW00006 | Limpopo | MARUDE SECONDARY (FORMER VECCO COLLEGE) | 905332030 | Thulamela | Construction 51% - 75% | Active - Contracted | 2019-04-01 | 2021-02-03 | 2023-03-31 | 2023-02-03 | 2023-02-03 | 0 | 41080270 | 41080270 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197003 | LE21DPW00007 | Limpopo | GIDELA SECONDARY | 912521543 | Greater Giyani | Construction 26% - 50% | Active - Contracted | 2019-04-01 | 2021-01-26 | 2022-07-26 | 2022-07-26 | 2023-03-01 | 0 | 26988210 | 26988210 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197004 | LE21DOE03013 | Limpopo | Mangolwane Secondary | 924641142 | Makhuduthamaga | Practical Completion (100%) | Active - Contracted | 2020-06-24 | 2020-06-25 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 348506 | 1936142 | 2284648 | Education Infrastructure Grant | Upgrading and Additions
|  | 197007 | Rehab 02 | Limpopo | Rehabilitation,Renovations and Refurbishment Programme | Rehab 02 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-05-01 | 2024-06-30 | 2024-07-30 | 2024-09-30 | 1 | 0 | 1 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197008 | Upgrades02 | Limpopo | Upgrades 02 | Upgrades and Addition Progarmme | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-06-30 | 2030-09-30 | 2030-09-30 | 2030-09-30 | 1 | 1 | 2 | Education Infrastructure Grant | Upgrading and Additions
|  | 197035 | VAALOEVER | North West | VAALOEVER CON=MBINED SCHOOL | VAALOEVER | Lekwa-Teemane | Feasibility | Approved | 2021-01-15 |  | 2026-03-31 |  |  | 0 | 35000000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197036 | OPADIATLA PR | North West | OPADIATLA PRIMARY SCHOOL | OPADIATLA PR | Ditsobotla | Feasibility | Approved | 2019-01-15 |  | 2026-03-31 |  |  | 0 | 35000000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197037 | MOROKWENG PRIMARY SCHOOL | North West | MOROKWENG PRIMARY SCHOOL | MOROKWENG PR | Kagisano | Feasibility | Approved | 2019-01-15 |  | 2026-03-31 |  |  | 0 | 350000000 | 350000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197038 | GAOTIME SECON | North West | GAOTIME SECONDARY | GAOTIME SECONDARY SCHOOL | Moses Kotane | Feasibility | Approved | 2019-01-01 |  | 2026-03-31 |  |  | 0 | 35000000 | 35000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197060 | MOGAWANE MOSHOETE PRIMARY 001 | North West | MOGAWANE MOSHOETE PRIMARY SCHOOL | MOGAWANE MOSHOETE PRIMARY SCHOOL | Tswaing | Feasibility | Approved | 2019-01-15 |  | 2026-03-31 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197100 | IDT Management Fees | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-03-30 | 2026-03-30 | 2026-03-31 | 0 | 40000000 | 40000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 197101 | DBSA Management Fees | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-03-30 | 2024-03-30 | 2024-03-31 | 0 | 16000000 | 16000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 197102 | The Mvula Trust Management fees | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 76% - 99% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2030-03-30 | 2024-03-30 | 2024-03-31 | 0 | 24000000 | 24000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 197104 | MDOE/NEW/21-22/01(TBC) | Mpumalanga | Kwandisamfuyo Primary School | 800008789 | Msukaligwa | Project Initiation | Proposed | 2021-04-01 |  | 2024-06-01 |  |  | 7697760 | 54984000 | 62681760 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197105 | MDOE/NEW/21-22/02(TBC) | Mpumalanga | New Perdekop Primary School | new | Dr Pixley Ka Isaka Seme | Project Initiation | Proposed | 2021-04-01 |  | 2024-10-01 |  |  | 7697760 | 54984000 | 62681760 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197106 | MDOE/NEW/19-20/020 | Mpumalanga | Trichardtsfontein Primary School | 800023788 | Govan Mbeki | Feasibility | Proposed | 2023-04-01 |  | 2024-10-31 |  |  | 2663510 | 14797275 | 17460785 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197107 | MDOE/NEW/19-20/021 | Mpumalanga | Volksrust Primary School | 800024711 | Dr Pixley Ka Isaka Seme | Project Initiation | Proposed | 2023-04-01 |  | 2024-10-31 |  |  | 2704496 | 15024979 | 17729475 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197108 | MDOE/UPG/002/20-21(DPWRT/051/19) | Mpumalanga | Badplaas Laerskool | 800008953 | Chief Albert Luthuli | Design | Active - Contracted | 2022-04-01 |  | 2024-04-11 |  |  | 618073 | 3433738 | 4051811 | Education Infrastructure Grant | Upgrading and Additions
|  | 197110 | DPWRT/SAN/336/20M | Mpumalanga | Setsheng Secondary School | 800020396 | Dipaleseng | Practical Completion (100%) | Active - Contracted | 2021-05-01 |  | 2024-10-01 |  |  | 2432922 | 17378013 | 19810935 | Equitable Share | Upgrading and Additions
|  | 197111 | MDOE/UPG/1003/21-22 | Mpumalanga | Imisebeyelanga Primary School | 800006197 | Lekwa | Design | Active - Contracted | 2022-04-01 |  | 2024-10-01 |  |  | 201037 | 2010368 | 2211405 | Education Infrastructure Grant | Upgrading and Additions
|  | 197112 | MDOE/UPG/1005/21-22 | Mpumalanga | Emoyeni Primary School | 800003608 | Mkhondo | Design | Active - Contracted | 2021-04-01 |  | 2024-05-31 |  |  | 76654 | 766542 | 843196 | Education Infrastructure Grant | Upgrading and Additions
|  | 197122 | MDOE/UPG/144/21-22 | Mpumalanga | Bee Maseko Combined School | 800028746 | Msukaligwa | Project Initiation | Proposed | 2021-04-01 |  | 2024-10-01 |  |  | 733256 | 5237546 | 5970802 | Equitable Share | Upgrading and Additions
|  | 197123 | MDOE/UPG/145/21-22 | Mpumalanga | Evulinqondo Primary School | 800004101 | Msukaligwa | Project Initiation | Proposed | 2021-04-01 |  | 2023-10-01 |  |  | 665225 | 4751606 | 5416831 | Education Infrastructure Grant | Upgrading and Additions
|  | 197124 | MDOE/UPG/102/22-23 | Mpumalanga | Torbenite Primary School | 800023762 | Msukaligwa | Project Initiation | Proposed | 2021-04-01 |  | 2025-02-15 |  |  | 392000 | 2800000 | 3192000 | Equitable Share | Upgrading and Additions
|  | 197125 | MDOE/UPG/103/22-23 | Mpumalanga | Zendelingspost Combined School | 800025858 | Mkhondo | Design | Active - Not Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 392000 | 2800000 | 3192000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197126 | DPWRT/SAN/330/20MP(HLELIMFUNDO S--------- | Mpumalanga | Hlelimfundo Secondary School | 800035485 | Dr Pixley Ka Isaka Seme | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-10-01 |  |  | 285000 | 1710000 | 1995000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197127 | MDOE/SAN/1059/2023( DPWRT/SAN/336/20/MP ) | Mpumalanga | Ekuphakameni Primary School | 800003269 | Chief Albert Luthuli | Tender | Active - Not Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 337284 | 2409173 | 2746457 | Education Infrastructure Grant | Upgrading and Additions
|  | 197128 | MDOE/NEW/20-21/004 | Mpumalanga | Mphephethe Primary School | 800015586 | Steve Tshwete | Feasibility | Active - Not Contracted | 2021-04-15 |  | 2025-09-30 |  |  | 4115166 | 29394040 | 33509206 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197129 | MDOE/NEW/20-21/022 | Mpumalanga | New Vezikgono Senior Phase School | NEW | Thembisile | Feasibility | Active - Not Contracted | 2022-01-01 |  | 2026-01-31 |  |  | 5589352 | 31051956 | 36641308 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197132 | MDOE/MAIN/106/21-22 | Mpumalanga | Botleng Secondary School | 800001636 | Victor Khanye | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 309888 | 3098877 | 3408765 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197134 | MDOE/MAIN/021/19-20 | Mpumalanga | Sibongamandla secondary school | 800020693 | Emalahleni | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2021-06-15 | 2023-11-30 | 2023-03-31 | 2023-03-31 | 634199 | 2239875 | 2874074 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197136 | DPWRT/036/19MP | Mpumalanga | Thandulwazi Primary School | 800022970 | Thembisile | Construction 26% - 50% | Active - Contracted | 2022-04-15 |  | 2023-03-31 |  |  | 248408 | 2484077 | 2732485 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197145 | DPWRT/153/18/MP | Mpumalanga | Pine Ridge Combined School | 800018564 | Emalahleni | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 1598604 | 6717874 | 8316478 | Education Infrastructure Grant | Upgrading and Additions
|  | 197154 | MDOE/NEW/20-21/003 | Mpumalanga | New Emalahleni Primary School | new | Emalahleni | Project Initiation | Proposed | 2021-05-01 |  | 2025-01-31 |  |  | 5466380 | 39045568 | 44511948 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197155 | MDOE/NEW/21-22/03 | Mpumalanga | New Moloto Primary School | New | Thembisile | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-02-01 |  |  | 7697760 | 54984000 | 62681760 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197156 | MDOE/NEW/21-22/05 | Mpumalanga | New Empumelelweni Primary School | new | Thembisile | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-10-01 |  |  | 7697760 | 54984000 | 62681760 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197157 | MDOE/NEW/21-22/04 | Mpumalanga | New Doornkop Secondary School | new | Steve Tshwete | Design | Active - Not Contracted | 2021-04-01 |  | 2025-10-01 |  |  | 8784854 | 59915856 | 68700710 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197158 | DoE/NKD/MAIN/ 066 | Mpumalanga | Ebhudlweni Primary School | 800003079 | Emakhazeni | Project Initiation | Active - Not Contracted | 2021-04-15 | 2021-04-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 68917 | 275668 | 344585 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197160 | MDOE/MAIN/22-23/145 | Mpumalanga | Mafa Max Motloung Secondary School | 800029397 | Victor Khanye | Design | Active - Not Contracted | 2021-04-15 |  | 2023-09-30 |  |  | 368820 | 3688198 | 4057018 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197165 | MDOE/MAIN/22-23/32 | Mpumalanga | Mandlethu Secondary School | 800012229 | Thembisile | Terminated | Active - Not Contracted | 2021-04-15 | 2021-04-30 | 2024-08-30 | 2024-09-30 | 2024-09-30 | 577874 | 5778741 | 6356615 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197169 | DoE/NKD/MAIN/107 | Mpumalanga | Ndedema Primary School | 800016386 | Dr JS Moroka | Design | Active - Not Contracted | 2021-04-15 |  | 2025-09-30 |  |  | 248408 | 2484077 | 2732485 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 197170 | DoE/NKD/MAIN/1112 | Mpumalanga | Nkosiphile Primary School | 800017053 | Dr JS Moroka | Design | Active - Not Contracted | 2021-04-15 |  | 2024-03-31 |  |  | 43111 | 431114 | 474225 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197172 | DoE/NKD/MAIN/110 | Mpumalanga | Sithenjisiwe Secondary School | 800021386 | Dr JS Moroka | Design | Active - Not Contracted | 2021-04-15 |  | 2024-03-31 |  |  | 42444 | 1867540 | 1909984 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197173 | PWRT/MAIN/046/21/MP | Mpumalanga | Siyabuswa Primary School | 800021477 | Dr JS Moroka | Construction 1% - 25% | Active - Contracted | 2021-04-15 |  | 2024-03-31 |  |  | 221478 | 2214784 | 2436262 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197175 | DPWRT/070/21MP(MATLUSHE PRIMARY)--------- | Mpumalanga | Matlushe Primary School | 800034897 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-02 |  | 2026-03-31 |  |  | 4442135 | 31729536 | 36171671 | Equitable Share | New or Replaced Infrastructure
|  | 197176 | MDOE/NEW/20-21/004 (Mphephethe P school) | Mpumalanga | Mphephethe Primary School | 800015586 | Steve Tshwete | Design | Active - Not Contracted | 2021-04-01 |  | 2024-09-01 |  |  | 4115166 | 29394040 | 33509206 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197177 | MDOE/UPG/1010/21-22 | Mpumalanga | Mavimbela Primary School | 800035104 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 4698196 | 33558544 | 38256740 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 197178 | N/A(DPWRT/027/19/MP) | Mpumalanga | Masuku Primary School | 800013086 | Dr JS Moroka | Construction 1% - 25% | Active - Contracted | 2021-04-15 |  | 2022-09-30 |  |  | 1008000 | 7200000 | 8208000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197180 | MDOE/UPG/015/20-21 | Mpumalanga | Sithenjisiwe Secondary School | 800021386 | Dr JS Moroka | Design | Active - Not Contracted | 2021-04-15 |  | 2024-05-31 |  |  | 1193222 | 8523012 | 9716234 | Education Infrastructure Grant | Upgrading and Additions
|  | 197182 | MDOE/UPG/1021/21-22 | Mpumalanga | HTS Middelburg | 800004945 | Steve Tshwete | Design | Active - Not Contracted | 2021-04-15 |  | 2022-09-30 |  |  | 1435200 | 6517021 | 7952221 | Education Infrastructure Grant | Upgrading and Additions
|  | 197183 | MDOE/UPG/1026/21-22 | Mpumalanga | Thanduxolo Special School | 800005496 | Emalahleni | Design | Active - Not Contracted | 2021-04-15 |  | 2023-11-24 |  |  | 1199219 | 7495116 | 8694335 | Education Infrastructure Grant | Upgrading and Additions
|  | 197184 | MDOE/UPG/1000/21-22 | Mpumalanga | Ebhudlweni Primary School | 800003079 | Emakhazeni | Design | Active - Not Contracted | 2021-04-15 |  | 2024-05-31 |  |  | 1053020 | 7521572 | 8574592 | Education Infrastructure Grant | Upgrading and Additions
|  | 197185 | MDOE/UPG/1006/21-22 | Mpumalanga | Prince SJ Mahlangu Primary School | 800018713 | Dr JS Moroka | Terminated | Active - Not Contracted | 2021-04-15 |  | 2024-09-30 |  |  | 1042145 | 7443890 | 8486035 | Education Infrastructure Grant | Upgrading and Additions
|  | 197186 | MDOE/UPG/1007/21-22 | Mpumalanga | Khayalethu Primary School | 800007674 | Emalahleni | Design | Active - Not Contracted | 2021-04-15 |  | 2024-09-30 |  |  | 277200 | 1980000 | 2257200 | Education Infrastructure Grant | Upgrading and Additions
|  | 197187 | MDOE/UPG/1011/21-22 | Mpumalanga | Sibisi Primary School | 800020669 | Dr JS Moroka | Design | Active - Not Contracted | 2021-04-15 |  | 2024-06-28 |  |  | 163800 | 1170000 | 1333800 | Education Infrastructure Grant | Upgrading and Additions
|  | 197192 | MDOE/UPG/1016/21-22 | Mpumalanga | Bonginsimbi Secondary School | 800001412 | Emalahleni | Project Initiation | Active - Contracted | 2021-04-15 |  | 2025-03-31 |  |  | 212800 | 1520000 | 1732800 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197193 | DPWRT/SAN/248/20MP(MAKERANA PRIM--------- | Mpumalanga | Makerana Primary School | 800011841 | Thembisile | Project Initiation | Proposed | 2021-04-01 |  | 2023-03-31 |  |  | 158000 | 350000 | 508000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197194 | MDOE/UPG/1028/20-21 | Mpumalanga | Laerskool Ellof Primary School | 800009126 | Victor Khanye | Project Initiation | Proposed | 2021-04-01 |  | 2027-03-31 |  |  | 1013417 | 7238690 | 8252107 | Education Infrastructure Grant | Upgrading and Additions
|  | 197196 | DPWRT/SAN/271/20MP(MMADIMO PRIM)--------- | Mpumalanga | Mmadimo Primary School | 800014597 | Dr JS Moroka | Project Initiation | Proposed | 2021-04-01 |  | 2023-01-31 |  |  | 1435888 | 10256345 | 11692233 | Education Infrastructure Grant | Upgrading and Additions
|  | 197208 | MDOE/UPG/101/22-23 | Mpumalanga | Emthonjeni Primary School | 800003665 | Thembisile | Terminated | Active - Contracted | 2021-01-20 | 2022-04-30 | 2024-04-30 | 2023-03-30 | 2023-05-24 | 354711 | 2533651 | 2888362 | Education Infrastructure Grant | Upgrading and Additions
|  | 197216 | DPWRT/SAN/250/20/MP | Mpumalanga | Ndzudza Mabhoko | 800016535 | Thembisile | Construction 1% - 25% | Active - Contracted | 2021-04-01 | 2022-01-15 | 2023-05-16 | 2023-05-30 | 2023-06-30 | 226800 | 1620000 | 1846800 | Education Infrastructure Grant | Upgrading and Additions
|  | 197223 | MDOE/SAN/1060/2024(DPWRT/SAN/337/20/MP) | Mpumalanga | Hloniphani Primary School | 800005462 | Chief Albert Luthuli | Design | Active - Not Contracted | 2021-05-01 |  | 2022-09-15 |  |  | 88200 | 630000 | 718200 | Education Infrastructure Grant | Upgrading and Additions
|  | 197229 | MDOE/SAN/1061/2025(DPWRT/SAN/338/20/MP) | Mpumalanga | Issabeladale Primary School | 800006635 | Msukaligwa | Project Initiation | Approved | 2021-04-01 |  | 2023-10-01 |  |  | 285763 | 2041162 | 2326925 | Education Infrastructure Grant | Upgrading and Additions
|  | 197235 | DPWRT/SAN/339/20/MP | Mpumalanga | Umbhejeka Primary School | 800024232 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2021-05-01 | 2021-10-31 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 88200 | 1547897 | 1636097 | Education Infrastructure Grant | Upgrading and Additions
|  | 197239 | MDOE/SAN/149/2020 | Mpumalanga | Siyathokoza Secondary School | 800021584 | Emalahleni | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 176400 | 1260000 | 1436400 | Education Infrastructure Grant | Upgrading and Additions
|  | 197241 | N/A(DPWRT/SAN/275/20/MP) | Mpumalanga | Ramoshidi Secondary School | 800019119 | Dr JS Moroka | Construction 51% - 75% | Active - Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 201600 | 1440000 | 1641600 | Education Infrastructure Grant | Upgrading and Additions
|  | 197242 | MDOE/MAIN/22-23/128 | Mpumalanga | Khutsong Primary School | 800007963 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-09-15 |  |  | 0 | 3876926 | 3876926 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197243 | MDOE/SAN/1063/2027(DPWRT/SAN/340/20/MP) | Mpumalanga | Hambanatsi Primary School | 800005009 | Chief Albert Luthuli | Project Initiation | Proposed | 2021-05-01 |  | 2023-10-01 |  |  | 88200 | 630000 | 718200 | Education Infrastructure Grant | Upgrading and Additions
|  | 197252 | DPWRT/SAN/342/20/MP | Mpumalanga | Skoonuitsig Primary School | 800021873 | Lekwa | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2023-10-01 |  |  | 362821 | 2591579 | 2954400 | Education Infrastructure Grant | Upgrading and Additions
|  | 197253 | DPWRT/SAN/253/20MP(ROROBHANI SEC--------- | Mpumalanga | Rorobhani Senior Primary School | 800035601 | Thembisile | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 249535 | 1782392 | 2031927 | Education Infrastructure Grant | Upgrading and Additions
|  | 197258 | MDOE/SAN/294/2020 | Mpumalanga | Bongani Primary School | 800001339 | Thembisile | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 168885 | 1350000 | 1518885 | Education Infrastructure Grant | Upgrading and Additions
|  | 197259 | DPWRT/046/21MP MBONGO P------------------ | Mpumalanga | Mbongo Primary School | 800013763 | Dr JS Moroka | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 226800 | 1620000 | 1846800 | Education Infrastructure Grant | Upgrading and Additions
|  | 197260 | DPWRT/051/21MP MZAMO SEC----------------- | Mpumalanga | Mzamo Primary School | 800016105 | Emalahleni | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 201600 | 1440000 | 1641600 | Equitable Share | Upgrading and Additions
|  | 197261 | DPWRT/043/17/2020 | Mpumalanga | Moloto Primary School | 800015073 | Thembisile | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 201600 | 1440000 | 1641600 | Equitable Share | Upgrading and Additions
|  | 197262 | DPWRT/050/21MP SELE SEC------------------ | Mpumalanga | Sele Secondary School | 800020248 | Dr JS Moroka | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 30240 | 216000 | 246240 | Education Infrastructure Grant | Upgrading and Additions
|  | 197263 | DPWRT/SAN/281/20/MP | Mpumalanga | Arnot Primary School | 800000349 | Steve Tshwete | Design | Proposed | 2021-04-01 |  | 2025-09-15 |  |  | 19320 | 924344 | 943664 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197264 | DPWRT/047/21MP EKUKHANYENI P------------- | Mpumalanga | Ekukhanyeni primary school | 800003236 | Dr JS Moroka | Design | Proposed | 2021-04-01 |  | 2025-09-15 |  |  | 0 | 2293653 | 2293653 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197265 | MDOE/SAN/1066/2030(DPWRT/SAN/343/20/MP) | Mpumalanga | Phumelele Primary School | 800019836 | Chief Albert Luthuli | Construction 1% - 25% | Active - Contracted | 2021-05-01 |  | 2023-10-01 |  |  | 163800 | 1170000 | 1333800 | Education Infrastructure Grant | Upgrading and Additions
|  | 197266 | DPWRT/SAN/094/20MP EKUPHUMULENI --------- | Mpumalanga | Ekuphumuleni Primary School | 800003301 | Chief Albert Luthuli | Project Initiation | Proposed | 2021-05-01 |  | 2023-10-01 |  |  | 63000 | 450000 | 513000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197267 | MDOE/SAN/259/2020 | Mpumalanga | Siphokuhle Primary School | 800019737 | Mkhondo | Design | Proposed | 2021-05-01 |  | 2023-10-01 |  |  | 163800 | 1170000 | 1333800 | Education Infrastructure Grant | Upgrading and Additions
|  | 197268 | Delete | Mpumalanga | Itsoseng Primary School | 800026294 | Dr JS Moroka | Design | Proposed | 2021-04-01 |  | 2022-09-15 |  |  | 285973 | 2042665 | 2328638 | Education Infrastructure Grant | Upgrading and Additions
|  | 197282 | DPWRT/SAN/309/20MP | Mpumalanga | Makhosonke Primary School | 800011916 | Chief Albert Luthuli | Practical Completion (100%) | Active - Contracted | 2020-10-02 | 2020-10-06 | 2022-09-15 | 2021-02-08 | 2021-09-30 | 547227 | 2316149 | 2863376 | Education Infrastructure Grant | Upgrading and Additions
|  | 197285 | MDOE/UPG/005/21-22 | Mpumalanga | Homuzeya Primary School | 800035094 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-03-01 |  | 2025-02-13 |  |  | 686000 | 4900000 | 5586000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197287 | MDOE/UPG/1002/21-22 | Mpumalanga | Khokhovela Higher Primary School | 800034910 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-06-28 |  |  | 350074 | 3500736 | 3850810 | Education Infrastructure Grant | Upgrading and Additions
|  | 197288 | MDOE/UPG/1004/21-22 | Mpumalanga | Nkwenkwezi Primary School | 800034952 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-04-26 |  |  | 1552988 | 11092770 | 12645758 | Education Infrastructure Grant | Upgrading and Additions
|  | 197291 | MDOE/SAN/129/2020 | Mpumalanga | Vandama Primary School | 800035020 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2022-07-28 |  |  | 200346 | 1431040 | 1631386 | Education Infrastructure Grant | Upgrading and Additions
|  | 197301 | MDOE/UPG/100/22-23 | Mpumalanga | MOKGOMANA Primary School | 800034870 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-09-15 |  |  | 392000 | 2800000 | 3192000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197306 | MDOE/SAN/1025/2020 | Mpumalanga | Dlamakhosi Secondary School | 800034951 | Bushbuckridge | Project Initiation | Proposed | 2022-04-01 |  | 2024-03-28 |  |  | 38980 | 278425 | 317405 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197375 | MDOE/SAN/311/2020 | Mpumalanga | Mosipa Secondary school | 800034901 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-03-31 |  |  | 168000 | 1200000 | 1368000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197390 | MDOE/UPG/1072/20-21 | Mpumalanga | Morage Primary School | 800034920 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2020-04-01 |  | 2024-04-30 |  |  | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Upgrading and Additions
|  | 197445 | MDOE/UPG/134/20-21 | Mpumalanga | Ntshuxeko Primary School | 800035498 | Bushbuckridge | Pre - Feasibility | Active - Not Contracted | 2020-04-01 |  | 2024-07-26 |  |  | 709654 | 24598750 | 25308404 | Education Infrastructure Grant | Upgrading and Additions
|  | 197532 | MDOE/MAIN/22-23/16 | Mpumalanga | Khetsalwati Secondary School | 800002774 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 412356 | 4123567 | 4535923 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197563 | DPWRT/095/21/MP 1 | Mpumalanga | Masinakane Special School | 800029421 | Dr JS Moroka | Construction 76% - 99% | Active - Contracted | 2020-06-01 | 2020-07-01 | 2024-08-23 | 2024-09-23 | 2024-09-23 | 304156 | 2172548 | 2476704 | Education Infrastructure Grant | Upgrading and Additions
|  | 197566 | MDOE/MAIN/22-23/26 | Mpumalanga | Lundanda Primary school | 800002022 | Mbombela | Project Initiation | Proposed | 2022-08-01 |  | 2024-01-24 |  |  | 454388 | 4543888 | 4998276 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197567 | DoE/EHL/MAIN/106 | Mpumalanga | Bongani Primary School (Maint) | 800001347 | Mbombela | Site Handed - Over to Contractor | Active - Contracted | 2021-04-01 | 2021-05-01 | 2024-11-30 | 2024-11-30 | 2024-11-30 | 13824 | 98747 | 112571 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197568 | MDOE/MAIN/22-23/04 | Mpumalanga | Bongani primary school | 800001339 | Thembisile | Project Initiation | Proposed | 2022-08-01 |  | 2024-04-01 |  |  | 465872 | 4658723 | 5124595 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197569 | MDOE/MAIN/22-23/24 | Mpumalanga | Lomatidraai Primary school | 800010645 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-05-01 |  | 2024-11-02 |  |  | 308407 | 3084077 | 3392484 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197570 | MDOE/MAIN/02/21-22 | Mpumalanga | Engelsdraai Primary School | 800003723 | Msukaligwa | Project Initiation | Proposed | 2020-05-01 |  | 2025-03-31 |  |  | 199547 | 1425336 | 1624883 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197572 | MDOE/MAIN/22-23/28 | Mpumalanga | Magubha primary school | 800011551 | Nkomazi | Project Initiation | Proposed | 2022-05-01 |  | 2024-11-01 |  |  | 398956 | 3989569 | 4388525 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197578 | MDOE/PG/1001/20-21 | Mpumalanga | SETSHENG SECONDARY SCHOOL | 800020396 | Dipaleseng | Project Initiation | Proposed | 2021-04-01 |  | 2024-06-30 |  |  | 698659 | 5822158 | 6520817 | Education Infrastructure Grant | Upgrading and Additions
|  | 197580 | MDOE/MAIN/22-23/06 | Mpumalanga | Chweni Primary School | 800002147 | Mbombela | Construction 26% - 50% | Active - Not Contracted | 2021-05-01 | 2021-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 397456 | 3974569 | 4372025 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197603 | DoE-SERVICE PROVIDER | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2017-06-02 |  | 2025-07-30 |  |  | 120000000 | 0 | 120000000 | Equitable Share | Non-Infrastructure
|  | 197757 | DPWRT/095/21/MP | Mpumalanga | Lekazi Secondary School | 800010124 | Mbombela | Construction 26% - 50% | Active - Contracted | 2021-04-15 |  | 2024-09-01 |  |  | 252000 | 1800000 | 2052000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 197800 | MDOE/UPG/1022/21-22(DPWRT/324/19/MP) | Mpumalanga | Laerskool Laeveld | 800009381 | Mbombela | Tender | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 6157358 | 23812126 | 29969484 | Education Infrastructure Grant | Upgrading and Additions
|  | 197805 | DPWRT/2479/21MP(LAERSKOOL BERGLA--------- | Mpumalanga | Laerskool Bergland | 800009001 | Mbombela | Tender | Active - Not Contracted | 2020-04-01 |  | 2024-04-26 |  |  | 3485100 | 16042053 | 19527153 | Education Infrastructure Grant | Upgrading and Additions
|  | 197811 | MDOE/UPG/10203/21-22(DPWRT/072/19MP) | Mpumalanga | Nelspruit Primary School | 800016592 | Mbombela | Tender | Active - Not Contracted | 2020-04-01 |  | 2023-10-01 |  |  | 4660035 | 19084439 | 23744474 | Education Infrastructure Grant | Upgrading and Additions
|  | 197829 | LE20TMT17007 | Limpopo | J.H Moloto Secondary School | 922220279 | Polokwane | Tender | Active - Not Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 290037 | 4000000 | 4290037 | Education Infrastructure Grant | Upgrading and Additions
|  | 197830 | LE20TMT17006 | Limpopo | Hlalukweni secondary | 911361781 | Collins Chabane | Construction 1% - 25% | Active - Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 547685 | 3000000 | 3547685 | Education Infrastructure Grant | Upgrading and Additions
|  | 197831 | LE20TMT17045 | Limpopo | Mabine Primary School | 913420239 | Greater Giyani | Practical Completion (100%) | Active - Contracted | 2020-04-01 | 2020-04-02 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 165357 | 2066965 | 2232322 | Education Infrastructure Grant | Upgrading and Additions
|  | 197832 | LE20TMT17044 | Limpopo | Rethushegile Secondary School | 918510927 | Greater Letaba | Tender | Active - Contracted | 2020-04-01 |  | 2025-03-31 |  |  | 381391 | 7000000 | 7381391 | Education Infrastructure Grant | Upgrading and Additions
|  | 197833 | LE20TMT17048 | Limpopo | Ramonokane Primary | 996606604 | Elias Motsoaledi | On Hold | Active - Not Contracted | 2020-04-01 | 2020-04-02 | 2023-03-31 | 2021-03-31 | 2025-03-31 | 86087 | 1900000 | 1986087 | Education Infrastructure Grant | Upgrading and Additions
|  | 197834 | LE20TMT17056 | Limpopo | XIHOKO PRIMARY | 913420741 | Greater Tzaneen | On Hold | Active - Not Contracted | 2020-04-01 |  | 2023-03-31 |  |  | 86585 | 1786585 | 1873170 | Education Infrastructure Grant | Upgrading and Additions
|  | 197990 | OR-031111 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2022-04-01 | 2022-04-22 | 2023-01-06 | 2023-02-01 | 2023-03-27 | 0 | 325536 | 325536 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198003 | TBD:REPAIRS TO ABLUTION | Northern Cape | ROBANYANE TOTO II PRIMARY SCHOOL | 300101851 | Ga-Segonyana | Feasibility | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 500957 | 500957 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198004 | GDF - TBD | Northern Cape | RUSFONTEIN PRIMARY SCHOOL | 300101862 | Joe Morolong | Site Handed - Over to Contractor | Active - Contracted | 2022-04-01 | 2022-04-03 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 1200000 | 1200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198006 | GDF -TBD:ELECTRICITY_WATER_CONVERSION | Northern Cape | SEDIBENG PS | 300101901 | Ga-Segonyana | Feasibility | Active - Not Contracted | 2022-04-02 |  | 2023-03-31 |  |  | 0 | 819498 | 819498 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198062 | LE06LDOE00001 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 64807455 | 64807455 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198071 | MDOE/NEW/23-2024/001 | Mpumalanga | White River Primary School | new | Mbombela | Project Initiation | Proposed | 2021-04-01 |  | 2025-10-31 |  |  | 7697760 | 54984000 | 62681760 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 198112 | P9011727 | Eastern Cape | JOHN BISSEKER SENIOR SECONDARY SCHOOL | 200200292 | Buffalo City | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 16000000 | 16000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 198126 | P9011533 | Eastern Cape | VANANI FARM SCHOOL | 200200882 | Buffalo City | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 198129 | P9011720 | Eastern Cape | OVERTON PRIMARY SCHOOL | 200200673 | Buffalo City | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 9658748 | 9658748 | Education Infrastructure Grant | Upgrading and Additions
|  | 198157 | P9011719 | Eastern Cape | LANGUAGE ACADEMY (NOZIZWE JPS) | 200300496 | Mbhashe | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198160 | P9007181 | Eastern Cape | CLARKEBURY AGRICULTURAL SCHOOL (Prefab Hostel) | 200400084 | Engcobo | Practical Completion (100%) | Active - Not Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 30943129 | 30943129 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198161 | P9011543 | Eastern Cape | FALTEIN SECONDARY SCHOOL | 200300079 | Enoch Mgijima | Practical Completion (100%) | Active - Contracted | 2020-02-03 | 2020-08-03 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 14614914 | 14614914 | Education Infrastructure Grant | Upgrading and Additions
|  | 198163 | P9004815 | Eastern Cape | JAMANGILE SENIOR SECONDARY SCHOOL | 200400282 | Elundini | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 198211 | P9006223 | Eastern Cape | SONWABILE PRIMARY SCHOOL | 200200805 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 847568 | 847568 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198228 | P9007180 | Eastern Cape | CLARKEBURY AGRICULTURAL SCHOOL (Hostel Renovations) | 200400084 | Engcobo | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 627609 | 627609 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 198246 | P9009667_ | Eastern Cape | UPPER QORA JUNIOR SECONDARY SCHOOL | 200300638 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-05-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 259086 | 259086 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198250 | P9008083_ | Eastern Cape | MTYOBO PUBLIC PRIMARY SCHOOL | 200100537 | Ndlambe | Design | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 150000 | 0 | 150000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198302 | P9011582 | Eastern Cape | GIAMA Condition Assesments | 200999925 | Buffalo City | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2026-03-31 |  |  | 0 | 87213480 | 87213480 | Education Infrastructure Grant | Upgrading and Additions
|  | 198316 | P9011586 | Eastern Cape | DUDUMAYO SENIOR SECONDARY SCHOOL | 200400136 | King Sabata Dalindyebo | Construction 1% - 25% | Active - Contracted | 2020-07-01 | 2020-08-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 12007282 | 12007282 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198319 | P9011549 | Eastern Cape | CLAREMONT JUNIOR PRIMARY SCHOOL | 200600980 | Enoch Mgijima | Construction 76% - 99% | Active - Contracted | 2020-04-02 | 2020-08-03 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 3017139 | 3017139 | Education Infrastructure Grant | Upgrading and Additions
|  | 198320 | P0003732_ | Eastern Cape | JONGILIZWE SENIOR SECONDARY SCHOOL | 200400293 | Mhlontlo | Practical Completion (100%) | Active - Contracted | 2012-11-01 | 2013-01-31 | 2026-03-31 | 2025-03-31 | 2025-03-31 | 0 | 27391834 | 27391834 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198341 | OR-031076 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2022-04-08 | 2022-04-22 | 2022-08-19 | 2022-09-30 | 2022-10-07 | 0 | 141562 | 141562 | Education Infrastructure Grant | Non-Infrastructure
|  | 198351 | P9003536 | Eastern Cape | WATER , SANITATION & DESLUDGING | 200999925 | Buffalo City | Feasibility | Active - Contracted | 2020-02-03 |  | 2026-03-31 |  |  | 0 | 146733036 | 146733036 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198355 | P9008588 | Eastern Cape | FLOWER JUNIOR SECONDARY SCHOOL | 200300840 | Mbhashe | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-04-03 | 2025-03-01 | 2025-03-01 | 2025-03-31 | 215009 | 1264757 | 1479766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198440 | P9011591 | Eastern Cape | NOBANTU JUNIOR PRIMARY SCHOOL | 200200590 | Buffalo City | Design | Active - Not Contracted | 2020-07-01 |  | 2026-03-31 |  |  | 0 | 11466609 | 11466609 | Education Infrastructure Grant | Upgrading and Additions
|  | 198443 | P9011725 | Eastern Cape | PORT ALFRED JUNIOR SECONDARY SCHOOL | 200100633 | Ndlambe | Design | Active - Contracted | 2021-04-01 | 2021-04-03 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 0 | 600000 | 600000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198445 | P9004748 | Eastern Cape | MANZANA SENIOR SECONDARY SCHOOL | 200400487 | Enoch Mgijima | Design | Active - Not Contracted | 2020-07-01 |  | 2026-03-31 |  |  | 0 | 8109270 | 8109270 | Education Infrastructure Grant | Upgrading and Additions
|  | 198465 | P9007042 | Eastern Cape | NOMBULELO SECONDARY SCHOOL | 200100580 | Makana | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-04-03 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 938815 | 1632075 | 2570890 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198466 | P9009808_ | Eastern Cape | XUME PRIMARY SCHOOL | 200300669 | Mnquma | Construction 51% - 75% | Active - Contracted | 2020-04-01 | 2020-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 6430403 | 6430403 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198467 | P9011595 | Eastern Cape | NTLALO PUBLIC SECONDARY SCHOOL | 200600638 | Senqu | Design | Active - Not Contracted | 2021-04-01 | 2021-04-03 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 0 | 1227301 | 1227301 | Education Infrastructure Grant | Upgrading and Additions
|  | 198469 | P9011546 | Eastern Cape | JONGINTABA SENIOR SECONDARY SCHOOL | 200400300 | Mhlontlo | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 3823695 | 3823695 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198471 | P0004543 | Eastern Cape | LEADERSHIP INSTITUTE EAST LONDON (MANDLA MAKUPULA) | 200999925 | Buffalo City | Site Handed - Over to Contractor | Active - Contracted | 2021-04-01 | 2021-04-03 | 2026-03-31 | 2025-03-01 | 2025-03-31 | 0 | 15825000 | 15825000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198472 | P9011583 | Eastern Cape | ZAMEKA SECONDARY SCHOOL | 200200920 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-04-03 | 2025-03-31 | 2025-03-01 | 2025-03-31 | 0 | 295712 | 295712 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198477 | P9011596 | Eastern Cape | LUBALASI SENIOR PRIMARY SCHOOL (District Office) | 200500440 | Umzimvubu | Construction 76% - 99% | Active - Contracted | 2020-07-20 | 2020-08-01 | 2024-03-31 | 2024-03-01 | 2025-03-31 | 0 | 10974923 | 10974923 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198500 | P9008643_ | Eastern Cape | SEYISI PRIMARY SCHOOL | 200100689 | Nelson Mandela Bay | Feasibility | Active - Not Contracted | 2022-04-01 |  | 2026-03-31 |  |  | 2524674 | 0 | 2524674 | Education Infrastructure Grant | Upgrading and Additions
|  | 198528 | P9011731 | Eastern Cape | NEWTOWN HIGH SCHOOL | 200100051 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1000006 | 1000006 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198561 | P9011535 | Eastern Cape | GRENS VOORBEREIDINGSKOOL | 200200221 | Buffalo City | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-05-01 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 9430795 | 9430795 | Education Infrastructure Grant | Upgrading and Additions
|  | 198770 | GDE00348 | Gauteng | SOSHANGUVE VV PS (No EMIS yet) TW | N/A | City of Tshwane | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-13 |  |  | 1000000 | 10000000 | 11000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 198772 | GDE00032 | Gauteng | Clapham Secondary School | N/A | City of Tshwane | Feasibility | Approved | 2021-04-01 |  | 2026-03-13 |  |  | 1000000 | 1000000 | 2000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 198875 | W/500309098/SDS | KwaZulu-Natal | QHOBO SECONDARY SCHOOL | 500309098 | Msinga | Final Completion | Active - Contracted | 2019-08-21 | 2021-02-26 | 2023-06-30 | 2022-02-28 | 2023-04-01 | 50000 | 100000 | 150000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 198967 | GDE00354 | Gauteng |  |  |  | Project Initiation | Potential | 2021-04-01 |  | 2025-03-21 |  |  | 2000000 | 4000000 | 6000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198984 | GDE00355 | Gauteng |  |  |  | Project Initiation | Proposed | 2021-04-01 |  | 2026-04-11 |  |  | 1000000 | 2000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198986 | GDE00407 | Gauteng |  |  |  | Project Initiation | Approved | 2015-04-01 |  | 2025-09-30 |  |  | 397000 | 246211000 | 246608000 | Equitable Share | Maintenance and Repairs
|  | 198987 | GDE00411 | Gauteng |  |  |  | Project Initiation | Approved | 2020-04-01 |  | 2025-05-09 |  |  | 0 | 107875422 | 107875422 | Equitable Share | Maintenance and Repairs
|  | 198989 | GDE00398 | Gauteng |  |  |  | Construction 51% - 75% | Active - Contracted | 2019-04-01 | 2019-06-20 | 2026-03-13 | 2023-03-15 | 2023-03-25 | 15000000 | 91202953 | 106202953 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198994 | GDE00416 | Gauteng |  |  |  | Construction 51% - 75% | Active - Contracted | 2019-04-01 | 2020-04-15 | 2026-04-30 | 2023-05-31 | 2023-11-30 | 0 | 27000000 | 27000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 198995 | GDE00414 | Gauteng |  |  |  | Construction 1% - 25% | Approved | 2019-04-01 | 2019-05-24 | 2025-11-13 | 2022-03-15 | 2023-12-31 | 0 | 1706183615 | 1706183615 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199020 | GDE00405 | Gauteng |  |  |  | Design | Approved | 2020-11-14 |  | 2026-03-13 |  |  | 0 | 50000000 | 50000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 199024 | GDE00410 | Gauteng |  |  |  | Construction 51% - 75% | Active - Contracted | 2018-04-01 | 2018-04-15 | 2023-04-12 | 2021-03-12 | 2023-11-30 | 0 | 15074000 | 15074000 | Expanded Public Works Programme Intergrated Grant for Provinces | Non-Infrastructure
|  | 199027 | GDE00413 | Gauteng |  |  |  | Construction 51% - 75% | Active - Contracted | 2015-04-01 | 2015-05-08 | 2025-05-31 | 2021-01-20 | 2023-07-31 | 3583680 | 157068875 | 160652555 | Education Infrastructure Grant | Non-Infrastructure
|  | 199030 | GDE00255 | Gauteng |  |  |  | Feasibility | Approved | 2019-04-01 |  | 2026-01-16 |  |  | 0 | 19200000 | 19200000 | Education Infrastructure Grant | Non-Infrastructure
|  | 199034 | GDE00254 | Gauteng |  |  |  | Other - Compensation of Employees | Active - Contracted | 2017-04-01 | 2017-04-10 | 2025-05-08 | 2023-03-30 | 2024-07-31 | 0 | 232481000 | 232481000 | Education Infrastructure Grant | Non-Infrastructure
|  | 199182 | NEW SCHOOL PROGRAMME | KwaZulu-Natal | NEW SCHOOL PROGRAMME | ALL DISTRICTS | The Msunduzi | Project Initiation | Proposed | 2020-06-02 |  | 2025-08-30 |  |  | 59050000 | 200000000 | 259050000 | Equitable Share | New or Replaced Infrastructure
|  | 199277 | MDOE/UPG/151/21-22 | Mpumalanga | Andries Mashile Primary School | 800000273 | Dr JS Moroka | Project Initiation | Proposed | 2022-04-01 |  | 2024-09-01 |  |  | 1118964 | 7992601 | 9111565 | Education Infrastructure Grant | Upgrading and Additions
|  | 199279 | MDOE/MAIN/84/21-22 | Mpumalanga | Siphumelele Combined School | 800021295 | Mbombela | Pre - Feasibility | Proposed | 2022-04-01 |  | 2024-03-31 |  |  | 202413 | 2226538 | 2428951 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199280 | DoE/NKD/MAIN/ 001 | Mpumalanga | Litho Secondary School | 800010553 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 499672 | 4996723 | 5496395 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199281 | PWRT/SAN/259/20MP(MASINAKANE PRI--------- | Mpumalanga | Masinakane Special School | 800029421 | Dr JS Moroka | Pre - Feasibility | Proposed | 2020-04-01 |  | 2024-01-01 |  |  | 3104143 | 22172448 | 25276591 | Education Infrastructure Grant | Upgrading and Additions
|  | 199282 | MDOE/UPG/1020/21-22 | Mpumalanga | Mokebe Secondary School | 800014969 | Dr JS Moroka | Terminated | Proposed | 2021-04-01 | 2022-06-13 | 2024-05-16 | 2022-09-14 | 2022-09-29 | 2063610 | 14740068 | 16803678 | Education Infrastructure Grant | Upgrading and Additions
|  | 199284 | MDOE/UPG/139/21-22 | Mpumalanga | LD Moetanalo Secondary School | 800029330 | Steve Tshwete | Pre - Feasibility | Proposed | 2022-04-01 |  | 2025-03-30 |  |  | 861000 | 6150000 | 7011000 | Education Infrastructure Grant | Upgrading and Additions
|  | 199285 | MDOE/UPG/140/21-22 | Mpumalanga | Ezwenilethu Primary School | 800004168 | Dr JS Moroka | Project Initiation | Proposed | 2022-01-01 |  | 2022-12-31 |  |  | 365400 | 2610000 | 2975400 | Education Infrastructure Grant | Upgrading and Additions
|  | 199286 | MDOE/UPG/147/21-22 | Mpumalanga | Siphumule Primary School | 800021303 | Thembisile | Project Initiation | Proposed | 2022-01-01 |  | 2022-12-31 |  |  | 13615040 | 1906106 | 15521146 | Education Infrastructure Grant | Upgrading and Additions
|  | 199287 | MDOE/UPG/1025/21-22(DPWRT/MAIN/042/21/MP)) | Mpumalanga | Laerskool Nespruit | 800009480 | Mbombela | Site Handed - Over to Contractor | Active - Contracted | 2021-04-15 |  | 2023-05-16 |  |  | 2873423 | 7995352 | 10868775 | Education Infrastructure Grant | Upgrading and Additions
|  | 199288 | MDOE/MAIN/22-23/166 | Mpumalanga | Mkhanyo Primary School | 800003079 | Thembisile | Project Initiation | Proposed | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 4416268 | 4416268 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199289 | MDOE/UPG/149/21-22 | Mpumalanga | Khayelitjha Primary School | 800010058 | Thembisile | Pre - Feasibility | Proposed | 2022-01-01 |  | 2022-12-31 |  |  | 1906106 | 13615040 | 15521146 | Education Infrastructure Grant | Upgrading and Additions
|  | 199290 | MDOE/UPG/150/21-22 | Mpumalanga | Siyabuswa Primary School | 800021477 | Dr JS Moroka | Feasibility | Proposed | 2022-01-01 |  | 2022-12-31 |  |  | 1118964 | 7992601 | 9111565 | Education Infrastructure Grant | Upgrading and Additions
|  | 199291 | MDOE/UPG/152/21-22 | Mpumalanga | Ukhwezi Primary School | 800024133 | Emakhazeni | Feasibility | Proposed | 2022-01-01 |  | 2022-12-31 |  |  | 1509043 | 10778881 | 12287924 | Education Infrastructure Grant | Upgrading and Additions
|  | 199301 | DPWRT/SAN/237/20MP(SINETJHUDU) --------- | Mpumalanga | Sinetjhudu Primary School | 800021246 | Thembisile | Construction 1% - 25% | Active - Contracted | 2021-12-01 | 2022-01-01 | 2022-12-31 | 2022-12-31 | 2022-12-31 | 233800 | 1670000 | 1903800 | Education Infrastructure Grant | Upgrading and Additions
|  | 199305 | MDOE/GS/ALL/Education Infrastructure Grant (EIG)/G&S/17-18/004 | Mpumalanga | School furniture | Furniture | Mbombela | Construction 26% - 50% | Active - Not Contracted | 2020-04-01 | 2020-10-09 | 2025-01-31 | 2021-09-23 | 2021-02-26 | 0 | 8000000 | 8000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 199306 | MDOE/NEIMS/2020/21 | Mpumalanga | NEIMS Condition Assessment | assessment | Mbombela | Construction 26% - 50% | Potential | 2021-04-15 |  | 2024-09-01 |  |  | 250000 | 40000000 | 40250000 | Education Infrastructure Grant | Non-Infrastructure
|  | 199307 | MDOE/UPG/141/21-22 | Mpumalanga | Celani Primary School | 80002014 | Mbombela | Design | Proposed | 2021-04-01 |  | 2024-09-01 |  |  | 870530 | 6218072 | 7088602 | Education Infrastructure Grant | Upgrading and Additions
|  | 199309 | MDOE/UPG/142/21-22 | Mpumalanga | Zibokwane Primary School | 800025882 | Nkomazi | Design | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 542812 | 3877226 | 4420038 | Education Infrastructure Grant | Upgrading and Additions
|  | 199310 | MDOE/UPG/143/21-22 | Mpumalanga | Jerusalem Secondary School | 800007039 | Mbombela | Design | Proposed | 2021-04-01 |  | 2024-09-01 |  |  | 895701 | 6397866 | 7293567 | Education Infrastructure Grant | Upgrading and Additions
|  | 199312 | DPWRT/058/21MP(PHINDELA PRIMARY)--------- | Mpumalanga | Phindela Primary School | 800018291 | Nkomazi | Design | Proposed | 2021-04-15 |  | 2024-09-01 |  |  | 150920 | 1078000 | 1228920 | Education Infrastructure Grant | Upgrading and Additions
|  | 199315 | DPWRT/027/18MP MSHADZA SEC--------------- | Mpumalanga | Mshadza Secondary School | 800015768 | Mbombela | Design | Proposed | 2021-04-15 |  | 2024-09-01 |  |  | 392668 | 1710000 | 2102668 | Education Infrastructure Grant | Upgrading and Additions
|  | 199343 | MDOE/MAIN/76721-22 | Mpumalanga | Sele Primary School | 800035017 | Bushbuckridge | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2022-09-15 |  |  | 839280 | 6994000 | 7833280 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199344 | MDOE/MAIN/018/21-22 | Mpumalanga | Mabarhule Secondary School | 800035196 | Bushbuckridge | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 1277650 | 9126075 | 10403725 | Education Infrastructure Grant | Upgrading and Additions
|  | 199346 | MDOE/UPG/100/21-22 | Mpumalanga | Mzimba Secondary School | 800035167 | Bushbuckridge | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2022-04-15 |  |  | 602812 | 4305802 | 4908614 | Education Infrastructure Grant | Upgrading and Additions
|  | 199347 | MDOE/UPG/1001/21-22 | Mpumalanga | Rhandzekile Primary School | 800035210 | Bushbuckridge | Feasibility | Active - Not Contracted | 2020-04-01 |  | 2024-05-31 |  |  | 900084 | 9000840 | 9900924 | Education Infrastructure Grant | Upgrading and Additions
|  | 199359 | DoE/Boh/MAIN/151 | Mpumalanga | Bushbuckridge Secondary School | 800035079 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-09-15 |  |  | 11412 | 114125 | 125537 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199360 | MDOE/SAN/312/2020_ | Mpumalanga | MOKGOMANA Primary School | 800034870 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2022-04-15 |  |  | 150920 | 1078000 | 1228920 | Education Infrastructure Grant | Upgrading and Additions
|  | 199361 | DPWRT/SAN/063/21MP MORITHING------------- | Mpumalanga | Morithing Primary School | 800035497 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 150920 | 1078000 | 1228920 | Education Infrastructure Grant | Upgrading and Additions
|  | 199362 | DPWRT/SAN/062/21MP LM KGANANE S --------- | Mpumalanga | LM Kganane Secondary School | 800028613 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 178360 | 1274000 | 1452360 | Education Infrastructure Grant | Upgrading and Additions
|  | 199363 | DPWRT/SAN/061/21MP VUYELANI P------------ | Mpumalanga | Vuyelani Primary School | 800035214 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 288120 | 2058000 | 2346120 | Education Infrastructure Grant | Upgrading and Additions
|  | 199364 | DPWRT/SAN/060/21MP ESSELMAN P------------ | Mpumalanga | Esselman Primary School | 800034938 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 219520 | 1787520 | 2007040 | Education Infrastructure Grant | Upgrading and Additions
|  | 199368 | DPWRT/057/21MP(SIHLANGU PRIMARY)--------- | Mpumalanga | Sihlangu Primary School | 800020982 | Nkomazi | Feasibility | Proposed | 2022-04-01 |  | 2023-11-30 |  |  | 409200 | 2046000 | 2455200 | Education Infrastructure Grant | Upgrading and Additions
|  | 199384 | MDOE/MAIN/42/21-22 | Mpumalanga | Kamagugu Special School | 80028829 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-05-01 |  |  | 331210 | 2365789 | 2696999 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199385 | MDOE/MAIN/97/21-22 | Mpumalanga | Babutheni Secondary School | 800000463 | Dr JS Moroka | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 309887 | 3098874 | 3408761 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199386 | MDOE/MAIN/82/21-22 | Mpumalanga | Zigode Primary School | 800034850 | Bushbuckridge | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 69987 | 699874 | 769861 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199387 | DoE/GERT/MAIN/109 | Mpumalanga | Badjiesbuit Primary School | tbc | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 30055 | 300547 | 330602 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199391 | DoE/Boh/MAIN/156 | Mpumalanga | Barney Primary School | 800035077 | Bushbuckridge | Terminated | Active - Not Contracted | 2021-04-01 | 2021-05-15 | 2023-04-15 | 2023-04-15 | 2023-04-15 | 12455 | 124554 | 137009 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199392 | MDOE/MAIN/70/21-22 | Mpumalanga | Zamokuhle Primary School | 800025817 | Govan Mbeki | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 209741 | 1398276 | 1608017 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199393 | DoE/GERT/MAIN/102 | Mpumalanga | BASHELE PRIMARY SCHOOL | 800000729 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-12-15 |  |  | 209169 | 2091689 | 2300858 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199394 | MDOE/MAIN/43/21-22 | Mpumalanga | Ben Matlushe Primary School | 800034880 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 461099 | 3293565 | 3754664 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199395 | MDOE/MAIN/14/21-22 | Mpumalanga | Bergplaas Primary School | 800000968 | Mkhondo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 167472 | 1196231 | 1363703 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199397 | MDOE/MAIN/059/22 | Mpumalanga | Xiviti Primary School | 800035044 | Bushbuckridge | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 28790 | 287898 | 316688 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199398 | MDOE/DESIGN/2020/21 | Mpumalanga | Standardization of Civil and Electrical Services | new | Mbombela | Feasibility | Proposed | 2021-04-30 |  | 2023-11-30 |  |  | 2200000 | 0 | 2200000 | Education Infrastructure Grant | Non-Infrastructure
|  | 199400 | DoE/Boh/MAIN/178 | Mpumalanga | Boikhutso Primary School | 800035220 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 43246 | 432455 | 475701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199401 | DPWRT/SAN/227/20/MP | Mpumalanga | Bonginsimbi Secondary School | 800001412 | Emalahleni | Construction 1% - 25% | Active - Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 1137377 | 8124122 | 9261499 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199402 | MDOE/MAIN/020/21-22 | Mpumalanga | Weeber Primary School | 800002526 | Mkhondo | Project Initiation | Proposed | 2022-04-01 |  | 2024-03-31 |  |  | 16751 | 111675 | 128426 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199403 | MDOE/MAIN/121/22 | Mpumalanga | Waverly Secondary School | 800025239 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199404 | DoE/NKD/MAIN/111 | Mpumalanga | Borolo Primary School | 800001495 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 44555 | 851534 | 896089 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199407 | MDOE/MAIN/32/21-22 | Mpumalanga | Catfulani Primary School | 800001974 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 189872 | 1356231 | 1546103 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199409 | MDOE/MAIN/261/21-22 | Mpumalanga | Violet Tjiane Primary School | 800035305 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 26590 | 265898 | 292488 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199410 | DPWRT/116/17/MP | Mpumalanga | Chueu Primary School | 800034853 | Bushbuckridge | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2021-05-15 | 2025-04-15 | 2025-05-15 | 2025-05-15 | 5515 | 55145 | 60660 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199411 | DoE/Boh/MAIN/115 | Mpumalanga | Cottondale Circuit | OFFICES | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 45011 | 450114 | 495125 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199412 | MDOE/MAIN/80/21-22 | Mpumalanga | Craigburn Primary School | 800034854 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 44127 | 441271 | 485398 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199413 | DoE/NKD/MAIN/101 | Mpumalanga | Vezilwazi Secondary School | 800024604 | Dr JS Moroka | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 31245 | 312445 | 343690 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199414 | MDOE/MAIN/048/22 | Mpumalanga | Cunningmore Primary School | 800034991 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 35490 | 354899 | 390389 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199415 | MDOE/MAIN/262/21-22 | Mpumalanga | D&C Comprehensive School | 800002329 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 50435 | 360252 | 410687 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199418 | MDOE/MAIN/049/22 | Mpumalanga | Dilayi Primary School | 800035080 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 9986 | 99858 | 109844 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199419 | DoE/GERT/MAIN/107 | Mpumalanga | Ubuhlebolwazi Secondary School | 800024075 | Msukaligwa | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 325447 | 3254471 | 3579918 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199420 | DoE/NKD/MAIN/108 | Mpumalanga | Tweefontein north | n/a | Thembisile | Project Initiation | Active - Contracted | 2022-03-02 |  | 2023-03-31 |  |  | 31256 | 312556 | 343812 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199427 | DoE/EHL/MAIN/138 | Mpumalanga | Tsambokhulu Primary school | 800022889 | Nkomazi | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199428 | MDOE/MAIN/39/21-22 | Mpumalanga | Tokoloho Primary School | 800035314 | Dipaleseng | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 39852 | 398521 | 438373 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199429 | DoE/GERT/MAIN/101 | Mpumalanga | Thwahlele Primary School | 800023465 | Msukaligwa | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 44179 | 441787 | 485966 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199431 | DoE/Boh/MAIN/119 | Mpumalanga | Thabatlou Glory Hill Satellite | tbc | Victor Khanye | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 9921 | 99214 | 109135 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199432 | MDOE/MAIN/086/22 | Mpumalanga | Thabakgolo Primary School | 800035146 | Bushbuckridge | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 43446 | 434455 | 477901 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199435 | MDOE/MAIN/24/21-22 | Mpumalanga | Steve Tshwete 1 Circuit Office | n/a | Steve Tshwete | Practical Completion (100%) | Active - Contracted | 2022-04-01 | 2022-06-15 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 29639 | 1337879 | 1367518 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199436 | MDOE/MAIN/54/21-22 | Mpumalanga | Springbok Combined School | tbc | Emalahleni | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 15024 | 150235 | 165259 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199437 | MDOE/MAIN/102/21-22 | Mpumalanga | Somabedlana Primary School | 800022012 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 355479 | 3554789 | 3910268 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199439 | DoE/NKD/MAIN/104 other | Mpumalanga | Sizofunda Primary School | 800021774 | Victor Khanye | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 34779 | 1530272 | 1565051 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199440 | DoE/NKD/MAIN/103 | Mpumalanga | Sizabantwana Primary School | 800021642 | Thembisile | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 45355 | 1995638 | 2040993 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199442 | DoE/EHL/MAIN/127 | Mpumalanga | Sitintile Secondary School | 800021410 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 347899 | 3478987 | 3826886 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199444 | DPWRT/119/19/MP | Mpumalanga | Sisini Primary School | 800021329 | Nkomazi | Construction 26% - 50% | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 124787 | 1247873 | 1372660 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199447 | DoE/EHL/MAIN/124 | Mpumalanga | Sifunindlela Secondary School | 800020941 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 43246 | 432455 | 475701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199449 | MDOE/MAIN/41/21-22 | Mpumalanga | Sicelosetfu Secondary school | 800034207 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 29865 | 1138466 | 1168331 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199450 | MDOE/MAIN/107/21-22 | Mpumalanga | Sicelalwati Primary School | 800006924 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 299875 | 2998745 | 3298620 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199451 | MDOE/MAIN/45/21-22 | Mpumalanga | Sicelalwati Combined School | tbc | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 35690 | 2552521 | 2588211 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199452 | MDOE/MAIN/087/22 | Mpumalanga | Siboyiye Combined School | 800034957 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 62992 | 629918 | 692910 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199453 | DPWRT/028/19/MP | Mpumalanga | Sibongimpumelelo Primary School | 800020727 | Thembisile | Construction 51% - 75% | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 424377 | 4243770 | 4668147 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199454 | MDOE/MAIN/87/21-22 DPWRT/SAN/331/20/MP | Mpumalanga | Sibongile Primary School | 800020719 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 108775 | 1196522 | 1305297 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199455 | DoE/Boh/MAIN/124 | Mpumalanga | Shobiyana Secondary School | 800034985 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41245 | 1814793 | 1856038 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199456 | MDOE/MAIN/046/22 | Mpumalanga | Shatale Primary School | 800035145 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 40875 | 1798478 | 1839353 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199457 | MDOE/MAIN/83/21-22 | Mpumalanga | SEMONATE COMBINED SCHOOL | 800020289 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 86479 | 3805054 | 3891533 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199458 | DPWRT/SAN/280/20MP(BLANKPAN PRIM--------- | Mpumalanga | Sele Secondary School | 800020248 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 11245 | 112445 | 123690 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199459 | mdoe/main------------- | Mpumalanga | Sele Primary School | 800035016 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 389345 | 3244542 | 3633887 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199460 | MDOE/MAIN/015/21-22 | Mpumalanga | Sedibeng Primary School | 800035142 | Bushbuckridge | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2022-06-02 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 147760 | 1082869 | 1230629 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199461 | DoE/EHL/MAIN/132 | Mpumalanga | Sakhile Secondary School | 800019729 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41246 | 453701 | 494947 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199462 | DPWRT/MAIN/139/20MP(SAKHILE PRIM--------- | Mpumalanga | Sakhile Primary School | 800019711 | Thembisile | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 35463 | 1404280 | 1439743 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199463 | MDOE/MAIN/003/21-22 | Mpumalanga | Pungutsha Secondary School | 800018770 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 811200 | 811200 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199464 | MDOE/MAIN/91/21-22 | Mpumalanga | Pungutsha Secondary School | 800018770 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 234568 | 2345678 | 2580246 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199465 | MDOE/MAIN/084/22 | Mpumalanga | Pugishe Primary School | 800035088 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 14025 | 154270 | 168295 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199466 | DoE/NKD/MAIN/100 | Mpumalanga | Potsanyane Primary School | 800018671 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199467 | MDOE/MAIN/98/21-22 | Mpumalanga | Phopolo primary school | 800018382 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 314559 | 3145589 | 3460148 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199469 | DPWRT/MAIN/049/20MP PANORAMA SEC--------- | Mpumalanga | Panorama Secondary School | 800032631 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41245 | 412447 | 453692 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199471 | MDOE/MAIN/77/21-22 | Mpumalanga | Nyamande Secondary School | 800034840 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41211 | 453325 | 494536 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199472 | DoE/Boh/MAIN/146 | Mpumalanga | Nwaritsana Secondary School | 800035086 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 30211 | 302110 | 332321 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199473 | DoE/Boh/MAIN/191 | Mpumalanga | Nwankupana Primary School | 800035208 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 59889 | 2635112 | 2695001 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199474 | MDOE/MAIN/081/22 | Mpumalanga | Ntsie Primary School | 800035087 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 20000 | 200000 | 220000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199476 | DPWRT/041/20/MP | Mpumalanga | Nqobangolwazi Secondary School | 800030211 | Lekwa | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 407511 | 4482623 | 4890134 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199477 | MDOE/MAIN/080/22 | Mpumalanga | Nkwenkwezi Primary School | 800034952 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 109887 | 3386458 | 3496345 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199478 | MDOE/MAIN/060/22 | Mpumalanga | Nkulungwana Primary School | 800034841 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 90048 | 990528 | 1080576 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199479 | MDOE/MAIN/03/21-22 | Mpumalanga | Ngilandi Secondary School | 800016758 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 42357 | 482864 | 525221 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199481 | DoE/Boh/MAIN/101 | Mpumalanga | Ndimande Primary School | 800034840 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 114559 | 4853479 | 4968038 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199483 | MDOE/MAIN/079/22 | Mpumalanga | Narishe Primary School | 800035136 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 44311 | 443111 | 487422 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199484 | MDOE/MAIN/050/22 | Mpumalanga | Diwiti Secondary School | 800035082 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 91245 | 912448 | 1003693 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199485 | MDOE/MAIN/008/21-22 | Mpumalanga | Dlumana Secondary School | 800035022 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 0 | 67600 | 67600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199486 | MDOE/MAIN/103/21-22 | Mpumalanga | Driekoppies Combined school | 800002824 | Nkomazi | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 357128 | 3571277 | 3928405 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199487 | DPWRT/SAN/013/21/MP | Mpumalanga | Duduzile Secondary school | 800002873 | Dr JS Moroka | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 67213 | 672130 | 739343 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199488 | MDOE/MAIN/090/22 | Mpumalanga | Munyamana Primary School | 800035038 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 29877 | 298774 | 328651 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199489 | MDOE/MAIN/48/21-22 | Mpumalanga | Duma Primary School | 800002881 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 339624 | 2425886 | 2765510 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199490 | MDOE/MAIN/95/21-22 | Mpumalanga | Dumeleni Secondary School | 800002907 | Thembisile | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 675088 | 4822058 | 5497146 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199491 | MDOE/MAIN/076/22 | Mpumalanga | Muchuchi Primary School | 800035036 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 26000 | 259998 | 285998 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199492 | DoE/Boh/MAIN/193 | Mpumalanga | DyondekaniI Primary School | 800035184 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 12455 | 124554 | 137009 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199493 | DoE/EHL/MAIN/102 | Mpumalanga | Mshadza Secondary School | 800015768 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 124447 | 1244474 | 1368921 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199494 | DoE/GERT/MAIN/110 | Mpumalanga | Mpumelelo Primary School | 800015727 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 30788 | 307878 | 338666 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199495 | DoE/GERT/MAIN/113 | Mpumalanga | Mpuluzi Circuit Offices | n/a | Msukaligwa | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 354774 | 3547741 | 3902515 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199496 | DOE/EHL/MAIN/109 | Mpumalanga | Ehlanzeni District Offices | 800035530 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 824578 | 8245789 | 9070367 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199497 | DPWRT/MAIN/040/21MP | Mpumalanga | Mpakeni Primary School | 800015511 | Mbombela | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 45237 | 452369 | 497606 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199498 | MDOE/MAIN/65/21-22 12 | Mpumalanga | Ekulindeni Secondary School | 800003251 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 218138 | 1454250 | 1672388 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199499 | MDOE/MAIN/074/22 | Mpumalanga | MP Mokoena Secondary School | 800035060 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 12599 | 125989 | 138588 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199500 | MDOE/MAIN/21/21-22 | Mpumalanga | Ematjeketjeni Primary School | 800007328 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 61959 | 442565 | 504524 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199501 | MDOE/MAIN/90/21-22 | Mpumalanga | Emoyeni Primary School | 800003608 | Mkhondo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 158874 | 1588742 | 1747616 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199502 | DoE/Boh/MAIN/150 | Mpumalanga | Moratiseng Primary School | 800035135 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 35990 | 359898 | 395888 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199503 | DoE/EHL/MAIN/120 A | Mpumalanga | Emtfonjeni Primary School | 800003632 | Mbombela | Construction 76% - 99% | Active - Not Contracted | 2021-04-01 | 2021-05-01 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 69000 | 689998 | 758998 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199504 | MDOE/MAIN/073/22 | Mpumalanga | Morage Primary School | 800034920 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 24144 | 241441 | 265585 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199505 | DPWRT/SAN/060/20/MP | Mpumalanga | Entokozweni Secondary School | 800003822 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-04-15 |  |  | 73277 | 569231 | 642508 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199506 | MDOE/MAIN/38/21-22 | Mpumalanga | Moolman Primary School | 800015149 | Mkhondo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 36500 | 1556100 | 1592600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199507 | MDOE/MAIN/072/22 | Mpumalanga | Mokokwane Primary School | 800028563 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 40145 | 401447 | 441592 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199508 | DoE/Boh/MAIN/187 | Mpumalanga | ES Malele Secondary School | 800035122 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 40349 | 403487 | 443836 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199510 | MDOE/MAIN-SP/002/20-21 | Mpumalanga | Estralita Special School | 800004002 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 413857 | 1655428 | 2069285 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199512 | MDOE/MAIN/089/22 | Mpumalanga | Mmabatho Mokoena Secondary School | 800035069 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 0 | 61026 | 61026 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199513 | DoE/Boh/MAIN/185 | Mpumalanga | Farel Primary School | 800035123 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 10479 | 104789 | 115268 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199514 | DoE/Boh/MAIN/127 | Mpumalanga | Funjwa Primary School | 800034965 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-04-15 |  |  | 44246 | 442455 | 486701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199515 | DoE/Boh/MAIN/106 | Mpumalanga | Gavazana Primary School | 800035237 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 11121 | 111214 | 122335 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199516 | DPWRT/SAN/247/20/MP | Mpumalanga | Mkhutshwa Secondary School | 800026567 | Thembisile | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 43744 | 437441 | 481185 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199519 | MDOE/MAIN/17/21-22 | Mpumalanga | Mjokwane Secondary School | 800014365 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 317225 | 2265895 | 2583120 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199520 | MDOE/MAIN/36/21-22 | Mpumalanga | Gezingqondo Secondary School | 800035093 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 43688 | 436875 | 480563 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199521 | MDOE/MAIN/57/21-22 | Mpumalanga | Mispah Primary School | 800014340 | Mkhondo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 186813 | 1245421 | 1432234 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199522 | DoE/Boh/MAIN/173 | Mpumalanga | Glory Hill Teacher Development Centre | OFFICES | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 124788 | 1247878 | 1372666 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199523 | MDOE/MAIN/004/21-22 other | Mpumalanga | Middleburg Combined School | 800014274 | Steve Tshwete | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 1469500 | 1469500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199524 | MDOE/MAIN/002/20-21 A | Mpumalanga | Greendale Combined School | 800004770 | Emalahleni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 899289 | 3909954 | 4809243 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199525 | DoE/EHL/MAIN/139 | Mpumalanga | Mhwayi Primary School | 800014266 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199526 | MDOE/MAIN/104/21-22 | Mpumalanga | Mhlutshwa Primary School | 800026583 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 774081 | 5529150 | 6303231 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199527 | DoE/Boh/MAIN/109 | Mpumalanga | Greenvalley Primary School | 800034855 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 299281 | 2137726 | 2437007 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199532 | MDOE//MAIN/112 | Mpumalanga | Mgwenya circuit | n/a | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 44411 | 444112 | 488523 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199533 | DoE/Boh/MAIN/176 | Mpumalanga | Harmony Hill Primary School | 800019687 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 39875 | 398747 | 438622 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199534 | MDOE/MAIN/29/21-22 | Mpumalanga | Mganduzweni Secondary School | 800014050 | Mbombela | Project Initiation | Active - Contracted | 2024-04-01 |  | 2025-03-31 |  |  | 0 | 3426026 | 3426026 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199536 | MDOE//MAIN/120 | Mpumalanga | Hazyview Teachers center | OFFICES | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 42600 | 425998 | 468598 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199537 | DoE/Boh/MAIN/175 | Mpumalanga | Memezile Secondary School | 800013995 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 214577 | 2145774 | 2360351 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199539 | MDOE/MAIN/73/21-22 | Mpumalanga | Memezile Secondary School | 800013995 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 114786 | 765243 | 880029 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199540 | DoE/Boh/MAIN/192 | Mpumalanga | Hibemandla Primary School | 800035186 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 7899 | 78989 | 86888 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199541 | DPWRT/011/20MP(HIGHVELDPARK SEC) | Mpumalanga | Highveld Park Secondary School | 800005116 | Govan Mbeki | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 53868 | 4622158 | 4676026 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199544 | MDOE/MAIN/043/22 | Mpumalanga | Hlong Secondary School | 800028597 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 43246 | 432455 | 475701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199545 | MDOE/MAIN/116/22 | Mpumalanga | Mehlwemamba Primary School | 800013987 | Mkhondo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 42246 | 422455 | 464701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199547 | DoE/EHL/MAIN/130 | Mpumalanga | Mdumiseni Primary School | 800013904 | Victor Khanye | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 89877 | 898774 | 988651 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199548 | DoE/Boh/MAIN/132 | Mpumalanga | Hokisa Primary School | 800034994 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 240479 | 1717714 | 1958193 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199549 | DoE/EHL/MAIN/110 | Mpumalanga | Mbombela Circuit | 0ffice | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 40588 | 405879 | 446467 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199550 | MDOE/MAIN/105/22 | Mpumalanga | Holmdene Secondary School | 800005587 | Lekwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 42446 | 424455 | 466901 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199551 | MDOE/SAN/310/2020 other | Mpumalanga | Mbombela Circuit | 0ffice | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 16940 | 121000 | 137940 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199552 | DoE/Boh/MAIN/134 | Mpumalanga | Hoyo hoyo Secondary School | 800034995 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 1105850 | 7898934 | 9004784 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199556 | DoE/Boh/MAIN/194 | Mpumalanga | Ian Mackenzi Secondary School | 800035191 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-04-15 |  |  | 18787 | 187874 | 206661 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199557 | MDOE/MAIN/23/21-22 | Mpumalanga | Impilo Primary School | 800006213 | Emalahleni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 26395 | 263945 | 290340 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199559 | DoE/EHL/MAIN/111 | Mpumalanga | Insikazi Circuit Office | 100 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 43254 | 432544 | 475798 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199561 | MDOE//MAIN/119 | Mpumalanga | Ithemba Offices | OFFICES | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199562 | DoE/Boh/MAIN/172 | Mpumalanga | Kadishi Secondary School | 800028605 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 198790 | 1987898 | 2186688 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199564 | DoE/EHL/MAIN/113 | Mpumalanga | Kanyamazane Teachers Centre | OFFICES | Thaba Chweu | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 21145 | 211454 | 232599 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199565 | MDOE/MAIN/86/21-22 | Mpumalanga | Khanyisa Primary School | 800007625 | Thembisile | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 251164 | 1794033 | 2045197 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199566 | DoE/EHL/MAIN/122 | Mpumalanga | Khanyisile Primary School | 800007641 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 68989 | 689889 | 758878 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199567 | DoE/Boh/MAIN/147 | Mpumalanga | Maviljan Primary School | 800035085 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 42412 | 424124 | 466536 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199568 | MDOE/MAIN/053/22 | Mpumalanga | Khayelihle Primary School | 800034830 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 45111 | 1217220 | 1262331 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199569 | MDOE/MAIN/69/21-22 | Mpumalanga | Matimba Primary School | 800034789 | Thembisile | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 132646 | 947474 | 1080120 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199571 | MDOE/MAIN/009/21-22 | Mpumalanga | Matikinya Primary School | 800035033 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 169000 | 169000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199572 | MDOE/MAIN/19/21-22 | Mpumalanga | Ki Thwala Secondary School | 800013433 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 199616 | 1425835 | 1625451 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199573 | MDOE/MAIN/71/21-22 | Mpumalanga | Mathukwane Secondary School | 800034944 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 387134 | 2765243 | 3152377 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199575 | MDOE/MAIN/111/22 | Mpumalanga | Klein Vrystad Primary School | 800008011 | Mkhondo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 41147 | 411474 | 452621 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199577 | MDOE/MAIN/96/21-22 | Mpumalanga | Matempule Primary School | 800003169 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 308201 | 3082012 | 3390213 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199578 | MDOE/MAIN/22/21-22 | Mpumalanga | Kome Primary School | 800008441 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 40327 | 403265 | 443592 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199579 | DPWRT/MAIN/302/20MP | Mpumalanga | Laerskool Laeveld | 8000009381 | Mbombela | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 97866 | 652437 | 750303 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199580 | MDOE/MAIN/006/21-22 | Mpumalanga | Lamulelani Secondary School | Not on B5 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 0 | 270400 | 270400 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199581 | DoE/EHL/MAIN/134 | Mpumalanga | Masoyi Primary School | 800013078 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41246 | 412455 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199583 | DPWRT/MAIN/045/21/MP | Mpumalanga | Masobye Primary School | 800013045 | Dr JS Moroka | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 161323 | 1152313 | 1313636 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199584 | MDOE/MAIN/052/22 | Mpumalanga | Langa Secondary School | 800034831 | Nkomazi | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 41411 | 414112 | 455523 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199585 | MDOE/MAIN/22-23/159 | Mpumalanga | Masizakhe Primary School | 800013029 | Nkomazi | Site Handed - Over to Contractor | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 403382 | 2881306 | 3284688 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199586 | MDOE/MAIN/88/21-22 | Mpumalanga | Lekazi Secondary School | 800010116 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 112357 | 1123567 | 1235924 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199588 | MDOE/MAIN/054/22 | Mpumalanga | Lesedi Primary School | 800035126 | Thaba Chweu | Practical Completion (100%) | Active - Contracted | 2021-04-01 | 2021-05-01 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 40126 | 401258 | 441384 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199589 | MDOE/MAIN/002/21-22 | Mpumalanga | Masibekela Primary School | 800012948 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 135200 | 135200 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199590 | DoE/Boh/MAIN/143 | Mpumalanga | Lesodi Primary School | 800010280 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 33320 | 333201 | 366521 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199591 | MDOE/MAIN-OHS/001/21-22 | Mpumalanga | Masakhane Primary School | 800012815 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 0 | 45000 | 45000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199592 | DoE/Boh/MAIN/110 | Mpumalanga | Lethipele Secondary School | 800034860 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 6900 | 68998 | 75898 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199594 | MDOE/MAIN/067/22 | Mpumalanga | Marongwana Primary School | 800035066 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 39890 | 398898 | 438788 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199596 | PWRT/MAIN/010/21/MP | Mpumalanga | Letsakutfula Primary School | 800000455 | Mbombela | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 432876 | 4328759 | 4761635 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199597 | MDOE/MAIN/066/22 | Mpumalanga | Marifaan Primary School | 80012757 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 44246 | 442455 | 486701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199598 | MDOE/MAIN/20/21-22 | Mpumalanga | Libhabha Primary School | 800019877 | Dr Pixley Ka Isaka Seme | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 36527 | 365268 | 401795 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199600 | MDOE/MAIN/065/22 | Mpumalanga | Marcia Mokoena secondary school | 800035065 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 6521 | 65214 | 71735 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199601 | DoE/Boh/MAIN/167 | Mpumalanga | Lindani Primary School | 800010470 | Thaba Chweu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 827581 | 8275810 | 9103391 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199610 | MDOE/MAIN/063/22 | Mpumalanga | Machaye Secondary School | 800034832 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 39888 | 398879 | 438767 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199612 | MDOE/MAIN/064/22 | Mpumalanga | Mafemani Nxumalo Secondary School | 800035157 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 155922 | 1559220 | 1715142 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199615 | DoE/Boh/MAIN/103 | Mpumalanga | Mahlahluvana Primary School | 800034833 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 6788 | 67889 | 74677 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199616 | DoE/Boh/MAIN/112 | Mpumalanga | Makata Secondary School | 800034892 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 10879 | 108787 | 119666 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199617 | DoE/Boh/MAIN/171 | Mpumalanga | Makuke Secondary School | 800028621 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 102545 | 1025447 | 1127992 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199618 | MDOE/MAIN/68/21-22 | Mpumalanga | Malebo Secondary School | 800002062 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 250642 | 1790305 | 2040947 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199620 | MDOE/MAIN/81/21-22 | Mpumalanga | Mamosodi Primary School | 800034894 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 44974 | 449741 | 494715 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199621 | DoE/Boh/MAIN/163 | Mpumalanga | Mandondo Secondary School | 800035101 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 11201 | 112014 | 123215 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199622 | MDOE/MAIN/016/21-22 | Mpumalanga | Manukuse Secondary School | TBC | Bushbuckridge | Practical Completion (100%) | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 413857 | 1655428 | 2069285 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199623 | MDOE /BohD /P /005 | Mpumalanga | Manyakatana Primary School | 800034835 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 2201871 | 15727648 | 17929519 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 199627 | DoE/Boh/MAIN/130 | Mpumalanga | Maphutaditshaba Secondary School | 800034976 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 20575 | 205747 | 226322 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199628 | DoE/NKD/MAIN/109 | Mpumalanga | Manyazela Primary School | 800012393 | Victor Khanye | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 43456 | 434556 | 478012 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199629 | DoE/Boh/MAIN/139 | Mpumalanga | Manyangana Primary School | 800035031 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 41288 | 1200480 | 1241768 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199631 | DoE/EHL/MAIN/117 | Mpumalanga | Luthango Secondary school | 800010892 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 825330 | 5895217 | 6720547 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199633 | MDOE/MAIN/51/21-22 | Mpumalanga | Lusushwana Primary | 800010884 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 198991 | 1421365 | 1620356 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199634 | MDOE/MAIN/30/21-22 | Mpumalanga | Lungisani Secondary School | 800010868 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 33165 | 236895 | 270060 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199635 | MDOE/MAIN/59/21-22 | Mpumalanga | Lungelo Primary School | 800010897 | Mkhondo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 155743 | 1112457 | 1268200 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199637 | MDOE/MAIN/72/21-22 | Mpumalanga | Luka Secondary School | 800035195 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 81199 | 541327 | 622526 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199640 | MDOE/MAIN/85/21-22 | Mpumalanga | Louieville Combined School | 800030635 | Nkomazi | Construction 76% - 99% | Active - Contracted | 2021-04-01 |  | 2023-03-31 |  |  | 134221 | 1342211 | 1476432 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199641 | DoE/Boh/MAIN/166 | Mpumalanga | LM Kganane Secondary School | 800028613 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 36990 | 369898 | 406888 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199643 | MDOE/MAIN/019/21-22 | Mpumalanga | Siphumelele Combined School | 800021295 | Thembisile | Feasibility | Active - Not Contracted | 2021-06-01 |  | 2024-03-31 |  |  | 490893 | 4632169 | 5123062 | Education Infrastructure Grant | Upgrading and Additions
|  | 199648 | PWRT/SAN/334/16/MP | Mpumalanga | Masuku Primary School | 800013086 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-05-25 |  |  | 167879 | 1678791 | 1846670 | Education Infrastructure Grant | Upgrading and Additions
|  | 199652 | DPWRT/SAN/107/18 | Mpumalanga | Semonate Combined School | 800020289 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2023-04-15 |  |  | 242668 | 2022235 | 2264903 | Education Infrastructure Grant | Upgrading and Additions
|  | 199656 | PWRT/SAN/014/18/MP | Mpumalanga | Thokozani Primary School | 800023226 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2022-04-15 |  |  | 312083 | 2600695 | 2912778 | Education Infrastructure Grant | Upgrading and Additions
|  | 199666 | DPWRT/171/19MP(MBEDLWANA SEC)------------ | Mpumalanga | Mbedlwana Secondary School | 800013698 | Thembisile | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2022-04-15 |  |  | 172843 | 1440355 | 1613198 | Education Infrastructure Grant | Upgrading and Additions
|  | 199992 | MDOE/MAIN/76/21-22 | Mpumalanga | Alfred Matshine Combined School | 800034879 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 114665 | 764432 | 879097 | Education Infrastructure Grant | Maintenance and Repairs
|  | 199999 | MDOE/MAIN/044/22 | Mpumalanga | Ditau Secondary School | 800035121 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 43382 | 433816 | 477198 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200007 | MDOE/MAIN/67/21-22 | Mpumalanga | Ekuphakameni Primary School | 800003269 | Dr JS Moroka | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 352500 | 2350000 | 2702500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200012 | MDOE/MAIN/75/21-22 | Mpumalanga | Gezingqondo Secondary School | 800035093 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 264816 | 1765437 | 2030253 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200014 | MDOE/MAIN/66/21-22 | Mpumalanga | Sanqotho Primary School | 800019877 | Msukaligwa | Project Initiation | Active - Not Contracted | 2021-05-01 |  | 2024-03-31 |  |  | 202500 | 1385100 | 1587600 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200016 | MDOE/MAIN/74/21-22 | Mpumalanga | Harmony Hill Primary School | 800019687 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 184833 | 1232219 | 1417052 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200027 | MDOE/MAIN/042/22 | Mpumalanga | Mashishing Secondary School | 800012898 | Thaba Chweu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 40999 | 409987 | 450986 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200028 | DoE/Boh/MAIN/155 | Mpumalanga | Masilela Secondary School | 800034944 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 21456 | 214556 | 236012 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200048 | MDOE/MAIN/04/21-22 | Mpumalanga | Ndawonye Primary School | 800016337 | Mkhondo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 36500 | 3644295 | 3680795 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200053 | MDOE/MAIN/62/21-22 | Mpumalanga | Nhanyane Primary school | 800035379 | Nkomazi | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 10322 | 687672 | 697994 | Education Infrastructure Grant | Maintenance and Repairs
|  | 200567 | MDOE/MAIN/35/21-22 | Mpumalanga | Saselani Primary School | 800034956 | Bushbuckridge | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 1557112 | 1557112 | 3114224 | Education Infrastructure Grant | Maintenance and Repairs
|  | 202415 | GDE00002 | Gauteng | Actonville Training Centre LSEN | 700311704 | City of Ekurhuleni | Feasibility | Proposed | 2022-04-01 |  | 2025-07-18 |  |  | 5000000 | 35000000 | 40000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 202605 | MGUBHOSADDITIONAL SANITATION | Mpumalanga | Mgubho Combined School | 800014100 | Nkomazi | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 210900 | 1054500 | 1265400 | Education Infrastructure Grant | Upgrading and Additions
|  | 202606 | LOWVELDHSSADDITIONAL SANITATION | Mpumalanga | Lowveld High Secondary school | 800010736 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 717368 | 3586840 | 4304208 | Education Infrastructure Grant | Upgrading and Additions
|  | 202610 | BERGVLAMADDITIONALSANITATION | Mpumalanga | H/S Bergvlam Secondary school | 800005744 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2025-11-30 |  |  | 717368 | 3586840 | 4304208 | Education Infrastructure Grant | Upgrading and Additions
|  | 202613 | VALENCIAADITIONALSANITATION | Mpumalanga | Valencia Combined School | 800024521 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 281200 | 1406000 | 1687200 | Education Infrastructure Grant | Upgrading and Additions
|  | 202619 | VICTORYPARKADDITIONAL SANITATION | Mpumalanga | Victory Park Combined School | 800024661 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 210900 | 1054500 | 1265400 | Education Infrastructure Grant | Upgrading and Additions
|  | 202622 | KAMAGUGUADDITIONALSANITATION | Mpumalanga | Kamagugu Inclusive Special School | 800028829 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 281200 | 1406000 | 1687200 | Education Infrastructure Grant | Upgrading and Additions
|  | 202623 | INGWENYAMAADDITIONALSANITATION | Mpumalanga | Ingwenyama primary School | 800006296 | Nkomazi | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 372000 | 1860000 | 2232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 202624 | EMJINDINIADDITIONALSANITATION | Mpumalanga | Emjindini Secondary school | 800003574 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-03-31 |  |  | 210900 | 1054500 | 1265400 | Education Infrastructure Grant | Upgrading and Additions
|  | 202628 | ENZANIADDITIONAL SANITATION | Mpumalanga | Enzani Primary School | 800003848 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2023-12-30 |  |  | 227440 | 1137200 | 1364640 | Education Infrastructure Grant | Upgrading and Additions
|  | 202636 | GEDLEMBANEADITIONALSANITATION | Mpumalanga | Gedlembane Secondary school | 800004432 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 625000 | 3125000 | 3750000 | Education Infrastructure Grant | Upgrading and Additions
|  | 202641 | MTIMADZEADDITIONALSANITATION | Mpumalanga | Mtimandze Secondary school | 8000401144 | Nkomazi | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 465000 | 2325000 | 2790000 | Education Infrastructure Grant | Upgrading and Additions
|  | 202647 | TONGAVIEWADDITIONALSANITATION | Mpumalanga | Tongaview primary School | 800032862 | Nkomazi | Feasibility | Proposed | 2023-04-01 |  | 2023-11-30 |  |  | 168720 | 843600 | 1012320 | Education Infrastructure Grant | Upgrading and Additions
|  | 202649 | DPWRT/133/18/MP(SCHOEMANSDAL SEC--------- | Mpumalanga | Schoemansdal primary School | 800019968 | Nkomazi | Design | Active - Not Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 23830075 | 4649771 | 28479846 | Education Infrastructure Grant | Upgrading and Additions
|  | 202665 | CYRILCLARKEADDITIONALSANITATION | Mpumalanga | Cyril Clarke Secondary school | 800002303 | Mbombela | Feasibility | Proposed | 2022-04-01 |  | 2023-03-30 |  |  | 372000 | 1860000 | 2232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 202666 | JOHNMDLULIADDITIONALSANITATION | Mpumalanga | John Mdluli primary | 800007112 | Mbombela | Feasibility | Proposed | 2022-04-01 |  | 2023-03-30 |  |  | 372000 | 1860000 | 2232000 | Education Infrastructure Grant | Upgrading and Additions
|  | 202668 | BARBERTON WATERANDSEWER | Mpumalanga | Barberton Laer/s primary | 800000653 | Mbombela | Feasibility | Proposed | 2023-04-01 |  | 2024-11-30 |  |  | 54600 | 273000 | 327600 | Education Infrastructure Grant | Upgrading and Additions
|  | 202669 | BERGLANDADDITIONALSANITATION | Mpumalanga | Bergland Primary School | 800009001 | Mbombela | Feasibility | Proposed | 2022-04-01 |  | 2024-11-30 |  |  | 281200 | 1406000 | 1687200 | Education Infrastructure Grant | Upgrading and Additions
|  | 202678 | non infrastructure | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Not Contracted | 2022-04-01 | 2022-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 400000000 | 400000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 203678 | TBA 94 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2021-04-01 |  | 2024-03-29 |  |  | 30000000 | 142000000 | 172000000 | Equitable Share | Maintenance and Repairs
|  | 203969 | GDE00309 | Gauteng | RIETVALLEI EXTENSION 1 SECONDARY SCHOOL | 700400524 | Mogale City | Feasibility | Approved | 2021-11-01 |  | 2026-04-02 |  |  | 2000000 | 10000000 | 12000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 204177 | P9005951_ | Eastern Cape | MTHAWELANGA JUNIOR PRIMARY SCHOOL | 200600522 | Enoch Mgijima | Design | Active - Not Contracted | 2018-04-01 |  | 2026-03-31 |  |  | 0 | 7209303 | 7209303 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 204179 | P9004565_ | Eastern Cape | NCAPAI JUNIOR SECONDARY SCHOOL | 200300411 | Umzimvubu | Practical Completion (100%) | Active - Contracted | 2018-09-01 | 2018-09-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5669263 | 5669263 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 204181 | P9013187 | Eastern Cape | AMAZIZI SENIOR SECONDARY SCHOOL | 200200017 | Ngqushwa | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204182 | P9013358 | Eastern Cape | BAMBILANGA SENIOR SECONDARY SCHOOL | 200400015 | King Sabata Dalindyebo | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204183 | P9013204 | Eastern Cape | BLIKANA SENIOR SECONDARY SCHOOL | 200600049 | Senqu | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204184 | P9013206 | Eastern Cape | BROOKSNEK JUNIOR SECONDARY SCHOOL | 200501417 | Umzimvubu | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204185 | P9013220 | Eastern Cape | BULUGHA PRIMARY SCHOOL | 200200066 | Great Kei | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204186 | P9013262 | Eastern Cape | CANDU JUNIOR SECONDARY SCHOOL | 200300837 | Mbhashe | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204187 | P9013276 | Eastern Cape | CHEBENCA JUNIOR SECONDARY FARM SCHOOL | 200400076 | Elundini | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204188 | P9013251 | Eastern Cape | CINTSA EAST PRIMARY SCHOOL | 200200086 | Great Kei | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204189 | P9013202 | Eastern Cape | CWEBENI JUNIOR SECONDARY SCHOOL | 200400092 | Umzimvubu | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204190 | P9013213 | Eastern Cape | DALASILE PRIMARY SCHOOL | 200600125 | Enoch Mgijima | Design | Active - Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204191 | P9013200 | Eastern Cape | DUNGU JUNIOR SECONDARY SCHOOL | 200500152 | Umzimvubu | Design | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1321327 | 1321327 | Education Infrastructure Grant | Upgrading and Additions
|  | 204192 | P9013231 | Eastern Cape | ELUNYAWENI JUNIOR SECONDARY SCHOOL | 200400155 | Elundini | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204193 | P9013209 | Eastern Cape | EMAZWENI JUNIOR PRIMARY SCHOOL | 200500183 | Mbizana | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204194 | P9013243 | Eastern Cape | ESIDWADWENI PRIMARY SCHOOL | 200400169 | Mhlontlo | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204195 | P9013350 | Eastern Cape | FARVIEW JUNIOR SECONDARY SCHOOL | 200500228 | Umzimvubu | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204196 | P9013212 | Eastern Cape | FEZIWE PRIMARY SCHOOL | 200200178 | Buffalo City | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204197 | P9013230 | Eastern Cape | FRANK MOSHESH JUNIOR SECONDARY SCHOOL | 200400184 | Elundini | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204198 | P9013246 | Eastern Cape | GANGATA JUNIOR SECONDARY SCHOOL | 200400193 | Nyandeni | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204201 | P9013240 | Eastern Cape | GCINA JUNIOR SECONDARY SCHOOL | 200600209 | Enoch Mgijima | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204203 | P9013235 | Eastern Cape | GEORGE NTANTA JUNIOR SECONDARY SCHOOL | 200500253 | Ingquza Hill | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204205 | P9013221 | Eastern Cape | GUATA JUNIOR SECONDARY SCHOOL | 200600231 | Sakhisizwe | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204206 | P9013252 | Eastern Cape | GUBEVU PRIMARY SCHOOL | 200300118 | Mnquma | Tender | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204277 | P9013253 | Eastern Cape | GUQA JUNIOR PRIMARY SCHOOL | 200500280 | Mbizana | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204278 | P9013232 | Eastern Cape | IZAGWITYI PRIMARY SCHOOL | 200300150 | Mnquma | Design | Active - Not Contracted | 2019-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204280 | P9013272 | Eastern Cape | JAMES KOBI JUNIOR SECONDARY SCHOOL | 200401332 | King Sabata Dalindyebo | Design | Active - Not Contracted | 2023-03-31 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204283 | P9013224 | Eastern Cape | MPOZA JUNIOR SECONDARY SCHOOL | 200400649 | Mhlontlo | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204290 | P9013189 | Eastern Cape | JONGILANGA SENIOR SECONDARY SCHOOL | 200300168 | Mbhashe | Design | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 888741 | 888741 | Education Infrastructure Grant | Upgrading and Additions
|  | 204304 | LE22ITRU00001 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 26% - 50% | Active - Contracted | 2021-01-01 | 2021-02-04 | 2023-03-31 | 2022-03-31 | 2022-03-31 | 0 | 4443424 | 4443424 | Education Infrastructure Grant | Non-Infrastructure
|  | 204309 | P9008608_ | Eastern Cape | MPIKWANA JUNIOR SECONDARY SCHOOL | 200400645 | King Sabata Dalindyebo | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 1000 | 1000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204318 | P9013219 | Eastern Cape | NYATELA SENIOR SECONDARY SCHOOL | 200600649 | Senqu | Design | Active - Not Contracted | 2019-04-02 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204319 | P9006939_ | Eastern Cape | NOTINTSILA JUNIOR SECONDARY SCHOOL | 200400834 | Nyandeni | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 1121 | 1121 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204320 | P9011728 | Eastern Cape | SITOROMO JUNIOR SECONDARY SCHOOL | 200600754 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 2500000 | 2500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204444 | P9007048 | Eastern Cape | JABAVU HIGH SCHOOL | 200200283 | Raymond Mhlaba | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 6000000 | 6000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204446 | P9004882 | Eastern Cape | SCHOOLS & OFFICE FURNITURE - 02 | 200999925 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204447 | P9013433 | Eastern Cape | BERLIN HIGH SCHOOL | 200100320 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204448 | P9013364 | Eastern Cape | JONGILANGA SENIOR SECONDARY SCHOOL | 200300168 | Mbhashe | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204449 | P9013270 | Eastern Cape | JUMBA SENIOR SECONDARY SCHOOL | 200401269 | King Sabata Dalindyebo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204450 | P9013190 | Eastern Cape | KHONJWAYO SENIOR PRIMARY SCHOOL | 200500358 | Ingquza Hill | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204451 | P9013269 | Eastern Cape | LEPPAN PRIMARY SCHOOL | 200400356 | Mhlontlo | Design | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1321327 | 1321327 | Education Infrastructure Grant | Upgrading and Additions
|  | 204452 | P9013194 | Eastern Cape | LUXOLO INTERMEDIATE SCHOOL | 200100475 | Dr Beyers Naude | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204453 | P9013192 | Eastern Cape | MANZANA SENIOR SECONDARY SCHOOL | 200400487 | Engcobo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204454 | P9013203 | Eastern Cape | MATTHEW GONIWE PRIMARY SCHOOL | 200200777 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204456 | P9008737 | Eastern Cape | MBODLENI SENIOR SECONDARY SCHOOL | 200500383 | Umzimvubu | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204457 | P9013273 | Eastern Cape | MPEKO PRIMARY SCHOOL | 200200497 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204458 | P9013201 | Eastern Cape | MVUBU PRIMARY SCHOOL | 200500813 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204459 | P9013186 | Eastern Cape | MZIKAYISE DALASILE SENIOR SECONDARY SCHOOL | 200400693 | Engcobo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204460 | P9013184 | Eastern Cape | NGUBESIZWE SENIOR SECONDARY SCHOOL | 200300443 | King Sabata Dalindyebo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1321327 | 1321327 | Education Infrastructure Grant | Upgrading and Additions
|  | 204461 | P9013205 | Eastern Cape | NOMBIZO SENIOR PRIMARY SCHOOL | 200400819 | Mhlontlo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204462 | P9013195 | Eastern Cape | NOSIZWE HIGH SCHOOL | 200200635 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204463 | P9013188 | Eastern Cape | PAMBILI SENIOR SECONDARY SCHOOL | 200501017 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204465 | P9013208 | Eastern Cape | ST MARKS TECHNICAL SENIOR SECONDARY SCHOOL | 200500726 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204466 | P9013185 | Eastern Cape | SUKUDE SENIOR SECONDARY SCHOOL | 200501171 | Ntabankulu | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204467 | P9013196 | Eastern Cape | TSHATSHU PRIMARY SCHOOL | 200200972 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-30 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204469 | P9013199 | Eastern Cape | ZANOKHANYO JUNIOR SECONDARY SCHOOL | 200300680 | Mnquma | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1321327 | 1321327 | Education Infrastructure Grant | Upgrading and Additions
|  | 204470 | P9008735 | Eastern Cape | MACACUMA SENIOR PRIMARY SCHOOL | 200600406 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 693882 | 693882 | Education Infrastructure Grant | Upgrading and Additions
|  | 204471 | P9008736 | Eastern Cape | MBEKWA JUNIOR SECONDARY SCHOOL | 200500615 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 693882 | 693882 | Education Infrastructure Grant | Upgrading and Additions
|  | 204472 | P9013260 | Eastern Cape | KAMASTONE PRIMARY SCHOOL | 200600979 | Enoch Mgijima | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204473 | P9013239 | Eastern Cape | KINKELBOS PRIMARY SCHOOL | 200100389 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204474 | P9013247 | Eastern Cape | LOWER DIDIMANA JUNIOR PRIMARY SCHOOL | 200600382 | Enoch Mgijima | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204475 | P9013245 | Eastern Cape | LUKHANYO JUNIOR SECONDARY SCHOOL | 200300241 | Mnquma | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204476 | P9013226 | Eastern Cape | MAGCAKINI JUNIOR SECONDARY SCHOOL | 200400449 | Nyandeni | Project Initiation | Proposed | 2021-04-01 |  | 2024-03-30 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204477 | P9013228 | Eastern Cape | MASIZAKHE HIGH SCHOOL | 200100500 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204478 | P9013241 | Eastern Cape | MATOMELA SENIOR SECONDARY SCHOOL | 200200440 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-30 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204479 | P9013210 | Eastern Cape | MAZIBUKO SENIOR SECONDARY SCHOOL | 200600456 | Sakhisizwe | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204480 | P9013215 | Eastern Cape | MZUXOLILE HIGH SCHOOL | 200200534 | Ngqushwa | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204481 | P9013214 | Eastern Cape | NGCATARU JUNIOR SECONDARY SCHOOL | 200400738 | Engcobo | Design | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204482 | P9013223 | Eastern Cape | NONYAMEKO PRIMARY SCHOOL | 200200629 | Amahlathi | Design | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204483 | P9013242 | Eastern Cape | NTLALONTLE JUNIOR SECONDARY SCHOOL | 200600639 | Emalahleni | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204484 | P9013182 | Eastern Cape | KUYASA SENIOR SECONDARY SCHOOL | 200200334 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 900522 | 900522 | Education Infrastructure Grant | Upgrading and Additions
|  | 204485 | P9013233 | Eastern Cape | NTLANEZWE SENIOR PRIMARY SCHOOL | 200500425 | Mbizana | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204486 | P9013278 | Eastern Cape | OVISTON PRIMARY SCHOOL | 200600655 | Walter Sisulu | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204487 | P9013244 | Eastern Cape | SAJINI JUNIOR SECONDARY SCHOOL | 200300558 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204488 | P9013258 | Eastern Cape | SEYMOUR PRIMARY SCHOOL | 200200754 | Raymond Mhlaba | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Upgrading and Additions
|  | 204489 | P9013249 | Eastern Cape | SIKITINI SENIOR PRIMARY SCHOOL | 200500243 | Ingquza Hill | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204490 | P9013324 | Eastern Cape | TSHAPHILE SENIOR PRIMARY SCHOOL | 200401066 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204491 | P9013332 | Eastern Cape | ZWELIHLE SENIOR SECONDARY SCHOOL | 200401213 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204492 | P9013254 | Eastern Cape | LOWER NDAKANA JUNIOR SECONDARY SCHOOL | 200300228 | Mnquma | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204493 | P9013255 | Eastern Cape | MAMATA PRIMARY SCHOOL | 200200408 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204494 | P9013257 | Eastern Cape | NANGAMSO SECONDARY SCHOOL | 200200537 | Amahlathi | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204495 | P9013274 | Eastern Cape | NGONYAMA JUNIOR PRIMARY SCHOOL | 200400749 | King Sabata Dalindyebo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204496 | P9013264 | Eastern Cape | RIVERVIEW PRIMARY SCHOOL | 200400967 | Mbhashe | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204497 | P9013271 | Eastern Cape | SIDANDA PRIMARY SCHOOL | 200400995 | King Sabata Dalindyebo | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204498 | P9013177 | Eastern Cape | SIDINANE SENIOR SECONDARY SCHOOL | 200501098 | Elundini | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Upgrading and Additions
|  | 204499 | P9013265 | Eastern Cape | ZULUMEMA PRIMARY SCHOOL | 200600954 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204500 | P9013259 | Eastern Cape | ZWELITSHA PRIMARY SCHOOL | 200200961 | Buffalo City | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-30 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Upgrading and Additions
|  | 204501 | P9008739 | Eastern Cape | SAFE SANITATION PROGRAMME | 200999925 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 349629 | 349629 | Education Infrastructure Grant | Upgrading and Additions
|  | 204512 | P9013315 | Eastern Cape | LOWER MGWALANA PRIMARY SCHOOL | 200200369 | Enoch Mgijima | Project Initiation | Proposed | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204581 | ECD MAIN 001 | North West | ECD MAINTENANCE SUBSIDY | ECD MAIN 001 | Mafikeng | Project Initiation | Approved | 2022-04-01 |  | 2026-03-30 |  |  | 0 | 10000000 | 10000000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 204585 | P9011616 | Eastern Cape | CLARKEBURY AGRICULTURAL SCHOOL - Sanitation | 200400084 | Engcobo | Design | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 26914656 | 26914656 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204587 | P9011631 | Eastern Cape | MAKAULA SENIOR SECONDARY SCHOOL - Sanitation (Hostel) | 200500534 | Umzimvubu | Design | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 12650000 | 12650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204588 | P9008430_ | Eastern Cape | SCHOOLS & OFFICE FURNITURE - 01 | 200999925 | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 30000 | 30000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204589 | P9007300_ | Eastern Cape | PHANDULWAZI AGRICULTURAL HIGH SCHOOL - Water | 200200684 | Raymond Mhlaba | Construction 51% - 75% | Active - Contracted | 2021-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8493981 | 8493981 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204590 | P9011719/ | Eastern Cape | NOZIZWE PRIMARY SCHOOL (Language Academy) | 200300496 | Buffalo City | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 7481110 | 7481110 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204591 | P9006791_ | Eastern Cape | NYANGA SENIOR SECONDARY SCHOOL - Water | 200400893 | Engcobo | Construction 26% - 50% | Active - Contracted | 2021-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 7196735 | 7196735 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204592 | P9006381 | Eastern Cape | CHARLES DUNA PUBLIC SCHOOL | 200100112 | Nelson Mandela Bay | Construction 51% - 75% | Active - Contracted | 2021-04-01 | 2022-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 3477159 | 3477159 | Education Infrastructure Grant | Upgrading and Additions
|  | 204593 | P9007299_ | Eastern Cape | St MATTHEWS HIGH SCHOOL | 200200816 | Amahlathi | Construction 51% - 75% | Active - Contracted | 2021-04-01 | 2022-08-12 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 5344609 | 5344609 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204594 | P9011630 | Eastern Cape | LA-GRANGE SENIOR SECONDARY SCHOOL - Sanitation | 200501091 | Matatiele | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 2716969 | 2716969 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204595 | P9006781_ | Eastern Cape | NDAMASE SENIOR SECONDARY SCHOOL - Water | 200400716 | Nyandeni | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 5957595 | 5957595 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204596 | P9011710 | Eastern Cape | MZOMHLE SENIOR SECONDARY SCHOOL | 200200528 | Buffalo City | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 5000000 | 5000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204598 | P9006651_ | Eastern Cape | BLYTHSWOOD HIGH SCHOOL - Water | 200300024 | Mnquma | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 8278319 | 8278319 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204599 | P9010502_ | Eastern Cape | NCUNCUZO SENIOR SECONDARY SCHOOL | 200600552 | Intsika Yethu | Construction 51% - 75% | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 7324144 | 7324144 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204600 | P9006988_ | Eastern Cape | MAHEDI JUNIOR SECONDARY SCHOOL | 200600417 | Senqu | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2025-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 8157926 | 8157926 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204601 | P9011654 | Eastern Cape | LA-GRANGE SENIOR SECONDARY SCHOOL - Water (Phase II) | 200501091 | Matatiele | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 949464 | 949464 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204602 | P9006981_ | Eastern Cape | NKULULEKO SENIOR SECONDARY SCHOOL | 200600589 | Walter Sisulu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 5948222 | 5948222 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204604 | P9006788_ | Eastern Cape | NOMPUMALANGA SPECIAL SCHOOL - Water | 200501355 | Mbizana | Construction 51% - 75% | Active - Contracted | 2021-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 4787298 | 4787298 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204605 | P9006657_ | Eastern Cape | DALINDYEBO SENIOR SECONDARY SCHOOL - Water | 200400106 | King Sabata Dalindyebo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 3325055 | 3325055 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204623 | P9011634 | Eastern Cape | MOUNT ARTHUR GIRLS HIGH SCHOOL - Fire | 200601142 | Emalahleni | Design | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 6651221 | 6651221 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204641 | P9007303_ | Eastern Cape | THUBALETHU SECONDARY SCHOOL - Water | 200100908 | Raymond Mhlaba | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 2962336 | 2962336 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204642 | P9007294_ | Eastern Cape | ST THOMAS SPECIAL SCHOOL | 200200819 | Buffalo City | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 203820 | 203820 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204643 | P9006793_ | Eastern Cape | RIETBERG PRIMARY SCHOOL | 200100652 | Sundays River Valley | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 5733 | 5733 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204644 | P9006659_ | Eastern Cape | DALUXOLO JUNIOR SECONDARY SCHOOL | 200300060 | Mnquma | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 111092 | 111092 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204645 | P9004807_ | Eastern Cape | ESINYAMENI SENIOR PRIMARY SCHOOL | 200500216 | Mbizana | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 93714 | 93714 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204651 | P9006737_ | Eastern Cape | HUNTLY GLEN FARM SCHOOL | 200100326 | Raymond Mhlaba | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 3226 | 3226 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204658 | P9006777_ | Eastern Cape | MOUNT ARTHUR GIRLS HIGH SCHOOL - Water (Phase II) | 200601142 | Emalahleni | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 3226 | 3226 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204660 | P9004898 | Eastern Cape | AYLIFF PRIMARY SCHOOL | 200200027 | Ngqushwa | Project Initiation | Active - Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204670 | P9005473 | Eastern Cape | BETHELSDORP ROAD PRIMARY SCHOOL | 200100065 | Nelson Mandela Bay | Feasibility | Active - Not Contracted | 2020-10-01 |  | 2026-03-31 |  |  | 0 | 233675 | 233675 | Education Infrastructure Grant | Upgrading and Additions
|  | 204688 | P9008733 | Eastern Cape | FENCING | 200999925 | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 15000000 | 15000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204699 | P9005117_ | Eastern Cape | ESIGUBUDWINI PRE - PRIMARY | 200800931 | Ingquza Hill | Construction 76% - 99% | Active - Contracted | 2021-04-01 | 2021-04-02 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 1599141 | 1599141 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204702 | P9010650 | Eastern Cape | NEWTOWN HIGH SCHOOL | 200100051 | Raymond Mhlaba | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1016370 | 1016370 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204704 | P0003559 | Eastern Cape | MCEULA PRIMARY SCHOOL | 200600469 | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 289810 | 289810 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204710 | P0002086_ | Eastern Cape | MASAKHANE COMBINED SCHOOL | 200100554 | Makana | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 176850 | 176850 | Education Infrastructure Grant | Upgrading and Additions
|  | 204713 | 200501459 | Eastern Cape | NDZULULWAZI SENIOR SECONDARY SCHOOL | 200501459 | Umzimvubu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 113207 | 113207 | Education Infrastructure Grant | Upgrading and Additions
|  | 204714 | P0002585 | Eastern Cape | ITHEMBELIHLE COMPREHENSIVE SCHOOL | 200100344 | Nelson Mandela Bay | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 111966 | 111966 | Education Infrastructure Grant | Upgrading and Additions
|  | 204717 | P0002319_ | Eastern Cape | MRWABO PRIMARY SCHOOL | 200500777 | Matatiele | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 3705031 | 3705031 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204721 | 200500777_ | Eastern Cape | MRWABO PRIMARY SCHOOL | 200500777 | Matatiele | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 108679 | 108679 | Education Infrastructure Grant | Upgrading and Additions
|  | 204723 | 200500515 | Eastern Cape | MAGOBA JUNIOR SECONDARY SCHOOL | 200500515 | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 89521 | 89521 | Education Infrastructure Grant | Upgrading and Additions
|  | 204869 | 200400197_ | Eastern Cape | GAVIN JUNIOR SECONDARY SCHOOL | EC | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 77456 | 77456 | Education Infrastructure Grant | Upgrading and Additions
|  | 204871 | 200600548 | Eastern Cape | NCEBA PUBLIC SCHOOL | 200600548/P9005101 | Enoch Mgijima | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 76981 | 76981 | Education Infrastructure Grant | Upgrading and Additions
|  | 204875 | P0002093_ | Eastern Cape | MPAKO JUNIOR SECONDARY SCHOOL | 200400636 | King Sabata Dalindyebo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 65660 | 65660 | Education Infrastructure Grant | Upgrading and Additions
|  | 204877 | TBA_388 | Eastern Cape | MDENI SENIOR SECONDARY SCHOOL | 200300314 | Mbhashe | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 51622 | 51622 | Education Infrastructure Grant | Upgrading and Additions
|  | 204878 | P9004945_ | Eastern Cape | UPPER MBULUKWEZA JUNIOR SECONDARY SCHOOL | 200300754 | Intsika Yethu | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 40755 | 40755 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204879 | P9008731 | Eastern Cape | BUTTERWORTH HIGH SCHOOL | 200300741 | Mnquma | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 31225 | 31225 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204880 | 200401058_ | Eastern Cape | TIPINI JUNIOR SECONDARY SCHOOL | 200401058 | King Sabata Dalindyebo | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 22641 | 22641 | Education Infrastructure Grant | Upgrading and Additions
|  | 204882 | 200500990 | Eastern Cape | NYANISO SENIOR SECONDARY SCHOOL | 200500990 | Matatiele | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 22641 | 22641 | Education Infrastructure Grant | Upgrading and Additions
|  | 204886 | P0002693_ | Eastern Cape | JIBA SENIOR SECONDARY SCHOOL | 200500333 | Ingquza Hill | Project Initiation | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10868 | 10868 | Education Infrastructure Grant | Maintenance and Repairs
|  | 204927 | NSNP KIT 001 | North West | NSNP KITCHEN PROGRAMME | 1 | Mafikeng | Construction 1% - 25% | Approved | 2022-04-01 | 2023-10-30 | 2024-03-01 | 2024-03-15 | 2025-03-25 | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 204944 | P9004946_ | Eastern Cape | WHEATLANDS JUNIOR SECONDARY SCHOOL | 200401281 | Elundini | Project Initiation | Active - Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 0 | 10868 | 10868 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205324 | MDOE/MAIN/15/22-23 | Mpumalanga | Zwide Primary School | 800029512 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 120582 | 803880 | 924462 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205326 | MDOE/MAIN/55/21-2202 | Mpumalanga | Likhweti Primary School | 800010421 | Mbombela | Project Initiation | Active - Contracted | 2021-04-01 |  | 2024-04-15 |  |  | 321170 | 2294076 | 2615246 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205345 | MDOE/MAIN/108/21-22 | Mpumalanga | Buhlebuyeta Primary School | 800001727 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 299672 | 2996723 | 3296395 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205346 | MDOE/MAIN/22-23/05 | Mpumalanga | Camalaza Secondary School | 800001875 | Nkomazi | Project Initiation | Active - Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 487835 | 4878345 | 5366180 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205348 | MDOE/MAIN/047/22 | Mpumalanga | Chayiwe Primary School | 800034964 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-31 |  |  | 39878 | 398778 | 438656 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205351 | MDOE/MAIN/22-23/07 | Mpumalanga | Duma Primary School | 800002881 | Mbombela | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 408735 | 4087345 | 4496080 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205353 | MDOE/MAIN/22-23/08 | Mpumalanga | EJ Singwane Secondary School | 800003178 | Mbombela | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 621326 | 6213255 | 6834581 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205355 | MDOE/MAIN/111/21-22 | Mpumalanga | Ekwazini Secondary School | 800003335 | Steve Tshwete | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 584018 | 5840181 | 6424199 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205356 | MDOE//MAIN/114 | Mpumalanga | Emakhazeni Combined Boarding School | 800035652 | Emakhazeni | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 240495 | 3404954 | 3645449 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205357 | MDOE/MAIN/22-23/09 | Mpumalanga | Ematholeni Primary school | 800003491 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 654389 | 6543888 | 7198277 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205358 | DPWRT/MAIN/044/21MP | Mpumalanga | Emtfuntini Primary School | 800008599 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2022-03-01 |  | 2025-03-31 |  |  | 492357 | 4923567 | 5415924 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205359 | DPWRT/SAN/187/20MP | Mpumalanga | Engabezweni Secondary School | 800026724 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 531121 | 5311214 | 5842335 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205361 | MDOE/MAIN/22-23/11 | Mpumalanga | Enzani Primary School | 800003848 | Mbombela | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 321457 | 3214569 | 3536026 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205399 | DoE/Boh/MAIN/186 | Mpumalanga | Mmasekobe Secondary School | 800035131 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 40699 | 406987 | 447686 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205400 | MDOE/MAIN/46/21-22 | Mpumalanga | Siyamukela Primary School | 800034783 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 23464 | 1407484 | 1430948 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205401 | MDOE/MAIN/22-23/18 | Mpumalanga | Khulamshika Primary School | 800007807 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 621326 | 6213255 | 6834581 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205409 | MDOE/MAIN/22-23/262 | Mpumalanga | Ziphakamiseni Secondary School | 800029629 | Thembisile | Project Initiation | Active - Not Contracted | 2024-04-01 |  | 2025-03-31 |  |  | 309887 | 3098874 | 3408761 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205425 | MDOE/MAIN/119/22 | Mpumalanga | Tisiteni Primary School | 800023606 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 214322 | 2143215 | 2357537 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205431 | DoE/NKD/MAIN/033 | Mpumalanga | Imemeza Secondary School | 800006189 | Emakhazeni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 221457 | 2214578 | 2436035 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205442 | MDOE/MAIN/095/22 | Mpumalanga | Thubelihle Primary School | 800023209 | Thembisile | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 1334323 | 1334323 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205449 | MDOE/MAIN/22-23/01 | Mpumalanga | Khombindlela Secondary School | 800007724 | Mbombela | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 205781 | 2057817 | 2263598 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205454 | MDOE/MAIN/112/21-22 | Mpumalanga | Sukumani Primary School | 800022571 | Emalahleni | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 689987 | 6899871 | 7589858 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205457 | MDOE/MAIN/22-23/17 | Mpumalanga | KHULA SAKHILE SECONDARY SCHOOL | 800007773 | Lekwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2024-03-31 |  |  | 422134 | 4221343 | 4643477 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205564 | MDOE/MAIN/22-23/225 | Mpumalanga | Sithabile Primary School | 800021360 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 342116 | 3421156 | 3763272 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205569 | MDOE/MAIN/22-23/222 | Mpumalanga | Siphendulwe | 800021261 | Emalahleni | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 601458 | 6014578 | 6616036 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205594 | MDOE/MAIN/22-23/206 | Mpumalanga | Qokisa High School | 800034954 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 465887 | 4658874 | 5124761 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205597 | MDOE/MAIN/22-23/204 | Mpumalanga | Pungutsha Secondary School | 800018770 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 623235 | 6232345 | 6855580 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205604 | DPWRT/SAN/231/20/MP | Mpumalanga | Kroomdraai Primary School | 800008524 | Emalahleni | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-12-31 |  |  | 340960 | 3409601 | 3750561 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205620 | DOE/NKD/P090 | Mpumalanga | Lefiso Primary School | 80009993 | Dr JS Moroka | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 302458 | 3024587 | 3327045 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205629 | DoE/NKD/MAIN/032 | Mpumalanga | Mabande Secondary School | 800011049 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 634649 | 4533211 | 5167860 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205634 | MDOE/MAIN/22-23/178 | Mpumalanga | Mvuzo Primary School | 800015230 | Steve Tshwete | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 501121 | 5011211 | 5512332 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205649 | MDOE/MAIN/22-23/27 | Mpumalanga | Magcekeni Primary School | 800030429 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 432845 | 4328459 | 4761304 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205659 | MDOE/MAIN/22-23/30 | Mpumalanga | Majika Primary School | 800011775 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 357127 | 3571277 | 3928404 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205663 | MDOE/MAIN/22-23/31 | Mpumalanga | Maminza Primary School | 800000430 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 357127 | 3571277 | 3928404 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205667 | MDOE/MAIN/22-23/33 | Mpumalanga | Manzolwandle Primary School | 800012443 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 399123 | 3991232 | 4390355 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205675 | MDOE/MAIN/22-23/36 | Mpumalanga | Mbangwane Primary School | 800013656 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 429672 | 4296723 | 4726395 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205679 | MDOE/MAIN/115/22 | Mpumalanga | Mbalenhle Secondary School | 800013623 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-03-31 |  |  | 395128 | 2822346 | 3217474 | Education Infrastructure Grant | Maintenance and Repairs
|  | 205685 | MDOE/MAIN/22-23/35 | Mpumalanga | Mawewe Primary School | 800013524 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-03-31 |  |  | 301407 | 3014077 | 3315484 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206035 | P9007107 | Eastern Cape | INYIBIBA PUBLIC SECONDARY SCHOOL | 200100338 | Raymond Mhlaba | Design | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 10819034 | 10819034 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206036 | P9006084 | Eastern Cape | MATYEBA PRIMARY SCHOOL | 200400513 | Mhlontlo | Design | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 8912492 | 8912492 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206058 | P9007169 | Eastern Cape | MTHONYAMENI SENIOR PRIMARY SCHOOL | 200400675 | Mhlontlo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 8580183 | 8580183 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206059 | P9006849_ | Eastern Cape | LUNGELOLETHU PRIMARY SCHOOL | 200200382 | Amahlathi | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 7402008 | 7402008 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206060 | P9004896 | Eastern Cape | MZONGWANA JUNIOR SECONDARY SCHOOL | 200500832 | Matatiele | Tender | Active - Not Contracted | 2021-12-01 |  | 2024-06-28 |  |  | 0 | 6576325 | 6576325 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206061 | P9013378 | Eastern Cape | STERKSPRUIT JUNIOR SECONDARY SCHOOL | 200600800 | Senqu | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 6303068 | 6303068 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206062 | P9007139_ | Eastern Cape | MBOZISA JUNIOR SECONDARY SCHOOL | 200400543 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 6090036 | 6090036 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206063 | P9011519 | Eastern Cape | NTSELAMANZI PRIMARY SCHOOL | 200200656 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 5964722 | 5964722 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206064 | P9010095 | Eastern Cape | MOSHI PRIMARY SCHOOL | 200400630 | Engcobo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 5944685 | 5944685 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206065 | P9010056 | Eastern Cape | MATSHONA JUNIOR SECONDARY SCHOOL | 200600236 | Intsika Yethu | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 5734991 | 5734991 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206066 | P0004244 | Eastern Cape | DALIBUNGA COMPREHENSIVE HIGH SCHOOL | 200401247 | Nyandeni | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 5716682 | 5716682 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206067 | P9004909 | Eastern Cape | NCERA PRIMARY SCHOOL | 200200544 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 4737760 | 4737760 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206068 | P9004885 | Eastern Cape | NOMPENDULO PRIMARY SCHOOL | 200300478 | Intsika Yethu | Design | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 4376936 | 4376936 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206069 | P9006022 | Eastern Cape | WINTERBERG AGRICULTURAL HIGH SCHOOL | 200100862 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 4287579 | 4287579 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206070 | P9004951 | Eastern Cape | LUKUNI JUNIOR SECONDARY SCHOOL | 200400402 | Nyandeni | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 4157489 | 4157489 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206071 | P9010046 | Eastern Cape | CHIEF MALEFANE PRIMARY SCHOOL | 200600101 | Enoch Mgijima | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 4002428 | 4002428 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206072 | P9013368 | Eastern Cape | CAFUTWENI JUNIOR SECONDARY SCHOOL | 200300041 | Mnquma | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3621494 | 3621494 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206073 | P0004437 | Eastern Cape | LUNDINI PRIMARY SCHOOL | 200501380 | Mbizana | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3508997 | 3508997 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206074 | P9009235 | Eastern Cape | ZIMISELE JUNIOR SECONDARY SCHOOL | 200501327 | Ingquza Hill | Tender | Active - Not Contracted | 2021-12-01 |  | 2024-06-28 |  |  | 0 | 3353135 | 3353135 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206075 | P9011548 | Eastern Cape | HLWAHLWAZI JUNIOR SECONDARY SCHOOL | 200500305 | Ingquza Hill | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3351413 | 3351413 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206076 | P9010094 | Eastern Cape | KHALENI SENIOR PRIMARY SCHOOL | 200500354 | Mbizana | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3317354 | 3317354 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206077 | P9009920 | Eastern Cape | SHUKUNXA JUNIOR SECONDARY SCHOOL | 200400992 | Mhlontlo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3102353 | 3102353 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206078 | P9007132_ | Eastern Cape | RAFUZA MNTUYEDWA SENIOR PRIMARY SCHOOL | 200400962 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2984751 | 2984751 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206079 | P9010067 | Eastern Cape | MBANGA PRIMARY SCHOOL | 200400526 | Mbhashe | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2859342 | 2859342 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206080 | P9004911 | Eastern Cape | MAYIBENYE SENIOR SECONDARY SCHOOL | 200500605 | Ingquza Hill | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2733522 | 2733522 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206081 | P9007129 | Eastern Cape | NGUBESIZWE PRIMARY SCHOOL | 200400771 | Mhlontlo | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2642688 | 2642688 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206082 | P9010096 | Eastern Cape | MAVUSO PRIMARY SCHOOL | 200200444 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2623316 | 2623316 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206083 | P9006899_ | Eastern Cape | UNATHI SENIOR SECONDARY SCHOOL | 200201047 | Buffalo City | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2591027 | 2591027 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206084 | P0004035 | Eastern Cape | LUTSHEKO JUNIOR SECONDARY SCHOOL | 200400416 | Nyandeni | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2473466 | 2473466 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206085 | P9010073 | Eastern Cape | MBANYANA JUNIOR SECONDARY SCHOOL | 200400528 | Mbhashe | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2461009 | 2461009 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206086 | P9010093 | Eastern Cape | MGWEDE JUNIOR SECONDARY SCHOOL | 200500669 | Mbizana | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2370119 | 2370119 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206087 | P9010387 | Eastern Cape | TSHATSHENI PRIMARY SCHOOL | 200400164 | Nyandeni | Tender | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 2291476 | 2291476 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206088 | P9006522 | Eastern Cape | ATHENKOSI PRIMARY SCHOOL | 200200024 | Buffalo City | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206089 | P9009696_ | Eastern Cape | BAJONGE JUNIOR SECONDARY SCHOOL | 200400010 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206090 | P9004601 | Eastern Cape | BOTSABELO JUNIOR SECONDARY SCHOOL | 200400049 | Elundini | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206091 | P9008714 | Eastern Cape | ENKWENKWEZINI SECONDARY SCHOOL | 200200164 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2024-06-28 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206092 | P9008715 | Eastern Cape | LANGALIVELILE PRIMARY SCHOOL | 200200353 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206093 | P9008716 | Eastern Cape | LAPHUMILANGA JUNIOR SECONDARY SCHOOL | 200300208 | Mbhashe | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206094 | P9008717 | Eastern Cape | LOWER GQAGA PRIMARY SCHOOL | 200400374 | Engcobo | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206095 | P9008718 | Eastern Cape | MAJALI TECHNICAL SENIOR SECONDARY SCHOOL | 200400457 | Port St Johns | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206096 | P9008719 | Eastern Cape | MGCOTYELWA JUNIOR PRIMARY SCHOOL | 200400583 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206097 | P9008720 | Eastern Cape | MJOBENI JUNIOR SECONDARY SCHOOL | 200400605 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206098 | P9008722 | Eastern Cape | MKAMELA JUNIOR SECONDARY SCHOOL | 200500690 | Ingquza Hill | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206099 | P9008724 | Eastern Cape | NQEKETO JUNIOR SECONDARY SCHOOL | 200400843 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206100 | P9008725 | Eastern Cape | NTSINTSANA JUNIOR SECONDARY SCHOOL | 200500982 | Ntabankulu | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206101 | P9008726 | Eastern Cape | PAKAMANI JUNIOR SECONDARY SCHOOL | 200501004 | Ingquza Hill | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206102 | P9008727 | Eastern Cape | QOKOLWENI SENIOR SECONDARY SCHOOL | 200401252 | King Sabata Dalindyebo | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206103 | P9008728 | Eastern Cape | ROXENI PRIMARY SCHOOL | 200200735 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206104 | P9008730 | Eastern Cape | WABAN SENIOR SECONDARY SCHOOL | 200401139 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206105 | P9007694 | Eastern Cape | OPERATIONS & MAINTENANCE (Ah Hoc) | 200999925 | Buffalo City | Pre - Feasibility | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 52010000 | 52010000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206106 | P9009853 | Eastern Cape | ECD MAINTENANCE PROGRAMME | 200999925 | Buffalo City | Pre - Feasibility | Active - Contracted | 2023-03-31 |  | 2026-03-31 |  |  | 0 | 14292000 | 14292000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 206107 | P9009917 | Eastern Cape | TEMBELANI HIGH SCHOOL | 200200831 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1938366 | 1938366 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206108 | P0004443 | Eastern Cape | EMMANGWENI PRIMARY SCHOOL | 200200158 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1778711 | 1778711 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206109 | P0004438 | Eastern Cape | NONKQUBELA SENIOR SECONDARY SCHOOL | 200500939 | Mbizana | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206110 | P0004426 | Eastern Cape | DABULINGWE SENIOR PRIMARY SCHOOL | 200400098 | Engcobo | Project Initiation | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1553079 | 1553079 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206111 | P9007253_ | Eastern Cape | kwaNOBUHLE SENIOR SECONDARY SCHOOL | 200401300 | King Sabata Dalindyebo | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1426726 | 1426726 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206112 | P0002692 | Eastern Cape | NGCUNGENI JUNIOR SECONDARY SCHOOL | 200500877 | Ingquza Hill | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1399936 | 1399936 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206113 | P0004425 | Eastern Cape | NGELE PRIMARY SCHOOL | 200200562 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1279213 | 1279213 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206114 | P9006972_ | Eastern Cape | GCOBANI INTERMEDIATE PRIMARY SCHOOL | 200200199 | Buffalo City | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1212088 | 1212088 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206115 | P9011613 | Eastern Cape | NONTANGANA SENIOR PRIMARY SCHOOL | 200401357 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1093856 | 1093856 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206116 | P9010388 | Eastern Cape | WAYO JUNIOR SECONDARY SCHOOL | 200501292 | Ntabankulu | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 1006309 | 1006309 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206117 | P9007246_ | Eastern Cape | HH MAJIZA SENIOR SECONDARY SCHOOL | 200200233 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 990994 | 990994 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206118 | P0004444 | Eastern Cape | LENYE PRIMARY SCHOOL | 200200357 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 844201 | 844201 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206119 | P0002708 | Eastern Cape | PONDOLWENDLOVU COMM SECONDARY S SCHOOL | 200400918 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 744305 | 744305 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206120 | P0004445 | Eastern Cape | NONZWAKAZI JUNIOR PRIMARY SCHOOL | 200600620 | Enoch Mgijima | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 734329 | 734329 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206121 | P0004424 | Eastern Cape | ELETHU PRIMARY SCHOOL | 200200147 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 630772 | 630772 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206122 | P0004434 | Eastern Cape | QULUQU PRIMARY SCHOOL | 200400955 | Engcobo | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 584932 | 584932 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206123 | P0004421 | Eastern Cape | NYWARA PRIMARY SCHOOL | 200400900 | Mhlontlo | Pre - Feasibility | Active - Not Contracted | 2021-12-02 |  | 2026-03-31 |  |  | 0 | 294014 | 294014 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206124 | P9013380 | Eastern Cape | EMANGQUZU JUNIOR SECONDARY SCHOOL | 200500176 | Ingquza Hill | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 225169 | 225169 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206125 | P0004436 | Eastern Cape | JONGULWANDLE JUNIOR SECONDARY SCHOOL | 200400306 | Intsika Yethu | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 211230 | 211230 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206126 | P9007019 | Eastern Cape | NOTHONTO PRIMARY SCHOOL | 200100590 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 198268 | 198268 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206127 | P0004442 | Eastern Cape | TINIS PRIMARY SCHOOL | 200100789 | Raymond Mhlaba | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 170206 | 170206 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206128 | P9006502 | Eastern Cape | RUZE JUNIOR SECONDARY SCHOOL | 200400972 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 103450 | 103450 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206129 | P0004255 | Eastern Cape | COZA JUNIOR SECONDARY SCHOOL | 200400090 | Nyandeni | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 53069 | 53069 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206130 | P9011622 | Eastern Cape | HAMBURG PRIMARY SCHOOL - Sanitation | 200200235 | Ngqushwa | Pre - Feasibility | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1002986 | 1002986 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206134 | P9007293_ | Eastern Cape | IKWEZI LOKUSA SPECIAL SCHOOL - Water | 200400275 | King Sabata Dalindyebo | Construction 76% - 99% | Active - Contracted | 2016-06-01 | 2016-08-01 | 2026-03-31 | 2024-03-31 | 2024-03-31 | 0 | 2924190 | 2924190 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206135 | P9011569 | Eastern Cape | LUGWIJINI JUNIOR SECONDARY SCHOOL | 200500456 | Mbizana | Construction 1% - 25% | Active - Contracted | 2018-04-01 | 2018-06-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206136 | P9005467 | Eastern Cape | BETHEL JUNIOR SECONDARY SCHOOL | 200500029 | Mbhashe | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 600348 | 600348 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206137 | P0004062 | Eastern Cape | BISANA JUNIOR SECONDARY SCHOOL | 200500036 | Ingquza Hill | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206138 | P9005506 | Eastern Cape | BOTSABELO JUNIOR SECONDARY SCHOOL | 200400049 | Elundini | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206139 | P9005886 | Eastern Cape | BURU JUNIOR SECONDARY SCHOOL | 200300721 | Mnquma | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206141 | P9010442 | Eastern Cape | EMDIKISWENI JUNIOR SECONDARY SCHOOL | 200500189 | Mbizana | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206142 | P9008415 | Eastern Cape | EMNCOTSHO PRIMARY SCHOOL | 200200160 | Buffalo City | Tender | Active - Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206143 | P9007153_ | Eastern Cape | EMTAMVUNA JUNIOR SECONDARY SCHOOL | 200500196 | Mbizana | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 93714 | 93714 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206144 | P9005476 | Eastern Cape | ENTSIMEKWENI JUNIOR SECONDARY SCHOOL | 200600181 | Senqu | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206145 | P0003814 | Eastern Cape | ENYANISWENI JUNIOR SECONDARY SCHOOL | 200600182 | Enoch Mgijima | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441319 | 441319 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206146 | P9008418 | Eastern Cape | ESIKWAYINI JUNIOR SECONDARY SCHOOL | 200400172 | Mhlontlo | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 443349 | 443349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206148 | P9006943_ | Eastern Cape | DIMBAZA CENTRAL SECONDARY SCHOOL | 200200121 | Buffalo City | Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 7664818 | 7664818 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206162 | P0003787 | Eastern Cape | FORT BOWKER JUNIOR PRIMARY SCHOOL | 200300097 | Mbhashe | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206170 | P9006501 | Eastern Cape | ALIWAL NORTH HIGH SCHOOL | 200600012 | Walter Sisulu | Pre - Feasibility | Active - Not Contracted | 2021-12-01 |  | 2024-03-31 |  |  | 0 | 4200000 | 4200000 | Education Infrastructure Grant | Upgrading and Additions
|  | 206173 | P0004277 | Eastern Cape | DETYANA JUNIOR SECONDARY SCHOOL | 200400118 | Mhlontlo | Design | Active - Not Contracted | 2021-12-01 |  | 2024-03-31 |  |  | 0 | 688741 | 688741 | Education Infrastructure Grant | Upgrading and Additions
|  | 206174 | P9013379 | Eastern Cape | SINAKHO HIGH SCHOOL | 200500308 | Umzimvubu | Design | Active - Not Contracted | 2021-12-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206175 | P9010973 | Eastern Cape | DUMEZWENI SENIOR SECONDARY SCHOOL | 200500144 | Ntabankulu | Design | Active - Not Contracted | 2020-10-20 |  | 2026-03-21 |  |  | 222992 | 3457848 | 3680840 | Education Infrastructure Grant | Upgrading and Additions
|  | 206176 | P9010993 | Eastern Cape | MOSA SIBI SENIOR SECONDARY SCHOOL | 200500741 | Matatiele | Design | Active - Not Contracted | 2020-10-20 |  | 2026-03-31 |  |  | 210092 | 3367672 | 3577764 | Education Infrastructure Grant | Upgrading and Additions
|  | 206177 | P9011594 | Eastern Cape | UPPER TYIRA JUNIOR SECONDARY SCHOOL | 200401110 | Mhlontlo | Design | Active - Not Contracted | 2020-02-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Upgrading and Additions
|  | 206178 | P9013419 | Eastern Cape | ALEXANDRIA HIGH SCHOOL | 200100024 | Nelson Mandela Bay | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206179 | P9013422 | Eastern Cape | ALEXANDRIA PRIMARY SCHOOL | 200100023 | Ndlambe | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206181 | P9007188 | Eastern Cape | ALICE PRIMARY SCHOOL | 200200006 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206182 | P9006843 | Eastern Cape | AMASANGO SPECIAL SCHOOL - New site | 200101027 | Makana | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206183 | P9007086_ | Eastern Cape | ARTHUR MFEBE SENIOR SECONDARY SCHOOL | 200601046 | Intsika Yethu | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206184 | P9013389 | Eastern Cape | AYLIFF PRIMARY SCHOOL | 200200027 | Ngqushwa | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206186 | P9006511 | Eastern Cape | BATHANDWA NDONDO SENIOR SECONDARY SCHOOL | 200600452 | Sakhisizwe | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206187 | P9013225 | Eastern Cape | BELE PRIMARY SCHOOL | 200400033 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206188 | P9013369 | Eastern Cape | BONXA HIGH SCHOOL | 200500094 | Ntabankulu | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206189 | P9013360 | Eastern Cape | BUTTERWORTH HIGH SCHOOL | 200300741 | Mnquma | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206190 | P9013402 | Eastern Cape | CAGUBA SENIOR SECONDARY SCHOOL | 200400066 | Port St Johns | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206191 | P9007113 | Eastern Cape | CALA COMMUNITY SCHOOL | 200600083 | Sakhisizwe | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206193 | P9013267 | Eastern Cape | CAMERON NGUDLE SENIOR SECONDARY SCHOOL | 200400067 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206194 | P9010380 | Eastern Cape | DALIWONGA SENIOR SECONDARY SCHOOL | 200601092 | Intsika Yethu | Tender | Approved | 2022-01-04 |  | 2025-01-04 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206195 | P9007178 | Eastern Cape | CENYU PUBLIC SCHOOL | 200200082 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206198 | P9009697_ | Eastern Cape | CLARKEBURY AGRICULTURAL SCHOOL | 200400084 | Engcobo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206199 | P9013371 | Eastern Cape | ZWELITSHA SENIOR SECONDARY SCHOOL | 200501381 | Ntabankulu | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206201 | P9006532 | Eastern Cape | COFFEEBAY JUNIOR SECONDARY SCHOOL | 200400087 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206203 | P9013384 | Eastern Cape | D G COSSIE PUBLIC PRIMARY SCHOOL | 200600122 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206204 | P9013390 | Eastern Cape | ZWELEMFUNDO PUBLIC SCHOOL | 200200991 | Buffalo City | Tender | Approved | 2022-04-01 |  | 2026-01-04 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206205 | P9007023 | Eastern Cape | D M SKOSANA SENIOR SECONDARY SCHOOL | 200600123 | Sakhisizwe | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206207 | P0003883 | Eastern Cape | DEBE PRIMARY SCHOOL | 200200114 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206208 | P9013425 | Eastern Cape | DIKISHE JUNIOR SECONDARY SCHOOL | 200400123 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206210 | P9013398 | Eastern Cape | DILIZA JUNIOR SECONDARY SCHOOL | 200500127 | Ingquza Hill | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206212 | P9013434 | Eastern Cape | DIMBAZA CENTRAL SECONDARY SCHOOL | 200200121 | Buffalo City | Design | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206213 | P9013268 | Eastern Cape | DUMSI SECONDARY SCHOOL | 200500150 | Mbizana | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206215 | P9013227 | Eastern Cape | EDWARD ZIBI SENIOR SECONDARY SCHOOL | 200501208 | Elundini | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206217 | P9007193 | Eastern Cape | EMFUNDWENI SENIOR SECONDARY SCHOOL | 200200156 | Ngqushwa | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206218 | P9006043 | Eastern Cape | ZWELAKHE SENIOR SECONDARY SCHOOL | 200501338 | Ntabankulu | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206219 | P9006524 | Eastern Cape | EMIZAMOYETHU SENIOR SECONDARY SCHOOL | 200400159 | Engcobo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206221 | P9013392 | Eastern Cape | ENGCOBO VILLAGE SENIOR SECONDARY SCHOOL | 200400167 | Engcobo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206222 | P9013395 | Eastern Cape | ENKWENKWEZINI SECONDARY SCHOOL | 200200164 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206223 | P9013413 | Eastern Cape | ZIZAMELE PRIMARY SCHOOL | 200501332 | Mhlontlo | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206225 | P9013424 | Eastern Cape | ESETHU PRIMARY SCHOOL | 200400181 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206227 | P9013374 | Eastern Cape | ZINYOSINI SENIOR SECONDARY SCHOOL | 200501331 | Ntabankulu | Tender | Approved | 2022-01-04 |  | 2026-01-04 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206229 | P9013396 | Eastern Cape | XHENTSE SENIOR SECONDARY SCHOOL | 200401148 | Nyandeni | Tender | Approved | 2022-01-04 |  | 2026-01-04 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206230 | P9009899 | Eastern Cape | WINTERBERG AGRICULTURAL HIGH SCHOOL | 200100862 | Raymond Mhlaba | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206231 | P9013275 | Eastern Cape | ET THABANE PRIMARY SCHOOL | 200400273 | Elundini | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206235 | P9009861_ | Eastern Cape | FEZEKA PRIMARY SCHOOL | 200200177 | Ngqushwa | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206236 | P9013388 | Eastern Cape | GERMAN VILLAGE JUNIOR SECONDARY SCHOOL | 200200205 | Ngqushwa | Tender | Active - Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206237 | P9013370 | Eastern Cape | GILLESPIE PRIMARY SCHOOL | 200500254 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206239 | P9013381_ | Eastern Cape | GQUMAHASHE JUNIOR PRIMARY SCHOOL | 200200217 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206241 | P9013211 | Eastern Cape | GUNGULULU PRIMARY SCHOOL | 200400242 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206243 | P9013409 | Eastern Cape | GUNYENI SENIOR PRIMARY SCHOOL | 200500279 | Ingquza Hill | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206244 | P9007120 | Eastern Cape | HAMBURG PRIMARY SCHOOL | 200200235 | Ngqushwa | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206252 | P0003900 | Eastern Cape | GINGA`S JUNIOR SECONDARY SCHOOL | 200500255 | Ingquza Hill | Tender | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206253 | P9007199_ | Eastern Cape | GOXE PRIMARY SCHOOL | 200500266 | Mbizana | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206254 | P0003905 | Eastern Cape | HH MAJIZA SENIOR SECONDARY SCHOOL | 200200233 | Amahlathi | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206255 | P9004963 | Eastern Cape | HILLSIDE JUNIOR SECONDARY SCHOOL | 200500294 | Ingquza Hill | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206256 | P0004354 | Eastern Cape | IMIDUSHANE SENIOR SECONDARY SCHOOL | 200200267 | Ngqushwa | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206257 | P9004878 | Eastern Cape | IMIQHAYI SENIOR SECONDARY SCHOOL | 200200270 | Buffalo City | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206258 | P9007050_ | Eastern Cape | JALI PRIMARY SCHOOL | 200500330 | Mbizana | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206259 | P9003246 | Eastern Cape | JOZANA`S HOEK JUNIOR SECONDARY SCHOOL | 200600312 | Senqu | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206260 | P9007099_ | Eastern Cape | KANYAYO JUNIOR SECONDARY SCHOOL | 200500346 | Mbizana | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206261 | P9007024_ | Eastern Cape | KHALENI PRIMARY SCHOOL | 200500354 | Mbizana | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206262 | P0003779 | Eastern Cape | KOLELE JUNIOR PRIMARY SCHOOL | 200200324 | Buffalo City | Pre - Feasibility | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 441349 | 441349 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206263 | P9013266 | Eastern Cape | HOERSKOOL BARKLY EAST | 200600266 | Senqu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206264 | P9013420 | Eastern Cape | IKAMVA LESIZWE PUBLIC SCHOOL | 200100375 | Ndlambe | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206266 | P9013207 | Eastern Cape | JAMANGILE SENIOR SECONDARY SCHOOL | 200400282 | Elundini | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206267 | P9013431 | Eastern Cape | JONGIMISHINI SENIOR PRIMARY SCHOOL | 200300170 | Intsika Yethu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206268 | P9013406 | Eastern Cape | JONGIMPUMA JUNIOR PRIMARY SCHOOL | 200400295 | Port St Johns | Tender | Active - Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206270 | P9007015_ | Eastern Cape | JONGINTABA SENIOR SECONDARY SCHOOL | 200400300 | Mhlontlo | Design | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206271 | P9013198 | Eastern Cape | JUMBA SENIOR SECONDARY SCHOOL | 200401269 | King Sabata Dalindyebo | Design | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206272 | P9013416 | Eastern Cape | K T MCHASA SENIOR SECONDARY SCHOOL | 200400310 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206274 | P9006029 | Eastern Cape | KAMBI PRIMARY SCHOOL | 200400315 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206275 | P9013403 | Eastern Cape | KHONJWAYO SENIOR PRIMARY SCHOOL | 200500358 | Ingquza Hill | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206276 | P9013375 | Eastern Cape | KHULANGOPHONDO SENIOR SECONDARY SCHOOL | 200500554 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206277 | P9013383 | Eastern Cape | KUBUSIE COMBINED SCHOOL | 200200328 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206278 | TBA 88 | Western Cape | (A) Nomzamu Technical HS (MEILE1) | TBC | City of Cape Town | Project Initiation | Active - Not Contracted | 2022-02-28 |  | 2027-03-31 |  |  | 15000000 | 66000000 | 81000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 206279 | P9013365 | Eastern Cape | KwaSHUSHU SENIOR SECONDARY SCHOOL | 200500213 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206281 | P9006637 | Eastern Cape | LINDANI SENIOR SECONDARY SCHOOL | 200100455 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206283 | TBA 89 | Western Cape | (B) Nomzamu PS no 2 (MEILE1) | TBC | City of Cape Town | Project Initiation | Active - Not Contracted | 2022-02-28 |  | 2029-03-30 |  |  | 8000000 | 33000000 | 41000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 206284 | P9013399 | Eastern Cape | LINDUBUHLE JUNIOR SECONDARY SCHOOL | 200400360 | Port St Johns | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206285 | TBA 98 | Western Cape | (C) Nomzamu PS no 1 (MEILE1) | TBC | City of Cape Town | Project Initiation | Active - Not Contracted | 2022-02-28 |  | 2027-03-31 |  |  | 14000000 | 62000000 | 76000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 206286 | P9008660 | Eastern Cape | LOWER BUFUMBA SENIOR PRIMARY SCHOOL | 200400369 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206287 | P9006050 | Eastern Cape | LUBALASI JSS (DISTRICT OFFICE) | 200500440 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206289 | TBA 92 | Western Cape | (D) Nomzamu Pre-PS (MEILE1) | TBC | City of Cape Town | Design | Active - Not Contracted | 2022-02-28 |  | 2024-03-29 |  |  | 7000000 | 26000000 | 33000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 206290 | P9007254_ | Eastern Cape | ULANA AGRICULTURAL SCHOOL | 200200871 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206291 | P9006012 | Eastern Cape | LUGXOGXO JUNIOR SECONDARY SCHOOL | 200400399 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206292 | P9006013 | Eastern Cape | LUKHANYO PRIMARY SCHOOL | 200501405 | Mbizana | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206294 | P9007245 | Eastern Cape | LUKHOZI HIGH SCHOOL | 200200377 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206295 | P9005919 | Eastern Cape | UGIE HIGH SCHOOL | 200401085 | Elundini | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206298 | P9013397 | Eastern Cape | TUTOR NDAMASE SENIOR SECONDARY SCHOOL | 200401076 | Nyandeni | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206303 | P9010005_ | Eastern Cape | LUMKWANA JUNIOR PRIMARY SCHOOL | 200400404 | Mbhashe | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206304 | P9013415 | Eastern Cape | TOLWENI PRIMARY SCHOOL | 200501218 | Mhlontlo | Tender | Approved | 2022-01-04 |  | 2026-01-04 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206307 | P9013401 | Eastern Cape | LUNGISANI SENIOR PRIMARY SCHOOL | 200400408 | Senqu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206308 | P9007026_ | Eastern Cape | THOBELANI SENIOR SECONDARY SCHOOL | 200200843 | Raymond Mhlaba | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206309 | P9013367 | Eastern Cape | LUTATENI SENIOR SECONDARY SCHOOL | 200500479 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206311 | P9013405 | Eastern Cape | LUTSHAYA SENIOR SECONDARY SCHOOL | 200500482 | Port St Johns | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206312 | P9006038 | Eastern Cape | TEMPLETON HIGH SCHOOL | 200100771 | Raymond Mhlaba | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206314 | P9013400 | Eastern Cape | MAGOMBENI SENIOR PRIMARY SCHOOL | 200400451 | Port St Johns | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206315 | P9006500 | Eastern Cape | MASIBAMBISANE COMBINED PRIMARY SCHOOL | 200200423 | Ngqushwa | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206321 | P9006041 | Eastern Cape | MASIHLANGANE SECONDARY SCHOOL | 200201011 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206322 | P9006001 | Eastern Cape | MATATIELE PUBLIC PRIMARY SCHOOL | 200501582 | Matatiele | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206323 | P9006999_ | Eastern Cape | ST MATTHEWS PRIMARY SCHOOL | 200200817 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206324 | P9013366 | Eastern Cape | MBODLENI SENIOR SECONDARY SCHOOL | 200500383 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206325 | P9006051 | Eastern Cape | MBONGWENI SENIOR SECONDARY SCHOOL | 200400540 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206326 | P9007142 | Eastern Cape | ST MATTHEWS HIGH SCHOOL | 200200816 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206328 | P9013376 | Eastern Cape | ST MARKS TECHNICAL SENIOR SECONDARY SCHOOL | 200500726 | Umzimvubu | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206329 | P9006357 | Eastern Cape | MBUQE JUNIOR SECONDARY SCHOOL | 200400547 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206330 | P9013382 | Eastern Cape | SONWABILE PRIMARY SCHOOL | 200200805 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206331 | P9006015 | Eastern Cape | MCHENI JUNIOR PRIMARY SCHOOL | 200400551 | Mhlontlo | Tender | Active - Not Contracted | 2021-10-01 |  | 2024-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206332 | P9007130_ | Eastern Cape | MENDWANA JUNIOR PRIMARY SCHOOL | 200300318 | Mbhashe | Tender | Active - Not Contracted | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206333 | P9007006_ | Eastern Cape | SIZINGISILE SENIOR SECONDARY SCHOOL | 200200970 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206334 | P9009856 | Eastern Cape | SIYAKHULA FINISHING SCHOOL | 200200791 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206336 | P9005213 | Eastern Cape | SILANGWE PRIMARY SCHOOL | 200501108 | Mbizana | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206337 | P9013428 | Eastern Cape | SITOROMO JUNIOR SECONDARY SCHOOL | 200600754 | Senqu | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206338 | P9007078_ | Eastern Cape | SIKITINI PRIMARY SCHOOL | 200500243 | Ingquza Hill | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206339 | P9013385 | Eastern Cape | SIKHULULE PUBLIC SCHOOL | 200200764 | Amahlathi | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206340 | P9007182 | Eastern Cape | MENZIWA SENIOR SECONDARY SCHOOL | 200400576 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206341 | P9013418 | Eastern Cape | SANDISULWAZI HIGH SCHOOL | 200100680 | Sundays River Valley | Tender | Active - Contracted | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206342 | P9013377 | Eastern Cape | SAHLULO PRIMARY SCHOOL | 200100680 | Port St Johns | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206344 | P9006244 | Eastern Cape | MGUDLWA SENIOR SECONDARY SCHOOL | 200400584 | Engcobo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206345 | P9008482 | Eastern Cape | GWEBINKUMBI JUNIOR SECONDARY SCHOOL | 200500283 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206346 | P0003888 | Eastern Cape | MGWEBI JUNIOR SECONDARY SCHOOL | 200300330 | Mnquma | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206347 | P9010452 | Eastern Cape | KU-BHA PRIMARY SCHOOL | 200500368 | Mbizana | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206348 | P9007037 | Eastern Cape | MHLOBO JUNIOR SECONDARY SCHOOL | 200601052 | Intsika Yethu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206349 | P9007243 | Eastern Cape | MIDDLEDRIFT CMC | 200999925 | Raymond Mhlaba | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206350 | P9007175 | Eastern Cape | MLUNGISI PUBLIC SCHOOL | 200200486 | Amahlathi | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206351 | P0004238_ | Eastern Cape | KUBUSIE JUNIOR SECONDARY SCHOOL | 200400335 | Mhlontlo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206352 | P0002826 | Eastern Cape | KUHLE JUNIOR SECONDARY SCHOOL | 200200329 | Amahlathi | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206353 | P9010986_ | Eastern Cape | kwaNDELA PRIMARY SCHOOL | 200500380 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206354 | P9013427 | Eastern Cape | MNTLA PRIMARY SCHOOL | 200300356 | Mnquma | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206355 | P9007229_ | Eastern Cape | KWEZI JUNIOR SECONDARY SCHOOL | 200400346 | Mnquma | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206356 | P9006030 | Eastern Cape | MNUKWA SENIOR SECONDARY SCHOOL | 200500725 | Matatiele | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206357 | P9006016 | Eastern Cape | MOOROSI AGRICULTURAL SCHOOL | 200501015 | Matatiele | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206358 | P9003508 | Eastern Cape | LUMKWANA JUNIOR PRIMARY SCHOOL | 200400404 | Engcobo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206359 | P9009589 | Eastern Cape | LUNDINI PRIMARY SCHOOL | 200501380 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206360 | P9006031 | Eastern Cape | MOSA SIBI SENIOR SECONDARY SCHOOL | 200500741 | Matatiele | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206361 | P9006017 | Eastern Cape | MOUNT AYLIFF SENIOR SECONDARY SCHOOL | 200500784 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206362 | P9006826 | Eastern Cape | LUPINDO SENIOR SECONDARY SCHOOL | 200500470 | Matatiele | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206364 | P0004272 | Eastern Cape | MABELE JUNIOR SECONDARY SCHOOL | 200601013 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206365 | P9004959 | Eastern Cape | MAHLUBINI JUNIOR SECONDARY SCHOOL | 200600419 | Intsika Yethu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206366 | P9005908 | Eastern Cape | MANGANYELA JUNIOR SECONDARY SCHOOL | 200400480 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206367 | P9005816 | Eastern Cape | MASIBAMBISANE COMBINED PRIMARY SCHOOL | 200200423 | Ngqushwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206368 | P0003809 | Eastern Cape | MASIHLANGANE SECONDARY SCHOOL | 200201011 | Amahlathi | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Upgrading and Additions
|  | 206370 | P9007176_ | Eastern Cape | MATYEBA PRIMARY SCHOOL | 200400513 | Mhlontlo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206371 | P9013373 | Eastern Cape | MOUNT AYLIFF SENIOR SECONDARY SCHOOL | 200500784 | Umzimvubu | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206372 | P9007049_ | Eastern Cape | MBUNGWA PRIMARY SCHOOL | 200500631 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206373 | P0002101 | Eastern Cape | MFAMZI JUNIOR SECONDARY SCHOOL | 200300321 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206374 | P9011550 | Eastern Cape | MHLAKULO PRIMARY SCHOOL | 200400593 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206375 | P9007022 | Eastern Cape | MPEKO PRIMARY SCHOOL | 200400641 | King Sabata Dalindyebo | Tender | Active - Not Contracted | 2021-10-01 |  | 2026-03-31 |  |  | 0 | 848692 | 848692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206376 | P9011738 | Eastern Cape | MIDDLE TYIRA JUNIOR SECONDARY SCHOOL | 200400599 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206377 | P0003833 | Eastern Cape | MKUNYAZO SENIOR PRIMARY SCHOOL | 200600494 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206378 | P9013430 | Eastern Cape | RHODES JUNIOR SECONDARY SCHOOL | 200600709 | Senqu | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206379 | P9006018 | Eastern Cape | MPINDWENI SENIOR SECONDARY SCHOOL | 200401306 | King Sabata Dalindyebo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206380 | P9005092 | Eastern Cape | MONTGOMERY STATE AIDED SCHOOL | 200400629 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206381 | P9005911 | Eastern Cape | MPAKAMA JUNIOR SECONDARY SCHOOL | 200400635 | Mbhashe | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206382 | P0003491 | Eastern Cape | MPEKO PRIMARY SCHOOL | 200200641 | King Sabata Dalindyebo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206383 | P9009878 | Eastern Cape | MZOMHLE SENIOR SECONDARY SCHOOL | 200200528 | Buffalo City | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206384 | P0003046 | Eastern Cape | MZOMTSHA HIGH SCHOOL | 200200530 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206385 | P9004572 | Eastern Cape | NDAKANA PRIMARY SCHOOL | 200200549 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206386 | P9005922 | Eastern Cape | NDUNGUNYA JUNIOR SECONDARY SCHOOL | 200600559 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206387 | P9005013 | Eastern Cape | NGOBOZANA JUNIOR SECONDARY SCHOOL | 200500881 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206390 | P9009810_ | Eastern Cape | NGUBESIZWE PRIMARY SCHOOL | 200400771 | Mhlontlo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206392 | P9005840 | Eastern Cape | NOBANDLA SENIOR PRIMARY SCHOOL | 200600591 | Emalahleni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206393 | P9005861 | Eastern Cape | NONTSWABU PRIMARY JUNIOR SCHOOL | 200400826 | Nyandeni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206394 | P0003055 | Eastern Cape | NTSONKOTHA SENIOR SECONDARY SCHOOL | 200600642 | Emalahleni | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206395 | P9007090_ | Eastern Cape | PROSPECT PRIMARY SCHOOL | 200501034 | Matatiele | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206396 | P0003892 | Eastern Cape | QHOBOSHANE JUNIOR SECONDARY SCHOOL | 200600687 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206397 | TBC 102 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2022-02-28 |  | 2025-03-31 |  |  | 18000000 | 82000000 | 100000000 | Equitable Share | Upgrading and Additions
|  | 206400 | P0003136 | Eastern Cape | RED HILL JUNIOR SECONDARY SCHOOL | 200501062 | Ingquza Hill | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206401 | P9008427_ | Eastern Cape | SITOROMO JUNIOR SECONDARY SCHOOL | 200600754 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206402 | P9008432_ | Eastern Cape | SIYABULELA PRIMARY SCHOOL | 200500193 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206403 | TBC 031 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2022-02-28 |  | 2025-03-31 |  |  | 18000000 | 82000000 | 100000000 | Equitable Share | Upgrading and Additions
|  | 206405 | P9005503 | Eastern Cape | TAUKA JUNIOR SECONDARY SCHOOL | 200501181 | Ingquza Hill | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206406 | P9005583 | Eastern Cape | TEMBELITSHA JUNIOR SECONDARY SCHOOL | 200501184 | Matatiele | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206407 | P9003223 | Eastern Cape | THOBILE DYANTYI JUNIOR SECONDARY SCHOOL | 200600793 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206408 | P0003948 | Eastern Cape | TWAZI JUNIOR SECONDARY SCHOOL | 200501243 | Ingquza Hill | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206409 | P9005796 | Eastern Cape | UPPER NCUNCUZO JUNIOR SECONDARY SCHOOL | 200600876 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206410 | P9005833 | Eastern Cape | UPPER QUTSA JUNIOR SECONDARY SCHOOL | 200300639 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206412 | P9010682 | Eastern Cape | XOLOBENI JUNIOR SECONDARY SCHOOL | 200501296 | Mbizana | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206413 | P9008424_ | Eastern Cape | XUMABOKWE JUNIOR SECONDARY SCHOOL | 200600930 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206414 | P9008428 | Eastern Cape | ZABALAZA JUNIOR PRIMARY SCHOOL | 200200914 | Buffalo City | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206415 | P0003418 | Eastern Cape | ZIMISELE JUNIOR SECONDARY SCHOOL | 200501327 | Ingquza Hill | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206416 | P9006913_ | Eastern Cape | ZWELIHLANGENE JUNIOR SECONDARY SCHOOL | 200600959 | Intsika Yethu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 183766 | 183766 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206421 | P9013411 | Eastern Cape | QOKOLWENI SENIOR SECONDARY SCHOOL | 200401252 | King Sabata Dalindyebo | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206423 | P9006032 | Eastern Cape | MPONDOMBINI SECONDARY SCHOOL | 200500764 | Mbizana | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206424 | P9013372 | Eastern Cape | MSUKENI PRIMARY SCHOOL | 200500780 | Ntabankulu | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206425 | P9013423 | Eastern Cape | PORT ALFRED JUNIOR SECONDARY SCHOOL | 200100633 | Ndlambe | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206426 | P9006005 | Eastern Cape | MTENGWANE SENIOR SECONDARY SCHOOL | 200400671 | Mhlontlo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206427 | P9007036 | Eastern Cape | Peddie CMC (DISTRICT OFFICE) | 200999925 | Ngqushwa | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206428 | P9013432 | Eastern Cape | OVERTON PRIMARY SCHOOL | 200200673 | Buffalo City | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206429 | P9013393 | Eastern Cape | MTIRARA SENIOR SECONDARY SCHOOL | 200600528 | Emalahleni | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206430 | P9013414 | Eastern Cape | MTONDELA SENIOR PRIMARY SCHOOL | 200400678 | Mhlontlo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206431 | P9006007 | Eastern Cape | NTLAZA JUNIOR SECONDARY SCHOOL | 200400864 | Nyandeni | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206432 | P9013429 | Eastern Cape | MYOLWA PRIMARY SCHOOL | 200404035 | Port St Johns | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206433 | P9013412 | Eastern Cape | NQWILISO SENIOR SECONDARY SCHOOL | 200400847 | Mhlontlo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206434 | P9006044 | Eastern Cape | MZAMO SENIOR PRIMARY SCHOOL | 200500826 | Umzimvubu | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206435 | P9013386 | Eastern Cape | MZAMOMHLE PRIMARY SCHOOL | 200200385 | Raymond Mhlaba | Design | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206436 | P9013362 | Eastern Cape | NQABARA SENIOR SECONDARY SCHOOL | 200300503 | Mbhashe | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206437 | P9013387 | Eastern Cape | NATHANIEL PAMLA HIGH SCHOOL | 200200539 | Ngqushwa | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206438 | P9006035 | Eastern Cape | NDABANKULU SENIOR SECONDARY SCHOOL | 200300420 | Mnquma | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206440 | P9013363 | Eastern Cape | NQABANE SENIOR SECONDARY SCHOOL | 200300499 | Mbhashe | Tender | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206441 | P9013394 | Eastern Cape | NEWTOWN HIGH SCHOOL | 200100051 | Raymond Mhlaba | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206442 | P9006037 | Eastern Cape | NONKQUBELA SENIOR SECONDARY SCHOOL | 200600614 | Emalahleni | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206443 | P9013410 | Eastern Cape | NGCUNGENI JUNIOR SECONDARY SCHOOL | 200500877 | Emalahleni | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206444 | P9006006 | Eastern Cape | NGQELENI SENIOR SECONDARY SCHOOL | 200400756 | Nyandeni | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206445 | P9006036 | Eastern Cape | NGUBESIZWE SENIOR SECONDARY SCHOOL | 200300444 | Mbhashe | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206446 | P9005762 | Eastern Cape | NGXAMNGXA PUBLIC SCHOOL | 200200578 | Amahlathi | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206447 | P9013407 | Eastern Cape | NOGEMANE SENIOR SECONDARY SCHOOL | 200401238 | Nyandeni | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206449 | P9006024 | Eastern Cape | NONGEKE SECONDARY SCHOOL | 200500935 | Mbizana | Design | Approved | 2022-01-04 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206450 | P9013361 | Eastern Cape | NOMAKA MBEKI TECHNICAL SENIOR SECONDARY SCHOOL | 200300433 | Mbhashe | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206451 | P9005752_ | Eastern Cape | SINOLWAZI SENIOR SECONDARY SCHOOL | 200400005 | King Sabata Dalindyebo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 6700 | 6700 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206452 | P9005337_ | Eastern Cape | kwaNTOZONKE SENIOR SECONDARY SCHOOL | 200300198 | Mnquma | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 6000 | 6000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206453 | P9004943_ | Eastern Cape | BAVUMA JUNIOR SECONDARY SCHOOL | 200400020 | Mhlontlo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 4500 | 4500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206454 | P9005331_ | Eastern Cape | EZINGQAYI SENIOR SECONDARY SCHOOL | 200300744 | Mnquma | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 3867 | 3867 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206455 | P9004939_ | Eastern Cape | SAKAKUDE JUNIOR SECONDARY SCHOOL | 200600725 | Senqu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 3500 | 3500 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206456 | P0003606_ | Eastern Cape | VUYOLWETHU PRIMARY SCHOOL | 200200892 | Ngqushwa | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 1195 | 1195 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206457 | P9005330_ | Eastern Cape | AMABHELE HIGH SCHOOL | 200200010 | Raymond Mhlaba | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 1000 | 1000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206458 | P0003583 | Eastern Cape | NONKULULEKO SENIOR SECONDARY SCHOOL | 200600615 | Enoch Mgijima | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 618 | 618 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206461 | P0003608_ | Eastern Cape | XEZI SENIOR PRIMARY SCHOOL | 200401147 | Port St Johns | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10723 | 10723 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206462 | P9008614_ | Eastern Cape | MACOSA PRIMARY SCHOOL | 200400436 | King Sabata Dalindyebo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 10000 | 10000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206463 | P9010501 | Eastern Cape | MVUZO JUNIOR SECONDARY SCHOOL | 200600535 | Intsika Yethu | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10000 | 10000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206464 | P9008603_ | Eastern Cape | NONCEDO JUNIOR PRIMARY SCHOOL | 200200618 | Buffalo City | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 10000 | 10000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206465 | P9008741 | Eastern Cape | TYELINZIMA JUNIOR SECONDARY SCHOOL | 200401081 | Engcobo | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10000 | 10000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206466 | P9006220 | Eastern Cape | UGIE HIGH SCHOOL | 200401085 | Elundini | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2026-03-31 |  |  | 0 | 10000 | 10000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206469 | P0001596_ | Eastern Cape | LENKOE JUNIOR PRIMARY SCHOOL | 200500402 | Matatiele | Project Initiation | Active - Not Contracted | 2021-04-01 |  | 2025-03-30 |  |  | 0 | 8900 | 8900 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206481 | P9013180 | Eastern Cape | E N SEKU SECONDARY SCHOOL | 200400144 | King Sabata Dalindyebo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 828692 | 828692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206482 | P9005877 | Eastern Cape | MTHONYAMENI SENIOR PRIMARY SCHOOL | 200400675 | Mhlontlo | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206485 | P9013404 | Eastern Cape | GOBIZIZWE SENIOR PRIMARY SCHOOL | 200400215 | Port St Johns | Tender | Approved | 2022-01-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206486 | P9013408 | Eastern Cape | JONGIKAYA PRIMARY SCHOOL | 200500340 | Mhlontlo | Tender | Approved | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206487 | P9009844 | Eastern Cape | EGQILI SENIOR SECONDARY SCHOOL | 200600160 | Walter Sisulu | Tender | Approved | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 206488 | P9013417 | Eastern Cape | UMTATA COMMUNITY JUNIOR SECONDARY SCHOOL | 200500726 | Umzimvubu | Tender | Approved | 2022-04-01 |  | 2026-03-31 |  |  | 0 | 628692 | 628692 | Education Infrastructure Grant | Upgrading and Additions
|  | 206493 | P9008734 | Eastern Cape | HEALDTOWN COMPREHENSIVE SCHOOL (Phase2) | 200100296 | Raymond Mhlaba | Final Completion | Active - Contracted | 2016-06-01 | 2023-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 0 | 12005802 | 12005802 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206513 | TBA 050 | Western Cape |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2022-04-01 |  | 2027-03-31 |  |  | 3400000 | 13856000 | 17256000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 206517 | BAPO | North West | REKGONNE BAPO SECONDARY SCHOOL | BAPO | Local Municipality of Madibeng | Project Initiation | Approved | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 206629 | DBSA MANAGEMENT FEE | North West | DBSA MANAGEMNT FEE | DBSA MANAGEMENT FEE | Mafikeng | Project Initiation | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 14000000 | 0 | 14000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 206693 | REF 2023 | Free State | REFURBISHMENTS | REF 2023 | Mangaung | Design | Active - Contracted | 2022-03-03 |  | 2025-03-31 |  |  | 0 | 306000000 | 306000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206707 | PART 2023 | Free State | PARTNERSHIPS KAGISHO TRUST | PART 2023 | Mangaung | Feasibility | Approved | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 5000000 | 5000000 | Equitable Share | Upgrading and Additions
|  | 206712 | PART SHA 2023 | Free State | PARTNERSHIPS KAGISHO TRUST SHANDUKA | PART SHA 2023 | Mangaung | Feasibility | Approved | 2022-03-03 |  | 2023-03-31 |  |  | 0 | 14000000 | 14000000 | Equitable Share | Upgrading and Additions
|  | 206727 | ECD 2023 | Free State | PRE GRADE R COMMUNITY CENTRES | ECD 2023 | Mangaung | Design | Approved | 2022-03-03 |  | 2025-03-31 |  |  | 0 | 20000000 | 20000000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 206728 | MAIN 2023 | Free State | Day-to-Day General Maintenance buildings | MAIN 2023 | Mangaung | Construction 1% - 25% | Approved | 2022-03-03 | 2022-06-01 | 2024-03-31 | 2024-03-31 | 2024-03-31 | 0 | 3000000 | 3000000 | Equitable Share | Maintenance and Repairs
|  | 206729 | MAN FEES 2023 | Free State | DBSA MANAGEMENT FEES | MAN FEES 2023 | Mangaung | Not Applicable | Active - Contracted | 2022-03-03 |  | 2025-03-31 |  |  | 60000000 | 0 | 60000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206768 | TBD_ LOUISVALE PRIMARY SCHOOL | Northern Cape | LOUISVALE PRIMARY SCHOOL | 300101101 | Dawid Kruiper | Project Initiation | Proposed | 2022-05-05 |  | 2022-08-08 |  |  | 0 | 2260024 | 2260024 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206772 | TBD_BUCKLANDS (NGK) PRIMARY SCHOOL | Northern Cape | BUCKLANDS PRIMARY SCHOOL | 300011202 | Siyancuma | Project Initiation | Active - Not Contracted | 2022-04-20 |  | 2022-08-18 |  |  | 0 | 220000 | 220000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206776 | OR-032659 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Construction 1% - 25% | Active - Not Contracted | 2022-02-18 |  | 2022-08-17 |  |  | 0 | 54933 | 54933 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206778 | ST352/2021 & ST374/2021 | Northern Cape | BEACON PRIMARY SCHOOL | 300015201 | Sol Plaatjie | Construction 51% - 75% | Active - Contracted | 2022-03-11 |  | 2023-03-31 |  |  | 0 | 8126954 | 8126954 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206784 | ST405/2022 | Northern Cape | FLOORS HIGH SCHOOL | 300011401 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-04-06 |  | 2025-03-31 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206787 | ST404/2021 | Northern Cape | HOERSKOOL NOORD KAAP | 300011402 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-06-06 |  | 2025-03-31 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206792 | ST411/2021 | Northern Cape | JJ ADAMS INTERMEDIATE SCHOOL | 300041205 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-03-01 |  | 2025-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206800 | TBD:CONVERSION INTO SPECIAL SCHOOL | Northern Cape | ALPHA PRIMERE SKOOL | 300021201 | Emthanjeni | Project Initiation | Proposed | 2022-09-28 |  | 2024-03-31 |  |  | 2000000 | 8898716 | 10898716 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 206817 | ADMINISTRATION BLOCK | Northern Cape | OLEBOGENG INTERMEDIATE SCHOOL | 300101562 | Joe Morolong | Feasibility | Active - Contracted | 2023-04-01 |  | 2025-03-30 |  |  | 861379 | 2000000 | 2861379 | Education Infrastructure Grant | Upgrading and Additions
|  | 206866 | TBDCLSR | Northern Cape | FANIE MALAN LAERSKOOL | 300041101 | Dawid Kruiper | Project Initiation | Active - Contracted | 2023-04-01 |  | 2025-03-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 206867 | ST420/2022 | Northern Cape | KAREEPAN PRIMARY SCHOOL | 300100629 | Joe Morolong | Practical Completion (100%) | Active - Contracted | 2022-02-28 | 2022-03-20 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206868 | ST020/2022-23 | Northern Cape | ZINGISA PRIMARY SCHOOL | 300016219 | Sol Plaatjie | Pre - Feasibility | Proposed | 2022-05-04 |  | 2024-03-31 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206876 | TBD:WATER | Northern Cape | PHILLIPSTOWN HOERSKOOL | 300021208 | Renosterberg | Project Initiation | Approved | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 650000 | 650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206878 | DRPW_WATER_MAINTENANCE | Northern Cape | KITLANYANG PRIMARY SCHOOL | 300045207 | Joe Morolong | Feasibility | Approved | 2022-06-06 |  | 2023-03-31 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206887 | TBD:WATER:GEOHYDROLOGIST | Northern Cape | HOERSKOOL GARIES | 300033302 | Kamiesberg | Project Initiation | Proposed | 2022-05-20 |  | 2023-03-31 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206889 | ST437/2022 | Northern Cape | HOERSKOOL GARIES | 300033302 | Kamiesberg | Project Initiation | Approved | 2022-04-07 |  | 2023-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206891 | TBD_CONVERSION/ERADICATION | Northern Cape | PERDE-EILAND NGK PRIMERE SKOOL | 300043222 | Kai !Garib | Feasibility | Approved | 2022-06-20 |  | 2023-03-29 |  |  | 0 | 50000 | 50000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 206898 | ECD TBD789 | Northern Cape | LAERSKOOL SEODIN | 300045211 | Ga-Segonyana | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 230517 | 5000000 | 5230517 | Education Infrastructure Grant | Upgrading and Additions
|  | 207040 | ST367/2021 | Northern Cape | THAE PRIMARY SCHOOL | 300102079 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 143583 | 143583 | Education Infrastructure Grant | Upgrading and Additions
|  | 207047 | ELECTRICITY4 | Northern Cape | VAN DER WALTSPOORT | 300024221 | Ubuntu | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 651239 | 651239 | Education Infrastructure Grant | Upgrading and Additions
|  | 207049 | FENCING1 | Northern Cape | BADIHILE PRIMARY SCHOOL | 300100042 | Ga-Segonyana | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 351000 | 351000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207050 | FENCING2 | Northern Cape | GAMOHANA INTERMEDIATE SCHOOL | 300100404 | Ga-Segonyana | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 509906 | 509906 | Education Infrastructure Grant | Upgrading and Additions
|  | 207051 | ST421/2022 | Northern Cape | GARIEP HIGH SCHOOL | 300022402 | !Kheis | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 650000 | 650000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207052 | ST277/2021 | Northern Cape | KALAHARI HIGH SCHOOL | 300045401 | Ga-Segonyana | Practical Completion (100%) | Active - Contracted | 2022-04-01 | 2022-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 6687406 | 6687406 | Education Infrastructure Grant | Upgrading and Additions
|  | 207054 | ST329/2021 | Northern Cape | NCWELENGWE PRIMARY SCHOOL | 300101492 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 928212 | 928212 | Education Infrastructure Grant | Upgrading and Additions
|  | 207057 | ST406/2021 | Northern Cape | WARRENVALE COMBINED SCHOOL | 300017305 | Magareng | Construction 51% - 75% | Active - Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 0 | 1150942 | 1150942 | Education Infrastructure Grant | Upgrading and Additions
|  | 207074 | ST427/2022 | Northern Cape | ISAGO PRIMARY SCHOOL | 300011204 | Sol Plaatjie | Design | Active - Not Contracted | 2022-02-18 |  | 2022-08-18 |  |  | 0 | 691209 | 691209 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207081 | TBD:MAINTENANCE TO SCHOOL | Northern Cape | PORT NOLLOTH LAERSKOOL | 300031209 | Richtersveld | Project Initiation | Proposed | 2022-04-06 |  | 2025-03-31 |  |  | 0 | 1198310 | 1198310 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207082 | TBD:CONVERSION_TOILETS | Northern Cape | MARUMO INTERMEDIATE SCHOOL | 300101121 | Ga-Segonyana | Feasibility | Approved | 2022-06-20 |  | 2024-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207083 | TBD_ MATJIESKLOOF | Northern Cape | MATJIESKLOOF PRIMARY SCHOOL | NEW | Nama Khoi | Project Initiation | Active - Not Contracted | 2022-04-07 |  | 2023-02-28 |  |  | 0 | 150000 | 150000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207084 | CONVERSION_TBD | Northern Cape | MARCH PRIMARY SCHOOL | 300101099 | Joe Morolong | Feasibility | Approved | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207085 | ST433/2022 | Northern Cape | MONTSHIWA PRIMARY SCHOOL | 300011207 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-02-05 |  | 2022-05-06 |  |  | 0 | 894769 | 894769 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207087 | TBD_ MOSHAWENG SECONDARY SCHOOL | Northern Cape | MOSHAWENG SECONDARY SCHOOL | 300101402 | Joe Morolong | Project Initiation | Approved | 2022-04-07 |  | 2022-08-26 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207088 | TBD_ PETRUSVILLE | Northern Cape | PETRUSVILLE HIGH SCHOOL | 300021402 | Renosterberg | Project Initiation | Approved | 2022-05-06 |  | 2022-10-05 |  |  | 0 | 380000 | 380000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207089 | TBD_ RENEILWE PRIMARY SCHOOL | Northern Cape | RENEILWE PRIMARY SCHOOL | 300014207 | Sol Plaatjie | Project Initiation | Approved | 2022-06-22 |  | 2022-12-30 |  |  | 0 | 1144085 | 1144085 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207091 | TBD_ SALT LAKE | Northern Cape | SALT LAKE PRIMARY SCHOOL | 300011211 | Siyancuma | Project Initiation | Proposed | 2022-04-08 |  | 2022-08-25 |  |  | 0 | 120000 | 120000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207092 | MOBILE | Northern Cape | ELIZABETH WIMMER SKOOL | 300031204 | Khi-Ma | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207093 | ST434/2022:ELECTRICITY | Northern Cape | ST PETERS PRIMARY SCHOOL | 300016216 | Sol Plaatjie | Design | Approved | 2022-04-07 |  | 2022-10-20 |  |  | 0 | 1141388 | 1141388 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207095 | MAINTENANCE TO ROOF | Northern Cape | ST JOHNS (RC) PRIMARY SCHOOL | 300021211 | Sol Plaatjie | Project Initiation | Approved | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 618607 | 618607 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207096 | ST432/2022 | Northern Cape | SOL PLAATJE | 300012215 | Sol Plaatjie | Project Initiation | Approved | 2022-06-06 |  | 2023-03-31 |  |  | 0 | 1800000 | 1800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207098 | TBD_ ANDERSON PRIMARY SCHOOL | Northern Cape | ANDERSON PRIMARY SCHOOL | 300016202 | Siyancuma | Design | Proposed | 2022-04-07 |  | 2022-08-26 |  |  | 0 | 931000 | 931000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207099 | TBD_AUGRABIES INTERMEDIATE SCHOOL | Northern Cape | AUGRABIES INTERMEDIATE SCHOOL | 300043212 | Kai !Garib | Tender | Proposed | 2022-05-05 |  | 2022-08-04 |  |  | 0 | 489077 | 489077 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207100 | ST419/2021 | Northern Cape | BA GA LOTLHARE INTERMEDIATE SCHOOL | 300100037 | Joe Morolong | Tender | Approved | 2022-03-17 |  | 2023-03-31 |  |  | 0 | 554588 | 554588 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207101 | ST317/2021 | Northern Cape | BA GA LOTLHARE INTERMEDIATE SCHOOL | 300100037 | Joe Morolong | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-08-19 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207102 | MAINTENANCE TO SCHOOL:TBD | Northern Cape | NOURIVIER MET PRIMERE SKOOL | 300034208 | Kamiesberg | Project Initiation | Proposed | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 829172 | 829172 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207103 | TBD_ BA GA LOTLHARE _ | Northern Cape | BA GA LOTLHARE INTERMEDIATE SCHOOL | 300100037 | Joe Morolong | Project Initiation | Active - Not Contracted | 2022-06-14 |  | 2022-10-20 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207104 | SCHOOL MAINTENANCE | Northern Cape | NEW SNAUSWANE PRIMARY SCHOOL | N/A | Joe Morolong | Project Initiation | Proposed | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 1200000 | 1200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207105 | ST347/2021 | Northern Cape | BATLHARO TLHAPING SECONDARY SCHOOL | 300100095 | Ga-Segonyana | Design | Active - Not Contracted | 2022-01-25 | 2022-01-31 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 0 | 680000 | 680000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207106 | TBD_ BATLHARO TLHAPING SECONDARY SCHOOL _ | Northern Cape | BATLHARO TLHAPING SECONDARY SCHOOL | 300100095 | Ga-Segonyana | Project Initiation | Active - Not Contracted | 2022-04-06 |  | 2022-10-02 |  |  | 0 | 800000 | 800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207107 | ST015/2022-23 | Northern Cape | MAIKAELELO INTERMEDIATE SCHOOL | 300101004 | Joe Morolong | Project Initiation | Proposed | 2022-08-05 |  | 2023-03-31 |  |  | 0 | 1577784 | 1577784 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207108 | GAFFIE MAREE:MAINTENANCE | Northern Cape | LAERSKOOL GAFFIE MAREE | 300031208 | Richtersveld | Project Initiation | Proposed | 2022-04-05 |  | 2023-03-31 |  |  | 0 | 1198310 | 1198310 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207109 | ST326/2021 | Northern Cape | BOITSHOKO PRIMARY SCHOOL | 300015203 | Sol Plaatjie | Practical Completion (100%) | Active - Contracted | 2022-02-18 | 2022-04-08 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 0 | 1020002 | 1020002 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207111 | ST018/2022-23 | Northern Cape | CARDINGTON PRIMARY SCHOOL | 300100230 | Ga-Segonyana | Construction 1% - 25% | Approved | 2022-02-05 |  | 2022-08-31 |  |  | 0 | 1510735 | 1510735 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207113 | TBD_COLESBERG | Northern Cape | COLESBERG GEKOMBINEERDE SKOOL | 300023302 | Umsobomvu | Project Initiation | Proposed | 2022-05-05 |  | 2022-11-23 |  |  | 0 | 400000 | 400000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207114 | ST319/2021 | Northern Cape | WRENCHVILLE PRIMERE SKOOL | 300045218 | Ga-Segonyana | Tender | Approved | 2022-05-06 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207115 | ST323/2021 | Northern Cape | WILLIE THERON PRIMARY SCHOOL | 300021212 | Emthanjeni | Construction 26% - 50% | Active - Contracted | 2021-10-12 | 2021-10-26 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 6780000 | 6780000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207116 | MAINTENANCE:WESTERKIM | Northern Cape | WESTERKIM PRIMARY SCHOOL | 300042222 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207117 | TBD_COLESBERG PUBLIC | Northern Cape | COLESBERG PUBLIC PRIMARY SCHOOL | 300023203 | Umsobomvu | Tender | Proposed | 2022-05-05 |  | 2022-11-11 |  |  | 0 | 753341 | 753341 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207118 | TBD_ DEBEN PRIMARY SCHOOL | Northern Cape | DEBEN PRIMERE SCHOOL | 300044203 | Gamagara | Tender | Proposed | 2022-05-06 |  | 2022-11-10 |  |  | 0 | 1661809 | 1661809 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207119 | TBD_ DIE KUIL | Northern Cape | DIE KUIL INTERMEDIATE SCHOOL | 300045203 | Kgatelopele | Design | Proposed | 2022-06-10 |  | 2022-11-25 |  |  | 0 | 550000 | 550000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207120 | TBD_ DR IZAK | Northern Cape | DR IZAK VAN NIEKERK | 300032301 | Nama Khoi | Project Initiation | Proposed | 2022-05-12 |  | 2022-10-27 |  |  | 0 | 3500000 | 3500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207121 | OR-031790 | Northern Cape | DUTTON PRIMARY SCHOOL | 300100337 | Ga-Segonyana | Construction 26% - 50% | Active - Contracted | 2022-01-07 | 2022-03-02 | 2022-06-10 | 2022-06-17 | 2022-06-24 | 0 | 221744 | 221744 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207122 | ST016/2022-23 | Northern Cape | EDIGANG PRIMARY SCHOOL | 300100345 | Joe Morolong | Construction 76% - 99% | Active - Not Contracted | 2022-03-09 |  | 2023-03-31 |  |  | 0 | 1125089 | 1125089 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207123 | TBD_ ELIZABETH WIMMER | Northern Cape | ELIZABETH WIMMER SKOOL | 300031204 | Khi-Ma | Project Initiation | Proposed | 2022-05-05 |  | 2022-11-30 |  |  | 0 | 1829172 | 1829172 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207124 | TBD_ ELIZABETH WIMMER PRIMARY SCHOOL | Northern Cape | ELIZABETH WIMMER SKOOL | 300031204 | Khi-Ma | Project Initiation | Proposed | 2022-04-13 |  | 2022-10-28 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207125 | TBD_EUREKA INTERMEDIATE SCHOOL | Northern Cape | EUREKA INTERMEDIERE SKOOL | 300023301 | Sol Plaatjie | Project Initiation | Proposed | 2022-06-10 |  | 2022-11-30 |  |  | 0 | 600000 | 600000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207126 | TBD_FERDINAND BRECHER PRIMARY SCHOOL | Northern Cape | FERDINAND BRECHER PRIMARY SCHOOL | 300031205 | Nama Khoi | Project Initiation | Proposed | 2022-04-08 |  | 2022-08-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207127 | TBD_ FLOORS NORTH | Northern Cape | FLOORS NORTH INTERMEDIATE SCHOOL | 300012203 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-08-26 |  |  | 0 | 230000 | 230000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207128 | OR-032049 | Northern Cape | FRANCES BAARD DISTRICT OFFICE - HADISON PARK | 300010201 | Gamagara | Construction 76% - 99% | Active - Contracted | 2022-01-07 | 2022-01-28 | 2022-04-08 | 2022-04-29 | 2022-06-30 | 0 | 74133 | 74133 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207129 | TBD_FRANCE BAARD DISTRICT OFFICE | Northern Cape | FRANCES BAARD DISTRICT OFFICE - HADISON PARK | 300010201 | Gamagara | Feasibility | Proposed | 2022-07-12 |  | 2023-01-08 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207130 | TBD_ PEME | Northern Cape | FRANCES BAARD DISTRICT:PEME | N/A | Sol Plaatjie | Feasibility | Proposed | 2022-07-07 |  | 2023-03-31 |  |  | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207131 | MAINTENANCE AT CYBER LABS | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 300100101 | Sol Plaatjie | Feasibility | Approved | 2022-07-07 |  | 2023-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207132 | ST054/2022-23 | Northern Cape | GAAESI PRIMARY SCHOOL | 300100383 | Joe Morolong | Tender | Proposed | 2022-05-11 |  | 2022-06-30 |  |  | 0 | 1742266 | 1742266 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207133 | TBD_ GALALETSANG | Northern Cape | GALALETSANG SCIENCE SECONDARY SCHOOL | 300100397 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-09-30 |  |  | 0 | 1675857 | 1675857 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207134 | ST345/2021 | Northern Cape | VAN ZYLSRUS INTERMEDI?RE SKOOL | 300045213 | Joe Morolong | Tender | Active - Not Contracted | 2022-05-06 |  | 2023-03-31 |  |  | 200000 | 0 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207135 | ST316/2021 | Northern Cape | GALALETSANG SCIENCE SECONDARY SCHOOL | 300100397 | Ga-Segonyana | Tender | Approved | 2022-05-05 |  | 2022-10-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207136 | ST333/2021 | Northern Cape | GALOTOLO PRIMARY SCHOOL | 300100401 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-01-07 |  | 2022-11-30 |  |  | 0 | 515293 | 515293 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207137 | ADMINISTRATION BLOCK12 | Northern Cape | BOJELAKGOMO PRIMARY SCHOOL | 300100166 | Joe Morolong | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 3813059 | 3813059 | Education Infrastructure Grant | Upgrading and Additions
|  | 207138 | CLASSROOM BLOCK8 | Northern Cape | AB KOLWANE PRIMARY SCHOOL | 300105057 | Ga-Segonyana | Feasibility | Active - Contracted | 2022-04-01 |  | 2024-03-30 |  |  | 0 | 13483074 | 13483074 | Education Infrastructure Grant | Upgrading and Additions
|  | 207139 | TBD_ GARIEP | Northern Cape | GARIEP HIGH SCHOOL | 300022402 | !Kheis | Design | Proposed | 2022-07-12 |  | 2023-01-12 |  |  | 0 | 2500000 | 2500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207140 | ST430/2022 | Northern Cape | GRIQUATOWN INTERMEDIATE SCHOOL | 300016301 | Siyancuma | Design | Proposed | 2022-04-15 |  | 2022-09-30 |  |  | 0 | 3133233 | 3133233 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207141 | ST428/2022 | Northern Cape | HOERSKOOL THERON | 300022303 | Emthanjeni | Construction 76% - 99% | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 949865 | 3000000 | 3949865 | Education Infrastructure Grant | Upgrading and Additions
|  | 207142 | ST338/2021 | Northern Cape | KIMBERLEY TRAINING CENTRE | 300010704 | Sol Plaatjie | Design | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 570775 | 570775 | Education Infrastructure Grant | Upgrading and Additions
|  | 207143 | ST424/2022: STRUCTURAL ASSESSMENT | Northern Cape | HANTAM PRIMERE SKOOL | 300033206 | Hantam | Site Handed - Over to Contractor | Active - Contracted | 2022-05-06 | 2022-05-20 | 2022-10-14 | 2022-12-23 | 2022-12-30 | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207144 | TBD_ HANTAM | Northern Cape | HANTAM PRIMERE SKOOL | 300033206 | Hantam | Feasibility | Proposed | 2022-04-07 |  | 2022-08-31 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207145 | ST310/2021:STRUCTURAL ASSESSMENT | Northern Cape | HANTAM SECONDARY SCHOOL | 300033401 | Hantam | Site Handed - Over to Contractor | Active - Contracted | 2022-04-08 | 2022-04-22 | 2022-09-16 | 2022-10-14 | 2022-11-30 | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207146 | TBD_ HANTAM SECONDARY SCHOOL | Northern Cape | HANTAM SECONDARY SCHOOL | 300033401 | Hantam | Feasibility | Proposed | 2022-04-07 |  | 2022-10-28 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207147 | STRUCTURAL ASSESSMENT | Northern Cape | NEW SCHOOL VALSPAN SECONDARY SCHOOL | NEW | Phokwane | Feasibility | Active - Not Contracted | 2022-04-10 |  | 2023-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207148 | TBD_ IK NKOANE | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Tender | Proposed | 2022-02-11 |  | 2022-06-17 |  |  | 0 | 2958490 | 2958490 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207149 | OR-032686 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Construction 51% - 75% | Proposed | 2022-04-08 | 2022-04-16 | 2023-01-23 | 2023-03-31 | 2023-03-31 | 0 | 1500000 | 1500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207151 | ST425/2022 | Northern Cape | CALVINIA HIGH SCHOOL | 300033402 | Hantam | Site Handed - Over to Contractor | Active - Contracted | 2022-06-06 | 2022-06-20 | 2022-10-10 | 2022-10-17 | 2022-10-31 | 0 | 850000 | 850000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207153 | TBD_GARIES | Northern Cape | GARIES HIGH SCHOOL | 300022402 | !Kheis | Project Initiation | Proposed | 2022-04-15 |  | 2022-10-28 |  |  | 0 | 4088709 | 4088709 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207154 | ST423/2022 | Northern Cape | HO?RSKOOL GROBLERSHOOP | 300043402 | !Kheis | Construction 26% - 50% | Active - Contracted | 2022-04-06 | 2022-06-20 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 9000000 | 9000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207155 | ST355/2021 | Northern Cape | HOERSKOOL HARTSWATER | 300017401 | Phokwane | Practical Completion (100%) | Active - Contracted | 2022-04-01 |  | 2023-04-01 |  |  | 0 | 841392 | 841392 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207156 | MOBILES2223 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 376427 | 3000000 | 3376427 | Education Infrastructure Grant | Upgrading and Additions
|  | 207157 | OR-032285 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Construction 26% - 50% | Active - Contracted | 2022-04-01 | 2022-04-02 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 0 | 10000000 | 10000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207158 | ST344/2021 | Northern Cape | KALAHARI HIGH SCHOOL | 300045401 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-12 |  | 2022-10-28 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207159 | OR-032284 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2022-04-01 | 2022-04-02 | 2025-03-31 | 2025-03-30 | 2025-03-31 | 0 | 40000000 | 40000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207160 | OR-032283 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2022-04-01 | 2022-04-02 | 2024-03-30 | 2024-03-31 | 2024-03-31 | 0 | 25000000 | 25000000 | Education Infrastructure Grant | Upgrading and Additions
|  | 207161 | TBD_ KALAHARI | Northern Cape | KALAHARI HIGH SCHOOL | 300045401 | Ga-Segonyana | Project Initiation | Proposed | 2022-04-07 |  | 2022-09-30 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207164 | TBD_KATHU HIGH SCHOOL | Northern Cape | KATHU HIGH SCHOOL | 300044402 | Gamagara | Project Initiation | Proposed | 2022-08-11 |  | 2023-02-08 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207167 | TBD_ RICHMOND | Northern Cape | HOERSKOOL RICHMOND | 300024303 | Ubuntu | Project Initiation | Active - Not Contracted | 2022-05-05 |  | 2022-09-30 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207168 | ST334-2021 | Northern Cape | HOERSKOOL THERON | 300022303 | Emthanjeni | Design | Active - Not Contracted | 2021-04-01 |  | 2022-07-29 |  |  | 0 | 1000000 | 1000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207173 | TBD_HOMEVALE | Northern Cape | HOMEVALE HIGH SCHOOL | 300012402 | Sol Plaatjie | Feasibility | Proposed | 2022-05-05 |  | 2022-10-31 |  |  | 0 | 1900000 | 1900000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207175 | ST027/2022-23 | Northern Cape | HUTCHINSON PRIMARY SCHOOL | 300024206 | Ubuntu | Design | Proposed | 2022-06-10 |  | 2022-10-28 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207176 | TBD_ IKEMELENG | Northern Cape | IKEMELENG PRIMARY SCHOOL | 300100532 | Gamagara | Design | Active - Not Contracted | 2022-06-10 |  | 2022-10-31 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207180 | TBD_REPAIRS TO ROOF | Northern Cape | INEELENG PRIMARY SCHOOL | 3000100542 | Ga-Segonyana | Project Initiation | Proposed | 2022-05-06 |  | 2022-09-30 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207182 | MAINTENANCE - CORRECTIVE | Northern Cape | MONOKETSI INTERMEDIATE SCHOOL | 300101360 | Joe Morolong | Feasibility | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 450000 | 450000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207183 | TBD_ BOREHOLE | Northern Cape | ITEKELENG PRIMARY SCHOOL | 300100561 | Joe Morolong | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-10-28 |  |  | 0 | 600000 | 600000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207184 | ST341/2021 | Northern Cape | MORELIG INTERMEDIATE SCHOOL | 300042306 | Kai !Garib | Design | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 371891 | 371891 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207193 | ST017/2022-23 | Northern Cape | ITOTLENG COMMERCIAL SECONDARY SCHOOL | 300100573 | Joe Morolong | Design | Active - Not Contracted | 2022-03-09 |  | 2022-06-30 |  |  | 0 | 2639448 | 2639448 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207195 | ST431/2021 | Northern Cape | JJ ADAMS INTERMEDIATE SCHOOL | 300041205 | Dawid Kruiper | Construction 26% - 50% | Active - Not Contracted | 2022-03-10 |  | 2022-08-31 |  |  | 0 | 7083139 | 7083139 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207196 | TBD_JJ DREYER | Northern Cape | JJ DREYER PRIM?RE SKOOL | 300022203 | Siyathemba | Project Initiation | Active - Not Contracted | 2022-06-09 |  | 2022-10-28 |  |  | 0 | 800000 | 800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207197 | MAINTENANCE - CORRECTIVE2 | Northern Cape | MOSHAWENG SECONDARY SCHOOL | 300101402 | Joe Morolong | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 250000 | 250000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207198 | MAINTENANCE - CORRECTIVE15 | Northern Cape | NAMETSEGANG SECONDARY SCHOOL | 300101486 | Joe Morolong | Design | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207200 | ST023/2022-23 | Northern Cape | NEWTON PRIMARY SCHOOL | 300013211 | Sol Plaatjie | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 300000 | 300000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207201 | TBD_ KEATLHOLELA | Northern Cape | KEATLHOLELA PRIMARY SCHOOL | 300100641 | Joe Morolong | Design | Active - Not Contracted | 2022-06-06 |  | 2022-11-30 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207202 | ST318/2021: | Northern Cape | REKGARATLHILE HIGH SCHOOL | 300101821 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-06 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207203 | ST343/2021:STRUCTURAL ASSESSMENT | Northern Cape | HOERSKOOL NOORD KAAP | 300011402 | Sol Plaatjie | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207204 | MAINTENANCE - CORRECTIVE256 | Northern Cape | HOERSKOOL NOORD KAAP | 300011402 | Sol Plaatjie | Feasibility | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207205 | MAINTENANCE - CORRECTIVE159 | Northern Cape | NORVALSPONT INTERMEDIATE SCHOOL | 300023209 | Umsobomvu | Design | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 989610 | 989610 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207206 | TBD_REMEDIAL WORK:STRUCTURAL ASSESSMENT | Northern Cape | REKGARATLHILE HIGH SCHOOL | 300101821 | Ga-Segonyana | Feasibility | Active - Not Contracted | 2022-07-12 |  | 2023-03-31 |  |  | 0 | 1850000 | 1850000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207207 | MAINTENANCE - CORRECTIVE19- DONOR | Northern Cape | OLYVENHOUTSDRIFT PRIMERE SKOOL | 300041212 | Dawid Kruiper | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 589828 | 589828 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207208 | ST048/2022-23 | Northern Cape | OMANG PRIMARY SCHOOL | 300101568 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 2366625 | 2366625 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207209 | ST412/2021 | Northern Cape | RIETFONTEIN GEKOMBINEERDE SKOOL | 300041301 | Dawid Kruiper | Practical Completion (100%) | Active - Not Contracted | 2022-05-07 |  | 2023-03-31 |  |  | 0 | 850000 | 850000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207210 | ST047/2022-23 | Northern Cape | OREEDITSE PRIMARY SCHOOL | 300101579 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1182305 | 1182305 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207211 | MAINTENANCE - CORRECTIVE53 | Northern Cape | PERDE-EILAND NGK PRIMERE SKOOL | 300043222 | Kai !Garib | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 589828 | 589828 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207212 | ST414/2021 | Northern Cape | KHUIS PRIMARY SCHOOL | 300100715 | Joe Morolong | Design | Active - Not Contracted | 2022-01-14 |  | 2022-07-28 |  |  | 0 | 1442000 | 1442000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207213 | MAINTENANCE - CORRECTIVE583 | Northern Cape | PESCODIA PRIMARY SCHOOL | 300014212 | Sol Plaatjie | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 5021475 | 5021475 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207214 | MAINTENANCE - CORRECTIVE589 | Northern Cape | PETRUSVILLE HIGH SCHOOL | 300021402 | Renosterberg | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207215 | ST035/2022-23 | Northern Cape | PHILLIPSTOWN HOERSKOOL | 300021208 | Renosterberg | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 2800000 | 2800000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207217 | MAINTENANCE - CORRECTIVE269 | Northern Cape | PNIEL-LANDGOED PRIMARY SCHOOL | 300013306 | Dikgatlong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207218 | ST331/2021 | Northern Cape | PULELO PRIMARY SCHOOOL | 300101691 | Joe Morolong | Tender | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 1207700 | 1207700 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207219 | ST034/2022-23 | Northern Cape | ROODEPAN SECONDARY SCHOOL (NEW) | NEW | Sol Plaatjie | Feasibility | Active - Not Contracted | 2022-06-20 |  | 2023-03-31 |  |  | 0 | 2000000 | 2000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207220 | ST314/2021:STRUCTURAL ASSESSMENT | Northern Cape | LAERSKOOL KATHU | TBD | Gamagara | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-10-27 |  |  | 0 | 1400000 | 1400000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207221 | MAINTENANCE - CORRECTIVE4269 | Northern Cape | REAKANTSWE SECONDARY SCHOOL | 300012304 | Dikgatlong | Project Initiation | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207222 | SA VAN WYK:R&R ST010-2022-3 | Northern Cape | SA VAN WYK HIGH SCHOOL | 300032402 | Nama Khoi | Construction 1% - 25% | Approved | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 489077 | 489077 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207223 | TBD_ KATHU LAERSKOOL | Northern Cape | LAERSKOOL KATHU | TBD | Gamagara | Feasibility | Active - Not Contracted | 2022-07-12 |  | 2023-07-21 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207225 | ST359/2021 | Northern Cape | HOERSKOOL SAUL DAMON | 300042403 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207226 | ST311/2021 | Northern Cape | LAERSKOOL KLEINZEE | 300033221 | Nama Khoi | Project Initiation | Active - Not Contracted | 2022-05-05 |  | 2022-11-23 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207227 | TBD_ KLEINZEE | Northern Cape | LAERSKOOL KLEINZEE | 300033221 | Nama Khoi | Feasibility | Active - Not Contracted | 2022-07-13 |  | 2023-02-28 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207228 | ST311/2021_1 | Northern Cape | LAERSKOOL KURUMAN | 300045210 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-05-05 |  | 2022-09-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207230 | ST415/2022:R&R | Northern Cape | SC KEARNS | 300043306 | Dawid Kruiper | Tender | Active - Not Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 773301 | 773301 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207231 | TBD_ KURUMAN | Northern Cape | LAERSKOOL KURUMAN | 300045210 | Ga-Segonyana | Feasibility | Active - Not Contracted | 2022-07-07 |  | 2023-01-31 |  |  | 0 | 1650000 | 1650000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207232 | ST302/2021 | Northern Cape | ST PETERS PRIMARY SCHOOL | 300016216 | Sol Plaatjie | Site Handed - Over to Contractor | Active - Contracted | 2022-04-01 | 2022-04-19 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 0 | 3000000 | 3000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207235 | TBD_LELIEFONTEIN INTERMEDIATE SCHOOL | Northern Cape | LELIEFONTEIN INTERMEDIATE SCHOOL | 30002306 | Kamiesberg | Feasibility | Active - Not Contracted | 2022-04-14 |  | 2022-09-30 |  |  | 0 | 319100 | 319100 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207236 | ST045/2022-23 | Northern Cape | LESEDI SECONDARY SCHOOL | 300100873 | Gamagara | Tender | Active - Not Contracted | 2022-03-10 |  | 2022-08-31 |  |  | 0 | 3569722 | 3569722 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207237 | TBD_ LETSHEGO | Northern Cape | LETSHEGO PRIMARY SCHOOL | 300014401 | Sol Plaatjie | Project Initiation | Active - Not Contracted | 2022-06-09 |  | 2022-10-28 |  |  | 0 | 850000 | 850000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207238 | TBD_MAHIKANENG | Northern Cape | MAHIKANENG PRIMARY SCHOOL | 300100999 | Ga-Segonyana | Project Initiation | Active - Not Contracted | 2022-06-09 |  | 2023-03-31 |  |  | 0 | 750000 | 750000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207239 | ST422/2022_HOSTEL | Northern Cape | STRYDENBURG COMBINED SCHOOL | 300022307 | Thembelihle | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 4000000 | 4000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207240 | TETLANYO:R&R | Northern Cape | TETLANYO SECONDARY SCHOOL | 300016402 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 200000 | 200000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207241 | TBD_MALHERBE | Northern Cape | STEPHEN MALHERBE PRIMERE SKOOL | 300031211 | Richtersveld | Project Initiation | Active - Not Contracted | 2022-09-14 |  | 2023-04-19 |  |  | 0 | 6852286 | 6852286 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207242 | ST370/2021 | Northern Cape | THAE PRIMARY SCHOOL | 300102079 | Joe Morolong | Tender | Active - Not Contracted | 2022-05-04 |  | 2023-03-31 |  |  | 0 | 1342929 | 1342929 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207243 | ST050/2022-23 | Northern Cape | TSOE PRIMARY SCHOOL | 300104019 | Joe Morolong | Tender | Active - Not Contracted | 2022-05-05 |  | 2023-03-31 |  |  | 0 | 1395093 | 1395093 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207244 | TBD_MANKURWANE | Northern Cape | MANKURWANE INTERMEDIATE SCHOOL | 300016212 | Sol Plaatjie | Project Initiation | Active - Not Contracted | 2022-05-05 |  | 2022-12-30 |  |  | 0 | 350000 | 350000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207245 | ST019/2022-23 | Northern Cape | MAPOTENG PRIMARY SCHOOL | 300101090 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-03-09 |  | 2022-06-30 |  |  | 0 | 1077365 | 1077365 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207246 | ST046/2022-23 | Northern Cape | MARUPING PRIMARY SCHOOL | 300101123 | Ga-Segonyana | Tender | Active - Not Contracted | 2022-03-09 |  | 2022-11-30 |  |  | 0 | 1712838 | 1712838 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207248 | TBD_ MATSHANENG | Northern Cape | MATSHANENG INTERMEDIATE SCHOOL | 300101163 | Joe Morolong | Tender | Active - Not Contracted | 2022-03-09 |  | 2023-01-27 |  |  | 0 | 797672 | 797672 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207249 | TBD_ MECWETSANENG | Northern Cape | MECWETSANENG PRIMARY SCHOOL | 300101178 | Joe Morolong | Project Initiation | Active - Not Contracted | 2022-04-04 |  | 2022-09-30 |  |  | 0 | 500000 | 500000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207250 | ST413/2021 | Northern Cape | JJ BOOYSEN PRIMARY SCHOOL | 300024207 | Ubuntu | Construction 26% - 50% | Active - Contracted | 2022-06-05 |  | 2024-03-31 |  |  | 6595284 | 30000000 | 36595284 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 207251 | TBD_ ROOF | Northern Cape | PABALELO PRIMARY SCHOOL | 300101596 | Phokwane | Design | Active - Not Contracted | 2022-03-18 |  | 2023-04-28 |  |  | 0 | 850000 | 850000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207253 | OR-028987 | Northern Cape | HEAD OFFICE - IK NKOANE EDUCATION HOUSE | 30001000 | Sol Plaatjie | Tender | Active - Not Contracted | 2022-06-24 |  | 2022-10-28 |  |  | 0 | 351000 | 351000 | Education Infrastructure Grant | Non-Infrastructure
|  | 207258 | TBD_ZF MGCAWU | Northern Cape | ZF MGCAWU NEW SPECIAL SCHOOL | N/A | Dawid Kruiper | Feasibility | Approved | 2022-07-22 |  | 2025-03-24 |  |  | 15000000 | 75150336 | 90150336 | Education Infrastructure Grant | New or Replaced Infrastructure
|  | 207320 | TBD_ GIRL HIGH SCHOOL | Northern Cape | KIMBERLEY GIRLS HIGH SCHOOL | 300011403 | Sol Plaatjie | Feasibility | Active - Not Contracted | 2022-05-05 |  | 2022-10-28 |  |  | 0 | 266582 | 266582 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207368 | GDE00409 | Gauteng | Assessment and Valuation @Varoius Facilities | Various | City of Ekurhuleni | Project Initiation | Approved | 2022-04-01 |  | 2026-03-13 |  |  | 2000000 | 0 | 2000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 207369 | GDE00406 | Gauteng | Title Deeds Search | Various | City of Johannesburg | Project Initiation | Approved | 2022-04-01 |  | 2025-04-12 |  |  | 200000 | 0 | 200000 | Education Infrastructure Grant | Non-Infrastructure
|  | 207370 | GDE00400 | Gauteng | Chemical Toilets @various schools | Various | City of Johannesburg | Project Initiation | Approved | 2022-04-01 |  | 2025-04-12 |  |  | 6000000 | 0 | 6000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 207371 | GDE00402 | Gauteng | Septic Tanks @various scho | Various | City of Johannesburg | Project Initiation | Approved | 2022-04-01 |  | 2026-03-13 |  |  | 6000000 | 0 | 6000000 | Education Infrastructure Grant | Non-Infrastructure
|  | 207373 | GDE00434 | Gauteng | Devon ECD | N/A | City of Ekurhuleni | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-07-11 | 2025-11-14 | 2026-03-13 | 1576000 | 0 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207374 | GDE00435 | Gauteng | Etwatwa/Dephney Masuku ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-13 | 2025-09-20 | 2026-03-30 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207375 | GDE00436 | Gauteng | Kagiso ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-30 | 2025-09-29 | 2026-03-30 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207376 | GDE00437 | Gauteng | Katlehong ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-13 | 2025-09-19 | 2026-03-13 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207377 | GDE00438 | Gauteng | Kwasokhulumi Early Childhood Centre | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-30 | 2025-09-29 | 2026-03-16 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207378 | GDE00439 | Gauteng | Kwathema / Eyethu Sonke ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-30 | 2025-09-29 | 2026-03-30 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207379 | GDE00440 | Gauteng | Mohlakeng ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-30 | 2025-09-29 | 2026-03-30 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207380 | GDE00441 | Gauteng | Munsieville ECD | N/A | City of Johannesburg | Site Handed - Over to Contractor | Approved | 2022-04-01 | 2022-06-15 | 2025-06-30 | 2026-09-29 | 2026-03-30 | 0 | 1576000 | 1576000 | Equitable Share | Maintenance and Repairs
|  | 207381 | GDE00442 | Gauteng | Renovation of ECD | N/A | City of Johannesburg | Tender | Approved | 2022-04-01 |  | 2025-06-30 |  |  | 0 | 45166000 | 45166000 | Equitable Share | Maintenance and Repairs
|  | 207382 | GDE00443 | Gauteng |  |  |  | Other - Packaged Ongoing Project | Approved | 2022-04-01 |  | 2025-03-31 |  |  | 0 | 9051000 | 9051000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 207384 | GDE00415 | Gauteng | Maintenance ES @various schools | N/A | City of Johannesburg | Project Initiation | Approved | 2022-04-01 |  | 2026-04-11 |  |  | 0 | 10130000 | 10130000 | Equitable Share | Maintenance and Repairs
|  | 207385 | GDE00338 | Gauteng | Sharicrest Primaru School | 700110312 | City of Johannesburg | Project Initiation | Approved | 2020-07-06 |  | 2023-04-05 |  |  | 240000 | 1260000 | 1500000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 207386 | GDE00331 | Gauteng | SELCOURT PRIMARY SCHOO | G18030012/1 | City of Ekurhuleni | Project Initiation | Approved | 2021-04-01 |  | 2026-03-13 |  |  | 500000 | 1500000 | 2000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 207396 | GDE00258 | Gauteng | Norkem Park High School | 700260471 | City of Ekurhuleni | Project Initiation | Proposed | 2022-04-01 |  | 2026-03-13 |  |  | 300000 | 700000 | 1000000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 207427 | GDE00245 | Gauteng | Mulbarton Primary School | 799110486 | City of Johannesburg | Feasibility | Approved | 2022-04-06 |  | 2025-04-12 |  |  | 152800 | 802200 | 955000 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 207692 | DPWRT/SAN/201/20MP AZALEA PRIM --------- | Mpumalanga | Azalea Combined School | 800000398 | Lekwa | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-03-03 |  |  | 1429848 | 14298489 | 15728337 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207693 | DoE/EHL/MAIN/128 | Mpumalanga | Vutselani Primary School | 800025130 | Mbombela | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 486701 | 486701 | Education Infrastructure Grant | Infrastructure Transfers - Current
|  | 207694 | MDOE/MAIN/47/21-22 | Mpumalanga | Umpopoli Primary School | 800024354 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 3902971 | 3902971 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207695 | MDOE/MAIN/05/22-23 | Mpumalanga | Thandulwazi Primary School | 800022970 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 1456587 | 1456587 | ECD Infrastructure Component | Maintenance and Repairs
|  | 207696 | MDOE/MAIN/17/22-23 | Mpumalanga | Sokisi Secondary School | 800035045 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 2461158 | 2461158 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207697 | MDOE/MAIN/22-23/228 | Mpumalanga | Siyeta Primary School | 800021618 | Chief Albert Luthuli | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 4651496 | 4651496 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207698 | MDOE/MAIN/04/22-23 | Mpumalanga | Sitintile Secondary School | 800021410 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 2908365 | 2908365 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207699 | DoE/NKD/MAIN/048 1 | Mpumalanga | Elusindisweni Primary School | 800003459 | Steve Tshwete | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 257213 | 2572139 | 2829352 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207700 | MDOE/MAIN/22-23/62 | Mpumalanga | Sindzawonye Primary School | 800200273 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 3907003 | 205632 | 4112635 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207701 | MDOE/MAIN/22-23/94 | Mpumalanga | Empucukweni Secondary School | 800003616 | Emalahleni | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 688747 | 6887474 | 7576221 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207703 | DoE/EHL/MAIN/131 | Mpumalanga | Sidloko Primary School | 800020867 | Nkomazi | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 453701 | 453701 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207705 | DPWRT/028/19/MP 01 | Mpumalanga | Sibongimpumelelo Primary School | 800020727 | Thembisile | Practical Completion (100%) | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 3501110 | 3501110 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207707 | MDOE/MAIN/03/22-23 | Mpumalanga | Sibhulo Secondary School | 800020651 | Mbombela | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 819643 | 819643 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207708 | DPWRT/MAIN/038/21/MP | Mpumalanga | Shongwe Boarding School | 800020578 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 4031123 | 4031123 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207712 | MDOE/MAIN/22-23/99 | Mpumalanga | Hlabangemehlo Primary School | 800005173 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2024-04-04 |  |  | 442344 | 4423443 | 4865787 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207713 | MDOE/MAIN/10/22-23 | Mpumalanga | Samuel Mhlanga Primary School | 800035481 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 716958 | 0 | 716958 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207714 | MDOE/MAIN/02/22-23 | Mpumalanga | Sambo Primary School | 800029314 | Nkomazi | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 1026000 | 1026000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207715 | MDOE/MAIN/14/22-23 | Mpumalanga | Hoxani EMS | MP00546 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 672543 | 4803880 | 5476423 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207716 | MDOE/MAIN/22-23/12 | Mpumalanga | Hoyi Primary School | 800005686 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 335765 | 3357650 | 3693415 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207717 | DoE/Boh/MAIN/217 | Mpumalanga | Imizamoyethu Primary School | 800029363 | Mkhondo | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 84440 | 844409 | 928849 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207718 | MDOE/MAIN/22-23/13 | Mpumalanga | Inkunzi Secondary School | 800006478 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 357127 | 3571277 | 3928404 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207719 | MDOE/MAIN/06/22-23 | Mpumalanga | Phakgamang Primary School | 800018119 | Dr JS Moroka | Project Initiation | Active - Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 2290664 | 2290664 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207720 | MDOE/MAIN/22-23/112 | Mpumalanga | INSIKA SECONDARY SCHOOL | 800006510 | Chief Albert Luthuli | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 442344 | 4423443 | 4865787 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207721 | MDOE/MAIN/22-23/114 | Mpumalanga | Jeremia Mdaka Primary School | 800007021 | Emalahleni | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 387477 | 3874778 | 4262255 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207722 | MDOE/MAIN/22-23/15 | Mpumalanga | Khaliphani Primary School | 800007575 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 312356 | 3123567 | 3435923 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207723 | MDOE/MAIN/09/22-23 | Mpumalanga | Ndabeni Primary School | 800034962 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 2461158 | 2461158 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207724 | MDOE/MAIN/12/22-23 | Mpumalanga | Mtembeni Primary School | 800035035 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 1435158 | 1435158 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207725 | MDOE/MAIN/22-23/20 | Mpumalanga | KwaJelusa Primary School | 800008623 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 245813 | 2458139 | 2703952 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207726 | MDOE/MAIN/22-23/21 | Mpumalanga | Kwalodakada Primary School | 800008672 | Nkomazi | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 205877 | 2058774 | 2264651 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207727 | MDOE/MAIN/22-23/23 | Mpumalanga | LEGOGOTE PRIMARY SCHOOL | 8 | Mbombela | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 268407 | 2684077 | 2952484 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207728 | MDOE/MAIN/13/22-23 | Mpumalanga | Mogoroshi Secondary School | 800035008 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-04-01 |  | 2024-03-31 |  |  | 0 | 3487158 | 3487158 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207729 | DPWRT/MAIN/040/20MP | Mpumalanga | Lovunywa Secondary School | 800010710 | Nkomazi | Practical Completion (100%) | Active - Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 358407 | 3584077 | 3942484 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207730 | MDOE/MAIN/11/22-23 | Mpumalanga | Malwana Primary School | 800035030 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 265830 | 1898789 | 2164619 | Education Infrastructure Grant | Maintenance and Repairs
|  | 207731 | MDOE/MAIN/036/22 | Mpumalanga | Mapetekoane Primary School | 800035003 | Bushbuckridge | Project Initiation | Active - Not Contracted | 2022-01-04 |  | 2025-01-04 |  |  | 39855 | 398556 | 438411 | Education Infrastructure Grant | Maintenance and Repairs
|  | 208013 | LE22DOE00002 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Not Contracted | 2020-04-01 | 2022-04-02 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 0 | 6000000 | 6000000 | Equitable Share | Maintenance and Repairs
|  | 208174 | DOE/NEWECD/DSD /ECD1 | KwaZulu-Natal | Ethekwini South ECD Farm Centre Intervention project | ECD1 | eThekwini | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 100000 | 400000 | 500000 | Equitable Share | New or Replaced Infrastructure
|  | 208176 | DOE/NEWECD/DSD /ECD2 | KwaZulu-Natal | Ethekwini North ECD Farm Centre Intervention project | ECD2 | eThekwini | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 100000 | 400000 | 500000 | Equitable Share | New or Replaced Infrastructure
|  | 208177 | DOE/NEWECD/DSD /ECD3 | KwaZulu-Natal | King Cetshwayo ECD Farm Centre Intervention project | ECD3 | Mthonjaneni | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 350000 | 400000 | Equitable Share | New or Replaced Infrastructure
|  | 208186 | DOE/NEWECD/DSD /ECD4 | KwaZulu-Natal | Umzinyathi ECD Farm Centre Intervention project | ECD4 | Endumeni | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208190 | DOE/NEWECD/DSD /ECD5 | KwaZulu-Natal | Ugu ECD Farm Centre Intervention project | ECD5 | Ray Nkonyeni | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208192 | DOE/NEWECD/DSD /ECD6 | KwaZulu-Natal | Umkhanyakude ECD Farm Centre Intervention project | ECD6 | Umhlabuyalingana | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208193 | DOE/NEWECD/DSD /ECD7 | KwaZulu-Natal | Zululand ECD Farm Centre Intervention project | ECD7 | Abaqulusi | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 100000 | 300000 | 400000 | Equitable Share | New or Replaced Infrastructure
|  | 208195 | DOE/NEWECD/DSD /ECD8 | KwaZulu-Natal | Edumbe ECD | ECD8 | eDumbe | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 534500 | 1000000 | 1534500 | Equitable Share | New or Replaced Infrastructure
|  | 208196 | DOE/NEWECD/DSD /ECD9 | KwaZulu-Natal | Umgungundlovu ECD Farm Centre Intervention project | ECD9 | Mpofana | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208197 | DOE/NEWECD/DSD /ECD10 | KwaZulu-Natal | Ilembe ECD Farm Centre Intervention project | ECD10 | Mandeni | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 150000 | 350000 | 500000 | Equitable Share | New or Replaced Infrastructure
|  | 208198 | DOE/NEWECD/DSD /ECD11 | KwaZulu-Natal | Uthukela ECD Farm Centre Intervention project | ECD11 | Okhahlamba | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208199 | DOE/NEWECD/DSD /ECD12 | KwaZulu-Natal | Amajuba ECD Farm Centre Intervention project | ECD12 | Newcastle | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208200 | DOE/NEWECD/DSD /ECD13 | KwaZulu-Natal | Ixopo ECD | ECD13 | Ubuhlebezwe | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 534500 | 1000000 | 1534500 | Equitable Share | New or Replaced Infrastructure
|  | 208201 | DOE/NEWECD/DSD /ECD14 | KwaZulu-Natal | Umzimkhulu ECD | ECD14 | Umzimkhulu | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 534500 | 1000000 | 1534500 | Equitable Share | New or Replaced Infrastructure
|  | 208202 | DOE/NEWECD/DSD /ECD15 | KwaZulu-Natal | Greater Kokstad ECD | ECD15 | Greater Kokstad | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 534500 | 1000000 | 1534500 | Equitable Share | New or Replaced Infrastructure
|  | 208203 | DOE/NEWECD/DSD /ECD16 | KwaZulu-Natal | Harry Gwala ECD Farm Centre Intervention project | ECD16 | Ubuhlebezwe | Tender | Active - Not Contracted | 2022-04-01 |  | 2025-03-31 |  |  | 50000 | 150000 | 200000 | Equitable Share | New or Replaced Infrastructure
|  | 208231 | DOE/MNG/DSD/ECD17 | KwaZulu-Natal |  |  |  | Other - Packaged Ongoing Project | Active - Not Contracted | 2022-04-01 |  | 2023-03-31 |  |  | 0 | 15505000 | 15505000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208492 | ECD MAINTENANCE | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Contracted | 2022-04-01 | 2022-04-02 | 2030-03-31 | 2023-03-31 | 2030-03-31 | 0 | 15879000 | 15879000 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208493 | ES REFURB | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Not Contracted | 2022-04-01 | 2022-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 200000000 | 200000000 | Equitable Share | Rehabilitation, Renovations & Refurbishment
|  | 208494 | LE23ECDSEKHU 1 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 2095095 | 2095095 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208502 | LE23ECDWATERBERG 1 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 899896 | 899896 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208506 | re-use also | Limpopo | MASISI ECD FACILITY | LE23ECD00072 | Musina | Construction 1% - 25% | Active - Contracted | 2022-04-01 | 2022-05-02 | 2023-03-01 | 2023-03-15 | 2023-03-31 | 0 | 2843657 | 2843657 | ECD Infrastructure Component | New or Replaced Infrastructure
|  | 208508 | LE23ECDMOPANI CLUSTER 1 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 2336195 | 2336195 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208517 | LE23ECDMOPANI CLUSTER 2 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 2004369 | 2004369 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208525 | LE23ECDCAPRICORN CLUSTER 1 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 1785340 | 1785340 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208532 | LE23ECDCAPRICORN CLUSTER 2 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 1763938 | 1763938 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208539 | LE23ECDVHEMBE 1 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-03-31 |  |  | 0 | 2075635 | 2075635 | ECD Infrastructure Component | Maintenance and Repairs
|  | 208547 | LE23ECDVHEMBE 2 | Limpopo |  |  |  | Other - Packaged Ongoing Project | Active - Contracted | 2022-06-01 |  | 2023-04-30 |  |  | 0 | 2921285 | 2921285 | ECD Infrastructure Component | Maintenance and Repairs
|  | 212139 | LE22IDT00002 | Limpopo | Monala Primary | 921111481 | Mogalakwena | Construction 1% - 25% | Active - Contracted | 2021-04-01 | 2022-02-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 5152719 | 20610876 | 25763595 | Education Infrastructure Grant | Upgrading and Additions
|  | 212140 | LE6SFURN2223 | Limpopo | LDOE HEAD OFFICE | LP08000 | Polokwane | Construction 1% - 25% | Active - Contracted | 2020-04-01 | 2020-04-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 0 | 100000 | 100000 | Education Infrastructure Grant | Non-Infrastructure
|  | 212141 | LE20LDOE0002 | Limpopo | HEAD OFFICE | LP800 | Polokwane | Project Initiation | Active - Not Contracted | 2022-02-05 |  | 2025-03-31 |  |  | 4000000 | 16000000 | 20000000 | Education Infrastructure Grant | Maintenance and Repairs
|  | 212142 | LE21TMT17166 | Limpopo | DAVID MUTSHINYALO SECONDARY | 929311564 | Thulamela | Tender | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1233602 | 4934408 | 6168010 | Education Infrastructure Grant | Upgrading and Additions
|  | 212143 | LE20TMT17039 | Limpopo | Serupa Primary | 921141246 | Mogalakwena | Tender | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1238598 | 4954390 | 6192988 | Education Infrastructure Grant | Upgrading and Additions
|  | 212144 | LE21TMT17184 | Limpopo | MODUME PRIMARY | 913420413 | Ba-Phalaborwa | Feasibility | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1222326 | 4889302 | 6111628 | Education Infrastructure Grant | Upgrading and Additions
|  | 212145 | LE21TMT17198 | Limpopo | Sebakanaga Secondary | 996606603 | Elias Motsoaledi | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1222326 | 4889302 | 6111628 | Education Infrastructure Grant | Upgrading and Additions
|  | 212146 | LE20TMT17054 | Limpopo | Tutwana Primary | 922221609 | Polokwane | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1222326 | 4889302 | 6111628 | Education Infrastructure Grant | Upgrading and Additions
|  | 212147 | LE20TMT17062 | Limpopo | Leeupoort Laerskool | 910130635 | Thabazimbi | Construction 1% - 25% | Active - Not Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1222326 | 4889302 | 6111628 | Education Infrastructure Grant | Upgrading and Additions
|  | 212148 | LE20TMT17066 | Limpopo | Mphanama Primary | 925610506 | Greater Tubatse/Fetakgomo | Tender | Active - Not Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 8148837 | 8148837 | Education Infrastructure Grant | Upgrading and Additions
|  | 212149 | LE21TMT17194 | Limpopo | Phuti Makibelo Primary School | 922221302 | Polokwane | Design | Active - Not Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 8148837 | 8148837 | Education Infrastructure Grant | Upgrading and Additions
|  | 212150 | LE20TMT17050 | Limpopo | Tlakale Mashashane Secondary School | 922221586 | Polokwane | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 8148837 | 8148837 | Education Infrastructure Grant | Upgrading and Additions
|  | 212151 | LE20TMT17034 | Limpopo | ABRAHAM SEROTE SECONDARY - | 924650160 | Elias Motsoaledi | Feasibility | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 7130233 | 7130233 | Education Infrastructure Grant | Upgrading and Additions
|  | 212152 | LE20TMT17064 | Limpopo | HAROLD RHUDZANI PRIMARY SCHOOL | 9055332066 | Makhado | Tender | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 7130233 | 7130233 | Education Infrastructure Grant | Upgrading and Additions
|  | 212153 | LE20TMT17036 | Limpopo | Masete Primary School | 920331964 | Blouberg | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2037209 | 8148838 | 10186047 | Education Infrastructure Grant | Upgrading and Additions
|  | 212154 | LE21TMT17199 | Limpopo | Sekete Secondary | 992201202 | Polokwane | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 46575 | 2041953 | 2088528 | Education Infrastructure Grant | Upgrading and Additions
|  | 212155 | LE20TMT17057 | Limpopo | Ditlalemeso Secondary School | 923242217 | Greater Tzaneen | Construction 1% - 25% | Active - Not Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212156 | LE21TMT17176 | Limpopo | Magaingwana Primary School | 926540737 | Maruleng | Construction 1% - 25% | Active - Not Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212157 | LE21TMT17189 | Limpopo | MUNAU PRIMARY | 928332219 | Makhado | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212158 | LE20TMT17033 | Limpopo | VUTIVI PRIMARY SCHOOL | 993303101 | Makhado | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212159 | LE20TMT17067 | Limpopo | Namakgale Primary | 913420444 | Ba-Phalaborwa | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212160 | LE20TMT17060 | Limpopo | Pfumbada Primary | 928330015 | Thulamela | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212161 | LE21TMT17167 | Limpopo | Duvhuledza Primary | 930360511 | Thulamela | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212162 | LE21TMT17169 | Limpopo | Hovheni Primary | 915540553 | Greater Tzaneen | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212163 | LE21TMT17197 | Limpopo | Sango Combined | 928330015 | Elias Motsoaledi | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212164 | LE20TMT17008 | Limpopo | J.K. TABANE HIGH SCHOOL | 923260239 | Lepele-Nkumpi | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212165 | LE20TMT17065 | Limpopo | King Nchabeleng Secondary School | 996606500 | Greater Tubatse/Fetakgomo | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212166 | LE21TMT17175 | Limpopo | Madobi Primary | 912520542 | Collins Chabane | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212167 | LE21TMT17179 | Limpopo | MATAMELA PRIMARY SCHOOL | 930320940 | Collins Chabane | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212168 | LE20TMT17046 | Limpopo | Mmatshipi High | 904220910 | Polokwane | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212169 | LE21TMT17180 | Limpopo | Matome Modika Secondary | 915510583 | Polokwane | Feasibility | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212170 | LE22ITRU00002 | Limpopo | LDOE HEAD OFFICE ITRU SERVICES | 0 | Polokwane | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 13602505 | 54410018 | 68012523 | Education Infrastructure Grant | Non-Infrastructure
|  | 212171 | LE20TMT17023 | Limpopo | Seboeng Primary School | 925661177 | Makhuduthamaga | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212172 | LE21TMT17196 | Limpopo | Rehlahleng Special School | 996606318 | Greater Tubatse/Fetakgomo | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212173 | LE21TMT17191 | Limpopo | Ntsedzeni Secondary | 930361088 | Thulamela | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212174 | LE21TMT17188 | Limpopo | Mukula Secondary | 930351302 | Thulamela | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212175 | LE21TMT17174 | Limpopo | Loboli Secondary | 924650627 | Elias Motsoaledi | Construction 1% - 25% | Active - Not Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 325818 | 1303272 | 1629090 | Education Infrastructure Grant | Upgrading and Additions
|  | 212176 | LE21TMT17187 | Limpopo | Muila Primary | 931340159 | Makhado | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212177 | LE21TMT17185 | Limpopo | Mogologolo Primary | 184/397/6 | Lepele-Nkumpi | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212178 | LE21TMT17183 | Limpopo | MAZWE SEC | 921110594 | Lephalale | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 2036364 | 2036364 | Education Infrastructure Grant | Upgrading and Additions
|  | 212179 | LE20TMT17061 | Limpopo | ST Gregories College | 996606535 | Elias Motsoaledi | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 1018605 | 4074418 | 5093023 | Education Infrastructure Grant | Upgrading and Additions
|  | 212180 | LE21TMT17177 | Limpopo | MAHLASHI PRIMARY SCHOOL | 92560442 | Greater Tubatse/Fetakgomo | Design | Active - Not Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212181 | LE21TMT17178 | Limpopo | MAKONDE PRIMARY SCHOOL | 930350248 | Collins Chabane | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212182 | LE20TMT17038 | Limpopo | Maragane Primary School | 921230279 | Makhuduthamaga | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212183 | LE21TMT17181 | Limpopo | Matsiri Mokgokong Primary | 922220576 | Polokwane | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212184 | LE21TMT17186 | Limpopo | Mphakati Primary | 911360283 | Collins Chabane | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212185 | LE21TMT17168 | Limpopo | Eureka Primary | 923260178 | Lepele-Nkumpi | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 815884 | 3259535 | 4075419 | Education Infrastructure Grant | Upgrading and Additions
|  | 212186 | LE21TMT17190 | Limpopo | Ndaedzo Secondary | 930320230 | Thulamela | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212187 | LE21TMT17192 | Limpopo | NTSHOENG PRIMARY SCHOOL | 924651873 | Ephraim Mogale | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212188 | LE20TMT17063 | Limpopo | Itshomeleng Primary School | 905340562 | Molemole | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 815884 | 3259535 | 4075419 | Education Infrastructure Grant | Upgrading and Additions
|  | 212189 | LE21TMT17171 | Limpopo | Kgahlana Morulana Secondary | 924640354 | Makhuduthamaga | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 815884 | 3263535 | 4079419 | Education Infrastructure Grant | Upgrading and Additions
|  | 212190 | LE21TMT17193 | Limpopo | NYAKU SECONDARY SCHOOL | 925631572 | Greater Tubatse/Fetakgomo | Design | Active - Contracted | 2022-05-01 |  | 2025-06-30 |  |  | 0 | 3054545 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212191 | LE21TMT17172 | Limpopo | Kgolokgotlha Ledwaba Secondary | 922220354 | Polokwane | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 815884 | 3263535 | 4079419 | Education Infrastructure Grant | Upgrading and Additions
|  | 212192 | LE21TMT17200 | Limpopo | TLHABELENI PRIMARY SCHOOL | 918512190 | Greater Letaba | Design | Active - Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3045545 | 3045545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212193 | LE20TMT17069 | Limpopo | Moratiwa Primary | 996606319 | Makhuduthamaga | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 814884 | 3259535 | 4074419 | Education Infrastructure Grant | Upgrading and Additions
|  | 212194 | LE21TMT17165 | Limpopo | C.M Sehlapelo Primary | 922220125 | Polokwane | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 610909 | 2443636 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212195 | LE21TMT17173 | Limpopo | Kolokoshani Secondary School | 930321141 | Makhado | Project Initiation | Active - Not Contracted | 2022-02-01 |  | 2025-03-31 |  |  | 610909 | 2443636 | 3054545 | Education Infrastructure Grant | Upgrading and Additions
|  | 212196 | LE18DBS09004 | Limpopo | RAMATAU SECONDARY | 926540386 | Maruleng | Construction 51% - 75% | Active - Contracted | 2018-02-01 | 2018-04-01 | 2023-03-31 | 2023-03-01 | 2023-03-01 | 3472525 | 13890102 | 17362627 | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment
|  | 212197 | LE20TMT17040 | Limpopo | Akani Secondary School | 912520016 | Collins Chabane | Design | Active - Not Contracted | 2022-05-01 |  | 2024-06-30 |  |  | 0 | 3972558 | 3972558 | Education Infrastructure Grant | Upgrading and Additions
|  | 212198 | ECD/2022/223 | Mpumalanga |  |  |  | Other - Packaged Ongoing Project | Proposed | 2022-07-21 |  | 2024-03-31 |  |  | 675029 | 12498101 | 13173130 | ECD Infrastructure Component | Maintenance and Repairs
|  | 212230 | LE21DOE00216 | Limpopo | Ramohlakano Primary | 920211497 | Blouberg | Construction 1% - 25% | Active - Contracted | 2022-02-01 | 2022-04-01 | 2023-03-31 | 2023-03-01 | 2023-03-01 | 76517 | 3060692 | 3137209 | Education Infrastructure Grant | Upgrading and Additions