## Sheet1
ANNEXURE A: 2014/15 - GAUTENG PROJECTS
FINANCIAL YEAR | CLIENT DEPT | PROVINCE | OFFICE | MUNICIPALITY | TOWN | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | FIRST DELIVERY DATE | CONTRACT PERIOD | CONTRACTOR LATEST ALLOCATION | CONTRACTOR EXPENDITURE PREVIOUS YEARS | CONTRACTOR EXPENDITURE CURRENT YEAR | CONTRACTOR CASH FLOW AMOUNT | CONSULTANT AUTHORISATION | CONSULTANT LATEST ALLOCATION | CONSULTANT EXPENDITURE PREVIOUS YEARS | CONSULTANT EXPENDITURE CURRENT YEAR | CONSULTANT CASH FLOW AMOUNT | ALLOCATION | EXPENDITURE
2014 | ARTS AND CULTURE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | ARCHIVES BUILDING | HERITAGE - UPGRADING OF FIRE PROTECTION SYSTEM AND REFURBISH MENT OF HVA C AND RELATED INSTALLATIONS | 048495 | 5B | 2013/01/08 | 2014/07/07 | 18 | 56000000 | 65036570.43 | 26841132.63 | 198921732.52 | 22266685.75 | 1083442 | 11934924.92 | 1774851.52 | 22266685.75 | 57083442 | 28615984.15
2014 | CORRECTIONAL SERVICES | GAUTENG | JOHANNESBURG | SEDIBENG DISTRICT MUNICIPALITY | HEIDELBERG (GAUTENG) | PRISON | NEW SCHOOL WITH CLASSROOM AND LIBRARY | 032538 | 5B | 2014/03/14 | 2015/03/27 | 10 | 2000000 | 0 | 3399351.01 | 5798369.2 | 2528582.01 | 0 | 1176838.11 | 592741.97 | 2528582.01 | 2000000 | 3992092.98
2014 | CORRECTIONAL SERVICES | GAUTENG | JOHANNESBURG | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG | PRISON | LEEUWKOP:PRISON:REPLACEMENT OF BOILERS AND MAINTENANCE OF BOILERS FOR THE PERIOD OF 24 MONTHS | 047918 | 5B | 2012/01/25 | 2014/06/05 | 24 | 7000000 | 12650296.44 | 0 | 21796400.29 | 3700000 | 439180 | 2815087.05 | 76017.57 | 3700000 | 7439180 | 76017.57
2014 | DEFENCE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | AIR DEFENCE ARTILLERY GROUP | ADA FORMATION: DEQUAR ROAD: BARRIER FREE PROJECT FOR PEOPLE WITH DISABILITIES: BUILDING H3: ONE OUTDOOR PLATFORM LIFT, C ONVERTION OF TOILETS AND RAMPS / PATHWAYS | 046324 | 6A | 2013/11/22 | 2015/03/06 | 8 | 2069550 | 0 | 1971001.62 | 2299500 | 919463.21 | 220994 | 400877.3 | 417499.85 | 919463.21 | 2290544 | 2388501.47
2014 | DEFENCE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | MILITARY HOSPITAL | 1 MILITARY HOSPITAL : UPGRADE OF UNINTERRUPTED POWER SUPPLY (UPS) | 054105 | 5B | 2015/01/27 | 2015/03/26 | 2 | 0 | 0 | 4306094.64 | 5517530.46 | 83000 | 0 | 0 | 0 | 83000 | 0 | 4306094.64
2014 | HOME AFFAIRS | GAUTENG | JOHANNESBURG | EKURHULENI METROPOLITAN MUNICIPALITY | BRAKPAN | STATE BUILDINGS AND HOUSING | BRAKPAN: DHA DISTRICT OFFICE: R & R OF EXISTING BLD ON CNR V OORTREKKER/HIGH STR | 046109 | 6A | 2012/06/20 | 2014/11/05 | 12 | 1212449 | 12395954.27 | 1846557.01 | 14275497.65 | 3510548.18 | 1151288 | 2246921.42 | 608712.45 | 3510548.18 | 2363737 | 2455269.46
2014 | HOME AFFAIRS | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA |  | DHA: NEW CORPORATION BUILDING: POWER DISTRIBUTION AND OTHER RELATED WORK. | 047441 | 6A | 2011/09/06 | 2014/09/12 | 6 | 1711143 | 10267699.23 | 3920173.71 | 14138608.22 | 4700000 | 0 | 2895369.62 | 747031.88 | 4700000 | 1711143 | 4667205.59
2014 | HOME AFFAIRS | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | CO-OPERATION BUILDING | DHA NEW CORPORATION BUILDING: REFURBISHMENT OF 13TH FLOOR | 050666 | 6A | 2013/10/09 | 2014/08/08 | 6 | 1400000 | 2021286.66 | 2219165.38 | 4240452.04 | 762870.7 | 92402 | 453532.14 | 92401.97 | 762870.7 | 1492402 | 2311567.35
2014 | HOME AFFAIRS | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | CO-OPERATION BUILDING | REPLACEMENT OF LIFTS AT BVR | 049589 | 5B | 2014/01/05 | 2014/07/08 | 6 | 1000000 | 0 | 1986075.89 | 3121512.59 | 170000 | 26807 | 131456.25 | 0 | 170000 | 1026807 | 1986075.89
2014 | RURAL DEVELOPMENT AND LAND REFORM | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | OLD CO-OPERATION BUILDING | HERITAGE - REPLACEMENT OF LIFTS | 050723 | 6A | 2013/06/05 | 2014/06/06 | 10 | 1124490 | 1912979.01 | 1083823.4 | 3305322.62 | 343332.8 | 87844 | 232262.75 | 110095.44 | 343332.8 | 1212334 | 1193918.84
2014 | SA POLICE SERVICE | GAUTENG | JOHANNESBURG | SEDIBENG DISTRICT MUNICIPALITY | DIEPSLOOT | POLICE STATION AND SINGLE QUARTERS | CONSTRUCTION_OF POLICE STATION | 024322 | 5B | 2013/02/14 | 2015/02/20 | 18 | 0 | 69025424.91 | 0 | 59348731.69 | 15837305.73 | 2000000 | 9796131.83 | 2851044.96 | 15837305.73 | 2000000 | 2851044.96
2014 | SA POLICE SERVICE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA |  | BON ACCORD: NATIONAL INTERVENTION UNIT: LAVENDER RD | 030805 | 5B | 2013/01/08 | 2015/01/16 | 24 | 2394457 | 19176894.9 | 2842106.6 | 127428694.98 | 34764001.01 | 2211414 | 25177909.58 | 2984935.42 | 34764001.01 | 4605871 | 5827042.02
2014 | SA POLICE SERVICE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | CENTRAL POLICE STATION AND SINGLE QUARTERS | SEALING OF ROOF OF RESIDENTIAL BLOCK,REPLACEMENT OF DOWN PIP ES AND UPGRADING OF WET SERVICES | 039074 | 5B | 2012/07/02 | 2014/12/04 | 9 | 5616075 | 8572681.27 | 2376978.26 | 16264755.63 | 6640957.31 | 200000 | 3530118.96 | 541587.77 | 6640957.31 | 5816075 | 2918566.03
[8 empty] | 13 |  |  |  |  | 81528164 | 201059787.12 | 52792460.15 | 476457107.89 | 96226746.7 | 7513371 | 60791429.93 | 10796920.8 | 96226746.7 | 89041535 | 63589380.95