## Sheet1
ANNEXURE C: 2016/17 - GAUTENG PROJECTS
FINANCIAL YEAR | CLIENT DEPT | PROVINCE | OFFICE | MUNICIPALITY | TOWN | SUBURB | COMPLEX | DESCRIPTION | WCS NO | STATUS | FINANCIAL TENDER DATE | FIRST DELIVERY DATE | CONTRACT PERIOD | CONTRACTOR LATEST ALLOCATION | CONTRACTOR EXPENDITURE PREVIOUS YEARS | CONTRACTOR EXPENDITURE CURRENT YEAR | CONTRACTOR CASH FLOW AMOUNT | CONSULTANT AUTHORISATION | CONSULTANT LATEST ALLOCATION | CONSULTANT EXPENDITURE PREVIOUS YEARS | CONSULTANT EXPENDITURE CURRENT YEAR | ALLOCATION | EXPENDITURE
2016 | ARTS AND CULTURE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA |  | NATIONAL LIBRARY OF SOUTH AFRICA | HERITAGE - OLD BUILDING: REMEDIAL WORK | 047073 | 5B | 2012/08/29 | 2017/03/29 | 24 | 46133782 | 39992095.58 | 45678054.08 | 97113735.31 | 19051281.75 | 2800000 | 13724053.08 | 1522288.56 | 48933782 | 47200342.64
2016 | CORRECTIONAL SERVICES | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | BAVIAANSPOORT | PRISON | INSTALLATION OF A NEW STANDBY GENERATOR | 053863 | 6A | 2016/09/30 | 2017/01/25 | 6 | 1000000 | 0 | 1151478.03 | 1272940.16 | 382000 | 171285 | 28042.29 | 330770.26 | 1171285 | 1482248.29
2016 | DEFENCE | GAUTENG | JOHANNESBURG | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG |  |  | UPGRADING OF KITCHEN EQUIPMENT,,ASB | 053688 | 5B | 2016/06/22 | 2016/12/22 | 6 | 1500000 | 0 | 1808554.2 | 2314936.36 | 300000 | 100000 | 67124.71 | 0 | 1600000 | 1808554.2
2016 | JUSTICE AND CONSTITUTIONAL DEVELOPMENT | GAUTENG | JOHANNESBURG | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | JOHANNESBURG |  | HIGH COURT | ADDITIONAL ACCOMMODATION: CONVERSION TO THE 7 AND 9 TO 12 FL OORS | 041546 | 6A | 2009/03/20 | 2016/11/29 | 30 | 18400000 | 394940784.21 | 36251965.31 | 440493492.11 | 69685985.56 | 3600000 | 60770806.76 | 4906309.62 | 22000000 | 41158274.93
2016 | JUSTICE AND CONSTITUTIONAL DEVELOPMENT | GAUTENG | JOHANNESBURG | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | VARIOUS CENTRES (GTJ) |  | MAGISTRATE'S OFFICE | CONSTRUCTION OF FACILITIES FOR PEOPLE WITH DISABILITIES:GROU P4:KRUGERSDORP,KHUTSONG | 054067 | 6A | 2015/11/20 | 2016/08/15 | 6 | 582400 | 0 | 1059708.66 | 1129135.8 | 340014.67 | 72000 | 165351.2 | 108081.49 | 654400 | 1167790.15
2016 | JUSTICE AND CONSTITUTIONAL DEVELOPMENT | GAUTENG | JOHANNESBURG | CITY OF JOHANNESBURG METROPOLITAN MUNICIPALITY | VARIOUS CENTRES (GTJ) |  | MAGISTRATE'S OFFICE | CONSTRUCTION OF FACILITIES FOR PEOPLE WITH DISABILITIES:GROU P2:TEMBISA,MEADOWLANDS,KLIPTOWN | 054047 | 5B | 2015/12/15 | 2016/08/15 | 6 | 320000 | 0 | 1400502.31 | 1673395.62 | 472880.85 | 96000 | 218933.83 | 148050.87 | 416000 | 1548553.18
2016 | JUSTICE AND CONSTITUTIONAL DEVELOPMENT | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | MAMELODI |  | MAGISTRATE'S OFFICE | CONSTRUCTION OF A NEW BUILDING | 044028 | 5B | 2013/11/20 | 2017/01/19 | 30 | 32000000 | 41106624.54 | 48227601.63 | 112147259.68 | 36023566.56 | 4400000 | 17161396.81 | 4260781.97 | 36400000 | 52488383.6
2016 | SA POLICE SERVICE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA |  | CENTRAL POLICE STATION AND SINGLE QUARTERS | SEALING OF ROOF OF RESIDENTIAL BLOCK,REPLACEMENT OF DOWN PIP ES AND UPGRADING OF WET SERVICES | 039074 | 6A | 2012/07/02 | 2016/12/13 | 9 | 1252703 | 15473077.64 | 1176186.63 | 16725780.7 | 9229517.11 | 500000 | 5508035.86 | 1814004.24 | 1752703 | 2990190.87
2016 | SA POLICE SERVICE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | CENTURION | ERASMIA | POLICE STATION | SAPS: ERASMIA: CONNECTION OF SERVICES TO ERVEN 656 & 657 | 050143 | 5B | 2013/03/25 | 2016/12/09 | 6 | 3000000 | 13164034.93 | 2276662.54 | 17472393.17 | 5703971.89 | 800000 | 4340502.15 | 227791.76 | 3800000 | 2504454.3
2016 | SA POLICE SERVICE | GAUTENG | PRETORIA | CITY OF TSHWANE METROPOLITAN MUNICIPALITY | PRETORIA | SILVERTON | FORENSIC LABORATORY | FORENSIC SCIENCE LABOROTORY: SILVERTONRIFD SMART SHELVES: IN STALLATION OF SOCKET POWER POINTS | 053705 | 5B | 2016/02/02 | 2016/08/01 | 6 | 425505 | 0 | 394250 | 605505.37 | 160751.4 | 58824 | 101927.4 | 57554.04 | 484329 | 451804.04
[14 empty] | 104614390 | 504676616.9 | 139424963.39 | 690948574.28 | 141349969.79 | 12598109 | 102086174.09 | 13375632.81 | 117212499 | 152800596.2