## 23 April 2020 (hidden)
NCC COVID 19 PROJECT PROGRESS REPORT NO.18 - 23 APRIL 2020
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
1 | Western Cape | Tanks | 504 | 4500211013 | Nel Tanks cc | 410 | 433 | 40 | 21 | 37 | 0 | Complete
|  |  |  | 4500211001 | Jojo Tanks | 182 | 182 | 0 | 0 | 0 | 0 | Complete | Last 34 delivered today
|  | Tankers | 18 | 4500211025 | MidMar Plant Hire | 18 | 18 | N/A | N/A | 15 | 0 | Complete | Tanker Purchase order funds will be depleted by this week. 3 x Trucks already off-hired
| Challenges | Tanker order will be depleted by the end of this week.
Effective utlisation fo Tankers as requested by the Province as some Tankers has been standing for more than a week - not being utilised!
City of Cape Town Assignment Agreements still not signed by Rand Water & awaiting City of Cape Town's implementation Plan: Programme to do the installation of the 214 x Tanks!
In some areas where Tanks where delivered the Municipality indicated that is will only be used on a contigency basis, as their informal settlement areas have either access to Tap stands and or existing Tanks installed (Hermanus; Lambert's Bay; Plettenberg Bay)
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
2 | Eastern Cape | Tanks | 129 | 4500211001 | Jojo Tanks | 129 | 129 | 58 | 0 | 0 | 0 | All delivered | The payment for 129 has been processed for this work.
The Agreement with Amathole water to be finalized
0
|  | Tankers | 0 |  |  |  |  | N/A | N/A |  |  |  | 30 Tankers committed . Still at SCM
| Challenges | No approved Assignment Agreements in-place i.e. Ceding the Tank Installation Works
Information from DWS that 58 tanks have been installed is yet to be verified by the M& Es .
1 tank has been stolen. Case no is 56/4/2020. Matter with the Police
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | N/A | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
3 | Northern Cape | Tanks | 391 | 4500211060 | Griekwaland Wes Korporate | 145 | 55 | 147 | 0 | 0 | 90 | TBC
|  |  |  | 4500211001 | Jojo Tanks | 201 | 201 |  | 0 | 0 | 0 | TBC
|  | Tankers | 30 |  | Mulalo | 10 | 10 | N/A | N/A | 10 | 0 | All Delivered | Operating from 6 April
[5 empty] | Luhlavana | 10 | 10 | N/A | N/A | 10 | 0 | All Delivered | Operating from 5 April
[5 empty] | Keeme Trading | 13 | 13 | N/A | N/A | 13 | 0 |  | Operating from 3 April
| Challenges | Assigned Supplier for NC didn’t quote for the tanks installation
GWK are reluctant to deliver before payment and DWS rep has requested we cancel and reassign the rest of the order
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
4 | North West | Tanks | 600 | 4500211017 | Thoka Geosciences | 600 | 733 | 470 | 3 | 258 | 0 | All Delivered | Over delivery due to initial tanks delivered to Bojanala, which exceeded its allocation due to cancellation of service provider. No more deliveries to be done.
|  |  |  | 4500211076 | Daneesa
|  |  |  | 4500211009 | Loxiontym Investment
|  | Tankers | 30 | 4500210998 | Aqua Transport and Plant Hire | 50 | 50 | N/A | N/A | 50 | 0 | All Delivered | 50 Tankers have been delivered
|  |  |  | 4500211021 | Storky Consulting
|  |  |  | 4500211086 | Belgium
| Challenges | SED issues for construction of tank stands
Awaiting approved Assignements Agreements
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
5 | Free State | Tanks | 400 | 4500211001 | Jojo Tanks | 120 | 120 | 120 | 0 | 0 | 0 | All delivered | 120 tanks have been delivered to various areas in Free State, composed of 118 x5.25kl and 2 x10kl. Invoices received and are being paid. Confirmation of delivery of tanks outstanding from RH. Assignment agreement with water boards required for construction of tank stands.
|  |  |  | 4500211019 | IMPOQO Trading CC | 180 | 180 | 180 | 0 | 0 | 0 | All delivered | 180 tanks delivered composed of 80 x 10kl, 50 x5kl and 50x2.5kl. All tanks are temporarily installed and operational. Steel material for fabricating tank stands can only be sourced after lockdown. Estimated completion of tank stands 14 days after lockdown (20 May 2020). Purchase Order to be adjusted for the additional 30x10kl tanks delivered. Approval of payment received from RH. Invoice submitted for payment.
|  |  |  | 4500211088 | TLG Commercial Sourcing | 100 | 100 | 96 | 0 | 0 | 0 | All delivered | 100 x 5kl tanks have been delivered to various areas in Free State. Construction of tank stands outstanding. Contractor engaging municipalities to provide local people who can assist with construction of tank stands. It is anticipated that construction and installation of tanks will be completed by the 30th April 2020, subject to availability of material.
|  | Tankers | 40 | 4500210987 | Xmoor Transport | 40 | 40 | N/A | N/A | 40 | 0 | All delivered | All 40 x 10kl tankers have been delivered to various areas in FS. The purchase order was for 40 tankers and Xmoor supplied additional 21 tankers to other areas as requested by RW. Purchase Order to be adjusted. Cleanliness Certificates submitted to RW.
|  |  | 8 | 4500211079 | SEDTRADE | 8 | 8 | N/A | N/A | 8 | 0 | All delivered | All 8 x water tankers have been deployed to various areas of FS. Cleanliness Certificates submitted to RW
|  |  | 10 | 4500211021 | Storky Consulting | 10 | 0 | N/A | N/A | 0 | 0 | cancelled | Supplier failed to deploy tankers and order was terminated
| Challenges | Due to the urgent need for water ,FS is not constructing tanks stands but doing temporary installation to get the tanks operational
Quantities delivered not aligned with the Order
Delays with construction of tank stands due to unavailability of material
Assignment agreement with Water Boards required
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
6 | Limpopo | Tanks | 625 | 4500211001 | JoJo Tanks | 635 | 440 | 0 | 190 | 218 | 195 | 2020-04-24 | Quantities of ordered tanks increased from 625 to 635. Construction of stands in progress. 190 tank stands constructed to date and 201 tanks installed.
|  | Tankers | 34 | 4500211021 | Storky Consulting | 34 | 34 | N/A | N/A | 34 | 0 |  | All tankers were in operation
|  |  |  | 4500210998 | Aqua Transport and Plant
| Challenges | Assignment agreement not signed by PH yet.
Quantities for Jojo tanks increased to 635
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
7 | Gauteng | Tanks | 412 | 4500211001 | Jojo Tanks | 406 | 406 | 169 |  | 15 | 0 | All delivered | Variation orders to be raised for stands construction
|  |  | 240 | 4500211010 | Pabi n Sbu Holdings | 57 | 57 |  | 36 | 21 | 0 | All delivered | Construction of stands in progress
|  |  | 60 | 4500211026 | Zenzo Projects | 60 | 60 |  | 20 | 40 | 0 | All delivered | Construction of stands in progress. 40 stands costructed to date. There is a conflict with municipality on the remaining stands
|  |  | 3200 | 4500210999 | Osher Fuels | 3034 | 1284 | 383 | 998 | 286 | 1750 |  | Remaining deliveries awaiting PH to confirm areas.Total delivered revised due to 100 tanks diverted to another province. Construction of Stands in progress. Payment claim submitted and under review.
|  |  | 20 | 4500211016 | Melo Enterprise | 20 | 20 |  |  | 20 | 0 | All delivered | All tanks delivered and on the stands.
|  |  | 500 | 4500211112 | Thabzo Holdings | 500 |  |  |  |  | 500 |  | Awaiting PH for delivery areas
|  |  | 200 | 4500211078 | SGT Electrical | 200 |  |  |  |  | 200 | 23/04/2020 | PH has allocated delivery of 100 x 10KL tanks for now.
|  |  | 200 | 4500211088 | TLG Services | 100 |  |  |  |  | 100 |  | Awaiting PH for delivery areas. Order for GP chanegd to 100 due 100 tanks delivered at Bloemfontein.
|  | Tankers | 10 | 4500211080 | GS Fencing | 10 | 5 | N/A | N/A | 5 | 5 | All delivered | Supplier delivered 5x18KL instead of 10x10KL. 5 tankers passed water quality test and DWS instructed to use
|  |  | 2 | 4500211025 | Midmar plant | 2 | 2 | N/A | N/A | 2 | 0 | All delivered
|  |  | 30 | 4500210987 | X - Moor | 30 | 30 | N/A | N/A | 30 | 0 | All delivered
| Challenges | DWS still has not signed the ceeding agreement with Rand Water and this is causing a delay on construction of stands
Most tankers are failing water quality tests
Tanks are not numbered which complicates the verification process. Concern on safety of Rand Water staff doing verifications
No or slow response from Regional head to sign off delivery notes
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
8 | Mpumalanga | Tanks | 300 | 4500211078 | SGT Electrical | 300 | 307 | 0 | 129 | 39 | -7 | All delivered | 166 stands have been completed and 35 tanks have been installed.The contractor has started with the delivery of tanks from storages to their respective sites for installation. The expected completion date is 30 April 2020. An invoice has been submitted for payment on the 23rd of April 2020.
|  |  | 100 | 4500211111 | Mpangazitha Projects | 100 | 100 | 0 | 28 | 37 | 0 | All delivered | Construction of tank stands in progress, the contractor has completed 72 stands and installed 37 tanks . The expected completion date is 30 April 2020. An invoice has been submitted for payment on the 23rd of April 2020.
|  |  | 100 | 4500210999 | Mthethwa Power House | 100 | 100 | 0 | 0 | 100 | 0 | All delivered | The Contractor has completed all the work, they are now preparing supporting documents to the invoice. The invoice will be submitted later today the 23rd of April 2020.
|  |  | 100 | 4500211110 | Osher Fuels | 100 | 100 | 0 | 0 | 0 | 0 | All delivered | PH to allocate delivery areas.
|  |  | 24 | 450021109 | Zenzo Projects | 24 | 24 | N/A | N/A | 24 | 0 | All delivered | Trucks started operating on the 28th of March and the last batch started on the 31st of March 2020. The Contractor has submitted an invoice on the 20th of April 2020 , awaiting signed log sheets.
|  |  | 6 | 4500211089 | SibusisoSobuhle Trading | 6 | 6 | N/A | N/A | 6 | 0 | All delivered | Trucks started operating on the 6th of April 2020. The contractor has been requested to submit an invoice for the work done.
|  |  | 10 | 4500211070 | Basadi Peniel Trading | 10 | 10 | N/A | N/A | 10 | 0 | All delivered | Trucks started operating on the 7th and the last truck on the 8th of April 2020. The supplier is preparing an invoice for the work done..
|  |  | 6 | 4500211068 | Dinaledi Tsa Metsi Trading | 6 | 6 | N/A | N/A | 6 | 0 | All delivered | Trucks started operating on the 4th and the last truck on the 7th of April 2020. The supplier has been requested to submit an invoice for the work done. One truck has been removed from operaration due to non-compliance, no replacement yet.
|  |  | 3 | 4500211113 | Sihlangu Semnikati Trad | 3 | 3 | N/A | N/A | 3 | 0 | All delivered | 2 trucks started operating on the 6th of April and the last one on the 7th of April 2020. The contractor has been requested to submit an invoice for the work done.
|  |  | 10 | 4500211110 | Mthethwa Power House | 10 | 10 | N/A | N/A | 10 | 0 | All delivered | The first batch started on the 8th of April and the last one on the 13th of April 2020. The supplier will submit an invoice tomorrow the 23rd of april 2020.
| Challenges | Tanks storages very far from installation points
Delivery of tanks to their respective sites is not easy as areas are scattered, the truck drops one tank and drive a long distance to drop another tank and so forth.
Some municipalities are not keen to the approach of temporal instalations, they want to wait for complete installations.
Some warehouses ran out of bricks and concrete mixture.
Business Forums are demanding that suppliers buy building material from them.
In some areas warehouses require permits.
No | Province | Tanks/Tankers | Committed | Order No | Supplier Name | Ordered | Delivered | In Used - Temporary installation | Being constructed | Installed permanetly on the stands and Trucks in operation | Still to be delivered | Expected Delivery date of the rest | Comments
9 | KwaZulu Natal | Tanks | 1000 | 4500211009 | Loxiontym Investment | 1000 | 1000 | 25 | 125 | 0 | 0 | Complete | 1000 tanks of 2500 litres have been delivered to PMB and completed on the 15th April 2020. Checks on the last invoice being done. Two invoices have been verified in full.
|  | Tankers | 8 | 4500211028 | Kuyenzakala | 8 | 7 | N/A | N/A | 7 | 1 | 2020-04-24 | 7 tankers have been delivered on the 23rd April 2020. Ugu Municipality requested a tanker dedicated to them and not conducting other work for another supplier. The supplier has to obtain 1 more truck to assist Ugu by the 24th April 2020. Supplier submitted invoice but signed timesheets from municipality pending.
|  |  | 10 | 4500211111 | Mpangazitha Projects | 10 | 10 | N/A | N/A | 10 | 0 |  | 10 tankers have been delivered on the 23rd April 2020. Zululand has two trucks operational and Umkhanyakude has four trucks operational. Supplier urged in writing to submit invoice and timesheets.
|  |  | 10 | 4500211081 | M Charlie Trading Enterprise | 10 | 10 | N/A | N/A | 10 | 0 |  | 10 tankers have been delivered on the 23rd April 2020. Supplier urged in writing to submit invoice and timesheets.
| Challenges | Tanker suppliers complaining that the R4000 rate per day for 10 000L trucks is too little for the expected number of trips that have to be conducted per day. Kuyenzakala submitted letter to RW.

## Details per Province (hidden)
COST ESTIMATE FOR THE IMPLEMENTATION OF COVID 19 NATIONAL PROJECT - PROVISION OF WATER SUPPLY, HYGIENE AND SAFETY
SCENARIO FINAL: PROPORTIONATE ON VARIOUS INTERVENTIONS BASED ON AVAILABLE FUNDS
PROVINCE: GAUTENG
Item | Description | R/unit, average | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 4477 |  | 66515754.1211
2 | Water Tanks bought for Water Board | 5252 | 0 |  | 0
3 | Water Tanks installed Water Board | 6000 | 0 |  | 0
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment |  | 40 | 30 | 7669780.4438 |  | 0
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 918713.1979 | 0.91919
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 79369287.7629
10 | Implementation Agent fee including project management fees |  | 5% |  | 4345577.4685
11 | Contingency (10%) |  | 10.37% |  | 8679923.3631
12 | VAT @15% |  | 15% |  | 13859218.2892
| Sub-Total 1 - Gauteng |  |  |  | 106254006.8836
99948281.7747
PROVINCE: FREE STATE
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 280 |  | 4160020.3605
2 | Water Tanks bought for Water Board | 5252 | 120 |  | 630240
3 | Water Tanks installed Water Board | 6000 | 120 |  | 720000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 48 | 30 | 9203736.5326
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation, charge outs) |  | 1% |  | 224877.6855
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 19203914.5786
10 | Implementation Agent fee including project management fees |  | 5% |  | 1063687.1283
11 | Contingency (10%) |  | 10.37% |  | 2101433.5875
12 | VAT @15% |  | 15% |  | 3355355.2942
| Sub-Total 2 - Free State |  |  |  | 25724390.5885
24464803.9515
PROVINCE: MPUMALANGA
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 600 |  | 8914329.3439
2 | Water Tanks bought for Water Board | 5252 | 0 |  | 0
3 | Water Tanks installed Water Board | 6000 | 0 |  | 0
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 59 | 30 | 11312926.1546
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 285743.8207
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 24778039.3192
10 | Implementation Agent fee including project management fees |  | 5% |  | 1351588.1908
11 | Contingency (10%) |  | 10.37% |  | 2709234.0609
12 | VAT @15% |  | 15% |  | 4325829.2356
| Sub-Total 2 - Free State |  |  |  | 33164690.8066
31086528.3878
PROVINCE: LIMPOPO
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 0 |  | 0
2 | Water Tanks bought for Water Board | 5252 | 635 |  | 3335020
3 | Water Tanks installed Water Board | 6000 | 635 |  | 3810000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 34 | 30 | 6519313.3772
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 212631.5952
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 18142004.9724
10 | Implementation Agent fee including project management fees |  | 5% |  | 1005762.2673
11 | Contingency (10%) |  | 10.37% |  | 1985324.2522
12 | VAT @15% |  | 15% |  | 3169963.7238
| Sub-Total 2 - Free State |  |  |  | 24303055.2157
23132532.1485
PROVINCE: EASTERN CAPE
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 0 |  | 0
2 | Water Tanks bought for Water Board | 5252 | 129 |  | 677508
3 | Water Tanks installed Water Board | 6000 | 129 |  | 774000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 30 | 30 | 5752335.3329
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 137259.1129
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 11606142.4457
10 | Implementation Agent fee including project management fees |  | 5% |  | 649245.1719
11 | Contingency (10%) |  | 10.37% |  | 1270692.1884
12 | VAT @15% |  | 15% |  | 2028911.9709
| Sub-Total 5 - Eastern Cape |  |  |  | 15554991.777
14932638.9545
PROVINCE: WESTERN CAPE
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 0 |  | 0
2 | Water Tanks bought for Water Board | 5252 | 615 |  | 3229980
3 | Water Tanks installed Water Board | 6000 | 615 |  | 3690000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 18 | 30 | 3451401.1997
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 174213.7696
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 14810634.9693
10 | Implementation Agent fee including project management fees |  | 5% |  | 824043.2743
11 | Contingency (10%) |  | 10.37% |  | 1621071.8202
12 | VAT @15% |  | 15% |  | 2588362.5096
| Sub-Total 6 - Western Cape |  |  |  | 19844112.5733
18952995.3079
PROVINCE: NORTHERN CAPE
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 0 |  | 0
2 | Water Tanks bought for Water Board | 5252 | 391 |  | 2053532
3 | Water Tanks installed Water Board | 6000 | 391 |  | 2346000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 33 | 30 | 6327568.8661
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation) |  | 1% |  | 178363.8378
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 15170504.7039
10 | Implementation Agent fee including project management fees |  | 5% |  | 843673.3861
11 | Contingency (10%) |  | 10.37% |  | 1660420.0241
12 | VAT @15% |  | 15% |  | 2651189.7171
| Sub-Total 6 - Western Cape |  |  |  | 20325787.8312
19404487.8808
PROVINCE: NORTH WEST
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 535 |  | 7948610.3317
2 | Water Tanks bought for Water Board | 5252 | 100 |  | 525200
3 | Water Tanks installed Water Board | 6000 | 100 |  | 600000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 50 | 30 | 9587225.5548
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
11 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 270926.5339
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 23197002.4203
10 | Implementation Agent fee including project management fees |  | 5% |  | 1281501.3913
12 | Contingency (10%) |  | 10.37% |  | 2538038.3345
13 | VAT @15% |  | 15% |  | 4052481.3219
| Sub-Total 8 - North West |  |  |  | 31069023.468
29474531.9993
PROVINCE: KWAZULU NATAL
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 0 |  | 0
2 | Water Tanks bought for Water Board | 5252 | 1000 |  | 5252000
3 | Water Tanks installed Water Board | 6000 | 1000 |  | 6000000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 35 | 30 | 6711057.8883
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 23667 |  | 2840040
6 | Hand soaps | 20 | 15000 |  | 300000
7 | PPE | 750 | 1500 |  | 1125000
8 | Disbursements (travelling, accommodation,charge outs) |  | 1% |  | 262783.4466
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 22490881.3349
10 | Implementation Agent fee including project management fees |  | 5% |  | 1242984.0208
11 | Contingency (10%) |  | 10.37% |  | 2460830.9627
12 | VAT @15% |  | 15% |  | 3929204.4478
| Sub-Total 9 - KwaZulu Natal |  |  |  | 30123900.7662
28588632.4783
PROVINCE: ALL - SUMMARY
Item | Description | R/unit | Quantity | Duration (in days) | Cost Estimate, R
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 5892 |  | 87538714.1572 | 82427832 | 5110882.1572
2 | Water Tanks bought for Water Board | 5252 | 2990 |  | 15703480 | 17510168 | -1806688
3 | Water Tanks installed Water Board | 6000 | 2990 |  | 17940000 | 20004000 | -2064000
4 | Water tankers will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 347 | 30 | 66535345.35 | 66535345.35 | 0
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 213003 |  | 25560360 | 25560335 | -25
6 | Hand Soaps | 20 | 135000 |  | 2700000 | 2700000 | 0
7 | PPE | 750 | 13500 |  | 10125000 | 10125000 | 0
8 | Disbursements (travelling, accommodation, charge outs) |  | 1% |  | 2665513 | 2665513.0435 | 0.043478
9 | SUBTOTAL - ALL 9 PROVINCES |  |  |  | 228768412.5072 | 227528193.3935 | -1240219.1137
10 | Implementation Agent fee including project management fees |  | 5% |  | 12608062.2993 | 13982251.732 | 1374189.4328
11 | Contingency (10%) |  | 10% |  | 25026968.5937 | 25040859.2223 | 13890.6286
12 | VAT @15% |  | 15% |  | 39960516.51 | 39982695.6522 | 22179.1422
| Sub-Total 9 - KwaZulu Natal |  |  |  | 306363959.9102 | 306534000 | -170040.0898
306534000

## DWS 18 04 2020
COST ESTIMATE FOR THE IMPLEMENTATION OF COVID 19 NATIONAL PROJECT - PROVISION OF WATER SUPPLY AND HYGIENE
Item | Description | R/unit | Quantity | Cost Estimate, R | Current Committed Purchase Orders, R | Variance (Budget-POs)
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 5548 | 82427832 | 61232728.05 | 21195103.95 | 5892 | 87538714.1572
2 | Water Tanks for installation by WSA's through Assignments |  | 3334 | 17510168 | 17510168 | 0 | 2990 | 15703480
3 | Provision for installation of tanks by the WSA's through Assignment Agreements | 6000 | 3334 | 20004000 | 20000000 | 4000 | 2990 | 17940000
4 | Water Tankers (Trucks) will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 347 | 66535345.35 | 54503920.6 | 12031424.75 | 347 | 66535345.35
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 213002.7917 | 25560335 | 25560335 | 0 | 213003 | 25560360
6 | Hand Soaps | 20 | 135000 | 2700000 | 2700000 | 0 | 135000 | 2700000
7 | PPE | 750 | 13500 | 10125000 | 10125000 | 0 | 13500 | 10125000
8 | Disbursements (travelling, accommodation, charge outs) |  | 1% | 2665513.0435 | 2665513.0435 | 0 | 0.01 | 2665513
9 | SUBTOTAL - ALL 9 PROVINCES |  |  | 227528193.3935 | 194297664.6935 | 33230528.7 | 0 | 228768412.5072 | 1240219.1137
10 | Implementation Agent fee including project management fees |  | 5.246% | 13982251.732 | 13982251.732 | 0 | 0.05 | 12608062.2993 | -1374189.4328
11 | Contingency (10%) |  | 10.37% | 25040859.2223 | 11752891.85 | 13287967.3723 | 0.1 | 25026968.5937 | -13890.6286
12 | VAT @15% |  | 15% | 39982695.6522 | 33004921.2413 | 6977774.4108 | 0.15 | 39960516.51 | -22179.1422
| TOTAL - ALL 9 PROVINCES |  |  | 306534000 | 253037729.5169 | 53496270.4832 | 0 | 306363959.9102 | -170040.0898
306534000
0
2665513.0435
296168.1159

## DWS Summary (hidden)
THE IMPLEMENTATION OF COVID 19 NATIONAL PROJECT - PROVISION OF WATER SUPPLY AND HYGIENE
Item | Description | R/unit | Quantity | Cost Estimate, R | Revised Budget, R | Current Committed Purchase Orders, R | Actual Paid R | % of budget Utilised
1 | Tanks Supplied and Installed by Service Provider | 14857.2156 | 5548 | 82427832 | 74427832 | 61232728.05 | #REF! | #REF! | 5892 | 87538714.1572
2 | Water Tanks bought for Water Board to installed |  | 3334 | 17510168 | 17510168 | 17510168 |  | 0% | 2990 | 15703480
3 | Water Tanks installed Water Board | 6000 | 3334 | 20004000 | 13000000 | 20000000 | #REF! | #REF! | 2990 | 17940000
4 | Water Tankers (Trucks) will be hired in order to fill the water tanks (5 000l to 18 000l), including establishment | 0 | 347 | 66535345.35 | 94827312.35 | 54503920.6 | #REF! | #REF! | 347 | 66535345.35
5 | Sanitizers that kill 99.9% of germs (for carrying to site and dispensers at all strategic locations | 120 | 213002.7917 | 25560335 | 25560335 | 25560335 | #REF! | #REF! | 213003 | 25560360
6 | Hand Soaps | 20 | 135000 | 2700000 | 2700000 | 2700000 | #REF! | #REF! | 135000 | 2700000
7 | PPE | 750 | 13500 | 10125000 | 10125000 | 10125000 | #REF! | #REF! | 13500 | 10125000
8 | Disbursements (travelling, accommodation, charge outs) |  | 1% | 2665513.0435 | 2665513.0435 | 2665513.0435 | #REF! | #REF! | 0.01 | 2665513
9 | SUBTOTAL - ALL 9 PROVINCES (INCLUDING DHSWS) |  |  | 227528193.3935 | 240816160.3935 | 194297664.6935 | #REF! | #REF! | 0 | 228768412.5072 | 1240219.1137
10 | Implementation Agent fee including project management fees |  | 5.246% | 13982251.732 | 13982251.732 | 13982251.732 | #REF! | #REF! | 0.05 | 12608062.2993 | -1374189.4328
11 | Contingency (10%) |  | 10.37% | 25040859.2223 | 11752892 | 11752891.85 | #REF! | #REF! | 0.1 | 25026968.5937 | -13890.6286
12 | VAT @15% |  | 15% | 39982695.6522 | 39982695.6522 | 33004921.2413 | #REF! | #REF! | 0.15 | 39960516.51 | -22179.1422
| TOTAL - ALL 9 PROVINCES |  |  | 306534000 | 306533999.7777 | 253037729.5169 | #REF! | #REF! | 0 | 306363959.9102 | -170040.0898
306534000
0
0

## Suppliers
Suppliers Paid
Tank/Tankers
| Date | Order No. | Supplier |  | Amount R | Province
| 2020-03-31 | IA | Rand Water |  | 7792996.3848
| 2020-04-08 | 4500211001 | Jojo Tanks | Tanks | 867284 | Gauteng
| 2020-04-14 | 4500211016 | Melo enterpirises | Tanks | 236499.6 | Gauteng
| 2020-04-23 | 4500211026 | Zenzo Project | Tanks | 392816.6 | Gauteng
| 2020-04-28 | 4500211010 | Pabi n Sbu | Tanks | 241448.6957 | Gauteng
| 2020-04-30 | 4500210999 | Osher Fuel | Tanks | 7831798.44 | Gauteng
| 2020-05-05 | 4500211001 | Jojo Tanks | Tanks | 524484 | Gauteng
| 2020-05-08 | 4500211088 | TLG | Tanks | 1156100 | Gauteng
| 2020-05-14 | 4500211025 | Midmar Plant Hire | Tankers | 219300 | Gauteng
| 2020-05-14 | 4500211078 | SGT Eletrical | Tanks | 1248588 | Gauteng
| 2020-05-29 | 4500210987 | Xmoor Transport | Tankers | 3767300 | Gauteng
| 2020-06-12 | 4500211021 | Strorky | Tankers | 173000 | Gauteng
| 2020-06-23 | 4500211022 | Strorky | Tankers | 224000 | Gauteng
| 2020-06-23 | 4500211078 | SGT Eletrical | Tanks | 138732 | Gauteng
| 2020-06-23 | 4500211080 | GS Fencing | Tanks | 1133000 | Gauteng
| 2020-06-26 | 4500211112 | Thabzo Holdings | Tanks | 3240000 | Gauteng
21394351.3357
| 2020-04-17 | 4500211001 | Jojo Tanks | Tanks | 338697 | FS
| 2020-04-20 | 4500211001 | Jojo Tanks | Tanks | 530 | FS
| 2020-04-28 | 4500211001 | Jojo Tanks | Tanks | 81000 | FS
| 2020-05-04 | 4500211088 | TLG Commercial | Tanks | 485415 | FS
| 2020-05-06 | 4500211001 | Jojo Tanks | Tanks | 583 | FS
| 2020-05-07 | 4500211019 | Impoqo | Tanks | 1131120 | FS
| 2020-05-21 | 4500210987 | Xmoor Transport | Tanker | 6011300 | FS
| 2020-05-25 | 4500211001 | Jojo Tanks | Tanks | 47950 | FS
| 2020-05-27 | 4500211002 | Jojo Tanks | Tanks | 44564 | FS
| 2020-06-19 | 4500211079 | SedTrade | Tanker | 1805000 | FS
| 2020-06-25 | 4500211019 | Impoqo | Tanks | 416196 | FS
| 2020-06-26 | 4500210987 | Xmoor Transport | Tanker | 2737860 | FS
13100215
| 2020-04-29 | 4500211111 | Mpangazitha | Tanks | 485415 | MP
| 2020-04-30 | 4500211109 | Zenzo Project | Tanker | 1970913.0435 | MP
| 2020-05-04 | 4500211110 | Mthethwa Power House | Tanker | 1404035 | MP
| 2020-05-06 | 4500211078 | SGT | Tanker | 3468300 | MP
| 2020-05-07 | 4500211110 | Mthethwa Power House | Tanker | 341000 | MP
| 2020-05-08 | 4500211068 | Dinaledi Tsa Metsi Trad | Tanker | 629000 | MP
| 2020-05-08 | 4500211089 | Sibusisosobuhle Trading | Tanker | 860000 | MP
| 2020-05-13 | 4500211070 | Basadi Peniel | Tanker | 679520 | MP
| 2020-05-22 | 4500211109 | Zenzo Project | Tanker | 1147650 | MP
| 2020-06-03 | 4500211078 | SGT Eletrical | Tanks | 1770000 | MP
| 2020-06-03 | 4500211110 | Mthethwa Power House | Tanker | 880000 | MP
| 2020-06-04 | 4500211110 | Mthethwa Power House | Tanker | 205500 | MP
| 2020-06-11 | 4500211070 | Basadi Peniel Trading | Tanker | 219116 | MP
| 2020-06-12 | 4500211070 | Basadi Peniel Trading | Tanker | 587200 | MP
| 2020-06-19 | 4500211070 | Basadi Peniel Trading | Tanker | 304000 | MP
| 2020-06-23 | 4500211089 | Sibusisosobuhle Trading | Tanker | 316800 | MP
| 2020-06-24 | 4500211070 | Basadi Peniel Trading | Tanker | 169000 | MP
| 2020-06-26 | 4500211109 | Zenzo Project | Tanker | 1851450 | MP
| 2020-06-26 | 4500211109 | Zenzo Project | Tanker | 833500 | MP
| 2020-06-26 | 4500211089 | Sibusisosobuhle Trading | Tanker | 376800 | MP
| 2020-06-26 | 4500211070 | Basadi Peniel Trading | Tanker | 505950 | MP
19005149.0435
| 2020-04-17 | 4500211001 | Jojo Tanks | Tanks | 1916162 | LIMP
| 2020-05-14 | 4500211021 | Storky | Tanker | 929000 | LIMP
| 2020-05-20 | 4500211021 | Storky | Tanker | 311600 | LIMP
| 2020-05-21 | 4500211001 | Jojo Tanks | Tanks | 548190 | LIMP
| 2020-05-19 | 4500211021 | Storky | Tanker | 1216300 | LIMP
4921252
| 2020-04-20 | 4500211001 | Jojo Tanks | Tanks | 442212 | EC
| 2020-05-21 | 4500210999 | Osher Fuel | Tanks | 1164996 | EC
| 2020-06-22 | 4500211226 | Phila Development | Tanker | 1445000 | EC | ü
| 2020-06-23 | 4500211272 | Rolung Over Trading CC | Tanker | 180998.24 | EC | ü
| 2020-06-25 | 4500211224 | Vaxogyn | Tanker | 365000 | EC | ü
| 2020-06-25 | 4500211273 | Qumanco Trading | Tanks | 437000 | EC | ü
| 2020-06-26 | 4500211225 | MSB Ultra Construction CC | Tanker | 485000 | EC | ü
4520206.24
| 2020-03-31 | 4500211013 | Nel Tank | Tanks | 1295000 | Western Cape | ü
| 2020-05-06 | 4500211001 | Jojo Tank | Tanks | 208119 | Western Cape | ü
| 2020-05-11 | 4500211025 | Midmar Plant Hire | Tanker | 736736.7652 | Western Cape | ü
| 2020-05-15 | 4500211001 | Jojo Tank | Tanks | 20568 | Western Cape | ü
| 2020-05-28 |  | Overberg | Tanks | 477750 | Western Cape | ü
| 2020-06-19 | 4500211025 | Midmar Plant Hire | Tanker | 1189134.7043 | Western Cape | ü
| 2020-06-24 |  | Overberg | Tanks | 241500 | Western Cape | ü
4168808.4696
| 2020-04-17 | 4500211060 | GWK | Tanks | 158010.77 | NC | ü
| 2020-04-17 | 4500211001 | Jojo Tanks | Tanks | 635382 | NC | ü
| 2020-04-28 | 4500211077 | Keeme Trading | Tankers | 233000 | NC | ü
| 2020-05-04 | 4500211060 | GWK | Tanks | 27197.3739 | NC | ü
| 2020-05-08 | 4500211001 | Jojo Tanks | Tanks | 219392 | NC | ü
| 2020-05-11 | 4500211122 | Luhlavana | Tankers | 1047826.087 | NC | ü
| 2020-05-11 | 4500211077 | Keeme Trading | Tankers | 226500 | NC | ü
| 2020-05-12 | 4500211077 | Keeme Trading | Tanker | 162000 | NC | ü
| 2020-05-13 | 4500211060 | GWK | Tanks | 205097.39 | NC | ü
| 2020-05-14 | 4500210999 | Osher Fuel | Tanks | 1615696.32 | NC | ü
| 2020-05-29 | 4500211077 | Keeme Trading | Tankers | 270000 | NC | ü
| 2020-06-02 | 4500211077 | Keeme Trading | Tankers | 310500 | NC | ü
| 2020-06-23 | 4500211071 | Mulalo Business Enterprises | Tankers | 1125600 | NC | ü
| 2020-06-24 | 4500211077 | Keeme Trading | Tankers | 636000 | NC | ü
| 2020-06-25 | 4500211078 | Keeme Trading | Tankers | 257600 | NC | ü
| 2020-06-26 | 4500211071 | Mulalo Business Enterprises | Tankers | 720700 | NC | ü
| 2020-06-26 | 4500211122 | Luhlavana | Tankers | 818400 | NC | ü
8668901.9409
| 2020-04-29 | 4500211086 | Belgium Civil | Tanker | 442000 | NW | ü
| 2020-04-29 | 4500211017 | Thoka Geosciences | Tanks | 1480401.8 | NW | ü
| 2020-04-29 | 4500211009 | Loxiontym | Tanks | 1253575.6522 | NW | ü
| 2020-04-30 | 4500211076 | Daneesa | Tanks | 1980493.2261 | NW | ü
| 2020-05-08 | 4500211086 | Belgium Civil | Tanker | 617500 | NW | ü
| 2020-05-12 | 4500211017 | Thoka Geosciences | Tanks | 1264313.3913 | NW | ü
| 2020-05-22 | 4500210998 | Aqua Transport | Tanker | 4595850 | NW | ü
| 2020-05-21 | 4500211021 | Storky | Tanker | 1061800 | NW | ü
| 2020-05-29 | 4500211086 | Belgium Civil | Tanker | 370500 | NW | ü
| 2020-06-24 | 4500211076 | Daneesa | Tanks | 2158757 | NW | ü
| 2020-06-24 | 4500211076 | Daneesa | Tanks | 2072539.2 | NW | ü
| 2020-06-26 | 4500211086 | Aqua Transport | Tanker | 4467335.6 | NW | ü
| 2020-06-26 | 4500211086 | Belgium Civil | Tanker | 692300 | NW
22457365.8696
| 2020-04-14 | 4500211009 | Loxiontym Investment | Tanks | 1550660.8 | KZN | ü
| 2020-04-24 | 4500211009 | Loxiontym Investment | Tanks | 679905.12 | KZN | ü
| 2020-04-29 | 4500211009 | Loxiontym Investment | Tanks | 751474.08 | KZN | ü
| 2020-05-04 | 4500211111 | Mpangazitha | Tanker | 385000 | KZN | ü
| 2020-05-06 | 4500211028 | Kuyenzakala | Tanker | 344000 | KZN | ü
| 2020-05-11 | 4500211028 | Kuyenzakala | Tanker | 256000 | KZN | ü
| 2020-05-14 | 4500211111 | Mpangazitha | Tanker | 316000 | KZN | ü
| 2020-05-18 | 4500211078 | SGT Electrical | Tanks | 924880 | KZN | ü
| 2020-05-25 | 4500211111 | Mpangazitha | Tanker | 400000 | KZN | ü
| 2020-05-25 | 4500211028 | Kuyenzakala | Tanker | 289000 | KZN | ü
| 2020-06-02 | 4500210999 | Osher Fuel | Tanks | 698997.6 | KZN | ü
| 2020-06-19 | 4500211028 | Kuyenzakala | Tanker | 76000 | KZN | ü
6671917.6
0
| TOTAL Amount Excl. Vat paid |  |  |  | 104908167.4991
Hygien Product ( Sanitizers, Hand Soap, etc.)
| Date | Order No. | Supplier |  | Amount R | Province
| 2020-04-28 |  | TSOMAN |  | 2399373.913
| 2020-04-28 |  | OPP |  | 623655.39
| 2020-04-28 |  | MOEPATUTSEE PROJECTS |  | 2759280
| 2020-04-28 |  | BULKENG |  | 2391560
| 2020-05-06 |  | Tebfin |  | 2399585
| 2020-05-11 |  | Thari Tsosang |  | 2806600
| 2020-05-11 |  | Speedy Two Star |  | 845891.3043
| 2020-05-11 |  | Triple P Trading |  | 1496363
| 2020-05-11 |  | PVMT Trading |  | 1232706.9565
| 2020-05-11 |  | Zingambile |  | 1095804.3478
| 2020-05-11 |  | OPP Group |  | 1461289.0348
| 2020-05-12 |  | Speedy Two Star |  | 563043.4783
| 2020-05-14 |  | TTM Trading |  | 2399585
| 2020-05-15 |  | LemazoTrading Project |  | 1620275.5
| 2020-05-15 |  | Shadi & Georg |  | 1620275.5
| 2020-05-15 |  | Mapeete Enter |  | 1408934.78
| 2020-05-22 |  | Wandeme Resource |  | 1496363
| 2020-05-25 |  | Zingambili |  | 990735.6522
| 2020-05-27 |  | Kerstin Kinsey Holdings |  | 2397315
| 2020-05-27 |  | Lwande Group |  | 1232706.9565
| 2020-06-08 |  | South West Resources |  | 2399585
| 2020-06-08 |  | Zamangwane Consultant |  | 2399585
| TOTAL Amount Excl. Vat paid |  |  |  | 38040513.8135
Disbursements
| Date | Order No. | Supplier |  | Amount R | Province
| 2020-05-19 |  | Vision Communication |  | 167720 | 3804051.3813
| 2020-05-21 |  | Notefull Gauteng (Courier Services) |  | 319581.84
| 2020-05-22 |  | Blue Sky Vision (Courier Services) |  | 469625.17
| 2020-05-22 |  | Kone Holdings (Courier Services) |  | 376763.4696
| 2020-05-27 |  | Blue Sky Vision (Courier Services) |  | 106274.2174
| 2020-06-09 |  | Vision Communication |  | 19032
| 2020-06-08 |  | Notefull Gauteng (Courier Services) |  | 219869.0957
| 2020-06-22 |  | Blue Sky Vision (Courier Services) |  | 89720.6522
| 2020-06-22 |  | Notefull Gauteng (Courier Services) |  | 54742.2696
|  |  | Other Costs - RW |  | 2503159.06
| TOTAL Amount Excl. Vat paid |  |  |  | 4326487.7743
Monitor and Evaluation ( Contingency)
| Date | Order No. | Supplier |  | Amount R | Province
| 2020-05-15 |  | Entsika Consult |  | 2998520
| 2020-05-15 |  | Pridin Trading |  | 2982336
| 2020-05-15 |  | Kukama Early Dev |  | 2603902.61
| TOTAL Amount Excl. Vat paid |  |  |  | 8584758.61
|  | Grand Total Paid |  |  | 155859927.697
|  | Grand Total Paid incl of IA |  |  | 163652924.0818
| Grand Total Incl. Vat |  |  |  | #REF!
Formulas:
Date = [Date, row above]
Note on G143: Lucky Ncobela: Lucky Ncobela: 0% rated but for consistence in the calculation

## Bank (hidden)
Liquidity
TOTAL INVESTMENTS Incl of VAT FOR NCC COVID-19
| Call Deposit | SBSA - NCC Covid-19 | 4000000
|  | Nedbank Asset | 110000000
|  | RMB - NCC Covid-19 | 4000000
Current Account
|  | Cash Available | 118000000

## Process (hidden)
PROCESS FLOW COVAID 19 PROJECT |  |  | 2020-03-29
FINANCE REQUIREMENTS TO SPEED UP PAYMENTS
Time | Activities | Responsible Person
00h00 - 09h00 | Finance received update SCM data file | Treasury
09h00 | Submission of Invoices for same day payment | Program Manager
00h00 - 10h00 | Update the Bank Data Base for NCC CVD19 | Treasury
10h00 - 11h00 | Bank File data base to be approved | Treasury
11h00 - 13h00 | Run the payment process | Account Payable
13h00 - 14h00 | 1st Payment Releaser | Account Payable
14h00 - 14h30 | 2nd Payment Releaser | Treasury
15h30 -16h00 | Payment report submitted to NCC CVD 19 via CFO | Finance
Ongoing | Receipting and Submission of Invoices + supporting doc | Program Manager
Notes on Receipting
Email the signed invoice to FSS: Fservicedesk@randwater.co.za and cc Ms. Ntokozo Mazibuko.
Valid Invoice must be :
1. Sign Invoice by Authorised PM with Board Number.
2. Match the GR (Receipting)
3. Have a valid RW VAT number and Supplier VAT number.
4. Need the name of the Receptor's for any clarity that might be needed
5. The Project Manager is expected to keep a hard copy file on the project that would include all project documents, such as, appointment letters, agreements, procurement process documents, etc.