## Slide 1: QUARTER 3 report (2020/21) Portfolio committee

## Slide 2: PURPOSE
The purpose is to present the:
  Quarter 3 performance report; and
  Quarter 3 financial report

## Slide 3: NDA PROGRAMMING WITHIN THE COVID-19 ENVIRONMENT
NDA continued to implement CARA programme through close monitoring and provision of support to the implementing NPO’s.
The Covid-19 pandemic has largely constrained the NDA’s resource mobilization efforts. The impact of the pandemic has seen the reprioritization of resources by donors leading to a significant impact on NDA’s ability to raise resources for CSO development work
The NDA experienced great success in collaborating with CSOs in the implementation of the volunteer programme which contributed towards significant easing of the effects of Covid-19 on the poor and vulnerable. Moreover, 2000 work opportunities were created through the implementation of the programme
A capacity building programme geared towards strengthening the governance and financial management capability of CSOs has been undertaken with a great measure of success. More CSOs are able to contribute towards the economic development of their communities following these administrative and technical programmes
A significant number of CSOs have been grant funded to pursue socio-economic developmental work in the form of sewing projects, ECD programmes, food security and advocacy on Gender Based Violence and Femicide.

## Slide 4: TREND FOR QUARTERLY PERFORMANCE TODATE

## Slide 5: SUMMARY OF QUARTER 3 PERFORMANCE
Item |  |  |  | 
 | Overall Achievement | Program 1 Achievement | Program 2 Achievement | Program 3 Achievement
Total number of KPIs | 19 | 7 | 7 | 5
Number of KPIs achieved | 8 | 2 | 2 | 4
Number of KPIs not achieved | 10 | 5 | 4 | 1
Number of KPIs not due for reporting | 1 | - | 1 | -
% of targets achieved in the APP | 44% | 28% | 33% | 80%

## Slide 6: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 1 | Percentage (%) implementation of Consequence Management in relation to IFW cases |  |  |  | 
Object of Change | Compliance to Institutional Policies, PFMA and National Treasury regulations by NDA staff |  | Impact | Improved governance and operational efficiency | 
Targets | Annual target | 80% | Quarter Target | 60% | 
Quarter 3 Achievements | (55%) 31 Cases of irregular expenditure were identified and they are in various stages of implementation as follows: 3 Write-offs recommended; 7 Recoveries Recommended; 1 Offer to pay in instalments received; 1 Case to be absorbed by TWF; 7 verbal warnings issued by Supervisors; 1 Written warning issued in Finance Issued 4 recovery notices and currently assessing 4 cases of Fruitless and Wasteful expenditure relating to interest. |  |  |  | 
Reason for deviation | There is inadequate capacity in the Business Unit responsible for the KPI. That has resulted in the underperformance reported. The process is lengthy as it requires compliance with HR policies, PFMA and National Treasury regulations that are highly procedural. |  |  |  | 
Correct Measures | A recruitment process for a legal officer to support the business unit is in progress and should be finalized by 31 January 2021 |  |  |  | 

## Slide 7: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 2 | Percentage (%) reduction of cumulative balance of IFW expenditure reported in the prior year annual Financial Statements |  |  |  | 
Object of Change | Reduction in instances of IFW expenses in the NDA |  | Impact | Reduce in the IFW expenses in NDA | 
Targets | Annual target | 80% | Quarter Target | 60% | 
Quarter 3 Achievements | 0% is being reported however, On the 11 Nov 2020 NDA management filed a qualifying condonation submission with the National Treasury (NT) as prescript under the PFMA and NT Regulations. The submission involved 421 transactions amounting to R96.1 million. If condoned, that will representing 66% reduction of the cumulative balance of IFW expenditure reported prior year. |  |  |  | 
Reason for deviation | The performance for KPI is highly dependent on the National Treasury’s decision to write-off the historical IFW expenditure incurred in the 2019/20 financial year. |  |  |  | 
Correct Measures | Further investigative measures will continue and HR disciplinary process will be carried out and thereof a report to the effect will be prepared in the 3rd quarter. A further submission for condonation of eligible expense will then be prepared based on the said report requesting NT to further consider disposing the submission favourably in the 3rd quarter. |  |  |  | 

## Slide 8: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 3 | Percentage (%) compliance to the NDA preferential procurement policy |  |  |  | 
Object of Change | Historically disadvantaged communities accessing economic opportunity |  | Impact | Economically uplift communities, which historically have been disadvantaged in accessing economic opportunity under normal conditions | 
Targets | Annual target | 100% | Quarter Target | 100% | 
Quarter 3 Achievements | 100% of procurement of services and goods within NDA has prioritized organizations that fall within the BBBEE Levels 1, 2, 3 &4. However 89% of the services and goods were sources from organizations falling with Levels 2. |  |  |  | 
Reason for deviation | There was no deviation reported |  |  |  | 
Correct Measures | Management will continue manage and monitoring the procurement implementation plan as approved |  |  |  | 

## Slide 9: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 4 | Amended NDA Act |  |  |  | 
Object of Change | Streamline the legal provisions of the NDA Act with that of PFMA by removing existing bottle-necks that affect the performance of NDA work |  | Impact | Improved governance and operational efficiency | 
Targets | Annual target | Position document on the NDA Act amendment | Quarter Target | Position document approved by the Board | 
Quarter 3 Achievements | A draft position document was developed upon consulting with senior management and board. The draft document was then submitted to the Board in October 2020 for approval. |  |  |  | 
Reason for deviation | The Board requested for management to carry out further consultation and this process has led to a delay in having a final draft document in place ready for approval |  |  |  | 
Correct Measures | A final draft of the position document will be submitted for approval by the Board in the 4th quarter. |  |  |  | 

## Slide 10: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 5 | Approved NDA Turnaround Strategy |  |  |  | 
Object of Change | To repurpose the NDA programme in alignment to the NDA mandate and Government’s policy direction |  | Impact | Will affect the NDA programme agenda for the next five years | 
Targets | Annual target | NDA Turnaround Strategy approved | Quarter Target | Approved NDA Turnaround Strategy | 
Quarter 3 Achievements | Consultation sessions with NDA Management and Board happened to concretizes on the key pillars of the turnaround strategy. The following Key pillars were identified : Business Turnaround, inclusive of audit turnaround measures Financial Sustainability of the NDA Strategic Partnerships Digitisation and System Integration Community and Economic Development Evidence based Research and Evaluation |  |  |  | 
Reason for deviation | There were delays in obtaining the Board’s direction and inputs on the concept document of Turnaround Strategy The planning session was held in October 2020 that served as a basis to solicit further Board guidance and further inputs from external stakeholders |  |  |  | 
Correct Measures | The procurement process of appointing a SP to develop a Turnaround Strategy will be completed in February 2021 |  |  |  | 

## Slide 11: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 6 | Approved Employee Climate Survey framework |  |  |  | 
Object of Change |  |  | Impact | A commonly desired organizational culture linked to a strategy to attract and retain the employee to NDA / make NDA an employer of choice. | 
Targets | Annual target | Approved framework for Employee Climate Survey | Quarter Target | Consultation with internal stakeholders on the framework for Employee Climate Survey | 
Quarter 3 Achievements | Consultations sessions happened in November 2020 involving internal stakeholders. Feedback from the sessions were documented to inform the Climate Survey Framework. |  |  |  | 
Reason for deviation | None |  |  |  | 
Correct Measures | Further engagement may be conducted in January 2021 before finalising the development of the framework for Employee Climate Survey |  |  |  | 

## Slide 12: Program 1: GOVERNANCE AND ADMINISTRATION
KPI 7 | Approved Brand Strategy |  |  |  | 
Object of Change | To improve NDA client experience, highlight competitive advantage and programmatic performance |  | Impact | Would enhance NDA’s reputation and ensure that all key stakeholders understand and appreciate its mandate and the brand promise of “Unlocking Potential’’. | 
Targets | Annual target | Draft Brand Strategy | Quarter Target | Development of draft brand strategy | 
Quarter 3 Achievements | A Draft Brand Strategy has not been produced, however, a Draft Brand Strategy Concept Document was developed upon receiving inputs through consultative sessions that were held in the 2nd quarter |  |  |  | 
Reason for deviation | There were delays in finalising the consultation process that in turn affected the drafting of the draft brand strategy document |  |  |  | 
Correct Measures | Conclusion of consultative session and drafting of a final Draft of Brand Strategy Document to be presented to EXCO for approval by end of 4th quarter |  |  |  | 

## Slide 13: Program 2: CSO DEVELOPMENT
KPI 8 | Rand value of resources raised to fund CSOs development interventions |  |  |  | 
Object of Change | To raise funds for the funding of CSOs for the advancement of community based socioeconomic interventions and transformational projects |  | Impact | The two KPIs are interlined and they have the potential of ensuring that the primary mandate of sourcing funds from alternative sources besides governments is achieved for the benefit of economically disadvantaged communities | 
Targets | Annual target | R100 million | Quarter Target | R75million | 
Quarter 3 Achievements | R12 000 000 |  |  |  | 
Reason for deviation | Resource mobilization efforts have been largely hampered by human resource constraints and a demanding focus on key programmes (CARA and Volunteer Programme) |  |  |  | 
Correct Measures | Recruitment is underway to mitigate capacity challenges. Further efforts will also be directed towards the strengthening of the resource mobilization approach and process. |  |  |  | 

## Slide 14: Program 2: CIVIL SOCIETY ORGANISATION DEVELOPMENT
KPI 10 | Number of integrated development initiatives coordinated |  |  |  | 
Object of Change | NDA will coordinate activities to link CSOs with the private sector CSI units which will create an enabling environment for the private sector to invest in CSOs |  | Impact | The KPI ensures that community development work supported by the NDA has a buy-in from all stakeholders hence increasing the chances of community projects achieving the set goals. | 
Targets | Annual target | 9 | Quarter Target | 6 | 
Quarter 3 Achievements | Two (2) Integrated Development initiatives (IDIs) had been concluded by end of the 3rd quarter. 3 more IDIs from Western Cape, Gauteng &Limpopo were at the final stage of implementation. |  |  |  | 
Reason for deviation | Lengthy negotiations with various stakeholders in provinces affected the planning and implementation process of the Integrated Development initiatives. |  |  |  | 
Correct Measures | 3 Integrated Development initiatives that were at the final stage of completion will be finalized by end of February 2021. Additional 4 Integrated Development initiatives in the provinces of Kwa-Zulu Nata, Mpumalanga, Free State and North West had prepared the implementation concept plan and will be implemented through the 4th quarter. |  |  |  | 

## Slide 15: Program 2: CSO DEVELOPMENT
KPI 9 | Number of strategic partnerships established |  |  |  | 
Object of Change | Raise funds for funding of CSOs for the advancement of community based socioeconomic interventions and transformational projects |  | Impact | The two KPIs are interlined and they have the potential of ensuring that the primary mandate of sourcing funds from alternative sources besides governments is achieved for the benefit of economically disadvantaged communities | 
Targets | Annual target | 5 | Quarter Target | 3 | 
Quarter 3 Achievements | At the end the quarter no partnership agreement had been signed. However consultative engagements with five (5) potential partners were still going to determine areas of collaboration. Consultations are being finalised with the following potential partners: SA Tourism - rural community tourism; SASSA on formalizing the working relations in the provinces; Small Business Development Initiative (SBDI); LFP Group, a private sector partner to support cooperatives in mobilizing resources and building capacity in technical skills of smallholdings; Gauteng Department of Social Development. |  |  |  | 
Reason for deviation | Agreeing and scheduling of meetings with contact persons within the potential partners has been a challenge and finalizing areas of commitment with partners has taken long than anticipated |  |  |  | 
Correct Measures | Consultative to be concluded leading to the signing off of partnership agreements by March 2021 |  |  |  | 

## Slide 16: Program 2: CSO DEVELOPMENT
KPI 11 | Number of Work opportunities created as a result of CSOs development interventions |  |  |  | 
Object of Change | Economically disadvantaged community members access work opportunities created by NDA programmes. |  | Impact | Improvement of the livelihoods of beneficiaries through increased income in households of mainly unemployed youth and women. | 
Targets | Annual target | 2000 | Quarter Target | 2000 | 
Quarter 3 Achievements | 2061 work opportunities - were created through the NDA Covid-19 Volunteer Programme. The work opportunities were created equitably across the 9 province and with focus being placed on vulnerable and economically challenged communities. The programme was implemented through the CSOs that have been supported through the NDA capacity building programme. |  |  |  | 
Reason for deviation | There was no significant deviation warranting explanation |  |  |  | 
Correct Measures | No corrective measures were necessary however follow-up monitoring of the programme will continue through the 4th quarter |  |  |  | 

## Slide 17: Program 2: CSO DEVELOPMENT
KPI 12 | Value of increased CSO income generated as a result of NDA interventions |  |  |  | 
Object of Change | As a result of NDA interventions and assistance organisations will strengthen sustainability within their organisations and create work and income opportunities for beneficiaries; |  | Impact | The KPI aims at increasing economic freedom of economically disadvantaged households by reducing dependency on social grants and other government subsidies. | 
Targets | Annual target | R24 000 000 | Quarter Target | R24 000 000 | 
Quarter 3 Achievements | R1 251 145 verified and reported, the contributing provinces were Eastern Cape and Western Cape with amounts of R839 715 and R411 430 respectively |  |  |  | 
Reason for deviation | The collation of data on income generated by CSO’s that were referred by NDA is a lengthy process and relies on an aggressive monitoring visits being carried out regularly; the monitoring process has not fully been realised due to the health risk associated with Covid-19 pandemic. |  |  |  | 
Correct Measures | The collation of data from CSO’s that were referred by NDA and accessed opportunities from DSD and SASSA PPE procurement services will be finalised in quarter 4. |  |  |  | 

## Slide 18: Program 2: CSO DEVELOPMENT
KPI 13 | Number of CSOs empowered through on-line and e-development interventions |  |  |  | 
Object of Change | Training scheduled for Quarter 3 is based on the needs of each organization. Training interventions focus on Governance, NPO Compliance and Resource Mobilization. |  | Impact | The KPI empowers organizations to improve governance structures and systems that introduces efficient and effectiveness when running community development programmed | 
Targets | Annual target | 300 | Quarter Target | 0 | 
Quarter 3 Achievements | 243 CSOs were provided with capacity build support by end of the 3rd quarter. The capacity building support entails various capacity intervention such as Organizational management, Mentorship support, Technical support, linkages to resource opportunities. |  |  |  | 
Reason for deviation | The was not due for report however, having adopted the Virtual Platform of conferencing and carrying out training workshops target by the beginning of the 3rd quarter, the programme was able to rollout the capacity building support interventions the CSOs. |  |  |  | 
Correct Measures | Further implementation and monitoring of implementation with be pursuit throughout the 4th quarter |  |  |  | 

## Slide 19: Program 2: CSO DEVELOPMENT
KPI 14 | Percentage (%) disbursement of funds for grant funding |  |  |  | 
Object of Change | To support CSO’s in their efforts to alleviate poverty. The main areas funded are increased income generation, creation of work opportunities, to raise awareness and support victims of GBV&F |  | Impact | The KPI ensures that grant funds that NDA contracts with CSOs are appropriated managed and disbursed off to the rightful grantees within the legal prescripts. | 
Targets | Annual target | 95% | Quarter Target | 95% | 
Quarter 3 Achievements | 77% of the committed fund were disbursed on time to the CSO. |  |  |  | 
Reason for deviation | 33% of the remaining grants could not be released pending fulfillment of conditions in the grant agreements such processing of monitoring reports. The grant management process being a result based, requires that such procedural conditions be take in account to ensures fiduciary responsibility by the NDA |  |  |  | 
Correct Measures | Addendum will be prepared requesting the transfer of funds following a review of monitoring reports and finalisation of necessary documentation to effect payment in the 4th quarter |  |  |  | 

## Slide 20: Program 3: RESEARCH
KPI 15 | Number of research publications that informed development practice on Government Priorities |  |  |  | 
Object of Change | To generate empirical evidence for enhanced development policy |  | Impact | Contributed towards the implementation of dialogues. Strengthened social partnerships through the engagement with the research findings | 
Targets | Annual target | 3 research Reports | Quarter Target | 2 research Reports | 
Quarter 3 Achievements | The NDA concluded 4 research studies, these studies were on the following research areas: Behaviour change and modification in the wake of COVID-19 – Policy implications for the Social Development Portfolio Strategies Requirements for transforming the civil society sector in South Africa Analysis of best practices in ECD centres in the Eastern Cape Province in the context of legislation and policy Creating capacities and building capabilities for the civil society sector in South Africa |  |  |  | 
Reason for deviation | The deviation is due to additional study completed by the University of Fort Hare on ECD policy, which we have been conducting for the past 3 years as longitudinal study on the implementation of the EDC policy adopted by government in 2015/16. |  |  |  | 
Correct Measures | No corrective measures required to correct non-performance. However, there are 3 additional research studies that are in progress which one will be concluded by the end of the 4th Quarter and the other two will be concluded in the next financial year. |  |  |  | 

## Slide 21: Program 3: RESEARCH
KPI 16 | Approved Research and Evaluation agenda |  |  |  | 
Object of Change | To set out a framework for research and evaluation work to be undertaken by the NDA periodically. |  | Impact | The NDA has a defined framework that informs research and evaluation work to be undertaken in fulfilment of its secondary mandate. | 
Targets | Annual target | Approved Research and Evaluation agenda | Quarter Target | Consultation with internal and external NDA stakeholders | 
Quarter 3 Achievements | Approved Research and Evaluation agenda was achieved– the research strategy and agenda was presented to the NDA EXCO in the first quarter, and the Board for approval in the second quarter. The agenda aims at supporting the government priority areas which were announced in the state of natation address by the president – it focuses on 4 areas relevant to the NDA mandate. |  |  |  | 
Reason for deviation | Due to findings from Internal Audit on the absence of an approved research and evaluation agenda for the NDA, this KPI was fast tracked and completed before the planned period to ensure that research and evaluations are anchored on strategic priorities of government. |  |  |  | 
Plan to correct non-achievement | No corrective measures required for this KPI as it has been achieved. However, all research studies are now linked to the research agenda and adopted by the NDA and the DSD portfolio on Monitoring, Evaluation, reporting and Research Committee. |  |  |  | 

## Slide 22: Program 3: RESEARCH
KPI 17 | Number of evaluation reports that contribute to development practice |  |  |  | 
Object of Change | NDA Evidence Based Evaluation results that guide and programme design and implementation |  | Impact | The NDA has a defined framework that informs research and evaluation work to be undertaken in fulfilment of its secondary mandate. | 
Targets | Annual target | 3 evaluation reports | Quarter Target | 2 evaluation reports | 
Quarter 3 Achievements | 2 (two) Evaluation Reports were completed during this period. These covered the following operational areas of the NDA programmes. Both evaluations were conducted by Quest Research Services, appointed through a competitive bid process. People with disability income generation projects supporting and; Evaluation of the NDA early childhood development programme as implemented by the resource and training organisations (RTOs). |  |  |  | 
Reason for deviation | There is no deviation from the target. However, the NDA is currently conducting a Rapid Assessment Study on the Volunteers programme that started to be implemented as a response to COVID 19 and will be concluded in the fourth Quarter. |  |  |  | 
Plan to correct non-achievement | The rapid assessment study on the NDA Volunteer Programme is at the data collection stage and its final report is expected by the end of March 2021 and will be used to inform the future plans on this programme by the NDA. |  |  |  | 

## Slide 23: Program 3: RESEARCH
KPI 18 | Number of external dialogues to engage on the NDA research outputs |  |  |  | 
Object of Change | To promote debates and dialogues on development policy, between stakeholders (public, civil society, private and academic sectors) |  | Impact | The dialogues and debates provide a platform for social partners to share the research outcomes and debate on development policy. | 
Targets | Annual target | 5 dialogues sessions | Quarter Target | 3 dialogues sessions | 
Quarter 3 Achievements | 3 policy dialogue sessions were held via virtual platforms with partner research institutions. The dialogues were in the following areas: Creating capabilities and building capacities for the civil society sector in South Africa, in collaboration with HSRC Food Security & Nutrition Dialogue – the impact of COVID-19 on food and nutrition security in South Africa. Hosted in collaboration with HSRC and DSD South Africa’s integrated approach to addressing poverty, inequality and exclusion. Hosted in collaboration with University of Johannesburg, Centre for Social Development in Africa (CSDA) |  |  |  | 
Reason for deviation | The negotiation with institutions with professional webinars platforms was only concluded in September 2020 to provide platforms for conducting dialogue sessions. Thus we started implementing the activities of this KPI during the third quarter |  |  |  | 
Plan to correct non-achievement | There are two dialogue sessions planned which one will be conducted in fourth quarter one on ECD – social and emotional learning for 2-4 years children in ECD centres and Funding Mechanisms of the Civil society Sector. |  |  |  | 

## Slide 24: Program 3: RESEARCH
KPI 19 | Number of times NDA research work is referenced by researchers |  |  |  | 
Object of Change | Demonstrate credibility and relevance of evidence produced by NDA research outputs in the field of development |  | Impact | Increased use of evidence in policy formulation and review by policy makers | 
Targets | Annual target | 5 NDA research work citations/referenced | Quarter Target | 3 NDA research work citations/referenced | 
Quarter 3 Achievements | 3 citations/references made on NDA research published work, there citations were the following: Moreno et al (2018) Cross-Cross cultural perspectives of LGBTQ psychology from five different countries: Current state and recommendations. NDA work cited/referenced Magongo, B. (2016). Enhancing civil society participation in the South African development agenda: The role of civil society organisations. Parktown: The National Development Agency. The Impact of Income-Generating Projects on Stimulating the Development of Entrepreneurial Activities in Communities: The Holding Hands Case, published by the International Journal of Business and Economic Affairs (IJBEA) 1(1), 36-46 (2016). NDA work cited/referenced Magongo, B. (2013). Civil society participation in income- generating activities in South Africa. Faye et al (2020) A Review of the Results of Senegal's Response to the COVID-19 Pandemic Through State of Emergency and Curfew, Sumerianz Journal of Biotechnology, Vol. 3, No. 5, pp. 26-37. NDA work cited/referenced Magongo, B., 2020. "South Africa containment response to COVID-19 pandemic: Review of outcomes |  |  |  | 
Reason for deviation | There is no deviation from the target for this KPI, however, since the indicator relies on outside our control environment we have set systems and process to continuously inform us if there is a new citation or reference of our work in the research environment |  |  |  | 
Plan to correct non-achievement | The research work is continuously uploaded on the research platforms such as ‘Research gate’, to monitor NDA research that has been cited or referenced by other research publications. |  |  |  | 

## Slide 25
Financial Expenditure Report

## Slide 26: REVENUE – QTR 3 YTD – December 2020
YTD under-receipt against full year budget (R12,5 m), relates largely to R9,9m of 2019-20 accumulated funds not yet brought into actual receipts, as the 2019-20 committed expenditure has not yet disbursed, and matching of income to expenses cannot occur.
Under-receipt in conditional grants relates to DSD Limpopo funds ear-marked for capacity building, not yet recognised in YTD receipts, as the expenditure has not yet been incurred.
The Committee to note that adjusted transfer revenue amounts to R216,240 million, as the NDA’s transfer allocation for 2020-21 has been reduced by National Treasury by R8,304 million. This amount was refunded to DSD in January 2021.

## Slide 27: EXPENDITURE PER PROGRAMME – QTR 3 YTD – December 2020
A total amount of R177,7m has been spent to date, which represents a budget utilisation of 51% as at the end of December 2020.
Programme 2 has spent 48% of its full year adjusted budget (incl 19-20 commitments), and has 52% of the budget, remaining for implementation over the last 3 months. Excluding the CARA project, Prog 2 has spent 65% (R85m) of its full year budget, whilst 35% of budget (R46m) remains for spend over the last 3 months. There has been underspending on mobilisation and formalisation, capacity building, NDA grant funding and CARA grants.
Programme 1 has spent 57% of its full year budget, and has 43% remaining for implementation. There has been underspending on consulting & professional fees, IT costs, audit fees, and travel.
Programme 3 has spent 51% of its full year budget, as at the end of December 2020. There has been underspending on research studies, and monitoring and evaluation.
Employee compensation spend is aligned with expected spend, except for the payment of salary increases for the senior management team, that was planned to be implemented in April 2020, but which has been delayed.

## Slide 28: EXPENDITURE VARIANCE ANALYSIS – QTR 3 YTD – December 2020
The NDA has spent R177,7 million to date, and has underspent against the YTD budget by R45,9m.
The main areas of underspending relate to NDA grant funding (R6,6m), CARA (R21m), consulting fees (R3,5m), IT costs (R3,4m), audit fees (R1,3m), travel (R1,1m), capex (R2,5m).
The NDA has put firm plans in place to ensure spend or commitment of the remaining budget before financial year end.

## Slide 29: EXPENDITURE PER PROGRAMME DETAILED– QTR 3 YTD

## Slide 30: PLANS TO UTILISE BGT BEFORE YEAR END PER PROGRAMME – PROGRAMME 2
Mobilisation & formalisation – R1,2m bgt remaining- planned to be spent on integrated development initiatives in EC, FS, KZN and Limpopo. Spend on 16 days of activism projects in EC in Dec 2020 is still to be processed from the remaining funds.
Capacity Building – R2,8 m relates to 3p funded capacity building, based on 3P conditions. R1,1m of budget remains for NDA funded projects – planned to be spent mainly on printed training manuals and producing digital copies of training handbooks on financial management, governance, project management and administration for CSO’s.
Grant Funding – R11,5m of budget remaining. R4,9m relates to funds rolled over from the previous FY, and which will disburse as grant conditions are met. R6,6m of the 2020-21 bgt remains. R3,4m has been assessed by internal management committees and proposed to the Board for approval in Jan 2021. The Board meets at the end of January to consider these projects for approval. The remaining budget of R3,2m is planned to be assessed by the management and governance committees by end Feb 2021, and will be committed in full by financial year end.
The 6 month Volunteer Programme ended in Dec 2020, and the remaining funds of R1,8m will be reprioritised to other priority spend areas.
Project monitoring and support – R2,8m will expend in full by year end due to the volume of CARA projects whose progress is being monitored.
Digitisation of CSO initiatives – the available budget has been reprioritised to R4,5m by the Board, and has not yet been utilised. The TOR’s for Digitisation have been finalised, and were approved by the Board for tender issue on 29 Jan 2021. The tender is in the process of being advertised, and the NDA plans to award this tender and commit the funds before financial year end.

## Slide 31: PLANS TO UTILISE BGT BEFORE YEAR END PER PROGRAMME – PROGRAMME 3
Research studies – R1,59m bgt remaining- part of this bgt includes commitments rolled over from the previous financial year. As the studies commissioned take between 9-12 months to complete, 2019-20 studies to the value of R800k will become payable before current FY end. Some of these studies include – ‘Requirements for Transforming CSO’s’, ‘Civil Society Regulatory Frameworks’, ‘Civil Society Funding Mechanisms’.
Additionally, R770k will be committed to the planned study on the ‘Role of Cooperatives in the Economic Reconstruction and Recovery Plan of SA’. The appointment of a research institution to conduct this study, is at evaluation stage of the SCM bid processes, and will be awarded and committed before financial year end.
Evaluation studies – R724k - A service provider was appointed following SCM processes to conduct a rapid assessment study of the NDA’s Volunteer Programme in response to Covid-19. Approximately R470k has been committed to this study. The remaining balance will be transferred to other areas of priority.

## Slide 32: PLANS TO UTILISE BGT BEFORE YEAR END PER PROGRAMME – PROGRAMME 1
Marketing & communication – R865k – 2 advertorials planned, replacement of branding material for all provinces to be procured before year end.
Consulting & professional fees – R4,5m – skills audit awarded, and committed. Turnaround strategy – TOR’s to be finalised by BSC, and tender advertised, awarded and committed before year end. TOR’s for Brand Strategy to be developed, advertised and committed before year end. Automation of financial reports project – Great Plains – will conclude before year end.
IT Costs - R3,4m – committed to SW licence costs that will be paid before year end for VIM, Vam, Microsoft, Sage, Great Plains
Audit fees – R2,5m – The Auditor-General has commenced the interim audit in earnest, and this budget is expected to be spent or committed in full by year end;
Lease costs – R2,4m – is projected to be spent on monthly lease costs to end of March 2021.
Capex – R3,2m - Disaster Recovery Site tender was awarded in Nov 2020, and implementation is proceeding in the 4th quarter. The full amount has been committed, and will partially expend before year end.

## Slide 33: Recommendation
It is proposed that the Portfolio Committee notes the:
  Quarter 3 performance report; and
  Quarter 3 financial report

## Slide 34: Thank you
THANK YOU