## 5 KPA
I
NATIONAL KEY PERFORMANCE AREA | HIGH LEVEL FOCUS AREAS | STRATEGIC OBJECTIVES | PROGRAMMES | DETAILED QUESTIONS | DOCUMENTATION | COMMENTS
SERVICE DELIVERY AND INFRASTRUCTURE | Integrated human settlement development | All communities housed in formal housing in line with BNG Infrastructure to support human settlement in place Community facilities to support human settlement provided in line with norms and standards | Housing Provision | Does the municipality have a housing plan? Is your municipality meeting the housing needs of the community, if No give reasons. What capacity is required to fulfil this function? Housing backlog? No. of housing projects in progress and planned. What are the major hindrances to the implementation of a housing programme? Is there a plan in place to address this - describe. | Housing Sector Plan,List of Housing Projects | The municipality is in the process of preparing a housing sector plan.There are 6 on going housing projects.500 proposed houses for each of the four wards with Impendle as the developer.The projects are managed by the Director Technical .All the projects at still at the feasibiity phase and some of the projects are alleged to be unviable to attract good implementing agents.The DoH has not provided any administration fees and interest generated from the housing allocation is ploughed back into the housing development.The district has also not provided a commitment letter for the provision of bulk services. Some of the projects are however rural housing projects or insitu upgrades with water being already in place.There is poor coordination with the WSA for the timely delivery of services.Municipality needs a housing administrator
|  |  | Infrastructure to support housing | List of all housing, infrastructure & community facility project currently being implemented | Housing Sector Plan,List of Housing Projects | List of housing projects attached
|  |  |  | Is basic infrastructure such as water, access roads, sanitation etc to support housing programmes in place? |  | District responsible for MIG. Each housing project should have a certificate from district supporting that they will provide bulk infrastructure but no budget provisions have been made to date.All proposed projects are currently at a feasibility stage.
|  |  |  | Are there adequate community facilities such as libraries, sports fields, child care facilities in place to support housing development ? |  | Community facilities have not been provided in accordance with norms and standards. Impendle has one library and one community hall under repair. MPCC complete, recruited tenants for MPCC.There are four halls in the current financial year budget R500 000 each) but there was poor response to adverts for the implementation of the projects. There is need to readvertise and appoint SP
|  |  |  | Backlogs - details for housing,roads,water.Details of asset management plan | Backlog Study | No backlog study. No asset management strategy, no road maintenance plan
| Capital expenditure | Municipality providing the capital infrastructure for sustainable development | Capital budget | % of capital budget over total municipal budget. Expenditure patterns and application of funds. % of capital budget spent.Any MIG projects???Are there any capital projects funded through loan or internal funds? | Capital budget assessment Reports | The municipality does not receive direct MIG funding. Municipality alleges that District does not inlude them in MIG prioritsation processes.Municipality has R3.5m in its capital budget and this takes up 31% of its budget. There is 31% expenditure to date on capital budget. The challenge is sourcing suitable service providers for the halls .The municipality does not have any loans for capital development.
|  |  | List of capital grants received | Provide list of all capital grants received ,source and application incl expenditure as reported in the in year reports. | Budget and AFS | List of grants was provided but the Municipality does not have records of MOAs or Business plans.Total grants R7 828 740.31 and expenditure to date is R2 523 204.03
|  |  | Capital Investment Plan | Has the municipality prepared a 5 yr capital investment plan? | Capital investment plan | No capital investment plan and no maintenance plan for assets created.
LOCAL ECONOMIC DEVELOPMENT | Local Economic Development, Job Creation, Expanded Public Works Programme and Municipal Infrastructure | To create vibrant and resilient local economies | LED Unit and personnel | Does the municipality have an LED Officer/Manager? Is there a staffed unit in place | LED Unit Organogram | There is an LED Officer driving LED in the municipality. No other staff in structure.
|  |  | KZN LED Programme | Does the municipality have an LED strategy? What are the major LED opportunities in your municipality? What role should the municipality be playing in facilitating these opportunities - what is hindering the municipality in this regard? Has the municipality accessed funding through the KZN LED programme? List projects? | LED Strategy | An LED Strategy was prepared at a District Level through Gijima EU Programme.No strategies in place for Impendle.Impendle strrengths are listed in Study. The municipality has not benfitted from the Gijima funding.Had submitted a proposal for support in establishing an LED unit but project was not supported.No LED projects currently running except for piggery and community garderns through Dept Of Agic and these are more aligned to poverty alleviation.The projects are however not viable.Non of the projects are funded by the municipality
|  |  | Provincial programme of learnership and internship on municipal infrastructure | Are there any learnership and interns in the organisation. List details |  | The municipality had 2 interns in LED but these have since been permanetly employed in other positions in the municipality.
|  |  | Operational PMUs to implement MIG | Are you aware of any Programme Management Unit having been set up to assist in implementing MIG in this District? What role do you think the municipality should be playing regarding MIG? |  | Not taking part in MIG prioritisation. Money for current year already spent. There is need to address issue of involvement in MIG with the District
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT | Capacity building, systems, human resource development and improved organizational culture. | A seamless capacitated and transparent government to the people. | Organizational structure and HR systems. (municipal structures) | Does the municipality have an approved organizational structure? Are there job descriptions for each post in structure and do they conform with TASK System and the powers and functions assigned to the municipality? Are all senior management positions filled Provide details of key senior personnel in each department, highest qualification and experience. Provide list of critical vacant positions and critical positions filled in the last year and whether it was vacant or new post. | Organogram | Impendle is a grade 2 municipality with a staff compliment of 39. It has an approved structure signed by unions .Have personnel files for each member of staff but some of the the files do not have proper records. Team to assess files.All staff files are easily accesible. Some of the files do not have signed job descriptions.Job desciptions have been submitted to the Job evaluation Committee.Not all senior management positions are filled.Positions of Manager Development Planning and Manager Corporate Services are vacant. Structure has 5 section 57 positions and only 2 are filled but the incumbents are not regarded as Section 57 although they report to the MM.To provide list of vacant positions.There is a general lack of middle management in the municipality and hence delegations are difficult to implement.
|  |  | Assessment of vacant positions | Provide list of vacant positions and indicate whether approved and budgeted for ,frozen and currently advertised. | List of vacant positions | In finance Finance Officer and Finance clerk not filled.In tech, no housing Adminstrator ,Technician/Foreman and no building inspector.In planning no IDP Officer and Environmental Officer although provided for in structure. Unit has Town Planner and Economic Dev Officer.
|  |  | Turnover of staff, general morale | % of staff budget over total operational budget. How many staff are currently employed? Are all posts filled? If no, what is required to fill these posts? What are the critical posts that need to be filled as a priority? Of the posts that are filled, do the staff have adequate capacity to fulfil their responsibilities or is further training required? Does the municipality have a computerized HR/Payroll system? Does the municipality have conditions of service policies in place? Details of HR conflicts within the organization? Are the staff generally happy? Is the municipality able to keep staff? | Copy of organizational chart. List of staff, Dept. and description of work performed. Details of HR/Payroll system. Absentee Records & frequency of disciplinary hearings. | 30% of staff budget goes to salaries.39 total staff and 4 temps totalling 43 .Impendle total budget R11.2m. Staff packages ( MM R380 000, CFO R348 000,Tech R352 000,Officers R155 000). Conditions of services in place. Municipality has a computerised payroll system but not integrated with FMS.No exit interviews are done to inform staff retention strategies. Rural environment and hence can not attract good people.Training of current staff essential to enhance skillls. Staff turnover is generally too high and no proper records of activities were being kept to inform new incumbents.All the senior staff members are new and have no record of the past activities/projects/documents. The municipality has outstanding labour disputes e.g Finance Officer for the past 2 years.
|  |  | Skills Audit | Has a skills Audit been undertaken? Is there a skills development plan. Is it updated each year and does it get submitted to SETA. What is the % of the operational budget that is spent on staff training | Skills Audit Report, Skills Development Plan | Skills audit done in 2007 by Empilweni.No skills development plan is done annually for submissin to LGSETA as required.Provincial Treasury has done a skills audit for finance staff and there is evidence of a lack of financial skills and competencies in the finance department. An assessment of qualifications of all the 33 staff in the employ of Impendle was done during the review and only 12 had either a diploma or a degree. Most of the senior staff are not qualified to be in positions they are currently occupying. Municipality has a budget for training of R90 000 but only spent 5%.
|  |  | HR Policies | Details of approved HR policies. Recruitment ,selection, dismissal ,S & T,Cellphone etc | Policies | No adopted policies in place. Procedures in place but no clear policy for recruitment, No claims for travelling due to no policy, all ready but not adopted due to section 139. To get all the draft policies and review
|  |  | Staff files | Are staff files well maintained, are relevant docs to be kept in files available, are appointment letters filed including signed job profiles? |  | Staff files are not in order and some do not have standard employee information such as appointment letters,ID ,licence, beneficiary statements, employment contract, qualifications and leave records. Municipality has an unspent grant for a clocking system from MISG for R50 000.
|  |  | Employment Equity Plan | Status |  | Empilweni appointed to do EEP but work was never completed. Work substandard. Not been paid for the work.There is evidence of inability to monitor SP. Service Level agreement in place but no clear deliverables.No HR expert to manage consultant.To check contract
|  |  | Delegations | Has a system of delegations been developed and adopted in terms of Systems Act and MFMA | Delegations register | No delegations register in place.CFO has no signing powers at the bank. Currently Acting MM who was appointed as the LED Officer and Tech Manager have signing powers. This is in contravention of the MFMA
|  |  | Standing rules and orders. | Are the rules of standing orders being applied. | Standing Rules and order | Standing rules in place and alleged to be followed .
|  |  | Execution of resolutions | Is there a system of monitoring the execution of resolutions. Are resolutions executed timeously. Is there effective communication of resolutions to Departments. | Database of resolutions of meetings | Resolutions register in place, not up to date, Report on execution of resolutions done every council meeting.Meetings done every first Thursday of the month. To check resolutions register and council minutes for verification.
|  |  | Meetings | Details of council meetings, how often, what other meetings. Are portfolio committees in place? How functional are they? Are minutes of meetings recorded timeously. Is there e a minute book. | TORs for Portfolio Com,Minutes of meetings | No records management system hence record keeping is very poor. Registry clerk in place but not competent. In process of training. Council meeting once a month. No portfolio committees in place.
|  |  | A programme of Local Government Learnership and Internships | Has a learnership programme on municipal operational and financial management been provided at your municipality? If yes give details. | Details of programmes, content and name of service provider. Names of attendees/ beneficiaries to be supplied. | CFO attended training on budget principles and has on the job training on abacus.No other training has taken place.
|  |  | Kwanaloga executive leadership development programme | When attended and names of attendees. | Training Programme | CFO attended leadership development programme.
|  |  | Management Assistance Programme (financial systems, policies, procedures, internal control, risk management, IT, financial management systems) | Has the municipality been provided with support through MAP? If yes give details of support provided. | Details of programmes, content and name of service provider. | MAP programme useful.Not effectively used. DLGTA to provide details of MAP support
MUNICIPAL TRANSFORMATION AND INSTITUTIONAL DEVELOPMENT | Performance Monitoring, Evaluation and Communication | Accountable and transparent local democracy | OPMS | Is a performance management system in place? What aspects does it cover? What information system exists? Is performance audited. Are performance agreements made public and do they get sent to MEC . Does the municipality have SDBIPs linked to performance agreements? Was an annual report prepared by the end of January including a performance report? Are the targets set in the system realistic and measurable? Have councillors been capacitated on OPMS? | OPMS Framework, System of capturing indicators. Copy of orgaisational scorecard and SDBIPs | No PMS in place ,no support has been received from province to develop OPMS. No performacne agreements in place. Had approached district to deal with performacne contracts but to no avail. No SDBIPs.No Annual report has ever been prepared and no operational plans are in place for units. There are no set targets for the delivery of the IDP and budget
|  |  | Performance Agreements | Number of managers with signed performance agreements vs total. Is there are system of reviewing and evaluating performance . Is there a performance evaluation committee. How effective is it? | Signed performance agreements and annual performance plans. Minutes of reviews, Minutes of Audit Committee meetings | Managers have appointment letters only and no employment or annual performance contracts and plans.CFO contract not signed by MM.Former MM refused to sign contract .Municipality did not seek legal advise to deal with matter. A resolution was taken for Audit Committee shared services but not implemented. Umngeni indicated that Impendle was to contribute R150 000 for the shared services and the discussions failed. To check with Umngeni.
MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT | Financial Sustainability | Self sustained and financially viable municipality | Budget | Was 2007/08 Budget prepared on time and following recommended procedure in terms of budget circulars? Was budget accompanied by the relevant documentation in terms of MFMA S 17 .3? Was the 2007/08 adjustment budget prepared and was a mid year assessment undertaken? Are plans already underway for the preparation of the 2008/09 budget in line with approved process plan? Does the Mayor understand role in IDP and budget preparation to approval. |  | 2007/08 prepared on time but was not adopted on time.Only adopted on the 29th June. 2007/08 Adjustment budget tabled in January. No alignment of IDP,PMS and budget in the current year. IDP does not have a financial plan. Community participation in IDP not done properly hence delays in approvals.Municipality has not appointed SP for conversion. Have prepared a conversion plan.Siyaya Management Services appointed to assist with conversion. .Budget not GRAP compliant.The 2008/09 process plan was adopted and is being followed. Mayor aware of her roles in terms of IDP and budget.No training has however been undertaken for Councillors on budgetting.
|  |  | Operating budget | Is it balanced and cash backed? Does budget include provisions for bad debt, indigent provision,provision to repay creditors. Does actual income and expenditure compare with budgeted income and expenditure.List of grants received and application including expenditure to date. |  | The budget is balanced and cash backed but there are roll overs due to late appointment of service providers. Budget makes provision for bad debt at 1% of debt.Current Debt stands at R178 888. Debts from dismissals not included.List of grants received- HIV R49 000,FMG ,Tourism, Community Communication Initiative, IDP Inter monitoring, MAP , Community garderns,Libraries, CDWs, DBSA R94 0000-.Challenge is that the business plans and MOAs for the grants are not in files and hence in some cases municipality is not sure of the application of the grant funding.
|  |  | Financial Policies and procedures | List of policies in place and gaps |  | No Financial policies have been formally adopted.All are in draft format as appointee was stopped by Prov Treasury. To provide list and copies of policies.Service providers stopped to avoid duplication with Prov Treasury Work.
|  |  | AFS | Status of Financial Statements submission to AG 's Office and Status of Audit Opinion for past 3 years |  | Have prepared AFS and hae received AG report with a disclaimer.
|  |  | IDP | 5 yr IDP document in place,IDP reviews undertaken. IDP aligned to budget. Municipality has a vision and mission statement. IDP objectives clearly stated and linked to municipal budget. Did IDP undergo public consultation. Minutes of IDP Forum. Is IDP done in house or by consultants. Is there a member of staff responsible for driving IDP.Does IDP have multi year budget and 5 year capital works plan.Is there an IDP Implementation report submitted quarterly. Does each dept have an operational plans and SDBIPs linked to IDP objectives?? | IDP,IDP Review, MEC Comments,IDP Process Plan,Adverts for public comments, notices of meetings for IDP review, IDP Forum list | IDP in place and reviews are undertaken in line with process plan. Public consultation is undertaken through Newspapers and notices at tribal courts. IDP Forum in place. IDP is done inhouse.Copy of comments from IDP Engagements to be provided.Municipality is in the process of finalising Spatial Development Framework and LUMS as part of the IDP Review. The IDP is prepared by the Town Planner as there is no IDP Officer.IDP implementation poor as there is no PMS or SDBIPs with clear targets for monitoring.
|  |  | MFMA Compliance | In year reporting etc |  | Assessment done under separate cover
|  |  | SCM | Is there a Policy on SCM in compliance with MFMA, Was the policy approved by council and is it in line with BBBEE and PPPFA. Have the bid committees been established and how functional are they? Is there a manager responsible for SCM and is the person appointed in line with competenccy framework? Any training in SCM for bid committee members.Do the Bid Committees have proper terms of reference.Does the municipality report quarterly to Council on the implementation of the SCM policy.Does the municipality keep a record of tender awards. Does the municipality have a database of service providers. How is it managed and maintained? | SCM Policy,TORs for bid Committees, List and designation of bid committees membership | No SCM policy has been adopted but using draft prepared by Service Provider .Bid Committees are in place since Sept 2007 but bid specs are done by procuring department.Due to lack of senior management bid committees are comprised of unqualified staff. Had a briefing by treasury but no formal training as yet. Negotiating with SAMDI for futher training in SCM. Provincial training offers taining for one person at a time. All 3 bid committees are place but no evidence of TORs was provided except for letters of appointment to service on the bid committees.Signed acceptance letters were provided. CFO sits in the adjudication committes.There was no evidence of signed declaration of interest . Bid Com met for only 3 tenders which are above the threshold for quotes : GMAP,Vat and housing sector plan.Quotation system needs to be reviewed
|  |  | Audit Committee | Is it in place, is it functional, who are the members, how often does it meet,get minutes of the Audit Committee meetings.Is there a charter to guide Audit Committee? | Minutes of audit Committee meetings, Audit Reports | Audit Committee not in place.Investigating shared service with Umngeni.Have R150 000 in budget for audit
|  |  | Internal Audit | Is it in place, is it functional,who does it report to. Is there an audit Plan and program for the year? Has a risk assessment been undertaken.If not assess possibility of outsourcing function | Structure of internal audit,internal audit plan,organisational risk assessment report | Internal Audit is not in place.Investigating shared service with Umngeni
|  |  | Asset Register | Does the municipality have an asset register?Is it maintained? Are all assets clearly marked and reconciled to asset regster.Check compliance with GMAP. | Asset Register | Municipality has no asset register.Prov treasury had indicated they will do the asset register. Assets are not marked at all.Siyaya contract cancelled before finalising asset register.
| Free basic Services which target poor households, appropriate billing systems and a reduction in municipal debt | Provision of FBS targeting poor and ability to collect | Integrated billing and debt management system | Has the municipality completed a land audit i.e. record of every property and owner? Has the municipality started to develop a rates policy and valuation roll? Date of implementation? Does the Municipality have an integrated billing and debt management system in place? If yes is it successful; what problems are being experienced. If no what is preventing the municipality putting this in place? Is there a credit control policy.Is there capacity to implement or is it outsourced ? Does the municipality have adequate pay points? Is there capacity to collect debt.Are there adequate customer enquiry centres. Are meters read regularly | Land Audit Report, Rates policy, Credit control policy | In the process of appointing SP for valuation and to include land audit. Province is finalising arrangements for co funding as the municipal budget is not adequate.Implementation is June 2009. Municipality uses Abacus as FMS and does billing for water on behalf of the district. No evidence of a service level agreement was produced. Municipality does not have a credit control policy and can not handover debtors.Has no capacity for debt collection. The municipality has one pay point at the offices. No customer care and help desk.
|  |  | FMS | Billing System used and effectiveness.What financial software package is used | assess software | Billing system not so effective. Abacus is the FMS
|  |  | Municipal indigent policy | Does the municipality have an indigent policy? What areas does it cover?Is there an indigent register ? How often is it updated? | Indigent policy and register | A draft indigent policy is in place but no indigent register as process was stopped by DLGTA Finance Unit. Currently supporting a few indigents on the ESKOM database.The R668 000 ES allocation for FBE and others is utilised for the support to indigent families.
|  |  | FBS | What are the major hindrances to providing free basic services? What other infrastructural priorities exist in the Municipality e.g. roads, public transport, health, schools? Which would you classify as the highest priority? | FBS Policy | No indigent policy or register and hence can not effectively provide FBS.Only for Electricity through ES. Considering for refuse removal
| Public empowerment, participation and community development | Deepen community participation in municipal governance and local service delivery | Ward Committee | Have ward committee been established in all wards? How was the establishment process undertaken? How representative are the WCs. Is there a policy for ward committees. How functional are the WCs, How often do they meet?Have they received any training in the past 12 months?State nature and duration. | WC Policy and details of membership | Isibuko seAfrica was appointed through province to establish ward committees in all wards.Not fully functional and not trained. No policy for ward committees has been adopted and no budget is allocated for ward committees.
|  |  | CDWs | State number and wards. Assess linkage with ward committee system. Reporting lines in municipality. | Reporting document for CDWs | 2 CDWs in place. Allocation of R14 000 from province is utilised for operational requirements and tel allowance. Have been provided with a computer.Considering getting a laptop. CDWs have good relations with ward councillors are well integrated into the municipality
|  |  | Traditional Authorities | Assess relationship of municipality with traditional leaders.How are they involved in municipal activities. | Traditional Leadership Engagement Framework | 4 TA- nxamalala,Dlamini Mulefu and Basotho. Nxamalala & Basotho involved in council activities.All housing projects are in traditional authority land
|  |  | Community Imbizos | List details of community imbizos held and attendance. | Public participation report | No imbizos are held .Road show attempts failed. Cant use schools but sports grounds and open air.Last process was rushed. Mayor and MM were not in talking terms. Councillor contribution to budget was limited and hence delays in budget approval.
|  |  | Communication plan | Is there an approved communication plan and strategy, is it being implemented. Does municipality have a website and newsletter.Is there a complaints management system and information desk? | Communication Plan and calendar of events | No communication Strategy. Have a website but not updated. www.impendle.gov.za. But the domain could not be found upon checking. No IT .no newsletter,have advertising centres in tribal authority, ward committees.Paid R11 000 to Service Provider for website but no website running.Municipality does not have an annual calendar of events to inform the various processes in the municipal year.
|  |  | Councillor Training on Community Participation | Have councillors been trained on community participation.State nature of training and effectiveness | Training Programme | Details of councillor training: IDP through Vantage,Non got certificates as they did not bother finish. No budget for councillor training.
|  |  | Unit responsible for public participation in place | is there a champion in organisation for public participation and ward committees?? |  | No unit responsible for public participation. However municipality has a grant for Communication Initiative and this has not been utilised as there is no business plan in files to indicate the use of the grant. There is no dedicated resource to deal with public participation.
| Anti-Corruption | Clean and accountable government | Anticorruption policy | Has this been a problem over the past 12 months and have there been notifiable cases or criminal charges layed? | Anti corruption policy and strategy | A comprehensive risk assessment was done by provincial treasury and Ptreasury is ready to come for a presentation.Municipality has not seen any documentation/ report on the risk assessment.No anti corruption policy or strategy .
|  |  | Internal Audit and AG reports | Has the Auditor General raised any queries with regard to fraud and financial misconduct? Describe areas of where the municipality is particularly vulnerable to corruption. Does the municipality have access to any Provincial policies or support? If yes are they effective and useful? If no - do they need them? | AG report | Financials have a disclaimer
|  |  | Internal controls and risk assessment | Assess effectiveness and issues raised in AG report on controls.Has a risk assessment been undertaken. Is there a risk management plan | Risk Assessment | Assessment done by Provincial Treasury but not yet presented to municipality

## MFMA
Assessment Impendle Municipality-5 February 2008
A | DEBTORS ADMINISTRATION | RESPONSE - CFO (05-02-2008) | Proposed action | Due date
1 | Are all accounts sent out on a monthly basis? | Yes | No action.
2 | How often is the debtors control account balanced? | No-objective to balance monthly | Debtors control account must be balanced and then monthly thereafter | 2008-03-31
3 | Are all transactions updated on a monthly base to the general ledger ? | No-Updated every six months. | Must be updated every month | 2008-03-31
4 | What is the average payment rate? | 40,39% | Compile indegent register and pass entries for subsidy | 2008-06-30
5 | Are accounts sent out correctly? | Yes | No action.
6 | Are consumer deposits sufficient? | No Deposits | No action.
7 | Are consumer deposits adjusted regularly through a system? | No | No action.
8 | Is the deposit control vote balanced monthly? | No | No action.
9 | Is the meter reading system satisfactory? | No meter readings | No action.
10 | Is the meter reading function outsourced? | No service | No action.
11 | Are meter readings captured manually or electronically? | No meter readings | No action.
12 | What is the frequancy of enquiries on accounts? | Three to four per month | No action.
13 | What is water and electricity lossess? | No water and electricity services | N/A
14 | Is statistics kept correctly on sales and purchases both units and value? | N/A | N/A
15 | What is the total outstanding debtors? | R165 777 | Noted
16 | What is provission for bad debts? | R19 136 | Must be revised | 2008-03-31
17 | Please supply age analyssis(2007/8 of debtors | System cannot provide correct information | Service provider must correct | 2008-03-31
18 | Are all meters read monthly? | No meter readings | N/A
19 | Are cut - offs performed regularly? | No | N/A
20 | Is the payment of services prioritized? | No | They only have rates that is levied monthly
21 | Is pre-paid vending machine system satisfactory? | No pre-paid | N/A
22 | Are write-offs of debt done frequently? | No- Indegents register not in place | Indigent register to be compiled and the write-offs can be done | 2008-06-30
23 | Does Council make use of an attorney to recover debt? | No | Attorney to be used when idegent register has been don | 2008-06-30
24 | Are indigent people identified and captured on system? | No | Indigent register to be compiled | 2008-06-30
25 | Are FBS systems in place ?
26 | Is data cleansing necessary? | No | No action.
27 | How is remote paypoints cash collected? | No remote paypoints | No need.
28 | Are handwritten receipts in use? | Yes | Receipts must be computerised | 29 February 2009
29 | What is the control over hand receipt books? | Revenue clerk balances daily | No action.
30 | Does organs of state owe Council money? | Yes | No action.
31 | Are such cases reported i.t.o. legislation | No | Will be reported to national and provincial treasury | 29 February 2009
32 | Is a meter audit to be performed? | No meters | N/A
B | ACTS-MFMA/MPRA
1 | Has a implimentation plan for the MPRA been approved? | Yes | No action
2 | Are you in line with the planning module? | Yes | The progress in terms of the plan to be monitored | 2008-02-29
3 | Has a implimentation plan for the MFMA been approved? | Yes | No action
4 | When is the planned implimentation date of MPRA? | 2009-07-01
5 | Has a provider for compilation of valuation roll been appointed? | No | Bid will be awarded before end of February 2008 | 2008-02-29
6 | Will Municipality need assistance with implimentation? | Yes | DBSA deployee can assist | 2009-06-30
7 | How far is the implementation of the MFMA? | 60% | Implement PMS ,employment and performance contracts to be completed | 2008-06-30
C | ASSET REGISTER
1 | Is the asset register up to date? | No | All assets to be numbered and asset register compiled | 30 April 2008
2 | Are all assets identifiable and numberred? | No | Service provider to be appointed to perform this | 2008-02-29
3 | Are assets unbundled for GAMAP/GRAP purposes? | No | When assets register has been compiled this can be done | 2008-07-31
4 | Are assets controlled through the financial system? | No | System to manage assats to be implemented | 2008-07-01
5 | When last was a asset count performed? | Never | No action
6 | Is the register compiled GAMAP format? | No | New asset register will complied to GAMAP/GRAP | 2008-06-30
7 | Are assets maintained/safeguarded properly? How is it done? | Locked up and night guard | No action
D | AUDIT
1 | Has an audit report for 2006/2007 been received? | Yes-Disclaimer | No action
2 | Has audit report with management responses on it be tabled to council | Yes -25 January 2008 | Follow-up to ensure corrective actions be implemented | 2008-03-31
3 | Do you need assistance on problem areas of the audit report? | Yes -capacity not available | DBSA deployee to asssist | 2008-03-31
4 | Do you have an internal audit unit? | No | Possibility of shared service to be investigated. | 2008-03-31
5 | Is a Audit committee opperative? | No | Possibility of shared service to be investigated. | 2008-03-31
6 | Do you have an performance audit committee? | No | Possibility of shared service to be investigated. | 2008-03-31
E | BUDGET
1 | Timetable approved?(Budget and IDP)-31 August | Yes | Ensure that budget process is according to the plan | 2008-02-29
2 | Are you in line with the time table? | Yes | Ensure that budget process is according to the plan | 2008-02-29
3 | Budget linked to IDP? | Yes | No action
4 | Has SDBIP been approved-28 days after budget approval | No | SDBIP will be compiled for 2008/9 | 2008-05-31
5 | Need assistance in compiling 2008/2009 budget? | No | No action
6 | Has a budget-and treasury office been established | Yes | Staffing to be finalised | 2008-03-31
7 | Has a budget cash flow been drawn up? | Yes | No action
8 | Has an adjustment budget been approved? | Yes | No action
9 | Is expenditure control exsercised? | Yes | No action
F | CASHFLOW
1 | Is cashflow projections done on monthly basis? | Yes | No action
2 | Is it compared with budgetted projections? | Yes | No action
3 | Are remedial actions taken if applicable? | Yes | No action
G | COMMUNICATION
1 | Do you experience communication problems inter- departmentally? | No | No action
2 | Are there weekly/monthly management meetings? | Will start with weekly meetings. | Ensure implementation
3 | Is monthly reporting done? | Yes | Ensure implementation
H | CREDITORS
1 | Are creditors paid on a 30 day basis? | Yes | No action
2 | Is a procurement unit/system in place? | Yes | Procurement committees to be trained | 2008-03-31
3 | Are spendings on project contracts properly managed? | Yes | No action
4 | Are creditors outstanding for more than 60 days? | NO | No action
5 | If yes,what is the reason for that? | N/A | No action
6 | Are all creditors reconciled with system at every payment? | No- Started to use creditors module. | Financial system to be implemented fully | 2008-04-30
7 | Is the control account balanced monthly? | No | Ensure monthly implementation once creditors are on system | 2008-03-31
8 | Are all creditors paid through financial system? | NO | Will be implemented | 2008-03-31
9 | Are all transactions update monthly to the general ledger? | No -Monthend journals are processed | No action
10 | Are sufficient control measures in place for procurement and payments? | No -with new organogram it will be addressed | Staff structure to be implemented | 2008-03-31
o
I | DELEGATED POWERS
1 | Is a delegated system approved and maintained? | No | Delegation register must be developed and approve by council
2 | Supply a copy of the delegations. | N/A | No action
J | FINANCIAL STATEMENTS
1 | Was AFS done by yourselves or outsourced? | Outsourced | Training and assistance will be given with compilation of 2007/8AFS
2 | Need assistance for compiling 2007/2008 AFS? | Yes | DBSA deployee will provide assistance | 2008-08-31
K | FINANCIAL SYSTEM
1 | Are all staff members well acquainted in operating the system? | No.Busy with training | Ensure training by service provider is given | 2008-03-31
2 | Are all work regularly updated? | No.Busy with training | Ensure training by service provider is given | 2008-03-31
3 | Are daily/monthly backups done? | Yes | Ensure that backups are kept at different venues. | 2008-02-29
4 | Who is responsible for updating the various modules on the system? | Revenue clerk and Intern | No action
5 | Who verifies whether this was done? | CFO | No action
6 | Is training needed? | Yes | Service provider to provide training | 2008-03-31
7 | Is the system in balance and maintained as such? | No | Ensure fully implementation of financial system | 2008-06-30
8 | Is the system set up in such a way that controls are enhanced? | Yes | No action
L | INTEGRATED DEVELOPMENT PLAN
n
1 | Financial plan included? | No | Financial plan must be compiled for inclusion in reviewed IDP | 2008-03-30
2 | When last was it reviewed? | 2006/7 | No action
M | INVENTORY
1 | How often is stock taking performed? | No Stores | No action
2 | Are measures in place to prevent "outdated" stock? | N/A | N/A
3 | Monthly balancing to control account performed? | N/A | N/A
N | JOB DESCRIPTIONS
1 | Are all staff members in posession of a comprehensive job description document? | Yes | No action
2 | Are workflow charts for every discipline in place(i.e.debtors,creditors,etc) | Yes | No action
3 | Are proper operating manuals inplace for all disciplines in finance? | In process | Procedures to be developed | 2008-08-31
O | POLICIES
1 | Are the following policies approved and in operation?
a | Asset Management | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
b | Budget | Compiled not approved | Policy to be work shopped and approved by council | 1900-01-29
c | Credit Control and Debt Collection | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
d | Fraud Prevention | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
e | Indigent | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
f | Investment and Cash Management | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
g | Rates | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
h | Supply Chain Management | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
i | Tariff | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
j | Travel and Subsistance | Compiled not approved | Policy to be work shopped and approved by council | 2008-04-30
k | Accounting Policy | No | Policy to be compiled, work shopped and approved by council | 2008-04-30
P | RECONCILIATIONS
1 | Are the following reconciliations done on a monthly base?
a | Bank | Yes | Ensure correctness | 2008-02-29
b | Creditors | No | Ensure monthly reconciliation | 2008-03-31
c | Debtors | Yes | Ensure correctness | 2008-03-31
d | Inventory | N/A | No action
e | Salaries | Yes | Ensure correctness | 2008-03-31
f | Valuation roll | No | No action. New valaution roll will be reconciled
Q | REGISTERS
1 | Are the following registers in place?
a | Investment | Yes | Ensure correctness and balancing with general ledger | 2008-03-31
b | Database for service providers | Yes | Ensure regular updating | 2008-03-31
c | Loans | No loans | N/A
d | Contracts(Projects) | No | Contracts register to be implemented | 2008-03-31
e | Deposit | No | No action
f | Asset | No | Asset register to be compiled by service provider | 2008-04-30
R | REPORTING
1 | Are the following reporting done?
a | Section 54-MFMA-Mid-year budget and performance report | Yes | No action
b | Section 127-MFMA-Annual report | No | Steps must be taken to ensure compliance for 2007/8 annual report | 2009-01-31
c | Quarterly on SCM implimentation | No | Must be implemented | 2008-04-30
d | MIG spendings report-monthly and quarterly | No MIG grants | No action
e | FMG spendings-monthly | Yes | No action
f | Contracts exceeding R 1 000 000 over 3 years-quarterly | No such contracts | No action
g | Public Private Partnerships-quarterly | Yes | No action
h | Municipal entities-quarterly | Yes | No action
i | Section 52-MFMA-quarterly-budget implimentation | No | Must be implemented | 2008-04-30
j | Section 11-MFMA-quarterly-withdrawals not approved | Yes | No action
k | Section 72-MFMA-review performance of Mun. | Yes | No action
l | Annual performance management report-DORA | No | Must be implemented | 2008-07-31
m | Section 66-MFMA-monthly salaries and wages | No | Must be implemented. | 2008-04-30
n | Section 70-MFMA-impending shortfalls,overspendings,overdrafts | No it was not necessary up to now. | No action
o | Section 8/9-MFMA-bank account detail | Yes | Ensure compliance | 2008-06-30
p | Deviations from the supply chain policy? | No deviations | No action
S | SALARIES
1 | Are you experiencing problems as far as cashflow is concerned? | No | No action
2 | Are salaries reconciled monthly? | Yes | No action
3 | What system is in operation? | Payday | Noted
4 | Are all benefits paid monthly in time? | Yes | No action
5 | Are receipts issued for employee service account deductions? | No | Ensure that employees pay their accounts | 2008-03-31
6 | Is sufficient controls in place to prevent"dummy" employees? | Yes- Will introduce clock system | Clock system to be investigated as well as controls on recruitment and exits
7 | Is the leave provision adequate? | No | Leave provision to be calculated and compared with provision in budget | 2008-02-29
8 | Are a proper record kept of all leave accrued / taken / due? | Yes | Ensure that record keeping is adeguate | 2008-04-30
9 | Are personel files kept up to date? | Yes | Ensure that system is operational | 2008-03-31
10 | Are there any outstanding debt ito salaries and benefits to 3rd parties? | No | No action
T | SUPPLY CHAIN MANAGEMENT
1 | Are committees been instituted? | Yes | No action
2 | Who does the specifications for procurements? | Each Department | No action
3 | Who does evaluatians for procurements? | Evaluation Committee | Training must be provided | 2008-04-30
4 | Who does adjudication for procurements? | Adjudication committee | Training must be provided | 2008-04-30
5 | Is the system operation effectively? | Yes | Ensure proper fnctioning of system
U | TRAINING
1 | Is there a need for training? | Yes | Training needs to be assessed | 2008-03-31
2 | If yes, what type of training and how many staff are involved? | All financial areas. Eight | Training needs to be assessed | 2008-08-31

## P & F
Municipality: Impendle
MUNICIPAL CAPACITY ASSESSMENT FOR POWERS AND FUNCTIONS
FUNCTION AS PER CONSTITUTION SCHEDULES 4B AND 5B | PERFORMED BY MUNICIPALITY ITSELF | PERFORMED BY EXTERNAL AGENT(NAME) | WHERE PERFORMED (In township areas only, or for the entire Municipal area) | SHOULD BE EXECUTED BUT NO CAPACITY | UNNECESSARY/NOT APPLICABLE
Air pollution
Building regulation | no |  |  | yes
Child care
Fire (shared) | no | Umgungundlovu District | entire
Disaster Management |  | Umgungundlovu District | entire
Local Tourism | yes
Municipal airports | n/a
Municipal planning | yes |  | entire
Stormwater management systems | yes |  | entire
Trading regulations |  |  |  | yes
Public Transport
Beach | n/a
Billboards | yes |  | entire
Cemeteries | yes |  | entire
Cleansing | yes |  | entire
Control of Public Nuisance | no |  |  | yes
Liquor regulation | no |  |  | yes
Animals pounds etc | no |  |  | yes
Fences | no |  |  | yes
Dog Licensing | no |  |  | yes
Regulation of food sales | no |  |  | yes
Local amenities | yes |  | entire
Local Sports Facilities | yes
Markets | no |  |  | yes
Abbatoirs | no
Parks and Recreation |  |  |  | yes
Roads | yes |  | entire
Noise pollution
Refuse removal | yes |  | townships
Street trading | yes
Street lighting |  | ESKOM
Traffic and Parking | n/a
Housing | yes |  | entire
Note: Housing is not a listed in schedule 4B and 5B functions for LM's, but should be included in this schedule
(complete in consultation with municipal officials)
Source Demarcations Board Web site

## Housing
IMPENDLE MUNICIPALITY HOUSING PROJECTS LIST
| Name of housing project | Ward | Number of beneficiaries | Amount of subsidy | Status of services- water, sanitation and roads | Tribal Authority | Progress to date | Challenges
1
2
3
4
5
6

## STOPPED PROJECTS
LIST OF STOPPED PROJECTS
NAME OF PROJECT | PROJECT VALUE | SOURCE OF FUNDING | NAME OF SERVICE PROVIDER | EXPENDITURE TO DATE | STATUS OF PROJECT PROGRESS | DATE PROJECT STOPPED
| R900 000 | Municipality | Siyaya Management Services | over 70% | stopped and non of the deliverables were achieved
Deliverables
Revised AFS 2006/07
GMAP compliant asset register reconcilling to ledger
Workshop reviewed and developed financial policies
GRAP conversion plan
GMAP version of revised 2006/07 AFS
Clear 2004 to 2007 audit queries
Status quo analysis

## Grants Received
ASSESSMENT OF GRANTS RECEIVED
Name of grant | Source | Grant Amount | Date of transfer/MOA | Name of Service Provider appointed | Date of appointment | Balance | Project Progress | Challenges | Alternative use
HIV | Umgungundlovu DC | 100000 | 2004-07-01 | various |  | 49620.5
MFMA Implementation | DLGTA | 145000 | 2005-10-01 | Roshan Morar |  | 100000 |  | No MOA/Business Plan | Property rates
Tourism | Umgungundlovu DC | 100000 | 2004-02-01 | no appointment yet |  | 100000 |  | No MOA/Business Plan
Community Communication Initaitive | DLGTA | 50000 | 2004-10-01 | Vantage |  | 21500 |  | No MOA/Business Plan
IDP Review | DLGTA | 300000 | 2001 to 2007 | MHA and S Zuma |  | 207500
Interdepartmental monitoring | DLGTA | 100000 | 2005-05-01 | not appointed |  | 100000 |  | No MOA/Business Plan | Property rates
LUMS | DLGTA | 250000 | 2003/2005/2007 | MHA |  | 131183.9 |  |  | Property rates
Municipal Propoerty Rates | DLGTA | 228000 | 2005 | Dataworld,Zitha Attorneys |  | 75548.4
Financial Management Grant | National Treasury | 1250000 | 2004/2007 | various |  | 350693
DBSA | DBSA | 587000 | 2005 | various |  | 94921.86
MAP | DLGTA | 2700000 | 2004 to 2006 | various |  | 968804.32
Community Gardens | Department of Health | 285000 | 2005-04-01 | various |  | 130392.33
Library Services | DLGTA | 3139792.17 | 2005 to 2007 | Various Construction |  | 0
Housing Services | Department of housing | 312500 | 2005/2006 | Various Construction |  | 50419
CDWs | DLGTA | 24000 | 2005-12-01 | Various |  | 14455.34
Capacity Support | DLGTA | 400000 | 2006/2007 | Khulekani Zulu |  | 298410.73
MSIG | NT | 734000 | 2007-07-01 | advertising costs |  | 728868.51
Housing Services Ward 2 | Department of housing | 650655 | 2007-08-01 | Various Professional SP |  | 400855 |  | No capacity
Housing Services Ward 3 | Department of housing | 650655 | 2007-09-01 | Various Professional SP |  | 367015 |  | No capacity
Housing Services Ward 4 | Department of housing | 650655 | 2007-10-01 | Various Professional SP |  | 473805 |  | No capacity
Free Basic Services Electricity | National Treasury | 668000 | 2007-11-01 | Eskom |  | 641543.42 |  | No indigent Register

## Staff Infor
| Name & Surname | ID Number | Permanent/ Temporary | Department | Designation | Salary Level | Qualifications | Post ID | Date of appointment | Job description in place | Position occupied before current appointment
1 | Phindi P | 5912300753085 | P | Corporate | Committee Officer | 104690.88 | Bachelor of arts | CSS003 | 1/10/2002 | No | Educational Opportunities Council
Gcaba
2 | Sibongile A Dlamini | 7701050355086 | T | Corporate | Secretary: Mayor | 104690.88 | Bachelor of Administration in Public | CSS012 | 17/05/2006 | No
3 | Thabani S.Khwela | 6708025513088 |  | Finance | CFO | 300000 | National Diploma in Accounting | FDS001 | 1/5/2007 | No | n/a
4 | Trevor G | 7405085231086 | P | Finance | Financial Officer | 122139.36 | No Qualification | FDS003 | 2/6/2003 | No | n/a
Pitout
5 | Bawinile S. Mkhize | 7306060840083 | P | Finance | Jnr Revenue Officer | 104690.88 | Executive Secretarial Diploma | FDS002 | 1/7/2001 | No | Clerk
6 | Lindiwe P. Mhlongo | 6512241174083 | P | Finance | Cashier | 61406.4 | Secretarial Course | CSS004 | 1/10/2002 | No | Girl Friday/enquiry Clerk/Teller
7 | S.K Chirwa | 7909055820083 | T | Finance | Finance Intern | R160 000.00 | Honours Degree in Policy & Development | INT002 | 2/4/2007 | No
8 | N.L Nzimande | 8402280614082 | T | Finance | Finance Intern | R160 000.00 | B com in Economics and supply chain | INT001 | 2/4/2007 | No | Receptionist
9 | Zamaswazi P. Nkosi | 8102160513087 | P | Corporate | Secretary:Corpporate Services | 104690.88 | Diploma inPublic Relations &Media Studies | CSS012 | 1/11/2002 | No | Receptionist,Customer clerk Services Clerk
10 | Themba Phoswa | 7502110329081 | P | Corporate | Human Resource Officer | 122138.88 | Degree Bachelor of arts/ HR Diploma | CSS013 | 1/6/2006 | No
11 | Penelop V. Mjwara | 8509010923086 | P | Corporate | Receptionist | R48 290.93 | LED Certificate | CSS015 | 2/01/2008 | No | Administration ,Bookeeping
12 | Nondumiso N.Zondi | 8410310419083 | P | Corporate | Registry Clerk | R48 290.93 | LED Certificate | CSS014 | 2/01/2008 | No
13 | Vusumuzi S. Dlamini | 5309095288080 | P | Corporate | Security Guard | 50488.32 | Handgun Certificate | TSS05 | 1/7/2001 | No
14 | Masidada Ngubane | 4807255552089 | P | Corporate | Security Guard | 50488.32 | Shootung Certificate | TSS004 | 1/7/2001 | No
15 | Nokuthula E. Zuma | 5901060341082 | P | Corporate | General Worker/Assistant | 38351.76 | n/a | CSS002 | 1/7/2001 | No | n/a
16 | T M. Ngcobo | 5107095378087 | P | Corporate | Hall Caretaker | 38351.76 | n/a | CSS007 | 1/7/2004 | No | n/a
17 | Sanele J.Thabethe | 8101195394083 | T | Corporate | Mayoral Aid | 53663.28 | VIP Protection Cert. | CSS011 | 11/4/2006 | No | n/a
18 | Sfiso B. Funeka | 8312276220085 | T | Corporate | Mayoral Aid | 53663.28 | VIP Protection Cert. | CSS009 | 11/4/2006 | No | n/a
19 | Ndodo S. Mthembu | 8012105932088 | T | Corporate | Mayoral Aid | 53663.28 | VIP Protection Cert. | CSS010 | 11/4/2006 | No | n/a
20 | J.A.C Mumford | 5209155139183 | T | Technical | Executive Technician | 300000 | No Qualifications | TECHIN02 | 16/05/2007 | No | n/a
21 | Sandile L. Mkhize | 7508145712084 | P | Technical | LED Officer(AMM) | 122139.36 | Undergraduate Public Mngt; Office Admin | CSS006 | 1/10/2002 | No | Office Assistant
22 | G.K Zulu | 7708055727086 | T | Technical | Development Planner | R150 000.00 | Town & Regional Planning Diploma | DPLAN01 | 1/5/2007 | No
23 | Bhekukwenza R. Ndlovu | 5810205433086 | P | Technical | General Worker | 50488.32 | n/a | TSS005 | 1/7/2001 | No
24 | Bhekekhaya L. Ngcobo | 5107095378087 | P | Technical | Messenger/Driver | 50488.32 | Driving Technique Cert. | TSS007 | 8/3/1999 | No
25 | G.G Mkhize | 7112030687087 | P | Technical | Librarian | 65874 |  | TECH04 | 1/8/2007 | No | n/a
26 | P.R Nkomo | 7602145333080 | P | Technical | Library Assistant | R48 290.93 | National Diploma in Mechanical Engineering | TECH05 | 30/8/2007 | No | Field Worker;Management Graduate Worker
27 | B.Mzilikazi | 7609190407081 | P | Technical | Library Assistant | R48 290.93 | Receptionist Diploma | TECHO6 | 3/9/2007 | No
28 | BS Dlamini |  | P | Technical | Cleaner Library | R38 359.89 | Matric | CSS014 | 1/11/2007 | No | Hiv & Aids Communicator
29 | Nozipho B.Gwala | 8307250841088 | T | Technical | Tech Intern | 21600 | N4 Human Resource Mngt Certificate | CSSINO1 | 1/9/2007 | No | Cleaner
30 | J.C Moloyi | 6612075697082 | T | Technical | Temp Security Gua rd | 29760 | No Qualifications | TEMP002 | 22/2/2007 | No
31 | Malusi S Dumakude | 7802155442082 | T | Technical | Temp Security Guard | 29760 | No Qualifications | TEMP001 | 19/6/2004 | No
32 | Mandlakhe R. Zulu | 5312225297088 | T | Technical | Temp Security Guard | 29760 | No Qualifications | TEMP003 | 28/9/2007 | No
33 | Thobile M. Ngcobo | 8110100629087 | T | Corporate | Hr Intern | 21600 | National Diploma in Human Resource Manager | CSSINO2 | 2/01/2008 | No
38
39
40
41
42
43
44
45
46
47
48
49
50

## Action Plan
KPA | TASK ID | ASSIGNED TASK | SUBTASKS | ACTIVITIES | KEY PERFORMANCE INDICATORS | OUTCOME | RESPONSIBILITY | START | FINISH | FUNDING SOURCE | AMOUNT
MUNICIPAL TRANSFORMATION AND INSTITUIAON LDEVELOPMENT | C1 | Organisational review | Review organisational structure | Revise macro organogram, consult managers, submit item to council | Revised macro organogram approved by Council | Functional macro organogram approved by Council to deliver effective services. | AMM & Council | Feb | March | n/a | 0
| C2 |  | Review job descriptions | Consult Job Evaluation Committee to verify status of ILM job descriptions | Job descriptions approved by the Job Evaluation Committee | Implementation of Job descripions and salary scales as determined by JEC, and based on Council approval. | AMM | Feb | June | n/a | 0
| C3 | Recruit of Municipal Staff | Recruit municipal manager | Submit item to council, advertise position, facilitate shortlisting, interviews and appointment. | Council minutes, adverts, applications received and municipal manager appointed | Normalization of management & leadership in the municipality leading to improved service delivery | Council/ AMM | Feb | March | MAP | 30000
| C4 |  | Recruit senior managers in line with policy. | Submit item to council, advertise positions, facilitate shortlisting, interviews and appointment. | Council minutes, adverts, applications received and senior manager(s) appointed | Normalization of management & leadership in the municipality leading to improved service delivery | Council and MM | May | July | MAP | 30000
| C5 |  | Re-organisation and placement of existing HR (staff) | Drafting and approval of collective agreement for the placement of staff | Collective agreement, staff placed | All staff placed in new structure based on skills and competencies | MM | May | June | MAP | 550000
| C6 |  | Identify critical posts and fill vacancies as budgeted | Conduct audit of critical posts that will impact on service delivery, legislative compliance and critical priority powers and functions. | Audit report, positions filled | Municipality performing key service delivery functions for the provision of basic services | MM | May | August | Municipality | 30000
| C7 |  | Regularise appointment of existing senior managers | Review contracts and amend if necessary in line with legislation; submit item to council; prepare and conclude employment agreements | Council minutes; signed employment agreements | Regularised staff appointments for improved service delivery | AMM & Council | Feb | March |  | 0
| C8 | Human Resources Development Plan | Review and develop Human Resources policies | Review existing policies and draft outstanding HR policies | Council minutes ; Policies approved by council | A set of HR Policies adopted by council and implemented to achieve a regular working environment | Municipality,DBSA & Service Provider (Empilweni) | Feb | May | n/a | 0
| C9 |  | Develop employment equity plan | Review employment and demographic data; prepare EE Plan using prescribed template; Obtain Council approval; submit EE Plan | EE Plan submitted to Dept of Labour | Municipality achieving equity targets in line with legislation | Municipality,DBSA & Service Provider (Empilweni) | Feb | June | n/a | 0
| C10 |  | Review workplace skills plan | Review skills audit conducted in 2007; Update where necessary and revise WSP; Obtain Council approval | Skills development plan submitted to the LG Seta | Staff training needs identified and training plan in place for implementation | Municipality/SP (Empilweni) | Feb | July |  | 0
| C11 |  | Counduct staff and councillor training | HODs to establish training needs of staff in line with WPSP and make provisions for a budget to conduct staff and councillor training. Focussed training on Financial Management and Systems, SCM,IDP,Budget,PMS,Public Participation, | Council minutes; Certificates of attendance | Fully capacitated municipality and improved governance and service delivery | Municipality and Service Provider | April | ongoing | Municipal budget | 190000
| C12 |  | Finalise outstanding disputes | Identify disputes and segregate into internal and external and appoint legal representation if required to result in dispute settlement certificates or agreements | Council minutes; disciplinary tribunal(s) records; certificates of resolution of disputes from SALGBC or CCMA | Municipality complying with labour Relations Regulations. Stability in Labour Relations resulting in improvement in service delivery | AMM/MM | Feb | June | n/a | 0
| C13 |  | Create and update staff and councillors personal files | Audit all personal files and create a schedule of outstanding documents in files. Update staff files to hold all relavant documents as required by HR | Schedule of outstanding documents; letters to individual staff & councillors requesting documents; documents submitted & filed | Updated staff files with all staff records | AMM | Feb | March | n/a | 0
MUNICIPAL TRANSFORMATION AND INSTITUIAON LDEVELOPMENT | C14 | Establish as system of performance management | Develop a system of delegations | Develop draft delegations policy by adapting generic policy provided by DLGTA. Submit draft to council for consideration and approval | Council minutes; approved Delagations Policy | Delegated powers aprroved by Council resulting in improved organisational effieciency and accountability | Acting MM/CMTP Coordinator and DBSA Deployee | Feb | end of March | n/a | 0
| C15 |  |  | Adapt register sourced from the DBSA; Submit draft to council for consideration and approval | Approved Delegations Register signed by all concerned | Delegated powers aprroved by Council resulting in improved organisational effieciency and accountability | MM | May | June | n/a | 0
| C16 |  | Develop and workshop codes of good practice | Source codes from SALGA, DLGTA or other municipalities; Adapt codes, consult staff and submit draft to Council for consideration (workshop) and approval | Approved Codes Good Practice | Improvement in the conduct of staff & councillors in respect of HIV&AIDS, Sexual Harrasment, Use of Municipal Assets and so on | MM | May | July | n/a | 0
| C17 |  | Develop a performance management system | Review existing PMS Policy, Framework & procedures. Establish key performance indicators and workshop with Council. Submit for approval by Council draft proposal on the establishment of assessment panels. | Performance Management System, Policy & Framework approved by council. Council Resolution approving assessment panels. | Effective measurement of the performance of managers and the organisation against preapproved IDP service delivery goals and targets | AMM | March | July | DLGTA | 200000
| C18 |  |  | Conduct performance assessments of managers on a quarterly basis. Review organisational performance every six months. Submit report to council for consideration & approval | Performance review report submitted to Council; Council minutes | Management of performance in line with IDP, Budget and SDBIP | MM and Council | July | 2009-06-01 | n/a | 0
| C19 | Establishment of a records management system | Liaise with Provincial archives for establishment of RMS. | Contact relevant officials at KZN archives with a view to holding a meeting with them to establish types of assistance they offer | Office established & appropriate facilities installed | Effective and efficient document management in the municipality | AMM/Provincial Archives | Feb | March | n/a | 0
| C20 |  | Purchase of files,filing cabinets.etc | Establish and seek approval for the specification, submit requisition forms; order and take delivery; Install filing cabinets & files | Office established & appropriate facilities installed | Effective and efficient document management in the municipality | AMM/ Service Provider | Feb | March | MAP | 50000
| C21 |  | Training of Registry Clerk | Liaise with Provincial Archives regarding training they offer. Arrange for training to take place either in Impendle or PMB | Office established & appropriate facilities installed | Effective and efficient document management in the municipality | AMM/Provincial Archives | March | August | n/a | 0
| C22 |  | Installation of an electronic registry system | Investgate feasibility, identify budget, begin requisition processes, purchase and install. Train users. | Fully functional system installed and users trained | Effective and efficient document management in the municipality | MM | May | 2008-12-01 | DLGTA | 500000
FINANCIAL VIABILITY AND MANAGEMENT | F1 | Investigate and upgrade or purchase Financial Management System | Billing | Investigate billing module of the FMS & upgrade where necessary | A reliable billing system | Timely billing and collection of monies owed | AMM/CFO/DBSA Deployee | April | June |  | 1000000
| F2 |  | Payroll | Investigate Payroll module of the FMS & upgrade where necessary. Integrate payroll into the FMS if possible . | FMS with payroll integrated | Reliable payment of staff salaries and councillor allowances | AMM/CFO/DBSA Deployee | April | June
| F3 |  | Leave management | Investigate leave management module of the FMS & upgrade where necessary. Integrate leave management into the FMS if possible . | FMS with leave management integrated | Reliable management of staff leave. Realistic leave provision | AMM/CFO/DBSA Deployee | April | June
| F4 |  | Generation of required reports | Investigate whether the system is able to produce reports in the format required & update where necessary | Regular management Reports produced and submitted timely | Effective and timely reprot to council and external authorities & role players including the AG | AMM/CFO/DBSA Deployee | April | June
| F5 |  | Asset management module | Investigate assets management module & upgrade where required | Record of all assets kept and updated regulary | Efficient and effective assets management in the municipality | AMM/CFO/DBSA Deployee | April | June
| F6 |  | Upgrade other relevant modules of the FMS | Investigate whether other modules of the FMS require upgrading. | Fully functional system installed and users trained | Effective and efficient financial management system | AMM/CFO/DBSA Deployee | July | December
| F7 |  | Train Staff on new modules | Train users on the whole FMS or upgraded modules or as required. | Effective utilisation of FMS | Fully functional FMS with trained users. Effective and efficient financial management system | MM/CFO/DBSA Deployee; Service Provider | July | ongoing
| F8 |  | Conclude service level agreement | Review existing service level agreement and negotiate if necessary | Servvilce level agreement signed by all parties |  | Council and Service Provider | July | July
| F9 | Review Supply Chain Management System | Review Policy and procedures | Review existing policy & procedures and update where necessary. Refer updated policy to council for approval | Policies approved by council | Policy approved by council resulting in efficient purchasing mechanisms | AMM/ DBSA Deployee/Provincial Treasury | February | April |  | 0
| F10 |  | Refine standard tender documents | Review existing tender documents | Reviewed tender procedure document | Effective implementation of the supply chain management policy of the municipality | AMM/CFO/ DBSA Deployee/Provincial Treasury | March | May |  | 0
| F11 |  | Review Committees | Revisit the composition and effectiveness of existing committees. Train committees | Committees appointed by the MM & trained | Effective implementation of the supply chain management policy of the municipality | AMM/CFO/ DBSA Deployee/Provincial Treasury | March | May |  | 0
| F12 |  | Procurement plan | Prepare procurement sheculde in line with budget/SDBIP | Develop an annual procurement plan in line with approved budget | Effective implementation of the supply chain management policy of the municipality | AMM/CFO/ DBSA Deployee/Provincial Treasury | March | June |  | 0
| F13 |  | Establish database of service providers | Investigate use of provincial or district database. | Data base established or linkages with the provincial database | Effective implementation of the supply chain management policy of the municipality | AMM/CFO/ DBSA Deployee/Provincial Treasury | March | June |  | 0
| F14 | Annual Report | Develop a municipal performance report | Review organisational performance every six months. Submit report to council for consideration & approval | Municipal Annual Performance Report in line with MSA and MFMA | Identification and correction of possible gaps in the implementation of the IDP, Budget, SDBIP | DBSA Deployee/ CMTP Coordinator | March | June |  | 0
| F15 |  | Develop action plan or correction measures for issues raised by AG in audit report | Prepare action plan/corrective measures and submit to council for approval | Annual Report; Council minutes | Effective response to the issues raised by the AG and plan to avoid repetition | AMM/CFO/DBSA Depolyee | February | March |  | 0
| F16 |  | Table available components of the annual report | Table available components of the annual report to council for approval | Annual Report; Council minutes | Compliance with legilative requirement as well as the creation of an enabling environment for monitoring | AMM/Mayor/Annual Report Committee | February | March |  | 0
| F17 |  | Prepare and adopt oversight report | Assist Council to prepare & adopt oversight report | Oversight report adopted by Council | Compliance with legilative requirement as well as the creation of an enabling environment for monitoring | AMM/Council/Oversight Committee | February | March
| F18 |  | Submit to relevant authorities | Submit Annual Report to Provincial Treasury; Auditor General & DLGTA | Letters to provincial speaker, treasury, AG & DLGTA; annual report | Compliance with legilative requirement as well as the creation of an enabling environment for monitoring | AMM | February | March |  | 0
FINANCIAL VIABILITY AND MANAGEMENT | F19 | Address audit Issues | Address issues in the Auditor Generals Report | Implement & monitor implementation of action plan as per council approval | Reports submitted to Council & council decisions | Audit issues adequately addressed & corrective measures to prevent future occurance taken | AMM/CFO/DBSA Deployee | February | June |  | 0
| F20 | Review IDP | Review process plan | Arrange IDP Steering Committee meeting to review the IDP process plan | Revised process plan, approved by council | Submission of the draft and final IDP on time and in the correct format | AMM | February | mid March |  | 0
| F21 |  | Table draft IDP | Discuss draft IDP with Mayor. Mayor to table draft IDP to Council. | Draft IDP; Council Minutes | Submission of the draft and final IDP on time nd in the correct format | AMM | March | March |  | 0
| F22 |  | Public participation | Convene IDP Representative forum meetings. Attend all budget & IDP road shows | Records of meetings, adverts & public submissions (if any) | Compliance with legislative requirements & the involvement of community in the affairs of the municipality | AMM | March | May |  | 0
| F23 |  | Adopt IDP | Submit final draft IDP to Mayor & Council for adoption | Council resolution; IDP | Municipality will have a strategic document guiding its activities | Council | May | end of May |  | 0
| F24 | Prepare budget for 2008/09 | Review process plan in line with IDP | Arrange IDP Steering Committee meeting to review the budget process plan | Revised process plan, approved by council | Chances for the submission of the draft and final IDP on time and in the correct format improved | AMM | March | March |  | 0
| F25 |  | Develop budget guidelines | Review previous guidelines or existing guidelines and adapt for ILM | Guidelines approved by the relevant authority | Enable the preparation of the budget of the ILM | DBSA Deployee/CFO | February | March |  | 0
| F26 |  | Table draft budget | Discuss draft budget with Mayor. Mayor to table draft budget to Council. | Draft Budget tabled by the Mayor to Council and council resolution to that effect | Compliance with legislative requirements | AMM/Mayor/CFO/DBSA Deployee | March | March |  | 0
| F27 |  | Submit draft budget to relevant authorities | Submit draft budget to provincial treasury | Letter to provincial treasury & draft budget | Compliance with legislative requirements & enable provincial treasury to assist the ILM | CFO | March | March |  | 0
| F28 |  | Public participation | Convene IDP Representative forum meetings to present draft budget & IDP. Attend all budget & IDP road shows. Present draft budget to all ward committees | Records of meetings, adverts & public submissions (if any) | Compliance with legislative requirements & the involvement of community in the affairs of the municipality | AMM/CFO | April | May |  | 0
| F29 |  | Adopt budget | Submit final draft IDP to Mayor & Council for adoption | Council resolution approving the budget. | Compliance with legisltaive requirements. Council will have a financial plan to guide its expenditure | Council | May | May |  | 0
| F30 | SDBIP | Develop SDBIPs | Prepare draft SDBIP in line with national treasury guidelines and submit to mayor for tabling to council | SDBIP - approved by council | A tool in place to monitor the implementation of budget and the attainment of service delivery targets and the enabling of adjustments where required | MM/CFO/DBSA Deployee/CMTP Coordinator | May | June |  | 0
| F31 | Performance Agreements | Develop Performance Agreements aligned to SDBIPs | Prepare draft Performance Agreements in line with performance regulations & submit to mayor for tabling to council | Draft performance agreements submitted to the Mayor & Council | Compliance with legislative requirements. Tool in place to monitor & assess performance of managers | MM/DBSA Deployee/CMTP Coordinator/Mayor | May | June |  | 0
| F32 | Establish Internal Audit Unit | Pursue shared services option with Umngeni | Review correspondence between Umngeni LM & ILM about the sharing of IAU. Revive the initiative and if founf to be feasible enter into service level agreement. If not feasible advertise the service | Functional Internal audit appointed | An environemnt created where risk is minimised & mitigated or eliminated. Compliance will improve. Good governence promoted. | AMM | March | June | MAP | 50000
FINANCIAL VIABILITY AND MANAGEMENT | F33 | Establish Audit Committee | Pursue shared services option with Umngeni | Review correspondence between Umngeni LM & ILM about the sharing of IAU. Revive the initiative and if founf to be feasible enter into service level agreement. If not feasible advertise the service | Functonal Audit Committee appointed | An environemnt created where risk is minimised & mitigated or eliminated. Compliance will improve. Good governence promoted. | AMM/DBSA Deployee/CMTP Coordinator | March | June | MAP | 150000
| F34 | Review and develop Financial Policies | Credit control and debt collection policy | Review draft policy prepared by service provider. Submit to council for consideration & approval | Approved credit control and debt collection policy | Reduction in debtors; improvement in revenue collection. Reduction in bad debts and the provision thereof | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June |  | 0
| F35 |  | Asset management | Review draft policy prepared by service provider. Submit to council for consideration & approval | Assets management policy approved by council | It will be possible to account for the assets of the municipality and to insure them | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F36 |  | Budget | Review draft policy prepared by service provider. Submit to council for consideration & approval | Approved budget, | Budget will be prepared and approved with legal framework | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F37 |  | Fraud Prevention | Review draft policy prepared by service provider. Submit to council for consideration & approval | Fraud Prevention Plan approved by Council | An environemnt created fraud is detected early or minimised, mitigated or eliminated. Good governence promoted. | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F38 |  | Indigent | Review draft policy prepared by service provider. Submit to council for consideration & approval | Indigent Policy approved by Council | An environment created where the poor are serviced and assisted through targeted interventions including the provision of free basic services. | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F39 |  | Investment and cash management | Review draft policy prepared by service provider. Submit to council for consideration & approval | Investment and Cash Management Policies approved by Council | Risk for fraud is minismised or eliminated. Good governence promoted | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F40 |  | Tarrif | Review draft policy prepared by service provider. Submit to council for consideration & approval | Tarrif Policy approved by Council | Complaince with legislative requirements. Adjustments for inflation and growth will happen within an approved framework | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F41 |  | Travel and Subsistence | Review draft policy prepared by service provider. Submit to council for consideration & approval | Travel & Subsistence Policy approved by Council | An environemnt created where risk is minimised & mitigated or eliminated. Compliance will improve. Good governence promoted. | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F42 |  | Accounting Policy | Review draft policy prepared by service provider. Submit to council for consideration & approval | Accounting Policy approved by Council | An environemnt created where risk is minimised & mitigated or eliminated. Compliance will improve. Good governence promoted. | AMM/CFO/DBSA Deployee/ SP (Siyaya Management Services) | March | June | n/a | 0
| F43 | Credit Control and debt management | Develop Debt Recovery Plan and Strategy | Prepare & workshop draft plan and submit to council for approval | Developed Debt Recovery Plan approved by Council | Reduction in debtors; improvement in revenue collection. Reduction in bad debts and the provision thereof | AMM/CFO/DBSA Deployee | March | June | n/a | 0
| F44 |  | Develop indigent register | Review existing indigent register and eliminate discrepancies. Employ teams to register more households and update the register. | Updated Indigent Register | An environment created where the poor are serviced and assisted through targeted interventions including the provision of free basic services. | AMM/CFO/Service Provider | March | June | DLGTA | 150000
FINANCIAL VIABILITY AND MANAGEMENT | F45 | Municipal Property Rates Act implementation | Identify potential funding to implement the MPRA | Identify potential funding sources within and outside the municipality. Approach funding sources and confirm where required. Enter into memoranda of understanding | Memoranda of Understanding; Correspondence with relevant parties | Funds available to implement the MPRA | AMM/CFO | February | March | DLGTA/DBSA/Municipality | 2500000
| F46 |  | Rates Policy | Review draft policy prepared by service provider. Submit to council for consideration & approval | Property Rates Policy approved by Council | Improvement in the revenues of the municipality | AMM/CFO/DBSA Deployee/ Service Provider | July | December | DLGTA/DBSA/Municipality
| F47 |  | Public consultation process | Develop and implement strategy to consult affected parties | Public participation records | Public opinion would be taken into account when implementing the MPRA | AMM/CFO/DBSA Deployee/ Service Provider | July | 2009-06-01 | DLGTA/DBSA/Municipality
| F48 |  | Land Audit | Appoint Service Provider to conduct land audit as part of the implementation of MPRA | Audit report submitted to council | Creation of an environment that allows valuation of properties for MPRA purposes | AMM/CFO/DBSA Deployee/ Service Provider | July | December | DLGTA/DBSA/Municipality
| F49 |  | Develop Valuation roll | Service Provider to develop valuation roll within policy approved by the municipality | Approved Valuation Roll | Fair value attached to properties for the purpose of rates collection resulting in the improvement of municipal coffers | MM/CFO/DBSA Deployee/ Service Provider | July | 2009-06-01 | DLGTA/DBSA/Municipality
| F50 | Asset register | Identification and tagging of assets | Physical count and identification and tagging of assests | All assets tagged | Assets of the municipality identified and location known. Prevention of abuse and loss of assets | MM/CFO/DBSA Deployee/ Service Provider | March | May | n/a | 0
| F51 |  | Valuation of assets | Value the assets in terms a starndard or accepted procudure | Assets captured and reconciled into ledger | Fair value attached to the assets of the municipality | MM/CFO/DBSA Deployee/ Service Provider | March | May | n/a | 0
| F52 |  | Integrate into FMS ( GRAP and GMAP compliant) | Investigate and integrate assets register into FMS | Integrated asset management system | Efficiency in the management of assets of the municipality | MM/CFO/DBSA Deployee/ Service Provider | March | May | n/a | 0
| F53 |  | Develop an Asset Management Plan which includes fleet management | Prepare draft assets management plan and submit same to council for approval | Asset Management Plan approved by Council | Efficiency in the management of assets of the municipality | MM/CFO/DBSA Deployee/ Service Provider | March | May | n/a | 0
| F54 | MFMA | Develop and implement MFMA compliance checklist | Review and adapt MFMA compliance checklist developed by IMFO. Submit to management for approval | Compliance checklist | Improvement in timely compliance with MFMA requirements | AMM/CFO/DBSA Deployee | March | March | n/a | 0
| F55 | Conditional Grants | Review and Manage all grants | Review and update grant schedules | Grants review schedule | Improvement in the management of grants and the submission of reports to relevant authorities | CFO/MAP/CMTP Coordinator | March | March | n/a | 0
| F56 |  | Ensure expenditure according to MOAs | Review & update MOAs | Business Plan developed for each MOA where required | Compliance with agreed terms and conditions of each grant | CFO/MAP/CMTP Coordinator | March | April | n/a | 0
| F57 | Staff and Councillors loans | Investigate staff and councillor loans | Review acknolwdgements where available to check whether terms are met. Prepare and conclude acknowledgements where they do not exist | Investigation report considered by Council | Collection of all monies due to council from previous councillors and staff | AMM/CFO/DBSA Deployee | March | March | n/a | 0
| F58 |  | Ensure signing of acknowledgement of debts | Review acknolwdgements where available to check whether terms are met. Prepare and conclude acknowledgements where they do not exist | Acknowledgement of debts signed | Collection of all monies due to council from previous councillors and staff | AMM/CFO/DBSA Deployee | March | March | n/a | 0
| F59 |  | Arrange for repayments | Review acknolwdgements where available to check whether terms are met. Prepare and conclude acknowledgements where they do not exist | Monthly payroll printouts and reports to Council | Collection of all monies due to council from previous councillors and staff | AMM/CFO/DBSA Deployee | March | ongoing | n/a | 0
| F60 | Develop by- laws | Identify and develop relevant by laws | Identify and develop relevant by laws | Approved by laws | Improvement in service delivery and control of municipal activities. | AMM/DBSA Deployee/MM | March | December | n/a | 0
| F61 | IT | Conduct IT Audit ( Infrastructure networking,software and hardware audit as well as service) | Procure service provider to conduct investigation of IT application software licences, email ,intranet,LAN Maintenance,daily backups,anti virus,passwords IT faults management and assessment Report | Fully functional IT and users trained | Efficiency in the management of the municipality and the delivery of services to the community | CFO/ AMM/Service Provider | March | May | MAP/DLGTA | 70000
| F62 |  | Implement findings of audit | Implementation of the findings of the audit. Monitor the implementation and conduct training | Fuly functional IT Systems | Efficiency in the management of the municipality and the delivery of services to the community | CFO/ Acting MM/Service Provider | April | September | MAP/DLGTA | 500000
SERVICE DELIVERY AND INFRASTRUCTURE | T1 | Integrated human settlement | Finalise transfer of water services to the UDM | Negotiations with the Water Services Authority, namely District Municipality | Conclude service level agreement for billing | Transfer of water and sanitation assets & liabilities will be completed. Service delivery normalization particularly issues of customer care as well as operations and maintenance | AMM/CFO | March | March |  | 0
| T2 |  |  |  | Conlude assets and liabilities transfer agreement |  | AMM/CFO | March | March |  | 0
| T3 |  |  |  | Conclude staff transfer agreement |  | AMM/CFO | March | March |  | 0
| T4 |  |  | Negotiate and reconcile monies owed to the ILM by the District Municipality | Funds transferred to Impendle LM | Badly needed funds will be available for use in service delivery | AMM/CFO/MM | April | June |  | 0
| T5 |  | Finalise housing sector plan | Review Housing Sector plan if available. If not, prepare housing sector plan. Submit draft to council for approval | Housing Sector Plan | Clear delivery housing strategy for the municipality aligned to the IDP | AMM/MTS/DoH | April | July | DoH | 200000
| T6 |  | Develop capacity to manage housing projects | Negotiate and conclude HR support agreement with DoH | Appointed Housing Administrator and two assistants | Improved Housing Delivery in Impendle LM | AMM/MTS | March | March | DoH | 375000
| T7 |  | Assess services for the ongoing housing projects | Compeltion of current needs assessment projects. | Assessment report on the status of services (water, electricity, sanitation, roads, etc) | Council will know what and where are services still required. | AMM/MTS/DBSA Deployee | April | June | n/a | 0
| T8 |  | Facilitate appointment of project manager/IA for halls | Review tender proposals received; invite tenderers to a presentation; recommend and select appropriate tenderer. Review project scope. | Appointed Project Manager; Council decision reviewing project scope | Community halls completed by the end of the FY. | AMM/MTS/DBSA Deployee | March | June | n/a | 0
| T9 |  | Investigate the status of the Thusong Services Centre | Investigate the arrangement regarding the finaliastion and operational requirements for the MPCC including the R500 000 funding transferred to the District | Functional MPCC | Fully let and functional MPCC with no added financial burden on the municipality | AMM/MTS/DLGTA | March | August | n/a | 0
| T10 |  | Develop systems and procedures for technical projects | Obtain existing procedure manuals and adapt same for ILM. Submit to council for approval. | Systems and Procedures in place for all technical works | Efficiency in the delivery of services | AMM/MTS/DBSA Deployee/MM | March | August | n/a | 0
| T11 |  | Finalise LUMS | Investigate & report on the status of LUMS for ILM. Complete or update project where necessary. Submit report to council and other relevant authorities | LUMS adopted and being implemented in line with approvals and zoning regulations | Efficient land and development administration in ILM | Acting MM and Council/DLGTA/DBSA Deployee | March | August | DLGTA | 200000
GOVERNANCE AND PUBLIC PARTICIPATION | G1 | Promote good governance | Develop a communication plan (internal and external) | Appoint Service Provider to assist municipality develop a communication plan. | Communication Plan approved by Council | Effective communication inside and outside of the municipality | MM/Service Provider | May | August | DLGTA | 200000
| G2 |  | Update and maintain municipal website | To form part of IT investigation and upgrade | [6 empty] | 0
| G3 |  | Annual calendar of events | Develop and maintain an annual calender of events | Approved Annual Calender | Effective management of events, avoidnace of overlaps and repitition | AMM | May | end June | n/a | 0
| G4 |  | Conduct IDP and Budget road Shows | Set up Steering Committee, Identify areas, set dates and logistics, marketing embark on road shows. | Road shows records; Attendance registers | Public views would have been taken into account when preparing the final IDP & Budget in terms of the MFMA | AMM/Mayor & Council | April | May | Municipality | 100000
| G5 |  | Risk Management | Appoint Service Provider to assist ILM to develop and implement a risk management plan | Service Provider appointed; Risk Management Plan approved | An environment created where risk is mitigated, minimised, deflected or eliminated. Promotion of good governance | AMM/Provincial Treasury/Service Provider/MM | March | August | Provincial Treasury | 200000
| G6 |  | Insure all assets as per assset register | Invite tenders for risk cover | Tenders received; adverts and Service provider appointed | An environment created where risk is mitigated, minimised, deflected or eliminated. Promotion of good governance | AMM/CFO | March | June | Municipality | 200000
| G7 |  | Develop a fraud prevention plan and anti corruption strategy | Appoint Service Provider to assist ILM to develop and implement a fraud prevention plan | Service Provider appointed; Fraud Prevention Plan approved | An environment created where risk is mitigated, minimised, deflected or eliminated. Promotion of good governance | AMM/CFO/DBSA Deployee | March | August | MAP | 200000
| G8 |  | Conduct workshop on the Public participation Framework | Identify stakeholders/potential participants; arrange and conduct workshops | Stakeholders participating; Workshop records; attendance registers/certificates | Improved undertsnading of the importance of public participation among councillors and staff as well as other stakeholders involved | DLGTA | March | August | DLGTA | 100000
| G9 |  | Active participation in District IGR Forum and technical Committees | Regular attendance of District IGR Forum, submit reports as may be required; Give feedback to councillors and stakeholders | Reports submitted to the IGR Forum and records of issues resolved or deliberated. | Improved relationship with the District and its family of municipalities and corrdination of service delivery | AMM/Mayor/MM | February | ongoing | n/a | 0
LOCAL ECONOMIC DEVELOPMENT | ED 1 | Review LED Strategy | Workshop and refine LED Strategy to all stakeholders | Appoint Service Provider to assist municipality review the LED Strategy. | Reviewed LED Strategy | Readiness for Local Economic Development in ILM | AMM/MTS/Service Provider | March | August | DED/DLGTA | 100000
| ED 2 |  | Implement Strategy in line with budget provisions | Implementation of strategy recommendations & projects | Projects implemented | Local Economic Development in ILM | MM | July | ongoing | DED/DLGTA | 1000000
ED 3
ED 4
ED 5
ED 6
ED 7
TOTAL | [10 empty] | 8875000
Note on L4: Pravashnee: ADVERTISING COSTS
Note on L6: allan: MAP Allocation
Note on L12: nobuhle: to inlude basic book keeping