the greater kokstad municipality

turnaround strategy

Prepared by the municipal manager

table of contents

1.	Background	3

2.	review of the auditor general reports 	5

3.	SUMMARY OF THE AUDITOR GENERAL FINDINGS 	5

4.	strategic INTERVENTIONS  	7

5.	budget 	Error! Bookmark not defined.

6.	sources  	7

7.	legend   	7

# 1.	Background

The Greater Kokstad Municipality (GKM) receives conditional grants from National and Provincial Departments for the implementation of its various projects and programs as per its budget and the IDP. Funding for these projects is allocated under the Division of Revenue Act (DoRA), Act No. 1 of 2006, and the Municipal Finance Management Act (MFMA). Such funding is also regarded as Conditional Grant funding due to conditions attached to it, and it requires stringent controls and regular reporting to the funding Department.  In addition to providing reports on a regular basis, that is monthly and quarterly reports, such programs are subjected to audits by the Office of the Auditor General.

In addition, all organs of state, as required by various laws, should be subjected to external audits by the Office of the Auditor General at the end of each financial year. As such, the GKM has been subjected to such audits over the past years. An analytical review of the Auditor General reports over the past five years indicates that the Municipality has been technically insolvent for the past five years and that if not addressed as a matter of urgency, the situation could deteriorate even further.

- Municipalities and local government organisations do not get into trouble overnight.  Problems accumulate over an extended period of time, frequently 5 – 10 years or longer.

- The root of the problem most often lies in the fact that those in the leadership have accepted an unacceptable situation over an extended period of time.

- Lack of oversight and accountability by the Council and or senior management are evident in most deeply troubled municipalities.

- Inadequate information often contributes to poor performance monitoring and financial reporting; this is a leadership issue, not a technology issue.

- As performance deteriorates management are not monitoring performance and responding appropriately.

| WARNING SIGN | SOURCE | GREATER KOKSTAD MUNICIPALITY |
| --- | --- | --- |
| Council and senior management acceptance of poor financial performance | Non or poor response to Auditor General reports | √ |
| Lack of middle management depth | Observation | √ |
| Lack of accountability or illogical reporting relationships involving managers/ supervisors | Auditor General reports | √ |
| Generally poor Council, Management and staff relations | MAP assessment report | √ |
| Poor communication channels | Observations and through discussions | √ |
| Inadequate information management and reporting systems and processes | Auditor General reports | √ |
| Increasing accumulated deficits and deteriorating liquidity of the Municipality | Auditor General reports | √ |
| No long-term budgets and plans or unrealistic/missing budget targets | Auditor General reports and external correspondence | √ |
| A liquidity squeeze, such as decreasing cash reserves and days cash on hand | Auditor General reports | √ |
| Rapidly escalating costs (Operational , especially personnel and Capital) | Auditor General reports and audited financial statements | √ |
| Aging Facilities and Equipment (lack of reinvestment) | Observation | √ |
| Inability to pay for debts (creditors) as they become due | Auditor General report | √ |
| Qualified Audit Reports (disclaimers in five consecutive years ) | Auditor General reports | √ |

# 2.	review of the auditor general reports

| KPI | 2001 - 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| GOVERNANCE | There was a significant increase in staff costs of 40%, legality of which was questioned by the AG |  | Report outstanding |
|  | Minutes of council meetings were not signed and/or bound and other were missing |  |  |
|  | Minutes of meetings – lack of control (“there does not appear to be an organised method or manner of tracking and administering the minute keeping process”) |  |  |
|  | No internal audit committee |  |  |
|  | No financial policies and procedures manual |  |  |
|  | No fringe benefits tax levied on vehicles and Councillors loans |  |  |

| KPI | 2001 – 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| FINANCIAL MANAGEMENT | VAT balances and transactions are materially incorrect |  | Report outstanding |
|  | General ledger journals – there were no controls in terms of supporting documentation for journals and audit trail |  |  |
|  | “the prevailing state of affairs is viewed in a most serious light and is indicative of the lack of overall management control” |  |  |
|  | The continued failure to complete financial statements on time gives an indication that Council finance employees do not have the capacity to carry out this function” |  |  |
|  | Financial statements were prepared by Mumford and Projects cc Financial Statements were prepared by Alan H English Financial Statements were prepared by Finance Department assisted by Integrasol (Pty) Ltd | Financial Statements were prepared by the Finance Department | Financial Statements were prepared by the Finance Department, assisted by Gobodo & Company |

| KPI | 2001 – 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| EXPENDITURE CONTROL | Leases relating to fixed assets and long term liabilities could not be accounted for |  | Report outstanding |
|  | Creditors balances could not be substantiated |  |  |
|  | External loan balances could not be confirmed and finance charges totalling R 2,4 million had not been accounted for |  |  |
|  | Operating expenditure was not substantiated |  |  |

| KPI | 2001 – 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| REVENUE MANAGEMENT | Electricity income from Bhongweni is understated |  | Report outstanding |
|  | Water income from Bhongweni is overstated |  |  |
|  | Water income from Kokstad is understated |  |  |
|  | Debtors balances are not substantiated |  |  |
|  | Rates penalties and collection charges income was incorrectly stated 29% of purified water was not sold to consumers and represented a loss of R 1,3 million |  |  |

| KPI | 2001 - 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| ASSET MANAGEMENT | Council has been informed since 1984/5 that the asset register has not been written up A proper asset register could not be produced for audit purposes |  | Report outstanding |
|  | Cash resources of the municipality are depleted |  |  |
|  | Current debtors are overstated by R 16 million |  |  |
|  | Provision for bad debts has not been substantiated |  |  |
|  | Investments are not accessible and the recoverability thereof is questionable (NRB) Balances of external investments could not be confirmed Capital assets were not funded |  |  |

| CASH MANAGEMENT | Bank overdraft figure is misstated External investments balance |  | Report outstanding |
| --- | --- | --- | --- |

| KPI | 2001 - 2005 | 2006 | 2007 |
| --- | --- | --- | --- |
| BUDGETING AND REPORTING | Capital commitments of R 37 million could not be substantiated Financial statements were submitted late. There was no response to management letters issued by the Auditor General Previous year audit report had not been addressed (1989/99, 1999/2000) |  | Report outstanding |
| LIQUIDITY | The municipality had an accumulated deficit of R 3, 16 and in terms of ordinance 25 of 1974 had to report the matter to the Premier As at 30 June 2002, the municipality was insolvent and the deficit amounted to R 15,151,585 |  | Report outstanding |
|  | The Municipality was technically insolvent Furthermore statutory funds totalling R 32,236,431 were included in the AFS but not supported by Cash or investment |  |  |

- SUMMARY OF THE AUDIT FINDINGS

| DETAILS | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Audit Opinion | Disclaimer | Disclaimer | Disclaimer | Disclaimer | Disclaimer | Disclaimer | Report outstanding |
| Qualification matters | 22 | 24 | 17 | 5 | 10 | 23 |  |
| Emphasis of matter | 70 | 30 | 12 | 12 | 20 | 23 |  |
| TOTAL | 92 | 54 | 29 | 17 | 30 | 46 |  |
| Change |  | -41,30% | -46,29% | -41,37% | +76,47% | +53,33% |  |

# 4.	strategic INTERVENTIONS

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Governance and Compliance | ORGANOGRAM REVIEW | GKM to review its organisational structure for efficiency and effectiveness, discuss with the labour forum and submit to the Council for approval | October 2007 | All Executive Managers |
|  | REVIEW OF COUNCIL COMMITTEES | GKM to review the Committees of the Council, their Terms of Reference (ToR) and the frequency of the sitting thereof | November 2007 | MM |
|  | POLICY REVIEW | GKM to review all its policies, delegations of authority and submit the same for Council approval | November 2007 | MM & EM-CS |
|  | IDP | Review of the Municipal IDP, alignment thereof with the budgeting process and submit for Council approval | March 2008 | CFO and EM-IPD |
|  | PMS | GKM to develop and implement a Performance Management system after consultation with the local labour forum and to submit the same for Council approval | March 2008 | EM-CS |
|  | KPI | GKM to develop and implement the Key Performance Indicators (KPI) | March 2008 | MM |
|  | SBDIP | GKM to establish internal controls for the monitoring of performance for both the institution and the employees | March 2008 | MM & CFO |
|  | Strategic Review | GKM to undertake annual review of strategic objectives and submit for Council approval | April 2008 | MM & EM-CS |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Asset Management | Asset Verification | GKM to conduct 100% asset verification twice per annum | 1st – 15/12/2007 2nd – 30/06/2007 | All Executive Managers led by the CFO |
|  | ADDITIONS | All additions to fixed assets to be properly recorded (individually on the Fixed Asset Register) with reference to the Purchase date, Order, Invoice and amount paid | Ongoing | CFO |
|  | LOSS CONTROL | CFO to be informed with immediate effect of all assets lost (whether as a result of theft or damage) and insurance claims to be submitted in time | Ongoing | All Executive Managers |
|  | INSURANCE | GKM to review the insurance of its assets against loss for its adequacy and where deemed necessary approach other Service Providers for a competitive price, | March 2008 | CFO & MM |
|  | ASSET MANAGEMENT POLICY | GKM to develop an asset management policy, in line with GRAP/GAAP/GAMAP that will look at the entire life-cycle of the asset from acquisition to disposal | March 2008 | All Executive Managers |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Unspent Grants | REVIEW | GKM to compile a list of all unspent grants, identify the ones where funds were received and separate from the ones where funds are still outstanding | October 2007 | CFO |
|  | INVESTMENT | GKM to invest separately (a separate bank account for each grant), funds for all pending projects and report according to the reporting conditions of the grant; | October 2007 | CFO |
|  | UNFUNDED PROJECTS | Where projects were identified but funds have not been received, CFO to confirm continued funding of |  |  |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Balance Owing to Sisonke | AMOUNT OWING BY SISONKE | GKM to arrange a special meeting with Sisonke to try and resolve the matter. First meeting between the CFO’s 2nd meeting between the MM’s ; and Final meeting between the two Councils as per the SLA | January 2008 | CFO & MM |
|  | REVIEW OF THE SLA | GKM to review the SLA between itself and Sisonke and ensure that the SLA in its entirety has been complied with and bring the matter to closure | November 2007 | MM |
|  | WORKING COMMITTEE | GKM to establish an operational working committee of officials between itself and Sisonke to devise strategies on how to respond to urgent water and sewerage matters | November 2007 | MM & EM-CS |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Long-term Liabilities | CONFIRMATION OF LIABILITIES | GKM to obtain confirmations of loans outstanding, monthly instalments, and the repayment period outstanding on each loan | October 2007 | CFO |
|  | RELEASE OF LIENS AND PLEDGES | GKM to indentify and release all pledges against municipal assets and debtors used to secure loans from 3rd parties | November 2007 | CFO & MM |
|  | COST OF BORROWING | GKM to review the cost of borrowing and through an analytical review process to ascertain that the interest rate charged by the lenders is commensurate | November 2007 | CFO & MM |
|  | CONSOLIDATIONS OF LONG TERM DEBTS | GKM to review the options of consolidating loans by approaching funders with reduced interest rates and affordable repayment periods, Once the market has been analysed, GKM to approach one bank with a view of consolidating all long-term loans | November 2007 | CFO & MM |
|  | REDUCTION OF LOANS | GKM to look at reducing the long-term longs through the disposal of non-strategic immovable assets | January 2007 | All Executive Managers |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Revenue Management | Analytical review | GKM to conduct an analytical review of all revenue streams over the past five years, looking at the top five revenue streams as well as identifying other revenue streams not yet explored | October 2007 | All Executive Managers |
|  | ELECTRICITY AUDIT | GKM to conduct the electricity audit which will identify losses that are incurred by the Municipality as a result of illegal connections | November 2007 | CFO & EM-IPD |
|  | BILLING SYSTEM | GKM to review the billing system, check the contact details of the account holders to ensure that statements are sent to the correct people for speedy payments | November 2007 | CFO |
|  | REVIEW OF THE INVOICING METHOD | GKM to approach Easy Pay as well as Financial Service Providers with a view of facilitating direct payments to the bank as opposed to queuing up at municipal offices. | November 2007 | CFO & MM |
|  | FINALISE THE DEBTOR CLEANSING PROCESS | GKM to finalise the debtor-cleansing process and where monies are deemed irrecoverable, GKM to take the necessary action (write off, hand over to the attorneys and/or sale property by execution) | March 2008 | CFO & MM |
|  | LINKING OF THE BILLING SYSTEM TO THE INDIGENT DATA BASE | GKM to link its billing system to the Municipal indigent database so to avoid billing where monies will not be recovered. | March 2008 | CFO |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Investments | CONFIRMATION OF ALL INVESTMENTS | GKM to obtain confirmation of all investments from the institutions | November 2007 | MM |
|  | REVIEW OF ROI | GKM to review the return on investment, compare with the cost of borrowing and where deemed necessary utilise the investments to settle long term debts that are incurring interest which is more than investment interest | November 2007 | CFO & MM |
|  | REVIEW OF THE ROI ON CONDITIONAL GRANTS | GKM to review the return on investments for all conditional grants, check whether there are no alternatives of maximising the return on investments | November 2007 | CFO & MM |
|  | RECALL | GKM to recall all investments where return on investments are not viable and to re-invest and/or utilise the investment to settle long term debts | November 2007 | CFO & MM |
|  | RISK ASSESSMENT | GKM to conduct a risk assessment, only of institutions where it has resolved to continue investing funds, in light of losses as a result of the liquidation of the New Republic Bank | November 2007 | CFO and MM |
|  | MONTHLY REPORTING | CFO to provide a monthly report on all investment for consideration by the Executive Management and the EXCO | Monthly | CFO |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Cash and Bank | RECONCILLIATIONS | All bank reconciliations to be done on a monthly basis | Monthly | CFO |
|  |  | Main account to be reconciled on a weekly basis with the reconciliations signed by the CFO as proof that they have been properly done | Weekly | CFO |
|  | Annual Cash Flow | GKM to prepare an annual cash flow for all major cash accounts to ensure that there is sufficient cash to pay for expenses as they fall due | November 2007 | CFO |
|  | Monthyl cash flow | GKM to prepare monthly cash flow for submission to the Executive Management meeting and the EXCO | Monthly | CFO |
|  | INTERNAL CONTROLS | GKM to review internal controls and risks associated with its cash management both from a banking point of view as well as | November 2007 | CFO |
|  | CONFIRMATION OF BANK BALANCES AND INTEREST EARNED | GKM to obtain confirmations of bank balances on all accounts and proof of interest earned from all financial institutions for the financial year end | June 30, 2008 | CFO & MM |

| DETAILS | SUB-ITEM | ACTIVITY | DEADLINE | RESPONSIBILITY |
| --- | --- | --- | --- | --- |
| Project Management | REVIEW OF ALL PROJECTS | GKM to compile a list of all projects indicating the source of funding and where required the deadline for the funding to have been fully utilised | November 2007 | EM-IPD |
|  |  | GKM to provide a separate list of projects that require urgent attention either as a result of non/poor performance by the appointed service provider or delays in the Supply Chain process | November 2007 | EM-IPD |
|  | monthly reporting | GKM to prepare a monthly report on all projects with expenditure to date and clearly indicating whether each project is on course for completion within preset timeframes, where deadlines are going to be missed, recommending the required action. | Monthly | EM-IPD |
|  | NEW ANCHRO PROJECTS Monthyl cash flow | GKM to identify new anchor projects, include in the IDP and approach National & Provincial Departments for project funding | March 2008 | CFO & EM-IPD |
|  | REFURBISHMENT & EXPANSION OF 85 HOPE STREET | GKM to appoint Project Managers that will oversee the refurbishment of the Municipal Offices at 85 Hope Street to create space for the growth of the institution and to ensure that all Departments are housed under one roof to improve service delivery; | March 2008 | CFO & EM-IPD |

6.	budget

| NO. | aCTIVITY | SUb-activity | deadline | cost | responsibility |
| --- | --- | --- | --- | --- | --- |
|  | Human Resources Management | Review of the municipal organogram and consultation with all relevant stakeholders | October 2007 | Internal resources (MM, HOD’s) | MM & Executive Managers |
|  |  | Costing of the organogram to identify budget savings and to indentify posts that needs to be filled urgently | November 2007 | Internal resources (CFO and CSM) | MM & Executive Managers |
|  |  | Filling of all vacant posts to ensure effective and efficient service delivery | Advertising – 11/07 Short-listing and interviews – 12/07 All vacant posts filled – 01/08 | R 350 000.00 | MM and EM-CS |

| NO. | aCTIVITY | SUb-activity | deadline | cost | responsibility |
| --- | --- | --- | --- | --- | --- |
|  | Revenue enhancement and operating expenditure control | Analytical review of revenue and expenditure over the past five years | November 2007 | Internal resources | MM |
|  |  | Analytical review of Eskom expenditure and income over the past five years to assess the level of losses | November 2007 | R 1,000,000.00 | CFO and EM-IPD |
|  |  | Audit of the electricity metres to assess the level of electricity stolen/used illegally | November 2007 |  |  |
|  |  | Research of other revenue generating options available to the GKM | March 2007 | R 1,000,000.00 | MM |
|  | Expenditure Control | Identify the top 20 operating expenses over the past 5 years | November 2007 | Internal resources | CFO |
|  |  | Identify core and non-core expenses cut down on non-essential expenses | November 2007 | Internal resources | CFO, MM & all EM’s |
|  |  | Prepare monthly income and expenditure reports for the Executive Management and EXCO | Monthly | Internal resources | CFO |

| NO. | aCTIVITY | SUb-activity | deadline | cost | responsibility |
| --- | --- | --- | --- | --- | --- |
|  | Cash Flow Management | Analysing the long-term debt situation of the GKM and explore possibilities of consolidating loans with a reduced cost of borrowing | November 2007 | Internal resources | MM & CFO |
|  |  | Review the possibilities of disposing non-strategic immovable assets with a view of enhancing the cash flow position of the institution | Worship – 11/07 Business – 01/08 Residential – 03/08 Other – 05/08 | Internal resources | MM & EM’s |
|  |  | Review the debtors control and the debt management system, ensuring that the debtor-cleansing process is complete | March 2008 | R 500,000.00 | MM & CFO |
|  |  | Prepare monthly cash flow on a monthly basis for review by the Executive Management and EXCO. Cash flow reports to form part of quarterly reports to the full Council | Monthly | Internal resources | CFO |

| NO. | aCTIVITY | SUb-activity | deadline | cost | responsibility |
| --- | --- | --- | --- | --- | --- |
|  | Financial Management, internal controls and compliance | Address all the Auditor General queries that resulted in the disclaimer | May 2007 | R 1,000,000.00 | CFO |
|  |  | Ensure compliance with all the relevant statutes, especially the MFMA and its regulations, MPRA, MSA | Ongoing | Internal resources |  |
|  |  | Prepare monthly financial reports for review by the Executive Management and EXCO | Ongoing | Internal resources |  |
|  |  | Prepare monthly reports in compliance with all the grant funding requirements | Ongoing | Internal resources |  |

| NO. | aCTIVITY | SUb-activity | deadline | cost | responsibility |
| --- | --- | --- | --- | --- | --- |
|  | Governance | Review all policies and delegations of authority | November 2007 | R 500,000.00 | MM |
|  |  | Create protocol policy with regard to relations between council and staff | November 2007 | Internal resources | MM |
|  |  | Review the council structures/council committees and makes recommendations to the council | November 2007 | Internal resources | MM |
| 7. | Other matters |  |  |  |  |
|  | TOTAL |  |  |  |  |

# 6.	TURNAROUND STRATEGY

| Strategic Thrust | Component | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Strategic Objectives | Municipal Manager | Development of the Municipal SDBIP for ‘08/09 with realisable &measurable goals | Approved SDBIP | Alignment Synergy Strategic Leadership | Municipality to have an approved SDBIP that is aligned to the IDP | Draft: April 2008 Final: 1ST WEEK OF May 2008 | Municipal Manager |
|  |  | Development of Components/ Sectional SDBIP’s | Approved Component/Sectional SDBIP’s | Enhanced synergy | Components plans aligned to the Municipal IDP and budget | Draft end of March ‘08 Final: end of April ‘08 | Executive Managers |
|  |  | Review of SDBIP’s | Reviewed SDBIP’s | Performance Management and mid-term budget review | Achievement (review) of targets falling prior to the review date | Jan. ‘08 | Municipal Manager & Executive Managers |
|  |  | Compliance to set Norms and Standards | Periodic Reports | Improved efficiency & Service Delivery | 100% compliance with all the reporting requirements | Monthly | Municipal Manager |
|  |  | Improve effectiveness & Efficiency: Strategic Diary and Extended MANCO Meetings | Implementation of meeting resolution | Improved efficiency & Service Delivery Project monitoring and oversight | Implement all resolutions | Within set timeframes | Regional Manager |
|  |  | Improve effectiveness & efficiency: Regional Budget Committee | Implementation of meeting resolutions | Improved efficiency & Service Delivery | Implement all resolutions | Within timeframes | Regional Managers |

| Strategic Thrust | Component | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Strategic Objectives | Municipal Manager | Submission of monthly reports (to Exco, Council, etc.) | Relevant Report | Performance management; Quality of work | Monthly | 7th day of the following month | Municipal Manager |
|  |  | Implementation of the Municipal EPMDS in line with DPSA Guidelines | Compliance with Guidelines | Employee satisfaction, Enhanced employer/employee relations Enhanced image | 100% Compliance | Sept ‘07 | Municipal Manager |
| Protocol & Policy review |  | Drive the policy review program and establish procedures to implement policies | Review policies and procedures to establish a framework for decision making | Enhanced capacity | All policies, rules of order and by-laws reviewed | Management October ’07 Council November ’07 | Municipal Manager |
|  |  | Implement all policies, procedures and processes | Compliance | Enhanced image | 100% Compliance | Within set timeframes | Municipal Manager |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Service Delivery Improvement Program | Municipal Manager | Establishment of the Municipal profile, identification of the service backlogs and linking of the targets with Millennium Development Goals (MDG) | Compliance | Improved service delivery | 100% access to free basic services by the indigent; | Immediately | Municipal Manager |
|  |  |  |  |  | Access to services as per millennium development goals | Bucket system – ‘2007 Clean water – ‘2010 Electricity – ‘2012 |  |
|  |  | Set-up of Monitoring and Evaluation methods | Monitoring and Evaluation Process Plan | Improved service delivery Enhanced image | Developed M&E Process Plan | Nov. ’07 | Municipal Manager |
|  |  |  | Compliance | Improved service delivery Enhanced image | 100% compliance | Monthly | Municipal Manager |
|  |  | Meeting with local business and other stakeholders | Turnaround time in addressing queries, business needs and requests | Enhanced image Enhanced client relations Information /knowledge sharing | Conduct monthly meetings with established business fora and other stakeholders | Monthly | Municipal Manager (Executive Managers to attend) |

| Strategic Thrust | Component | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Ensure compliance with the Service Level Expectations | Social Development | Monitor and report to clients and stakeholders | Reports | All SDBIP targets achieved and the budget spent Client satisfaction | Submission of Reports | Monthly | EM: Social Development |
| Effective Management of Traffic and law enforcement with the Municipality |  | To ensure the safety of the citizens of the Municipality | Reports | Enhanced quality | Accurate Reports | Monthly | EM: Social Development |
| Ensure effective efficient and timely responses to disasters taking place within the Municipality |  | To ensure that the Municipality has in place, plans, mechanisms and capacity to respond to all forms of Disaster and emergencies that could occur | Disaster Management Strategy and Disaster Mngt. Plan | Disaster Manager Strategy and Disaster Management Plan | Submission of Reports | Strategy April ‘08 Plan May ’08 | EM: Social Development |
|  |  |  | % Expenditure on budget | Service Delivery | 100% expenditure | March ‘08 | EM: Social Development |

| Strategic Thrust | Component | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Effective and efficient local environmental Management program | Social Development | Implement Annual waste management program and ensure compliance with environmental requirements | Achieving of project milestones as per plan | Service Delivery | All project milestones achieved | June ‘08 | EM: Social Development |
| Effective stakeholder management |  | Improved efficiency & effectiveness: Local Liaison with Safety and Security Stakeholders, Waste Management and Transport | Implementation of resolutions | Service Delivery & client Satisfaction | All resolutions implemented | Monthly | EM: Social Development |
|  |  | Submission of Reports: Municipal Manager | Reports | Information sharing | All liaison meetings to be reported to the Municipal Manager, relevant Council Committees and the Council | Monthly | EM: Social Development |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Internal Compliance with legislative requirements | Social Development (Disaster Mngt.) | Conduct Hazard identification and risk assessments | Procedures | Improved safety | Identify and develop safe working procedures | Jan ’08 | EM:SD |
|  |  | Conduct OHS inspections in all municipal offices | OHS Reports | Improved safety | Report findings on OHS | Jan ’08 | EM:SD |
|  |  | Draft and implement necessary legal (SHE Reps) appointments in all municipal workplaces | Appointments made in all municipal workplaces and/or departments | Improved safety Safety skill capacity building | Appoint all line managers as section 16(2) of the OHS Act | Jan ’08 | EM:CS |
|  |  | Establishment of OHS Committees in municipal Workplaces | Established OHS Committees | Improved safety & shared responsibility | All workplaces with +20 staff to have OHS Committees | Jan ’08 | EM:SD |
| Provision of OHSE equipment and facilities |  | Ensure that employees performing high risk tasks have adequate equipment and facilities | Equipment, training and facilities | Employee satisfaction and improved safety s | Provision of necessary equipment | Jan ’08 | EM: CS |
| Emergency evacuation plan and procedures |  | Design emergency evacuation plans and procedures | Plans and Procedures | Improved safety | Conducting of emergency drills | Jan ’08 | EM:SD |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Effective management of consultants and contractors | Infrastructure, Planning and Development (IPD) | Monitoring of consultant and contractors implementing capital projects of the Municipality | Monthly monitoring and evaluation of services provided by the Consultants and Contractors | Quality control Service Delivery Implementation of the SDBIP | Timely implementation of all projects Accurate consultants database | Monthly | EM: IPD |
|  |  | Ensure contractors and consultants’ compliance to norms and standards | Quality and standard of service | Quality control | 100% Compliance to norms and standards | Monthly | EM: IPD |
| Provision of bid document |  | Preparation of bid documentation in line with generally accepted Contracts agreements (penalty clauses) | Bid Documents | Service Delivery & quality control | Complete Bid Documentation | Within the set timeframes | EM: IPD |
| Finalisation of Final Accounts |  | Reduce the number of outstanding final accounts | No. of final accounts cleared/finalised | Quality of data | Final Accounts of completed projects to be closed within three months | Monthly | EM: IPD |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Provision of Technical Support and reporting on progress to the Council through the relevant Committee | Infrastructure, Planning & Development | To ensure that the Municipality and its Council is kept abreast on the level of service regarding infrastructure and repairs | Meetings | Leadership Service Delivery Client satisfaction | Implement Council & committee resolutions | Monthly | EM: IPD |
| Fast – track the provision of repairs and renovations |  | Ensure Implementation of the repairs and renovations according to the SDBIP, especially civil work; | Repairs completed | Service delivery Client satisfaction | All requested R&R Finalised | Within set timeframes | EM: IPD |
| Provision of ad-hoc services minor new works and repairs |  | Ensure the implementation of ad-hoc capital project requests (minor new works) | Ad hoc project requests completed | Service delivery Client satisfaction | All requested minor new works completed on time | Within the set timeframes | EM: IPD |
| Utilisation of emerging contractors in line with the BBBEE |  | To empower emerging contractors | % of procurement value to emerging contractors | Job creation and enhanced BBBEE | Initial 30% of the Municipal R&R Services shall be allocated to BEE companies thereafter escalating at 20% p.a. | Jan. ’08 | EM: IPD |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Effective reporting | Infrastructure, Planning and Development (IPD) | Ensure effective and accurate reporting on EPWP | Monthly reports | Quality reports | Provision of the report | 7th day of each month | EM:IPD |
| Creating an enabling environment for targeted groups (BBBEE) |  | To empower the BBBEE Contractors | % Rand Value spent on BBBEE Groups | Job creation and enhanced BBBEE | 80% of Technical Services 60% of Program Management | March ‘08 | EM:IPD |
| Training of emerging contractors |  | To capacitate (skilling) the emerging contractors | Number of emerging contractors trained | Job creation and enhanced BBBEE | 100 emerging contractors | June ‘08 | EM:IPD |
| Promotion of labour intensive construction Methods |  | To increase the number of job opportunities | No of jobs created | Job creation | 500 labour intensive job opportunities | June ‘08 | EM:IPD |
| Special projects |  | To ensure successful completion of special projects | No. of special projects completed | Job creation and enhanced BBBEE | To complete all special projects | June ‘08 | EM:IPD |
| Stakeholder facilitation |  | Enhance and improve the efficiency and effectiveness of the regional contractors forum | Report on resolutions taken | Stakeholder satisfaction Enhanced image | All resolutions recommended to Head Office for consideration | Within set timeframes | EM:IPD |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Fleet Management | Financial Services | To ensure effective and efficient management of municipal and subsidised vehicles | Checked log returns | Enhanced asset utilisation | 100% Compliance to Transport handbook | 7th of each subsequent month | CFO |
| Moveable asset management |  | To ensure effective management and efficient utilisation of movable municipal assets | Completed movable asset register | Enhanced asset utilisation | All movable assets are bar-coded , registered and reconciled | Jan. ’08 June ’08 | CFO |
| Manage loss and theft of state assets |  | To ensure the safe-guarding of movable state assets | Internal Controls | Enhanced asset utilisation | 100% Compliance to internal controls | Monthly | CFO |
| Security & ICT Management |  | Ensure management of security and ICT to safeguard municipal assets and information | Renovated buildings | Enhanced efficiency | Renovate buildings by March ’08 | March’08 | EM:CS CFO & EM: IPD |
|  |  |  | Installed security system | Improved safety (documents and staff) & time mngt. | Install security system by March ’08 | After renovations | EM:CS |
|  |  |  | Improved documents security and storage systems | Improved safety (documents and staff) & time mngt. | 100% compliance to security standards | Monthly | EM:CS |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Compliance with Supply Chain Management | Financial Services (Supply Chain Management) | To ensure that the Municipality’s Supply Chain operates in compliance with the MFMA and Treasury Regulations | Compliance | Enhanced efficiency | 100% Compliance | Monthly | CFO |
|  |  |  | Contracts administration | Enhanced efficiency | Effective management of deposits, guarantees and variation orders | Monthly | CFO |
| Effectiveness and efficiency of bid committees |  | Enhance and improve the efficiency and effectiveness of the Committees | Report on resolutions taken (Minutes) | Service delivery | Implementation of all resolutions of the bid committees | Within set timeframes | CFO |
| Norms and Standards |  | To develop SCM Components’ Norms and Standards | Norms and Standards | Service delivery | Developed Norms and Standards | Jan ’08 | CFO |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Revenue and expenditures control | Financial Services (Governance) | To ensure effective and efficient control of revenue and expenditure | Monitoring of revenue/expenditure | Increased revenue and costs reduction | 100% utilisation of budget | June ’08 | CFO |
|  |  |  |  |  | 100% Collection of revenue/debts due | June ‘08 | CFO |
|  |  |  |  |  | Reduction of operational expenditure by 10% from previous year | June ’08 | CFO |
| Compliance with MFMA and Treasury Regulations |  | To ensure that the GKM Complies with the MFMA and Treasury Regulations | Compliance | Unqualified audit reports | 100% compliance | June ’08 | CFO |
|  |  |  | Payment of creditors within 30 days | Supplier satisfaction | 100% compliance | Monthly | CFO |
|  |  |  | Reduced Audit queries | Unqualified audit report | Reduction of audit queries by 30% from the previous financial year | Within specified timeframe | CFO |
|  |  | To ensure proper allocation of expenditure/revenue | Cleared suspense accounts | Quality control | Clearance of all suspense accounts | June’08 | CFO |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Cash management | Financial Services (Cash Management) | To ensure effective control of municipal cash resources | Bank reconciliations | Risk reduction | Conduct bank reconciliations on a weekly basis and submit to the Mayor and MM | Weekly | CFO |
|  |  |  | Improved cash management | Risk reduction | 100% Compliance | Monthly | CFO |
|  |  |  | Consolidated long term loans | Expenditure reduction | 100% Compliance | June ’08 | CFO |
| Internal Controls and Internal Audit Support |  | To ensure that the municipality has effective internal controls to detect and prevent Fraud and Risks related thereto | Effective Internal audit | Risk reduction | Approved Regional Policy /Plan | June ‘08 | CFO |
|  |  |  | Effective audit committee | Compliance | 100% Compliance | Monthly | CFO |
| Risk Management and fraud prevention |  | To ensure effective implementation of Fraud and Risk Prevention Policy/Plans | Developed Municipal Policy/Plans | Risk reduction | Approved Policy /Plan | June ‘08 | CFO |
|  |  |  | Compliance |  | 100% Compliance | Monthly | CFO |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| HR Management | Corporate Services | Reduction of Vacant Posts | No. of posts filled | Service delivery | Filled all strategic posts (15 identified) | March ‘08 | EM: CS |
|  |  | Development of Municipal Induction Programme | Induction Programme for all new employees | Reduced learning curve | All new employees taken through the Induction Programme | Program start: April ‘08 Within a month of new appointment | EM: CS |
|  |  | Implementation of the EAP Programme | Staff assistance (social issues) provided by EAP | Employee satisfaction Enhance staff performance Harmonious working environment | Awareness program | March ‘08 | EM:CS |
|  |  |  |  |  | Provision of EAP assistance to all staff members referred /Volunteer | As and when needed | AM: HR |
|  |  | Reduction of the Payroll as a % of total budget | Reduction of payroll expenditure | Service delivery | Reduce 42-35% (P1) Reduce 35-30% (P2) | Sept. ’07 (phase 1) July ’08 (phase 2) | EM:CS |
| Performance Management |  | To enhance EPMDS capacity within the Municipality | Municipal EPMDS S Training | Employee satisfaction | All relevant HR Staff Trained on EPMDS (Local Govt. Guidelines) | June ‘08 | EM:CS |
|  |  | To implement the EPMDS | Compliance to Local Govt. Implementation guidelines | Performance management Service delivery | 100% Compliance | June ‘07 | EM: CS |

| Strategic Thrust | Perspective | Strategic Objective | Key Performance Indicator / Measure | Target | Timeframe | Accountability |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Output | Outcome |  |  |  |
| Training and skills development | Corporate Services | To conduct a skills audit in order to identify the skills gap To implement the Workplace skills plan by providing training | Training on Identified skills gaps | Enhanced Capacity | All training on identified skills gap completed | March ‘08 | EM:CS |
|  |  | To implement the ABET Training Programme | No. of people trained | Enhanced capacity | 60% of employees as per the skills audit to be trained by the end of the financial year | June ’08 | EM: CS |
| Labour relation matters |  | To improve employer employee relations | Grievances lodged and DC matters | Harmonious working environment | Finalisation of all outstanding grievances by the end of the financial year | June ‘07 | AM: HR |
|  |  |  |  |  | Compliance to grievances and DC procedures for new cases | Monthly | EM: CS |
| Transformation |  | To ensure Municipal recruitment and selections processes take into account the approved Employment Equity Plan & targets | Developed Municipal EE Plan & Targets | Transformed work environment | Approved Municipal EE Plan & targets | Nov. ‘07 | EM: CS |
|  |  |  | Compliance to approved EE Plan & targets | Transformed environment | 100% Compliance | Each Appointment | EM: CS |

# 7.	sOURCES

7.1	 Auditor General reports – 2000-2006

7.2 	Greater Kokstad Municipal Recovery Plan

7.3	Greater Kokstad Municipality – Human Resources Audit and Implementation

7.4	Kuyasa “New Dawn” – A turnaround Strategy for the Greater Kokstad Municipality

7.5 	Assessment to determine whether MAP objectives at Greater Kokstad were achieved

8. 	LEGEND

8.1	MM		- 	Municipal Manager;

8.2	EM-CS		-	Executive Manager – Corporate Services;

8.3	EM-IPD	-	Executive Manager – Infrastructure, Planning and Development;

8.4	EM-SD		- 	Managers – Social Development;

8.5	CFO 		- 	Chief Financial Officer

8.6	EXCO		-	Executive Committee of the Council

8.7	Council 	- 	The full Council of the Greater \Kokstad Municipality

# Comments

May not be applicable for this report.

May not be applicable for this report.

May not be applicable for this report.

May not be applicable for this report.

May not be applicable for this report.