TABLE OF CONTENT

Page

1.    	Executive Summary								5

2.	Introduction		 							10

3.         MDDA Vision, Mission and Values						11

3.1	Vision 								11

3.2	Mission 								11

3.3	MDDA Values 							12

4.	The MDDA mandate and beneficiary groups				12

4.1	Mandate								12

4.2	Beneficiary groups, focus areas and general approach		13

4.2.1   Beneficiary groups						13

4.2.2	Focus areas							14

4.2.3	General approach						14

5.	The legislative framework that supports the work of the

MDDA                                                                                              	15

6.	Summary of MDDA achievements in the financial year 2007/8		17

7.	MDDA external and internal challenges and their implications

to the organization								21

7.1       MDDA external challenges						21

7.2       MDDA internal challenges						24

8.         MDDA 2007 – 2010 Strategic Focus					24

8.1       Rationale								25

8.2       Overall objective							27

8.3       Purpose								27

8.4       Result areas in relation to purpose statement 			27

8.5       Strategic Objectives in relation to result areas			28

9.         Risks and risk containment measures					51

9.1       Policy level								51

9.2 	Operational level							51

9.3 	Beneficiary level							52

9.4	Risk identified register and analysis report 			53

9.5	Action plan to mitigate the risks					55

10. 	 Services delivery improvement program					60

10.1	 Grant Funding Cycle						61

10.2 	Project Tracking System						64

11. 	Information Technology Plan						65

11.1 General IT Controls and Facillities Management Plan		66

12. 	Institutional Capacity required to implement MDDA program

initiatives to the period 2008 -2011                                           		67

13. 	MDDA Human Resources Plan for Implementation of its

strategic focus 2008 – 2011							69

13.1	Organisational Structure						70

14. 	Reporting									71

# 15.	Strategic Objectives in relation to Key Result Areas 		72

# Financial Year 2009/10

# Strategic Objectives in relation to Key Result Areas 		87

# Financial Year 2010/11

17.	Finance Implications and Budget for the period 2008 – 2011	102

“MDDA is a statutory development agency for promoting and ensuring media development and diversity, set up as a partnership between the South African Government and major print and broadcasting companies to assist in (amongst others) developing community and small commercial media in South Africa, in terms of the MDDA Act No 14 of 2002."

STRATEGIC AND BUSINESS PLAN

EXECUTIVE SUMMARY

1.	 Executive Summary

- This document reflects the strategic path the Media Development and Diversity Agency (MDDA) is taking for the period starting 2008 and ending in 2011, in accordance with Treasury Regulations (as amended), Notice 29644 of 20 February 2007, MTEF Treasury Guidelines June 2007 and Framework for Managing Programme Performance Information May 2007, issued in terms of the Public Finance Management Act, 1999.

- It outlines the overall strategic approach that the MDDA is proposing for the period 2008-2011, the legislative and environmental context within which the MDDA is placed, the key program focus areas and the organisational and resource implications of the proposed strategic approach.

- The MDDA (the Agency) is a statutory development agency for promoting and ensuring media development and diversity, set up as a partnership between the South African Government and major print and broadcasting companies to assist in (amongst others) developing community and small commercial media in South Africa.  It was established in 2003, in terms of the MDDA Act, No 14 of 2002 and started providing grant funding to projects on the 29th January 2004.

- The Agency operates within a broad legislative framework including the MDDA Act itself, the Constitution Act, the Public Finance Management Act, the Electronic Communications Act, the ICASA Act, the Promotion of Administrative Justice Act, the Promotion of Access to Information Act, the Skills Development Act, the Broad-based Black Economic Empowerment Act and the Labour Relations Act, amongst others.

- The vision of the MDDA is that “Each and every South African Citizen should have access to a choice of a diverse range of media”

- The MDDA “is a development agency that will assist in building an environment where a diverse, vibrant and creative media flourishes and reflects the needs of all South Africans.”  The MDDA does this by (amongst others);

- The provision of grants and subsidies to media projects and the promotion of media development and diversity

- Leveraging resources and support through technical assistance

- Conducting and funding research

- Facilitating capacity building

- Advocating for media diversity.

- The MDDA works primarily with historically disadvantaged persons and communities; priority will continue to be to increase our focus on rural and poor communities as well as historically diminished language and cultural groups and inadequately served communities. Accordingly we will continue to increase work done in provinces outside of Gauteng and the Western Cape.

- The Agency will continue to focus on ensuring that all citizens can access information in a language of their choice and contributing to the transformation of media access, ownership and control patterns in South Africa.

- Since its formation, the MDDA has achieved some major milestones including (as at 31 January 2008) the awarding of grants to the amount of R55.2m to over 172 projects, the provision of 49 bursaries to different radio and print media and the receipt of unqualified audits since its establishment.

- The major challenges that are faced by the MDDA include; the limited funding that it has including the duration of existing funding agreements (which are to expire in 2009), the regulatory framework that governs the MDDA in terms of the regulations requiring Tax certificates and audited financials from groups that are in their formative stages, the generally disempowering environment in print media, the lack of skills amongst the socioeconomic groups that are targeted by the MDDA, the limited broadcast frequency and the limited exposure of the small commercial and community media to advertising revenues and marketing skills.

- The purpose of the MDDA programs in this period is to “strengthen the sector though the provision of resources, knowledge and skills in pursuit of promoting media development and diversity”

- In this context, the Agency will in the ensuing period, focus its work on:

  - advocacy for the alternative sector,

  - giving grants and seed funding support for community radio in the nodal areas,

  - capacity building interventions with the MDDA beneficiaries including mentorship,

  - monitoring and evaluation,

  - research and increasing knowledge of the MDDA to better structure program intervention and innovation,

  - stakeholder management, and

  - resource mobilisation.

Monitoring and Evaluation will play a key role in structuring future program involvement, design and development.

- The rationale for the MDDA strategic focus for the ensuing period is predicated on the fact that historically disadvantaged communities are deprived of access to information that can assist them to participate actively in socio-economic improvement and democratic processes of the country. Current media is still insufficiently diverse with respect to reflection of the concerns of especially the socio-economically marginalised communities. Approximately 80% of the SA population is African, yet a huge number of indigenous language media products are written and produced in English. This is in direct contradiction to the notion of recognising all languages on an equal basis as prescribed by the constitution.

- Several risks and /or constraints exist that can limit the impact and work of the MDDA in this period. Amongst others is the legislative and regulatory framework which may prove to be inflexible. The delay in the finalisation of the Regulation to be prescribed by ICASA in terms of the Section 89 of the Electronic Communications Act of 2005. The limited human resource base within the MDDA may limit response levels to demand. Another is the possibility of the misuse of funds by the beneficiaries. The MDDA has reviewed a number of legislative, regulatory and policy positions and has planned in the ensuing period to suggest a limited number of changes that may assist in the smooth functioning of the organisation. The board has also agreed to review a number of internal operational and HR policies and procedures as well as maintaining stringent controls at the project management level.

- In this context the MDDA has developed a set of interventions to mitigate against these risks. A key strategy to mitigate risk will be the management and institution of strict controls in the organisation through internal and external audits. Increase the staff’ complement to the extent reasonably possible within the funding constraints and the regulatory limit of 25% funds spent on administration. The board will continue with briefings to the minister and the portfolio committee on any problems that may be encountered and how these have been resolved. Staff development, performance management and a diligent process of project assessment and monitoring will continue to be a routine of the MDDA.

- Accordingly, the Agency reviewed its staff compliments from 13 in the financial year 2006/7 to 19 and 21 going forward given the human resources requirements identified to implement the Strategic and Business Plan. Expanding activities will require an expansion of the staff complement, the scale of which will become clearer as there is more clarity in particular regarding the financial impact of the provisions of the ECA Act with respect to the MDDA, a matter that will depend on the Regulations being prescribed by ICASA on the contributions of the Broadcasting service licensees.

17.	The financial projections for the MDDA are based on a scenario of Broadcasting Service Licensee contributions being 0.2 % of their annual turnover. This is also based on the assumption that Broadcasting Service Licensees will contribute to the MDDA and that the Agency will have a Memorandum of Understanding with USAASA aimed at providing a framework for working together and sharing information with respect to universal service and access in the broadcasting industry. Hence, the budget below shows an increase in red from 2008 – 2010, but for the purpose of planning, our budget is based on the current income streams. Accordingly, projections in this regard are as follows:

| Description | 2008/09 | 2009/10 | 2010/11 |
| --- | --- | --- | --- |
| Total budget from GCIS | 14 558 000 | 16 709 000 | 18 449 000 |
| Broadcasting Service Licensees | 19 930 000 6 000 000 | 21 723 000 6 000 000 | 21 723 000 6 000 000 |
| Print Funders | 4 800 000 | 4 800 000 | 4 800 000 |
| TOTAL | 37 288 000 25 358 000 | 43 232 000 27 509 000 | 44 972 000 29 249 000 |

STRATEGIC AND BUSINESS PLAN 2007-2010

2.	 Introduction

This document reflects the strategic path the Media Development and Diversity Agency (MDDA) is taking for the period starting 2008 and ending in 2011, in accordance with Treasury Regulations (as amended), Notice 29644 of 20 February 2007, MTEF Treasury Guidelines June 2007 and Framework for Managing Programme Performance Information May 2007, issued in terms of the Public Finance Management Act, 1999.

It outlines the overall strategic approach that the MDDA is proposing for the period 2008-2011, the legislative and environmental context within which the MDDA is placed, the program focus areas and the organisational and resource implications of the proposed strategic approach.

This strategic approach and business plan was discussed, considered and endorsed by the MDDA board meeting held on the 01st February 2008. The strategic approach and business plan is the responsibility and prerogative of the board and who have duly considered same as part of their governance role as required by the MDDA Act and the Public Finance Management Act (PFMA).

The MDDA (the Agency) is a statutory development agency for promoting and ensuring media development and diversity, set up as a partnership between the South African Government and major print and broadcasting companies to assist in (amongst others) developing community and small commercial media in South Africa.  It was established in 2003, in terms of the MDDA Act, No 14 of 2002 and started providing grant funding to projects on the 29th January 2004.

The MDDA receives funding from government, as well as from major commercial and public media entities [Caxton (Pty) Ltd, Independent Newspaper (Pty) Ltd, Johnnic (now called AVUSA) Publishing Ltd, Kagiso Broadcasting (Pty) Ltd, Media 24 Ltd, Midi (Pty) Ltd (etv), Electronic Media Network Ltd (M-Net), PRIMEDIA Broadcasting  (Pty) Ltd, the SABC Ltd ].

3.	The MDDA Vision, Mission and Values

3.1 	Vision

3.2	Mission

“

The MDDA does this by;

- The provision of grants and subsidies to individuals media projects and the promotion of media development and diversity

- Leveraging resources and support through technical assistance

- Conducting and funding research

- Facilitating capacity building

- Advocating for media diversity

3.3	MDDA Values

In fulfilling its mission the MDDA is committed to uphold the following values and their meaning:

| VALUE STATEMENT | MEANING |
| --- | --- |
| Integrity | We are honest, reliable, fair, accountable and responsible for our actions |
| Caring | We are tolerant; courteous and respectful to our staff and clients alike |
| Professionalism | We are efficient, effective, service delivery orientated, punctual, performance driven and work collectively |
| Commitment: | We are passionate, go the extra mile, responsive, have a strong work ethic, are consistent and accessible |
| Transparency | We are open and participatory in our dealings with internal and external parties |

4.	The MDDA mandate and beneficiary groups

4.1	Mandate

The mandate of the MDDA is to

  - Create an enabling environment for media development and diversity which reflects the needs and aspirations of all South Africans.

  - Redress exclusion and marginalisation of disadvantaged communities and persons from access to the media and the media industry.

  - Promote media development and diversity by providing support primarily to community and small commercial media projects.

  - Encourage ownership and control of, and access to, media by historically disadvantaged communities as well as by historically diminished indigenous language and cultural groups.

  - Encourage the development of human resources and training, and capacity building, within the media industry, especially amongst historically disadvantaged groups.

  - Encourage the channelling of resources to the community media and small commercial media sectors.

  - Raise public awareness with regard to media development and diversity issues.

  - Support initiatives which promote literacy and it culture of reading.

  - Encourage research regarding media development and diversity; and

  - Liaise with other statutory bodies such as the Independent Communications Authority of South Africa (ICASA) and the Universal Service and Access Agency (USAASA).

4.2	Beneficiary groups, focus areas and general approach

4.2.1	Beneficiary groups

The MDDA works primarily with;

- Historically disadvantaged persons/communities especially in rural areas outside of Gauteng and the Western Cape

- Historically diminished language and cultural groups

- Inadequately served communities

4.2.2	Focus areas

The MDDA will focus on the following areas to fulfil its mandate;

- Community media projects

- Small commercial media projects

- Research, training and development projects

    - General approach

In general the MDDA, shall through all its activities:

- Actively encourage collaboration between different media groups.

- Encourage collaboration between media groups and other community entities (including USAASA, telecentres, Thusong Service Centre (former MPCC’s), Arts centres, CBO’s and NGO’s)

- Actively collaborate with other national Development Finance Institutions (DFIs) such as SEDA, NEF, IDC, Umsobomvu Youth Fund, National Youth Commission, etc.

- Work closely with MAPPSETA, ISSETSETA, NEMISA, etc. in respect to skills development programme.

The MDDA will prioritise support for media projects focusing on rural communities and/or audiences not adequately served by existing media. The Agency will also focus on creating an enabling environment for media development and diversity.

5. 	The legislative framework that supports the work of the MDDA.

In addition to the Media Development and Diversity Agency Act No 14, of 2002 that establishes the MDDA, the MDDA work is guided by a number of relevant and related legislation, which it is required to comply with, including and most importantly the Constitution of the Republic of South Africa.

Key amongst these laws, is the Public Finance Management Act No, 1.of 1996, the Electronic Communications Act No 35 of 2005, Constitution Act 108 of 1996, the BBBEE Act No.59 of 2003, the Labour Relations Act No 96 of 1995, the Employment Equity Act of 2000, the Skills Development Act and other relevant legislation, Regulations prescribed in terms of the respective legislations that are signed into law by the President from time to time, MDDA Regulations and relevant Government policy positions.

The MDDA Act has been “strengthened” by the enactment of the Electronic Communications Act of 2005. The Electronic Communications Act of 2005 (ECA) opens up a new possibility with respect to the financing of the Media Development and Diversity Agency (MDDA).  As a result of this new law, there is an opportunity for growth, as major changes may arise in view of the ECA.

The ECA provides for a potentially sustainable mechanism for funding the objects of the MDDA Act, subject to the convincing Broadcasting Service Licensees that their contributions are in good use in the hands of the MDDA, in terms of its mandate.

Section 87 of the ECA provides that:  “(1) Despite the repeal of the Telecommunications Act by this Act, the Universal Service Fund established in terms of section 65(1) of the Telecommunications Act continues to exist in terms of this Act and will henceforth be called the Universal Service and Access Fund, and the Agency must keep account of the Fund in its books and credit the Fund with —

(a) Universal service contributions referred to in section 89; and

(b) Money accruing to the Universal Service and Access Fund from any other source.

(2) all moneys received, the amounts of which in terms of subsection (1) must be credited to the Universal Service and Access Fund in the books of the Agency, must be paid into the National Revenue Fund established by section 185 of the Constitution.”

Section 89 provides that: “ (1) Subject to subsection (3), every holder of a license granted or considered to have been granted in terms of Chapter 3 must pay, in addition to any other fees contemplated in this Act or the related legislation, the prescribed annual contributions of the licensee’s licensed activity to the Universal Service and Access Fund. (2) The Authority must prescribe—

(a) the basis and manner of determination of such contributions, which must not exceed 1 per cent of the licensee’s annual turnover or such other percentage of the licensee’s annual turnover as may be determined by the Minister after consultation with the affected parties, by notice in the Gazette; and (b) the dates when such contributions become payable and the manner in which they may be paid.

(3) Broadcasting service licensees contributing to the Media Development and Diversity Agency (‘‘MDDA’’) must have their annual MDDA contribution set off against their prescribed annual contribution to the Universal Service and Access Fund.”

The Agency analysed the ECA in the previous financial year, developed an approach and an MDDA Fund Development Strategy, engaged with Broadcasting Funding partners, engaged with USAASA and ICASA,  In accordance with the Agencies fund development strategy, a Roundtable with Broadcast Service Licensees was held on the 22nd October 2007, Sunnyside Park Hotel, Parktown. The Minister (in the Presidency) attended the roundtable and the Communications Minister sent a representative.

This followed a joint workshop with USAASA (also attended by ICASA) in August 21 – 22, 2007 where both Agencies shared their understanding and an approach to the ECA. The Agencies agreed to develop a MoU and to suggest to the respective Board’s that Broadcast Service Licensees make their contributions to MDDA, whereas the other Communication Service Licensees (in particular Telecommunications) continue to contribute through the USAF. MDDA Board approved the approach and accordingly this informed the Agency submission to ICASA, whereas USAASA needed the DoC’s direction.  ICASA hearings were held from the 12th – 14th March 2008. It is expected that the Regulation will be published in and around April / May 2008.

MDDA is in discussion with USAASA, NEMISA, MAPPSETA, ISSETSETA, DoC, etc. and is considering entering into Memoranda of Understanding in order to ensure complementary and supportive roles in pursuit of its legislative mandate.

6. 	Summary of MDDA achievements in the financial year 2007/8

In the financial year 2007/8, the Agency has, amongst others activities, began implementing the Strategic Plan 2007/10, studied the mandate as determined by the Board and operationalised the Strategic Planning 2007/8. This detailed Operational Plan gave meaning and effect to the Strategic and Business Plan 2007-10 as approved by the Board in March 2007 and tabled in Parliament.

The Operational Plan is in line with the Treasury Regulations in terms of PFMA; objectives are measurable and aligned to the Budget. This assists the Accounting Authority (the Board) in its additional responsibility to ensure that the annual report and audited financial statements fairly present the performance against predetermined objectives of the Agency. This is a requirement in terms of the Treasury Regulations and Section 55 (2) (a) of the PFMA. Accordingly, this Operational Plan is a subject matter / agenda item of every Board and Executive Management meeting in line with the regulatory requirements and good corporate governance. This exercise has added value to the Agency in terms of providing an ongoing oversight on the implementation. This ensures that the Agency complies with the requirements of Auditor General’s audit finding in terms of Section 20(2) (c) of the Public Audits Act No. 25 of 2004 on the reported information relating to performance against predetermined objectives.

The Agency also held valuable engagements with strategic stakeholders (amongst others ICASA, USAASA, GCIS, PMSA, MAC Council, NEMISA, MAPPSETA, NCRF, SAPO, SABC, ENABLIS, World Bank, etc.), undertook a number of organizational tasks including job evaluation, developing a benchmark guideline for project’s budgets facilitating funding decisions, review of schedule of approvals and disbursement and other normal day to day activities of the Agency.

The commitment and hard work of staff has been shown through the deliverables, amongst others, funding approvals amounting to approximately R55m, thereby increasing the number of beneficiary projects to 172, as at January 2008.

The agency still has challenges ahead, ranging from ensuring that funding is properly used by projects, assessing the impact of the Agency’s intervention’s countrywide and against the national priorities and the MDDA Act.

Operationally, it is very clear that the staff composition as it stands cannot sustain the workload. This has been independently confirmed through both the Bulumko Report (which propose a 32 staff complement) and ICMS Report (which propose a 24 staff complement) Reports. The Board has decided that the increase in staff capacity be progressive in order to be sustainable and achieve the strategic objectives of the Agency. This is critical to avoid staff fatigue and to ensure that Management focuses.  The complement for the financial year 2008/9 will be 19 and will increase to 21 depending on the availability of funding.

Further, the Delegation of Authority is being developed and properly streamlined, in order to further formalise role definition between the Board and Management. Hitherto, through the guidance of the MDDA board, the dedication of management and staff, and the adherence to King 2 Commission principles of Governance as well as the dictates of the Public Finance and Management Act, the MDDA can highlight the following achievements in the pursuit of its Vision and Mission in the financial year 2007/8.

- The ongoing review of the organization, systems and procedures, and policies,

- Populating the organisation with staff to run the affairs of the organisation,

- Engagement with Broadcasting Service Licensees regarding the ECA and the forthcoming review of the funding agreements,

- Ongoing discussions with Print Media Association of SA (PMSA) regarding the forthcoming review of the funding agreements,

- Increase in the Government funding, with R9m for the MTEF 2008/11 over and above the R2m increase in 2007/8,

- The spending of approximately R55m in grants for 172 media projects cumulatively  as at January 2008,

- The provision of  bursaries to 49 different radio and print managers as at January 2008,

- The evaluation of MDDA organizationally after 4 years of operation,

- The consistent receipt of unqualified audits with even no matters of emphasis,

- Putting MDDA on the public agenda – SAFM Radio interviews, Annual Report launch, SABC TV News coverage, City Press, The Media Magazine, Leadership Magazine, CEO Magazine, Gauteng Companies, BizCommunity, CNBC Africa, Alfred Nzo Community Radio, etc.

- The development of capacity in Monitoring and Evaluation, Project Management, Records Management and Financial Management

- The development of a database of grassroots publications in partnership with AIPSA

- Envisioning TV: Research in the Policy, Strategy and Models for Community Television in South Africa – HSRC

- Equal in the Eyes of the Media: Research into the Visibility and Access to the Media by Underserved Groups

- Out in the Media? Knowledge, Attitude and Practices of the Media towards Lesbian, Gay, Bisexual, Transgender and Intersex Issues and Stories – Gay and Lesbian Archives (GALA)

- Grassroots Advertising Procurement Feasibility Study – Association of Independent Publishers (AIP)

- Print, Distribution, Circulation and Marketing of the Grassroots Press in South Africa – Graeme Addison

- Research into Indigenous Language Newspapers – Harambe Concepts

- Revealing Race: A Study on the Representation of Race and Racism in the Media - Media Monitoring Project

- Research into the Development of SMME TV, an IPTV and Social Media Platforms for Small, Medium and Micro Enterprises

- Maintaining good relations with stakeholders – funders, parliament, the Presidency, DoC, GCIS, ICASA, USAASA, NCRF, beneficiaries and  research institutions

- Working as a team internally

- Staff development e.g. Project Management, Records Management, Financial Management,

- The growth of demand for MDDA support,

- The growth in the demand for increased funding for MDDA, i.e. Parliament, the Ruling Party, etc.

- Reaching our disbursement targets within time.

In spite of these achievements the MDDA has faced a number of external and internal challenges.  These are outlined in the next section of this plan.

7. 	MDDA external and internal challenges and their implications to the organisation

  - MDDA external challenges

The limited funding income against the value of requests received and the need out there, and the duration of funding agreements (which are about to expire in 2009) is a challenge for the MDDA. This could frustrate the MDDA from delivering on its mandate and can lead to uncertainty amongst staff and project beneficiaries alike, similarly the initiatives who submit applications to the Agency could be demoralised. Again in the light of the ECA provision for funding and the potential growth of the sectors served by the Agency, the MDDA may not be able to respond to new opportunities in time and at the same pace as they develop.

The regulatory framework of the MDDA is also another challenge. The qualifying criteria and demand for Tax certificates and audited financial statements, whilst desirable and are in law are very difficult to meet by newly emerging organisation that do not have capacity and, systems in place. This may lead to the MDDA supporting those that are better established, stronger with more resources.

The environment for print media development is not enabling. There is little diversity in ownership and the control of the mainstream print media. The socio-economic conditions and the lack of skills amongst the historically disadvantaged communities, poses a real challenge with respect to the MDDA delivering on its mandate and may call to question the sustainability strategies for the MDDA funded projects. In addition, the lack of skills within projects to plan and to manage funds in accordance with budgets against determined objectives and in accordance with the contract signed with MDDA, similarly internal controls and financial management at projects level.

Another key challenge is the high recruitment of people from the sector to more lucrative commercial and public broadcast media. Due to the shortage of skills in the sector, staffs are mobile and move on as soon as they are trained, many moving out of the small media sector. This impact negatively on the management and sustainability of the MDDA supported projects and could drain MDDA resources due to a demand for ongoing support. It therefore requires that MDDA continue to support these projects, as they lead to the growth of the industry and therefore contribute in many ways to economic development. The community and small commercial media sector de facto provides a training ground for the broad media industry.

The limited broadcast frequency spectrum could impact on the ability of the MDDA supporting more community and radio and television, the lack of diversity with regard to distribution and printing facilities could lead to the closure of some of the MDDA supported initiatives that cannot sustain the costs of printing and distribution.

Another key challenge for the sector is the exposure of small commercial and community media to marketing and advertising revenues. The sector is not able to attract these revenues as these are dominated by the big media owners. This continues to frustrate the efforts of the sector and limits their growth and sustainability as these may continue to rely on MDDA type of funding.

In addition to small commercial and community media, South Africa has a wide range of niche/atypical community media such as publications produced by trade unions, non-governmental organizations, religious institutions, student bodies and so on. This atypical community media reaches and serves communities which are not necessarily served by mainstream media. This includes workers, rural dwellers, unemployed people, students and other categories served by unions, NGOs and other such similar organizations. To illustrate, each of the more than 60 trade unions in South Africa produces media on a regular basis. Typically, the key problems they face have less to do with funding for production but more to do with skills, product development, management, business planning, content development and distribution.

Similarly, the more than 15,000 NGOs that exist in the country also produce media for the communities they serve. Such media is normally funded from the programme funds of the NGOs. In other cases, many NGOs also struggle to fund the production of media from their programme funds. The MDDA regards this atypical media as having an important role and contribution to make in the development and diversification of the media. The MDDA strategic plan and operational plans will ensure that the MDDA takes action to facilitate the realisation of this potential.

A major challenge for the MDDA is how it can utilise the potential that exists for the small commercial media sector for distribution and possible revenues from their associated alternative organizations such as South African Post Office (SAPO), Union Federations, NGOs and other such groups in civil society.  As an example 3 Union federations have more than 2 million members and there are more than 15000 NGOs in the country. In this context, the MDDA will through its stakeholder management initiative lead a process where its beneficiaries might find value that could lead to their long term sustainability as well as address some of the key systemic issues in the media environment in general. A media co-operative could be contracted by unions and use economies of scale to earn income from such contracts thereby securing financial resources. This can even serve as a stable to secure common advertising for various publications, follow the hub approach, etc.

To achieve the above, the Agency will strengthen its advocacy and lobbying activity, through targeted and systemic engagements with unions, NGOs to introduce the MDDA and the above objective.

Lastly, there remains a challenge of the co-ordination of efforts by all DFI’s, training etc. in the media sector. The impact of regulations relevant and related to the work of the Agency, like those of ICASA (the licensing framework, etc.), etc., need an ongoing check.

7.2 	MDDA internal challenges

A key challenge for the MDDA is the level of organisational skills and capacity both in terms of numbers, knowledge and skills given the broad spectrum of projects across the country. The more the projects expand the less is the capacity of the MDDA to manage, monitor and evaluate, and report on these projects adequately. Monitoring suffers as Project Managers prepare for new projects. This state of affairs could lead to staff fatigue, stress, poor project selection for funding and poor monitoring and evaluation of the impact of the Agency interventions in pursuit of its mandate.

Another challenge is the inadequacy of the MDDA financial resources which limit the MDDA’s ability to recruit and retain appropriate and the best staff the market can offer. There is a general dissatisfaction by staff regarding salaries and benefits offered by the organisation in comparison to those of similar organisations in the market. This could lead to high staff-turnover levels, poorly motivated staff and poor performance. The need has arisen for the policies of the organisation to be reviewed and aligned competitively to the market given the growth of the Agency and the need to retain staff.  Lastly, the Agency need to create an environment that acknowledges and appreciates the “extra mile” contribution by staff.

On the overall the ongoing challenges are with respect to ensuring that the plan is measurable, realistic, implementable within the resource constraints and that there is functional communication strategy.

8.	MDDA 2008-2011 Strategic focus

In this section, we outline the strategic focus that the MDDA will assume given the external and internal challenges that have been articulated and the support that is anticipated from the MDDA funders and stakeholders. The focus is also based on the analysis of the challenges facing the sector and the review of the mandate of the MDDA. The plan is therefore intended to ensure that the Agency turns the tide and changes the media landscape. Further, it adds the Agencies value into some of the 24 Apex Priorities identified by the President, in his State of the Nation Address, in order to advance towards the realisation of the all important goal of a better life for all.

8.1	Rationale

Historically disadvantaged communities are deprived of access to information that can assist them to participate actively in the democratic processes of our country. Current media (in particular print) lacks diversity and recognition of indigenous languages and culture. Approximately 80% of the SA population is African, yet a huge number of indigenous language media products are written and produced in English. This is in direct contradiction to the notion of recognising all languages on an equal basis as prescribed by the constitution.

Advertising tends to be biased toward media houses with adequate financial resources. Marketing skills are also lacking in the sector. In many communities, especially rural communities, frequency spectrum allocation, printing facilities and distribution are inadequate. This frustrates efforts of small community initiated media to advance and to be effective.

Small commercial media projects have limited access to printing in terms of lack of resources (costs and facilities) as a result of long distances that they have to travel.

Distribution of publications is a huge challenge, both in terms of costs, capacity to circulate, readership and with respect to compliance with various Municipal by-laws.

Access to advertising for small commercial media remains a stumbling block to their growth and viability. Similarly their inability to acquire the Audit Bureau of Circulation (ABC) certificate disadvantages them in the market.

The sector lacks appropriate and relevant skills in respect of marketing; financial management and production management.

English remains a dominant language used at the expense of the societal diversity of languages, in particular as it relates to indigenous languages. Society still has a challenge regarding literacy and the culture of reading.

In general, the sustainability of small commercial media targeting historically disadvantaged communities under the current market conditions is a challenge. There is a dearth of knowledge and information that can adequately identify critical issues in the small commercial and community media sectors in South Africa. The absence of this information, at primary or secondary levels, limits innovation and learning for the sector in general.

The small commercial and community media sector is further disadvantaged by the lack of appropriate skills in the management, development and sustenance of their efforts. This situation could lead to a further decimation of the sector and the limitation of the work of the MDDA.

These problems are highlighted in the AMDI report, the SANEF study on the skills shortage in the sector, and the Loan Fund reports. The apparent lack of skills within the media is therefore a challenge for advancing, defending, deepening and promoting the democratic dispensation in South Africa.

Some of the causes of these issues are rooted in the legacy of apartheid and the historical monopoly in the print media industry as well as the socio-economic conditions faced by the disadvantaged communities and the lack of exposure to resources, good and proper education by the Historically Disadvantaged Communities.

The consequence of these issues is that there is too little diversity in ownership and programme content in the media. This leads to information deprived communities that lack participation in the democratic processes of the country.

Another consequence is that the small commercial media projects are faced with anti-competitive challenges.  As a result this affects the pursuit of the mandate of MDDA, in particular, access to a media of their choice; ownership and control by historically disadvantaged communities as well as the diversity of media, reflection and representation of the indigenous languages in the media landscape, informed participation of the poor and HDI’s in development processes and communication for all.

There is also the lack of research and information specific to the sectors that inform program development and strategic focus (e.g. not much information on the number of indigenous language newspapers in SA, number of readers of such newspapers, etc.

Inadequate skills and experience make community and small commercial ventures unviable and unsustainable.

Access to information and a choice of media for all, is a fundamental right of citizens, especially the poor. All South Africans should have equal access to a diverse choice of media (public, commercial and community). All citizens should have access to media in all languages, accordingly support of indigenous languages in print, TV and internet-based media should be consolidated.

8.2	Overall objective

The overall objective of the MDDA strategic focus for the period 2008-2011 as informed by the vision and mandate of the MDDA is,

“To ensure that all citizens can access information in a language of their choice and to transform media access, ownership and control patterns in South Africa”

8.3	Purpose

The purpose of the MDDA in the next three years is to continue to;

“To strengthen the sector though the provision and leveraging of resources, knowledge and skills in pursuit of promoting media development and diversity”

8.4	Key Result Areas in relation to the purpose statement

In pursuit of the purpose statement the MDDA will focus its efforts in the following result areas:

- Advocacy for media development and diversity ,

- Stakeholder management,

- Grant  funding for community and small commercial media, and seed funding support  for community radio in the nodal areas,

- Capacity building interventions for beneficiary organisations and communities including mentorship,

- Fundraising and resource mobilisation,

- Monitoring & evaluation, research and knowledge management – focus on impact assessment and evaluation,

- Media literacy and the promotion of the culture of reading.

The above priorities are determined by the Agency within the constraint of its resources both human and financial, taking into account the potential increase in its capacity. Therefore, greater attention will be given to some priorities will be given to some activities over and above others, in consultation with the Board.

The strategic approach of the Agency is to find synergies, involve MDDA supported projects in the respective provinces and to the extent possible dovetail with other activities.

In general our key focus areas are aligned to the following categories of the Apex Priorities:

- The further acceleration of economic growth and development;

- Speeding up the process of building the infrastructure needed to achieve economic and social goals;

- Improvement of the effectiveness of interventions directed at the Second Economy and poverty eradication;

- Enhancing the impact of programmes targeting the critical important area of education and training;

  - Pre-determined Strategic Objectives in relation to Key Result Areas

Financial Year 2008/9

# KEY RESULT AREA 1: ADVOCACY FOR MEDIA DEVELOPMENT AND DIVERSITY

| STRATEGIC OBJECTIVE: To contribute towards improving the operating environment of the community and small commercial media sectors |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Establish baseline data on advertising revenue for small commercial and community media sector | Enabling and operating environment | 1 | Baseline data available | Partnership with AIPSA. Grassroots Advertising Procurement feasibility study done with Association of Independent Publishers (AIP) | Baseline data established |  |  |  |
| Engage and mobilise support for the MDDA | Enabling and operating environment | 1 | Increased support for the work of MDDA |  | Increased support for the work of MDDA |  |  |  |
| Prepare submissions and position papers to ICASA for the review of regulations governing the Community Broadcasting sector. | Regulatory environment | 1 | 1 submission made to ICASA | 3 submissions made in 2007/8 | 1 submission made to ICASA |  |  |  |
|  |  | 2 | Regulatory changes accepted and effected by ICASA | Regulations prescribed in 2007/8 | Regulatory changes accepted and effected by ICASA |  |  |  |
| Prepare submissions to the Minister in the Presidency regarding MDDA Act possible amendments. | Legislative environment | 1 | Changes / amendments to MDDA Act | Draft amendments tabled to the Board and were subjected to the Analysis of ECA (Bulumko Report) | Changes / amendments to MDDA Act |  |  |  |
| Prepare submissions to the Parliament regarding MDDA Act possible amendments. | Legislative environment | 1 | Changes / amendments to MDDA Act | Draft amendments tabled to the Board and were subjected to the Analysis of ECA (Bulumko Report) | Changes / amendments to MDDA Act |  |  |  |
| Lobby advertising and marketing industry using the MAC Charter Council process | Enabling and operating environment | 1 | % or Rand increase in advertising revenue for small commercial and community media | Community Radio advert spent in 2005 – R19m of R2bn (Source Motswako Media) | 5 % increase in advertising revenue for small commercial and community media |  |  |  |
| Advertising training programme with AMASA | Enabling and operating environment | 1 | 10 people trained through AMASA | 2 partnerships between industry bodies (like AIPSA, AMASA) in place | 10 people trained through AMASA |  |  |  |
| Create a competitive environment for the small commercial and community media industry |  | 1 | 2 Provincial hubs in place providing multimedia, printing and distribution facilities for community and small commercial media | 1 Provincial hub in place providing printing and distribution facilities for community and small commercial media | 2 Provincial hubs in place providing multimedia, printing and distribution facilities for community and small commercial media |  |  |  |
|  |  | 2 | An agreement with SAPO to use their database network to distribute community and small commercial newspapers | Initial discussions held with SAPO | An agreement with SAPO to use their database network to distribute community and small commercial newspapers |  |  |  |
|  |  | 3 | % of discounted rates provided to community and small commercial newspapers for printing and distribution | N/E | 5 % discounts provided to community and small commercial newspapers for printing and distribution |  |  |  |
| Research on the viability of a low interest loan fund undertaken |  | 1 | Research report in place | Phase one research conducted. Service provider for Phase 2 appointed. | Research report in place |  |  |  |
|  |  | 2 | Strategy developed | NE | Strategy developed |  |  |  |
| Targeted and systemic engagement of unions and NGOs - CWU, Labour Media Forum (convened by Patrick Craven), SA Labour Bulletin, Agenda, Media watch NGOs, | Support for atypical media | 1 | 2 meetings held | A call for proposal on the feasibility study on the viability of a media co-operative issued in March 2008. 5 atypical media funded in 2006/7/8 ( Media Training Centre for Health, Zisize, Agenda Magazine, Gender Advocacy Programme, Umbele Wolwazi Education Trust) | 2 meetings held |  |  |  |
|  |  | 2 | Feasibility study report on the viability of a media co-operative produced and published | A call for proposal on the feasibility study on the viability of a media co-operative issued in March 2008. | Feasibility study report on the viability of a media co-operative produced and published |  |  |  |
|  |  | 3 | Feasibility study report on the viability of a media co-operative discussed by a focal group / seminar | Research seminars held in 2007/8 | Feasibility study report on the viability of a media co-operative discussed by a focal group / seminar |  |  |  |
| Engagement with DPLG | Local Government support for small commercial and community media | 1 | Partner with DPLG in convening the Multilingual Conference | A meeting and a roundtable held with DPLG | Partner with DPLG in convening the Multilingual Conference |  |  |  |
|  |  | 2 | Draft an MoU with DPLG | Meetings held with DPLG | Draft an MoU with DPLG |  |  |  |

KEY RESULT AREA 2:  STAKEHOLDER MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen relations with MDDA contractual and non-contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Develop partnerships with academic institutions and SABC | Stakeholder Management | 1 | 1 joint initiative in media development and diversity undertaken with stakeholders (Seminar on trends of media ownership and control) | 1 joint venture with Sol Plaatjies Media Leadership Institute Discussions and plans for an initiative on analysing the trends on media ownership and control held with GCIS, SABC and PMSA. | 1 joint initiative in media development and diversity undertaken with stakeholders (Seminar on trends of media ownership and control) |  |  |  |
| Develop and set up forums/summits with advertising companies to promote small commercial media | Increased advertising revenue for small commercial media | 1 | 1 engagement with advertising companies and media directors’ cycle. | Advertising and marketing summit held in 2007. Advertising toolkit is being developed. | 1 engagement with advertising companies and media directors’ cycle. |  |  |  |
| Sign MoU with USAASA | MoU with USAASA | 1 | Signed MoU | Joint USAASA/MDDA workshop held. Draft MoU developed in 2007. | Signed MoU |  |  |  |
| Signed MoU with MAPPSETA | MoU with MAPPSETA | 1 | Signed MoU | Discussions held with MAPPSETA. Draft MoU developed in 2007 | Signed MoU |  |  |  |
| Signed MoU with ISSETSETA | MoU with ISSETSETA | 1 | Signed MoU | Draft MoU with MAPPSETA developed in 2007 | Signed MoU |  |  |  |
| Signed MoU with DoC | MoU with DoC | 1 | Signed MoU | Commitment to working together accepted by both parties | Signed MoU |  |  |  |
| Maintain contacts database | Keep in touch with stakeholders | 1 | Updating the database | Database developed | Updating the database |  |  |  |

KEY RESULT AREA 3: GRANT AND SEED FUNDING

| STRATEGIC OBJECTIVE: To promote and strengthen the small commercial print and community media sector |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Prepare calls for applications Conduct project assessment including site visits. Prepare and submit project reports Select projects and submit for board approval Enter project grant agreements Disburse grants Prepare reports on grant funding activity | Grant funding | 1 | At least 1 community radio per 12 district municipality funded | 14 community radio funded in 13 districts in 2006/7. 12 community radios funded in 2007/8 | At least 1 community radio per 12 district municipality funded |  |  |  |
|  |  | 2 | At least 1 community newspaper per district municipality funded | 2 community newspapers funded in two districts | 2 community newspapers funded in two districts |  |  |  |
| Fund community television initiatives |  | 3 | At least 1 Community Television initiative funded | Community TV funding strategy developed in 2007/8 | At least 1 Community Television initiative funded |  |  |  |
| Fund two provincial hub initiatives |  | 4 | At least 1 hub per province (print & radio) funded | Eastern Cape provincial hub supported in 2006/7 and Western Cape in 2007/8 | At least 1 hub per province (print & radio) funded |  |  |  |
| Study on student Media funding | Support for student media | 5 | Viability study on student media in place | Service provider appointed in 2007/8. Study work in progress. | Viability report on student media in place |  |  |  |
| Appointment of service provider to conduct a feasibility study on the viability of media cooperatives |  | 6 | Research report on the viability of media cooperatives completed. | Call for proposals issued in 2007/8 | Research report on the viability of media cooperatives completed. |  |  |  |
|  |  | 7 | 4 atypical media funded | A call for proposal on the feasibility study on the viability of a media co-operative issued in March 2008. 5 atypical media funded in 2006/7/8 ( Media Training Centre for Health, Zisize, Agenda Magazine, Gender Advocacy Programme, Umbele Wolwazi Education Trust) | 4 atypical media projects funded |  |  |  |
|  |  | 8 | 2 new media projects funded | Women’s Net supported in 2006/7 Mahala Media funded in 2007/8 | 2 new media projects funded |  |  |  |
| Assessment of the content development initiatives | Content development | 9 | Content initiatives assessment concept paper completed | N/E | Content initiatives assessment concept paper completed |  |  |  |
|  |  | 10 | 5 small commercial newspapers and 1 magazine | 18 small commercial newspapers and 1 magazine funded in 2006/7 | 5 small commercial newspapers and 1 magazine |  |  |  |
| Status report on seed funding initiative | Seed funding | 1 | Status report in place | 4 nodal point stations provided with seed funding support in 2007/8 | Status report in place |  |  |  |
| Communication with un-served nodal point projects |  | 2 | 4 CRs in the nodal areas funded | 4 CR’s in nodal areas funded in 2007/8 | 4 CRs in the nodal areas funded |  |  |  |
| Enter into an agreement with the service providers |  | 3 | Service provider service level agreement in place | 6 service level agreements concluded with 6 service providers in 2007/8 besides mentors. | Service provider service level agreement in place |  |  |  |
| Monitor the service provider management process for seed funding |  | 5 | Service provider performance targets established | SLA schedule 1 provides a schedule of deliverables. | Service provider performance targets established |  |  |  |
| Monitor and evaluate projects | Monitoring and Evaluation | 1 | Monitoring and evaluation plan in place | Monitoring was limited to desktop. Plan exists; M & E Unit is being established with Programme Manager and Project Officer. Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation plan in place | . . |  |  |
|  |  | 2 | Monitoring and evaluation checklist | Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation checklist |  |  |  |
|  |  | 3 | 10 projects monitored | Programme Manager and Project Officer appointed in 2007/8 | 10 projects monitored |  |  |  |
|  |  | 4 | Monitoring reports in place | Programme Manager and Project Officer appointed in 2007/8 | Monitoring reports in place |  |  |  |
|  |  | 5 | Monitoring and evaluation unit established | Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation unit established |  |  |  |
|  |  | 6 | Monitoring and evaluation staff commences work. | Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation staff commences work. |  |  |  |
| Undertake evaluation of MDDA systems and processes | Improvement of systems and processes | 7 | Evaluation report in place | Service provider appointed in 2007/8 | Evaluation report in place |  |  |  |

KEY RESULT AREA 4: CAPACITY BUILDING INTERVENTIONS FOR BENEFICIARY ORGANISATIONS AND COMMUNITIES (INCLUDING MENTORSHIP)

| STRATEGIC OBJECTIVE: To enhance the sustainability of community and small commercial media |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Implement training plan | Capacity building | 1 | 25 community and small commercial media initiatives would be trained | 30 people trained in 2007/8 A number of Projects mentored in 2007/8 | 25 community and small commercial media initiatives would be trained |  |  |  |
| Implement Exchange programme |  | 2 | 10 exchange events are held | 1 exchange event in 2007/8 | 10 exchange events are held |  |  |  |
| Maintain and grow the mentor and training database |  | 3 | 10 appropriately skilled mentors / trainers on the database, 5 of whom are accredited | 46 mentors / trainers on database in 2007/8 | 10 appropriately skilled mentors / trainers on database, 5 of whom are accredited |  |  |  |
| Conduct training workshops for beneficiaries on identified capacity issue and needs |  | 4 | 2 workshops on financial management involving 60 beneficiaries conducted | 1 workshop on financial management involving 30 beneficiaries conducted | 2 workshops on financial management involving 60 beneficiaries conducted |  |  |  |
| Disseminate handbooks and toolkits on marketing |  | 5 | 100 marketing handbook and toolkits disseminated to MDDA projects | Service provider appointed and work is in progress. | 100 marketing handbook and toolkits disseminated to MDDA projects |  |  |  |
| Facilitate accreditation for MDDA trainers | Use of accredited service providers | 6 | 10 accredited Service providers recorded in MDDA database | 46 registered service providers in MDDA database | 10 accredited Service providers recorded in MDDA database |  |  |  |
| Monitor and evaluate capacity building intervention initiatives and prepare reports | Monitoring and evaluation | 1 | Monitoring and evaluation plan in place | M & E Unit is being established. Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation plan in place |  |  |  |
|  |  | 2 | 5 capacity building initiatives involving 5 beneficiaries evaluated | 5 bursaries in Essentials for Broadcast Management issued in 2007/8. 3 people trained in Radio Production learnership programmes. | 5 capacity building initiatives involving 5 beneficiaries evaluated | . |  |  |
|  |  | 3 | Monitoring and evaluation reports submitted | Programme Manager and Project Officer appointed in 2007/8 | Monitoring and evaluation reports submitted |  |  |  |
| Report on the movement of trained people within the sector produced and disseminated |  | 1 | Continue desktop research on the movement of trained people within the sector. | Initial desktop research on the movement of trained people within the sector undertaken. | Continue desktop research on the movement of trained people within the sector. |  |  |  |
|  |  | 2 | Research report on the movement of trained people within the sector in place | Initial desktop research on the movement of trained people within the sector undertaken. | Research report on the movement of trained people within the sector in place |  |  |  |
| Establish database of people trained through MDDA funding |  | 3 | Database of trained people | Initial desktop research on the movement of trained people within the sector undertaken. Initial desktop research on the movement of trained people within the sector undertaken. | Database of trained people |  |  |  |

KEY RESULT AREA 5: MONITORING $ EVALUATION, RESEARCH AND KNOWLEDGE MANAGEMENT

| STRATEGIC OBJECTIVE: To enhance innovation and learning in the sector |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Develop a research and knowledge management plan | Research | 1 | Research and knowledge management plan in place | Project Officer appointed | Research and knowledge management plan in place |  |  |  |
|  |  | 2 | 3 research projects undertaken | 3 research projects considered in 2007/8 | 3 research projects undertaken |  |  |  |
|  |  | 3 | 3 research reports published | 3 research reports published | 3 research reports published |  |  |  |
|  |  | 4 | 3 research seminars involving 20 beneficiaries conducted | 2 research seminars held | 3 research seminars involving 20 beneficiaries conducted |  |  |  |
| Monitor and evaluate projects | Monitoring and evaluation | 1 | Monitoring and evaluation plan in place | Monitoring was limited to desktop. Currently ongoing monitoring and evaluation conducted by Program Managers. M & E Unit has been established with a dedicated Programme Manager and Project Officer. | Monitoring and evaluation plan in place |  |  |  |
|  |  | 2 | Monitoring and evaluation checklist | M & E staff employed | Monitoring and evaluation checklist |  |  |  |
|  |  | 3 | 50 projects monitored and evaluated | Monitoring was limited to desktop. Currently ongoing monitoring and evaluation conducted by Program Managers. M & E staff employed | 50 projects monitored and evaluated |  |  |  |
|  |  | 4 | Monitoring and evaluation reports in place | Programme Manager and Project Officer appointed. | Monitoring and evaluation reports in place |  |  |  |
| Impact assessment and evaluation research – focusing on the projects, socio-economical impact of MDDA interventions | Social impact evaluation and assessment | 1 | Research report | Short-term evaluation of MDDA conducted in 2007/8 Stakeholder perception survey conducted in 2007/8 | Research report on the impact of MDDA funding support |  |  |  |
| Publish a quarterly Journal and monograph series of the state of Media Development and Diversity in S.A. | State of media development and diversity | 1 | Journal conceptualised and designed | N/A | Journal conceptualised and designed |  |  |  |
|  |  | 2 | Partnerships with existing journals explored. | N/A | Partnerships with existing journals explored. |  |  |  |
|  |  | 3 | Journal outlined and business strategy developed | N/A | Journal outlined and business strategy developed |  |  |  |
|  |  | 4 | Journal published annually from 2009/10 | N/A | Journal published annually from 2009/10 |  |  |  |
| Maintain MDDA resource centre | Resource Centre | 1 | Updated Resource Centre records in place | MDDA Resource centre in place | Updated Resource Centre records in place |  |  |  |
|  |  | 2 | 16 staff, 9 board members and beneficiaries from time to time use Resource Centre | N/E | 16 staff, 9 board members and beneficiaries from time to time use Resource Centre |  |  |  |
|  |  | 3 | 172 project records stored | Project information currently stored under project tracking system | 172 project records stored |  |  |  |
| Maintain real time filing, archiving and information management system and | Information Management System | 1 | Updated Information management records in place | Information management system designed | Updated Information management records in place |  |  |  |
|  |  | 2 | Information Management System Piloted with 1 MDDA unit | N/E | Information Management System Piloted with 1 MDDA unit |  |  |  |
|  |  | 3 | All MDDA staff trained on the IMS | One training session for staff held in 2007/8 | All MDDA staff trained on the IMS |  |  |  |
|  |  | 4 | IMS successfully implemented across MDDA | System designed and implementation in progress. | IMS successfully implemented across MDDA |  |  |  |
| Monitor and track legislative and policy issues affecting the media. | Policy and legislative issues | 1 | Policy and Legislation monitoring strategy in place | An analysis of Electronic Communications Act of 2005 conducted. ICASA regulation making process monitored and submissions made. | Policy and legislation monitoring strategy in place |  |  |  |
|  |  | 2 | 2 policies and legislation reviewed | An analysis of Electronic Communications Act of 2005 conducted. ICASA regulation making process monitored and submissions made. | 2 policies reviewed |  |  |  |
| Conduct workshops on policy changes with beneficiaries |  | 3 | 1 policy workshop with beneficiaries held on the ECA and related policy | Community Television seminar held in April 2007 | 1 policy workshop with beneficiaries held on the ECA and related policy |  |  |  |
| Provide, manage and commission research and research grants and applications through the GFC | Research grants | 1 | 1 Research grants approved | 2 research grant issued in 2007/8 (MMP and Mahala Media | 1 Research grants approved |  |  |  |

KEY RESULT AREA 6: MEDIA LITERACY AND CULTURE OF LEARNING

| STRATEGIC OBJECTIVE: To promote media literacy and the culture of learning |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Partnership with the Dept of Education (DoE), Dept of Provincial and Local Gvt (DPLG), PMSA, READ and other relevant stakeholders in place | Media literacy and culture of learning | 1 | 2 Partnerships in place | Partnerships with DPLG discussed and MDDA joined the process of convening the multilingualism conference. | 2 Partnerships in place |  |  |  |
|  |  | 2 | 2 consultations with DoE, DPLG, GCIS, SABC, PMSA, READ and targeted district municipality | Concept paper developed and discussed with GCIS. Partnerships with DPLG discussed and MDDA joined the process of convening the multilingualism conference. Discussions held with PMSA, which is in support of the activity. | 2 consultations with DoE, DPLG, GCIS, SABC, PMSA, READ and targeted district municipality |  |  |  |
|  |  | 3 | Consulted parties MOU / agreements for partnering in media Literacy and culture of learning initiatives | Concept paper developed and discussed with GCIS. | Consulted parties MOU / agreements for partnering in media Literacy and culture of learning initiatives |  |  |  |
| Convene media learner assemblies/summits on the role of media per district municipality | Media literacy and culture of learning | 1 | 1 summit in Alfred Nzo district municipality convened | Concept paper developed and discussed with GCIS. | 1 summit in Alfred Nzo district municipality convened |  |  |  |
|  |  | 2 | Share results / report with DoE with the aim of feeding results into high impact results at the DoE. | N/E | Share results / report with DoE with the aim of feeding results into high impact results at the DoE. |  |  |  |

KEY RESULT AREA 7:  COMMUNICATIONS AND PUBLIC AWARENESS WITH REGARD TO THE SECTOR AND THE MDDA IN GENERAL

| STRATEGIC OBJECTIVE: To enhance and position the MDDA as a leader in media development and diversity. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| Finalise the MDDA perception survey | A perception survey | 1 | 1 survey conducted | Service provider appointed in 2007. Draft report produced in March 2007 | 1 survey conducted |  |  |  |
| Develop an MDDA branding and communication strategy and plan | MDDA branding strategy and plan | 1 | Strategy and Plan developed | Service provider appointed in 2007 | Strategy and Plan developed |  |  |  |
| Conducting seminars throughout different provinces and other similar initiatives, aimed at engaging the public regarding the state of media development and diversity in the country. | Recognition by stakeholders of the role of MDDA in media development and diversity | 1 | 1 seminar conducted | MDDA made presentations at similar opportunities in Limpopo convened by Youth Commission, GCIS, etc. Articles covering the topic written in a number of publications, City Press, Bizcommunity, IT Web, etc. A number of radio and television interviews held, with SABC 2, 3, CNBC Africa, SAFM, Alfred Nzo CR, etc. Seminar on the trends of ownership and control of media planned in 2007 | 1 seminar conducted |  |  |  |
| To promote MDDA and its products to potential and actual customers | Public awareness | 1 | Communication Strategy and implementation | Service provider appointed | Communication strategy and implementation |  |  |  |

KEY RESULT AREA 8:  FUNDRAISING AND RESOURCE MOBILISATION

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base; accordingly increase the funding and resource base of the MDDA and its beneficiaries |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| To increase the level of transfers from MDDA funders. | GCIS and partners transfer | 1 | An increase of R2 m for 2008/9, R3m for 2009/10, and R4m from Government; e-TV increase of its contribution to R1.2m and increases committed in terms of the ECA / ICASA Regulation. | 100% transfer – R22million in 2007/8 | An increase of R2 m for 2008/9, R3m for 2009/10, and R4m from Government; e-TV increase of its contribution to R1.2m and increases committed in terms of the ECA / ICASA Regulation. |  |  |  |
| To increase and maintain funding revenue streams for the MDDA. | Revenue / income generation | 1 | An increase of R2 m for 2008/9, R3m for 2009/10, and R4m from Government; e-TV increase of its contribution to R1.2m and increases committed in terms of the ECA / ICASA Regulation, 0.2 % of Broadcast Service Licensee’s annual turnover. Revision of current funding agreements and alignment with the ICASA Regulation. Revision of current funding agreements with print media guided by the increase in contributions by Broadcast media. Mou with USAASA and DoC. | Fund Development Strategy developed. Discussions held with Broadcast Service Licensees and PMSA. Discussions held with DoC, USAASA and ICASA. | An increase of R2 m for 2008/9, R3m for 2009/10, and R4m from Government; e-TV increase of its contribution to R1.2m and increases committed in terms of the ECA / ICASA Regulation, 0.2 % of Broadcast Service Licensee’s annual turnover. Revision of current funding agreements and alignment with the ICASA Regulation. Revision of current funding agreements with print media guided by the increase in contributions by Broadcast media. Mou with USAASA and DoC. |  |  |  |
| To grow the capital base of the MDDA. | Capital growth | 1 | R24 m according to contracts and in time. Positive real return on capital. (subject to change post ECA exercise) | R22m in 2007/8 | R24m according to contracts and in time. Positive real return on capital. (subject to change post ECA exercise) |  |  |  |
| To increase the number of MAPPSETA contracts with the MDDA for training services. | Increased training fund and thereby increase skills in the sector | 1 | 1 contract signed | MDDA supported the partnership with NCRF, IAJ and MAPPSETA | 1 contract signed |  |  |  |
| Implement the MDDA Fund Development Strategy and Plan | Increased funding levels of MDDA programs | 1 | Present MDDA position to the ICASA public hearings on the ECA Section 89 Reg. | Fund Development Strategy and Plan developed. Roundtable with Broadcasting Service Licensees held. Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA | Present MDDA position to the ICASA public hearings on the ECA Section 89 Reg. |  |  |  |
|  |  | 2 | Regulation on contributions prescribed by ICASA | Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA | Regulation on contributions prescribed by ICASA |  |  |  |
| Partnership with Highway Africa 2008 | Convene a session on media sustainability | 1 | 1 day session convened as part of Highway Africa 2008 | Presentations made at Highway Africa 2007. | 1 day session convened as part of Highway Africa 2008 |  |  |  |
|  | Increase international fundraising for MDDA | 1 | At least 3 engagements with donors | MDDA Chairs the Media Funders Forum of Southern Africa. MDDA held discussions with World Bank. MDDA held discussions with the Flemish Government regarding Community Television. | At least 3 engagements with donors |  |  |  |

KEY RESULT AREA 9:  FINANCIAL MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| To maintain the regulated ratio of grant expenditure to capital | Compliance with Regulations | 1 | 25% on admin and 75 % on programs. 60% community media, small commercial media 25%, research 5%, unallocated 10% | 25% on admin and 75 % on programs limits held in 2007 | 25% on admin and 75 % on programs. 60% community media, small commercial media 25%, research 5%, unallocated 10% |  |  |  |
| To maintain adequate financial records of the MDDA. | Prudent financial management. | 1 | Approved MTEF 2008 – 2011 and budgets by the Board. 0% actual vs budget variance. | Board approved the MTEF 2007-2010 Low variance in 2007. | Approved MTEF 2008 – 2011 and budgets by the Board. 0% actual vs budget variance. |  |  |  |
| To ensure a clean audit by the Auditor General. | Unqualified audit reports | 1 | Unqualified audit report | Reports up to 2006/7 remained unqualified | Unqualified audit report |  |  |  |
| Strengthen financial management capacity | Prudent financial management. | 1 | Train finance staff on an ongoing basis. | Staff trained in 2007/8 | Train finance staff on an ongoing basis. |  |  |  |
|  |  | 2 | Fill in all vacancies | All vacancies filled | Fill in all vacancies |  |  |  |
|  |  | 3 | Attend to all Treasury requirements and submissions | Treasury submissions made | Attend to all Treasury requirements and submissions |  |  |  |
|  | Internal Auditing | 4 | Strengthen Internal Audit and Risk Management Unit | Board approved the new position of Internal Audit and Risk Manager | Strengthen Internal Audit and Risk Management Unit |  |  |  |

KEY RESULT AREA 10:  INTERNAL BUSINESS PROCESSES

| STRATEGIC OBJECTIVE: To strengthen the operational efficiencies of the MDDA so as to deliver sustainable media development and diversity content and impact |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| To equip MDDA with appropriate technologies | Information management systems in place | 1 | Information Management Plan | Information management plan designed No audit findings | Information Management Plan |  |  |  |
| To improve efficiencies and accountability in the delivery of MDDA Programs | Contract management | 1 | 100% funding based on contracts 100% service provided based on Service Level Agreements | Contract management systems in place | 100% funding based on contracts 100% service provided based on Service Level Agreements |  |  |  |
| To limit operational and consequential risk to the MDDA | Risk Management | 1 | Risk Management Strategy and Plan in place | Risk Management Strategy and Plan exist | Risk Management Strategy and Plan in place |  |  |  |
| To limit fraud in the MDDA | Fraud Prevention | 1 | Fraud Prevention Plan | Fraud Prevention Plan exist | Fraud Prevention Plan |  |  |  |
| To facilitate efficient decision making and communication as well promote participative democracy in the MDDA | Organisational structure and systems |  | Approved and clear organizational structure established 90% of established and funded posts filled Monitoring and evaluation staff appointed | Approved Organogram | Approved and clear organizational structure established 90% of established and funded posts filled Monitoring and evaluation staff appointed |  |  |  |
| To improve corporate governance | Corporate Governance | 1 | 100% compliance Completed Corporate Governance checklist completed | Compliance kept | 100% compliance Completed Corporate Governance checklist completed |  |  |  |

KEY RESULT AREA 11:  CUSTOMER PERSPECTIVE

| STRATEGIC OBJECTIVE: To maintain the image of the MDDA as the performing public institution with government at national, provincial and local spheres and its contractual and non contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2008/9 | ACTUAL | VARIANCE |  |
| To develop and maintain high MDDA client satisfaction levels. | Service quality | 1 | Perception survey | Service provider appointed in 2007 | Perception survey |  |  |  |
| To support and promote positive working relations within all staff units of the MDDA | Human resources management | 1 | Organisational climate survey | Survey conducted | Organisational climate survey |  |  |  |
|  |  | 2 | Human resources management plan | Board approved the appointment of an HR and Corporate Services Manager | Human resources management plan |  |  |  |
|  |  | 3 | Workplace skill audit | Board approved the appointment of an HR and Corporate Services Manager | Workplace skill audit |  |  |  |
|  |  | 4 | Staff Development Program | Board approved the appointment of an HR and Corporate Services Manager | Staff Development Program |  |  |  |
|  |  | 5 | Human Resources Unit established and staff employed | Organogram approved, including the appointment of an HR and Corporate Services Manager | Human Resources Unit established and staff employed |  |  |  |
|  | To comply with the legislative requirements governing Employers in South Africa | 6 | Employment Equity plan and 100% compliance | Compliance held | Employment Equity plan and 100% compliance |  |  |  |
|  | To maintain adequate staffing levels for the performance of the MDDA functions. | 7 | 100% Funded positions filled | Organogram fully populated | 100% Funded positions filled |  |  |  |
|  | To improve performance levels and objectively measure the performance of staff in the MDDA | 8 | Performance appraisal conducted | Performance appraisal conducted | Performance appraisal conducted |  |  |  |

9.  	Risks and risk containment measures

The implementation of the 2008-2011 strategic focus and plan can be impacted upon by the following risks at various levels.

9.1 	Policy level

At the policy level, legislation and the regulations governing the MDDA may prove to be inflexible and stifle program implementation e.g. the percentage allocations to administration and program funding in the regulations. Non-compliance with legislation governing the Agency may lead to Treasury limiting or cutting funding to the Agency.

In order to mitigate against this risk, management with the assistance of the Board will maintain strict compliance with the legislative framework through regular internal and external audits as well as board member self assessments. The Board and senior management will conduct regular meetings and sessions to brief the Minister and the Portfolio Committee to ensure continued support for the program. Management will also design effective fund development strategies and seek alternative local and international donor funding.

The MDDA has done an analysis of the MDDA Act, the ECA and various policy positions that impact on its operations. The Agency is working closely with ICASA, USAASA and the DoC in order to realise the opportunities provided by the ECA. At the regulatory level the MDDA will submit requests for certain changes in the legislative framework that could contribute to the smooth functioning of the MDDA and the achievement of its objectives.

9.2	Operational level

A risk exists that the Agency may not have sufficient and skilled human resources and progressive polices and systems that are sufficiently motivating to encourage effective performance and retain staff.

In response to this risk, management is committed to undertake regular organisational climate surveys and to commit to a regular staff development program and the review of polices and systems to facilitates and improve performance in the organisation.  In this regard the board has approved the revision of all organisational policies such as the HR Policies, the Remuneration Policy, Facilities Management and IT policies and others.

9.3 	Beneficiary level

At the beneficiary level a risk exists for the misuse of allocated funding and the collapse of confidence in the MDDA by stakeholders as a result.

In this regard the MDDA will apply diligent project assessment and continuous monitoring and auditing of the projects and take appropriate disciplinary and corrective actions where necessary through amongst other things, insistence to contractual agreements.

Lastly, the Agency is in receipt of applications worth more than R150m but has a budget of just between R22 m to R24 m. This leads to the Agency postponing consideration of some projects until it has the financial resources to support such a project. The postponement have the unintended consequence of either the project disintegrating or people loosing confidence in the Agency’s ability to assist them in pursuit of its mandate. The risk thereof is that of in ability to meet the mandate, damaging the reputation of the Agency and demoralising communities.

To mitigate this risk the Agency has decided to focus its energies in mobilising more financial resources, through the opportunities arising from the ECA, increasing the contributions of Government, international donor funding, renewing and aligning the funding agreement with the newly expected ICASA Regulation, etc.

# A detailed set of prioritised risks and containment measures established by the MDDA is shown in the matrix overleaf.

# 9.4	RISK IDENTIFIED REGISTER AND ANALYSIS REPORT

# Preamble

# The table highlights the top ten risks identified and actions to mitigate the risks. The scores (1- 5 indicate the likelihood and consequences) lead to ratings range from very high, medium and low. A high rating detects a high risk area that requires a lot of attention and high priority.

| Item | Risk | Cause | Score Likelihood | Score Consequence | Combined Score | Overall Rating |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Under spending on grants | Capacity and changes of people at beneficiary levels. | 1 | 1 | 1 | Low |
| 2. | Lack of adequate funds | Increased demand for MDDA support and no increase in funding contributions | 4 | 5 | 20 | High |
| 3. | Exceeding regulatory requirement on admin. expenses | Funding to the Agency from the Broadcast and Print Media does not keep up with inflation. Its only Government funding that increases with inflation. Funding from Print and Broadcast sector is fixed for 5 years | 2 | 5 | 10 | Medium |
| 4. | PFMA; Archive Act; Access to Information Act; PSA; Promotion of Administrative Justice Act | Non compliance No proper records management. | 2 | 4 | 8 | Low |
| 5. | Network security could be compromised. | Viruses; Power failures; Access control not adequate; Disasters (fire, floods, etc) | 2 | 4 | 8 | Low |
| 6. | Reputation of MDDA | Failure to complete and implement the communication strategy on MDDA work | 2 | 4 | 8 | Low |
| 7. | Inappropriate use of MDDA resources. | Inappropriate use of resources, e.g. amount of time that could be spent on the telephone and the costs, etc. | 3 | 4 | 8 | Low |
| 8. | Operational plan | Not enough capacity within MDDA to implement its mandate due to the growth of the sector and lack of consequential human resource capacity increase. | 4 | 4 | 16 | High |
| 9. | Beneficiaries and service providers (mentors, etc.) may not comply with contractual agreements. | Performance of beneficiaries and service providers not regularly reviewed and documented. Lack of monitoring and evaluation capacity. | 2 | 5 | 10 | Medium |
| 10. | Low productivity | Low staff morale | 2 | 5 | 10 | Medium |
| 11. | Non-adherence to code of conduct | Board members and officials not declaring their interests in projects | 2 | 5 | 10 | Medium |

9.5	ACTION PLAN TO MITIGATE THE RISKS

| Item | Risk | What policy or Control exists to Mitigate this risk? | Action plan | Priority | Responsibility | Deadline |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Under spending on grants | Regulations and a mentoring policy are in place. However the capacity of the sector to absorb funds is a threat. | Continue implementing and evaluating a mentoring policy. Regular (biweekly) management meetings dealing with projects. Follow up / site visits with projects by Project Managers. Strengthening of Monitoring and Evaluation capacity at MDDA. Quarterly review of budget versus grants allocated. Evaluate and take corrective steps. | High | Projects Director Internal Audit and Risk manager | Ongoing |
| 2. | Lack of adequate funds | The Act empowers the Agency to fundraise from a range of sources. | Mobilisation of resources for the Agency given priority. More time given to the ECA analysis and related work towards the publication of the to be prescribed Regulation by ICASA requiring 0.2% contributions from broadcasters. Lobbying and advocacy to ensure that the contributions from broadcasters are made to the MDDA. Focus work on fundraising internationally. Develop partnerships with strategic partners in the industry, i.e. DFI’s, MAPPSETA, ISSETSEAT, DoC, USAASA, etc. | High | CEO | Ongoing |
| 3. | Exceeding regulatory requirement on administration expenses. | Fiscal discipline & review of budget versus actual on a monthly basis. | Increase funding base from government. Regular communication with existing funders to maintain funding. Introduce a provision to accommodate inflation as the funding agreements are renewed. | High | CEO CFO PD Internal Audit and Risk Manager | Ongoing |
| 4. | PFMA; Archive Act; Access to Information Act; PSA; Promotion of Administrative Justice Act | The policies have been developed and checklist developed. | Due Diligence study was conducted in 2006/7 which assisted in identifying gaps and strategies to close those gaps. Keep abreast with the new developments that are likely to arise from National Treasury & DPSA on how public entities should operate. Regular completion of legislative compliance template. Continuous training and development of personnel. | High | CEO CFO Legal and Contract Management | On going |
| 5. | Network security could be compromised. | An IT network policy is being developed. Rules have been established, in the meantime. | IT is outsourced & regularly reviewed with internal auditors. Regular reminder to staff about the importance of confidentiality of passwords. Ensure uninterrupted power supply is procured & installed. Monitor ESKOMs “load shedding” plans and plan around that program. Ensure training is provided on use of fire extinguishers. Procure a first aid kit. Review the evacuation procedures and training is provided. | High | CFO HR and Corporate Services Manager | On going |
| 6. | Reputation of MDDA | A communication strategy is being developed & implemented. Mentors policy in place. Evaluation of MDDA practices and processes is being undertaken. | Ongoing implementation of communication strategy. Re-branding and raising of the MDDA profile. Development of public awareness programme. | High | CEO | Ongoing |
| 7. | Inappropriate use of MDDA resources. | Telephone management system in place. Policies are in place. Performance Management System is in place. | Review job profiles, job descriptions and the Performance Management System. Monitoring the costs relating to the unreasonable use of MDDA resources. Evaluate and take corrective steps. Performance Appraisals to be done twice a year. Regular awareness to staff about the importance of appropriate use of resources. Development of work plans and set targets for staff against predetermined objectives in the Strategic Plan, monitored by respective Managers. | Medium | CFO PD HR and Corporate Services Manager All Staff | Ongoing |
| 8. | Operational plan | Every staff member has an action plan on how to address the issues in the operational plan. Board approved a new Organogram accommodating ideal structure and the funded positions. | To monitor implementation through performance management system 2 times a year. Evaluate and take corrective steps. Fill all vacancies as soon as the funding is available. | High | CEO CFO PD HR and Corporate Services Manager All staff | 3 times a year |
| 9. | Beneficiaries and service providers may not comply with contractual agreements | Service level agreements in place. New Organogram provides for a position of Legal and Contract Management. In addition, the New Organogram also accommodates a position of Internal Audit and Risk Manager. | Ensure regular evaluation of beneficiaries and service provider’s compliance with SLA’s. Evaluate and take corrective steps. Ensure mentoring procedures for beneficiaries are developed and implemented. Beef up staffing (legal, monitoring and evaluation) at MDDA. | Medium | CEO CFO Legal and Contract Management Responsible Manager | Ongoing |
| 10. | Low productivity | A performance management system is place. New Organogram accommodates a position of HR and Corporate Services Manager. | Regular awareness to staff about MDDA value system. Organise team building exercises. Monitor through performance management system. Performance review is performed at 2 times a year. Evaluate and take corrective steps. Organise an Organizational Climate Survey. Improve internal communication. Review of remuneration and grading system. | High | CEO CFO PD HR and Corporate Services Manager | Ongoing |
| 11. | Non-adherence to code of conduct | Code of Conduct exist. An annual register for declaration of interests by the Board and staff. | Ensure all Board members regularly declare their interests at every Board meeting. Ensure regular awareness to staff about the importance of declaring their interests in projects they are involved in and implications of non-compliance. | High | CEO CFO Internal Audit and Risk Manager | Ongoing End of year Board update their declarations |

10. 	Service delivery improvement program

The MDDA service delivery program is under girded by its value statements and its commitment to the Batho Pele Principles. These values amongst others include the MDDA commitment to integrity, professionalism and transparency.

  - Grant funding cycle

At the operational level, the service delivery process will be through the MDDA grant funding cycle illustrated in fig 1 below:

Fig1: Grant Funding Cycle

Fig2: Grant Funding Cycle Expanded

(a) 	Pre-assessment phase

The pre-assessment phase of the cycle consists of the definition of criteria for the assessment of project which defines what projects would qualify for assistance from the MDDA as well as calling fro proposals. This stage is managed primarily by the Project Director and the Research & Development Program Manager.

(b)	Pre-selection phase

Key activities for this phase include; the registration of new applications received, completing the project checklist, following up outstanding, information, completion of the application, recording the projects on the Project Tracking System (PTS), sending of acknowledgement letters and passing projects onto the Project Director and the Project Director sending same to the Project Managers. The main person who is involved at this stage is the Project Administrator.

The Project Managers would upon receipt of the applications, read the applications, evaluate them against MDDA criteria and regulations, complete the Initial screening form and prepare presentation to the Pre-Selection Panel.

The panel then consisting of the Project Managers and the Project Director convenes and undertakes the initial screening of the applications to determine their likely chances of success. Applications are then classified into the following categories: Strong applications that are likely to be approved by the Board, Weak applications that need more information, those to be rejected out right because they do not fall within the mandate of the MDDA and those that need mentoring and a feasibility assessment.

- Assessment and selection phase

In this phase, a questionnaire is refined for a site visit to the projects and a site visit is undertaken.  The critical elements that are assessed in the site visit are issues of:

  - Governance

  - Financial Management and systems

  - Policies and procedures

  - Community Participation (community media)

  - Research experience and methodology (research)

  - Sustainability

The projects are then given time (approximately 1 Week) to address any gaps that are identified.

(d)	Selection phase

In the selection phase, the Program Manager completes a Project Justification report,	completes memos for submission, and participates in a Mock Board meeting, revises the submission and submits same to the board.

(d) 	Contracting

Should the project be rejected a letter of rejection is sent. Should the project be approved, an acceptance letter is sent to the project.  If it is an approval in principle, the project is informed of the Board’s decision and the conditions precedent and the relevant follow-up reports are submitted as and when they are required.

If the Board has approved grant funding the project, the Program Manager develops a contract together with a Schedule of Particulars which outlines the terms of the payment from the MDDA together with the expected outputs and outcomes of the project and the reporting requirements.

If a mentor has been appointed in this phase, the Program Manager, together with the project identifies a Mentor and sends a brief to the mentor, drafts a work-plan and budget for the mentor, contracts with the mentor, designs a mentoring contract for the project. Generally, the project needs are identified and three mentors are identified, reference checked and sent to projects and the projects then choose their Mentor.

Contact is then maintained with the mentor. The Projects Officer then sends a happy/sad letter, a report is sought from the mentor, it is evaluated, finalized and recommendations made to the Project Director, CEO and the Board and the Mentor is paid.  		;

(e)	Implementation and monitoring phase

In this phase the following activities are:

- Maintenance of  contact with mentors;

- Ensuring the  receipt of “happy/sad” letter from projects;

- Seeking  report from mentor

- Evaluation of the mentoring report

- Finalization of the monitoring report

- The Generation of payment for mentors;	 and

- Presenting  recommendations to Project Director, CEO, Finance and Operations Committee & Board;

Should the project be rejected a letter of rejection is sent. Should the project be approved, an acceptance letter is sent to the project.  If it is an approval in principle, the project is informed of the Board’s decision and the conditions precedent and the relevant follow-up reports are submitted as and when they are required.

(f)	Monitoring

In this phase, project reviews are done and project reports submitted. These will identify areas that need attention. Monitoring visits are conducted and reports are prepared and submitted to the board.

(g)	Project Closure

In this phase the key activities that are involved are: reminding the projects of the need for final reports, receiving and assessing the project financial and narrative reports, forwarding memos to Finance, disbursing of final tranches, closing the project and submitting the final reports to the board.

(h) 	Impact assessment phase

The impact assessment phase includes; the drafting of an evaluation brief; finalizing the evaluation methodology to be used, identifying of a relevant consultant to contract, monitoring compliance with the contract, receiving of a desk top study, assessing the evaluation report, paying the consultant, completing the evaluation sheet, sharing the report with MDDA leadership and incorporating the findings into MDDA strategic planning process.

10.2	Project Tracking System

The MDDA has invested in a progressive Information and Communications Technology systems called the Project Tracking System generally used in the grant funding environment and is customised for the purposes of the MDDA. This system allows for the storage and updating of information on the status of each project on a regular basis. This improves project management and feedback to MDDA beneficiaries.

11. 	Information Technology Plan

The MDDA has in place a number of IT systems that improve the control environment of the organisation in various areas. At the accounting and financial controls level, the MDDA uses Pastel Accounting software which is supported by Com-com Solutions on a monthly basis and as when the need arises.

At the program level, the Project Tracking System (PTS) is a web based application and is supported by Kids Africa.  The PTS will allow the Agency access to information on all funded projects thereby promoting effective and efficient grant making systems and structure.

In the facilities management environment the matrix overleaf sets out MDDAs approach to facilities management and general IT controls.

11.1	GENERAL IT CONTROLS AND FACILITIES MANAGEMENT PLAN

| AREA | ACTIVITIES | ACTION DATE |
| --- | --- | --- |
| Policies and procedures | Board approval of formal IT policies, standards and procedures. These will encompass physical access, logical access, back up and recovery process. | 2008/9 |
| Raising floor in the computer room | Investigation on floor raising to establish appropriateness for the MDDA will be conducted given the equipment mounted on the wall and the size of the organisation | Ongoing |
| Water detectors in the computer room | Investigation on installation of water detectors to establish appropriateness for the MDDA will be conducted given the size of the organisation | Ongoing |
| A fire suppression system | Investigation on installation of a fire suppression system to establish appropriateness for the MDDA will be conducted given the size of the organisation Fire extinguishers are in place | Ongoing |
| Emergency power-off switches inside or outside the computer facility. | The USP is already in the server Investigation on the possible procurement of a generator will be undertaken. | Ongoing |
| Backup and restore systems | A test restore procedure will be implemented and logs printed and stored every 2nd week. | Ongoing |

12.	Institutional capacity required to implement MDDA program initiatives in the period 2008-2011

Operationally, it is very clear that the staff composition as it stands cannot sustain the workload that is envisaged in the ensuing period. This has been independently confirmed through both the Bulumko Report (which propose a 32 staff complement) and ICMS Report (which propose a 24 staff complement) Reports.

It is recommended that the increase in staff capacity be progressive in order to be sustainable and achieve the strategic objectives of the Agency in line with the proposed Human Resources Plan in the matrix overleaf. This is critical to avoid staff fatigue and to ensure that Management focus.

Further, the Delegation of Authority needs to be properly streamlined, in order to ensure that there is proper role definition between the Board and Management to avoid unnecessary conflict.

The following principles were important in determining the proposed structure of the MDDA:

- The maintenance of a limited span of control where a Manager should not be overly spread to manage a wide portfolio which could lead to a compromise in work outputs and standards.

- Role clarity and the avoidance of role confusion where for instance the CFO having to manage the HR functions of the organisation.

- Delegation of authority to the appropriate levels in order to facilitate decision making and to be responsive.

- Consideration for growth in the work and portfolio of grants to be managed by the MDDA. There is a greater demand for project review and monitoring. Failure to manage this might lead to a higher rate of default and poor contract management by Program Managers.

- Separation of functions especially in Finance where procurement, accounting and disbursements for instances were done by one person. This could easily lead to open the organisation up to fraud.

- Consideration for the law (PFMA) which prescribes certain positions and/or portfolios that must be in place e.g. CFO, and Internal Audit.

- Consideration of good corporate governance, which require such position as Board Secretary or Company Secretary.

- Availability of funds.

13.	MDDA Human Resource Plan for implementation of its strategic focus 2008-2011

| Established posts | Positions filled |
| --- | --- |
| Position | Number of positions | Year 1: 2008/2009 | Year 2:2009/2010 | Year3 :2010/2011 |
| Chief Executive Officer | 1 | 1 | 1 | 1 |
| Chief Financial Officer | 1 | 1 | 1 | 1 |
| HR & Corporate Service Director | 1 | 1 | 1 | 1 |
| Program Director | 1 | 1 | 1 | 1 |
| Internal Auditor and Risk Manager | 1 | 1 | 1 | 1 |
| Program Manager | 4 | 4 | 4 | 4 |
| Finance Manager | 1 | 0 | 1 | 1 |
| Project Officer | 4 | 4 | 4 | 4 |
| Financial Administration | 1 | 1 | 1 | 1 |
| Finance and Disbursement Officer | 1 | 1 | 1 | 1 |
| Contract Management and Legal | 1 | 1 | 1 | 1 |
| Company Secretary | 1 | 0 | 1 | 1 |
| Receptionist | 1 | 1 | 1 | 1 |
| Office Assistant and Cleaner | 1 | 1 | 1 | 1 |
| Executive Secretary (CEO’s office) | 1 | 1 | 1 | 1 |
| Manager in the office of the CEO | 1 | 1 | 1 | 1 |
| Admin Assistant | 3 | 1 | 1 | 3 |
| Total staff complement | 25 | 21 | 23 | 25 |

Structure

14. 	Financial Implications and budget for the period 2008-2011

The budgets for the period are appendix 1 of this document.

15.	Reporting

In accordance with treasury regulation (Notice number 29644 of 20 February 2007) below is the detail of specific plans for reporting to some of the various institutional frameworks that govern the MDDA:

| INSTITUTION | REPORT AREA | FREQUENCY |
| --- | --- | --- |
| MDDA Board | General Strategic and business plan Annual report | Quarterly meetings February/March annually May/June Annually |
| Executive Authority | Statutory functions Strategic and business plan Annual report | Quarterly |
| GCIS | Administratively MTEF | Quarterly July/August Annually |
| Auditor General | Auditing | Annually |
| Parliament | Strategic and business plan Annual Report | March annually July/August Annually |
| Funders (Broadcast and Print Media) | General Projects | Quarterly |

16.  Financial Year 2009/10

# KEY RESULT AREA 1: ADVOCACY

| STRATEGIC OBJECTIVE: To contribute towards improving the operating environment of the community and small commercial media sectors |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Establish baseline data on advertising revenue for small commercial and community media sector | Enabling and operating environment | 1 | Baseline data available | NE |  |  |  |  |
| Lobby advertising and marketing industry using the MAC Charter Council process | Enabling and operating environment | 1 | % or Rand increase in advertising revenue for small commercial and community media | Community Radio advert spent in 2005 – R19m of R2bn (Source Motswako Media) |  |  |  |  |
| Advertising training programme with AMASA | Enabling and operating environment | 1 | 10 people trained through AMASA | 2 partnerships between industry bodies (like AIPSA, AMASA) in place |  |  |  |  |
| Create a competitive environment for the small commercial and community media industry |  | 1 | 2 Provincial hubs in place providing multimedia, printing and distribution facilities for community and small commercial media | 1 Provincial hub in place providing printing and distribution facilities for community and small commercial media |  |  |  |  |
|  |  | 2 | An agreement with SAPO to use their database network to distribute community and small commercial newspapers | N/E |  |  |  |  |
|  |  | 3 | % of discounted rates provided to community and small commercial newspapers for printing and distribution | N/E |  | Ongoing |  |  |
| Research on the viability of a low interest loan fund undertaken |  | 1 | Research report in place | Service provider appointed |  |  |  |  |
|  |  | 2 | Strategy developed | NE |  |  |  |  |

KEY RESULT AREA 2:  STAKEHOLDER MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen relations with MDDA contractual and non-contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Develop partnerships with academic institutions and SABC | Stakeholder Management | 1 | 1 joint initiative in media development and diversity undertaken with stakeholders | 1 joint venture with Sol Plaatjies Media Leadership Institute |  |  |  |  |
| Develop and set up forums/summits with advertising companies to promote small commercial media | Increased advertising revenue for small commercial media | 1 | 1 engagement with advertising companies and media directors cycle. | Advertising and marketing summit held in 2007. |  |  |  |  |
| Sign MoU with USAASA | MoU with USAASA | 1 | Signed MoU | Joint USAASA/MDDA workshop held. Draft MoU developed in 2007. |  |  |  |  |
| Signed MoU with MAPPSETA | MoU with MAPPSETA | 1 | Signed MoU | Discussions held with MAPPSETA. Draft MoU developed in 2007 |  |  |  |  |
| Signed MoU with ISSETSETA | MoU with ISSETSETA | 1 | Signed MoU | Draft MoU with MAPPSETA developed in 2007 |  |  |  |  |
| Signed MoU with DoC | MoU with DoC | 1 | Signed MoU | Commitment to working together accepted by both parties |  |  |  |  |

KEY RESULT AREA 3: GRANT AND SEED FUNDING

| STRATEGIC OBJECTIVE: To promote and strengthen the small commercial print and community media sector |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Prepare calls for applications Conduct project assessment including site visits. Prepare and submit project reports Select projects and submit for board approval Enter project grant agreements Disburse grants Prepare reports on grant funding activity | Grant funding | 1 | At least 1 community radio per district municipality funded | 12 community radios funded in 2007/8 |  |  |  |  |
|  |  | 2 | At least 1 community newspaper per district municipality funded | 2 community newspapers funded in two districts |  |  |  |  |
| Fund community television initiatives |  | 3 | 2 Community Television initiatives funded | Community TV funding strategy developed in 2007/8 |  |  |  |  |
| Fund two provincial hub initiatives |  | 4 | At least 1 hub per province (print & radio) funded | Eastern Cape provincial hub supported in 2006/7 and Western Cape in 2007/8 |  |  |  |  |
| Appointed service provider undertakes viability study on student Media funding |  | 5 | Viability study on student media in place | Proposals for the research received in 2006/7 and adjudication process undertaken in 2007/8 |  |  |  |  |
| Appointed service provider conducts a feasibility study on the viability of media cooperatives |  | 6 | 1 media co-operative per district funded guided by the feasibility study on the viability of c-operatives | Call for proposals issued in 2007/8 |  |  |  |  |
|  |  | 7 | 4 atypical media funded | 3 atypical media projects (Agenda Journal in KZN, Gender Advocacy Programme in the Western Cape, Umbele Wolwazi Education Trust in KZN funded in 2007/8 |  |  |  |  |
|  |  | 8 | 2 new media projects funded | Women’s Net supported in 2006/7 Mahala Media funded in 2007/8 |  |  |  |  |
| Appointed service provider undertakes an assessment of the content of MDDA funded projects |  | 9 | Content initiatives assessment report in place | N/E |  |  |  |  |
|  |  | 10 | 10 small commercial newspapers and 1 magazine | 8 small commercial newspapers and 1 magazine funded in 2006/7 |  |  |  |  |
| Status report on seed funding initiative | Seed funding | 1 | Status report in place | 4 nodal point stations provided with seed funding support in 2007/8 |  |  |  |  |
| Communication with un-served nodal point projects |  | 2 | 11 CRs in the nodal areas funded | 4 CR’s in nodal areas funded in 2007/8 |  |  |  |  |
| Enter into an agreement with the service providers |  | 3 | Service provider service level agreement in place |  |  |  |  |  |
| Monitor the service provider management process for seed funding |  | 5 | Service provider performance targets established |  |  |  |  |  |
| Monitor and evaluate projects | Monitoring and Evaluation | 1 | Monitoring and evaluation plan in place | Monitoring was limited to desktop | Monitoring and evaluation plan in place |  |  |  |
|  |  | 2 | Monitoring and evaluation checklist |  | Monitoring and evaluation checklist |  |  |  |
|  |  | 3 | 10 projects monitored |  | 10 projects monitored |  |  |  |
|  |  | 4 | Monitoring reports in place |  | Monitoring reports in place |  |  |  |
|  |  | 5 | Monitoring and evaluation unit established |  | Monitoring and evaluation unit established |  |  |  |
|  |  | 6 | Monitoring and evaluation staff appointed |  | Monitoring and evaluation staff appointed |  |  |  |
| Undertake evaluation of MDDA systems and processes |  | 7 | Service provider appointed | Service provider appointed in 2007/8 | Evaluation report in place |  |  |  |

KEY RESULT AREA 4: CAPACITY BUILDING INTERVENTIONS FOR BENEFICIARY ORGANISATIONS AND COMMUNITIES

| STRATEGIC OBJECTIVE: To enhance the sustainability of community and small commercial media |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Implement training plan | Capacity building | 1 | 25 community and small commercial media initiatives would be trained | 30 people trained in 2007/8 A number of Projects mentored in 2008/9 |  |  |  |  |
| Implement Exchange programme |  | 2 | 10 exchange events are held | 1 exchange event in 2007/8 |  |  |  |  |
| Maintain and grow the mentor and training database |  | 3 | 100 appropriately skilled mentors / trainers on the database, 50 of whom are accredited | 46 mentors / trainers on database in 2007/8 |  |  |  |  |
| Conduct training workshops for beneficiaries on identified capacity issue and needs |  | 4 | 2 workshops on financial management involving 60 beneficiaries conducted | 1 workshop on financial management involving 30 beneficiaries conducted |  |  |  |  |
| Disseminate handbooks and toolkits on marketing |  | 5 | 100 marketing handbook and toolkits disseminated to MDDA projects | Tender awarded and service provider appointed |  |  |  |  |
| Facilitate accreditation for MDDA trainers |  | 6 | 50 accredited Service providers recorded in MDDA database | 46 registered service providers in MDDA database |  |  |  |  |
| Monitor and evaluate capacity building intervention initiatives and prepare reports | Monitoring and evaluation | 1 | Monitoring and evaluation plan in place | N/E |  |  |  |  |
|  |  | 2 | 5 capacity building initiatives involving 5 beneficiaries evaluated | N/E |  | . |  |  |
|  |  | 3 | Monitoring and evaluation reports submitted | N/E |  |  |  |  |
| Report on the movement of trained people within the sector produced and disseminated |  | 1 | Research report on the movement of trained people within the sector in place | Research on the movement of trained people within the sector undertaken |  |  |  |  |
| Establish database of people trained through MDDA funding |  | 2 | Database of trained people | N/E |  |  |  |  |

KEY RESULT AREA 5: RESEARCH AND KNOWLEDGE MANAGEMENT

| STRATEGIC OBJECTIVE: To enhance innovation and learning in the sector |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Develop a research and knowledge management plan | Research | 1 | Research and knowledge management plan in place | N/E |  |  |  |  |
|  |  | 2 | 4 research projects undertaken | 3 research projects considered in 2007/8 |  |  |  |  |
|  |  | 3 | 4 research reports published | 3 research reports published |  |  |  |  |
|  |  | 4 | 3 research seminars involving 20 beneficiaries conducted |  |  |  |  |  |
| Maintain MDDA resource centre | Resource Centre | 1 | Updated Resource Centre records in place | MDDA Resource centre in place |  |  |  |  |
|  |  | 2 | 16 staff, 9 board members and beneficiaries from time to time use Resource Centre | N/E |  |  |  |  |
|  |  | 3 | 172 project records stored | Project information currently stored under project tracking system |  |  |  |  |
| Maintain real time filing, archiving and information management system and | Information Management System | 1 | Updated Information management records in place | Information management system design in place |  |  |  |  |
|  |  | 2 | Information Management System Piloted with 1 MDDA unit | N/E |  |  |  |  |
|  |  | 3 | All MDDA staff trained on the IMS | N/E |  |  |  |  |
|  |  | 4 | IMS successfully implemented across MDDA | N/E |  |  |  |  |
| Develop policy and legislative strategy developed | Policy and legislative issues | 1 | Policy and Legislation monitoring strategy in place | An analysis of Electronic Communications Act of 2005 |  |  |  |  |
|  |  | 2 | 2 policies and legislation reviewed | An analysis of Electronic Communications Act of 2005 |  |  |  |  |
| Conduct workshops on policy changes with beneficiaries |  | 3 | 1 policy workshop with beneficiaries held on the ECA and related policy | NE |  |  |  |  |
| Provide, manage and commission research and research grants and applications through the GFC | Research grants | 1 | 2 Research grants approved | 2 research grant issued in 2008/9 (MMP and Mahala Media |  |  |  |  |

KEY RESULT AREA 6: MEDIA LITERACY AND CULTURE OF LEARNING

| STRATEGIC OBJECTIVE: To promote media literacy and the culture of learning |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Partnership with the Dept of Education (DoE), Dept of Provincial and Local Gvt (DPLG) and other relevant stakeholders in place | Media literacy and culture of learning | 1 | 2 Partnerships in place | N/E |  |  |  |  |
|  |  | 2 | 2 consultations with DoE, DPLG, GCIS, SABC and targeted district municipality | N/E |  |  |  |  |
|  |  | 3 | Consulted parties MOU / agreements for partnering in media Literacy and culture of learning initiatives | N/E |  |  |  |  |
| Convene media learner assemblies/summits on the role of media per district municipality |  | 1 | 1 summit in a district municipality convened | N/E |  |  |  |  |

KEY RESULT AREA 7:  COMMUNICATIONS AND PUBLIC AWARENESS WITH REGARD TO THE SECTOR AND THE MDDA IN GENERAL

| STRATEGIC OBJECTIVE: To enhance and position the MDDA as a leader in media development and diversity. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| Conduct a MDDA perception survey | A perception survey | 1 | 1 survey conducted | Service provider appointed in 2007 |  |  |  |  |
| Develop an MDDA branding and communication strategy and plan | MDDA branding strategy and plan | 1 | Strategy and Plan developed | Service provider appointed in 2007 |  |  |  |  |
| Conducting seminars throughout different provinces and other similar initiatives, aimed at engaging the public regarding the state of media development and diversity in the country. | Recognition by stakeholders of the role of MDDA in media development and diversity | 1 | 1 seminar conducted | MDDA made presentations at similar opportunities in Limpopo convened by Youth Commission, GCIS, etc. Articles covering the topic written in a number of publications, City Press, Bizcommunity, IT Web, etc. Seminar on the trends of ownership and control of media planned in 2007 |  |  |  |  |
| Journal and publication on media development and diversity in S.A. | Concept paper developed | 1 | Concept paper | Articles covering the topic written in a number of publications, City Press, Bizcommunity, IT Web, etc. |  |  |  |  |
| To promote MDDA and its products to potential and actual customers | Public awareness | 1 | Communication Strategy and implementation | Service provider appointed |  |  |  |  |

KEY RESULT AREA 8:  FUNDRAISING AND RESOURCE MOBILISATION

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base; accordingly increase the funding and resource base of the MDDA and its beneficiaries |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| To increase the level of transfers from MDDA funders. | GCIS and partners transfer | 1 | R3 m increase | 100% transfer - R24m in 2008/9 |  |  |  |  |
| To increase and maintain funding revenue streams for the MDDA. | Revenue /income generation | 1 | R3 million increase from GCIS in 2007/08 |  |  |  |  |  |
| To grow the capital base of the MDDA. | Capital growth | 1 | R3 m increase (subject to change post ECA exercise) | R24m in 2008/9 |  |  |  |  |
| To increase the number of MAPPSETA contracts with the MDDA for training services. | Increased training fund and thereby increase skills in the sector | 1 | 1 contract signed | MDDA supported the partnership with NCRF, IAJ and MAPPSETA |  |  |  |  |
| Implement the MDDA Fund Development Strategy and Plan | Increased funding levels of MDDA programs | 1 | Present MDDA position to the ICASA public hearings on the ECA Section 89 Reg. | Fund Development Strategy and Plan developed. Roundtable with Broadcasting Service Licensees held. Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA |  |  |  |  |
|  |  | 2 | Regulation on contributions prescribed | Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA |  |  |  |  |
| Partnership with Highway Africa 2008 | Convene a session on media sustainability | 1 | 1 day session convened as part of Highway Africa 2008 | Presentations made at Highway Africa 2008. |  |  |  |  |
|  | Increase international fundraising for MDDA | 1 | At least 3 engagements with donors | MDDA Chairs the Media Funders Forum of Southern Africa |  |  |  |  |

KEY RESULT AREA 9:  FINANCIAL MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| To maintain the regulated ratio of grant expenditure to capital | Compliance with Regulations | 1 | 25% on admin and 75 % on programs. 60% community media, small commercial media 25%, research 5%, unallocated 10% | 25% on admin and 75 % on programs limits held in 2007 |  |  |  |  |
| To maintain adequate financial records of the MDDA. | Prudent financial management. | 1 | Approved budgets by the Board. 0% actual vs budget variance. | Board approved the MTEF 2008-2011 Low variance in 2007. |  |  |  |  |
| To ensure a clean audit by the Auditor General. | Unqualified audit reports | 1 | Unqualified audit report | Reports up to 2006/7 remained unqualified |  |  |  |  |

KEY RESULT AREA 10:  INTERNAL BUSINESS PROCESSES

| STRATEGIC OBJECTIVE: To strengthen the operational efficiencies of the MDDA so as to deliver sustainable media development and diversity content and impact |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| To equip MDDA with appropriate technologies | Information management systems in place | 1 | Information Management Plan | Information management plan designed No audit findings |  |  |  |  |
| To improve efficiencies and accountability in the delivery of MDDA Programs | Contract management | 1 | 100% funding based on contracts 100% service provided based on Service Level Agreements | Contract management systems in place |  |  |  |  |
| To limit operational and consequential risk to the MDDA | Risk Management | 1 | Risk Management Strategy and Plan in place | Risk Management Strategy and Plan exist |  |  |  |  |
| To limit fraud in the MDDA | Fraud Prevention | 1 | Fraud Prevention Plan | Fraud Prevention Plan exist |  |  |  |  |
| To facilitate efficient decision making and communication as well promote participative democracy in the MDDA | Organisational structure and systems |  | Approved and clear organizational structure established 90% of established and funded posts filled Monitoring and evaluation staff appointed | Approved Organogram |  |  |  |  |
| To improve corporate governance | Corporate Governance | 1 | 100% compliance Completed Corporate Governance checklist | Compliance kept |  |  |  |  |

KEY RESULT AREA 11:  CUSTOMER PERSPECTIVE

| STRATEGIC OBJECTIVE: To maintain the image of the MDDA as the performing public institution with government at national, provincial and local spheres and its contractual and non contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2009/10 | ACTUAL | VARIANCE |  |
| To develop and maintain high MDDA client satisfaction levels. | Service quality | 1 | Perception survey | Service provider appointed in 2007 |  |  |  |  |
| To support and promote positive working relations within all staff units of the MDDA | Human resources management | 1 | Organisational climate survey | Survey conducted |  |  |  |  |
|  |  | 2 | Human resources management plan |  |  |  |  |  |
|  |  | 3 | Workplace skill audit |  |  |  |  |  |
|  |  | 4 | Staff Development Program |  |  |  |  |  |
|  |  | 5 | Human Resources Unit established and staff employed | Organogram approved |  |  |  |  |
|  | To comply with the legislative requirements governing Employers in South Africa | 6 | Employment Equity plan and 100% compliance | Compliance held |  |  |  |  |
|  | To maintain adequate staffing levels for the performance of the MDDA functions. | 7 | 100% Funded positions filled | Organogram fully populated |  |  |  |  |
|  | To improve performance levels and objectively measure the performance of staff in the MDDA | 8 | Performance appraisal conducted | Performance appraisal conducted |  |  |  |  |

17.	Financial Year 2010/11

# KEY RESULT AREA 1: ADVOCACY

| STRATEGIC OBJECTIVE: To contribute towards improving the operating environment of the community and small commercial media sectors |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 20010/11 | ACTUAL | VARIANCE |  |
| Establish baseline data on advertising revenue for small commercial and community media sector | Enabling and operating environment | 1 | Baseline data available | NE |  |  |  |  |
| Lobby advertising and marketing industry using the MAC Charter Council process | Enabling and operating environment | 1 | % or Rand increase in advertising revenue for small commercial and community media | Community Radio advert spent in 2005 – R19m of R2bn (Source Motswako Media) |  |  |  |  |
| Advertising training programme with AMASA | Enabling and operating environment | 1 | 10 people trained through AMASA | 2 partnerships between industry bodies (like AIPSA, AMASA) in place |  |  |  |  |
| Create a competitive environment for the small commercial and community media industry |  | 1 | 2 Provincial hubs in place providing multimedia, printing and distribution facilities for community and small commercial media | 1 Provincial hub in place providing printing and distribution facilities for community and small commercial media |  |  |  |  |
|  |  | 2 | An agreement with SAPO to use their database network to distribute community and small commercial newspapers | N/E |  |  |  |  |
|  |  | 3 | % of discounted rates provided to community and small commercial newspapers for printing and distribution | N/E |  | Ongoing |  |  |
| Research on the viability of a low interest loan fund undertaken |  | 1 | Research report in place | Service provider appointed |  |  |  |  |
|  |  | 2 | Strategy developed | NE |  |  |  |  |
| Seminar on atypical media |  |  |  |  |  |  |  |  |

KEY RESULT AREA 2:  STAKEHOLDER MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen relations with MDDA contractual and non-contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 20010/11 | ACTUAL | VARIANCE |  |
| Develop partnerships with academic institutions and SABC | Stakeholder Management | 1 | 1 joint initiative in media development and diversity undertaken with stakeholders | 1 joint venture with Sol Plaatjies Media Leadership Institute |  |  |  |  |
| Develop and set up forums/summits with advertising companies to promote small commercial media | Increased advertising revenue for small commercial media | 1 | 1 engagement with advertising companies and media directors cycle. | Advertising and marketing summit held in 2007. |  |  |  |  |
| Sign MoU with USAASA | MoU with USAASA | 1 | Signed MoU | Joint USAASA/MDDA workshop held. Draft MoU developed in 2007. |  |  |  |  |
| Signed MoU with MAPPSETA | MoU with MAPPSETA | 1 | Signed MoU | Discussions held with MAPPSETA. Draft MoU developed in 2007 |  |  |  |  |
| Signed MoU with ISSETSETA | MoU with ISSETSETA | 1 | Signed MoU | Draft MoU with MAPPSETA developed in 2007 |  |  |  |  |
| Signed MoU with DoC | MoU with DoC | 1 | Signed MoU | Commitment to working together accepted by both parties |  |  |  |  |

KEY RESULT AREA 3: GRANT AND SEED FUNDING

| STRATEGIC OBJECTIVE: To promote and strengthen the small commercial print and community media sector |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 20010/11 | ACTUAL | VARIANCE |  |
| Prepare calls for applications Conduct project assessment including site visits. Prepare and submit project reports Select projects and submit for board approval Enter project grant agreements Disburse grants Prepare reports on grant funding activity | Grant funding | 1 | At least 1 community radio per district municipality funded | 12 community radios funded in 2007/8 |  |  |  |  |
|  |  | 2 | At least 1 community newspaper per district municipality funded | 2 community newspapers funded in two districts |  |  |  |  |
| Fund community television initiatives |  | 3 | 2 Community Television initiatives funded | Community TV funding strategy developed in 2007/8 |  |  |  |  |
| Fund two provincial hub initiatives |  | 4 | At least 1 hub per province (print & radio) funded | Eastern Cape provincial hub supported in 2006/7 and Western Cape in 2007/8 |  |  |  |  |
| Appointed service provider undertakes viability study on student Media funding |  | 5 | Viability study on student media in place | Proposals for the research received in 2006/7 and adjudication process undertaken in 2007/8 |  |  |  |  |
| Appointed service provider conducts a feasibility study on the viability of media cooperatives |  | 6 | 1 media co-operative per district funded guided by the feasibility study on the viability of c-operatives | Call for proposals issued in 2007/8 |  |  |  |  |
|  |  | 7 | 4 atypical media funded | 3 atypical media projects (Agenda Journal in KZN, Gender Advocacy Programme in the Western Cape, Umbele Wolwazi Education Trust in KZN funded in 2007/8 |  |  |  |  |
|  |  | 8 | 2 new media projects funded | Women’s Net supported in 2006/7 Mahala Media funded in 2007/8 |  |  |  |  |
| Appointed service provider undertakes an assessment of the content of MDDA funded projects |  | 9 | Content initiatives assessment report in place | N/E |  |  |  |  |
|  |  | 10 | 10 small commercial newspapers and 1 magazine | 8 small commercial newspapers and 1 magazine funded in 2006/7 |  |  |  |  |
| Status report on seed funding initiative | Seed funding | 1 | Status report in place | 4 nodal point stations provided with seed funding support in 2007/8 |  |  |  |  |
| Communication with un-served nodal point projects |  | 2 | 11 CRs in the nodal areas funded | 4 CR’s in nodal areas funded in 2007/8 |  |  |  |  |
| Enter into an agreement with the service providers |  | 3 | Service provider service level agreement in place |  |  |  |  |  |
| Monitor the service provider management process for seed funding |  | 5 | Service provider performance targets established |  |  |  |  |  |
| Monitor and evaluate projects | Monitoring and Evaluation | 1 | Monitoring and evaluation plan in place | Monitoring was limited to desktop | Monitoring and evaluation plan in place |  |  |  |
|  |  | 2 | Monitoring and evaluation checklist |  | Monitoring and evaluation checklist |  |  |  |
|  |  | 3 | 10 projects monitored |  | 10 projects monitored |  |  |  |
|  |  | 4 | Monitoring reports in place |  | Monitoring reports in place |  |  |  |
|  |  | 5 | Monitoring and evaluation unit established |  | Monitoring and evaluation unit established |  |  |  |
|  |  | 6 | Monitoring and evaluation staff appointed |  | Monitoring and evaluation staff appointed |  |  |  |
| Undertake evaluation of MDDA systems and processes |  | 7 | Service provider appointed | Service provider appointed in 2007/8 | Evaluation report in place |  |  |  |

KEY RESULT AREA 4: CAPACITY BUILDING INTERVENTIONS FOR BENEFICIARY ORGANISATIONS AND COMMUNITIES

| STRATEGIC OBJECTIVE: To enhance the sustainability of community and small commercial media |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 20010/11 | ACTUAL | VARIANCE |  |
| Implement training plan | Capacity building | 1 | 25 community and small commercial media initiatives would be trained | 30 people trained in 2007/8 ??? Projects mentored in 2007/8 |  |  |  |  |
| Implement Exchange programme |  | 2 | 10 exchange events are held | 1 exchange event in 2007/8 |  |  |  |  |
| Maintain and grow the mentor and training database |  | 3 | 100 appropriately skilled mentors / trainers on the database, 50 of whom are accredited | 46 mentors / trainers on database in 2007/8 |  |  |  |  |
| Conduct training workshops for beneficiaries on identified capacity issue and needs |  | 4 | 2 workshops on financial management involving 60 beneficiaries conducted | 1 workshop on financial management involving 30 beneficiaries conducted |  |  |  |  |
| Disseminate handbooks and toolkits on marketing |  | 5 | 100 marketing handbook and toolkits disseminated to MDDA projects | Tender awarded and service provider appointed |  |  |  |  |
| Facilitate accreditation for MDDA trainers |  | 6 | 50 accredited Service providers recorded in MDDA database | 46 registered service providers in MDDA database |  |  |  |  |
| Monitor and evaluate capacity building intervention initiatives and prepare reports | Monitoring and evaluation | 1 | Monitoring and evaluation plan in place | N/E |  |  |  |  |
|  |  | 2 | 5 capacity building initiatives involving 5 beneficiaries evaluated | N/E |  | . |  |  |
|  |  | 3 | Monitoring and evaluation reports submitted | N/E |  |  |  |  |
| Report on the movement of trained people within the sector produced and disseminated |  | 1 | Research report on the movement of trained people within the sector in place | Research on the movement of trained people within the sector undertaken |  |  |  |  |
| Establish database of people trained through MDDA funding |  | 2 | Database of trained people | N/E |  |  |  |  |

KEY RESULT AREA 5: RESEARCH AND KNOWLEDGE MANAGEMENT

| STRATEGIC OBJECTIVE: To enhance innovation and learning in the sector |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 20010/11 | ACTUAL | VARIANCE |  |
| Develop a research and knowledge management plan | Research | 1 | Research and knowledge management plan in place | N/E |  |  |  |  |
|  |  | 2 | 4 research projects undertaken | 3 research projects considered in 2007/8 |  |  |  |  |
|  |  | 3 | 4 research reports published | 3 research reports published |  |  |  |  |
|  |  | 4 | 3 research seminars involving 20 beneficiaries conducted |  |  |  |  |  |
| Maintain MDDA resource centre | Resource Centre | 1 | Updated Resource Centre records in place | MDDA Resource centre in place |  |  |  |  |
|  |  | 2 | 16 staff, 9 board members and beneficiaries from time to time use Resource Centre | N/E |  |  |  |  |
|  |  | 3 | 172 project records stored | Project information currently stored under project tracking system |  |  |  |  |
| Maintain real time filing, archiving and information management system and | Information Management System | 1 | Updated Information management records in place | Information management system design in place |  |  |  |  |
|  |  | 2 | Information Management System Piloted with 1 MDDA unit | N/E |  |  |  |  |
|  |  | 3 | All MDDA staff trained on the IMS | N/E |  |  |  |  |
|  |  | 4 | IMS successfully implemented across MDDA | N/E |  |  |  |  |
| Develop policy and legislative strategy developed | Policy and legislative issues | 1 | Policy and Legislation monitoring strategy in place | An analysis of Electronic Communications Act of 2005 |  |  |  |  |
|  |  | 2 | 2 policies and legislation reviewed | An analysis of Electronic Communications Act of 2005 |  |  |  |  |
| Conduct workshops on policy changes with beneficiaries |  | 3 | 1 policy workshop with beneficiaries held on the ECA and related policy | NE |  |  |  |  |
| Provide, manage and commission research and research grants and applications through the GFC | Research grants | 1 | 2 Research grants approved | 2 research grant issued in 2008/9 (MMP and Mahala Media |  |  |  |  |

KEY RESULT AREA 6: MEDIA LITERACY AND CULTURE OF LEARNING

| STRATEGIC OBJECTIVE: To promote media literacy and the culture of learning |
| --- |
| ACTIVITIY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| Partnership with the Dept of Education (DoE), Dept of Provincial and Local Gvt (DPLG) and other relevant stakeholders in place | Media literacy and culture of learning | 1 | 2 Partnerships in place | N/E |  |  |  |  |
|  |  | 2 | 2 consultations with DoE, DPLG, GCIS, SABC and targeted district municipality | N/E |  |  |  |  |
|  |  | 3 | Consulted parties MOU / agreements for partnering in media Literacy and culture of learning initiatives | N/E |  |  |  |  |
| Convene media learner assemblies/summits on the role of media per district municipality |  | 1 | 1 summit in a district municipality convened | N/E |  |  |  |  |

KEY RESULT AREA 7:  COMMUNICATIONS AND PUBLIC AWARENESS WITH REGARD TO THE SECTOR AND THE MDDA IN GENERAL

| STRATEGIC OBJECTIVE: To enhance and position the MDDA as a leader in media development and diversity. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| Conduct a MDDA perception survey | A perception survey | 1 | 1 survey conducted | Service provider appointed in 2007 |  |  |  |  |
| Develop an MDDA branding and communication strategy and plan | MDDA branding strategy and plan | 1 | Strategy and Plan developed | Service provider appointed in 2007 |  |  |  |  |
| Conducting seminars throughout different provinces and other similar initiatives, aimed at engaging the public regarding the state of media development and diversity in the country. | Recognition by stakeholders of the role of MDDA in media development and diversity | 1 | 1 seminar conducted | MDDA made presentations at similar opportunities in Limpopo convened by Youth Commission, GCIS, etc. Articles covering the topic written in a number of publications, City Press, Bizcommunity, IT Web, etc. Seminar on the trends of ownership and control of media planned in 2007 |  |  |  |  |
| Journal and publication on media development and diversity in S.A. | Concept paper developed | 1 | Concept paper | Articles covering the topic written in a number of publications, City Press, Bizcommunity, IT Web, etc. |  |  |  |  |
| To promote MDDA and its products to potential and actual customers | Public awareness | 1 | Communication Strategy and implementation | Service provider appointed |  |  |  |  |

KEY RESULT AREA 8:  FUNDRAISING AND RESOURCE MOBILISATION

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base; accordingly increase the funding and resource base of the MDDA and its beneficiaries |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| To increase the level of transfers from MDDA funders. | GCIS and partners transfer | 1 | R4 m increase | 100% transfer - R27million in 2009/10 |  |  |  |  |
| To increase and maintain funding revenue streams for the MDDA. | Revenue /income generation | 1 | R4 million increase from GCIS in 2007/08 |  |  |  |  |  |
| To grow the capital base of the MDDA. | Capital growth | 1 | R4 m increase (subject to change post ECA exercise) | R27million in 2009/10 |  |  |  |  |
| To increase the number of MAPPSETA contracts with the MDDA for training services. | Increased training fund and thereby increase skills in the sector | 1 | 1 contract signed | MDDA supported the partnership with NCRF, IAJ and MAPPSETA |  |  |  |  |
| Implement the MDDA Fund Development Strategy and Plan | Increased funding levels of MDDA programs | 1 | Present MDDA position to the ICASA public hearings on the ECA Section 89 Reg. | Fund Development Strategy and Plan developed. Roundtable with Broadcasting Service Licensees held. Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA |  |  |  |  |
|  |  | 2 | Regulation on contributions prescribed | Submissions made to ICASA on the draft Regulation. Discussions held between USAASA, ICASA and MDDA |  |  |  |  |
| Partnership with Highway Africa 2008 | Convene a session on media sustainability | 1 | 1 day session convened as part of Highway Africa 2010 | Presentations made at Highway Africa 2008. |  |  |  |  |
|  | Increase international fundraising for MDDA | 1 | At least 3 engagements with donors | MDDA Chairs the Media Funders Forum of Southern Africa |  |  |  |  |

KEY RESULT AREA 9:  FINANCIAL MANAGEMENT

| STRATEGIC OBJECTIVE: To strengthen, grow and protect the MDDA capital base. |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| To maintain the regulated ratio of grant expenditure to capital | Compliance with Regulations | 1 | 25% on admin and 75 % on programs. 60% community media, small commercial media 25%, research 5%, unallocated 10% | 25% on admin and 75 % on programs limits held in 2007 |  |  |  |  |
| To maintain adequate financial records of the MDDA. | Prudent financial management. | 1 | Approved budgets by the Board. 0% actual vs budget variance. | Board approved the MTEF 2008-2011 Low variance in 2007. |  |  |  |  |
| To ensure a clean audit by the Auditor General. | Unqualified audit reports | 1 | Unqualified audit report | Reports up to 2006/7 remained unqualified |  |  |  |  |

KEY RESULT AREA 10:  INTERNAL BUSINESS PROCESSES

| STRATEGIC OBJECTIVE: To strengthen the operational efficiencies of the MDDA so as to deliver sustainable media development and diversity content and impact |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| To equip MDDA with appropriate technologies | Information management systems in place | 1 | Information Management Plan | Information management plan designed No audit findings |  |  |  |  |
| To improve efficiencies and accountability in the delivery of MDDA Programs | Contract management | 1 | 100% funding based on contracts 100% service provided based on Service Level Agreements | Contract management systems in place |  |  |  |  |
| To limit operational and consequential risk to the MDDA | Risk Management | 1 | Risk Management Strategy and Plan in place | Risk Management Strategy and Plan exist |  |  |  |  |
| To limit fraud in the MDDA | Fraud Prevention | 1 | Fraud Prevention Plan | Fraud Prevention Plan exist |  |  |  |  |
| To facilitate efficient decision making and communication as well promote participative democracy in the MDDA | Organisational structure and systems |  | Approved and clear organizational structure established 90% of established and funded posts filled Monitoring and evaluation staff appointed | Approved Organogram |  |  |  |  |
| To improve corporate governance | Corporate Governance | 1 | 100% compliance Completed Corporate Governance checklist | Compliance kept |  |  |  |  |

KEY RESULT AREA 11:  CUSTOMER PERSPECTIVE

| STRATEGIC OBJECTIVE: To maintain the image of the MDDA as the performing public institution with government at national, provincial and local spheres and its contractual and non contractual stakeholders |
| --- |
| ACTIVITY | KPA | KPI NO: | KPI’S | BENCHMARK | TARGET |  | BUDGET |
|  |  |  |  |  | 2010/11 | ACTUAL | VARIANCE |  |
| To develop and maintain high MDDA client satisfaction levels. | Service quality | 1 | Perception survey | Service provider appointed in 2007 |  |  |  |  |
| To support and promote positive working relations within all staff units of the MDDA | Human resources management | 1 | Organisational climate survey | Survey conducted |  |  |  |  |
|  |  | 2 | Human resources management plan |  |  |  |  |  |
|  |  | 3 | Workplace skill audit |  |  |  |  |  |
|  |  | 4 | Staff Development Program |  |  |  |  |  |
|  |  | 5 | Human Resources Unit established and staff employed | Organogram approved |  |  |  |  |
|  | To comply with the legislative requirements governing Employers in South Africa | 6 | Employment Equity plan and 100% compliance | Compliance held |  |  |  |  |
|  | To maintain adequate staffing levels for the performance of the MDDA functions. | 7 | 100% Funded positions filled | Organogram fully populated |  |  |  |  |
|  | To improve performance levels and objectively measure the performance of staff in the MDDA | 8 | Performance appraisal conducted | Performance appraisal conducted |  |  |  |  |

18.	Finance Implications and Budget for the period 2008 – 2011

# Footnotes

The ICASA Regulation could prescribe 0.5% of the Annual turnover of Licensees.

We have conservatively projected 0.2% of the broadcasting service licensees to be R19 930 000 for 2008/9 and R21 723 000 for 2009/10.

The difference (if ICASA Regulation is not with effect from 01 July 2008, as envisaged) for 2008/9 = R13 930 000

Bulumko Corporate Law Advisers & Consultants, Oct. 2006 (page 53) – commissioned in 2006 to conduct a due diligence and an analysis of the ECA implications for the Agency

ICMS Report, Sept. 2006, (page 8-10) – commissioned in 2006, to review job profiles and performance management system for the Agency.

Both community media and small commercial media

African Media Development Initiative Research Report on South Africa published by the BBC World Service Trust in 2006

Uninterrupted Power Supply (UPS) is in place

Given the size of the organisation

Bulumko Corporate Law Advisers & Consultants, Oct. 2006 (page 53)

ICMS Report, Sept. 2006, (page 8-10)

Note that seven new positions had been created in the MDDA but not yet filled at the time of writing. These are highlighted in green.  The positions of Project Officer:  Community Media and Finance & Disbursement Officer are vacant because staff that was occupying those posts resigned.

# Text boxes

# Constitution of the Republic of South Africa 1996 
Chapter 2 - Bill of Rights

# 32. Access to information

1)    Everyone has the right of access to :

a)    any information held by the state; and

b)    any information that is held by another person and that is required for the exercise or protection of any rights.

2)    National legislation must be enacted to give effect to this right, and may provide for reasonable measures to alleviate the administrative and financial burden on the state.

# Constitution of the Republic of South Africa 1996 
Chapter 2 - Bill of Rights

# 16. Freedom of expression

1)    Everyone has the right to freedom of expression, which includes

a)    freedom of the press and other media;

b)    freedom to receive or impart information or ideas;

c)    freedom of artistic creativity; and

d)    academic freedom and freedom of scientific research.

2)    The right in subsection (1) does not extend to

a)    propaganda for war;

b)    incitement of imminent violence; or

c)    advocacy of hatred that is based on race, ethnicity, gender or religion, and that constitutes incitement to cause harm.

“Each and every South African Citizen should have access to a choice of a diverse range of media”

The MDDA is development agency that will assist in building an environment where a diverse, vibrant and creative media flourishes and reflects the needs of all South Africans.”

Executive Secretary

Legal and Contract

Management Services

Projects Officer

PM:  Monitoring and Evaluation

Internal Audit & Risk Manager

Projects Officer

Projects Officer

Project Officer

Finance Disbursement Officer

Manager in the CEO’s Office

Finance Administration Officer

PM: Community Media

PM: Training & Research

PM: Small Commercial Media

Admin Assistant

CFO

Program Director

CEO

BOARD

Office Assistant

Receptionist

HR & Corporate Services Manager