CHIEF DIRECTORATE: NATIONAL EXAMINATIONS, ASSESSEMENT AND MEASUREMENT

MANAGEMENT PLAN

NATIONAL SENIOR CERTIFICATE (NSC)

2009

Capturing, standardization, resulting and certification

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Certification workshop – planning for development of the module on the IECS | DoE/ PEDs/Magna | 29 January 2009 |
| Resulting of all candidates - NSC 2008 examination | PEDs | 31 January 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Development of the Certification functionality on the IECS | DoE | 11 February 2009 |
| Finalising Registration of Senior Certificate May/June 2009 examinations | PEDs | 15 February 2009 |
| IPEC Meeting | DoE & PEDs | 16 – 18 February 2009 |
| Commencement of the NSC Supplementary examinations | PEDs | 17 February 2009 |
| Provincial statistics on blind/deaf candidates for the SC exam | PEDs | 20 February 2009 |
| Capturing of Grade 10 entries on the IECS completed | PEDs | 27 February 2009 |
| Development of the certification function on the IECS | DoE | Ongoing during Feb |
| NSLA coordinators meeting | DoE/PEDs | 23/24 February 2009 |
| Promotion of Grade 11 2008 Examinations on the ICES completed | PEDs | 27 February 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Testing of the certification module on the IECS | DoE/PEDs | 2 – 6 March 2009 |
| Specifications for Phase 2 – Certification module approved | DoE/PEDs | 3 March 2009 |
| Re-mark and re-check results released | PEDs | 6 March 2009 |
| PEDs place orders for Geography maps at government printers for May/June 2009 | DoE | 6 March 2009 |
| Submission of May/June 2009 question papers set by provinces to DoE | DoE | 6 March 2009 |
| Final testing of the certification module and feedback to Magna Fs | DoE/PEDs | 12 – 13 March 2009 |
| Closing date the Registration of NSC 2008 November examinations | PEDs | 15 March 2008 |
| Handing-over of May/June 2009 examination papers to PEDs Consignment 1 | DoE | 15 March 2009 |
| Training PEDs on certification module | Magna Fs / PEDs | 20 March 2009 |
| Implement certification module on the IECS and sign of | DoE/PEDs | 23 March 2009 |
| Dataset to Umalusi for printing of the 2008 NSC certificates (phase 1) (excluding supplementary exam results) | PEDs | 24 March 2009 |
| Capturing of supplementary marks commence | PEDs | 23 March 2009 |
| Finalise development of the Certification function for the November results | DoE | 23 March 2009 |
| Approval of specification for 2nd phase of the certification module | DoE/PEDs | 24 March 2009 |
| Marking of supplementary exams completed | PEDs | 27 March 2009 |
| Handing-over of May/June 2009 examination papers to PEDs Consignment 2 | DoE | 30 March 2009 |
| First testing session of phase 2 of the certification module on the IECS | DoE/PEDs | 30 – 31 March 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Resulting of Supplementary examinations tested and implemented | DoE/PEDs | 6 – 9 April 2009 |
| Handing-over of May/June 2009 examination papers to PEDs Consignment 3 | DoE | 10 April 2009 |
| Capturing of Supplementary marks completed | PEDs | 12 April 2009 |
| Second testing session of the certification module (Phase 2) | DoE/PEDs | 15 – 17 April 2009 |
| Setting and internal moderation of May/June 2010 and 2011 examination papers | DoE | 15 April 2009 –30 July 2009 |
| Identify marking centres | PED's | 30 April 2009 |
| Training of users on the resulting and certification module (Phase 2) | Magna Fs / PEDs | 20 April 2009 |
| Implementation of the certification module (Phase 2) | PEDs | 20 April 2009 |
| Resulting and preparation for release of supplementary results | DoE /PEDs | 24 April 2008 |
| Handing over Braille papers for SC to PEDs | DoE | 25 April 2009 |
| Printing and distribution of statement of results (Supplementary exams) | PEDs | 27 April 2009 |
| Finalise development of the Certification function for the supplementary exam/individuals | DoE | 28 April 2009 |
| Release of supplementary results NSC | DoE/PEDs | 28 April 2009 |
| Confirm final registration of candidates for the 2009 NSC examinations | DoE/PEDs | 30 April 2009 |
| Handing over of Grade 12 2009 examination question papers to PEDs: Consignment 1 | DoE | 30 April 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| SCHOOLS DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Writing of the SC Exam | PEDs | 27 April – 9 June 2009 |
| Start development of Item Banking function on the IECS | DoE | 1 May 2009 |
| Preliminary schedules to schools / colleges | PED | 6 May 2009 |
| Test resulting of the SC exam combinations according to regulations | DoE/PEDs | 11 – 15 May 2009 |
| Input from NSC consignment 1 received from PEDs | DoE | 15 May 2009 |
| Preliminary schedules back to PED's/DoE | PED | 29 May 2009 |
| Handing over of Grade 12 2009 examination question papers to PEDs: Consignment 2 | DoE | 30 May 2009 |
| Consignment 1 NSC finalized | DoE | 30 May 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| SCHOOLS DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Handing over Geography maps to Government printers | DoE | 2 June 2009 |
| Statistics on Grade 12 November 2009 examination question papers to be adapted for the blind and deaf received from PEDs. | DoE | 15 June 2009 |
| Input from NSC consignment 2 received from PEDs | DoE | 15 June 2009 |
| Second prelim to schools/colleges | PED | 15 June 2009 |
| Marking and capturing of marks for the SC supplementary examinations completed | PEDs | 26 June – 17 July 2009 |
| Handing over of Grade 12 2009 examination question papers to PEDs: Consignment 3 | DoE | 30 June 2009 |
| Consignment 2 NSC finalized | DoE | 30 June 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Marking finalised (SC) | PEDs | 13 July 2009 |
| Input from consignment 3 NSC received from PEDs | DoE | 15 July 2009 |
| Capturing of marks for the SC supplementary examinations completed | PEDs | 17 July 2009 |
| Resulting of the SC May/June examination | PEDs | 20 July 2009 |
| Printing of statements of symbols for the May/June SC exam | PEDs | 21 – 22 July 2009 |
| Standardisation (SC) | DoE | 23 – 24 July 2009 |
| Consignment 3 NSC finalized | DoE | 30 July 2009 |
| Handing over of Grade 12 2009 examination question papers to PEDs: Consignment 4(Final consignment) (Literature) | DoE | 30 July 2009 |
| Review and Enhancement of the IECS modules and functionalities | DoE/PEDs | 1 - 31 July 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Release of SC May/June examination results | PEDs | 7 August 2009 |
| Review and Enhancement of the IECS modules and functionalities | DoE/PEDs | 1 – 31 August 2009 |
| Input from consignment 4 NSC received from PEDs | DoE | 10 August 2009 |
| Consignment 4 NSC finalized | DoE | 20 August 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Moderation of CASS / SBA | PED | 1 – 30 September 2009 |
| Testing of all modules on the IECS for administering the 2009 NSC examination completed | DoE/PEDs | 30 September 2009 |
| Handing over of Brailled papers and papers for the deaf Grade 12 examination question papers to PEDs | DoE | 30 Sept 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Exam dates | PED/DoE | 26 October – 4 December 2009 |
| Monitoring of exams and marking | PED/DoE | 26 October – 4 December 2009 |
| Commence with capturing of SBA marks | PEDs | 30 October 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Hand over Guidelines to Practical Assessment Tasks for 2010 to PEDs | DoE | 5 November 2009 |
| Capturing of SBA marks completed | PEDs | 22 November 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |

| DELIVERABLE/ KEY ACTIVITY | RESPONSIBILITY | TIME FRAME |
| --- | --- | --- |
| Marking process | PED/DoE | 5 – 16 December 2009 |
| Final date for marked scripts to PED's / DoE | PED | 10 December 2009 |
| Final capturing of marks | PED/DoE | 12 December 2009 |
| Processing of all application for replacement certificates completed | DoE | 15 December 2008 |
| Schools close |  | 11 December 2009 |
| Capturing of marks (result) for NSC | DoE/PEDs | 7 - 19 December 2009 |
| Processing of data NSC | PEDs | 20 December 2009 |
| Pre-Standardization of the NSC examination | DoE/ PEDs/Umalusi | 21 – 23 December 2009 |
| Standardisation NSC | DoE/ PEDs/Umalusi | 24 December 2009 |
| Adjustment process and resulting | DoE/PEDs | 26 – 27 December 2009 |
| Verification by PEDs/districts/Circuits and principals | DoE/PEDs | 27 – 28 December 2009 |
| Resulting of the NSC results | DoE/PEDs | 24 – 27 December 2009 |
| Printing and distribution of statement of results | PEDs | 27 – 30 December 2009 |
| NEIC Meeting | DoE/ PEDs/Umalusi | 28 December 2009 |
| Approval of results for the 2009 NSC examination | Umalusi | 29 December 2009 |
| Printing of statements | PEDs | 31 December 2009 |
| Development of outstanding functions/ enhancements of the IECS | DoE | ONGOING |
| Printing of statements | PEDs | 2 January 2010 |
| Distribution of statements | PEDs | 3-4 January 2009 |
| Release of results for the 2009 NSC examination | Minister | 5 January 2010 |
| Closing date for application for re-mark/re-check (NSC) | PEDs | 22 January 2010 |
| Closing date for application for supplementary (NSC) | PEDs | 27 January 2010 |
| NSC 2010 supplementary examinations | DoE/PEDs | 16 February – 25 March 2010 |

IMPROVEMENT PLAN FOR THE 2009 NATIONAL SENIOR CERTIFICATE EXAMINATION

| ACTIVITY | RESP | DATE |
| --- | --- | --- |
| 1. Examining Panel to consider and apply comments from teachers and other institutions on the 2008 question papers. | DoE | Jan 09 - June 09 |
| 2. Examination Guidelines developed for all subjects and distributed to schools. | DoE/PEDs | 27 Feb 2009 |
| 3. Post test analysis conducted on selected question papers. | DoE | 30 May 09 |
| 4. Training session for internal moderators | DoE | May 09 |
| 5. Finalisation of candidate registration | DoE/PEDs | 30 June 09 |
| 6. Audit and verification of registration data | DoE | 31 July 09 |
| 7. Closing of registration function on system | DoE | 15 Aug 09 |
| 8. Printing of mark-sheets | PEDs | 31 Aug 09 |
| 9. Training of chief invigilators on mark-sheet control and exams | PEDs | 30 Sept 09 |
| 10. Criteria for appointment of markers | DoE/PEDs | 30 June 09 |
| 11. Marking guideline training for chief markers/moderators | DoE | Completed by 04 Dec 09 |
| 12. Training of markers | PEDs | 05 Dec 09 |
| 13. Testing on IECS completed and users trained | DoE | 31 Aug 09 |
| 14. Establish help desk for IECS | DoE | 30 June 09 |
| 15. Review of provincial capacity to manage exams | DoE/PEDs | 30 May 09 |